## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Sripur Balagar Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000292/2021-2022 | 2203/Hug | 14/12/2021 | 60 | MALLIKA ENTERPRISE | 46.52 | 26.77 | 0
2 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000126/2021-2022 | 2195/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
3 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002096/2021-2022 |  | 28/01/2022 | 0 | MALLIKA ENTERPRISE | 9.92 | 0 | 0
4 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002106/2021-2022 |  | 28/01/2022 | 0 | MALLIKA ENTERPRISE | 29 | 0 | 0
5 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002284/2020-2021 |  | 15/03/2021 | 0 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 10 | 0 | 0
6 | Hooghly Division | Srirampur Sub-Division | Providing 20 nos. Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000063/2023-2024 | 06/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100
7 | Hooghly Division | Srirampur Sub-Division | Laying Additional Pipe line for Providing Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000064/2023-2024 | 07/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100
8 | Hooghly Division | Srirampur Sub-Division | Providing balance Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000065/2023-2024 | 08/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.95 | 100
9 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within various habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000066/2023-2024 | 09/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100
10 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000067/2023-2024 | 10/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.92 | 100
11 | Hooghly Division | Srirampur Sub-Division | Extension of pipeline for providing FHTC Connection for Uttar Rajyadharpur Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000238/2023-2024 | 98/SER | 19/06/2023 | 30 | SURAJIT SINGHA RAY | 0.99 | 0.97 | 100
12 | Hooghly Division | Srirampur Sub-Division | Extension of pipeline due to providing FHTC Connection for Chapsara Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000239/2023-2024 | 99/SER | 19/06/2023 | 30 | SURAJIT SINGHA RAY | 1 | 1 | 100
13 | Hooghly Division | Srirampur Sub-Division | Providing 95 nos. F.H.T.C. in Uttar Rajyadharpur village of Uttar Rajyadharpur and its Adjoining Mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[Block-Serampore-Uttarpara] (Part-C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000870/2020-2021 | 230/SER | 26/02/2021 | 30 | H.R. CONSTRUCTION | 2.63 | 2.38 | 100
14 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000129/2021-2022 | 2198/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
15 | Hooghly Division | Srirampur Sub-Division | Computer Works | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002122/2021-2022 | 844312 | 05/10/2021 | 0 | ARATI ENGINEERING | 0.13 | 0 | 0
16 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002237/2020-2021 |  | 19/03/2021 | 0 | UNIQUE AGENCY | 20.43 | 0 | 0
17 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002239/2020-2021 |  | 15/03/2021 | 0 | JAGADHATRI CONSTRUCTION | 3 | 0 | 0
18 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002241/2020-2021 |  | 15/03/2021 | 0 | MAA TARA CONSTRUCTION | 4 | 0 | 0
19 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002244/2020-2021 |  | 15/03/2021 | 0 | J B CONSTRUCTION | 2 | 0 | 0
20 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002559/2020-2021 |  | 19/03/2021 | 0 | UNIQUE AGENCY | 16 | 0 | 0
21 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002560/2020-2021 |  | 19/03/2021 | 0 | MAA TARA CONSTRUCTION | 4 | 0 | 0
22 | Hooghly Division | Srirampur Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
23 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at old 1st tubewell site of Kulteghari PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000271/2025-2026 | 917/CHAN | 21/07/2025 | 20 | M/S RAJKUMAR KHAN | 4.17 | 0 | 0
24 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Tullyan, Keshabchak, Kulteghari, Mohanbati Mouza in KULTEGHORI PWSS, Block Tarakeswar under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000593/2022-2023 | 2852/HUG | 16/12/2022 | 30 | S K ENTERPRISE | 14.97 | 14.45 | 100
25 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000037/2021-2022 | 2098/1/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
26 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000134/2022-2023 | 2686/1/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0
27 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000519/2021-2022 |  | 23/07/2021 | 0 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0
28 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000534/2021-2022 |  | 23/07/2021 | 0 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0
29 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000593/2021-2022 |  | 17/08/2021 | 0 | M/S S.G. CONSTRUCTION | 34.67 | 0 | 0
30 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000848/2021-2022 |  | 21/09/2021 | 0 | M/S RAJKUMAR KHAN | 23.52 | 0 | 0
31 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001042/2021-2022 |  | 30/09/2021 | 0 | M/S S.G. CONSTRUCTION | 18.9 | 0 | 0
32 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002111/2021-2022 |  | 28/01/2022 | 0 | M/S S.G. CONSTRUCTION | 20 | 0 | 0
33 | Hooghly Division | Chandannagar Sub-Division | Laying pipe line For damaged portion of MALIA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000389/2022-2023 | 2142/HUG | 26/09/2022 | 20 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.95 | 4.95 | 100
34 | Hooghly Division | Chandannagar Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of MALIA PWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000478/2024-2025 | 4071/HUG | 19/12/2024 | 90 | SHREEOM ENTERPRISE | 9.11 | 0 | 0
35 | Hooghly Division | Chandannagar Sub-Division | Construction of 3.6 X 3.0 m Swicth Room with Additional Plinth Height along with laying DI rising main at 3rd boosting tubewell site for Malia Water Supply Scheme under Chandannagar Sub - Division, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000888/2020-2021 | 121/Chan | 24/02/2021 | 45 | M/S S.G. CONSTRUCTION | 4.97 | 4.9 | 100
36 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000033/2022-2023 | 1125/6/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
37 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000125/2021-2022 | 2197/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
38 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001919/2020-2021 |  | 15/02/2021 | 0 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 36 | 0 | 0
39 | Hooghly Division | Chandannagar Sub-Division | SURVEY | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002112/2021-2022 |  | 28/01/2022 | 0 | SIKHA ENTERPRISE | 5.1 | 0 | 0
40 | Hooghly Division | Chandannagar Sub-Division | Direct purchase of land for Lakshmipur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002242/2021-2022 | 844321 | 09/11/2021 | 0 | HOOGHLY ZILLA PARISHAD | 11.85 | 0 | 0
41 | Hooghly Division | Srirampur Sub-Division | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000100/2020-2021 | 1686/Hug | 17/12/2020 | 182 | S & P CONSTRUCTION | 24.9 | 0 | 98
42 | Hooghly Division | Srirampur Sub-Division | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000284/2020-2021 | 331/Hug | 11/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 0 | 100
43 | Hooghly Division | Srirampur Sub-Division | FHTC BORHAL (Z-I) PWSS | Assistant Engineer (Civil) |  | ORD/000510/2021-2022 | 113/SECC | 19/11/2021 | 35 | S & P ENTERPRISE | 53 | 53 | 100
44 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000185/2021-2022 |  | 24/05/2021 | 0 | M/S RAJKUMAR KHAN | 11.84 | 0 | 0
45 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000842/2021-2022 |  | 21/09/2021 | 0 | M/S R.M. CONSTRUCTION | 16.1 | 0 | 0
46 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000846/2021-2022 |  | 21/09/2021 | 0 | M/S RAJKUMAR KHAN | 9.49 | 0 | 0
47 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/002098/2021-2022 |  | 28/01/2022 | 0 | S & P ENTERPRISE | 55 | 0 | 0
48 | Central Drilling | Srirampur Sub-Division | SUPPLY & DELIVERY of pea size gravels at site for construction of tube well at BORHAL Z-II, hooghly district under CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) |  | ORD/000318/2022-2023 | 574/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.24 | 100
49 | Hooghly Division | Arambug Sub-Division | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of SAOTA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000098/2022-2023 | 1090/Hug | 03/06/2022 | 30 | MESSRS FREEDOM CONSTRUCTION | 30.73 | 22.81 | 100
50 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000942/2021-2022 |  | 24/09/2021 | 0 | SOUMYADIP DE | 44.16 | 0 | 0
51 | Hooghly Division | Arambug Sub-Division | Providing 1950 nos F.H.T.C. in Baikunthapur Village of Baikunthapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | Assistant Engineer | Junior Engineer (Civill) | ORD/000004/2021-2022 | 935/Hug | 06/05/2021 | 40 | PRADIP KUMAR ADHYA | 96.28 | 87.64 | 100
52 | Hooghly Division | Arambug Sub-Division | Providing 325 nos Functional Household Tap Connection (FHTC) with extension of pipeline at Baikunthapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | Assistant Engineer | Junior Engineer (Civill) | ORD/000075/2023-2024 | 1309/HUG | 10/05/2023 | 30 | TANISA ENTERPRISE | 20.47 | 20.4 | 100
53 | Hooghly Division | Arambug Sub-Division | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000357/2022-2023 | 615/Arg | 30/08/2022 | 20 | TANISA ENTERPRISE | 4.47 | 4.47 | 100
54 | Hooghly Division | Arambug Sub-Division | Providing 112 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Mallickpara, Palpara & Janapara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000358/2022-2023 | 616/Arg | 31/08/2022 | 20 | TANISA ENTERPRISE | 4.5 | 4.5 | 100
55 | Hooghly Division | Arambug Sub-Division | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000360/2022-2023 | 615/Arg | 31/08/2022 | 20 | TANISA ENTERPRISE | 4.47 | 0 | 100
56 | Hooghly Division | Arambug Sub-Division | Survey & Collection of Data through mobile app regarding availability of drinking water sanitation & others prarameters in primary schools, anganwari Centers. | Assistant Engineer | Junior Engineer (Civill) | ORD/000487/2021-2022 | 564/CH | 02/12/2021 | 12 | R.K. TRADERS | 3.64 | 3.64 | 100
57 | Hooghly Division | Arambug Sub-Division | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kanpur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000245/2021-2022 | 1996/Hug | 12/11/2021 | 30 | MANISHIKA CONSTRUCTION | 14.98 | 14.88 | 100
58 | Hooghly Division | Arambug Sub-Division | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of KANPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000345/2021-2022 | 46/Hug | 07/01/2022 | 30 | ASIT KUMAR KHANRUI | 7.34 | 0 | 100
59 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002099/2021-2022 |  | 28/01/2022 | 0 | MANISHIKA CONSTRUCTION | 14.88 | 0 | 0
60 | Hooghly Division | Arambug Sub-Division | Construction of 1 no.400 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation / Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System,Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I &II to OHR and for Direct Pumping from Proposed T.W NO.-III to nearest feasible distribution system , Construction of 1 No. 3.6 M X3.00 M Switch Room with Additional Plinth Height without Sanitary and Water Supply Arrangements at 3rd T.W, Construction of Boundary wall at 3 rd T.W Site,Soil Investigation works for constrution of OHR including & Providing 2202 nos, FHTC in Goghat for Augmentation of Goghat Water Supply Scheme under Arambagh Sub-DivisionP.H.E. Dte. of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000048/2022-2023 | 832/Hug | 20/04/2022 | 300 | M/S S.S. ENTERPRISE | 420.51 | 316.67 | 45
61 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of GOGHAT Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000380/2021-2022 | 611/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.85 | 3.83 | 100
62 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100
63 | Hooghly Division | Arambug Sub-Division | Construction of Boundary wall with internal Pathway at HW site of Goghat W/S Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte.Block Arambagh, District:- Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000482/2024-2025 | 4146/HUG | 26/12/2024 | 90 | DHIRENDRA ENGINEERING & CONSTRUCTION | 45.54 | 0 | 0
64 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOGHAT Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000808/2023-2024 | 594/HUG | 22/02/2024 | 60 | SPG ENTERPRISES | 31.67 | 0 | 0
65 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000020/2022-2023 | 1124/1/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
66 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000022/2023-2024 | 1234/3/Hug | 28/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
67 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000056/2022-2023 | 1688/6/HUG | 22/08/2022 | 0 | Resource Division | 22.44 | 0 | 0
68 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000099/2022-2023 | 1773/33/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
69 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000162/2021-2022 | 424/3/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0
70 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000192/2023-2024 | 1385/63/Hug | 15/05/2023 | 0 | Resource Division | 5.34 | 0 | 0
71 | Hooghly Division | Srirampur Sub-Division | Augmentation of RAJBALHAT Water Supply Scheme with Laying Distribution System, Rising Main, Construction of 3.6 M X3.00 M Switch Room, Boundary wall, Repairing of O.H.R, Bounday wall, Existing Switch Room & FHTC at Jangipara Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000043/2022-2023 | 827/Hug | 20/04/2022 | 180 | DIPTI TRADERS | 458.18 | 444.62 | 70
72 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Eastern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000193/2024-2025 | 536/SER | 17/09/2024 | 7 | M/S SHIVAM UDYOG | 4.98 | 0 | 99
73 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Northern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000202/2024-2025 | 547/SER | 19/09/2024 | 7 | M/S SHIVAM UDYOG | 4.99 | 0 | 99
74 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Southern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000207/2024-2025 | 552/SER | 19/09/2024 | 7 | ARUN SEAL AND CO. | 4.99 | 0 | 99
75 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Western zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000209/2024-2025 | 554/SER | 19/09/2024 | 7 | ARUN SEAL AND CO. | 4.97 | 0 | 99
76 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Rajbalhat (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000396/2021-2022 | 289/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 4.01 | 100
77 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Rajbalhat (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000397/2021-2022 | 301/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.12 | 1.96 | 100
78 | Hooghly Division | Srirampur Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at RAJBALHAT ZONE-III PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000446/2022-2023 | 2482/HUG | 21/11/2022 | 30 | R CONSTRUCTION | 12.44 | 11.72 | 0
79 | Hooghly Division | Srirampur Sub-Division | Providing 200 nos. FHTC of Rajbalhat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block- Jangipara]. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000648/2023-2024 | 3479/HUG | 29/11/2023 | 306 | SADHUKHAN ENTERPRISE | 21.58 | 16.02 | 99
80 | Hooghly Division | Srirampur Sub-Division | Laying pipe line within Morhal & Rajbalhat Mouza in Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001259/2024-2025 | 59/SER | 20/01/2025 | 7 | ARUN SEAL AND CO. | 5 | 0 | 0
81 | Hooghly Division | Srirampur Sub-Division | Shifting of existing water supply pipeline due to widening & strengthening of Box Culvert at neart Brindabon Chak, Badur Chak, Rajbalhat & Hariharpur, Block- Jangipara under Rajbalhat Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte . | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001307/2024-2025 | 79/SER | 20/01/2025 | 10 | ARUN SEAL AND CO. | 3.98 | 0 | 0
82 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000009/2022-2023 | 1122/6/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
83 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000158/2021-2022 | 422/3/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0
84 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000320/2023-2024 | 1384/17/Hug | 15/05/2023 | 0 | Resource Division | 1.71 | 0 | 0
85 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Aug. of Rajbalhat W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00015/2022-2023 | BP-2022-23-114 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.48 | 0 | 0
86 | Electrical | Srirampur Sub-Division | Quoation bill for new service connection at Rajbalhat | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00775/2022-2023 | 151 | 08/02/2023 | 0 | WBSEDCL | 3.85 | 0 | 0
87 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 5004123576 Reference ID- 503622497 SM Code- 09694 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01402/2024-2025 | 345 | 31/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
88 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 100000118583 Reference ID- 860312463 SM Code- 09694 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01992/2024-2025 | 480 | 01/10/2024 | 0 | WBSEDCL | 1.63 | 0 | 0
89 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. IV, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000061/2023-2024 | 1640/ED | 11/04/2023 | 90 | SUDIKSHA CONSTRUCTION | 10.68 | 10.39 | 0
90 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000168/2022-2023 | 3501/ED | 30/12/2022 | 90 | MAA KALI ENTERPRISE | 10.68 | 10.39 | 100
91 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJBALHAT PIPED W/S SCHEME, T.W. No. V, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002580/2023-2024 | 456/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 65
92 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERISLS OF 200 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000099/2022-2023 | 234/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 3.87 | 3.41 | 90
93 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ATY RAJBALHAT W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000100/2022-2023 | 233/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 2.79 | 2.79 | 100
94 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR RAJBALHAT W/S SCHEME, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000101/2022-2023 | 231/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 2.4 | 2.23 | 100
95 | Central Drilling | Srirampur Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000102/2022-2023 | 237/CMSD-II (D) | 20/05/2022 | 15 | M/S SAIKAT ENTERPRISE | 2.08 | 1.9 | 100
96 | Hooghly Division | Chinsuria Sub-Division | Providing 890 nos Functional Household Tap Connection (FHTC) within the Rameswarpur Mouza of Rameswarpur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000458/2021-2022 | 476/Hug | 10/03/2022 | 40 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.49 | 43.85 | 0
97 | Hooghly Division | Chinsuria Sub-Division | Providing 810 nos Functional Household Tap Connection (FHTC) within the Chandpur, Danpur, Keshabbati & Nandigram Mouza of Rameswarpur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000459/2021-2022 | 477/Hug | 10/03/2022 | 40 | M/S RAJKUMAR KHAN | 40.4 | 36.55 | 0
98 | Hooghly Division | Arambug Sub-Division | Providing 50 nos Functional Household Tap Connection (FHTC) within Kanaipur, Gohalisanra & Bali Village of Bali Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000247/2022-2023 | 711/HUG | 07/04/2022 | 50 | S.D ENTERPRISE (SAMIR KR. DAS) | 2.37 | 2.43 | 0
99 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BALI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000486/2024-2025 | 4150/HUG | 26/12/2024 | 90 | M/S T.K.B. CONSTRUCTION | 17.12 | 0 | 0
100 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000019/2022-2023 | 1124/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
101 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 130.33 | 30
102 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000122/2023-2024 | 1264/17/HUG | 03/05/2023 | 0 | Resource Division | 19.8 | 0 | 0
103 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000261/2023-2024 | 1386/40/Hug | 15/05/2023 | 0 | Resource Division | 10.44 | 0 | 0
104 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000513/2023-2024 | 3059/Hug | 11/10/2023 | 0 | Resource Division | 2.16 | 0 | 0
105 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New Connection of Choutara T/W-I W/S scheme under ED PHE Dte. (SM/12252) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06544/2023-2024 | 909 | 21/03/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
106 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New Connection of Choutara T/W-II W/S scheme under ED PHE Dte. (SM/12252) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06548/2023-2024 | 908 | 21/03/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
107 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chautara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000080/2022-2023 | 3462/ED | 30/12/2022 | 90 | DAS ENTERPRISE | 20.46 | 16.79 | 35
108 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 154.2 | 15
109 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000110/2023-2024 | 1264/5/HUG | 03/05/2023 | 0 | Resource Division | 11.27 | 0 | 0
110 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000250/2023-2024 | 1386/29/Hug | 15/05/2023 | 0 | Resource Division | 5.16 | 0 | 0
111 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - I, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562461, Dated - 16-02-2024, Application No. - 5004013365, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06156/2023-2024 | 795 | 22/02/2024 | 0 | WBSEDCL | 9.09 | 0 | 0
112 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - II, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562460, Dated - 16-02-2024, Application No. - 5004013396 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06157/2023-2024 | 796 | 22/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
113 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kamrai water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000085/2022-2023 | 3467/ED | 30/12/2022 | 630 | DEBJYOTI BASU | 22.37 | 22 | 95
114 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 366.41 | 15
115 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000111/2023-2024 | 1264/6/HUG | 03/05/2023 | 0 | Resource Division | 27.64 | 0 | 0
116 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000260/2023-2024 | 1386/39/Hug | 15/05/2023 | 0 | Resource Division | 13.21 | 0 | 0
117 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000509/2023-2024 | 3059/1/Hug | 11/10/2023 | 0 | Resource Division | 13.21 | 0 | 0
118 | Electrical | Chinsuria Sub-Division | Additional Quotation for new service connection at Kuchpala W/S Sch. , T/W No. - I [SM/12238] , Block - Polba-Dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 860296974, dt. - 15/04/2024, Application No. - 100000105244 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00189/2024-2025 | 74 | 18/04/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
119 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kuchpala W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04323/2023-2024 | 434 | 21/11/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
120 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kuchpala W/S Sch., T/W No. - I, Block - Polba-Dadpur under Dadpur CCC, WBSEDCL, Ref. Id. - 503553646,dt. - 11-03-2024, Application No. - 5003998904 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06460/2023-2024 | 887 | 15/03/2024 | 0 | WBSEDCL | 12.43 | 0 | 0
121 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kuchpala water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000161/2022-2023 | 3496/ED | 30/12/2022 | 90 | M/S DILIP MITRA | 21.59 | 20.76 | 90
122 | Hooghly Division | Srirampur Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD BANDPUR ICHAPASARA ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | BILL/00683/2024-2025 | BP-2024-25-500 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 8.03 | 0 | 0
123 | Hooghly Division | Srirampur Sub-Division | BANDHPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | ORD/000098/2023-2024 | 1371/HUG | 15/05/2023 | 865 | S GHOSH AND ASSOCIATES PVT LTD. | 632.36 | 418.44 | 10
124 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | RTOR000163/2022-2023 | 79/Hug | 06/01/2023 | 0 | Resource Division | 4.95 | 0 | 0
125 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | RTOR000304/2023-2024 | 1384/1/Hug | 15/05/2023 | 0 | Resource Division | 18.08 | 0 | 0
126 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | RTOR000378/2023-2024 | 3005/20/Hug | 05/10/2023 | 0 | Resource Division | 5.56 | 0 | 0
127 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | RTOR000490/2023-2024 | 3060/14/Hug | 11/10/2023 | 0 | Resource Division | 18.08 | 0 | 0
128 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | BILL/04445/2023-2024 | 506 | 08/12/2023 | 0 | WBSEDCL | 0.4 | 0 | 0
129 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | BILL/04446/2023-2024 | 507 | 08/12/2023 | 0 | WBSEDCL | 12.9 | 0 | 0
130 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandhpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | ORD/000128/2022-2023 | 3482/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 21.38 | 20.83 | 90
131 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BANDHPUR water supply scheme, TW No. III, Block: Chanditala-I, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | ORD/003084/2024-2025 | 479/ED | 18/03/2025 | 90 | S.K. ENTERPRISE | 11.3 | 0 | 0
132 | Hooghly Division | Srirampur Sub-Division | HIRE CHARGES BILL ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00044/2022-2023 | BP-2022-23-404 | 15/12/2022 | 0 | DHIRENDRA ENGINEERING & CONSTRUCTION | 2.36 | 0 | 0
133 | Hooghly Division | Srirampur Sub-Division | REGARDING DAMAGE OF PMGSY ROAD 1.027-SONAKA SIDE TO BEGAMPUR PLATFORM VIDE PACKAGE NO.WB08329 IN CHANDITALA-II BLOCK. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00181/2024-2025 | BP-2024-25-97 | 02/05/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9 | 0 | 0
134 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Begampur (Zone- I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000153/2022-2023 | 481/SER | 14/07/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.02 | 4.02 | 0
135 | Hooghly Division | Srirampur Sub-Division | Augmentation of BEGAMPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. . [2nd call of NIeT No. WBPHE/EE/13/HUG/2022-23 Sl No. 02] SL NO - 06 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000237/2022-2023 | 1786/HUG | 26/08/2022 | 30 | SURAJIT SINGHA RAY | 26.17 | 20.01 | 30
136 | Hooghly Division | Srirampur Sub-Division | Augmentation of BEGAMPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000424/2022-2023 | 2320/HUG | 02/11/2022 | 1096 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 245.02 | 192.73 | 25
137 | Hooghly Division | Srirampur Sub-Division | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-I W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000667/2022-2023 | 161/HUG | 16/01/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 0
138 | Hooghly Division | Srirampur Sub-Division | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000668/2022-2023 | 162/HUG | 16/01/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 0
139 | Hooghly Division | Srirampur Sub-Division | Laying Distribution of left out portion of pipeline to restore the water supply and other allied works at Begampur Water Supply Scheme (Zone-I) within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000782/2023-2024 | 530/HUG | 20/02/2024 | 15 | SURAJIT SINGHA RAY | 12.25 | 0 | 0
140 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | RTOR000012/2023-2024 | 1107/1/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0
141 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | RTOR000306/2023-2024 | 1384/3/Hug | 15/05/2023 | 0 | Resource Division | 5.77 | 0 | 0
142 | Electrical | Srirampur Sub-Division | payment of quotation of wbsedcl bill Begampur w/s scheme z II PH NO III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00744/2023-2024 | 33 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
143 | Electrical | Srirampur Sub-Division | Payment of Wbsedcl Quotation for Begampur W/S Scheme Zone-I, PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00745/2023-2024 | 32 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
144 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection of WBSEDCL for Begampur Kharsari P-II W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00773/2022-2023 | 145 | 30/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0
145 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur Kharsarai water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000053/2022-2023 | 2043/ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 0.27 | 50
146 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Begampur water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000199/2022-2023 | 826/ED | 14/02/2023 | 90 | CINZANO | 21.49 | 21.49 | 99
147 | Electrical | Srirampur Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Begampur Purba Tajpur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/001127/2022-2023 | 726/HMSD | 24/03/2023 | 30 | ART CONSORTIUM | 3.24 | 3.24 | 0
148 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/001176/2022-2023 | 2043 /ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 10.32 | 0
149 | Electrical | Srirampur Sub-Division | Quotation bill payment for Begampur w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | VCH/002688/2022-2023 |  | 04/11/2022 | 0 | WBSEDCL | 0.68 | 0 | 0
150 | Hooghly Division | Arambug Sub-Division | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000043/2023-2024 | 1158/HUG | 20/04/2023 | 30 | RANA ENTERPRISE | 7.31 | 5.72 | 95
151 | Hooghly Division | Arambug Sub-Division | Providing 1102 nos Functional Household Tap Connection (FHTC) within Paschim Thakurani Chak Mouza of PurbaThakurani Chak (Zone-I)Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000060/2022-2023 | 888./HUG | 29/04/2022 | 40 | DIPTI TRADERS | 52.17 | 45.78 | 0
152 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-I PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000109/2023-2024 | 1429/HUG | 18/05/2023 | 45 | MA CONSTRUCTION | 28.31 | 26.36 | 100
153 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PURBO THAKURANICHAWK , RAJHATO , KAKNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000169/2024-2025 | 3167/HUG | 10/09/2024 | 250 | MONDAL PRECISION PRIVATE LIMITED | 48.47 | 0 | 66
154 | Hooghly Division | Arambug Sub-Division | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000237/2023-2024 | 1157/Hug | 20/04/2023 | 30 | SUDIPTA SINHA | 6.7 | 6.02 | 10
155 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Internal Pathway & Land development at the Head Work Site of PURBA THAKURANICHAK ZONE-II Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000540/2022-2023 | 2741/HUG | 07/12/2022 | 45 | DILIP KUMAR GHOSH | 13.62 | 13.29 | 50
156 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00356/2023-2024 | BP-2023-24-296 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.71 | 0 | 0
157 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
158 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
159 | Hooghly Division | Arambug Sub-Division | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000741/2022-2023 | 617/HUG | 03/03/2023 | 270 | M/S RAJKUMAR KHAN | 266.71 | 249.15 | 80
160 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000090/2023-2024 | 1263/5/Hug | 03/05/2023 | 0 | Resource Division | 18.83 | 0 | 0
161 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000172/2023-2024 | 1386/43/Hug | 15/05/2023 | 0 | Resource Division | 3.73 | 0 | 0
162 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000238/2022-2023 | 127/26/Hug | 13/01/2023 | 0 | Resource Division | 19.18 | 0 | 0
163 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000331/2023-2024 | 2607/2/Hug | 29/08/2023 | 0 | Resource Division | 2.97 | 0 | 0
164 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000452/2023-2024 | 3057/23/Hug | 11/10/2023 | 0 | Resource Division | 3.73 | 0 | 0
165 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03829/2023-2024 | 287 | 20/09/2023 | 0 | WBSEDCL | 5.55 | 0 | 0
166 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03830/2023-2024 | 288 | 20/09/2023 | 0 | WBSEDCL | 7.41 | 0 | 0
167 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sahapur water supply scheme TW No I and II Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000233/2022-2023 | 864/ED | 14/02/2023 | 90 | TRIO CONCERN | 20.77 | 20.76 | 45
168 | Hooghly Division | Chandannagar Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/00229/2022-2023 | BP-2022-23-546 | 21/02/2023 | 0 | GOUR KUMAR DAS | 0.65 | 0 | 0
169 | Hooghly Division | Chandannagar Sub-Division | Route survey Design drawing & DPR preparation of Purba Ramnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000178/2022-2023 | 272/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.03 | 0
170 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of PURBA RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Repairing of Existing Switch Rooms, Boundary Wall of existing T.W Sites, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [AUGMENTATION SCHEME] [2nd Call of WBPHE/EE/33/HUG/2022-23(Sl No. 4)] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000229/2023-2024 | 2062/HUG | 17/07/2023 | 822 | BANSBERIA CONSTRUCTION CO. | 789.94 | 708.35 | 55
171 | Hooghly Division | Chandannagar Sub-Division | Repairing of 5.4 mtr x 3.6 mtr size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000574/2021-2022 | 534/CHAN | 12/11/2021 | 30 | SWASTIK ENTERPRISE | 2.96 | 2.94 | 0
172 | Hooghly Division | Chandannagar Sub-Division | Repairing of 3.6 mtr. x 3.0 mtr. size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000575/2021-2022 | 660/CHAN | 27/12/2021 | 30 | SWASTIK ENTERPRISE | 2.75 | 2.58 | 0
173 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | RTOR000077/2023-2024 | 1235/14/Hug | 28/04/2023 | 0 | Resource Division | 71.65 | 0 | 0
174 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | RTOR000137/2022-2023 | 2686/4/Hug | 01/12/2022 | 0 | Resource Division | 0.32 | 0 | 0
175 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | RTOR000298/2023-2024 | 1383/42/Hug | 15/05/2023 | 0 | Resource Division | 27.81 | 0 | 0
176 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | RTOR000464/2023-2024 | 3058/26/Hug | 11/10/2023 | 0 | Resource Division | 28 | 0 | 0
177 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H No . 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03771/2023-2024 |  | 05/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0
178 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H No 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03772/2023-2024 | 275 | 08/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0
179 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H NO 4 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03773/2023-2024 | 274 | 08/09/2023 | 0 | WBSEDCL | 5.06 | 0 | 0
180 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Ramnagar water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000222/2022-2023 | 853/ED | 14/02/2023 | 90 | C.M. ENTERPRISE | 21.49 | 20.88 | 85
181 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of SRIPUR PANDUAH W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000084/2023-2024 | 1338/HUG | 11/05/2023 | 30 | AMBIAN INFRASTRUTTURE | 16.02 | 16.02 | 85
182 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of SRIPUR (PANDUA) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000270/2022-2023 | 725/CH | 23/08/2022 | 45 | TOTON MONDAL | 4.99 | 4.99 | 0
183 | Hooghly Division | Chinsuria Sub-Division | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000326/2023-2024 | 2409/HUG | 11/08/2023 | 30 | OSMAN SEKH | 32.34 | 16.14 | 100
184 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under PANDUA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000346/2023-2024 | 2429/HUG | 11/08/2023 | 30 | GHOSH CONSTRUCTION | 42.89 | 37.8 | 80
185 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sripur Pandua (Retrofit) PWSS 2. Digsui Heora Z-I (Retrofit) PWSS 3. Digsui Heora Z-II (Retrofit) PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000835/2023-2024 | 213/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.48 | 0.48 | 45
186 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sripur village under Pandua Block, Panpara village of Pandua Block and Akna village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000989/2023-2024 | 263/CH | 14/03/2024 | 7 | ASHA ENTERPRISE | 0.95 | 0.95 | 100
187 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001885/2024-2025 | 246/CH | 19/02/2025 | 10 | ASHA ENTERPRISE | 2.73 | 0 | 0
188 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001916/2024-2025 | 267/CH | 20/02/2025 | 10 | ASHA ENTERPRISE | 1.66 | 0 | 0
189 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000347/2023-2024 | 3004/2/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0
190 | Electrical | Chinsuria Sub-Division | Quotation money deposition for new service connection at Sripur w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004132708 Reference ID- 503625865 SM Code- 13411 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00326/2024-2025 | 104 | 06/05/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
191 | Electrical | Chinsuria Sub-Division | Supply Xerox Paper ofice of the EE PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/01915/2022-2023 | 253 | 31/03/2023 | 0 | BARRACKPORE CENTRAL ZONE | 0.09 | 0 | 0
192 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pandua, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000170/2024-2025 | 1193/ED | 14/06/2024 | 90 | SUBHRA ENTERPRISE | 10.75 | 8.25 | 60
193 | Electrical | Chinsuria Sub-Division | "Supply, Delivery & Installation of S/P/M & other E/M equipments etc. for Sripur W/S. Sch. TW-III RA-I" | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001034/2022-2023 | 1320/ED | 17/08/2022 | 90 | SWAPAN ENTERPRISE | 7.37 | 7.07 | 0
194 | Electrical | Chinsuria Sub-Division | Withdrawing of 10 HP submersible pumping machinery and installation of standby pumping machinery and allied electrical/mechanical works at Sripur w/s scheme, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001135/2022-2023 | 1991/HMSD | 10/11/2022 | 21 | KUSHANI ENTERPRISE | 2.45 | 2.36 | 0
195 | Electrical | Chinsuria Sub-Division | Quatation bill for Sripur W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/002739/2022-2023 |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.96 | 0 | 0
196 | Electrical | Chinsuria Sub-Division | Quotation bill for Sripur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/002751/2022-2023 | 108 | 18/11/2022 | 0 | WBSEDCL | 2.96 | 0 | 0
197 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | RTOR000176/2023-2024 | 1385/47/Hug | 15/05/2023 | 0 | Resource Division | 0.58 | 0 | 0
198 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2Nos. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT MADHABPUR HW SITE AND KUMIRMORA Z-I 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000147/2024-2025 | 430/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 95
199 | Hooghly Division | Srirampur Sub-Division | Madhabpur Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000690/2022-2023 | 326/HUG | 03/02/2023 | 788 | ARUN SEAL AND CO. | 443.64 | 229.81 | 50
200 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000167/2022-2023 | 79/10/Hug | 06/01/2023 | 0 | Resource Division | 11.08 | 0 | 0
201 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000317/2023-2024 | 1384/14/Hug | 15/05/2023 | 0 | Resource Division | 11.08 | 0 | 0
202 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000494/2023-2024 | 3060/12/Hug | 11/10/2023 | 0 | Resource Division | 11.08 | 0 | 0
203 | Electrical | Srirampur Sub-Division | Madhavpur w/s scheme,P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/03774/2023-2024 | 273 | 08/09/2023 | 0 | WBSEDCL | 3.71 | 0 | 0
204 | Electrical | Srirampur Sub-Division | Madhavpur w/s scheme,P H No 2 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04511/2023-2024 | 554 | 21/12/2023 | 0 | WBSEDCL | 6.73 | 0 | 0
205 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Madhabpur water supply scheme TW No I and II Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000231/2022-2023 | 862/ED | 14/02/2023 | 899 | NEW RANBEE ENGINEERING | 20.36 | 17.07 | 40
206 | Electrical | Srirampur Sub-Division | Rectification & overhualing of VCB Panel, LT Panel, ATS Panel, AVR and transformer at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001207/2021-2022 | 145/AE-I/ED | 18/02/2022 | 90 | ORIENTAL ENGINEERING CO. | 1.9 | 0 | 0
207 | Electrical | Srirampur Sub-Division | Supply & Installation of NRV and other allied works at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001208/2021-2022 | 1009/AE-I/ED | 13/08/2021 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
208 | Electrical | Srirampur Sub-Division | Supply & Installation of Butterfly valve for pump set no-2 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001210/2021-2022 | 42/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
209 | Electrical | Srirampur Sub-Division | Supply & Installation of Butterfly valve & Check valve for pump set no-3 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001211/2021-2022 | 43/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
210 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) in GHOSHPUR PWSS, Block KHANAKUL-I under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000245/2023-2024 | 2100/HUG | 19/07/2023 | 587 | GHOSH BROTHERS | 95.26 | 79.36 | 80
211 | Hooghly Division | Arambug Sub-Division | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Ghoshpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001049/2023-2024 | 470/Arg | 05/07/2023 | 15 | MAYA CONSTRUCTION | 0.97 | 0.97 | 100
212 | Hooghly Division | Arambug Sub-Division | DAHAR KUNDU(ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly.[NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000153/2023-2024 | 1567/HUG | 29/05/2023 | 764 | ASIA CONSTRUCTION | 365.13 | 209.37 | 30
213 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) MAYAPUR PWSS (Z-II)- 1no¿s (2) BALUNDI PWSS - 4no¿s (3) BHALIA PWSS (Z-I)- 2 no¿s (4) BHALIA PWSS (Z-II)- 1 no¿s (5) DAHARKUNDU PWSS (Z-I)- 2 no¿s, (6) DAHARKUNDU PWSS (Z-II)- 2 no¿s, (7) GOBINDANAGAR PWSS(Z-I) ¿2 no¿s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002742/2024-2025 | 1150/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0
214 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000043/2023-2024 | 1234/16/Hug | 28/04/2023 | 0 | Resource Division | 8.15 | 0 | 0
215 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000491/2023-2024 | 3057/3/Hug | 11/10/2023 | 0 | Resource Division | 8.14 | 0 | 0
216 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-I,TW No-II Block-Arambag,Dist-Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03883/2023-2024 | 312 | 27/09/2023 | 0 | WBSEDCL | 8.01 | 0 | 0
217 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Daharkundu W/S. Sch. Z-I. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04085/2023-2024 | 354 | 12/10/2023 | 0 | WBSEDCL | 4.97 | 0 | 0
218 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-I, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000172/2022-2023 | 765/ED | 09/02/2023 | 90 | POLYCON ENGINEERS | 20.39 | 20.22 | 30
219 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR BETA PORABAZAR ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00658/2024-2025 | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 26.22 | 0 | 0
220 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 348.41 | 15
221 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000113/2023-2024 | 1264/8/HUG | 03/05/2023 | 0 | Resource Division | 48.05 | 0 | 0
222 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000501/2023-2024 | 3059/2/Hug | 11/10/2023 | 0 | Resource Division | 1.68 | 0 | 0
223 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04641/2023-2024 | 631 | 08/01/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
224 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04642/2023-2024 | 630 | 08/01/2024 | 0 | WBSEDCL | 24.56 | 0 | 0
225 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000282/2022-2023 | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 90
226 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAHISHGOT Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000301/2024-2025 | 3659/HUG | 13/11/2024 | 90 | MAA BUNAMATA ENTERPRISE | 16.12 | 0 | 0
227 | Hooghly Division | Arambug Sub-Division | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 301.94 | 45
228 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
229 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000217/2022-2023 | 127/Hug | 13/01/2023 | 0 | Resource Division | 35.96 | 0 | 0
230 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000488/2023-2024 | 3057/4/Hug | 11/10/2023 | 0 | Resource Division | 12.4 | 0 | 0
231 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mahisgot w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/14116) Application No-5004015913 Reference Id-503563370 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06067/2023-2024 | 755 | 16/02/2024 | 0 | WBSEDCL | 5.89 | 0 | 0
232 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mahisgot w/S Scheme,Zone-II,PH No-II Block-Khanakul-I Dist-Hooghly under ED,PHE Dte. (SM/14116) Application No-5004068599 Reference Id-503594190 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06468/2023-2024 | 892 | 18/03/2024 | 0 | WBSEDCL | 4.28 | 0 | 0
233 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisgot water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000176/2022-2023 | 769/ED | 09/02/2023 | 90 | M/S S R ENTERPRISE | 20.27 | 0 | 0
234 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00089/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.12 | 0 | 0
235 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00220/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 33.47 | 0 | 0
236 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00417/2023-2024 | BP-2023-24-342 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.93 | 0 | 0
237 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000153/2023-2024 | 1385/24/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0
238 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
239 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL BHANDARHATI ROAD | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00659/2024-2025 | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13.02 | 0 | 0
240 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR CHINSURAH DHANIAKHALI | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00660/2024-2025 | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 18.03 | 0 | 0
241 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FORHARIPAL DHANIAKHALI ROAD | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00661/2024-2025 | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 45.52 | 0 | 0
242 | Hooghly Division | Chinsuria Sub-Division | BHANDARHATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under DHANIAKHALI Block under Chinsurah Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000093/2023-2024 | 1357/HUG | 12/05/2023 | 842 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 302.26 | 104.6 | 50
243 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 no.150 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System & Construction of 5.4 M X3.65 M Switch Room with Additional Plinth Height, Sanitary and Water Supply Arrangements including Soil Investigation works for construction of OHR at Head Work Site for BHANDARHATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000125/2021-2022 | 1143/Hug | 29/06/2021 | 304 | UNIQUE AGENCY | 117.52 | 39.11 | 0
244 | Hooghly Division | Chinsuria Sub-Division | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No. -I & II to O.H.R and interconnection with distribution system including allied work of BHANDARHATI W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000130/2022-2023 | 441/Arg | 22/06/2022 | 30 | UNIQUE AGENCY | 3.93 | 0 | 99
245 | Hooghly Division | Chinsuria Sub-Division | Construction of approach road at Head work Site of BHANDARHATI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E.Dte. [Block - Arambagh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000430/2022-2023 | 734/Arg | 29/09/2022 | 15 | UNIQUE AGENCY | 3.67 | 3.62 | 0
246 | Hooghly Division | Chinsuria Sub-Division | Laying of pipe line for left out portion within command area of Samta, Dakshin Para, Kazi Para, Paschim Para habitation of Samta Village, Tnaksal, Dakshin Para habitation of Takshal Village & Balaichak, Kaji Para habitation of Balai Chak Village under BHANDARHATI Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block - Arambagh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000431/2022-2023 | 736/Arg | 29/09/2022 | 25 | UNIQUE AGENCY | 1.59 | 1.59 | 0
247 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000460/2021-2022 | 66/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 4.77 | 0
248 | Hooghly Division | Chinsuria Sub-Division | Additional Survey work for Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000461/2021-2022 | 67/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.35 | 0.31 | 0
249 | Hooghly Division | Chinsuria Sub-Division | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000591/2023-2024 | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0
250 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000644/2023-2024 | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0
251 | Hooghly Division | Chinsuria Sub-Division | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room & Boundary wall, Repairing of OHR in Zone-I & FHTC within Zone-I & II For Augmentation of BHANDARHATI ZONE-I &II Piped Water Supply Scheme under DHANIAKHALI Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000781/2022-2023 | 845/HUG | 23/03/2023 | 916 | DAS ENTERPRISE | 184.79 | 85.5 | 85
252 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DASGHARA II GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000917/2023-2024 | 252/CH | 12/03/2024 | 30 | TOTON MONDAL | 4.99 | 4.95 | 90
253 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000226/2022-2023 | 226/3/Hug | 24/01/2023 | 0 | Resource Division | 60.58 | 0 | 0
254 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000258/2023-2024 | 1386/37/Hug | 15/05/2023 | 0 | Resource Division | 22.62 | 0 | 0
255 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Bhandarhati w/s Scheme,PH No-V, Block-Dhaniakhali Dist-Hooghly under electrical division,PHE Dte.(SM/14040)Application No-5004059159 Reference Id-503589837. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00325/2024-2025 | 97 | 06/05/2024 | 0 | WBSEDCL | 10.74 | 0 | 0
256 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for Bhanderhati T/W-V W/S scheme under ED PHE Dte. (SM/14040) | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01163/2024-2025 | 291 | 15/07/2024 | 0 | WBSEDCL | 1.77 | 0 | 0
257 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Bhandarhati W/S. Sch. TW-III" | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03757/2023-2024 | 253 | 05/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0
258 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bhandarhati TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03789/2023-2024 |  | 11/09/2023 | 0 | WBSEDCL | 6.36 | 0 | 0
259 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Bhandarhati TW-III" | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03791/2023-2024 | 311 | 29/09/2023 | 0 | WBSEDCL | 0.11 | 0 | 0
260 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Bhanderhati PWSS, TW - IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04368/2023-2024 | 453 | 01/12/2023 | 0 | WBSEDCL | 4.22 | 0 | 0
261 | Electrical | Chinsuria Sub-Division | Quotation for New Service Connection at Bhandarhati W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04659/2023-2024 | 667 | 15/01/2024 | 0 | WBSEDCL | 8.52 | 0 | 0
262 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhandarhati water supply scheme, T.W. No.- I, II, III & IV, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000201/2022-2023 | 828/ED | 14/02/2023 | 760 | EASTERN INDIA SALES & SERVICE | 42.97 | 10.44 | 25
263 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000222/2024-2025 | 3434/HUG | 03/10/2024 | 360 | DIBYENDU DHARA | 47.26 | 0 | 50
264 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 90.27 | 50
265 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
266 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000084/2023-2024 | 1234/43/Hug | 28/04/2023 | 0 | Resource Division | 30.64 | 0 | 0
267 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000184/2023-2024 | 1385/55/Hug | 15/05/2023 | 0 | Resource Division | 12.9 | 0 | 0
268 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000469/2023-2024 | 3057/15/Hug | 11/10/2023 | 0 | Resource Division | 12.71 | 0 | 0
269 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mostafapur w/s Scheme,PH No-I Block-Khanakul-II District-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004136071 Reference Id-503627505. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00709/2024-2025 | 211 | 11/06/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
270 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mostafapur w/s scheme,TW No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004151915 Reference Id-503634018 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01590/2024-2025 | 357 | 07/08/2024 | 0 | WBSEDCL | 8.49 | 0 | 0
271 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mostafapur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002465/2023-2024 | 326/ED | 21/02/2024 | 90 | M.S ENTERPRISE | 21.9 | 0 | 0
272 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOSTAFAPUR water supply scheme, TW No. III, Block: Khanakul-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/003097/2024-2025 | 483/ED | 18/03/2025 | 90 | SUDIP PRADHAN | 11.3 | 0 | 0
273 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR BHANDARHATI KUMRUL ROAD | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00662/2024-2025 | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 5.52 | 0 | 0
274 | Hooghly Division | Chinsuria Sub-Division | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 172.02 | 20
275 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 24.08 | 20
276 | Hooghly Division | Chinsuria Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Shrirampur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000334/2023-2024 | 2418/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.91 | 8.57 | 25
277 | Hooghly Division | Chinsuria Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-IV) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002234/2024-2025 | 408/CH | 10/03/2025 | 15 | TECHVISION | 4.2 | 0 | 0
278 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000127/2023-2024 | 1264/22/HUG | 03/05/2023 | 0 | Resource Division | 21.65 | 0 | 0
279 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000492/2023-2024 | 3059/18/Hug | 11/10/2023 | 0 | Resource Division | 16.31 | 0 | 0
280 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shrirampur water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000089/2023-2024 | 2068/ED | 30/05/2023 | 90 | PURUSHOTTAM ENTERPRISE | 20.35 | 0 | 0
281 | Hooghly Division | Arambug Sub-Division | NAKUNDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000147/2023-2024 | 1502/HUG | 22/05/2023 | 664 | UNIQUE AGENCY | 554.69 | 332.9 | 50
282 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000055/2023-2024 | 1234/25/Hug | 28/04/2023 | 0 | Resource Division | 30.08 | 0 | 0
283 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000160/2023-2024 | 1385/31/Hug | 15/05/2023 | 0 | Resource Division | 10.84 | 0 | 0
284 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000212/2022-2023 | 127/17/Hug | 13/01/2023 | 0 | Resource Division | 35.47 | 0 | 0
285 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000329/2023-2024 | 2607/Hug | 29/08/2023 | 0 | Resource Division | 35.3 | 0 | 0
286 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000471/2023-2024 | 3057/13/Hug | 11/10/2023 | 0 | Resource Division | 10.84 | 0 | 0
287 | Electrical | Arambug Sub-Division | quotation of New Service Connection for Nakunda W/S Scheme, TW No-I Block-Goghat-I, Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02478/2023-2024 | 151 | 01/08/2023 | 0 | WBSEDCL | 5.07 | 0 | 0
288 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Nakunda W/s Scheme,TW No-2, Block-Goghat-II, Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02479/2023-2024 | 152 | 01/08/2023 | 0 | WBSEDCL | 5.56 | 0 | 0
289 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nakunda water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000177/2022-2023 | 770/ED | 09/02/2023 | 90 | R.M.D TRADING. | 20.61 | 20.59 | 40
290 | Hooghly Division | Arambug Sub-Division | Repairing of Concrete Roads damaged due to Laying of Augmentation work of GHOSHPUR Water Supply Scheme under KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000022/2023-2024 | 1102/HUG | 17/04/2023 | 30 | ARATI ENGINEERING | 18.55 | 0 | 0
291 | Hooghly Division | Arambug Sub-Division | AUGMENTATION of GHOSHPUR Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-KHANAKUL-I, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000324/2023-2024 | 2414/HUG | 11/08/2023 | 599 | GHOSH BROTHERS | 333.22 | 233.14 | 80
292 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at 3Nos. Proposed TubeWell Sites of Ghoshpur Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000474/2024-2025 | 4053/HUG | 19/12/2024 | 90 | M/S KAUSAR CONSTRUCTION | 23.36 | 0 | 0
293 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at Head Work Site of GHOSHPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000480/2024-2025 | 4056/HUG | 19/12/2024 | 90 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 23.74 | 0 | 0
294 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at GHOSHPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000771/2022-2023 | 742/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 11.32 | 100
295 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000099/2023-2024 | 1263/16/Hug | 03/05/2023 | 0 | Resource Division | 61 | 0 | 0
296 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000190/2023-2024 | 1385/61/Hug | 15/05/2023 | 0 | Resource Division | 0.31 | 0 | 0
297 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghoshpur W/S. Sch.PH-V | Assistant Engineer | Junior Engineer (Civill) | BILL/04584/2023-2024 | 585 | 28/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
298 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0
299 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghoshpur water supply scheme, T.W. No. I, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002474/2023-2024 | 335/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
300 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at PASCHIM JOYKRISHNAPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-18] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000051/2023-2024 | 1203/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.09 | 0
301 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.39 | 100
302 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000462/2023-2024 | 3058/22/Hug | 11/10/2023 | 0 | Resource Division | 26.06 | 0 | 0
303 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service Connection of Paschim Joykrishnapur w/s scheme,Zone-2,PH No-3 Distric- Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02004/2023-2024 | 105 | 19/07/2023 | 0 | WBSEDCL | 3.19 | 0 | 0
304 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Paschim Joykrishnapur W/S Scheme,Zone-I,TW No-III Block-Haripal Dist-hooghly under ED,PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03853/2023-2024 | 304 | 26/09/2023 | 0 | WBSEDCL | 10.44 | 0 | 0
305 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Paschim Joykrishnapur water supply scheme, Zone-I, T.W. No. I & Zone-II, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000003/2023-2024 | 1619/ED | 11/04/2023 | 897 | STANDARD ELECTRICALS | 21.81 | 19.77 | 40
306 | Electrical | Howrah Mechanical Sub-Division | Car Hire Charges Bill for official use office of the Executive Engineer Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000985/2023-2024 | 959/HMSD | 20/04/2023 | 365 | SANJIB PRADHAN | 5 | 1.16 | 1
307 | Electrical | Howrah Mechanical Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001104/2023-2024 | 2830/HMSD | 30/10/2023 | 182 | SANJIB PRADHAN | 0.86 | 0 | 42
308 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Joykrishnapur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001128/2022-2023 | 727/HMSD | 24/03/2023 | 30 | KUNAL ENTERPRISE | 3.01 | 0 | 0
309 | Electrical | Howrah Mechanical Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001901/2023-2024 | 3112/HMSD | 22/11/2023 | 196 | SIDDHARTHA CHATTERJEE. | 0.93 | 0 | 60
310 | Hooghly Division | Arambug Sub-Division | WBSEDCL bill for Atghara PWSS | Assistant Engineer | Junior Engineer (Civill) | BILL/00408/2022-2023 | BP-2022-23-659 | 29/03/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 5.37 | 0 | 0
311 | Hooghly Division | Arambug Sub-Division | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Arandi W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000140/2022-2023 | 1411/HUG | 12/07/2022 | 30 | OSMAN SEKH | 8.6 | 8.57 | 100
312 | Hooghly Division | Arambug Sub-Division | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF ATGHARA Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000192/2023-2024 | 1775/HUG | 15/06/2023 | 45 | SOUMYAJIT DUTTA | 7.34 | 7.34 | 100
313 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of ATGHARA Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000378/2021-2022 | 609/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.67 | 3.67 | 100
314 | Hooghly Division | Arambug Sub-Division | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection within Shrirampur, Kaiba & Atghara Mouza, Repairing of existing OHR at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000381/2022-2023 | 1181/HUG | 15/06/2022 | 60 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 207.8 | 193.71 | 10
315 | Hooghly Division | Arambug Sub-Division | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection Within Sekendarpur & Helan Mouza, Repairing of Switch room, Boundary wall at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000382/2022-2023 | 1180/HUG | 15/06/2022 | 810 | M/S R.K. CHOUDHURI | 139.82 | 67.92 | 80
316 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at 3rd TubeWell Sites of Dihibagnan & Atghara Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000471/2024-2025 | 4051/HUG | 19/12/2024 | 90 | GOURI ENTERPRISE | 15.53 | 0 | 0
317 | Hooghly Division | Arambug Sub-Division | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of ATGHARA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000671/2022-2023 | 165/HUG | 16/01/2023 | 30 | M/S EMON ENTERPRISE | 12.83 | 0 | 0
318 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000104/2022-2023 | 1773/38/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
319 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000146/2023-2024 | 1385/17/Hug | 15/05/2023 | 0 | Resource Division | 5.48 | 0 | 0
320 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000164/2021-2022 | 424/5/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0
321 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Atghara water supply scheme TW No I Block Khanakul I District Hooghly under ED PHED. | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2022-2023 | 936/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 10.36 | 40
322 | Central Drilling | Arambug Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT SOLEPUR DUTTAPUR (Z-II) PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000272/2022-2023 | 530/CMSD-II | 01/12/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0 | 100
323 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR ATGHARA PWSS, TW-III, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2022-2023 | 1562/CDD | 08/12/2022 | 30 | C.M. ENTERPRISE | 12.49 | 10 | 100
324 | Central Drilling | Arambug Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT ATGHARA PWSS TW-III, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000274/2022-2023 | 530/CMSD-II (D) | 01/12/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.83 | 100
325 | Hooghly Division | Chinsuria Sub-Division | Providing 934 nos F.H.T.C. in Kulipukur & Matukpur Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000021/2021-2022 | 959/Hug | 10/05/2021 | 30 | SAMRAT CONSTRUCTION | 48.63 | 45.38 | 80
326 | Hooghly Division | Chinsuria Sub-Division | Providing 717 nos F.H.T.C. in Marsit&Kshirkundi Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000328/2020-2021 | 400/Hug | 15/02/2021 | 30 | GHOSH CONCERN | 37.28 | 33.73 | 0
327 | Hooghly Division | Chinsuria Sub-Division | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of Namajgram & SUDARSHAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2021-2022 | 117/Hug | 19/01/2022 | 15 | TOTON MONDAL | 18.26 | 17.93 | 0
328 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000014/2021-2022 |  | 12/04/2021 | 0 | M/S T.K.B. CONSTRUCTION | 6.96 | 0 | 0
329 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000935/2021-2022 |  | 24/09/2021 | 0 | M/S T.K.B. CONSTRUCTION | 7.71 | 0 | 0
330 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001028/2021-2022 |  | 30/09/2021 | 0 | SAMRAT CONSTRUCTION | 19.34 | 0 | 0
331 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001125/2021-2022 |  | 16/11/2021 | 0 | GHOSH CONCERN | 24.1 | 0 | 0
332 | Hooghly Division | Arambug Sub-Division | Repairing of R.C.C. Elevated Reservoir of PATUL PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000485/2024-2025 | 4149/HUG | 26/12/2024 | 90 | R.K. TRADERS | 10.98 | 0 | 99
333 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002646/2024-2025 | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
334 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000102/2023-2024 | 1263/17/Hug | 03/05/2023 | 0 | Resource Division | 17.17 | 0 | 0
335 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-II | Assistant Engineer | Junior Engineer (Civill) | BILL/04592/2023-2024 | 593 | 29/12/2023 | 0 | WBSEDCL | 3.51 | 0 | 0
336 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No.-V, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001385/2023-2024 | 4735/ED | 15/12/2023 | 90 | MAA KALI ENTERPRISE | 10.74 | 10.35 | 30
337 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within ARAMBAGH Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000144/2023-2024 | 1497/HUG | 22/05/2023 | 30 | DEBANANDA CONSTRUCTION | 11.81 | 0 | 0
338 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of PURBARAYPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000490/2024-2025 | 4154/HUG | 26/12/2024 | 90 | M/S SHIVAM UDYOG | 11.84 | 0 | 0
339 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PURBARAYPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000762/2022-2023 | 746/HUG | 15/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 0 | 0
340 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000096/2023-2024 | 1263/11/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0
341 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Purba Raypur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000005/2023-2024 | 1621/ED | 11/04/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.75 | 0 | 0
342 | Hooghly Division | Arambug Sub-Division | Laying of pipe line for left out portion within command area of Jaykrishnapur Water Supply Scheme to facilate the FHTC Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000041/2023-2024 | 1170/HUG | 20/04/2023 | 30 | SADHUKHAN ENTERPRISE | 4.76 | 0 | 0
343 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Jaykrishnapur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000141/2023-2024 | 1494/HUG | 22/05/2023 | 30 | A.R. CONSTRUCTION | 11.83 | 0 | 0
344 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100
345 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of JAYKRISHNAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000489/2024-2025 | 4153/HUG | 26/12/2024 | 90 | BOSE ENTERPRISE (RATUL BOSE) | 11.84 | 0 | 0
346 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JAYKRISHNAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000774/2022-2023 | 746/hug | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 10.58 | 100
347 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jaykrishnapur w/s Scheme,TW no-3 Block-Goghat-I Dist-Hooghly under ED,PHE Dte(SM/15808) Application No-5004009573 Reference Id-503561825 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06051/2023-2024 | 748 | 16/02/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
348 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000865/2023-2024 | 3438/ED | 11/08/2023 | 90 | J.K. ENGINEERING CO. | 10.74 | 0 | 0
349 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001150/2022-2023 | 1502/ED | 28/03/2023 | 90 | M/S DILIP MITRA | 10.75 | 0 | 0
350 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000146/2023-2024 | 1507/HUG | 22/05/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 0 | 50
351 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000160/2023-2024 | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 23.3 | 65
352 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000346/2023-2024 | 3004/3/Hug | 05/10/2023 | 0 | Resource Division | 35.71 | 0 | 0
353 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Shibrai W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02905/2023-2024 | 202 | 21/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0
354 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Shibrai W/S. Sch. PH-IV Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05979/2023-2024 | 734 | 05/02/2024 | 0 | WBSEDCL | 7.63 | 0 | 0
355 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shibrai water supply scheme, T.W. No. I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000023/2023-2024 | 1700/ED | 18/04/2023 | 90 | A.G. ENTERPRISE | 22.81 | 11.69 | 50
356 | Hooghly Division | Chinsuria Sub-Division | BASTA Piped Water Supply Scheme with Sinking of tube-well, Laying Distrubtuion System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000780/2022-2023 | 844/HUG | 23/03/2023 | 923 | TOTON MONDAL | 142.86 | 81.67 | 60
357 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000115/2023-2024 | 1264/10/HUG | 03/05/2023 | 0 | Resource Division | 9.67 | 0 | 0
358 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000229/2023-2024 | 1386/8/Hug | 15/05/2023 | 0 | Resource Division | 3.33 | 0 | 0
359 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000502/2023-2024 | 3059/16/Hug | 11/10/2023 | 0 | Resource Division | 3.33 | 0 | 0
360 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basta W/S. Sch.TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04580/2023-2024 | 578 | 27/12/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
361 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basta W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05115/2023-2024 | 686 | 19/01/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
362 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of RASULPUR, SHYAMBALLAVPUR , DIHIBAGNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000264/2024-2025 | 3531/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.49 | 0 | 0
363 | Hooghly Division | Arambug Sub-Division | Laying CI/DI pipes & specials for rising main pipe line in between T.W No.- III to O.H.R. and interconnection with distribution system at 3rd Tube Well Site of DIHI BAGNAN W/S Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000520/2021-2022 | 176/Arg | 21/03/2022 | 10 | M/S ROY ENTERPRISE | 4.83 | 3.72 | 100
364 | Hooghly Division | Arambug Sub-Division | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000598/2021-2022 | 2231/HUG | 15/12/2021 | 30 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 12.8 | 12.09 | 95
365 | Hooghly Division | Arambug Sub-Division | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000599/2021-2022 | 1915/HUG | 27/10/2021 | 40 | M/S PRADYUT KUMAR HAZRA | 40.43 | 2.5 | 97
366 | Hooghly Division | Arambug Sub-Division | Providing 1700 nos F.H.T.C. in Dihibagnan, Para Bagnan & Bhabanipur village of Dihibagnan and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000918/2020-2021 | 1687/Hug | 17/12/2020 | 40 | M/S PRADYUT KUMAR HAZRA | 79.86 | 3.91 | 97
367 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Belmuri village under Dhaniakhali Block, Jot Haranda village of Dhnaiakhali Block and Radhaballavpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000985/2023-2024 | 259/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100
368 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DIHI BAGNAN PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000368/2024-2025 | 1452/ED | 25/07/2024 | 90 | BARMAN ROY TRADERS | 11.09 | 0 | 0
369 | Electrical | Arambug Sub-Division | Hiring of diesel driven contract carriage along with driver for the official use of the SEMC-I PHED | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000962/2023-2024 | 933_HMSD | 18/04/2023 | 365 | S.P. CONSTRUCTION | 5 | 1.58 | 30
370 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dihi Bagnan water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001476/2021-2022 | 552/ED | 22/03/2022 | 90 | BISALAXMI ENTERPRISE | 6.59 | 6.27 | 30
371 | Electrical | Arambug Sub-Division | Supply, delivery & installation of automatic Chlorinator for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002115/2022-2023 | 70/HMSD | 10/01/2023 | 7 | BISALAXMI ENTERPRISE | 0.8 | 0.8 | 100
372 | Electrical | Arambug Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002116/2022-2023 | 657/HMSD | 04/04/2022 | 15 | BOSE & CHATTERJEE INDUSTRIES | 2.37 | 2.37 | 30
373 | Hooghly Division | Arambug Sub-Division | DHARMMAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000005/2023-2024 | 1017/Hug | 06/04/2023 | 1057 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 407.11 | 113.73 | 50
374 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DHARMMAPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000294/2024-2025 | 3655/HUG | 13/11/2024 | 90 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 16.06 | 0 | 0
375 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000400/2024-2025 | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0
376 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000478/2023-2024 | 3057/9/Hug | 11/10/2023 | 0 | Resource Division | 12.23 | 0 | 0
377 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Dharmmapur w/s scheme,PH No-II Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte(SM/17716) Application no-5004012404 Reference Id-503561209 | Assistant Engineer | Junior Engineer (Civill) | BILL/06049/2023-2024 | 740 | 08/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
378 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dharmmapur w/s Scheme,PH No-I Block-Khanakul-I Dist-Hooghly under ED,PHE Dte(SM/17716) Application No-5004012408 Reference Id-503561211 | Assistant Engineer | Junior Engineer (Civill) | BILL/06050/2023-2024 | 741 | 08/02/2024 | 0 | WBSEDCL | 5.64 | 0 | 0
379 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dharmmapur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000050/2023-2024 | 1794/ED | 24/04/2023 | 830 | M/S, GHOSH ENTERPRISE | 20.35 | 2.89 | 30
380 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Ghatampur PWSS 2. Kanajoli PWSS 3. Bhatua PWSS 4. Shrirampur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000777/2023-2024 | 143/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.79 | 0.79 | 30
381 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000256/2023-2024 | 1386/35/Hug | 15/05/2023 | 0 | Resource Division | 4.56 | 0 | 0
382 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000363/2023-2024 | 3004/11/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0
383 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Bhatua PWSS, TW - I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04370/2023-2024 | 455 | 01/12/2023 | 0 | WBSEDCL | 15.6 | 0 | 0
384 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhatua water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000078/2023-2024 | 1924/ED | 15/05/2023 | 90 | UNITED ENTERPRISE | 23.21 | 11.53 | 50
385 | Hooghly Division | Srirampur Sub-Division | NILARPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000230/2023-2024 | 2063/HUG | 17/07/2023 | 270 | BANSBERIA CONSTRUCTION CO. | 411.87 | 170.81 | 40
386 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mundalika-I PWSS 2. Mundalika-II PWSS 3. Nilarpur PWSS 4. Gopalpur PWSS 5. Bishnupur PWSS 6. Radhanagar PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000944/2023-2024 | 114/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
387 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000037/2023-2024 | 1236/4/Hug | 28/04/2023 | 0 | Resource Division | 32.71 | 0 | 0
388 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000310/2023-2024 | 1384/7/Hug | 16/05/2023 | 0 | Resource Division | 7.93 | 0 | 0
389 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000349/2023-2024 | 3005/Hug | 05/10/2023 | 0 | Resource Division | 0.01 | 0 | 0
390 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000510/2023-2024 | 3060/8/Hug | 11/10/2023 | 0 | Resource Division | 7.93 | 0 | 0
391 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04635/2023-2024 | 635 | 08/01/2024 | 0 | WBSEDCL | 4.83 | 0 | 0
392 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04638/2023-2024 | 634 | 08/01/2024 | 0 | WBSEDCL | 8.22 | 0 | 0
393 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nilarpur water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000073/2023-2024 | 1929/ED | 15/05/2023 | 90 | SWAPAN ENTERPRISE | 23.08 | 22.49 | 90
394 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of HASAMPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000420/2022-2023 | 2306/HUG | 28/10/2022 | 60 | MALLIKA ENTERPRISE | 90.96 | 0 | 0
395 | Hooghly Division | Chandannagar Sub-Division | Construction of 1 (One) No. Pump House (3.0 x 3.6 m ) with additional plinth height including internal pathway at 6th tubewell site of Bandipur PWSS Scheme under Hooghly Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000765/2022-2023 | 145/Chan | 16/03/2023 | 40 | BMR ENGINEERING & CONSTRUCTION | 4.99 | 3.25 | 80
396 | Hooghly Division | Chandannagar Sub-Division | Repairing of pump house at 2nd TW site of Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000946/2023-2024 | 285/Chan | 15/03/2024 | 15 | SHREE JAGANNATH ENTERPRISE | 1 | 0.97 | 100
397 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at 2nd TW site of Bandipur Piped Water Supply Scheme Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000947/2023-2024 | 286/Chan | 15/03/2024 | 15 | SHREE JAGANNATH ENTERPRISE | 0.99 | 0.99 | 100
398 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main for Interconnection of Laying distribution system at 6th Tube well site of Bandipur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000949/2023-2024 | 287/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.92 | 0.89 | 100
399 | Hooghly Division | Chandannagar Sub-Division | Repairing Damaged pipeline at Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000954/2023-2024 | 292/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.37 | 0.37 | 100
400 | Hooghly Division | Chandannagar Sub-Division | Repairing of damaged FHTC connection at Bandipur PWSS under Chandannagar Sub-Division under Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002195/2024-2025 | 152/Chan | 31/01/2025 | 15 | MS CHANDIMATA CONSTRUCTION | 0.91 | 0 | 100
401 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 140.7 | 30
402 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0
403 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
404 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000059/2023-2024 | 1234/28/Hug | 28/04/2023 | 0 | Resource Division | 18.54 | 0 | 0
405 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000170/2023-2024 | 1385/41/Hug | 15/05/2023 | 0 | Resource Division | 5.59 | 0 | 0
406 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000433/2023-2024 | 3057/33/Hug | 11/10/2023 | 0 | Resource Division | 5.59 | 0 | 0
407 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhur Kunda w/s Scheme,Zone-II,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17719) Application No-5004320081 Reference Id- 503705387 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01374/2024-2025 | 339 | 30/07/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
408 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/17719) Application No-5004034182 Reference Id-503574967 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06200/2023-2024 | 811 | 28/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
409 | Hooghly Division | Chinsuria Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, HEAD QUARTER, HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00275/2023-2024 | BP-2023-24-232 | 31/07/2023 | 0 | PRADIP KUMAR ADHYA | 3.52 | 0 | 0
410 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION CHARGES | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00423/2024-2025 | BP-2024-25-343 | 02/08/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 3.89 | 0 | 0
411 | Hooghly Division | Chinsuria Sub-Division | REGARDING DAMAGE OF PMGSY ROAD MAHESHPUR MORE TO BHAUSANARA PART OF ANANTPUR CMDA MAHESHPUR MORE IN POLBA DADPUR BLOCK HOOGHLY DISTRICT. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01097/2023-2024 | BP-2023-24-788 | 29/01/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 17.94 | 0 | 0
412 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipeline for inter connection between T.W & Distribution for Augmentation of MAHESPUR ZONE-II Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within POLBA-DADPUR Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000136/2023-2024 | 1478/HUG | 19/05/2023 | 45 | SHREEOM ENTERPRISE | 12.11 | 9.61 | 50
413 | Hooghly Division | Chinsuria Sub-Division | Augmentation of MAHESHPUR (ZONE-II) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block under Chinsurah Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000212/2022-2023 | 1717/Hug | 24/08/2022 | 60 | M/S S.G. CONSTRUCTION | 207.78 | 186.81 | 100
414 | Hooghly Division | Chinsuria Sub-Division | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-II W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000347/2023-2024 | 2440/HUG | 12/08/2023 | 45 | BASU & SONS | 5.31 | 5.28 | 95
415 | Hooghly Division | Chinsuria Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 06 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000353/2022-2023 | 2011/HUG | 13/09/2022 | 30 | OSMAN SEKH | 11.32 | 11.23 | 25
416 | Hooghly Division | Chinsuria Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 07 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000354/2022-2023 | 2012/HUG | 13/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.59 | 0
417 | Hooghly Division | Chinsuria Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000365/2023-2024 | 2456/HUG | 12/08/2023 | 60 | M/S S & P CONSTRUCTION | 9.75 | 9.23 | 80
418 | Hooghly Division | Chinsuria Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-II PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000367/2023-2024 | 2457/HUG | 12/08/2023 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 9 | 8.8 | 75
419 | Hooghly Division | Chinsuria Sub-Division | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000368/2023-2024 | 2458/HUG | 12/08/2023 | 45 | M/S BIMAL DAS AND CO. | 5.31 | 5.28 | 95
420 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000462/2021-2022 | 68/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 4.76 | 0
421 | Hooghly Division | Chinsuria Sub-Division | Additional Survey work for Preparation of Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000463/2021-2022 | 69/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0.37 | 0
422 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of MAHESHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000742/2022-2023 | 649/HUG | 09/03/2023 | 45 | M/S PAULAMI ENTERPRISE | 5.77 | 5.77 | 100
423 | Hooghly Division | Chinsuria Sub-Division | Augmentation of MAHESHPUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block Under Chinsurah Sub-Division of Hooghly Division, PHE Dte. [2nd call of NIeT No. WBPHE/EE/10/HUG/2022-23 Sl No. 02] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000803/2022-2023 | 961/Hug | 31/03/2023 | 90 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 266.8 | 90.67 | 100
424 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Baichi PWSS 2. Mahespur PWSS 3. Uttar Chandannagar PWSS 4. Bahadurpur PWSS 5. Patna BhairavpurPWSS 6. Mandra PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000834/2023-2024 | 212/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 45
425 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion At Sugandha of Mahespur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000840/2023-2024 | 218/CH | 29/02/2024 | 7 | M/S BIMAL DAS AND CO. | 0.85 | 0.85 | 25
426 | Hooghly Division | Chinsuria Sub-Division | Construction of Protection Work at Maheshpur Zone - I under Chinsurah Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000851/2023-2024 | 735/HUG | 05/03/2024 | 30 | SHREEOM ENTERPRISE | 7.63 | 6.47 | 70
427 | Hooghly Division | Chinsuria Sub-Division | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000888/2023-2024 | 812/HUG | 11/03/2024 | 30 | SWARNA ENTERPRISE | 27.22 | 20.29 | 65
428 | Hooghly Division | Chinsuria Sub-Division | Laying Balance portion of Pipeline including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000891/2023-2024 | 815/HUG | 11/03/2024 | 45 | MALLIKA ENTERPRISE | 35.45 | 3.96 | 100
429 | Hooghly Division | Chinsuria Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room ,boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at different TW sites for Augmentation of DHARAMPUR (Maheshpur) Piped Water Supply Scheme, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001027/2023-2024 | 3594/HUG | 05/12/2023 | 60 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 27.85 | 21.94 | 40
430 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion At Amarpur Paschim Para of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001030/2023-2024 | 273/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.98 | 0.98 | 80
431 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion At Choto Pachrakhi of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001031/2023-2024 | 274/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.66 | 0.66 | 80
432 | Hooghly Division | Chinsuria Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at different TW sites for Augmentation of MAHESHPUR Piped Water Supply Scheme under CHINSURAH-MAGRA Block, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001481/2023-2024 | 3595/HUG | 05/12/2023 | 121 | TURNKEY BUSINESS ENGINEERS (I) PVT LTD | 32.82 | 0 | 40
433 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000003/2023-2024 | 1105/2/Hug | 17/04/2023 | 0 | Resource Division | 47.53 | 0 | 0
434 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000018/2022-2023 | 1123/6/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0
435 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000114/2022-2023 | 1991/HUG | 12/09/2022 | 0 | Resource Division | 42.71 | 0 | 0
436 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000257/2023-2024 | 1386/36/Hug | 15/05/2023 | 0 | Resource Division | 11.14 | 0 | 0
437 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Maheshpur (Zone - I) W/S Sch., [SM/10451] T/W No. - IV, Nr. Sugandhya Panchyate, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594865, Dt. - 02-04-2024, Application No. - 5004069700 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00075/2024-2025 | 41 | 09/04/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
438 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT MAHESHPUR (AUG.) W/S SCH., ZONE - II, P.H. NO. - III, dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00758/2023-2024 | 43 | 19/05/2023 | 0 | WBSEDCL | 2.71 | 0 | 0
439 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Maheshpur PWSS, Zone-I, TW - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04369/2023-2024 | 456 | 01/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0
440 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Maheshpur water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000220/2022-2023 | 851/ED | 14/02/2023 | 472 | P.K. ENGINEERING | 21.49 | 21.09 | 95
441 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAHESHPUR PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000377/2024-2025 | 1464/ED | 25/07/2024 | 90 | MAA TARA ENTERPRISE. | 11.1 | 0 | 30
442 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002330/2022-2023 | 2385//HMSD | 27/12/2022 | 30 | DEBASHISH GHOSH | 0.29 | 0.29 | 30
443 | Hooghly Division | Arambug Sub-Division | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000300/2023-2024 | 2363/HUG | 08/08/2023 | 809 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 345.13 | 50
444 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0
445 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000211/2022-2023 | 127/29/Hug | 13/01/2023 | 0 | Resource Division | 18.93 | 0 | 0
446 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000439/2023-2024 | 3057/30/Hug | 11/10/2023 | 0 | Resource Division | 14.98 | 0 | 0
447 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Sunia w/S Scheme,PH No-II, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18593) Application No-5004479490 Reference Id-503802380 | Assistant Engineer | Junior Engineer (Civill) | BILL/02308/2024-2025 | 607 | 05/12/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
448 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Sunia w/s Scheme,PH No-IV,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18593) Application No-5004475105 Reference Id-503799038 | Assistant Engineer | Junior Engineer (Civill) | BILL/02473/2024-2025 | 616 | 05/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
449 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/05994/2023-2024 | 747 | 08/02/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
450 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000917/2023-2024 | 3588/ED | 28/08/2023 | 90 | A.G. ENTERPRISE | 21.49 | 10.28 | 15
451 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer |  | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 450 | 30
452 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer |  | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0
453 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
454 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000463/2023-2024 | 3057/19/Hug | 11/10/2023 | 0 | Resource Division | 20.1 | 0 | 0
455 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme, PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004190291 Reference Id-503647427. | Assistant Engineer |  | BILL/00482/2024-2025 | 150 | 22/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
456 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004215163 Reference Id-503657720 | Assistant Engineer |  | BILL/00624/2024-2025 | 186 | 03/06/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
457 | Electrical | Arambug Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2023 WB-15C-5554 | Assistant Engineer |  | BILL/00625/2024-2025 | 187 | 03/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
458 | Electrical | Arambug Sub-Division | Supply of Fuel for 1(One) no Diesel luxury Taxi on contract Carriage for the office of the Assistant Engineer Howrah mechanical Sub Division PHE Dte(JJM Work for Hooghly District) for the Month of April 2024. | Assistant Engineer |  | BILL/00626/2024-2025 | 191 | 10/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
459 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme, PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/18597) Application No-5004034165 Reference Id-503574963 | Assistant Engineer |  | BILL/06198/2023-2024 | 812 | 28/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
460 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. IV, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer |  | ORD/000136/2024-2025 | 1162/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
461 | Hooghly Division | Chinsuria Sub-Division | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Bagdi Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000044/2024-2025 | 546/CH | 14/06/2024 | 7 | TOTON MONDAL | 4.79 | 4.69 | 95
462 | Hooghly Division | Chinsuria Sub-Division | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Pritala area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000045/2024-2025 | 547/CH | 14/06/2024 | 7 | JOY GURU ENTERPRISE | 4.79 | 4.73 | 95
463 | Hooghly Division | Chinsuria Sub-Division | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 180 M at Proposed TW site of Badinan W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000141/2022-2023 | 1412/HUG | 12/07/2022 | 30 | OSMAN SEKH | 9.29 | 8.93 | 0
464 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BAGNAN ZONE-I (Bagnan, Khanpur, Balarambati, Noapara, Mihirpur) PWSS under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000339/2023-2024 | 2426/HUG | 11/08/2023 | 30 | TOTON MONDAL | 19.11 | 22.89 | 98
465 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Bagnan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000562/2021-2022 | 130/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.03 | 4.01 | 0
466 | Hooghly Division | Chinsuria Sub-Division | Proposed Laying Distribution within Noapara & Bagnan Mouza & Repairing Of Switch Room of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000580/2022-2023 | 2902/HUG | 23/12/2022 | 90 | TOTON MONDAL | 103.85 | 102.37 | 100
467 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BAGNAN Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000599/2023-2024 | 3314/HUG | 10/11/2023 | 45 | SRI KRISHNA ENTERPRISE | 8.61 | 16.78 | 95
468 | Hooghly Division | Chinsuria Sub-Division | Repair and Renovation of R.C.C Elevated Reservoir & Balance FHTC for augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000600/2022-2023 | 2859/HUG | 16/12/2022 | 45 | M/S RAJKUMAR KHAN | 41 | 40.49 | 0
469 | Hooghly Division | Chinsuria Sub-Division | Proposed AUGMENTATION of BAGNAN Zone-II Piped Water Supply Scheme with Laying Distribution System , FHTC & Construction of 1 No 3.6 M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements &Boundary wall at Proposed T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000601/2022-2023 | 2860/HUG | 16/12/2022 | 45 | M/S ROY CONSTRUCTION AND CO. | 35.29 | 0 | 35
470 | Hooghly Division | Chinsuria Sub-Division | Proposed Laying Distribution within Kanuibanka Mouza , FHTC& Repairing Of Boundary Wall of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000605/2022-2023 | 2891/HUG | 22/12/2022 | 60 | M/S.N. ISLAM AND CO. | 85.47 | 81.31 | 70
471 | Hooghly Division | Chinsuria Sub-Division | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Bhuina Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000767/2023-2024 | 121/CH | 16/02/2024 | 15 | TOTON MONDAL | 4.79 | 9.3 | 95
472 | Hooghly Division | Chinsuria Sub-Division | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Brahman Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000768/2023-2024 | 122/CH | 16/02/2024 | 15 | JOY GURU ENTERPRISE | 4.79 | 9.23 | 95
473 | Hooghly Division | Chinsuria Sub-Division | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Kayastha Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000769/2023-2024 | 126/CH | 16/02/2024 | 15 | JOY GURU ENTERPRISE | 4.79 | 9.33 | 95
474 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 28.3 | 80
475 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Bagnan PWSS 2. Bhanderhati PWSS 3. Cheragram PWSS 4. Chopa PWSS 5. Dhamaitikri PWSS 6. Dhaniakhali PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000825/2023-2024 | 203/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
476 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 no. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BAGNAN W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000895/2023-2024 | 819/HUG | 11/03/2024 | 30 | TAPAS ADHYA | 14.7 | 13.9 | 100
477 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000223/2022-2023 | 226/Hug | 24/01/2023 | 0 | Resource Division | 2.85 | 0 | 0
478 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000273/2023-2024 | 1386/50/Hug | 15/05/2023 | 0 | Resource Division | 3.28 | 0 | 0
479 | Hooghly Division | Chinsuria Sub-Division | QUOTATION FOR WBSEDCL FOR ELECTRICAL DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/001389/2022-2023 | C112223783044 | 21/11/2022 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0
480 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New service Connection of Bagnan T/W-V W/S scheme under Electrical Division PHE Dte. (SM/11867) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02294/2024-2025 | BP-24-25-599 | 21/11/2024 | 0 | WBSEDCL | 5.92 | 0 | 0
481 | Electrical | Chinsuria Sub-Division | Quotation Bill foe New Service Connection at Bagnan W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02587/2023-2024 | 158 | 03/08/2023 | 0 | WBSEDCL | 3.74 | 0 | 0
482 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bagnan W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02590/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0
483 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charge at Bagnan w/s scheme, Zone-II, T.W. No.-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02725/2023-2024 | 182 | 11/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0
484 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bagnan water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000195/2022-2023 | 822/ED | 14/02/2023 | 90 | A.S. ENTERPRISE | 21.45 | 18.52 | 30
485 | Hooghly Division | Arambug Sub-Division | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of HAZIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000339/2021-2022 | 16/Hug | 04/01/2022 | 30 | M/S T.K.B. CONSTRUCTION | 19.85 | 20.37 | 0
486 | Hooghly Division | Arambug Sub-Division | PUKHURIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000272/2023-2024 | 2290/HUG | 03/08/2023 | 810 | M/S R.M. CONSTRUCTION | 360.54 | 68.78 | 10
487 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of PUKURIA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000375/2024-2025 | 3718/HUG | 19/11/2024 | 90 | JOY GURU ENTERPRISE | 16.06 | 0 | 0
488 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0
489 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000065/2023-2024 | 1234/32/Hug | 28/04/2023 | 0 | Resource Division | 15.57 | 0 | 0
490 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000133/2023-2024 | 1385/4/Hug | 15/05/2023 | 0 | Resource Division | 8.26 | 0 | 0
491 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000461/2023-2024 | 3057/20/Hug | 11/10/2023 | 0 | Resource Division | 8.26 | 0 | 0
492 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pukuria w/s Scheme,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004151686 Reference Id-503633620 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00413/2024-2025 | 101 | 05/05/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
493 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pukhuria w/s Scheme,PH No-I,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004294636 Reference Id-503691998 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01173/2024-2025 | 313 | 23/07/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
494 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pukhuria water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000047/2023-2024 | 1733/ED | 19/04/2023 | 988 | B.T. PROJECT PVT. LTD. | 41.11 | 0 | 10
495 | Electrical |  | Quotation Bill for New Service Connection at Bandipur W/S. Sch |  |  | BILL/06036/2023-2024 | 738 | 07/02/2024 | 0 | WBSEDCL | 18.99 | 0 | 0
496 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. V, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001530/2021-2022 | 174_ED | 01/02/2022 | 90 | M/S DILIP MITRA | 6.74 | 6.74 | 50
497 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. VI, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002574/2022-2023 | 3483/ED | 30/12/2022 | 90 | M/S S.R. ENTERPRISE | 10.82 | 10.8 | 30
498 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No.- IV, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001280/2023-2024 | 2442_ED | 13/10/2023 | 45 | R.N.S. TRADING | 6.14 | 5.99 | 50
499 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VII, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001521/2021-2022 | 172/ED | 01/02/2022 | 90 | RAJIB COMPANY | 6.59 | 6.59 | 100
500 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VI, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001522/2021-2022 | 171/ED | 01/02/2022 | 90 | ESENCE ENGINEERING CONCERN | 6.58 | 6.58 | 100
501 | Electrical |  | Supply delivery and installation of Chlorinator for BARUIPARA w/s scheme PH No. VI District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001523/2021-2022 | 103/HMSD | 18/01/2022 | 7 | STANDARD ELECTRICALS | 0.76 | 0.76 | 100
502 | Electrical |  | Supply delivery and installation of Chlorinator for Baruipara w/s scheme PH No. VII District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001528/2021-2022 | 83/HMSD | 14/01/2022 | 30 | M/S CHANDIMATA ELECTRICALS | 0.76 | 0.76 | 100
503 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. V, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001533/2021-2022 | 170/ED | 01/02/2022 | 90 | BIJAN ENTERPRISE | 6.63 | 6.57 | 100
504 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 359.37 | 30
505 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000251/2023-2024 | 1386/30/Hug | 15/05/2023 | 0 | Resource Division | 26.93 | 0 | 0
506 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000360/2023-2024 | 3004/21/Hug | 05/10/2023 | 0 | Resource Division | 17.29 | 0 | 0
507 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000536/2023-2024 | 3059/3/Hug | 11/10/2023 | 0 | Resource Division | 26.93 | 0 | 0
508 | Electrical | Chinsuria Sub-Division | Supply of diesel and mobile for inspection car of AE-I under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00258/2024-2025 | 90 | 26/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
509 | Electrical | Chinsuria Sub-Division | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2024 WB-04G-2822 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00460/2024-2025 | 145 | 22/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
510 | Electrical | Chinsuria Sub-Division | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 From 01/06/2024 to 30/06/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01368/2024-2025 | 330 | 30/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
511 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05126/2023-2024 | 699 | 22/01/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
512 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05128/2023-2024 | 698 | 22/01/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
513 | Electrical | Chinsuria Sub-Division | Supply of diesel & mobile oil for inspection car of AE-I under ED , PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06465/2023-2024 | 891 | 18/03/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
514 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kumrul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2022-2023 | 3468/ED | 30/12/2022 | 90 | DEY ENTERPRISE | 23.33 | 0 | 0
515 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002502/2023-2024 | 139/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.43 | 5
516 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003308/2023-2024 | 139_/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.15 | 0
517 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. CAR NO.- WB-04G-2822 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003411/2023-2024 | 139_AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.14 | 0
518 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 60
519 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 29.32 | 40
520 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-I GP of Balagrah Block. |  |  | ORD/000920/2023-2024 | 240/CH | 12/03/2024 | 30 | MAA BUNAMATA ENTERPRISE | 4.98 | 4.83 | 70
521 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-II GP of Balagrah Block. |  |  | ORD/000921/2023-2024 | 241/CH | 12/03/2024 | 30 | ASHA ENTERPRISE | 4.98 | 4.77 | 50
522 | Electrical |  | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814868 Application no- 5004498035 |  |  | BILL/02601/2024-2025 | 630 | 18/12/2024 | 0 | WBSEDCL | 8.62 | 0 | 0
523 | Electrical |  | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814816 Application no- 5004497772 |  |  | BILL/02602/2024-2025 | 629 | 18/12/2024 | 0 | WBSEDCL | 8.47 | 0 | 0
524 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001214/2023-2024 | 4492/ED | 23/11/2023 | 710 | MAA TARA CONSTRUCTION | 21.47 | 0 | 50
525 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000580/2023-2024 | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0
526 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000616/2023-2024 | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 14.22 | 75
527 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Rameswarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001919/2024-2025 | 270/CH | 20/02/2025 | 10 | SAMRAT CONSTRUCTION | 2.68 | 0 | 0
528 | Electrical |  | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18971), Reference Id- 503733787 Application no- 5004386169 |  |  | BILL/01969/2024-2025 | 479 | 01/10/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
529 | Electrical |  | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. (SM/18971), Reference Id- 503726898 Application no- 5004370950 |  |  | BILL/01970/2024-2025 | 481 | 01/10/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
530 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001244/2023-2024 | 4494/ED | 23/11/2023 | 90 | R.K.ENTERPRISE | 21.48 | 0 | 0
531 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000580/2023-2024 | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0
532 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000616/2023-2024 | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 13.45 | 75
533 | Electrical |  | Quotation for new service connection for source Augmentation of KAMARPARA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18972), Reference Id-503777915 Application no- 5004449275 |  |  | BILL/02271/2024-2025 | BP-24-25-585 | 19/11/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
534 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001245/2023-2024 | 4495/ED | 23/11/2023 | 90 | PADMA ENGINEERING CO. | 21.49 | 0 | 0
535 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 40
536 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0
537 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001879/2024-2025 | 243/CH | 19/02/2025 | 10 | SAMRAT CONSTRUCTION | 4.08 | 0 | 0
538 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001912/2024-2025 | 263/CH | 20/02/2025 | 10 | SAMRAT CONSTRUCTION | 2.75 | 0 | 0
539 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001258/2023-2024 | 4504/ED | 23/11/2023 | 90 | GOENKA ENTERPRISE | 10.75 | 0 | 0
540 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 340.16 | 15
541 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000112/2023-2024 | 1264/7/HUG | 03/05/2023 | 0 | Resource Division | 18.31 | 0 | 0
542 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000232/2023-2024 | 1386/11/Hug | 15/05/2023 | 0 | Resource Division | 13.46 | 0 | 0
543 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04133/2023-2024 | 386 | 01/11/2023 | 0 | WBSEDCL | 5.36 | 0 | 0
544 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04201/2023-2024 | 402 | 09/11/2023 | 0 | WBSEDCL | 7.87 | 0 | 0
545 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000091/2022-2023 | 3473/ED | 30/12/2022 | 901 | CINZANO | 20.51 | 0 | 90
546 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 20
547 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 27.84 | 50
548 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Malipara village under Polba Dadpur Block, Manipur village of Polba Dadpur Block and Prasadpur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000991/2023-2024 | 265/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
549 | Electrical |  | Quotation for new service connection at Goswamimalipara (Aug.)[SM/18953] W/S Sch., T/W No. - III, Block - Polba-dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 503619160, dt. - 25-06-2024, Application No. - 5004116875. |  |  | BILL/01141/2024-2025 | 263 | 03/07/2024 | 0 | WBSEDCL | 9.13 | 0 | 0
550 | Electrical |  | Quotation for new service connection at Goswamimalipara (Aug.) [SM/18953] W/s Sch., T/W No. - IV, Village & P. O. - Shenet, Dt. - Hooghly under Dadpur CCC, WBSEDCL, Ref. Id. - 503669411, Dt. - 11-07-2024, Application No. - 5004243696 |  |  | BILL/01190/2024-2025 | 311 | 22/07/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
551 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001277/2023-2024 | 4517/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 90
552 | Hooghly Division | Arambug Sub-Division | Providing 100 nos Functional Household Tap Connection (FHTC) within Dihibagnan, Para Bagnan & Bhabanipur Village of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000012/2022-2023 | 713/Hug | 07/04/2022 | 25 | BAKSHI ENTERPRISE | 11 | 6.39 | 0
553 | Hooghly Division | Arambug Sub-Division | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000230/2021-2022 | 1915/Hug | 27/10/2021 | 40 | M/S PRADYUT KUMAR HAZRA | 40.43 | 35.11 | 0
554 | Hooghly Division | Arambug Sub-Division | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | Assistant Engineer | Junior Engineer (Civill) | ORD/000311/2021-2022 | 2230/Hug | 15/12/2021 | 30 | M/S T.K.B. CONSTRUCTION | 25.6 | 9.48 | 0
555 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000124/2021-2022 | 2196/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
556 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000013/2021-2022 |  | 12/04/2021 | 0 | M/S PRADYUT KUMAR HAZRA | 75.95 | 0 | 0
557 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002583/2020-2021 |  | 19/03/2021 | 0 | M/S PRADYUT KUMAR HAZRA | 65 | 0 | 0
558 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for RAGHUBATI Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000246/2024-2025 | 3466/HUG | 04/10/2024 | 60 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 0 | 0
559 | Hooghly Division | Arambug Sub-Division | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000300/2023-2024 | 2363/HUG | 08/08/2023 | 809 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 434.8 | 50
560 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000445/2023-2024 | 3057/27/Hug | 11/10/2023 | 0 | Resource Division | 10.81 | 0 | 0
561 | Electrical | Arambug Sub-Division | Additional Quotation of New Service Connection for Raghubati w/S Scheme,PH No-I, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18672) Application No-100000123537 Reference Id-860318457 | Assistant Engineer | Junior Engineer (Civill) | BILL/02307/2024-2025 | 606 | 05/12/2024 | 0 | WBSEDCL | 0.96 | 0 | 0
562 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Raghubati W/S. Sch.TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04150/2023-2024 | 392 | 03/11/2023 | 0 | WBSEDCL | 5.08 | 0 | 0
563 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Raghubati W/S. Sch | Assistant Engineer | Junior Engineer (Civill) | BILL/06037/2023-2024 | 737 | 07/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
564 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raghubati water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000844/2023-2024 | 3412/ED | 10/08/2023 | 541 | M/S NABIN GOPAL SENGUPTA | 20.36 | 5.21 | 50
565 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 26.32 | 60
566 | Hooghly Division |  | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000716/2023-2024 | 3352/HUG | 17/11/2023 | 778 | A.R. CONSTRUCTION | 35.75 | 0 | 20
567 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001290/2023-2024 | 4522/ED | 23/11/2023 | 90 | TRIDENT ENTERPRISE | 22.03 | 0 | 0
568 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 60
569 | Hooghly Division |  | Connection of T.W. No. III with distribution, Construction of 5.4 x 3.65 m Pump Room with Sanitary arrangement and Boundary Wall at PABA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. |  |  | ORD/000649/2023-2024 | 3482/HUG | 29/11/2023 | 60 | DHIRENDRA ENGINEERING & CONSTRUCTION | 23.74 | 17.73 | 100
570 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paba water supply scheme, T.W. No. III, Block: Goghat-II, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002575/2022-2023 | 2046/ED | 01/12/2022 | 90 | M/S G P ENTERPRISE | 11.11 | 10.8 | 30
571 | Hooghly Division |  | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000597/2023-2024 | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 32
572 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000646/2023-2024 | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 0 | 20
573 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARADITYA Piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001292/2023-2024 | 4524/ED | 23/11/2023 | 90 | WIZARDTECH SOLUTION | 21.49 | 0 | 0
574 | Hooghly Division |  | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAKSA Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.HE Dte. within Chanditala-II Block. |  |  | ORD/000150/2023-2024 | 1536/HUG | 24/05/2023 | 30 | GHOSH ENTERPRISE | 11.79 | 9.45 | 100
575 | Electrical |  | Additional quotation for Baksa w/s scheme against application no.- 5003987334 Ref ID: 860295228 |  |  | BILL/06497/2023-2024 | 13 | 04/04/2024 | 0 | WBSEDCL | 0.93 | 0 | 0
576 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baksa water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001985/2023-2024 | 117/ED | 15/01/2024 | 90 | M.S.C. ENTERPRISE | 10.24 | 9.94 | 80
577 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.65 m X 3.60 m Switch Room with Sanitary & Water Supply & Sanitation Arrangement at 4th T/W Site of Kulihanda W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000117/2022-2023 | 399/CH | 06/05/2022 | 35 | SADHUKHAN ENTERPRISE | 4.99 | 4.2 | 0
578 | Hooghly Division | Chinsuria Sub-Division | Providing 800 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000208/2021-2022 | 1677/hug | 13/09/2021 | 30 | EVEREST CONSULTANT SERVICES | 35.63 | 33.42 | 0
579 | Hooghly Division | Chinsuria Sub-Division | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda & AMODGHATA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000355/2021-2022 | 116/Hug | 19/01/2022 | 20 | R.K. TRADERS | 25.16 | 24.33 | 0
580 | Hooghly Division | Chinsuria Sub-Division | Connection of 4th T.W. with existing distribution pipe line at Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000517/2023-2024 | 824/CH | 31/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.96 | 0.96 | 80
581 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Different area for providing FHTC in Kulihanda Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000837/2023-2024 | 215/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.94 | 45
582 | Hooghly Division | Chinsuria Sub-Division | Laying of HDPE Pipeline for providing FHTC at the left out portions of at Kulihanda Piped Water Supply Scheme under Chinsurah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000838/2023-2024 | 216/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.98 | 45
583 | Hooghly Division | Chinsuria Sub-Division | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Kulihanda W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000893/2023-2024 | 817/HUG | 11/03/2024 | 30 | M/S. R. M. CONSTRUCTION | 19.52 | 12.49 | 100
584 | Hooghly Division | Chinsuria Sub-Division | Providing 1969 nos F.H.T.C. in Kulihanda (CT) Village of Kulihanda and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000951/2022-2023 | 457CH | 01/10/2022 | 50 | MLG CONSTRUCTION | 102.5 | 0 | 0
585 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000517/2021-2022 |  | 23/07/2021 | 0 | MS PRADIP KUMAR PAL | 10.4 | 0 | 0
586 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000537/2021-2022 |  | 23/07/2021 | 0 | M/S S.G. CONSTRUCTION | 23.14 | 0 | 0
587 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000853/2021-2022 |  | 21/09/2021 | 0 | MS PRADIP KUMAR PAL | 14.04 | 0 | 0
588 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000857/2021-2022 |  | 21/09/2021 | 0 | M/S S.G. CONSTRUCTION | 23.77 | 0 | 0
589 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000146/2022-2023 | 135/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 5 | 4.78 | 0
590 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000147/2022-2023 | 134/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 3.92 | 3.74 | 0
591 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR construction of tube well at kulihanda pwss, polba dadpur block, hooghly district under cdd, phe dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000148/2022-2023 | 136/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 4.99 | 2.73 | 0
592 | Central Drilling | Chinsuria Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0 | 0
593 | Hooghly Division | Chinsuria Sub-Division | Providing 823 nos F.H.T.C. in the Rudrashanda,Mandaran & Sankpur village of Mandaran and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000104/2020-2021 | 1691/Hug | 17/12/2020 | 182 | MAA TARA CONSTRUCTION | 38.75 | 0 | 0
594 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000094/2021-2022 | 2097/34/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
595 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000591/2021-2022 |  | 17/08/2021 | 0 | MAA TARA CONSTRUCTION | 12.88 | 0 | 0
596 | Hooghly Division | Chinsuria Sub-Division | .... | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000827/2021-2022 | 844334 | 19/08/2021 | 0 | MOUMITA SINGHA BHATTACHATYA | 0.48 | 0 | 0
597 | Hooghly Division | Chinsuria Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
598 | Hooghly Division | Chinsuria Sub-Division | Rising Main in between 2nd T.W to O.H.R Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000116/2022-2023 | 398/CH | 06/05/2022 | 35 | M/S S.G. CONSTRUCTION | 2.69 | 0 | 100
599 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000159/2022-2023 | 1511/HUG | 22/07/2022 | 15 | R CONSTRUCTION | 19.73 | 17.48 | 100
600 | Hooghly Division | Chinsuria Sub-Division | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000354/2021-2022 | 115/Hug | 19/01/2022 | 30 | MERCANTILE HALL | 43.98 | 44.14 | 100
601 | Hooghly Division | Chinsuria Sub-Division | Rising Main Pipe line in between 3rd T.W By to pass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000481/2021-2022 | 111/CH | 10/02/2022 | 25 | M/S S.G. CONSTRUCTION | 4.18 | 0 | 0
602 | Hooghly Division | Chinsuria Sub-Division | Rising Main in between 2nd T.W to OHR Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000679/2022-2023 | 398/CH | 06/05/2022 | 35 | M/S S.G. CONSTRUCTION | 2.69 | 2.66 | 100
603 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000003/2021-2022 |  | 06/04/2021 | 0 | M/S BISWAS CONSTRUCTION | 7.43 | 0 | 0
604 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000021/2021-2022 |  | 12/04/2021 | 0 | GOBINDA MAITY | 3.29 | 0 | 0
605 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002291/2020-2021 |  | 15/03/2021 | 0 | GOBINDA MAITY | 16.4 | 0 | 0
606 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002539/2020-2021 |  | 19/03/2021 | 0 | M/S BISWAS CONSTRUCTION | 12 | 0 | 0
607 | Hooghly Division | Chinsuria Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
608 | Hooghly Division | Chinsuria Sub-Division | Making Interconnection from newly bored tube well to existing distribution system at Dwarbasini under Dwarbasini Water Supply Scheme Under Chinsurah Subdivision under Hooghly division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000521/2023-2024 | 819/CH | 31/08/2023 | 15 | JOY GURU ENTERPRISE | 0.85 | 0.86 | 95
609 | Hooghly Division | Chinsuria Sub-Division | Providing1663 nos F.H.T.C. in Bhuinpara, Sachitara,Kantagar & Prasadpur Village of Ayma Nababpur and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000613/2021-2022 | 932/HUG | 06/05/2021 | 40 | JAL PRAVAHIKA PVT. LTD | 13.14 | 13.14 | 100
610 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000091/2021-2022 | 2097/31/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
611 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001034/2021-2022 |  | 30/09/2021 | 0 | JAL PRAVAHIKA PVT. LTD | 32.84 | 0 | 0
612 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Western zone of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000208/2024-2025 | 553/SER | 19/09/2024 | 7 | TOTON MONDAL | 4.97 | 4.39 | 98
613 | Hooghly Division | Srirampur Sub-Division | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000295/2021-2022 | 2206/Hug | 14/12/2021 | 20 | ARUN SEAL AND CO. | 13.6 | 13.66 | 100
614 | Hooghly Division | Srirampur Sub-Division | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of RADHABALLAVPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000313/2021-2022 | 2232/Hug | 15/12/2021 | 20 | DREAM INFRASTRUCTURE | 4.92 | 4.91 | 100
615 | Hooghly Division | Srirampur Sub-Division | Providing additional 800 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000358/2020-2021 | 470/Hug | 26/02/2021 | 30 | M/S SHIVAM UDYOG | 29.36 | 3.42 | 0
616 | Hooghly Division | Srirampur Sub-Division | Laying CI/DI pipes & specials for connection with Main pipe line & T.W. No.-3 and interconnection including allied work with laying distribution system for Development of Morhal Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 08 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000376/2022-2023 | 2089/Hug | 21/09/2022 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 14.32 | 14.32 | 99
617 | Hooghly Division | Srirampur Sub-Division | Construction of 3.6 m. X 3.0 m. Switch Room without sanitary and water supply arrangement at 3rd tube well site of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division, P. H. E. Directorate. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000391/2021-2022 | 297/SER | 21/02/2022 | 30 | BAKSHI ENTERPRISE | 3.32 | 1.89 | 0
618 | Hooghly Division | Srirampur Sub-Division | Providing Add. 90 nos FHTC within the Morhal PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000505/2021-2022 | 164/Ser | 26/10/2021 | 30 | ARUN SEAL AND CO. | 3.78 | 3.78 | 0
619 | Hooghly Division | Srirampur Sub-Division | Providing additional 20 nos FHTC in Morhal PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000508/2021-2022 | 165/SER. | 26/10/2021 | 35 | TOTON MONDAL | 1.35 | 1.35 | 0
620 | Hooghly Division | Srirampur Sub-Division | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from House of Harimohan Shaw to Jora Culvert under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000738/2023-2024 | 308/SER | 29/12/2023 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 1 | 100
621 | Hooghly Division | Srirampur Sub-Division | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from Shaw para Kali Mandir to House of Harimohan Shaw under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000739/2023-2024 | 309/SER | 29/12/2023 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 1 | 100
622 | Hooghly Division | Srirampur Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MORHAL Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000755/2023-2024 | 390/HUG | 08/02/2024 | 60 | BANSBERIA CONSTRUCTION CO. | 31.57 | 0 | 75
623 | Hooghly Division | Srirampur Sub-Division | Repairing of Switch Room & Boundary Wall at existing TW sites, and Construction of Boundary wall at 3rdT.W Site of MORHAL Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000904/2023-2024 | 827/HUG | 11/03/2024 | 30 | BAKSHI ENTERPRISE | 13.28 | 5.92 | 60
624 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kotalpur PWSS 2. Morhal PWSS 3. Borhal PWSS 4. Antpur PWSS 5. Rajbalhat PWSS 6. Gopalpur-I PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000943/2023-2024 | 113/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
625 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 371.19 | 30
626 | Hooghly Division | Chinsuria Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-III) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002233/2024-2025 | 407/CH | 10/03/2025 | 15 | TECHVISION | 4.2 | 0 | 0
627 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000119/2023-2024 | 1264/14/HUG | 03/05/2023 | 0 | Resource Division | 42.75 | 0 | 0
628 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000267/2023-2024 | 1386/46/Hug | 15/05/2023 | 0 | Resource Division | 19.93 | 0 | 0
629 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000523/2023-2024 | 3059/37/Hug | 11/10/2023 | 0 | Resource Division | 19.93 | 0 | 0
630 | Electrical | Chinsuria Sub-Division | Lokabati PH__II Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05987/2023-2024 | 724 | 05/02/2024 | 0 | WBSEDCL | 17.53 | 0 | 0
631 | Electrical | Chinsuria Sub-Division | Lokabati PH__I Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05988/2023-2024 | 725 | 05/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
632 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Lokabati water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2022-2023 | 3469/ED | 30/12/2022 | 945 | INDRANI ENTERPRISE | 22.4 | 0 | 75
633 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 15.99 | 100
634 | Hooghly Division | Chandannagar Sub-Division | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in BASUBATI Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000747/2022-2023 | 683/Hug | 10/03/2023 | 935 | MINTU CHAKRABORTY | 618.81 | 221.78 | 70
635 | Hooghly Division | Chandannagar Sub-Division | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.16 | 100
636 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Basubati PWSS, Purushottampur PWSS, Nawpara PWSS, Bighati Z-II PWSS, Shibrambati Z-I PWSS, Sinhal Pathan PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000975/2023-2024 | 303/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
637 | Hooghly Division | Chandannagar Sub-Division | Sinking of 1no. additional tubewell with Construction of switch-room, Tubewell connection & Other works at BASUBATI Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002477/2024-2025 | 670/HUG | 12/03/2025 | 90 | MINTU CHAKRABORTY | 92.31 | 0 | 0
638 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000130/2022-2023 | 2471/3/Hug | 18/11/2022 | 0 | Resource Division | 19.58 | 0 | 0
639 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000158/2022-2023 | 01/11/Hug | 02/01/2023 | 0 | Resource Division | 19.58 | 0 | 0
640 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000191/2022-2023 | 109/1/Hug | 10/01/2023 | 0 | Resource Division | 55.09 | 0 | 0
641 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000206/2023-2024 | 1383/9/Hug | 15/05/2023 | 0 | Resource Division | 19.93 | 0 | 0
642 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Basubati W/S Sch, TW-I (Head Work site), Dist. Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01916/2023-2024 | 90 | 13/07/2023 | 0 | WBSEDCL | 3.85 | 0 | 0
643 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Basubati W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04512/2023-2024 | 553 | 21/12/2023 | 0 | WBSEDCL | 2.59 | 0 | 0
644 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000130/2022-2023 | 3484/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 23.01 | 22.71 | 90
645 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No. III, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000873/2023-2024 | 3446/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 11.5 | 0 | 0
646 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 212.01 | 30
647 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000125/2023-2024 | 1264/20/HUG | 03/05/2023 | 0 | Resource Division | 16.64 | 0 | 0
648 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000240/2023-2024 | 1386/19/Hug | 15/05/2023 | 0 | Resource Division | 12.09 | 0 | 0
649 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000512/2023-2024 | 3059/11/Hug | 11/10/2023 | 0 | Resource Division | 3.18 | 0 | 0
650 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05129/2023-2024 | 693 | 22/01/2024 | 0 | WBSEDCL | 11.8 | 0 | 0
651 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05131/2023-2024 | 694 | 22/01/2024 | 0 | WBSEDCL | 5.69 | 0 | 0
652 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Durgapur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000146/2022-2023 | 3489/ED | 30/12/2022 | 90 | M/S CHANDIMATA ELECTRICALS | 20.38 | 11.23 | 35
653 | Hooghly Division | Howrah Mechanical Sub-Division | Supply and delivery of 300 mm dia UPVC pipe (CD) at Bhagabatipur Water Supply Scheme under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000382/2023-2024 | 615/Chan | 21/08/2023 | 7 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 0.89 | 0 | 0
654 | Hooghly Division | Howrah Mechanical Sub-Division | Laying Distribution System, Laying D.I Pipes & Specials for Rising Main Pipe Line, Construction of 1No 3.6M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at T.W Site including providing FHTC in BHAGABATIPUR Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000418/2022-2023 | 2280/Hug | 19/10/2022 | 45 | BABUSONA CONSTRUCTION | 46.12 | 6.5 | 55
655 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BHAGABATIPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000769/2022-2023 | 752/HUG | 15/03/2023 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 100
656 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000165/2022-2023 | 79/1/Hug | 06/01/2023 | 0 | Resource Division | 59.68 | 0 | 0
657 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000198/2023-2024 | 1383/1/Hug | 15/05/2023 | 0 | Resource Division | 1.11 | 0 | 0
658 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000199/2022-2023 | 109/ 13/Hug | 10/01/2023 | 0 | Resource Division | 1.75 | 0 | 0
659 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection of Bhagabatipur W/s Scheme, PH No-I Dist-Hooghly under Electrical Division ,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02003/2023-2024 | 103 | 19/07/2023 | 0 | WBSEDCL | 2.6 | 0 | 0
660 | Electrical | Howrah Mechanical Sub-Division | Additional Quotation of New Service Connection for Bhagabatipur w/s Scheme,Tw no-I,Block-Haripal,Dist-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03884/2023-2024 | 296 | 21/09/2023 | 0 | WBSEDCL | 0.48 | 0 | 0
661 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Bhagabatipur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/06152/2023-2024 | 793 | 22/02/2024 | 0 | WBSEDCL | 12.75 | 0 | 0
662 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000077/2022-2023 | 3459/ED | 30/12/2022 | 90 | NITESH MANAGEMENT | 10.16 | 10.15 | 40
663 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000354/2023-2024 | 2446/HUG | 12/08/2023 | 60 | R.K.CONSTRUCTION | 40.9 | 12.1 | 50
664 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Bhanjipur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000410/2022-2023 | 512/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.78 | 4.78 | 0
665 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach Road at BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000506/2023-2024 | 2904/HUG | 21/09/2023 | 30 | M/S. NANDY ENTERPRISE | 8.83 | 8.81 | 100
666 | Hooghly Division | Chandannagar Sub-Division | BHANJIPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000607/2022-2023 | 2899/HUG | 22/12/2022 | 180 | M/S. NANDY ENTERPRISE | 457.97 | 240.5 | 60
667 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of BHANJIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000659/2022-2023 | 156/HUG | 16/01/2023 | 45 | SURAJIT SINGHA RAY | 28.4 | 27.33 | 100
668 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of BHANJIPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000711/2022-2023 | 448/HUG | 16/02/2023 | 60 | AMBIAN INFRASTRUTTURE | 12.25 | 12.25 | 100
669 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Gouribati PWSS, Bhanjipur PWSS, Shibrambati zone-II PWSS, Aymachapsara PWSS, Balarambati PWSS, Chandanpur PWSS). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000974/2023-2024 | 310/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
670 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000207/2023-2024 | 1383/10/Hug | 15/05/2023 | 0 | Resource Division | 15.6 | 0 | 0
671 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000218/2022-2023 | 109/ 23/Hug | 10/01/2023 | 0 | Resource Division | 23.69 | 0 | 0
672 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000367/2023-2024 | 3005/5/Hug | 05/10/2023 | 0 | Resource Division | 19.24 | 0 | 0
673 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme, PH No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03686/2023-2024 | 227 | 01/09/2023 | 0 | WBSEDCL | 4.93 | 0 | 0
674 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03689/2023-2024 | 228 | 01/09/2023 | 0 | WBSEDCL | 4.65 | 0 | 0
675 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bhanjipur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04415/2023-2024 | 493 | 07/12/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
676 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhanjipur water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000078/2022-2023 | 3460/ED | 30/12/2022 | 90 | M.S. ENTERPRISE | 22.27 | 22.24 | 100
677 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 32.51 | 100
678 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of Harat PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000409/2022-2023 | 511/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.21 | 4.21 | 0
679 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in HARAT Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000618/2022-2023 | 42/HUG | 04/01/2023 | 300 | TITAS CONSTRUCTION | 450.61 | 161.88 | 20
680 | Hooghly Division | Howrah Mechanical Sub-Division | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Rambati 2nd T/W site & Harat 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000937/2023-2024 | 282/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100
681 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000200/2022-2023 | 109/ 15/Hug | 10/01/2023 | 0 | Resource Division | 31.12 | 0 | 0
682 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000201/2023-2024 | 1383/5/Hug | 15/05/2023 | 0 | Resource Division | 11.78 | 0 | 0
683 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000399/2023-2024 | 3058/1/Hug | 11/10/2023 | 0 | Resource Division | 116.86 | 0 | 0
684 | Electrical | Howrah Mechanical Sub-Division | New Service Connection at Harat Piped W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02741/2023-2024 | 170 | 09/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
685 | Electrical | Howrah Mechanical Sub-Division | NEW SERVICE CONNECTION | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02746/2023-2024 |  | 08/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
686 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Harat Water Supply Scheme,TW No-II,Block-Haripal, Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03621/2023-2024 | 224 | 28/08/2023 | 0 | WBSEDCL | 5.57 | 0 | 0
687 | Electrical | Howrah Mechanical Sub-Division | Additional Quotation Of New Service Connection for Harat w/s Scheme,PH No-I,Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04079/2023-2024 | 349 | 11/10/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
688 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Harat w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/11290) Application No-5003979859 Reference Id-503541273 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/06474/2023-2024 | 902 | 19/03/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
689 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000083/2022-2023 | 3465/ED | 30/12/2022 | 90 | M/S A.K BANERJEE | 21.49 | 19.62 | 30
690 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. III, Block: Haripal, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002480/2023-2024 | 340/ED | 21/02/2024 | 90 | MOITRA ENGINEERING CO. | 10.74 | 10.44 | 10
691 | Hooghly Division | Chinsuria Sub-Division | HIRE CHARGES BILL EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00041/2022-2023 | BP-2022-23-405 | 15/12/2022 | 0 | PRADIP KUMAR ADHYA | 2.07 | 0 | 0
692 | Hooghly Division | Chinsuria Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000081/2024-2025 | 695/CH | 09/08/2024 | 15 | TECHVISION | 4.2 | 4.2 | 90
693 | Hooghly Division | Chinsuria Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underDhaniakhali Block (Part-II) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000082/2024-2025 | 696/CH | 09/08/2024 | 15 | TECHVISION | 4.2 | 4.2 | 100
694 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 No. switch-room at Proposed TW site of DHANIAKHALI ZONE-II Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000088/2023-2024 | 1342/HUG | 11/05/2023 | 30 | SOMNATH ADHYA | 6.15 | 6.15 | 100
695 | Hooghly Division | Chinsuria Sub-Division | Augmentation of DHANIAKHALI (ZONE-I) Water Supply Scheme with LDS & FHTC At Dhaniakhali Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000203/2022-2023 | 1657 | 16/08/2022 | 50 | SUJATA CONSTRUCTION | 177.27 | 173.43 | 100
696 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of DHANIAKHALI ZONE-II Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000261/2023-2024 | 2225/HUG | 31/07/2023 | 810 | PRADIP KUMAR ADHYA | 409.01 | 158.52 | 30
697 | Hooghly Division | Chinsuria Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000269/2024-2025 | 928/CH | 05/11/2024 | 5 | TOTON MONDAL | 4.85 | 0 | 90
698 | Hooghly Division | Chinsuria Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000270/2024-2025 | 929/CH | 05/11/2024 | 5 | M/S BIMAL DAS AND CO. | 2.82 | 2.16 | 90
699 | Hooghly Division | Chinsuria Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of 182 cum capacity of Dhaniakhali Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 01 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000283/2022-2023 | 1904/HUG | 05/09/2022 | 30 | ROY ENTERPRISE | 7.45 | 7.44 | 100
700 | Hooghly Division | Chinsuria Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at DHANIAKHALI (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL - 05 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000341/2022-2023 | 1955/HUG | 07/09/2022 | 45 | OSMAN SEKH | 22.63 | 21.96 | 0
701 | Hooghly Division | Chinsuria Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SOMRA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000490/2021-2022 | 616/Hug | 31/03/2022 | 122 | S.K. GHOSH | 3.41 | 0 | 0
702 | Hooghly Division | Chinsuria Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at POLBA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000491/2021-2022 | 619/Hug | 31/03/2022 | 122 | S.K. GHOSH | 3.41 | 0 | 0
703 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Dhaniakhali Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000541/2021-2022 | 131/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.82 | 4.81 | 0
704 | Hooghly Division | Chinsuria Sub-Division | Replacing of Sluice Valve and allied works at Head Work Site of Dhaniakhali Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000692/2023-2024 | 1114/CH | 15/12/2023 | 7 | M/S BIMAL DAS AND CO. | 0.95 | 0.85 | 100
705 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of DHANIAKHALI ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000749/2022-2023 | 650/Hug | 10/03/2023 | 60 | SOME ENTERPRISE | 6.08 | 6.08 | 95
706 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000005/2023-2024 | 1105/1/Hug | 17/04/2023 | 0 | Resource Division | 60.84 | 0 | 0
707 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000014/2022-2023 | 1123/2/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0
708 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000127/2022-2023 | 2211/1/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
709 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000280/2023-2024 | 1386/53/Hug | 15/05/2023 | 0 | Resource Division | 15.68 | 0 | 0
710 | Hooghly Division | Chinsuria Sub-Division | PAYMENT TO WBSEDCL | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/001350/2022-2023 |  | 11/11/2022 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0
711 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at DhaniakhaliZ-II, PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00805/2023-2024 | 57 | 02/06/2023 | 0 | WBSEDCL | 5.86 | 0 | 0
712 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dhaniakhali W/S. Sch. W/S. Sch. Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02592/2023-2024 | 155 | 03/08/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
713 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 17.21 | 59
714 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) in Chiladangi PWSS, Block Pursurah under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2023-2024 | 2099/HUG | 19/07/2023 | 45 | ARATI ENGINEERING | 94.38 | 0 | 0
715 | Hooghly Division | Arambug Sub-Division | Laying Distribution System for ANANDAPUR (Zone-I) Piped Water Supply Scheme including Repairing of existing Switch rooms, Boundary walls (Zone-I & Zone-II) at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000231/2022-2023 | 1780/HUG | 30/08/2022 | 45 | TAPAS ADHYA | 76.59 | 0 | 0
716 | Hooghly Division | Arambug Sub-Division | Laying Distribution System of ANANDAPUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6 M X 3.0 M Switch Rooms & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO-02 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000232/2022-2023 | 1781/HUG | 30/08/2022 | 45 | SARKAR CONSTRUCTION | 69.19 | 36.46 | 25
717 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Anandapur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000238/2022-2023 | 333/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.35 | 0
718 | Hooghly Division | Arambug Sub-Division | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000395/2022-2023 | 123/HUG | 26/09/2022 | 25 | M/S ROY CONSTRUCTION AND CO. | 15.22 | 15.22 | 100
719 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.28 | 100
720 | Hooghly Division | Arambug Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at ANANDAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000460/2022-2023 | 2511/HUG | 22/11/2022 | 45 | MS D.PALIT AND CO. | 27.59 | 20.07 | 0
721 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANANDAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000487/2024-2025 | 4151/HUG | 26/12/2024 | 90 | M/S RAJKUMAR KHAN | 17.7 | 0 | 0
722 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000026/2023-2024 | 1234/7/Hug | 28/04/2023 | 0 | Resource Division | 0.32 | 0 | 0
723 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000050/2022-2023 | 1590/5/Hug | 03/08/2022 | 0 | Resource Division | 15.4 | 0 | 0
724 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000098/2022-2023 | 1773/32/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
725 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000117/2022-2023 | 2209/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
726 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000147/2023-2024 | 1385/18/Hug | 15/05/2023 | 0 | Resource Division | 0.49 | 0 | 0
727 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000259/2022-2023 | 127/2/Hug | 13/01/2023 | 0 | Resource Division | 9.57 | 0 | 0
728 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Anandapur W/S. Sch. TW-III & IV, Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01816/2022-2023 | 205 | 21/03/2023 | 0 | WBSEDCL | 1.46 | 0 | 0
729 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anandapur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000048/2023-2024 | 1734/ED | 19/04/2023 | 90 | P.K. ENGINEERING | 21.49 | 20.91 | 70
730 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of SOALUK Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000125/2023-2024 | 1459/HUG | 18/05/2023 | 30 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 6.21 | 0 | 0
731 | Hooghly Division | Arambug Sub-Division | Laying Distribution System with providing Functional Household Tap Connection of SOALUK Piped Water Supply Scheme within Soaluk (North) Mouza including Repairing of existing Switch Rooms at PURSURAH Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 05 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000234/2022-2023 | 1783/HUG | 30/08/2022 | 30 | R.K. TRADERS | 52.81 | 52.81 | 0
732 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Soaluk Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000242/2022-2023 | 339/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.74 | 3.68 | 0
733 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir ,Construction of Boundary Wall Of Head Work site at SOALUK Piped Water Supply Scheme under ARAMBAGH Sub¿Division of Hooghly Division P.HE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000361/2023-2024 | 2453/HUG | 12/08/2023 | 600 | P.K. GHOSH & CO. | 31.41 | 21.27 | 100
734 | Hooghly Division | Arambug Sub-Division | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000602/2022-2023 | 2888/HUG | 22/12/2022 | 90 | M/S CARE | 191.47 | 0 | 0
735 | Hooghly Division | Arambug Sub-Division | Functional Household Tap Connection (FHTC) under JJM in SOALUK PWSS, Block. PURSURAH under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000603/2022-2023 | 2889/HUG | 22/12/2022 | 60 | M/S CARE | 86.64 | 82.65 | 70
736 | Hooghly Division | Arambug Sub-Division | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of SOALUK W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000672/2022-2023 | 170/HUG | 16/01/2023 | 30 | GITA ENTERPRISE | 13.54 | 13.54 | 100
737 | Hooghly Division | Arambug Sub-Division | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000686/2022-2023 | 281/HUG | 01/02/2023 | 90 | M/S CARE | 191.47 | 145.99 | 70
738 | Hooghly Division | Arambug Sub-Division | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF SOALUK Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000713/2022-2023 | 450/HUG | 16/02/2023 | 45 | TANISA ENTERPRISE | 7.5 | 7.5 | 0
739 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000008/2023-2024 | 1106/2/HUG | 17/04/2023 | 0 | Resource Division | 14.48 | 0 | 0
740 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000108/2022-2023 | 1773/42/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0
741 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000180/2022-2023 | 79/26/Hug | 06/01/2023 | 0 | Resource Division | 17.86 | 0 | 0
742 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Soaluk T/W-IV W/S scheme under Electrical Division PHE Dte. (SM/11467) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01614/2024-2025 | 376 | 12/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
743 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Soaluk W/S. Sch. PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01873/2022-2023 | 208 | 22/03/2023 | 0 | WBSEDCL | 3 | 0 | 0
744 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Soaluk water supply scheme, T.W. No.- I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000114/2022-2023 | 668/ED | 02/02/2023 | 90 | M/S BIPUL BANERJEE | 10.96 | 10.91 | 100
745 | Electrical | Arambug Sub-Division | Replacement of some electrical devices, equipments and items, outdoor lighting, voltage corrector etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000316/2022-2023 | 492/HMSD | 02/03/2023 | 30 | RADHARANI ENTERPRISE | 2.99 | 2.99 | 100
746 | Electrical | Arambug Sub-Division | Replacement of some electrical devices and equipments like mcc cum pdb etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000318/2022-2023 | 494/HMSD | 02/03/2023 | 30 | N.S. TRADING | 4.21 | 4.21 | 0
747 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 35
748 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SOALUK W/S SCH, UNDER HOOGHLY DISTRICT CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000353/2022-2023 | 1559/CDD | 08/12/2022 | 30 | ASHUTOSH DAS & CO | 12.66 | 9.62 | 0
749 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Fului Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000589/2022-2023 | 2848/HUG | 16/12/2022 | 45 | TITAS CONSTRUCTION | 47.25 | 46.85 | 0
750 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Betra Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000590/2022-2023 | 2849/HUG | 16/12/2022 | 30 | KOUSIK MONDAL | 25.28 | 25.06 | 100
751 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Tilari, Dwaripara, Kakand Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000591/2022-2023 | 2850/HUG | 16/12/2022 | 30 | TANISA ENTERPRISE | 23.9 | 18.73 | 0
752 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Kayapat, Shyampur, Tilati, Chakran Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000592/2022-2023 | 2851/HUG | 16/12/2022 | 776 | I R CONSTRUCTION | 37.54 | 0 | 100
753 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Shyambazar Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000594/2022-2023 | 2853/HUG | 16/12/2022 | 45 | MS K.B CONSTRUCTION | 51.48 | 51.44 | 0
754 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Badanganj Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000611/2022-2023 | 2922/HUG | 27/12/2022 | 30 | MS K.B CONSTRUCTION | 30.75 | 30.69 | 0
755 | Hooghly Division | Arambug Sub-Division | Laying balance pipeline and other allied works at Badangnj and Fului village within Badanganj Zone - I PWSS under Arambagh Sub Division, PHE Dte. Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/002317/2024-2025 | 663/HUG | 11/03/2025 | 45 | TITAS CONSTRUCTION | 39.19 | 0 | 0
756 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000009/2023-2024 | 1106/3/HUG | 17/04/2023 | 0 | Resource Division | 15.88 | 0 | 0
757 | Hooghly Division | Chandannagar Sub-Division | Emergent requirement of rectification of damages caused to road under Hooghly Highway Division II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00499/2023-2024 | BP-2023-24-400 | 26/09/2023 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.04 | 0 | 0
758 | Hooghly Division | Chandannagar Sub-Division | Laying balance pipeline and other allied works at ATISARA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000028/2025-2026 | 1173/HUG | 02/05/2025 | 60 | MINTU CHAKRABORTY | 33.71 | 0 | 0
759 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 15.85 | 100
760 | Hooghly Division | Chandannagar Sub-Division | Sinking of1 No. Additional tube-well , Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for atisara Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000235/2024-2025 | 3470/HUG | 04/10/2024 | 60 | M/S SHIVAM UDYOG | 26.55 | 0 | 0
761 | Hooghly Division | Chandannagar Sub-Division | Construction of boundary wall with Gate & Internal Pathway at ATISARA 2nd pump hou se site under Singur Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000269/2025-2026 | 915/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0
762 | Hooghly Division | Chandannagar Sub-Division | Construction of road with plinth protection and land development at ATISARA 2nd pump house site under Singur block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000270/2025-2026 | 916/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0
763 | Hooghly Division | Chandannagar Sub-Division | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R , TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in ATISARA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000703/2022-2023 | 404/HUG | 13/02/2023 | 899 | MINTU CHAKRABORTY | 769.58 | 608.6 | 97
764 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach road at Atisara W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000757/2023-2024 | 450/HUG | 15/02/2024 | 324 | MINTU CHAKRABORTY | 36.19 | 0 | 2
765 | Hooghly Division | Chandannagar Sub-Division | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 10.89 | 100
766 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Purusatyampur H/W site & Atisara 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000936/2023-2024 | 281/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100
767 | Hooghly Division | Chandannagar Sub-Division | Approach road at Atisara 2nd Tubewell site under Atisara water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000955/2023-2024 | 293/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.94 | 0.94 | 100
768 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Atisara PWSS, Beraberi PWSS, Barakamplur PWSS, Diara PWSS, Kamarkundu PWSS, Nanda PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000970/2023-2024 | 299/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
769 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000129/2022-2023 | 2471/Hug | 18/11/2022 | 0 | Resource Division | 20.08 | 0 | 0
770 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000157/2022-2023 | 01/04/Hug | 02/01/2023 | 0 | Resource Division | 20.08 | 0 | 0
771 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000190/2022-2023 | 109/Hug | 10/01/2023 | 0 | Resource Division | 102.73 | 0 | 0
772 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000262/2022-2023 | 902/Hug | 27/03/2023 | 0 | Resource Division | 20.08 | 0 | 0
773 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000287/2023-2024 | 1383/33/Hug | 15/05/2023 | 0 | Resource Division | 20.08 | 0 | 0
774 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Atisara W/s Sch.,T/W - I, Block - Singur | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02063/2023-2024 | 115 | 20/07/2023 | 0 | WBSEDCL | 5.59 | 0 | 0
775 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Atisara W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04502/2023-2024 | 543 | 19/12/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
776 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Atisara water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000123/2022-2023 | 3479/ED | 30/12/2022 | 90 | R.N.S. TRADING | 23.26 | 11.28 | 49
777 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00086/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.6 | 0 | 0
778 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00221/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.55 | 0 | 0
779 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00418/2023-2024 | BP-2023-24-343 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.37 | 0 | 0
780 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000175/2023-2024 | 1385/46/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0
781 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
782 | Electrical | Arambug Sub-Division | Supply & Delivery of standby submersible pumping machinery for Kapsit & others W/S. Sch. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | ORD/001120/2021-2022 | 556/HMSD | 17/03/2022 | 90 | DITHI ENTERPRISE | 0.79 | 0 | 0
783 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00358/2023-2024 | BP-2023-24-298 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.41 | 0 | 0
784 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
785 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
786 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000218/2023-2024 | 1383/20/Hug | 15/05/2023 | 0 | Resource Division | 0.1 | 0 | 0
787 | Hooghly Division | Arambug Sub-Division | RADHABALLAVPUR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under KHANAKUL-I Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000779/2022-2023 | 833/HUG | 22/03/2023 | 832 | M/S S.G. CONSTRUCTION | 364.99 | 274.46 | 80
788 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000075/2023-2024 | 1234/37/Hug | 28/04/2023 | 0 | Resource Division | 11.79 | 0 | 0
789 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000152/2023-2024 | 1385/23/Hug | 15/05/2023 | 0 | Resource Division | 9.95 | 0 | 0
790 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000224/2022-2023 | 127/22/Hug | 13/01/2023 | 0 | Resource Division | 20.88 | 0 | 0
791 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000403/2023-2024 | 3057/49/Hug | 11/10/2023 | 0 | Resource Division | 9.95 | 0 | 0
792 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04365/2023-2024 | 459 | 01/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0
793 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04484/2023-2024 | 530 | 15/12/2023 | 0 | WBSEDCL | 13 | 0 | 0
794 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000180/2022-2023 | 773/ED | 09/02/2023 | 812 | KARTICK BAL | 20.62 | 15.73 | 30
795 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 254.64 | 15
796 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000114/2023-2024 | 1264/9/HUG | 03/05/2023 | 0 | Resource Division | 25.36 | 0 | 0
797 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000498/2023-2024 | 3059/17/Hug | 11/10/2023 | 0 | Resource Division | 11.41 | 0 | 0
798 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05980/2023-2024 | 732 | 05/02/2024 | 0 | WBSEDCL | 10.71 | 0 | 0
799 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-I,Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05981/2023-2024 | 731 | 05/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
800 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000282/2022-2023 | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 90
801 | Hooghly Division | Chinsuria Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHINSURAH SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00107/2023-2024 | BP-2023-24-106 | 02/06/2023 | 0 | PRASUN ENTERPRISE (PRASUN BISWAS) | 3.59 | 0 | 0
802 | Hooghly Division | Chinsuria Sub-Division | HARIPUR Piped Water Supply Scheme with Sinking of tube-well, Laying Distribution System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000700/2022-2023 | 363/HUG | 08/02/2023 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 183.69 | 173.36 | 95
803 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Rudrani PWSS 2. Chalua PWSS 3. Kamrai PWSS 4. Haripur PWSS 5. Kumrul PWSS 6. Kuchpala PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000775/2023-2024 | 141/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 30
804 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000164/2022-2023 | 1264/HUG | 03/05/2023 | 0 | Resource Division | 10.79 | 0 | 0
805 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000255/2023-2024 | 1386/34/Hug | 15/05/2023 | 0 | Resource Division | 4.92 | 0 | 0
806 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000535/2023-2024 | 3059/4/Hug | 11/10/2023 | 0 | Resource Division | 6.06 | 0 | 0
807 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Haripur W/S Sch.[SM/14122], Block - Polba-Dadpur, WBSEDCL, Ref. Id. - 503619164, Dt. - 25/04/2024, Application No. - 5004117110 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00475/2024-2025 | 135 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
808 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Haripur W/S Sch., T/W No. - II, Block - Polba-dadpur, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02328/2023-2024 | 147 | 26/07/2023 | 0 | WBSEDCL | 2.9 | 0 | 0
809 | Electrical | Chinsuria Sub-Division | Quotation for new service Connection at Haripur W/S Sch., T/W No. - I, Block - Polba-Dadpur, District - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03711/2023-2024 | 252 | 05/09/2023 | 0 | WBSEDCL | 5.79 | 0 | 0
810 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001215/2022-2023 | 3490 / ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 10.08 | 98
811 | Hooghly Division | Arambug Sub-Division | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000159/2023-2024 | 1602/HUG | 01/06/2023 | 1035 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 292.77 | 65
812 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KOTA Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000245/2024-2025 | 3465/HUG | 04/10/2024 | 120 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 14.79 | 50
813 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0
814 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000053/2023-2024 | 1234/24/Hug | 28/04/2023 | 0 | Resource Division | 74.78 | 0 | 0
815 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000416/2023-2024 | 3057/42/Hug | 11/10/2023 | 0 | Resource Division | 14.17 | 0 | 0
816 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06048/2023-2024 | 742 | 08/02/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
817 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06101/2023-2024 | 765 | 16/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
818 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kota water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000174/2022-2023 | 767/ED | 09/02/2023 | 919 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 21.06 | 20.33 | 40
819 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000160/2023-2024 | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 23.77 | 65
820 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, FHTC of SHANKHANAGAR CHAK BANSBERIA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000185/2023-2024 | 1772/HUG | 15/06/2023 | 45 | SURAJIT SINGHA RAY | 40.36 | 9.51 | 45
821 | Hooghly Division | Chinsuria Sub-Division | Emmergency Reparing work of Different Dia Ditribution Pipeline under Chakbasberia water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000525/2023-2024 | 822/CH | 31/08/2023 | 15 | MAA BUNAMATA ENTERPRISE | 0.63 | 0.63 | 95
822 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000355/2023-2024 | 3004/8/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0
823 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000545/2023-2024 | 3059/24/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0
824 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Sankhanagar Chakbansberia W/S Sch. , T/W No. - I(Aug.), Block - Chinsurah- Mogra, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04082/2023-2024 |  | 10/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0
825 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Sankhanagar Chak Bansberia W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04090/2023-2024 | 355 | 12/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0
826 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sankhanagar & Chakbasnberia water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000022/2023-2024 | 1699/ED | 18/04/2023 | 90 | EMCON | 11.4 | 11.4 | 80
827 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Sankhanagar Chawk Bansberia w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000315/2022-2023 | 491/HMSD | 02/03/2023 | 30 | S.B.ENTERPRISE | 2.49 | 2.49 | 1
828 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 10.46 | 90
829 | Hooghly Division | Chinsuria Sub-Division | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System & Repairing works of 1st Pump House, Boundary Wall & Go-down Room for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000025/2023-2024 | 1108/HUG | 17/04/2023 | 30 | GOBINDA MAITY | 16.16 | 16.16 | 100
830 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 12.88 | 65
831 | Hooghly Division | Chinsuria Sub-Division | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF GURAP WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001466/2024-2025 | 130/CH | 29/01/2025 | 10 | ARUN SEAL AND CO. | 4.83 | 0 | 0
832 | Hooghly Division | Chinsuria Sub-Division | Laying UPVC Pipeline for Proper Drainage of Washout / Overflow Water to Nearby Pond & Replacement Of Damaged Sluice Valve At Head Works Site For Gurap Piped Water Supply Scheme Under Dhaniakhali Block Of Chinsurah Sub-Division Under Hooghly Division, Phe Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002523/2024-2025 | 314/CH | 21/02/2025 | 15 | ARUN SEAL AND CO. | 3.13 | 0 | 0
833 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000357/2023-2024 | 3004/18/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0
834 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-4 Gurap pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04473/2023-2024 | 523 | 12/12/2023 | 0 | WBSEDCL | 10.02 | 0 | 0
835 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gurap water supply scheme, T.W. No. I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2023-2024 | 1633/ED | 11/04/2023 | 90 | DITHI ENTERPRISE | 11.4 | 11.38 | 70
836 | Hooghly Division | Arambug Sub-Division | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of Radhaballvpur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000269/2021-2022 | 2123/Hug | 01/12/2021 | 20 | SWASTIK ENTERPRISE | 8.08 | 8.15 | 100
837 | Hooghly Division | Arambug Sub-Division | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of RADHABALLAVPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000313/2021-2022 | 2232/Hug | 15/12/2021 | 20 | DREAM INFRASTRUCTURE | 4.92 | 0 | 100
838 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000533/2021-2022 |  | 23/07/2021 | 0 | DOULPHIN ENTERPRISE (RANJIT KHANRA) | 1.97 | 0 | 0
839 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
840 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002616/2020-2021 |  | 19/03/2021 | 0 | DOULPHIN ENTERPRISE (RANJIT KHANRA) | 42 | 0 | 0
841 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00299/2023-2024 | BP-2023-24-250 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.76 | 0 | 0
842 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000138/2023-2024 | 1385/9/Hug | 15/05/2023 | 0 | Resource Division | 0.49 | 0 | 0
843 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
844 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000307/2023-2024 | 1384/4/Hug | 15/05/2023 | 0 | Resource Division | 0.62 | 0 | 0
845 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Borhal W/S. Sch. PH-2 & 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00001/2023-2024 | 26 | 11/05/2023 | 0 | WBSEDCL | 11.8 | 0 | 0
846 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-II) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000983/2023-2024 | 1632/ED | 11/04/2023 | 90 | INDTECH ASSOCIATES. | 22.81 | 22.17 | 85
847 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II) PWSS (TW-I), JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000374/2022-2023 | 1774/CDD | 02/01/2023 | 30 | C.M. ENTERPRISE | 12.52 | 11.06 | 0
848 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL W/S SCH (ZONE-II) (TW-II), JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000383/2022-2023 | 1994/CDD | 07/02/2023 | 30 | CHANDA ENTERPRISE | 25.08 | 22.93 | 100
849 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II, TW-I) JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000412/2022-2023 | 2003/CDD | 09/02/2023 | 30 | UTTAM KUMAR CHATTERJEE | 12.54 | 10.75 | 0
850 | Hooghly Division | Arambug Sub-Division | Construction of Approach Road at Tirol Zone-I Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000231/2024-2025 | 3467/HUG | 04/10/2024 | 15 | MINTU CHAKRABORTY | 3.45 | 0 | 0
851 | Hooghly Division | Arambug Sub-Division | TIROL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000268/2023-2024 | 2279/HUG | 03/08/2023 | 591 | UNIQUE AGENCY | 361.39 | 332.79 | 70
852 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0
853 | Hooghly Division | Arambug Sub-Division | Laying rising main pipe for inter connection between Proposed T.W & Distribution including Protection work of TIROL Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002257/2024-2025 | 572/HUG | 04/03/2025 | 60 | UNIQUE AGENCY | 16.09 | 0 | 0
854 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000030/2023-2024 | 1234/11/Hug | 28/04/2023 | 0 | Resource Division | 25 | 0 | 0
855 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000162/2023-2024 | 1385/33/Hug | 15/05/2023 | 0 | Resource Division | 9.36 | 0 | 0
856 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000420/2023-2024 | 3057/40/Hug | 11/10/2023 | 0 | Resource Division | 9.36 | 0 | 0
857 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- II, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038623 Ref. ID- 503577402 SM Code- 15886 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06230/2023-2024 | 831 | 04/03/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
858 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- I, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038621 Ref. ID- 503577388 SM Code- 15886 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06231/2023-2024 | 832 | 04/03/2024 | 0 | WBSEDCL | 6 | 0 | 0
859 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.( SM/158668) Application No-5004061104 Reference Id-503590562 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06457/2023-2024 | 886 | 15/03/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
860 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000031/2023-2024 | 1708/ED | 18/04/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 5.59 | 40
861 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for TIROL PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000166/2024-2025 | 1189/ED | 14/06/2024 | 271 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 10.73 | 0 | 0
862 | Hooghly Division | Arambug Sub-Division | GARMANDARAN ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000172/2023-2024 | 1671/HUG | 08/06/2023 | 827 | TITAS CONSTRUCTION | 476.79 | 125.04 | 55
863 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PUKURIA , GARMANDARAN Zone-I , GARMANDARAN Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000251/2024-2025 | 3529/HUG | 22/10/2024 | 221 | KHAN ENTERPRISE | 48.02 | 0 | 66
864 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000296/2024-2025 | 3656/HUG | 13/11/2024 | 90 | M/S BIMAL DAS AND CO. | 16.13 | 0 | 0
865 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0
866 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002298/2024-2025 | 1148/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0
867 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000064/2023-2024 | 1234/31/Hug | 28/04/2023 | 0 | Resource Division | 56.14 | 0 | 0
868 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000473/2023-2024 | 3057/61/Hug | 11/10/2023 | 0 | Resource Division | 14.12 | 0 | 0
869 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gar Mandaran w/s Scheme,Zone-II,PH no-III Block-Goghat-II Dist-Hooghly under Electrical division,PHe Dte.(SM/15887) Application No-5004498949 Reference Id-503815611 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02604/2024-2025 | 638 | 18/12/2024 | 0 | WBSEDCL | 9.44 | 0 | 0
870 | Electrical | Arambug Sub-Division | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-I,Block-Goghat-I Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03700/2023-2024 | 241 | 01/09/2023 | 0 | WBSEDCL | 4.17 | 0 | 0
871 | Electrical | Arambug Sub-Division | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-II Block-Goghat-II, Dist-Hooghly under Electrical Division ,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03701/2023-2024 | 242 | 01/09/2023 | 0 | WBSEDCL | 5.35 | 0 | 0
872 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000029/2023-2024 | 1706/ED | 18/04/2023 | 805 | UNITED TRADERS | 21.47 | 20.78 | 30
873 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000877/2023-2024 | 3450/ED | 11/08/2023 | 874 | M.D ENTERPRISE | 21.44 | 0 | 20
874 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BALI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000139/2023-2024 | 1492/HUG | 22/05/2023 | 690 | P.K. GHOSH & CO. | 11.81 | 0 | 90
875 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BALI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000772/2022-2023 | 743/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 9.91 | 100
876 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bali w/s Scheme, PH No-3 Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15803) Application No-5004191492 Reference Id-503647819. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00537/2024-2025 |  | 29/05/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
877 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bali water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001144/2022-2023 | 1496/ED | 28/03/2023 | 795 | RUBY ENTERPRISE. | 10.75 | 0 | 30
878 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PATUL PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte.. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000744/2022-2023 | 655/HUG | 09/03/2023 | 30 | R CONSTRUCTION | 11.31 | 9.95 | 100
879 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000100/2023-2024 | 1263/15/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0
880 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04593/2023-2024 | 594 | 29/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0
881 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patul water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000004/2023-2024 | 1620/ED | 11/04/2023 | 720 | NITESH MANAGEMENT | 10.74 | 0 | 50
882 | Hooghly Division | Chandannagar Sub-Division | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of KAIKALA Water Supply Scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000079/2022-2023 | 210/chan | 13/04/2022 | 30 | SWASTIK ENTERPRISE | 5 | 4.65 | 0
883 | Hooghly Division | Chandannagar Sub-Division | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) |  | ORD/000081/2021-2022 | 1147/Hug | 29/06/2021 | 40 | SATYA NARAYAN BISWAS | 72.55 | 48.89 | 100
884 | Hooghly Division | Chandannagar Sub-Division | Providing balance 81 nos F.H.T.C. in Baladbandh village of kaikala Zone-1 and its adjoining mouzas water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000123/2021-2022 | 354/chan | 16/08/2021 | 20 | MGM ENTERPRISE | 4.93 | 3.55 | 100
885 | Hooghly Division | Chandannagar Sub-Division | Providing 91 nos. tap connection at Ichapur mouza of Kaikala water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL VILLAGE" | Assistant Engineer (Civil) |  | ORD/000353/2021-2022 | 14/chan | 05/01/2022 | 20 | SWASTIK ENTERPRISE | 5 | 5.02 | 100
886 | Hooghly Division | Chandannagar Sub-Division | Providing F.H.T.C in leftout portion of Choutara, Basudebpur, Baladbandh, Baramba, Ichapur, Kaikala village of Kaikala Zone-II and its adjoining mouzas water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [Block-Haripal] of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000386/2022-2023 | 2139/HUG | 26/09/2022 | 45 | MALLIKA ENTERPRISE | 63.68 | 62.39 | 100
887 | Hooghly Division | Chandannagar Sub-Division | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) |  | ORD/000561/2021-2022 | 1147/HUG | 29/06/2021 | 40 | SATYA NARAYAN BISWAS | 72.55 | 17.52 | 100
888 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000852/2021-2022 |  | 21/09/2021 | 0 | SATYA NARAYAN BISWAS | 20.9 | 0 | 0
889 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/001037/2021-2022 |  | 30/09/2021 | 0 | SATYA NARAYAN BISWAS | 9.09 | 0 | 0
890 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/001039/2021-2022 |  | 30/09/2021 | 0 | SURAJIT SINGHA RAY | 5.04 | 0 | 0
891 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/001040/2021-2022 |  | 30/09/2021 | 0 | SIKHA ENTERPRISE | 4.58 | 0 | 0
892 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/001041/2021-2022 |  | 30/09/2021 | 0 | BRISTI CONSTRUCTION | 4.58 | 0 | 0
893 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/002110/2021-2022 |  | 28/01/2022 | 0 | SWASTIK ENTERPRISE | 5.1 | 0 | 0
894 | Hooghly Division | Arambug Sub-Division | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000014/2022-2023 | 715/Hug | 07/04/2022 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.57 | 12.35 | 100
895 | Hooghly Division | Arambug Sub-Division | Providing 1050 nos Functional Household Tap Connection (FHTC) within the command area (left out portion) of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2021-2022 | 2127/Hug | 01/12/2021 | 40 | DILIP KUMAR GHOSH | 36.01 | 43.58 | 100
896 | Hooghly Division | Arambug Sub-Division | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of GOURHATI Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000445/2021-2022 | 463/Hug | 10/03/2022 | 20 | ZENITH CONSTRUCTION | 18.73 | 16.44 | 40
897 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000166/2021-2022 | 427/2-2/Hug | 07/03/2022 | 0 | Resource Division | 10.43 | 0 | 0
898 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of RADHABALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000145/2023-2024 | 1498/HUG | 22/05/2023 | 690 | P.K. GHOSH & CO. | 11.83 | 7.91 | 85
899 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100
900 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at RADHABALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000763/2022-2023 | 747/HUG | 15/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 10.28 | 0
901 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Radhaballavpur w/s Scheme, TW No-3 Dist- Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02131/2023-2024 | 117 | 20/07/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
902 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Radhaballabpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000006/2023-2024 | 1622/ED | 11/04/2023 | 90 | M/S, GHOSH ENTERPRISE | 10.74 | 10.66 | 40
903 | Hooghly Division | Chinsuria Sub-Division | Augmentation Kola PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00497/2023-2024 | BP-2023-24-398 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 4.22 | 0 | 0
904 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of KOLA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000080/2023-2024 | 1314/HUG | 10/05/2023 | 30 | M/S T.K.B. CONSTRUCTION | 32.26 | 31.34 | 50
905 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 65
906 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000354/2023-2024 | 3004/19/Hug | 05/10/2023 | 0 | Resource Division | 20.39 | 0 | 0
907 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000538/2023-2024 | 3059/31/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0
908 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Kola W/S. Sch. " | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04320/2023-2024 | 440 | 23/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
909 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kola water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000018/2023-2024 | 1634/ED | 11/04/2023 | 90 | BIJAN ENTERPRISE | 11.4 | 11.08 | 95
910 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000101/2023-2024 | 1420/HUG | 17/05/2023 | 30 | SB ASSOCIATES | 11.82 | 0 | 0
911 | Hooghly Division | Arambug Sub-Division | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KAPSIT PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000501/2023-2024 | 2861/HUG | 20/09/2023 | 360 | SUBHAJIT BISWAS | 22.56 | 11.07 | 50
912 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kapsit w/s Scheme, PH No-3 Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004276344 Reference Id-503683335. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01142/2024-2025 | 264 | 03/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
913 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kapsit w/s Scheme,PH No-IV Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004320167 Reference Id- 503705436 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01375/2024-2025 | 335 | 30/07/2024 | 0 | WBSEDCL | 11.46 | 0 | 0
914 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kapsit water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001152/2022-2023 | 1504/ED | 28/03/2023 | 888 | A.K. ENTERPRISE | 21.93 | 8.12 | 100
915 | Hooghly Division | Arambug Sub-Division | MAYAPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000073/2023-2024 | 1300 | 08/05/2023 | 812 | MS PRADIP KUMAR PAL | 360.88 | 159.06 | 15
916 | Hooghly Division | Arambug Sub-Division | Revised Geo-reference drawing (CAD-GIS) and redsign of Network Distribution System of Mayapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte . | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000434/2024-2025 | 805/Arg | 23/08/2024 | 10 | APEX ENGINEERING | 0.83 | 0 | 0
917 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAYAPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000758/2023-2024 | 448/HUG | 15/02/2024 | 60 | MS PRADIP KUMAR PAL | 29.69 | 12.09 | 40
918 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000033/2023-2024 | 1234/13/Hug | 28/04/2023 | 0 | Resource Division | 44.08 | 0 | 0
919 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000187/2023-2024 | 1385/58/Hug | 15/05/2023 | 0 | Resource Division | 6.44 | 0 | 0
920 | Electrical | Arambug Sub-Division | Quotaion of New Service Connection for Mayapur w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15791) Application No-5004314243 Reference Id-503702554 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01355/2024-2025 | 334 | 30/07/2024 | 0 | WBSEDCL | 7.67 | 0 | 0
921 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Mayapur PWSS, Zone-I, TW - I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04372/2023-2024 | 462 | 01/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
922 | Electrical | Arambug Sub-Division | Quotation for New Service Connection at Mayapur W/S. Sch. Z=I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04612/2023-2024 | 611 | 04/01/2024 | 0 | WBSEDCL | 5.8 | 0 | 0
923 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-I) water supply scheme, T.W. No. I, II, III & IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000034/2023-2024 | 1711/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 40.97 | 0 | 0
924 | Hooghly Division | Arambug Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of JAGATPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000115/2023-2024 | 1444/HUG | 18/05/2023 | 30 | S.S. CONSULTANCY AND CONSTRUCTION | 31.19 | 31.18 | 65
925 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/16122) Application No-5004134007 Reference Id-503627506 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01002/2024-2025 | 262 | 03/07/2024 | 0 | WBSEDCL | 12.35 | 0 | 0
926 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme, TW No-4 Block-Khanakul-II,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03860/2023-2024 | 308 | 27/09/2023 | 0 | WBSEDCL | 7.56 | 0 | 0
927 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme, TW no-5 Block-Khanakul-II,Dist-Hooghly under Electrical division,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03861/2023-2024 | 289 | 20/09/2023 | 0 | WBSEDCL | 6.65 | 0 | 0
928 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jagatpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000030/2023-2024 | 1707/ED | 18/04/2023 | 90 | GHOSE ENGINEERING SYNDICATE | 21.93 | 21.82 | 40
929 | Electrical | Arambug Sub-Division | Hire Charges Bill of V.No.- WB-04G-2822 for official use of Electrical Division PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001029/2023-2024 | 591_AE-1_ED | 21/08/2023 | 7 | DASHRATH KUMAR PRAJAPATI | 5 | 1.95 | 10
930 | Electrical | Arambug Sub-Division | Hire Charges Bill for official use office of the Assistant Engineer -I PHED | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002498/2022-2023 | 203_ae1 | 27/03/2023 | 365 | DASHRATH KUMAR PRAJAPATI | 5 | 0.39 | 1
931 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000765/2023-2024 | 149/Chan | 16/02/2024 | 15 | TECHVISION | 0.84 | 0.84 | 98
932 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000290/2023-2024 | 1383/36/Hug | 15/05/2023 | 0 | Resource Division | 3.33 | 0 | 0
933 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Rajballavbati W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04221/2023-2024 | 412 | 09/11/2023 | 0 | WBSEDCL | 6.55 | 0 | 0
934 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Rajballabhbati PWSS, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04485/2023-2024 | 528 | 15/12/2023 | 0 | WBSEDCL | 1.71 | 0 | 0
935 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajaballabhbati water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000033/2023-2024 | 1710/ED | 18/04/2023 | 714 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.5 | 16.76 | 20
936 | Hooghly Division | Arambug Sub-Division | RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000148/2023-2024 | 1503/HUG | 22/05/2023 | 664 | UNIQUE AGENCY | 562.52 | 529.38 | 85
937 | Hooghly Division | Arambug Sub-Division | Laying Additional pipeline for connection of 3rd Tubewell with HDPE PE 80, PN 1.0 pipes with supporting structure, Horizontal Auger boring with water jet system and Approach Road at Ramnagar Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000318/2024-2025 | 3688/HUG | 14/11/2024 | 153 | UNIQUE AGENCY | 28.47 | 0 | 50
938 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100
939 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RAMNAGAR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000537/2023-2024 | 3088/HUG | 12/10/2023 | 550 | UNIQUE AGENCY | 34.81 | 23.65 | 45
940 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000047/2023-2024 | 1234/19/Hug | 28/04/2023 | 0 | Resource Division | 27.39 | 0 | 0
941 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000328/2023-2024 | 2607/1/Hug | 29/08/2023 | 0 | Resource Division | 14.19 | 0 | 0
942 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000432/2023-2024 | 3057/34/Hug | 11/10/2023 | 0 | Resource Division | 15.7 | 0 | 0
943 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ramnagar W/s scheme, PH No-I, District-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01919/2023-2024 | 93 | 13/07/2023 | 0 | WBSEDCL | 11.28 | 0 | 0
944 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ramnagar W/s Scheme, PH No-II, District-Hooghly Under Electrical Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01920/2023-2024 | 94 | 13/07/2023 | 0 | WBSEDCL | 10.9 | 0 | 0
945 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ramnagar w/s Scheme,PH No-3,Block-Arambag,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04078/2023-2024 | 346 | 11/10/2023 | 0 | WBSEDCL | 12.88 | 0 | 0
946 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Salepue Paschimpara Ramnagar W/S. Sch. TW-3 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04316/2023-2024 | 428 | 17/11/2023 | 0 | WBSEDCL | 1.21 | 0 | 0
947 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000054/2023-2024 | 1798/ED | 24/04/2023 | 90 | C.M. ENTERPRISE | 21.38 | 21.33 | 50
948 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000010/2024-2025 | 428/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.92 | 0.92 | 100
949 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2024-2025 | 429/chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100
950 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000012/2024-2025 | 430/chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100
951 | Hooghly Division | Chandannagar Sub-Division | SINHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000152/2023-2024 | 1566/HUG | 29/05/2023 | 730 | BIMAL KUMAR HALDER | 79.42 | 0 | 90
952 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000301/2023-2024 | 1383/45/Hug | 15/05/2023 | 0 | Resource Division | 1.42 | 0 | 0
953 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sinhal Patan water supply Scheme [SM/18103], T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. No. - 503588851, Dt. - 07-03-2024, Application No. - 5004057413 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06279/2023-2024 | 877 | 13/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
954 | Hooghly Division | Chandannagar Sub-Division | PAYMENT FOR ROAD RESTORATION | Assistant Engineer (Civil) |  | BILL/00266/2024-2025 | BP-2024-25-183 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.44 | 0 | 0
955 | Hooghly Division | Chandannagar Sub-Division | PAYMENT FOR ROAD RESTORATION | Assistant Engineer (Civil) |  | BILL/00267/2024-2025 | BP-2024-25-184 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 14.63 | 0 | 0
956 | Hooghly Division | Chandannagar Sub-Division | PAYMENT FOR ROAD RESTORATION | Assistant Engineer (Civil) |  | BILL/00268/2024-2025 | BP-2024-25-185 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 26.97 | 0 | 0
957 | Hooghly Division | Chandannagar Sub-Division | Restoration Works for Singur-Ugly Road | Assistant Engineer (Civil) |  | BILL/01133/2023-2024 | BP-2023-24-852 | 21/02/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 1.49 | 0 | 0
958 | Hooghly Division | Chandannagar Sub-Division | 1st Continuation order for the work of Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 02 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024) | Assistant Engineer (Civil) |  | ORD/000023/2024-2025 | 476/Chan | 26/04/2024 | 61 | PAUL AUTOMOBILES | 0.29 | 0 | 0
959 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000246/2023-2024 | 2109/HUG | 20/07/2023 | 775 | BAPPADITYA BANERJEE | 318.37 | 120.82 | 33
960 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000247/2023-2024 | 2110/HUG | 20/07/2023 | 780 | ARUN SEAL AND CO. | 410.87 | 292.23 | 10
961 | Hooghly Division | Chandannagar Sub-Division | Construction of structural shed for storing Mechanical pumps and machineries at Kamarkundu Zone-II OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil) |  | ORD/000247/2025-2026 | 897/CHAN | 21/07/2025 | 15 | TOTON MONDAL | 4.88 | 0 | 0
962 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000248/2023-2024 | 2111/HUG | 20/07/2023 | 744 | S.K. GHOSH | 289.99 | 19.94 | 10
963 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-VII) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000249/2023-2024 | 2112/HUG | 20/07/2023 | 896 | S. HATI | 288.45 | 59.13 | 70
964 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Z-7) 1st T/W site & Kamarkundu (Z-7) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) |  | ORD/000281/2024-2025 | 920/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
965 | Hooghly Division | Chandannagar Sub-Division | Repairing & Renovation work of Existing additional Room at under Kamarkundu zone-3 water supply scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000298/2025-2026 | 931/CHAN | 21/07/2025 | 20 | ASHA ENTERPRISE | 4.98 | 0 | 50
966 | Hooghly Division | Chandannagar Sub-Division | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & FHTC In Daluigaccha Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000396/2023-2024 | 2609/HUG | 29/08/2023 | 270 | SUJATA CONSTRUCTION | 227.52 | 0 | 0
967 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme with Sinking of tube-well, FHTC within Kamarkundu & Singur Mouza, construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000397/2023-2024 | 2610/HUG | 29/08/2023 | 820 | DAS ENTERPRISE | 149.29 | 88.36 | 60
968 | Hooghly Division | Chandannagar Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of KAMARKUNDU PWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000481/2024-2025 | 4057/HUG | 19/12/2024 | 120 | SWASTIK ENTERPRISE | 13 | 0 | 0
969 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-V) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000573/2023-2024 | 3114/HUG | 13/10/2023 | 541 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 129.13 | 13 | 50
970 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of KAMARKUNDU (ZONE-IV) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000574/2023-2024 | 3113/HUG | 13/10/2023 | 602 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 204.08 | 124.34 | 50
971 | Hooghly Division | Chandannagar Sub-Division | Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 05 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte.[ Period from 01.12.2023 to 30.04.2024]. | Assistant Engineer (Civil) |  | ORD/000657/2023-2024 | 930/Chan | 30/11/2023 | 152 | PAUL AUTOMOBILES | 0.72 | 0 | 0
972 | Hooghly Division | Chandannagar Sub-Division | Hiring of One number Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 06 (Six) months having contract carriage permit for playing within West Bengal from Regional Transport Authority for the office of the Assistant Engineer Chandannagar Sub-Division, PHE Dte. (Period from 01.10.2025 to 31.03.2026). | Assistant Engineer (Civil) |  | ORD/000668/2025-2026 | 1447/Chan | 23/09/2025 | 181 | ZENITH INFRASTRUCTURE | 0.86 | 0 | 0
973 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line & FHTC in SINGUR (CT ) & BURIGEON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000867/2023-2024 | 757/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 9.93 | 100
974 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000870/2023-2024 | 759/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.98 | 9.97 | 100
975 | Hooghly Division | Chandannagar Sub-Division | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000871/2023-2024 | 752/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.77 | 9.65 | 100
976 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000872/2023-2024 | 753/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.78 | 9.66 | 100
977 | Hooghly Division | Chandannagar Sub-Division | Laying left out pipe line For Augmentation of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000873/2023-2024 | 761/HUG | 05/03/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 7.28 | 6.85 | 100
978 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000874/2023-2024 | 760/HUG | 05/03/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 9.97 | 9.89 | 100
979 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line & FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000875/2023-2024 | 754/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.79 | 9.72 | 100
980 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line & FHTC in BURIGAON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000876/2023-2024 | 755/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 10 | 9.97 | 100
981 | Hooghly Division | Chandannagar Sub-Division | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000877/2023-2024 | 762/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.8 | 9.62 | 100
982 | Hooghly Division | Chandannagar Sub-Division | Laying additional pipe line & FHTC in SINGUR(CT)Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000878/2023-2024 | 756/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 9.89 | 100
983 | Hooghly Division | Chandannagar Sub-Division | Balance FHTC in SINGUR CT (P) Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000879/2023-2024 | 763/HUG | 05/03/2024 | 15 | SRI KRISHNA ENTERPRISE | 7.1 | 0 | 0
984 | Electrical | Chandannagar Sub-Division | Quotation money deposition for new service connection at Kamarkundu w/s scheme, Zone- VI, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004229746 Reference ID- 503663995 SM Code- 18397 | Assistant Engineer (Civil) |  | BILL/00822/2024-2025 | 218 | 18/06/2024 | 0 | WBSEDCL | 4.94 | 0 | 0
985 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Kamarkundu W/S Sch., Zone - V, T/W No. - I,[SM/18397], under Singur CCC, WBSEDCL, Ref. Id. - 503706067, Dt. - 30-07-2024, Application No. - 5004320836 | Assistant Engineer (Civil) |  | BILL/01591/2024-2025 | 356 | 07/08/2024 | 0 | WBSEDCL | 7.25 | 0 | 0
986 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-VI, TW-III | Assistant Engineer (Civil) |  | BILL/04570/2023-2024 | 576 | 27/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
987 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-I | Assistant Engineer (Civil) |  | BILL/04571/2023-2024 | 575 | 27/12/2023 | 0 | WBSEDCL | 4.52 | 0 | 0
988 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch.TW-II | Assistant Engineer (Civil) |  | BILL/04585/2023-2024 | 596A | 29/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0
989 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Kamarkundu PWSS, Zone-VI, TW - II | Assistant Engineer (Civil) |  | BILL/04586/2023-2024 | 589 | 28/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0
990 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-II | Assistant Engineer (Civil) |  | BILL/04854/2023-2024 | 673 | 17/01/2024 | 0 | WBSEDCL | 6.51 | 0 | 0
991 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | Assistant Engineer (Civil) |  | BILL/05906/2023-2024 | 720 | 31/01/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
992 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-IV | Assistant Engineer (Civil) |  | BILL/05910/2023-2024 | 716 | 29/01/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
993 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-III | Assistant Engineer (Civil) |  | BILL/05911/2023-2024 | 719 | 29/01/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
994 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | Assistant Engineer (Civil) |  | BILL/05913/2023-2024 | 718 | 29/01/2024 | 0 | WBSEDCL | 3.02 | 0 | 0
995 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-VI | Assistant Engineer (Civil) |  | BILL/05915/2023-2024 | 717 | 29/01/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
996 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-III | Assistant Engineer (Civil) |  | BILL/05985/2023-2024 | 730 | 05/02/2024 | 0 | CESC LIMITED. | 5.17 | 0 | 0
997 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-VII | Assistant Engineer (Civil) |  | BILL/06106/2023-2024 | 771 | 19/02/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
998 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-I, Z-VII | Assistant Engineer (Civil) |  | BILL/06107/2023-2024 | 773 | 19/02/2024 | 0 | WBSEDCL | 4.67 | 0 | 0
999 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-IV | Assistant Engineer (Civil) |  | BILL/06108/2023-2024 | 772 | 19/02/2024 | 0 | WBSEDCL | 7.2 | 0 | 0
1000 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamarkundu water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/001864/2023-2024 | 50/ED | 05/01/2024 | 731 | DAS ENTERPRISE | 172.16 | 53.44 | 55
1001 | Hooghly Division | Srirampur Sub-Division | KAPASHARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site at ZONE-I & Sinking of tube-well, LDS, Rising Main, FHT, Construction of switch-rooms & boundary walls at different TW site at ZONE-II, under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2023-2024 | 2335/HUG | 07/08/2023 | 549 | SAMIRON GHOSH | 934.14 | 592.08 | 10
1002 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000382/2023-2024 | 3005/16/Hug | 05/10/2023 | 0 | Resource Division | 22.91 | 0 | 0
1003 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000477/2023-2024 | 3060/4/Hug | 11/10/2023 | 0 | Resource Division | 22.95 | 0 | 0
1004 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Kapasaria w/s scheme, Zone- I, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000120622 Reference ID- 860314252 SM Code- 18624 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02124/2024-2025 | 559 | 11/11/2024 | 0 | WBSEDCL | 0.19 | 0 | 0
1005 | Electrical | Srirampur Sub-Division | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02923/2023-2024 | 211 | 24/08/2023 | 0 | WBSEDCL | 17.21 | 0 | 0
1006 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04024/2023-2024 | 317 & 318 | 03/10/2023 | 0 | WBSEDCL | 6.88 | 0 | 0
1007 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04608/2023-2024 | 608 | 04/01/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
1008 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No. V & VI, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000881/2023-2024 | 3454/ED | 11/08/2023 | 90 | R.N.S. TRADING | 20.83 | 0 | 0
1009 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000918/2023-2024 | 3589/ED | 28/08/2023 | 90 | R.N.S. TRADING | 41.38 | 38.54 | 90
1010 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. IX, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003086/2024-2025 | 480/ED | 18/03/2025 | 90 | SWAPAN ENTERPRISE | 11.3 | 0 | 0
1011 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VIII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003090/2024-2025 | 481/ED | 18/03/2025 | 90 | ANUPAMA ENGINEERING WORKS | 11.3 | 0 | 0
1012 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003095/2024-2025 | 482/ED | 18/03/2025 | 90 | S.P. CONSTRUCTION | 11.42 | 0 | 0
1013 | Electrical | Srirampur Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003739/2024-2025 | 331_AE-I/ED | 05/02/2025 | 176 | SWARUP LAL SARKAR | 0.84 | 0 | 0
1014 | Hooghly Division | Howrah Mechanical Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CANDANNAGORE SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00158/2023-2024 | BP-2023-24-136 | 15/06/2023 | 0 | GOUR KUMAR DAS | 0.77 | 0 | 0
1015 | Hooghly Division | Howrah Mechanical Sub-Division | REPAIRING OF ROAD FROM MAHESHPUR TO BHAUSANARA PART OF ANANTAPUR | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00431/2023-2024 | BP-2023-24-361 | 12/09/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 32.06 | 0 | 0
1016 | Hooghly Division | Howrah Mechanical Sub-Division | Haripal Jagajibanpur Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00498/2023-2024 | BP-2023-24-399 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 18.03 | 0 | 0
1017 | Hooghly Division | Howrah Mechanical Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL JAGJEEBANPUR ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00663/2024-2025 | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 18.03 | 0 | 0
1018 | Hooghly Division | Howrah Mechanical Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL JAGJEEBANPUR ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00665/2024-2025 | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 7.19 | 0 | 0
1019 | Hooghly Division | Howrah Mechanical Sub-Division | DAMAGED PIPELINE OF PMGSY ROAD FROM NANDAKUTHI TO DALALPUR UNDER HARIPAL BLOCK | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00931/2023-2024 | BP-2023-24-676 | 22/12/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.03 | 0 | 0
1020 | Hooghly Division | Howrah Mechanical Sub-Division | REGARDING DAMAGE OF PMGSY -III ROAD NAMELY NANDAKUTHI TO DALAPATIPUR PACKAGE NO.WB 08 350 UNDER HARIPAL BLOCK CAUSED BY LAYING OF PHE PIPE LINE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01804/2023-2024 | BP-2024-25-3 | 08/04/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 21 | 0 | 0
1021 | Hooghly Division | Howrah Mechanical Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of BANIDPUR PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000072/2023-2024 | 1281/HUG | 04/05/2023 | 45 | AYUSH ENTERPRISE | 93.94 | 93.5 | 100
1022 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000136/2022-2023 | 1345/Hug | 29/06/2022 | 270 | SOUMYADIP DE | 110.86 | 35.86 | 99
1023 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Chak Ananta (Part) Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6 M X 3.0M )& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000163/2022-2023 | 1563/HUG | 29/07/2022 | 45 | M/S R.M. CONSTRUCTION | 142.15 | 101.96 | 70
1024 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of Haripal Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000227/2022-2023 | 270/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.83 | 2.84 | 0
1025 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of HARIPAL ZONE-II PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000230/2022-2023 | 275/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.45 | 3.21 | 0
1026 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of structural shed for storing Mechanical pumps and machineries at Haripal Zone-I OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000248/2025-2026 | 898/CHAN | 21/07/2025 | 15 | JOY GURU ENTERPRISE | 4.88 | 0 | 0
1027 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of HARIPAL (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS within Aminpur & Chandinagar (Part) Mouza at HARIPAL Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000442/2022-2023 | 1347/Hug | 29/06/2022 | 300 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 183.24 | 145.88 | 50
1028 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) & Aminpur Mouza & Functional Household tap Connection, Construction of Boundary Wall & Switch Room at Proposed 2nd T.W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000443/2022-2023 | 2472/HUG | 18/11/2022 | 806 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 157.64 | 142.45 | 100
1029 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000448/2022-2023 | 2499/HUG | 22/11/2022 | 771 | B.R SUPPLIERS | 13.81 | 0 | 100
1030 | Hooghly Division | Howrah Mechanical Sub-Division | Balance work for special repairing of UPVC pipeline damaged due to construction of road with drain of PWD at Balarampur of Ashutosh G.P. under the command area of Haripal water supply scheme under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000450/2022-2023 | 337/CHAN | 12/07/2022 | 10 | GOUR KUMAR DAS | 3.88 | 3.05 | 0
1031 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000459/2022-2023 | 2510/HUG | 22/11/2022 | 45 | SPG ENTERPRISES | 27.65 | 26.53 | 0
1032 | Hooghly Division | Howrah Mechanical Sub-Division | Horizontal road crossing by trenchless method at Gopinagar More of Baidyabati- Tarakeswar Road (SH-12)and Haripal Station to Basudevpur More Road under Haripal (Zone-II) PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000484/2023-2024 | 2830/HUG | 14/09/2023 | 30 | SOUMYADIP DE | 8.98 | 8.98 | 100
1033 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Krishnapur, Chak Ananta(Part), Haripal, Chandinagar(Part), Kamar Chandi Mouza & Functional Household tap Connection, Rising Main at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000569/2022-2023 | 1599/HUG | 04/08/2022 | 45 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 193.1 | 161.04 | 100
1034 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000673/2022-2023 | 1345/HUG | 29/06/2022 | 30 | SOUMYADIP DE | 110.86 | 70.82 | 0
1035 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) Mouza & Functional Household tap Connection, Rising Main, Construction of Boundary Wall & Switch Room at H/W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000704/2022-2023 | 426/HUG | 15/02/2023 | 45 | SOUMYADIP DE | 128.29 | 123.02 | 100
1036 | Hooghly Division | Howrah Mechanical Sub-Division | Providing F.H.T.C in leftout portion (Anantapur, Avirampur, Mosapur, Dignagar, Gabati mouzas) of Haripal water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000801/2025-2026 | 2832/HUG | 17/11/2025 | 35 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 19.67 | 0 | 0
1037 | Hooghly Division | Howrah Mechanical Sub-Division | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Gopinagar, Aminpur and Khamarchandi Village of Haripal Zone II and it's adjoining mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte [Block- Haripal] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000897/2023-2024 | 820/HUG | 11/03/2024 | 30 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 6.63 | 0 | 0
1038 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000027/2022-2023 | 1125/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0
1039 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000141/2022-2023 | 2686/8/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0
1040 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000143/2021-2022 | 157/6/Hug | 24/01/2022 | 0 | Resource Division | 1.03 | 0 | 0
1041 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000152/2021-2022 | 423/3/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
1042 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000154/2022-2023 | 01/02/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
1043 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000203/2022-2023 | 109/6/Hug | 10/01/2023 | 0 | Resource Division | 20.79 | 0 | 0
1044 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000210/2023-2024 | 1383/13/Hug | 15/05/2023 | 0 | Resource Division | 11.2 | 0 | 0
1045 | Electrical | Howrah Mechanical Sub-Division | Quotation for New Service Connection of Haripal W/S scheme(Aug),Zone-II,PH No-II Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00730/2023-2024 | 16 | 02/05/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
1046 | Electrical | Howrah Mechanical Sub-Division | "Quotation Bill for New Service Connection at of Haripal W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01913/2022-2023 | 01 | 11/04/2023 | 0 | WBSEDCL | 5.42 | 0 | 0
1047 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Haripal water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2022-2023 | 840/ED | 14/02/2023 | 90 | DAS ENTERPRISE | 32.23 | 21.41 | 50
1048 | Electrical | Howrah Mechanical Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000946/2023-2024 | 1381/HMSD | 14/06/2023 | 184 | DEBASHISH GHOSH | 0.87 | 1.45 | 20
1049 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jatarpur village under Polba Dadpur Block, Tarabehari village of Polba Dadpur Block and Goai village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000997/2023-2024 | 271/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
1050 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0
1051 | Hooghly Division | Arambug Sub-Division | Augmentation of KRISHNANAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls in ZONE-II & Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I under KHANAKUL-I Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000224/2023-2024 | 2036/HUG | 13/07/2023 | 812 | M/S PRADYUT KUMAR HAZRA | 642.46 | 488.05 | 15
1052 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0
1053 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000300/2024-2025 | 3660/HUG | 13/11/2024 | 90 | SUDIPTA DAS | 16.08 | 0 | 0
1054 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000324/2024-2025 | 3665/HUG | 13/11/2024 | 90 | M/S B N ENTERPRISE | 16.12 | 0 | 0
1055 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0
1056 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0
1057 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002646/2024-2025 | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1058 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000184/2022-2023 | 79/22/Hug | 06/01/2023 | 0 | Resource Division | 38.01 | 0 | 0
1059 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-I, Z-II | Assistant Engineer | Junior Engineer (Civill) | BILL/04317/2023-2024 | 426 | 17/11/2023 | 0 | WBSEDCL | 5.3 | 0 | 0
1060 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-II, Z-II, | Assistant Engineer | Junior Engineer (Civill) | BILL/04318/2023-2024 | 425 | 17/11/2023 | 0 | WBSEDCL | 3.94 | 0 | 0
1061 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000190/2024-2025 | 1205/ED | 14/06/2024 | 90 | SWAPAN ENTERPRISE | 10.75 | 0 | 0
1062 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. V, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000193/2024-2025 | 1207/ED | 14/06/2024 | 90 | D.S. ENTERPRISE | 10.74 | 0 | 0
1063 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnanagar water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000992/2023-2024 | 3788/ED | 26/09/2023 | 90 | GLACIER ENGINEERING CO. | 21.75 | 21.71 | 40
1064 | Hooghly Division | Chandannagar Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR HAZRA MORE TO SUNDARPUR MORE ROAD | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | BILL/00664/2024-2025 | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 37.84 | 0 | 0
1065 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Zone-4) 1st T/W site & Paschim Narayanpur 1st T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000290/2024-2025 | 927/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
1066 | Hooghly Division | Chandannagar Sub-Division | PASCHIM NARAYANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000315/2023-2024 | 2387/HUG | 09/08/2023 | 812 | PRASUN ENTERPRISE (PRASUN BISWAS) | 714.76 | 110.52 | 10
1067 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | RTOR000195/2022-2023 | 109/ 10/Hug | 10/01/2023 | 0 | Resource Division | 73.57 | 0 | 0
1068 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | RTOR000404/2023-2024 | 3058/5/Hug | 11/10/2023 | 0 | Resource Division | 16.53 | 0 | 0
1069 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-II | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | BILL/04581/2023-2024 | 586 | 28/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
1070 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-I | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | BILL/04582/2023-2024 | 587 | 28/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
1071 | Hooghly Division | Hooghly Division | Material Requisition To Resource Division | Assistant Engineer(HQ) |  | RTOR000316/2023-2024 | 1384/13/Hug | 15/05/2023 | 0 | Resource Division | 10.42 | 0 | 0
1072 | Hooghly Division | Hooghly Division | MINI WATER SUPPLY SCHEME | Assistant Engineer(HQ) |  | VCH/000909/2022-2023 | C092250849619 | 28/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 713.77 | 0 | 0
1073 | Hooghly Division | Hooghly Division | REQUISITION OF FUND FOR SAJAL GRAM | Assistant Engineer(HQ) |  | VCH/001006/2022-2023 |  | 15/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 718.17 | 0 | 0
1074 | Hooghly Division | Hooghly Division | REQUISITION OF SAJAL GRAM | Assistant Engineer(HQ) |  | VCH/001043/2022-2023 |  | 21/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 718.17 | 0 | 0
1075 | Hooghly Division | Hooghly Division | Preparation of DPR mini PWSS | Assistant Engineer(HQ) |  | VCH/001723/2022-2023 | C092252696982 | 29/09/2022 | 0 | APEX ENGINEERING | 4.4 | 0 | 0
1076 | Hooghly Division | Arambug Sub-Division | ARUNDA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer |  | ORD/000290/2023-2024 | 2341/HUG | 07/08/2023 | 270 | SIBSANKAR CHOWDHURY | 833.08 | 0 | 0
1077 | Hooghly Division | Arambug Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for ARUNDA ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000381/2024-2025 | 3775/HUG | 25/11/2024 | 45 | I R CONSTRUCTION | 25.93 | 0 | 0
1078 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer |  | ORD/000843/2023-2024 | 723/HUG | 05/03/2024 | 60 | SPG ENTERPRISES | 64.34 | 0 | 50
1079 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)- 1 no?s (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no?s (3) ARUNDA PWSS (Z-I)- 4 no?s (4) ARUNDA PWSS (Z-II)- 5 no?s (5) POL PWSS ? 2no?s | Assistant Engineer |  | ORD/002744/2024-2025 | 1152/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1080 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000412/2023-2024 | 3057/45/Hug | 11/10/2023 | 0 | Resource Division | 12.79 | 0 | 0
1081 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000863/2023-2024 | 3435/ED | 11/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0
1082 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000925/2023-2024 | 3596/ED | 28/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0
1083 | Hooghly Division |  | Laying of HDPE pipeline and distribution at the left out portions of Chopa PWSS under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte. |  |  | ORD/000054/2024-2025 | 2345/HUG | 19/06/2024 | 300 | BOSE ENTERPRISE (RATUL BOSE) | 53.11 | 17.58 | 50
1084 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0
1085 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000578/2023-2024 | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 60
1086 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 0 | 60
1087 | Hooghly Division |  | Laying / Repairing Pipeline in damaged portion and other allied works for Chopa & Dighir Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000731/2023-2024 | 23/CH | 05/01/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 1.58 | 1.5 | 100
1088 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP-I GP of DHANIAKHALI Block. |  |  | ORD/000928/2023-2024 | 248/CH | 12/03/2024 | 30 | SAKALER SATHI SWAMBHAR GOSTHI | 4.98 | 0 | 65
1089 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001210/2023-2024 | 4488/ED | 23/11/2023 | 90 | H.K.DAS & CO. | 21.88 | 0 | 0
1090 | Hooghly Division |  | Sinking of 1no 300 X200 mm dia Tube Well 210 mtr. Depth by tube-well by D.R. Rig method for using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) to replace the exsisting T.W at head work site of Paonan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000053/2024-2025 | 2344/HUG | 19/06/2024 | 30 | BANSBERIA CONSTRUCTION CO. | 16.03 | 0 | 0
1091 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 45
1092 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.51 | 25
1093 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (six) Nos villages & HGJ villages of Paunan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. |  |  | ORD/000801/2023-2024 | 144/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 50
1094 | Electrical |  | Quotation for new service connection at Pownan W/S Sch. , (S. Aug.),[SM/18951] T/W No. - IV, Bihari Pally, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594866, Dt. - 02-04-2024, Application No. - 5004069653 |  |  | BILL/00077/2024-2025 | 39 | 09/04/2024 | 0 | WBSEDCL | 4.2 | 0 | 0
1095 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of Paunan Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001275/2023-2024 | 4515/ED | 23/11/2023 | 688 | S.S. ENTERPRISES | 21.91 | 2.91 | 50
1096 | Hooghly Division | Srirampur Sub-Division | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000299/2023-2024 | 2333/Hug | 07/08/2023 | 815 | S & P ENTERPRISE | 964.69 | 495.38 | 14
1097 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000174/2022-2023 | 79/9Hug | 06/01/2023 | 0 | Resource Division | 79.13 | 0 | 0
1098 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000379/2023-2024 | 3005/3/Hug | 05/10/2023 | 0 | Resource Division | 85.62 | 0 | 0
1099 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000520/2023-2024 | 3060/3/Hug | 11/10/2023 | 0 | Resource Division | 22.95 | 0 | 0
1100 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04447/2023-2024 | 505 | 08/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0
1101 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04448/2023-2024 | 503 | 08/12/2023 | 0 | WBSEDCL | 3.63 | 0 | 0
1102 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04449/2023-2024 | 502 | 08/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
1103 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04450/2023-2024 | 504 | 08/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0
1104 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000845/2023-2024 | 3413/ED | 10/08/2023 | 90 | MENAKA ENTERPRISE | 20.36 | 14.41 | 30
1105 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000846/2023-2024 | 3414/ED | 10/08/2023 | 90 | S.P. CONSTRUCTION | 22.37 | 21.63 | 70
1106 | Hooghly Division |  | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000591/2023-2024 | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0
1107 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000644/2023-2024 | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0
1108 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARISH CHAK piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001289/2023-2024 | 4521/ED | 23/11/2023 | 90 | T S CONSTRUCTION | 21.47 | 0 | 0
1109 | Hooghly Division |  | Sinking of Tubewell,Construction of Switch Room,Boundary wall,and rising main with interconnection at Danbatipur ,Chikrand W/s Scheme(Zone-1)Danbatipur , Naity; Chanditala-II Block underSerampore Sub-Division of Hooghly Division PHE Dte.. |  |  | ORD/000438/2024-2025 | 4042/HUG | 19/12/2024 | 183 | M/S T.K.B. CONSTRUCTION | 47.79 | 0 | 25
1110 | Hooghly Division |  | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 11.75 | 40
1111 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 14.26 | 100
1112 | Hooghly Division |  | Laying Distribution of left out portion and Land Development at Chikrand Jalapara at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000861/2023-2024 | 745/HUG | 05/03/2024 | 300 | SADHUKHAN ENTERPRISE | 59.95 | 8.96 | 80
1113 | Hooghly Division |  | Laying Distribution of left out portion of pipeline to restore the water supply at Chikrand Jalapara & Bankagacha (part) and other allied works at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte |  |  | ORD/000863/2023-2024 | 746/HUG | 05/03/2024 | 20 | AMBIAN INFRASTRUCTURE | 23.36 | 9.41 | 50
1114 | Hooghly Division |  | Laying Distribution of left out portion of pipeline at Chikrand Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000901/2023-2024 | 822/HUG | 11/03/2024 | 30 | S D ENTERPRISE | 24.19 | 22.77 | 80
1115 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Piarapur (P) village under Piarapur PWSS (2 nos.) 2. Baksa village under Baksa PWSS (2 nos.) 3. Naiti village under Chikrand PWSS (2 nos.) |  |  | ORD/001029/2023-2024 | 169/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 80
1116 | Electrical |  | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004377254 Reference ID- 503729858 SM Code- 18966 |  |  | BILL/02275/2024-2025 | BP-24-25-584 | 19/11/2024 | 0 | WBSEDCL | 5.2 | 0 | 0
1117 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND PIPED W/S SCHEME, Zone - I, T.W. No. IV, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000176/2024-2025 | 1200/ED | 14/06/2024 | 90 | NITESH MANAGEMENT | 10.72 | 0 | 0
1118 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND MINI PIPED W/S SCHEME, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000395/2024-2025 | 1479/ED | 25/07/2024 | 90 | SHIVAM ENTERPRISE | 7.58 | 0 | 0
1119 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001294/2023-2024 | 4526/ED | 23/11/2023 | 90 | DEBJYOTI BASU | 10.75 | 10.46 | 90
1120 | Hooghly Division |  | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] |  |  | ORD/000395/2023-2024 | 2601/HUG | 29/08/2023 | 812 | S & P ENTERPRISE | 917.75 | 91.79 | 40
1121 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000500/2023-2024 | 3060/1/Hug | 11/10/2023 | 0 | Resource Division | 19.2 | 0 | 0
1122 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone- I, T.W. NO- I, Dist.-Hooghly under PHE Dte. Application No- 5004091751 Reference ID- 503606734 SM Code- 18778 |  |  | BILL/00160/2024-2025 | 69 | 16/04/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
1123 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004303896 Reference ID- 503696996 SM Code- 18778 |  |  | BILL/01404/2024-2025 | 348 | 31/07/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
1124 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004303977 Reference ID- 503697862 SM Code- 18778 |  |  | BILL/01405/2024-2025 | 346 | 31/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
1125 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000935/2023-2024 | 3614/ED | 29/08/2023 | 90 | M/S P.P. ELECTRICALS | 20.34 | 16.06 | 40
1126 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000936/2023-2024 | 3615/ED | 29/08/2023 | 90 | INDRANI ENTERPRISE | 20.27 | 0 | 40
1127 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00087/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.19 | 0 | 0
1128 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00219/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.21 | 0 | 0
1129 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00416/2023-2024 | BP-2023-24-341 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.96 | 0 | 0
1130 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000157/2023-2024 | 1385/28/Hug | 15/05/2023 | 0 | Resource Division | 0.37 | 0 | 0
1131 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1132 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0
1133 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 80
1134 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 80
1135 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sarbanandapur village under Dhaniakhali Block, Uttar Mogalpur village of Dhnaiakhali Block and Chandpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000986/2023-2024 | 260/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100
1136 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Kedranagar village under Dhaniakhali Block, Acharpara village of Pandua Block and Balarampur village of PAndua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000987/2023-2024 | 261/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100
1137 | Hooghly Division |  | REPAIRING & RENOVATION OF RCC OVERHEAD RESERVOIR AT HEAD WORKS SITE OF BAHADURPUR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. |  |  | ORD/001855/2024-2025 | 234/CH | 19/02/2025 | 10 | B.S. ENTERPRISE | 4.85 | 0 | 0
1138 | Electrical |  | Electric quot. of WBSEDCL for New service Connection of Bahadurpur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18944) |  |  | BILL/01966/2024-2025 | 477 | 01/10/2024 | 0 | WBSEDCL | 5.51 | 0 | 0
1139 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001263/2023-2024 | 4508/ED | 23/11/2023 | 90 | GLACIER ENGINEERING CO. | 21.74 | 16.12 | 35
1140 | Hooghly Division |  | Sinking of 3 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PURBO THAKURANICHAWK , RAJHATO , KAKNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000169/2024-2025 | 3167/HUG | 10/09/2024 | 250 | MONDAL PRECISION PRIVATE LIMITED | 48.47 | 0 | 66
1141 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos |  |  | ORD/002647/2024-2025 | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1142 | Electrical |  | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-I,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994230 Reference Id-503551061. |  |  | BILL/00673/2024-2025 | 200 | 10/06/2024 | 0 | WBSEDCL | 10.68 | 0 | 0
1143 | Electrical |  | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-II,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994235 Reference Id-503551060. |  |  | BILL/00674/2024-2025 | 201 | 10/06/2024 | 0 | WBSEDCL | 10.3 | 0 | 0
1144 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of RAJHATO Piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001266/2023-2024 | 4511/ED | 23/11/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.47 | 20.86 | 30
1145 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of NALDANGA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000036/2023-2024 | 1135/HUG | 19/04/2023 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 14.93 | 11.31 | 100
1146 | Hooghly Division | Chinsuria Sub-Division | Providing 200 nos F.H.T.C. in Benabhauri Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000323/2020-2021 | 395/Hug | 15/02/2021 | 20 | M/S KAMALA ENTERPRISE | 10.45 | 10.22 | 0
1147 | Hooghly Division | Chinsuria Sub-Division | Providing 475 nos F.H.T.C. in KazidangaVillage of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000324/2020-2021 | 396/Hug | 15/02/2021 | 30 | PRADIP KUMAR ADHYA | 24.82 | 23.36 | 0
1148 | Hooghly Division | Chinsuria Sub-Division | Providing 1062nos F.H.T.C. in Akna & Kannagar Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2020-2021 | 397/Hug | 15/02/2021 | 30 | SATYA NARAYAN BISWAS | 54.14 | 50.97 | 0
1149 | Hooghly Division | Chinsuria Sub-Division | Providing 2776 nos F.H.T.C. in Naldanga Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000326/2020-2021 | 455/Hug | 24/02/2021 | 20 | S.K. GHOSH | 144.81 | 45.66 | 0
1150 | Hooghly Division | Chinsuria Sub-Division | Providing 1062nos F.H.T.C. in Akna & Kannagar Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000878/2020-2021 | 397/HUG | 15/02/2021 | 30 | SATYA NARAYAN BISWAS | 17.96 | 17.96 | 0
1151 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000168/2021-2022 | 428/2-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0
1152 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000592/2021-2022 |  | 17/08/2021 | 0 | SATYA NARAYAN BISWAS | 25.49 | 0 | 0
1153 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000845/2021-2022 |  | 21/09/2021 | 0 | M/S KAMALA ENTERPRISE | 7.63 | 0 | 0
1154 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001074/2021-2022 |  | 25/09/2021 | 0 | PRADIP KUMAR ADHYA | 11.12 | 0 | 0
1155 | Hooghly Division | Chinsuria Sub-Division | OHR | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001092/2021-2022 |  | 06/10/2021 | 0 | S.K. GHOSH | 23.55 | 0 | 0
1156 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002107/2021-2022 |  | 28/01/2022 | 0 | S.K. GHOSH | 32 | 0 | 0
1157 | Hooghly Division | Srirampur Sub-Division | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000881/2020-2021 | 1686/Hug. | 17/12/2020 | 40 | S & P ENTERPRISE | 103.59 | 0 | 98
1158 | Hooghly Division | Srirampur Sub-Division | Laying of C.I/D.I pipes & specials for connection of T.W No.-III with distribution system at 3rd TW Site and Laying HDPE pipe for extension of LDS with FHTC & Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement of Panchghara W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2023-2024 | 998/HUG | 05/04/2023 | 727 | MS CHANDIMATA CONSTRUCTION | 77.55 | 41.06 | 50
1159 | Hooghly Division | Srirampur Sub-Division | Providing 500 nos Functional Household Tap Connection (FHTC) at Jaykrishnapur & Panchghora Mouza of Panchghara W/S Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2022-2023 | 718/Hug | 07/04/2022 | 35 | MANISHIKA CONSTRUCTION | 21.8 | 14.38 | 0
1160 | Hooghly Division | Srirampur Sub-Division | Providing 50 nos. Functional Household Tap Connection (FHTC) to the Educational Institutions within the command area of various Water Supply Schemes (Retrofitting Schemes- Baksa, Chikrand, Panchghora & Augmentation Schemes- Chanditala, Janai, Begampur, Kharsarai, Purba Tajpur) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. [Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000315/2021-2022 | 219/SER | 20/12/2021 | 25 | M/S SHIVAM UDYOG | 2.08 | 2.08 | 0
1161 | Hooghly Division | Srirampur Sub-Division | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Panchghora Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000319/2021-2022 | 2308/Hug | 24/12/2021 | 20 | M/S S.G. CONSTRUCTION | 7.01 | 6.9 | 0
1162 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at different mouzas (Joykrishnapur) of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000340/2024-2025 | 638/SER | 05/11/2024 | 7 | MS CHANDIMATA CONSTRUCTION | 4.82 | 0 | 0
1163 | Hooghly Division | Srirampur Sub-Division | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000388/2021-2022 | 294/SER | 21/02/2022 | 45 | BAKSHI ENTERPRISE | 2.99 | 0 | 0
1164 | Hooghly Division | Srirampur Sub-Division | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Panchghora W/S Scheme, Chanditala-II Block under Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000746/2023-2024 | 378/HUG | 08/02/2024 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 35.41 | 29.9 | 80
1165 | Hooghly Division | Srirampur Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PANCHGHORA PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000786/2022-2023 | 879/HUG | 27/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 11.32 | 0
1166 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Panchghora PWSS 2. Chanditala PWSS 3. Madhabpur PWSS 4. Jagannathbati PWSS 5. Purbatajpur PWSS 6. Jangipara PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000942/2023-2024 | 112/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
1167 | Hooghly Division | Srirampur Sub-Division | Laying Rising Main and Protection work at Panchghora Jolapara of Panchghora W/s Scheme Chanditala-II Block under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001563/2024-2025 | 327/HUG | 05/02/2025 | 352 | BIMAL KUMAR HALDER | 31.5 | 0 | 35
1168 | Hooghly Division | Arambug Sub-Division | Providing 50 nos Functional Household Tap Connection (FHTC) within Dihibayra & Maheshpur Village of Dihibayra Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000013/2022-2023 | 714/Hug | 07/04/2022 | 20 | SAKSHI ENTERPRISE | 4.79 | 4.79 | 100
1169 | Hooghly Division | Arambug Sub-Division | Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of DIHI BAYARA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000127/2022-2023 | 439/Arg | 22/06/2022 | 30 | M/S TANISA ENTERPRISE | 4.43 | 0 | 100
1170 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000025/2022-2023 | 1124/6/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0
1171 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000518/2021-2022 |  | 23/07/2021 | 0 | DAS TRADING | 11.53 | 0 | 0
1172 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000840/2021-2022 |  | 21/09/2021 | 0 | DAS TRADING | 6.6 | 0 | 0
1173 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001902/2020-2021 |  | 15/02/2021 | 0 | M/S T.K.B. CONSTRUCTION | 4.8 | 0 | 0
1174 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002254/2020-2021 |  | 15/03/2021 | 0 | JAL PRAVAHIKA PVT. LTD | 32.35 | 0 | 0
1175 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-I), CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000025/2022-2023 | 296/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 3.99 | 100
1176 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-II) CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000125/2022-2023 | 299/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.78 | 100
1177 | Hooghly Division | Chinsuria Sub-Division | Providing 675 nos Functional Household Tap Connection (FHTC) within the command area of Chikrand Zone-II Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000294/2021-2022 | 2205/Hug | 14/12/2021 | 40 | ROY ENTERPRISE | 43.29 | 0 | 100
1178 | Hooghly Division | Chinsuria Sub-Division | Providing 1414 nos F.H.T.C. in Depara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000308/2020-2021 | 384/Hug | 15/02/2021 | 40 | BANBERIA CONSTRUCTION CO. | 73.86 | 105.42 | 100
1179 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000023/2021-2022 |  | 12/04/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 5.98 | 0 | 0
1180 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002287/2020-2021 |  | 15/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 30 | 0 | 0
1181 | Hooghly Division | Arambug Sub-Division | Providing 1102 nos F.H.T.C. in Daulat chak, Khune chak & Chanpanagari Village of Palaspai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000012/2021-2022 | 943/Hug | 06/05/2021 | 40 | DILIP KUMAR GHOSH | 63.84 | 23.44 | 100
1182 | Hooghly Division | Arambug Sub-Division | Providing 1670 nos F.H.T.C. in Narendapur & Palaspai Village of Palapai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000083/2021-2022 | 1149/Hug | 29/06/2021 | 40 | KARALI MOHAN KHAMRUI | 81.69 | 78.4 | 100
1183 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of Internal Pathway of PALASPAI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000452/2024-2025 | 4079/HUG | 19/12/2024 | 90 | TAPAS ADHYA | 26.94 | 0 | 0
1184 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001030/2021-2022 |  | 30/09/2021 | 0 | KARALI MOHAN KHAMRUI | 42.88 | 0 | 0
1185 | Hooghly Division | Chinsuria Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00230/2022-2023 | BP-2022-23-566 | 02/03/2023 | 0 | AATISH KUMAR SHAW | 0.77 | 0 | 0
1186 | Hooghly Division | Chinsuria Sub-Division | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-I) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000465/2021-2022 | 619/CH | 20/12/2021 | 25 | BOSE ENTERPRISE (RATUL BOSE) | 4.16 | 0.86 | 100
1187 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000466/2021-2022 | 620/CH | 20/12/2021 | 40 | BOSE ENTERPRISE (RATUL BOSE) | 2.44 | 2.4 | 100
1188 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000352/2023-2024 | 3004/9/Hug | 05/10/2023 | 0 | Resource Division | 2.86 | 0 | 0
1189 | Electrical | Chinsuria Sub-Division | Fuel Charges Bil | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00736/2022-2023 | 147 | 31/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0
1190 | Electrical | Chinsuria Sub-Division | Hiring Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00737/2022-2023 | 146 | 31/01/2023 | 0 | SUNIL RAJAK | 0.26 | 0 | 0
1191 | Electrical | Chinsuria Sub-Division | Hire Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00738/2022-2023 | 138 | 20/01/2023 | 0 | DILIP KUMAR GHOSH | 0.15 | 0 | 0
1192 | Electrical | Chinsuria Sub-Division | Fuel Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00739/2022-2023 | 137 | 20/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1193 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of S/P/M & other allied works for Rajhat W/S. Sch. Z-I, TW-III Dist-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000063/2022-2023 | 1035/ED | 28/06/2022 | 90 | C.M. ENTERPRISE | 9.45 | 9.4 | 100
1194 | Electrical | Chinsuria Sub-Division | Supply & installation of Automatic Chlorinator at Rajhat water supply scheme, Zone-I, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000597/2022-2023 | 1770/HMSD | 28/09/2022 | 7 | GANGULY ENGINEERING CO. | 0.8 | 0.8 | 100
1195 | Electrical | Chinsuria Sub-Division | Supply & installation of LED board and outside display board for depicting details of Pump/Valve operators at Zone-I & II, P.H. No.-III of Rajhat w/s scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2022-2023 | 2349/HMSD | 20/12/2022 | 10 | INDTECH ASSOCIATES. | 0.84 | 0.84 | 0
1196 | Electrical | Chinsuria Sub-Division | Supply & installation of LED board at Zone-I, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000599/2022-2023 | 2347/HMSD | 20/12/2022 | 10 | DAS ENTERPRISE | 0.79 | 0.79 | 0
1197 | Electrical | Chinsuria Sub-Division | Electric Supply | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001970/2022-2023 | 12 | 08/06/2022 | 0 | WBSEDCL | 7.29 | 0 | 0
1198 | Hooghly Division | Srirampur Sub-Division | Augmentation of Janai Zone-II Water Supply Scheme with Laying Distribution System, Laying Rising Main, Providing FHTC and Construction of 3.6 M X 3.00 M Switch Room, Boundary wall at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000050/2022-2023 | 834/Hug | 20/04/2022 | 90 | M/S S.C CIVIL ENTERPRISE | 146.57 | 111.95 | 65
1199 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JANAI (ZONE-II) 2ND TW SITE AND CHANDITALA PWSS NEAR THERO AREA UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000142/2024-2025 | 428/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.68 | 1.33 | 95
1200 | Hooghly Division | Srirampur Sub-Division | Augmentation of Janai Zone-I Water Supply Scheme with Construction of 450 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work including Laying Distribution System, Rising Main, FHTC, of existing Switch Room, Boundary Wall & at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000191/2022-2023 | 868//hug | 27/04/2022 | 300 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 378.23 | 343.15 | 100
1201 | Hooghly Division | Srirampur Sub-Division | Extension of Laying Distribution System for proposed Augemntation of JANAI Zone-I & II Water Supply Scheme Under Serampore Sub-Division under Hooghly Division,P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000231/2023-2024 | 2064/HUG | 17/07/2023 | 90 | M/S SHIVAM UDYOG | 41.09 | 39.68 | 99
1202 | Hooghly Division | Srirampur Sub-Division | Construction of switch-room & boundary wall, Rising Main for inter connection between T.W & Distribution, for AUGMENTATION of JANAI Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000240/2024-2025 | 3475/HUG | 04/10/2024 | 60 | SUNITI MAIRA | 11.75 | 0 | 0
1203 | Hooghly Division | Srirampur Sub-Division | Sinking of 2 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 5th Tube Well Site of BILASPUR W/S Scheme & 3rd Tube Well Site of JANAI W/S Scheme(ZONE-I) under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000252/2024-2025 | 3523/HUG | 22/10/2024 | 102 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 29.4 | 0 | 50
1204 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Janai (Zone-I) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000398/2021-2022 | 302/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.59 | 2.59 | 100
1205 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Janai (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000399/2021-2022 | 303/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 1.77 | 1.62 | 100
1206 | Hooghly Division | Srirampur Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JANAI ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000452/2022-2023 | 2502/HUG | 22/11/2022 | 30 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 10.95 | 10.2 | 0
1207 | Hooghly Division | Srirampur Sub-Division | Withdrawing and relaying of rising mainwith left out Functional Hosuehold Tap Connection at Janai Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000470/2024-2025 | 4050/HUG | 19/12/2024 | 45 | M/S SHIVAM UDYOG | 13.85 | 0 | 5
1208 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kapasharia PWSS 2. Janai PWSS 3. Begampur PWSS 4. Baksa PWSS 5. Chikrand PWSS 6. Kharsarai PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000941/2023-2024 | 111/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
1209 | Hooghly Division | Srirampur Sub-Division | Additional works for laying of water supply pipeline by HDD process and Protection of Pipe Line along Pond embankment and road side at Zone II of JANAI Water Supply Scheme under Serampore SubDivision, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001558/2023-2024 | 744/HUG | 05/03/2024 | 514 | M/S S & P CONSTRUCTION | 45.19 | 0 | 60
1210 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000007/2022-2023 | 1122/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
1211 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000035/2022-2023 | 1291/3/Hug | 24/06/2022 | 0 | Resource Division | 6.16 | 0 | 0
1212 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000044/2022-2023 | 1369/Hug | 06/07/2022 | 0 | Resource Division | 15.6 | 0 | 0
1213 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000059/2022-2023 | 1689/3/HUG | 22/08/2022 | 0 | Resource Division | 19.89 | 0 | 0
1214 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000123/2022-2023 | 2210/2/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
1215 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000157/2021-2022 | 422/2/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0
1216 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000321/2023-2024 | 1384/18/Hug | 15/05/2023 | 0 | Resource Division | 9.36 | 0 | 0
1217 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Janai w/s scheme, Zone- II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004099413 Reference ID- 503611354 SM Code- 09695 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00159/2024-2025 | 71 | 16/04/2024 | 0 | WBSEDCL | 4.56 | 0 | 0
1218 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Janai W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00537/2022-2023 | 131 | 16/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0
1219 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Janai water supply scheme, T.W. No.- I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000102/2022-2023 | 648/ED | 02/02/2023 | 90 | M/S BABUSONA ENTERPRISE | 10.74 | 10.47 | 100
1220 | Hooghly Division | Arambug Sub-Division | Providing 450 nos Functional Household Tap Connection (FHTC) within the command area of Harischak Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000247/2021-2022 | 1998/Hug | 12/11/2021 | 30 | M/S SHIVAM UDYOG | 20.68 | 15.86 | 0
1221 | Hooghly Division | Arambug Sub-Division | Providing 114 nos FHTC for different mouzas under Harishchak PWSS under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000501/2021-2022 | 524/ARG | 30/11/2021 | 45 | MAA JAGADHATRI CONSTRUCTION | 4.74 | 4.74 | 0
1222 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001894/2020-2021 |  | 15/02/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 77 | 0 | 0
1223 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT HARIPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000138/2024-2025 | 426/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 95
1224 | Hooghly Division | Srirampur Sub-Division | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 283.99 | 9
1225 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000507/2023-2024 | 3060/13/Hug | 11/10/2023 | 0 | Resource Division | 12.5 | 0 | 0
1226 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Haripur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 100000123497 Reference ID- 860318447 SM Code- 12250 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02303/2024-2025 | BP-24-25-597 | 21/11/2024 | 0 | WBSEDCL | 2.22 | 0 | 0
1227 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04443/2023-2024 | 501 | 08/12/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
1228 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04444/2023-2024 | 508 | 08/12/2023 | 0 | WBSEDCL | 9.7 | 0 | 0
1229 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000147/2022-2023 | 3490/ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 9.82 | 49
1230 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000192/2022-2023 | 785/ED | 09/02/2023 | 90 | SRI KRISHNA NIRMAN | 20.26 | 14.03 | 65
1231 | Hooghly Division | Chinsuria Sub-Division | Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00685/2023-2024 | BP-2023-24-529 | 17/10/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 12 | 0 | 0
1232 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 436.06 | 15
1233 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000109/2023-2024 | 1264/4/HUG | 03/05/2023 | 0 | Resource Division | 17.97 | 0 | 0
1234 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000262/2023-2024 | 1386/41/Hug | 15/05/2023 | 0 | Resource Division | 19.37 | 0 | 0
1235 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000516/2023-2024 | 3059/41/Hug | 11/10/2023 | 0 | Resource Division | 19.37 | 0 | 0
1236 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hasnan W/S Sch., T/W No. - I, Block - Polba-Dadpur, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03712/2023-2024 | 255 | 05/09/2023 | 0 | WBSEDCL | 12.17 | 0 | 0
1237 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hasnan W/S Sch. , T/W No - II, Block- Polba-Dadpur, Dist - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03713/2023-2024 | 254 | 05/09/2023 | 0 | WBSEDCL | 4.01 | 0 | 0
1238 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000084/2022-2023 | 3466/ED | 30/12/2022 | 90 | T.N. BANERJEE | 21.6 | 0 | 0
1239 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002464/2023-2024 | 325/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
1240 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 292.8 | 30
1241 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000121/2023-2024 | 1264/16/HUG | 03/05/2023 | 0 | Resource Division | 19.93 | 0 | 0
1242 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000486/2023-2024 | 3059/21/Hug | 11/10/2023 | 0 | Resource Division | 1.74 | 0 | 0
1243 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05321/2023-2024 | 696 | 22/01/2024 | 0 | WBSEDCL | 6.37 | 0 | 0
1244 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05334/2023-2024 | 697 | 22/01/2024 | 0 | WBSEDCL | 5.91 | 0 | 0
1245 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Simla water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000120/2022-2023 | 3476/ED | 30/12/2022 | 1678 | A.S. ENTERPRISE | 21.42 | 0 | 45
1246 | Hooghly Division | Chandannagar Sub-Division | Damages of Road from Dewanbheri to Paunan | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00503/2023-2024 | BP-2023-24-415 | 29/09/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 15.81 | 0 | 0
1247 | Hooghly Division | Chandannagar Sub-Division | RESTORATION OF DAMAGES ROAD NAMELY DEWANBHERI TO PAWNAN PART OF DEWANBHERI KACHARIMORE TO BILATPUR BRIDGE VIDE PACKAGE NO. WB-08-ADB-172 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01560/2023-2024 | BP-2023-24-887 | 04/03/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 14.63 | 0 | 0
1248 | Hooghly Division | Chandannagar Sub-Division | GOPALNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000053/2023-2024 | 1211/HUG | 27/04/2023 | 1070 | S. HATI | 499.95 | 262.58 | 90
1249 | Hooghly Division | Chandannagar Sub-Division | Route survey Design drawing & DPR preparation of Gopalnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000167/2022-2023 | 262/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.11 | 0
1250 | Hooghly Division | Chandannagar Sub-Division | Sinking of Three Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at GOPALNAGAR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000456/2022-2023 | 2507/HUG | 22/11/2022 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 36.31 | 34.06 | 0
1251 | Hooghly Division | Chandannagar Sub-Division | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room, Boundary wall & FHTC For Augmentation of GOPALNAGAR Piped Water Supply Scheme under SINGUR Block under Chandannagar Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000801/2022-2023 | 952/HUG | 30/03/2023 | 855 | LOKENIRMAN | 246.68 | 215.88 | 85
1252 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000147/2022-2023 | 2686/14/Hug | 01/12/2022 | 0 | Resource Division | 0.36 | 0 | 0
1253 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000155/2022-2023 | 01/06/Hug | 02/01/2023 | 0 | Resource Division | 28.33 | 0 | 0
1254 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000188/2022-2023 | 79/13/Hug | 06/01/2023 | 0 | Resource Division | 134.26 | 0 | 0
1255 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000266/2022-2023 | 902/3/Hug | 27/03/2023 | 0 | Resource Division | 28.33 | 0 | 0
1256 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000281/2023-2024 | 1383/30/Hug | 15/05/2023 | 0 | Resource Division | 28.33 | 0 | 0
1257 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Gopalnagar W/S sch. , T/W - II, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00736/2023-2024 | 23 | 11/05/2023 | 0 | WBSEDCL | 2.53 | 0 | 0
1258 | Electrical | Chandannagar Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT GOPALNAGAR W/S SCH. , T/W NO. - IV, DIST. - HOOGHLY | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00737/2023-2024 | 25 | 11/05/2023 | 0 | WBSEDCL | 4.09 | 0 | 0
1259 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01453/2022-2023 | 211 | 24/03/2023 | 0 | WBSEDCL | 0.7 | 0 | 0
1260 | Electrical | Chandannagar Sub-Division | Revised Quotation New service connection at Gopalnagar W/S Sch. , T/W No. - IV, Block - Singur, due to non payment of previous quotation for online banking transaction error. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04056/2023-2024 |  | 06/10/2023 | 0 | WBSEDCL | 4.09 | 0 | 0
1261 | Electrical | Chandannagar Sub-Division | Revised Quotation Bill for New Service Connection at Gopal Nagar W/S. Sch. TW-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04070/2023-2024 | 338 | 10/10/2023 | 0 | WBSEDCL | 0 | 0 | 0
1262 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gopalnagar water supply scheme, T.W. No.- I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000211/2022-2023 | 838/ED | 14/02/2023 | 791 | WEST BENGAL ENGINEERING CO. | 32.24 | 31.4 | 90
1263 | Hooghly Division | Chinsuria Sub-Division | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 275.85 | 20
1264 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000323/2023-2024 | 2407/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 26.42 | 40
1265 | Hooghly Division | Chinsuria Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & DistributionSystem ,Construction of switch-rooms & boundary walls at different TW site for Bishnupur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000330/2023-2024 | 2415/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 54.65 | 8.62 | 30
1266 | Hooghly Division | Chinsuria Sub-Division | Construction of Store room for temporary Chlorine and maintenance material storage For Dasghara Zone-I, Bishnupur and Shrirampur Piped Water Supply under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001034/2023-2024 | 277/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.95 | 0.95 | 100
1267 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000269/2023-2024 | 1386/48/Hug | 15/05/2023 | 0 | Resource Division | 19.19 | 0 | 0
1268 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000525/2023-2024 | 3059/36/Hug | 11/10/2023 | 0 | Resource Division | 19.19 | 0 | 0
1269 | Electrical | Chinsuria Sub-Division | Bishnupur PH__I Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05986/2023-2024 | 723 | 05/02/2024 | 0 | WBSEDCL | 7.9 | 0 | 0
1270 | Electrical | Chinsuria Sub-Division | Quotation of New service Connection Charge for Bishnupur w/s Scheme,TW No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12263) Application no-5003995286 Reference Id-503552526 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06105/2023-2024 | 762 | 16/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
1271 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000131/2022-2023 | 3485/ED | 30/12/2022 | 90 | C.M.S. ENGINEERING CONCERN | 22.86 | 20.79 | 45
1272 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 369.63 | 50
1273 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
1274 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000083/2023-2024 | 1234/42/Hug | 28/04/2023 | 0 | Resource Division | 48.75 | 0 | 0
1275 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000140/2023-2024 | 1385/11/Hug | 15/05/2023 | 0 | Resource Division | 15.88 | 0 | 0
1276 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000402/2023-2024 | 3057/50/Hug | 11/10/2023 | 0 | Resource Division | 15.88 | 0 | 0
1277 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987362 Reference Id-503547192 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06057/2023-2024 | 760 | 16/02/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
1278 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987354 Reference Id-503547191 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06058/2023-2024 | 758 | 16/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
1279 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ROUTHKHANA PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000149/2024-2025 | 1172/ED | 14/06/2024 | 90 | BINAPANI ENTERPRISE | 10.64 | 0 | 0
1280 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Routhkhana water supply scheme, T.W. No.- I & II, Block: Khanakul-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000169/2022-2023 | 3502/ED | 30/12/2022 | 90 | BINAPANI ENTERPRISE | 21.48 | 0 | 0
1281 | Hooghly Division | Srirampur Sub-Division | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 164.38 | 9
1282 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | RTOR000480/2023-2024 | 3060/17/Hug | 11/10/2023 | 0 | Resource Division | 13.96 | 0 | 0
1283 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Nababpur PWSS P.H. No.-I, Hooghly. Application No. 5004064466 Ref ID: 503597309 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/00035/2024-2025 | 21 | 05/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
1284 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Nababpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004064410 Reference ID- 503597307 SM Code- 12239 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/02122/2024-2025 | 560 | 11/11/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
1285 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000164/2022-2023 | 3498/ED | 30/12/2022 | 90 | ANJAN ENTERPRISE | 21.33 | 7.7 | 30
1286 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000193/2022-2023 | 786/ED | 09/02/2023 | 727 | M/S P.P. ELECTRICALS | 22.36 | 0 | 50
1287 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 31.22 | 100
1288 | Hooghly Division | Chandannagar Sub-Division | Providing 48 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000230/2025-2026 | 880/CHAN | 21/07/2025 | 20 | SWASTIK ENTERPRISE | 3.93 | 0 | 0
1289 | Hooghly Division | Chandannagar Sub-Division | Providing 47 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -I] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000261/2025-2026 | 879/CHAN | 21/07/2025 | 20 | KALYAN BANERJEE | 3.89 | 0 | 0
1290 | Hooghly Division | Chandannagar Sub-Division | Providing 48 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -III] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000262/2025-2026 | 909/CHAN | 21/07/2025 | 20 | RITAM ENTERPRISE | 3.93 | 0 | 0
1291 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for ASTARA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000353/2023-2024 | 2445/HUG | 12/08/2023 | 60 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 44.85 | 16.42 | 100
1292 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Astara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000408/2022-2023 | 510/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.07 | 4.07 | 0
1293 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of ASTARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000751/2022-2023 | 652/Hug | 10/03/2023 | 60 | APEX ENGINEERING | 12.25 | 12.25 | 100
1294 | Hooghly Division | Chandannagar Sub-Division | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.94 | 100
1295 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Astara PWSS, Baligori Z-I PWSS, Baligori Z-II PWSS, Talpur PWSS, Kulteghori PWSS, Santoshpur PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000980/2023-2024 | 308/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
1296 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000131/2022-2023 | 2471/2/Hug | 18/11/2022 | 0 | Resource Division | 12.06 | 0 | 0
1297 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000159/2022-2023 | 01/05/Hug | 02/01/2023 | 0 | Resource Division | 12.06 | 0 | 0
1298 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000216/2022-2023 | 109/ 22/Hug | 10/01/2023 | 0 | Resource Division | 27.67 | 0 | 0
1299 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000286/2023-2024 | 1383/32/Hug | 15/05/2023 | 0 | Resource Division | 12.27 | 0 | 0
1300 | Electrical | Chandannagar Sub-Division | Astara w/s scheme,P H No-1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03938/2023-2024 | 313 | 27/09/2023 | 0 | WBSEDCL | 5.81 | 0 | 0
1301 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for ASTARA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004031983 Ref. ID- 503573554 SM/11286 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06196/2023-2024 | 804 | 27/02/2024 | 0 | WBSEDCL | 6.23 | 0 | 0
1302 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Astara water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000075/2022-2023 | 3457/ED | 30/12/2022 | 90 | S S ENTERPRISES | 23.02 | 22.95 | 95
1303 | Hooghly Division | Chandannagar Sub-Division | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in PANRRA Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000001/2023-2024 | 988/Hug | 04/04/2023 | 300 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 611.8 | 281.67 | 80
1304 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 32.25 | 100
1305 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Panrra PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000412/2022-2023 | 514/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 6.22 | 6.22 | 0
1306 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach road at Panrra W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000759/2023-2024 | 451/HUG | 15/02/2024 | 30 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 20.55 | 0 | 0
1307 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000201/2022-2023 | 109/ 16/Hug | 10/01/2023 | 0 | Resource Division | 80.63 | 0 | 0
1308 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000208/2023-2024 | 1383/11/Hug | 15/05/2023 | 0 | Resource Division | 18.47 | 0 | 0
1309 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000408/2023-2024 | 3058/35/Hug | 11/10/2023 | 0 | Resource Division | 18.14 | 0 | 0
1310 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection Charge for Pannra w/S Scheme,TW No-II, Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03766/2023-2024 | 258 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
1311 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection at Pantra W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04613/2023-2024 | 612 | 14/03/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
1312 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Panrra water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000090/2022-2023 | 3472/ED | 30/12/2022 | 90 | SANKAR PRASAD DUTTA & CO. | 23 | 20.88 | 30
1313 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00298/2023-2024 | BP-2023-24-249 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.81 | 0 | 0
1314 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000166/2023-2024 | 1385/37/Hug | 15/05/2023 | 0 | Resource Division | 0.6 | 0 | 0
1315 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1316 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000030/2023-2024 | 1130/HUG | 19/04/2023 | 45 | BAKSHI ENTERPRISE | 40.32 | 17.24 | 30
1317 | Hooghly Division | Chinsuria Sub-Division | Providing 1400 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000553/2021-2022 | 1681/HUG | 13/09/2021 | 40 | BIMAL KUMAR HALDER | 55 | 22.79 | 0
1318 | Hooghly Division | Chinsuria Sub-Division | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000554/2021-2022 | 2201/HUG | 14/12/2021 | 30 | SARKAR CONSTRUCTION | 18.07 | 17.21 | 0
1319 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00353/2023-2024 | BP-2023-24-292 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.11 | 0 | 0
1320 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1321 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
1322 | Hooghly Division | Arambug Sub-Division | Requisition for Sajal Gram | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00093/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 23.35 | 0 | 0
1323 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00213/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 25.95 | 0 | 0
1324 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00410/2023-2024 | BP-2023-24-335 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 25.08 | 0 | 0
1325 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000165/2023-2024 | 1385/36/Hug | 15/05/2023 | 0 | Resource Division | 0.12 | 0 | 0
1326 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1327 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00084/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.28 | 0 | 0
1328 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00215/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.42 | 0 | 0
1329 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00412/2023-2024 | BP-2023-24-337 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.06 | 0 | 0
1330 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000158/2023-2024 | 1385/29/Hug | 15/05/2023 | 0 | Resource Division | 0.45 | 0 | 0
1331 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1332 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000007/2025-2026 | 489/CH | 04/04/2025 | 10 | DAS ENTERPRISE (SAMIR DAS) | 4.51 | 0 | 0
1333 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DIGSUI HEORAH PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte... | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000032/2023-2024 | 1132/HUG | 19/04/2023 | 30 | RANA ENTERPRISE | 32.74 | 24.55 | 80
1334 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of DIGSUI HOERA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000085/2023-2024 | 1339/HUG | 11/05/2023 | 30 | MAA JAGADHATRI CONSTRUCTION | 23.6 | 13.75 | 83
1335 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000255/2022-2023 | 722/CH | 23/08/2022 | 45 | SWARNA ENTERPRISE | 4.98 | 4.97 | 0
1336 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000267/2022-2023 | 723/CH | 23/08/2022 | 45 | SUDIPTA DAS | 4.98 | 4.93 | 100
1337 | Hooghly Division | Chinsuria Sub-Division | Emergency Repairing & Replacing Different dia distribution pipeline and necessary allied Works At Digsui Hoera Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000730/2023-2024 | 19/CH | 04/01/2024 | 15 | MAA BUNAMATA ENTERPRISE | 2.1 | 2.09 | 55
1338 | Hooghly Division | Chinsuria Sub-Division | Additional Laying of HDPE pipeline and interconnection work in distibution system of Digsui Heora Zone-I and Zone-II Water Supply Scheme for providing left over FHTC under Chinsurah Sub- Division, Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000790/2023-2024 | 535/HUG | 20/02/2024 | 15 | MAA JAGADHATRI CONSTRUCTION | 16.41 | 16.19 | 25
1339 | Hooghly Division | Chinsuria Sub-Division | Shifting of distribution pipeline for widening of G.T. Roadfrom Naksa mouza to Hoera mouza of Digsui Hoera GP of Digsui Hoera Zone -I & Zone -II Water Supply Scheme under Chinsurah sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001834/2024-2025 | 332/HUG | 05/02/2025 | 60 | SAMRAT CONSTRUCTION | 27.36 | 0 | 25
1340 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002012/2024-2025 | 300/CH | 20/02/2025 | 10 | DAS ENTERPRISE (SAMIR DAS) | 2.06 | 0 | 0
1341 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000375/2023-2024 | 3004/6/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0
1342 | Electrical | Chinsuria Sub-Division | New Connection of Digsui Heora W/S. Sch. Z-I, PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00002/2022-2023 | BP-2022-23-110 | 01/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.91 | 0 | 0
1343 | Electrical | Chinsuria Sub-Division | Quotation bill for New Connection of WBSEDCL at Digsui Heora W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00774/2022-2023 | 127 | 17/01/2023 | 0 | WBSEDCL | 3.83 | 0 | 0
1344 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical Mechanical equipments etc. with allied works for Digsui- Heora W/S. Sch. TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000241/2022-2023 | 1538/ED | 19/09/2022 | 90 | SRI KRISHNA NIRMAN | 8.93 | 8.88 | 100
1345 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Digsui Heora water supply scheme, Zone-II, T.W. No.- III, Block: Chinsurah Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001366/2022-2023 | 1917/ED | 21/11/2022 | 90 | M/S S.R. ENTERPRISE | 9.41 | 9.41 | 100
1346 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. with effect from 01.04.2023 to 31.08.2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001367/2022-2023 | 203/AE-I/ED | 27/03/2023 | 153 | DASHRATH KUMAR PRAJAPATI | 0.73 | 0.39 | 5
1347 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of sautomatic chlorinatorfor Digsui Heora W/S. Sch. Z-I, TW-III Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002560/2022-2023 | 69/HMSD | 10/01/2023 | 7 | SRI KRISHNA NIRMAN | 0.8 | 0.8 | 100
1348 | Electrical | Chinsuria Sub-Division | Digsui Heora W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002738/2022-2023 |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 21.72 | 0 | 0
1349 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 357.32 | 50
1350 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
1351 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/002746/2024-2025 | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1352 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | RTOR000085/2023-2024 | 1263/Hug | 03/05/2023 | 0 | Resource Division | 14.29 | 0 | 0
1353 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | RTOR000485/2023-2024 | 3057/62/Hug | 11/10/2023 | 0 | Resource Division | 14.29 | 0 | 0
1354 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004026546 Reference Id-503570690 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/00429/2024-2025 | 110 | 09/05/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
1355 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004073228 Reference Id-503597246 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/00441/2024-2025 | 125 | 17/05/2024 | 0 | WBSEDCL | 8.29 | 0 | 0
1356 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation DUBIR BHERI Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000078/2024-2025 | 693/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.5 | 0 | 0
1357 | Hooghly Division | Chinsuria Sub-Division | Source Augmentation of DUBIRBHERI Piped Water Supply Scheme by Sinking 2 Nos. Tube well , Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Repairing of Switch Room & Boundary Wall and other allied work to meet up the water demand, due to execution of FHTC under Hooghly Division P.H.E. Dte. within Polba Dadpur Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000687/2022-2023 | 282/HUG | 01/02/2023 | 732 | BIMAL KUMAR HALDER | 150.96 | 47.03 | 95
1358 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Dubir Bheri PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000802/2023-2024 | 145/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 50
1359 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dubir Bheri W/S Sch.(Aug.) , T/W no. - I, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02846/2023-2024 | 193 | 17/08/2023 | 0 | WBSEDCL | 10.34 | 0 | 0
1360 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dubir Bheri W/S Sch(Aug.)., T/W No. - II, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02847/2023-2024 | 194 | 17/08/2023 | 0 | WBSEDCL | 8.98 | 0 | 0
1361 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dubir Bheri water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000207/2022-2023 | 834/ED | 14/02/2023 | 450 | BARISAL TRADING CO. | 21.49 | 21.18 | 90
1362 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BATIKA-BAINCHI GP of PANDUA Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000922/2023-2024 | 242/CH | 12/03/2024 | 30 | RAJMAHAL ENTERPRISE | 4.99 | 4.81 | 90
1363 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000364/2023-2024 | 3004/15/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0
1364 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-V | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/04498/2023-2024 | 544 | 19/12/2023 | 0 | WBSEDCL | 36.89 | 0 | 0
1365 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/04499/2023-2024 | 545 | 19/12/2023 | 0 | WBSEDCL | 3.53 | 0 | 0
1366 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baichi water supply scheme, T.W. No.- I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000196/2022-2023 | 823/ED | 14/02/2023 | 90 | SRI KRISHNA NIRMAN | 21.49 | 20.94 | 90
1367 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00360/2023-2024 | BP-2023-24-300 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.33 | 0 | 0
1368 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1369 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
1370 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00293/2023-2024 | BP-2023-24-244 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.39 | 0 | 0
1371 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000196/2023-2024 | 1385/67/Hug | 15/05/2023 | 0 | Resource Division | 0.41 | 0 | 0
1372 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1373 | Hooghly Division | Arambug Sub-Division | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000252/2023-2024 | 2147/HUG | 24/07/2023 | 90 | GHOSH BROTHERS | 215.95 | 0 | 0
1374 | Hooghly Division | Arambug Sub-Division | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly[AUGMENTATION SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000322/2023-2024 | 2413/HUG | 11/08/2023 | 599 | GHOSH BROTHERS | 215.95 | 0 | 65
1375 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at CHILADANGI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000770/2022-2023 | 741/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 0 | 0
1376 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000144/2023-2024 | 1385/16/Hug | 15/05/2023 | 0 | Resource Division | 0.31 | 0 | 0
1377 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chiladangi water supply scheme, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001146/2022-2023 | 1498/ED | 28/03/2023 | 90 | DAS ENTERPRISE | 10.73 | 0 | 0
1378 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chiladangi water supply scheme, T.W. No. II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001531/2021-2022 | 3004_ED | 29/12/2021 | 90 | A.G. ENTERPRISE | 10.52 | 0 | 0
1379 | Hooghly Division | Chandannagar Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at BAMONJOL PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-16] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000049/2023-2024 | 1201/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.03 | 0
1380 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000542/2021-2022 |  | 23/07/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 18.51 | 0 | 0
1381 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for BHASTARA Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-DHANIAKHALI]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000077/2024-2025 | 692/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.5 | 0 | 0
1382 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BHASTARA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000601/2023-2024 | 3316/HUG | 10/11/2023 | 45 | SUDIPTA DAS | 8.59 | 7.11 | 95
1383 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 65
1384 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Digra Arsenic PWSS 2. Charsundalpur Arsenic PWSS 3. Asanpur Arsenic PWSS 4. Polba (Retrofit) PWSS 5. Baastara PWSS 6. Bakulia PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000833/2023-2024 | 211/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 45
1385 | Hooghly Division | Chinsuria Sub-Division | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF BHASTARA WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001464/2024-2025 | 128/CH | 29/01/2025 | 10 | M/S B N ENTERPRISE | 4.12 | 0 | 0
1386 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BHASTARA GP of DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. (Phase-II) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002018/2024-2025 | 315/CH | 21/02/2025 | 15 | JOY GURU ENTERPRISE | 3.4 | 0 | 0
1387 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000358/2023-2024 | 3004/17/Hug | 05/10/2023 | 0 | Resource Division | 35.98 | 0 | 0
1388 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-4 Bhastara pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04471/2023-2024 | 522 | 12/12/2023 | 0 | WBSEDCL | 3.73 | 0 | 0
1389 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-3 Bhastara pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04472/2023-2024 | 521 | 12/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0
1390 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhastara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000014/2023-2024 | 1630/ED | 11/04/2023 | 90 | M.S ENTERPRISE | 22.83 | 11.11 | 50
1391 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 2.48 | 59
1392 | Hooghly Division | Hooghly Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0
1393 | Hooghly Division | Hooghly Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 220.57 | 30
1394 | Hooghly Division | Hooghly Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0
1395 | Hooghly Division | Hooghly Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
1396 | Hooghly Division | Hooghly Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | RTOR000056/2023-2024 | 1234/26/Hug | 28/04/2023 | 0 | Resource Division | 51.53 | 0 | 0
1397 | Hooghly Division | Hooghly Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | RTOR000389/2023-2024 | 3057/57/Hug | 11/10/2023 | 0 | Resource Division | 17.57 | 0 | 0
1398 | Electrical | Hooghly Division | Quotation of New Service Connection for Samanta Khanda w/s Scheme, PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/16127) Application No-5004034170 Reference Id-503574968 | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | BILL/06199/2023-2024 | 814 | 28/02/2024 | 0 | WBSEDCL | 4.75 | 0 | 0
1399 | Electrical | Hooghly Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAMANTA KHANDA PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000137/2024-2025 | 1163/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0
1400 | Electrical | Hooghly Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanta Khanda water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000311/2022-2023 | 1241/ED | 06/03/2023 | 90 | R.M.D TRADING. | 22.84 | 0 | 0
1401 | Hooghly Division | Chandannagar Sub-Division | SIBRAMBATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000800/2022-2023 | 937/HUG | 29/03/2023 | 270 | M/S R.M. CONSTRUCTION | 311.17 | 247.04 | 100
1402 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000058/2023-2024 | 1235/7/Hug | 28/04/2023 | 0 | Resource Division | 3.7 | 0 | 0
1403 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000547/2023-2024 | 3058/21/Hug | 11/10/2023 | 0 | Resource Division | 7.76 | 0 | 0
1404 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati W/s Sch. Zone - II, T/W No. - III,[SM/15888], under Singur CCC, WBSEDCL, Ref. Id. - 503666629, Dt. - 18-06-2024, Application No. - 5004236084 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00851/2024-2025 | 247 | 24/06/2024 | 0 | WBSEDCL | 9.51 | 0 | 0
1405 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Sibrambati W/S. Sch.TW-I, Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04132/2023-2024 | 378 | 25/10/2023 | 0 | WBSEDCL | 5.8 | 0 | 0
1406 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Shibrambati W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04457/2023-2024 | 520 | 11/12/2023 | 0 | WBSEDCL | 4.42 | 0 | 0
1407 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibrambati water supply scheme, Zone-II, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002479/2023-2024 | 339/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 0 | 90
1408 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KISHORPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000108/2023-2024 | 1428/HUG | 17/05/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 11.28 | 99
1409 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of KISHORPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000488/2024-2025 | 4152/HUG | 26/12/2024 | 90 | MS PRADIP KUMAR PAL | 17.87 | 0 | 0
1410 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000094/2023-2024 | 1263/9/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0
1411 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Kishorepur W/S. Sch. PH-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04922/2023-2024 | 675 | 18/01/2024 | 0 | WBSEDCL | 4.48 | 0 | 0
1412 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kishorpur water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000001/2023-2024 | 1617/ED | 11/04/2023 | 751 | M/S G P ENTERPRISE | 10.74 | 7.95 | 20
1413 | Electrical | Arambug Sub-Division | Emergency replacement of burnt submersible pump-motor set by newly supplied pump-motor set, rewinding of the burnt submersible motor, replacement of voltage corrector and related works at Kishorpur w/s scheme, P.H No-I, Dist- Hooghly. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000319/2022-2023 | 495/HMSD | 02/03/2023 | 30 | SOMNATH ENTERPRISE | 3.58 | 3.32 | 100
1414 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 0 | 70
1415 | Hooghly Division | Arambug Sub-Division | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of GOBINDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000338/2021-2022 | 15/Hug | 04/01/2022 | 30 | SWASTIK ENTERPRISE | 14.91 | 14.8 | 0
1416 | Hooghly Division | Arambug Sub-Division | Renovation Work of R.C.C. Elevated Reservoir of GOBINDAPUR PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000681/2025-2026 | 2370/HUG | 10/09/2025 | 90 | M/S BIMAL DAS AND CO. | 10.05 | 0 | 0
1417 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000171/2023-2024 | 1385/42/Hug | 15/05/2023 | 0 | Resource Division | 1.39 | 0 | 0
1418 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Gobindopur W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/04319/2023-2024 | 427 | 17/11/2023 | 0 | WBSEDCL | 4.41 | 0 | 0
1419 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No. II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002487/2023-2024 | 138/ED | 16/01/2024 | 90 | MUKHERJEE ART CENTRE | 10.7 | 0 | 0
1420 | Hooghly Division | Arambug Sub-Division | BHALIA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] [2nd Call of WBPHE/EE/53/HUG/2022-23(Sl No. 2)] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000241/2023-2024 | 2079/HUG | 18/07/2023 | 898 | PRASUN ENTERPRISE (PRASUN BISWAS) | 496.11 | 93.78 | 30
1421 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000031/2023-2024 | 1234/12/Hug | 28/04/2023 | 0 | Resource Division | 43.14 | 0 | 0
1422 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000178/2023-2024 | 1385/49/Hug | 15/05/2023 | 0 | Resource Division | 13.46 | 0 | 0
1423 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000456/2023-2024 | 3057/22/Hug | 11/10/2023 | 0 | Resource Division | 13.46 | 0 | 0
1424 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connectio at Bhalia W/S. Sch. Z-I, TW-IV | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04161/2023-2024 | 396 | 06/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
1425 | Electrical | Arambug Sub-Division | "Quotation Bill for New Service Connection at Bhalia W/S. Sch. Z-I" | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04164/2023-2024 | 401 | 09/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
1426 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-I) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000009/2023-2024 | 1625/ED | 11/04/2023 | 90 | C.M.S. ENGINEERING CONCERN | 22.04 | 22.02 | 30
1427 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHALIA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000188/2024-2025 | 1204/ED | 14/06/2024 | 90 | C.M.S. ENGINEERING CONCERN | 10.95 | 0 | 0
1428 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ARANDI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000116/2023-2024 | 1445/HUG | 18/05/2023 | 675 | SAKSHI ENTERPRISE | 11.81 | 0 | 40
1429 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000224/2024-2025 | 3435/HUG | 03/10/2024 | 90 | T.K. INTERNATIONAL | 47.2 | 0 | 0
1430 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site at ARANDI , BATANOL Zone-I , GOPALBATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000426/2024-2025 | 3667/HUG | 13/11/2024 | 45 | DEV AND COMPANY | 31.66 | 0 | 0
1431 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ARANDI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000451/2024-2025 | 4080/HUG | 19/12/2024 | 90 | SRI KRISHNA ENTERPRISE | 17.15 | 0 | 0
1432 | Hooghly Division | Arambug Sub-Division | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-A) [Block-Arambagh] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001479/2023-2024 | 287/Arg | 14/03/2024 | 15 | TITAS CONSTRUCTION | 0.96 | 0 | 0
1433 | Hooghly Division | Arambug Sub-Division | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-B) [Block-Arambagh] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001480/2023-2024 | 288/Arg | 14/03/2024 | 15 | TITAS CONSTRUCTION | 0.84 | 0 | 0
1434 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARANDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000366/2024-2025 | 1450/ED | 25/07/2024 | 90 | MOITRA ENGINEERING CO. | 11.08 | 0 | 0
1435 | Hooghly Division | Chinsuria Sub-Division | RAJHAT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000240/2023-2024 | 2078/HUG | 18/07/2023 | 741 | TAPAS ADHYA | 118.43 | 97.58 | 80
1436 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000263/2023-2024 | 1386/42/Hug | 15/05/2023 | 0 | Resource Division | 2.94 | 0 | 0
1437 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000361/2023-2024 | 3004/14/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0
1438 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000504/2023-2024 | 3059/15/Hug | 11/10/2023 | 0 | Resource Division | 2.94 | 0 | 0
1439 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Rajhat(Uncovered)[Rajhat Uttar] W/S Sch.[SM/18095], T/W No. - I, Mahashay Para, Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599474, Dt. - 22-03-2024, Application No. - 5004078306 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00013/2024-2025 | 16 | 04/04/2024 | 0 | WBSEDCL | 11.27 | 0 | 0
1440 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rajhat Dakshinpara W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04458/2023-2024 | 519 | 11/12/2023 | 0 | WBSEDCL | 10.03 | 0 | 0
1441 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rajhat (for uncovered area) water supply scheme, T.W. No. I, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000074/2023-2024 | 1930/ED | 15/05/2023 | 90 | MOITRA ENGINEERING CO. | 11.6 | 11.3 | 90
1442 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJHAT UTTAR PROPOSED TW Site under Chirnurah Sub Division, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002584/2023-2024 | 459/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 7.16 | 90
1443 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Dighir PWSS 2. Gopinagar PWSS 3. Mandra PWSS 4. Jayramabti PWSS 5. Gurap PWSS 6. Hasampur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000826/2023-2024 | 204/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
1444 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001550/2024-2025 | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0
1445 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Gopinagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001047/2023-2024 | 291/CH | 15/03/2024 | 7 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 100
1446 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Radhanagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001048/2023-2024 | 292/CH | 15/03/2024 | 7 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 100
1447 | Hooghly Division | Chandannagar Sub-Division | GANDERPUKUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division Block-SINGUR, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000176/2023-2024 | 1681/HUG | 08/06/2023 | 664 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 357.8 | 201.4 | 85
1448 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000069/2023-2024 | 1235/10/Hug | 28/04/2023 | 0 | Resource Division | 15.57 | 0 | 0
1449 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000401/2023-2024 | 3058/16/Hug | 11/10/2023 | 0 | Resource Division | 8.67 | 0 | 0
1450 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Ganderpukur W/S Sch., T/W No. - I, Block - Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04074/2023-2024 | 339 | 10/10/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
1451 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Ganderpukur W/S Sch. , T/W No. - II, Block- Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04075/2023-2024 | 347 | 11/10/2023 | 0 | WBSEDCL | 2.39 | 0 | 0
1452 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ganderpukur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000041/2023-2024 | 1727/ED | 19/04/2023 | 90 | M/S DAS ENTERPRISE | 21.05 | 20.98 | 49
1453 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Bainchipota (Zone-2) 1st T/W site & Bainchipota (Zone-2) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000285/2024-2025 | 925/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0.93 | 100
1454 | Hooghly Division | Chandannagar Sub-Division | BAINCHIPOTA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000301/2023-2024 | 2365/HUG | 08/08/2023 | 877 | RAJ CONSTRUCTION | 300.28 | 74.12 | 60
1455 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000068/2023-2024 | 1235/8/Hug | 28/04/2023 | 0 | Resource Division | 23.33 | 0 | 0
1456 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000204/2023-2024 | 1383/7/Hug | 15/05/2023 | 0 | Resource Division | 5.75 | 0 | 0
1457 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000417/2023-2024 | 3058/11/Hug | 11/10/2023 | 0 | Resource Division | 5.75 | 0 | 0
1458 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - I, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589159, Dt. - 07-03-2024, Application No. - 5004058510 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06275/2023-2024 | 875 | 13/03/2024 | 0 | WBSEDCL | 9.63 | 0 | 0
1459 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - II, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589664, Dt. - 07-03-2024, Application No. - 5004059136 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06280/2023-2024 | 874 | 13/03/2024 | 0 | WBSEDCL | 0.64 | 0 | 0
1460 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000046/2023-2024 | 1732/ED | 19/04/2023 | 90 | BINAPANI ENTERPRISE | 20.52 | 6.05 | 30
1461 | Hooghly Division | Arambug Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For AUGMENTATION OF of LAKSHMIPUR W/S Scheme under ARAMBAGH Sub - Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000118/2023-2024 | 1447/HUG | 18/05/2023 | 30 | M/S KHAMRUI CONSTRUCTION | 31.29 | 28.32 | 100
1462 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Lakshmipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000243/2022-2023 | 364/Arg | 19/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.24 | 3.2 | 0
1463 | Hooghly Division | Arambug Sub-Division | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of Lakshmipur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000244/2021-2022 | 1995/Hug | 12/11/2021 | 30 | S. B. CONSTRUCTION | 11.36 | 4.84 | 100
1464 | Hooghly Division | Arambug Sub-Division | Augmentation of LAKSHMIPUR Water Supply Scheme with Laying of Distribution System at Goghat -I Block under Arambagh Sub-Division of Hooghly Division, PHE Dte. Hooghly. Sl no - 04 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000246/2022-2023 | 1800/HUG | 01/09/2022 | 45 | M/S RAJKUMAR KHAN | 112.72 | 107.91 | 96
1465 | Hooghly Division | Arambug Sub-Division | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000340/2021-2022 | 17/Hug | 04/01/2022 | 30 | S.M. ENTERPRISE | 8.23 | 8.47 | 0
1466 | Hooghly Division | Arambug Sub-Division | Repairing Of Switch Room, Boundary wall of T.W-1 & T.W-2 for Augemntation Of LAKSHMIPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000348/2023-2024 | 2439/HUG | 12/08/2023 | 45 | SADHUKHAN ENTERPRISE | 9.47 | 7.32 | 95
1467 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000119/2022-2023 | 2209/2/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
1468 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000258/2022-2023 | 127/15/Hug | 13/01/2023 | 0 | Resource Division | 7.19 | 0 | 0
1469 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Lakshmipur w/s scheme,TW No-3 District-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02128/2023-2024 | 118 | 20/07/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
1470 | Electrical | Arambug Sub-Division | Quotation of New service Connection for Lakshmipur W/s Scheme, TW No-4, Block-Goghat-I, Dist-hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02477/2023-2024 | 150 | 01/08/2023 | 0 | WBSEDCL | 2.69 | 0 | 0
1471 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Lakshmipur water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000215/2022-2023 | 849/ED | 14/02/2023 | 90 | PRADIP KUMAR DHABAL | 21.51 | 21.46 | 40
1472 | Central Drilling | Arambug Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Lakshmipur W/S Scheme (TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000008/2023-2024 | 18/CDD | 04/04/2023 | 30 | CHANDA ENTERPRISE | 30.35 | 12.81 | 42
1473 | Central Drilling | Arambug Sub-Division | Loading unloading & Shifting of Drilling Accessories , Supporting Vehicles along with Rig Machine JOHN DR 1500-I from Lakshmipur PWSS , Block ¿ Goghat-I, Hooghly District to PANCHLA Store Howrah under CDD, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000079/2023-2024 | 170/CMSD-II(D) | 30/06/2023 | 15 | UTTAM KUMAR CHATTERJEE | 0.51 | 0.46 | 100
1474 | Central Drilling | Arambug Sub-Division | ADDITIONAL WORK FOR CONSTRUCTION OF TUBE WELL AT LAKSHMIPUR PWSS TW-I, ARAMBAG BLOCK, UNDER CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000510/2022-2023 | 66/CMSD-I | 14/03/2023 | 10 | CHANDA ENTERPRISE | 0.86 | 0.86 | 100
1475 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 155.48 | 30
1476 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
1477 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000061/2023-2024 | 1234/27/Hug | 28/04/2023 | 0 | Resource Division | 192.54 | 0 | 0
1478 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000179/2023-2024 | 1385/50/Hug | 15/05/2023 | 0 | Resource Division | 17.48 | 0 | 0
1479 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000458/2023-2024 | 3057/21/Hug | 11/10/2023 | 0 | Resource Division | 17.48 | 0 | 0
1480 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s Scheme, Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17721) Application No-5004190543 Reference Id-503647430. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00483/2024-2025 | 149 | 22/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
1481 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s scheme, Zone-I,PH No-I Block-Goghat-II,under Electrical Division,PHE Dte.(SM/17721) Application No-5004243748 Reference Id-503669340. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00831/2024-2025 | 230 | 20/06/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
1482 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000049/2023-2024 | 1793/ED | 24/04/2023 | 668 | H.K.DAS & CO. | 22.39 | 0 | 40
1483 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHURKUNDA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000138/2024-2025 | 1164/ED | 14/06/2024 | 90 | H.K.DAS & CO. | 10.89 | 0 | 0
1484 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000045/2021-2022 | 2098/9/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
1485 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000140/2022-2023 | 2686/7/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0
1486 | Hooghly Division |  | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of Mainan Water Supply Scheme at Mainan Mouza under Arambag Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000299/2021-2022 | 2210/Hug | 14/12/2021 | 60 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 56 | 21.49 | 95
1487 | Hooghly Division |  | Laying of pipe line for left out portion within command area of Bhunia Para, Dakshin Khan Para, Das Para, Ghorui Para, Mainan Pry School habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-A) |  |  | ORD/000362/2022-2023 | 608/Arg | 31/08/2022 | 30 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 4.92 | 4.92 | 95
1488 | Hooghly Division |  | Laying of pipe line for left out portion within command area of Maity Para, Maj Mahissya Para, Mallik Para, Mete Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-B) |  |  | ORD/000363/2022-2023 | 609/Arg | 31/08/2022 | 30 | SARADA ENGINEERS CO OPERATIVE AND CONSTRUCTION SOCIETY LTD. | 4.9 | 4.9 | 95
1489 | Hooghly Division |  | Laying of pipe line for left out portion within command area of Middya Para, Panchtik Middya Para, Panja Para, Paschim Bandh habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-C) |  |  | ORD/000366/2022-2023 | 610/Arg | 31/08/2022 | 30 | R.S. CONSTRUCTION & CONSULTANCY | 4.9 | 4.9 | 95
1490 | Hooghly Division |  | Laying of pipe line for left out portion within command area of Paschim Bha Para, Sk Para, Uttar Bera Para, Uttar Khan Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-D) |  |  | ORD/000367/2022-2023 | 611/Arg | 31/08/2022 | 30 | SUSANTA KUMAR | 4.75 | 4.75 | 95
1491 | Hooghly Division |  | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of DIHI BAGNAN W/S Scheme under Arambag Sub-Division P.H.E. Dte. |  |  | ORD/000428/2021-2022 | 53/Arg | 31/01/2022 | 45 | ANNAPURNA CONSTRUCTION | 3.54 | 0 | 95
1492 | Hooghly Division |  | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of MAINAN PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000446/2024-2025 | 4085/HUG | 19/12/2024 | 90 | M/S S & P CONSTRUCTION | 11.13 | 0 | 0
1493 | Hooghly Division |  | Protection works and other allied works at Head Work Site of MAINAN Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000475/2024-2025 | 4054/HUG | 19/12/2024 | 90 | DILIP KUMAR GHOSH | 22.94 | 0 | 0
1494 | Hooghly Division |  | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000597/2023-2024 | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 32
1495 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 12.83 | 100
1496 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000646/2023-2024 | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 13.29 | 20
1497 | Electrical |  | Quotation of New Service Connection for Mainan w/s Scheme,PH No-4 Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004288912 Reference Id-503688427. |  |  | BILL/01158/2024-2025 | 293 | 15/07/2024 | 0 | WBSEDCL | 7.06 | 0 | 0
1498 | Electrical |  | Quotation of New Service Connection for Mainan w/s Scheme,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004320142 Reference Id- 503705441 |  |  | BILL/01376/2024-2025 | 336 | 30/07/2024 | 0 | WBSEDCL | 8.26 | 0 | 0
1499 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAINAN PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000370/2024-2025 | 1454/ED | 25/07/2024 | 90 | SUDIKSHA CONSTRUCTION | 22.11 | 0 | 0
1500 | Hooghly Division |  | BHALIA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] |  |  | ORD/000552/2023-2024 | 3181/HUG | 30/10/2023 | 518 | TANISA ENTERPRISE | 96.9 | 36.01 | 20
1501 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000448/2023-2024 | 3057/25/Hug | 11/10/2023 | 0 | Resource Division | 2.06 | 0 | 0
1502 | Electrical |  | Quotation of New Service Connection for Bhalia w/s Scheme,Zone-II,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/19014) Application No-5004416386 Reference Id-503753715 |  |  | BILL/01983/2024-2025 | 478 | 01/10/2024 | 0 | WBSEDCL | 6.49 | 0 | 0
1503 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001983/2023-2024 | 115/ED | 15/01/2024 | 502 | A.G. ENTERPRISE | 20.49 | 0 | 20
1504 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 397.14 | 50
1505 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000843/2023-2024 | 723/HUG | 05/03/2024 | 60 | SPG ENTERPRISES | 64.34 | 28.87 | 50
1506 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
1507 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | RTOR000410/2023-2024 | 3057/47/Hug | 11/10/2023 | 0 | Resource Division | 19.24 | 0 | 0
1508 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000154/2024-2025 | 1177/ED | 14/06/2024 | 90 | M/S G P ENTERPRISE | 10.74 | 0 | 0
1509 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000155/2024-2025 | 1178/ED | 14/06/2024 | 90 | M/S. UTTAM KUMAR CHATTERJEE. | 10.74 | 0 | 0
1510 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000816/2023-2024 | 3161/ED | 27/07/2023 | 614 | GLACIER ENGINEERING CO. | 21.83 | 0 | 50
1511 | Hooghly Division |  | Repairing & Renovation of Switch Room & Store Room at Head Works Site of Bakulia Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/000002/2025-2026 | 484/CH | 04/04/2025 | 10 | MAA BUNAMATA ENTERPRISE | 4.07 | 0 | 100
1512 | Hooghly Division |  | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] |  |  | ORD/000160/2023-2024 | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 24.5 | 65
1513 | Hooghly Division |  | Repairing & Renovation of Boundary Wall and Land Development at H/W Site of Bakulia Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002008/2024-2025 | 294/CH | 20/02/2025 | 29 | MAA BUNAMATA ENTERPRISE | 4.78 | 0 | 100
1514 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000221/2022-2023 | 226/1/Hug | 24/01/2023 | 0 | Resource Division | 178.88 | 0 | 0
1515 | Electrical |  | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-III under Electrical Division,PHE Dte.(SM/18644). Application No-5004112076. Reference Id-503617154. |  |  | BILL/00190/2024-2025 | 78 | 19/04/2024 | 0 | WBSEDCL | 19.66 | 0 | 0
1516 | Electrical |  | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-IV under Electrical Division,PHE Dte.(SM/18644). Application No-5004111585. Reference Id-503617124. |  |  | BILL/00191/2024-2025 | 79 | 19/04/2024 | 0 | WBSEDCL | 7.52 | 0 | 0
1517 | Electrical |  | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of April 2024. |  |  | BILL/00501/2024-2025 | 154 | 28/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1518 | Electrical |  | Supply of Fuel for 1(One) no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE DTe. for the Month of May 2024. Car No-WB 04H 0517 |  |  | BILL/00715/2024-2025 | 226 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1519 | Electrical |  | Supply of Fuel for 1(one) no Diesel Luxury taxi on Contract Carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of June 2024. |  |  | BILL/01151/2024-2025 | 283 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1520 | Electrical |  | Supply of Fuel for 1(One) no. Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer,Howrah mechanical Sub Division,PHE Dte for the Month of July 2024. |  |  | BILL/01636/2024-2025 | 413 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1521 | Electrical |  | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of August 2024. Car No. WB-04H-0517 From 01.08.2024 to 31.08.2024 |  |  | BILL/01975/2024-2025 | 467 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1522 | Electrical |  | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024 |  |  | BILL/02075/2024-2025 | 532 | 28/10/2024 | 0 | ARINDAM AUDDY | 0.07 | 0 | 0
1523 | Electrical |  | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024. |  |  | BILL/02076/2024-2025 | 534 | 28/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.18 | 0 | 0
1524 | Electrical |  | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of SEPTEMBER,2024 |  |  | BILL/02095/2024-2025 | 546 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.12 | 0 | 0
1525 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/000002/2024-2025 | 2404/HMSD | 26/04/2024 | 153 | ARINDAM AUDDY | 0.73 | 0.74 | 0
1526 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bakulia water supply scheme, T.W. No. I & II, Block: Balagarh, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000926/2023-2024 | 3597/ED | 28/08/2023 | 90 | R.M.D TRADING. | 21.89 | 0 | 0
1527 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0.16 | 15
1528 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/002957/2023-2024 | 2829_/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0 | 0
1529 | Hooghly Division | Arambug Sub-Division | GARMANDARAN ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000287/2023-2024 | 2336/HUG | 07/08/2023 | 784 | KHAN ENTERPRISE | 678.8 | 0 | 75
1530 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000297/2024-2025 | 3657/HUG | 13/11/2024 | 90 | ASHA ENTERPRISE | 16.14 | 0 | 0
1531 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0
1532 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 13.98 | 70
1533 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002298/2024-2025 | 1148/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0
1534 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000395/2023-2024 | 3057/54/Hug | 11/10/2023 | 0 | Resource Division | 19.35 | 0 | 0
1535 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004191479 Reference Id-503647821. | Assistant Engineer | Junior Engineer (Civill) | BILL/00536/2024-2025 | 179 | 30/05/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
1536 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004423599 Reference Id-503761602 | Assistant Engineer | Junior Engineer (Civill) | BILL/02033/2024-2025 | 508 | 21/10/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
1537 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Garmandaran w/s Scheme,Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/18646) Application No-5004431289 Reference Id-503764743 | Assistant Engineer | Junior Engineer (Civill) | BILL/02059/2024-2025 | 516 | 21/10/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
1538 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000876/2023-2024 | 3449/ED | 11/08/2023 | 90 | AMIT DAS | 21.46 | 0 | 0
1539 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000928/2023-2024 | 3599/ED | 28/08/2023 | 673 | UNITED TRADERS | 21.47 | 0 | 40
1540 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 34.59 | 40
1541 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0
1542 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001252/2023-2024 | 4501/ED | 23/11/2023 | 678 | S.G.-ENTERPRISE | 21.5 | 0 | 45
1543 | Hooghly Division |  | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0
1544 | Hooghly Division |  | Protection works and other allied works at 3rd & 4th TubeWell Site of BACCHANARI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000439/2024-2025 | 4043/HUG | 19/12/2024 | 90 | MS CHANDIMATA CONSTRUCTION | 15.46 | 0 | 100
1545 | Hooghly Division |  | Repairing of Boundary Wall, Switch Room & R.C.C. Elevated Reservoir of BACHHANARI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/002261/2024-2025 | 573/HUG | 04/03/2025 | 60 | MS CHANDIMATA CONSTRUCTION | 12.45 | 0 | 0
1546 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos |  |  | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1547 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BACHHANARI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000367/2024-2025 | 1451/ED | 25/07/2024 | 90 | DAS ENTERPRISE | 11.08 | 0 | 0
1548 | Electrical |  | Supply delivery and installation of Chlorinator for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001526/2021-2022 | 316/HMSD | 18/02/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.76 | 0.76 | 100
1549 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bachhanari water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001529/2021-2022 | 553_ED | 22/03/2022 | 90 | S.M. ELECTRICALS | 6.05 | 6.05 | 50
1550 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002572/2022-2023 | 659/HMSD | 04/04/2022 | 30 | NITESH MANAGEMENT | 2.74 | 2.74 | 100
1551 | Hooghly Division |  | Protection works and other allied works OF 3rd & 4th TubeWell Site of HAYATPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000443/2024-2025 | 4045/HUG | 19/12/2024 | 90 | S D ENTERPRISE | 15.52 | 0 | 0
1552 | Hooghly Division |  | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of HAYATPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000455/2024-2025 | 4076/HUG | 19/12/2024 | 90 | ROY ENTERPRISE | 11.55 | 0 | 0
1553 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos |  |  | ORD/002647/2024-2025 | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
1554 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. III, Block: Arambag , District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001520/2021-2022 | 472/ED | 10/03/2022 | 90 | DAS ENTERPRISE | 6.89 | 6.57 | 100
1555 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001524/2021-2022 | 540/HMSD | 17/03/2022 | 21 | MOITRA ENGINEERING CO. | 2.74 | 2.74 | 100
1556 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001525/2021-2022 | 542/HMSD | 17/03/2022 | 30 | KASHINATH PAL & CO. | 2.74 | 2.72 | 100
1557 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001534/2021-2022 | 473/ED | 10/03/2022 | 90 | S.P. ENTERPRISE | 6.92 | 6.36 | 50
1558 | Electrical |  | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002569/2022-2023 | 71/HMSD | 10/01/2023 | 7 | S P ENTERPRISE | 0.8 | 0.8 | 100
1559 | Electrical |  | Supply and installation of short MS casing pipe making TW foundation and S&F submersible AL. Ar. cable at Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002570/2022-2023 | 1928/HMSD | 03/11/2022 | 7 | DAS ENTERPRISE | 0.9 | 0.9 | 100
1560 | Electrical |  | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002571/2022-2023 | 1878/HMSD | 20/10/2022 | 7 | DAS ENTERPRISE | 0.8 | 0.8 | 100
1561 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer |  | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 133.5 | 30
1562 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer |  | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 13.6 | 70
1563 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
1564 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer |  | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0
1565 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000482/2023-2024 | 3057/6/Hug | 11/10/2023 | 0 | Resource Division | 12.85 | 0 | 0
1566 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004136337 Reference Id-503627274. | Assistant Engineer |  | BILL/00328/2024-2025 | 102 | 06/05/2024 | 0 | WBSEDCL | 10.8 | 0 | 0
1567 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-I Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004135566 Reference Id-503626938. | Assistant Engineer |  | BILL/00329/2024-2025 | 103 | 06/05/2024 | 0 | WBSEDCL | 10.73 | 0 | 0
1568 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Shantipur w/s Scheme, Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18592) Application No-5004190445 Reference Id-503647425. | Assistant Engineer |  | BILL/00481/2024-2025 | 151 | 22/05/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
1569 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHANTIPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer |  | ORD/000141/2024-2025 | 1167/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 5.84 | 30
1570 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000916/2023-2024 | 3587/ED | 28/08/2023 | 642 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.26 | 5.69 | 30
1571 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 80
1572 | Hooghly Division |  | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of AKNA PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. |  |  | ORD/000728/2023-2024 | 12/CH | 04/01/2024 | 15 | M/S BIMAL DAS AND CO. | 4.99 | 4.98 | 50
1573 | Hooghly Division |  | Construction of Approach Road for 3rd TW site of Akna PWSS in JJM under Polba Dadpur Block under Hooghly Division under Chinsurah Sub-Division PHE Dte |  |  | ORD/002017/2024-2025 | 316/CH | 21/02/2025 | 15 | ASHA ENTERPRISE | 4.99 | 0 | 0
1574 | Electrical |  | Quotation for new service connection at Akna(S. Aug.) W/S Sch.[SM/18943], T/W No. - III, Barol Chowmatha, Block - Polba-Dadpur, Dist. - Hooghly under Mogra CCC, WBSEDCL, Ref. Id. - 503586679, Dt. - 27-03-2024, Application No. - 5004053218 |  |  | BILL/00015/2024-2025 | 14 | 04/04/2024 | 0 | WBSEDCL | 7.46 | 0 | 0
1575 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001262/2023-2024 | 4507/ED | 23/11/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 4.07 | 90
1576 | Hooghly Division |  | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of AMRA Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000567/2023-2024 | 3192/HUG | 31/10/2023 | 60 | R.K. TRADERS | 7.56 | 6.57 | 100
1577 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0
1578 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 45
1579 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 25
1580 | Hooghly Division |  | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of AMRA Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block |  |  | ORD/001467/2024-2025 | 131/CH | 29/01/2025 | 31 | ASHA ENTERPRISE | 4.62 | 0 | 50
1581 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amra water supply scheme, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000032/2022-2023 | 1914/ED | 21/11/2022 | 90 | M/S MANABESH ROY | 9.39 | 9.1 | 98
1582 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of AMRA Piped W/S Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001274/2023-2024 | 4514/ED | 23/11/2023 | 90 | SRI KRISHNA NIRMAN | 21.5 | 0 | 0
1583 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000127/2021-2022 | 2195/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
1584 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000523/2021-2022 |  | 23/07/2021 | 0 | DIPTI TRADERS | 30.58 | 0 | 0
1585 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002285/2020-2021 |  | 15/03/2021 | 0 | DIPTI TRADERS | 30 | 0 | 0
1586 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002543/2020-2021 |  | 19/03/2021 | 0 | DIPTI TRADERS | 30 | 0 | 0
1587 | Hooghly Division | Chinsuria Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
1588 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME (HEAD WORKS), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000008/2022-2023 | 302/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.12 | 0
1589 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME, POLBADADPUR BLOCK UNDER HOOGHLY DISTRICT , CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2022-2023 | 294/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.3 | 0
1590 | Central Drilling | Chinsuria Sub-Division | ROUTINE MAINTENANCE OF COMPRESSOR AND REPAIRING OF OTHERS ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000242/2021-2022 | 635/CMSD-II (D) | 23/12/2021 | 15 | M/S B.P.TRADING CORPORATION | 3.37 | 3.34 | 0
1591 | Central Drilling | Chinsuria Sub-Division | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 0.7 | 0
1592 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000170/2021-2022 | 428/5-5/Hug | 07/03/2022 | 0 | Resource Division | 11 | 0 | 0
1593 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000190/2021-2022 |  | 24/05/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 23.32 | 0 | 0
1594 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000514/2021-2022 |  | 23/07/2021 | 0 | BIMAL KUMAR HALDER | 9.98 | 0 | 0
1595 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000535/2021-2022 |  | 23/07/2021 | 0 | BIMAL KUMAR HALDER | 9.98 | 0 | 0
1596 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000603/2021-2022 |  | 17/08/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 14.73 | 0 | 0
1597 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000847/2021-2022 |  | 21/09/2021 | 0 | TOTON MONDAL | 7.25 | 0 | 0
1598 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001095/2021-2022 |  | 06/10/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 6.67 | 0 | 0
1599 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001923/2020-2021 |  | 15/02/2021 | 0 | TOTON MONDAL | 16 | 0 | 0
1600 | Hooghly Division | Chinsuria Sub-Division | ... | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002577/2021-2022 | 844375 | 17/12/2021 | 0 | MOUMITA SINGHA BHATTACHATYA | 0.31 | 0 | 0
1601 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002613/2020-2021 |  | 19/03/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 10.96 | 0 | 0
1602 | Hooghly Division | Srirampur Sub-Division | Providing 47 nos. Functional Household Tap Connection (FHTC) in AWG Centers (the command area of Jangalpara, Jangipara & Rajbalhat Water Supply Scheme) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000314/2021-2022 | 220/SER | 20/12/2021 | 25 | M/S SAYAN CHAKRABORTY | 1.95 | 1.35 | 0
1603 | Hooghly Division | Srirampur Sub-Division | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000388/2021-2022 | 294/SER | 21/02/2022 | 45 | BAKSHI ENTERPRISE | 2.99 | 0.23 | 0
1604 | Hooghly Division | Srirampur Sub-Division | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000467/2020-2021 | 473/Hug | 26/02/2021 | 40 | RAJ CONSTRUCTION | 51.8 | 51.8 | 0
1605 | Hooghly Division | Srirampur Sub-Division | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000894/2020-2021 | 473/HUG | 26/02/2021 | 40 | RAJ CONSTRUCTION | 69.87 | 0.72 | 72
1606 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000004/2022-2023 | 1122/1/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
1607 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000122/2021-2022 | 2198/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
1608 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000843/2021-2022 |  | 21/09/2021 | 0 | RAJ CONSTRUCTION | 43.8 | 0 | 0
1609 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGALPARA W/S SCHEME, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000387/2022-2023 | 2000/CDD | 08/02/2023 | 30 | CHANDA ENTERPRISE | 12.54 | 8.98 | 0
1610 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001897/2020-2021 |  | 15/02/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 24 | 0 | 0
1611 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
1612 | Hooghly Division | Srirampur Sub-Division | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | Assistant Engineer (Civil) |  | ORD/000425/2024-2025 | 3522/HUG | 22/10/2024 | 316 | WATER TECH | 29.57 | 0 | 45
1613 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000837/2021-2022 |  | 21/09/2021 | 0 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 30.09 | 0 | 0
1614 | Hooghly Division | Chinsuria Sub-Division | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of DIGSUI HOERA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000359/2021-2022 | 120/Hug | 19/01/2022 | 30 | DAS TRADING | 41.69 | 12.25 | 100
1615 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/000007/2021-2022 |  | 12/04/2021 | 0 | M/S S.C CIVIL ENTERPRISE | 40.5 | 0 | 0
1616 | Central Drilling | Chinsuria Sub-Division | Fuel charges for the month of November,22. car number - WB04H 6870. | Assistant Engineer (Civil) |  | BILL/00063/2022-2023 | BP-2022-23-300 | 06/01/2023 | 0 | MIRA SERVICE STATION | 0.24 | 0 | 0
1617 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-I), CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) |  | ORD/000025/2022-2023 | 296/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 6.2 | 100
1618 | Central Drilling | Chinsuria Sub-Division | CONTINUATION FOR HIRING DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) |  | ORD/000096/2022-2023 | 361/CMSD-II (D) | 15/07/2022 | 30 | ASHUTOSH PAL | 0.73 | 0.52 | 100
1619 | Central Drilling | Chinsuria Sub-Division | CONTINUATION FOR HIRING OF DEASEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE , CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) |  | ORD/000268/2022-2023 | 361/ CMSD-II | 15/07/2022 | 15 | ASHUTOSH PAL | 0.73 | 0.29 | 100
1620 | Hooghly Division | Chandannagar Sub-Division | Providing 512 nos F.H.T.C. in Krishnabati & Gazipur village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000083/2020-2021 | 1549/Hug | 24/11/2020 | 365 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 18.11 | 3 | 100
1621 | Hooghly Division | Chandannagar Sub-Division | Providing 62 nos FHTC in Krishnabati village at Nawapara Habitation of Malia and its Adj. Mouzas Water Supply Scheme under Chandannagar Sub Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000423/2020-2021 | 59/Chan | 02/02/2021 | 16 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 2.17 | 0.31 | 100
1622 | Hooghly Division | Chandannagar Sub-Division | PROVIDING 72 NOS FHTC FOR MALIA PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2020-2021 | 88/CHAN | 15/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 3.16 | 0.41 | 100
1623 | Hooghly Division | Chandannagar Sub-Division | Providing 112 nos F.H.T.C. & extension of pipe line in left out portion of Dakshinkul, Baganbati& Hamir gachhi village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000880/2020-2021 | 327/HUG | 11/02/2021 | 30 | M/S S.G. CONSTRUCTION | 10.08 | 10.08 | 100
1624 | Hooghly Division | Chandannagar Sub-Division | Providing F.H.T.C in leftout portion and repairing boundary wall of Malia water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001246/2024-2025 | 3789/HUG | 25/11/2024 | 310 | ROSE ENTERPRISE | 11.75 | 0 | 100
1625 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001038/2021-2022 |  | 30/09/2021 | 0 | M/S S.G. CONSTRUCTION | 13.22 | 0 | 0
1626 | Hooghly Division | Chandannagar Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
1627 | Hooghly Division | Arambug Sub-Division | Providing 400 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of PATUL Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000097/2022-2023 | 1089/HUG | 03/06/2022 | 30 | K. JAGADHATRY & CO. | 23.18 | 0 | 0
1628 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000017/2021-2022 |  | 12/04/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 5.04 | 0 | 0
1629 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000530/2021-2022 |  | 28/07/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 41.45 | 0 | 0
1630 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000585/2021-2022 |  | 17/08/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 5.11 | 0 | 0
1631 | Hooghly Division | Chandannagar Sub-Division | Providing 224 nos Functional Household Tap Connection (FHTC) within the command area of Baidyapur Water Supply Scheme at Basudebpur Mouza Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000126/2021-2022 | 1444/Hug | 23/08/2021 | 30 | SARKAR CONSTRUCTION | 22.35 | 7.43 | 100
1632 | Hooghly Division | Chandannagar Sub-Division | Providing F.H.T.C in leftout portion and construction of boundary wall at head work site and 3rd tubewell site, laying pumping main at 3rd tubewell site of Baidyapur water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000221/2024-2025 | 3430/HUG | 03/10/2024 | 304 | BAPPADITYA BANERJEE | 65.68 | 0 | 50
1633 | Hooghly Division | Chandannagar Sub-Division | Special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Baidyapur W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000238/2025-2026 | 889/CHAN | 21/07/2025 | 20 | SWASTIK ENTERPRISE | 4.97 | 0 | 100
1634 | Hooghly Division | Chandannagar Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of BAIDYAPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000456/2024-2025 | 4075/HUG | 19/12/2024 | 90 | BIMAL KUMAR HALDER | 9.23 | 0 | 0
1635 | Hooghly Division | Chandannagar Sub-Division | PROVIDING 94 NOS. FHTC IN MIRZAPUR VILLAGE OF BAIDYAPUR AND ITS ADJ MOUZAS PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000461/2020-2021 | 89/CHAN | 15/02/2021 | 30 | TAPAS ADHYA | 4.62 | 1.55 | 100
1636 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Baidyapur PWSS,Madpur PWSS,Ghosha PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000981/2023-2024 | 309/chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.48 | 0.48 | 100
1637 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002108/2021-2022 |  | 28/01/2022 | 0 | SARKAR CONSTRUCTION | 7.5 | 0 | 0
1638 | Hooghly Division | Arambug Sub-Division | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of Bachhanari Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000231/2021-2022 | 1916/Hug | 27/10/2021 | 20 | ROY ENTERPRISE | 8.38 | 8.28 | 100
1639 | Hooghly Division | Arambug Sub-Division | Providing 450 nos F.H.T.C. in Bachhanari and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000248/2020-2021 | 250/Hug | 03/02/2021 | 30 | PRADIP KUMAR ADHYA | 30.31 | 5.22 | 100
1640 | Hooghly Division | Arambug Sub-Division | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of BACHHANARI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000337/2021-2022 | 14/Hug | 04/01/2022 | 20 | ROY ENTERPRISE | 6.02 | 6.02 | 100
1641 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of BACHHANARI W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000414/2021-2022 | 52/Arg | 31/01/2022 | 45 | S. B. CONSTRUCTION | 3.43 | 2.75 | 100
1642 | Hooghly Division | Arambug Sub-Division | Hiring of well maintained Diesel Motor Cab for the office of the Executive Engineer, Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2021-2022 | 148/HQHUG | 30/12/2021 | 365 | PRADIP KUMAR ADHYA | 1.25 | 1.25 | 100
1643 | Hooghly Division | Arambug Sub-Division | Construction of approach road at 3rd Tube Well site of Bachhanari Piped Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000570/2021-2022 | 215/ARG | 31/03/2022 | 7 | KARALI MOHAN KHAMRUI | 1.32 | 1.3 | 100
1644 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002104/2021-2022 |  | 28/01/2022 | 0 | M/S SHIVAM UDYOG | 19.5 | 0 | 0
1645 | Central Drilling | Arambug Sub-Division | Supply & delivery of Cotton Waste and other materials for drilling work at Bachanari PWSS, District Hooghly and other PWSS under Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000148/2023-2024 | 256/CMSD-I | 23/06/2023 | 15 | DEV ENTERPRISE | 1.46 | 0 | 0
1646 | Central Drilling | Arambug Sub-Division | SUPPLY AND DELIVERY OF COTTON WASTE AND OTHER MATERIALS FOR DRILLING WORK AT BACHHANARI PWSS DISTRICT HOOGHLY AND OTHER PWSS UNDER CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000191/2022-2023 | 256/CMSD-I | 23/06/2022 | 15 | M/S PRACHI ENGINEERING | 1.92 | 0 | 100
1647 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY KORES RIG MACHINE UNDER CMSD-II, CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000195/2021-2022 | 644/ CDD | 28/09/2021 | 30 | PADMA ENGINEERING & CO. | 11.2 | 8.36 | 100
1648 | Central Drilling | Arambug Sub-Division | PROVIDING TUBE WELL MATERIALS (150MM DIA CD), CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BACHHANARI, IN HOWRAH DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000362/2022-2023 | 113/CMSD-I | 06/05/2022 | 15 | ASHUTOSH DAS & CO | 3.11 | 3.11 | 0
1649 | Central Drilling | Arambug Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | Assistant Engineer | Junior Engineer (Civill) | ORD/000364/2022-2023 | 379/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.44 | 0.02 | 0
1650 | Central Drilling | Arambug Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.01 | 0
1651 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000161/2022-2023 | 292/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 4.21 | 90
1652 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER AIILIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AKNA W/S SCHEME (Z-I), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000195/2022-2023 | 292/ CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 4.21 | 0 | 100
1653 | Hooghly Division | Chinsuria Sub-Division | Providing 1002 nos F.H.T.C. in Dakatiar Bheri & Dubir Bheri Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000336/2020-2021 | 408/Hug | 15/02/2021 | 30 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 49.74 | 12.16 | 0
1654 | Hooghly Division | Chinsuria Sub-Division | Providing 1158 nos F.H.T.C. in Karichar Bheri, Maheswarbati & Ugly Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000337/2020-2021 | 409/Hug | 15/02/2021 | 30 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 58.94 | 10.08 | 0
1655 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of NATUN CHAR KRISHNABATI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000421/2022-2023 | 2307/HUG | 28/10/2022 | 30 | SARKAR CONSTRUCTION | 33.86 | 33.48 | 0
1656 | Hooghly Division | Chinsuria Sub-Division | Providing 867 nos Functional Household Tap Connection (FHTC) within the Natunchar Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000456/2021-2022 | 474/Hug | 10/03/2022 | 40 | M/S T.K.B. CONSTRUCTION | 43.24 | 34.45 | 25
1657 | Hooghly Division | Chinsuria Sub-Division | Providing 433 nos Functional Household Tap Connection (FHTC) within the Char Rampur, Chhera Char Krishnabati, Guptipara Char & Sabek Char Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2021-2022 | 475/Hug | 10/03/2022 | 20 | BIMAL KUMAR HALDER | 21.7 | 18.13 | 0
1658 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000167/2021-2022 | 428/1-1/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0
1659 | Hooghly Division | Howrah Mechanical Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR BAIDYABATI TARAKESWAR CHAMPADANGA ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00666/2024-2025 | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 10.6 | 0 | 0
1660 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room, boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at different TW sites for Augmentation of ENAYETPUR Piped Water Supply Scheme under HARIPAL Block, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000040/2023-2024 | 1162/HUG | 20/04/2023 | 865 | P.B. ENTERPRISE (PINTU BHADURI) | 70.38 | 23.04 | 45
1661 | Hooghly Division | Howrah Mechanical Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Enayetpur Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000293/2021-2022 | 2204/Hug | 14/12/2021 | 60 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 40.46 | 41.84 | 0
1662 | Hooghly Division | Howrah Mechanical Sub-Division | Repairing of 3.6 mtr x 3.0 mtr size existing pump house of Enayetpur PWSS scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000401/2021-2022 | 657/chan | 27/12/2021 | 30 | SURAJIT SINGHA RAY | 2.76 | 2.67 | 0
1663 | Hooghly Division | Howrah Mechanical Sub-Division | ENAYETPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20mtr. staging height including soil investigation work at HARIPAL Block under Chandannagar Sub- Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000419/2022-2023 | 2298/HUG | 21/10/2022 | 1046 | P.B. ENTERPRISE (PINTU BHADURI) | 918.91 | 729.36 | 90
1664 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of ENAYETPUR PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000478/2021-2022 | 170/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.84 | 4.84 | 0
1665 | Hooghly Division | Howrah Mechanical Sub-Division | Interconnection of replacement tube wells with existing Rising main at HWS of Enayetpur Water Supply Scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000568/2021-2022 | 532/Chan | 12/11/2021 | 15 | SWASTIK ENTERPRISE | 2.29 | 2.03 | 0
1666 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000030/2022-2023 | 1125/3/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
1667 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000140/2021-2022 | 157/5/Hug | 24/01/2022 | 0 | Resource Division | 3.1 | 0 | 0
1668 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000150/2021-2022 | 423/2/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
1669 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000211/2023-2024 | 1383/14/Hug | 15/05/2023 | 0 | Resource Division | 23.96 | 0 | 0
1670 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000228/2022-2023 | 109/5/Hug | 10/01/2023 | 0 | Resource Division | 104.08 | 0 | 0
1671 | Hooghly Division | Howrah Mechanical Sub-Division | Central Drilling Payment | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | VCH/002416/2021-2022 | C022228292462 | 09/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0
1672 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Enayetpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000209/2022-2023 | 836/ED | 14/02/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0
1673 | Central Drilling | Howrah Mechanical Sub-Division | PROVIDING TUBE WELL MATERIALS (200 MM DIA CM PIPE) CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000168/2021-2022 | 175/CMSD-II | 27/07/2021 | 15 | KUNDU ELECTRICAL ENTERPRISE | 4.41 | 2.3 | 0
1674 | Central Drilling | Howrah Mechanical Sub-Division | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT ENAYATPUR PWSS TW-I UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000169/2021-2022 | 339/CMSD-II | 13/09/2021 | 15 | S B S ENTERPRISE | 0.42 | 0.35 | 0
1675 | Central Drilling | Howrah Mechanical Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000170/2021-2022 | 176/CMSD-II | 27/07/2021 | 30 | S B S ENTERPRISE | 4.86 | 3.3 | 0
1676 | Central Drilling | Howrah Mechanical Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000176/2021-2022 | 172/CMSD-II | 27/07/2021 | 15 | M/S PRACHI ENGINEERING | 4.17 | 4.17 | 0
1677 | Hooghly Division | Chinsuria Sub-Division | Withdrawal & Re-Laying of DHAMAITIKAR and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division,P.H.E Dte. [Block - Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000264/2022-2023 | 719/CH | 23/08/2022 | 15 | SUDIPTA SINHA | 4.86 | 4.85 | 0
1678 | Hooghly Division | Chinsuria Sub-Division | Providing 502 nos F.H.T.C. in Dhamaitikar village of Dhamaitikar and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali](Part-A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000909/2020-2021 | 1337/HUG | 29/09/2020 | 30 | SOUMYADIP DE | 19.04 | 0.44 | 100
1679 | Hooghly Division | Srirampur Sub-Division | Laying of Pipeline for left out portion of Masat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000363/2023-2024 | 2450/HUG | 12/08/2023 | 468 | SADHUKHAN ENTERPRISE | 9.87 | 7.45 | 10
1680 | Hooghly Division | Srirampur Sub-Division | Laying of Pipeline for left out portion of Masat , Banamalipur, AusbaliMouza of MASAT Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000366/2023-2024 | 2451/HUG | 12/08/2023 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 8.03 | 7.76 | 35
1681 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Chhunche & Ausbati Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000583/2022-2023 | 2842/HUG | 16/12/2022 | 770 | K. JAGADHATRY & CO. | 39.46 | 35.68 | 30
1682 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Ajabnagar, Banamalipur & Mukundapur Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000584/2022-2023 | 2843/HUG | 16/12/2022 | 45 | BAKSHI ENTERPRISE | 46.45 | 42.95 | 20
1683 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Masat Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000585/2022-2023 | 2844/HUG | 16/12/2022 | 60 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 66.74 | 65.02 | 30
1684 | Hooghly Division | Srirampur Sub-Division | Laying Distribution System of Balanced portion with Additional laying including Repairing of Roads (Concrete) within Masat, Banamalipur, Ajabnagar and Ausbali mouzas in Masat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000898/2023-2024 | 821/HUG | 11/03/2024 | 30 | DILIP KUMAR GHOSH | 31.69 | 31.07 | 96
1685 | Hooghly Division | Srirampur Sub-Division | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MASAT Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000902/2023-2024 | 823/HUG | 11/03/2024 | 60 | G. T. AGRO CENTRE | 31.46 | 0 | 0
1686 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mollarber PWSS 2. Uttar Rajyadharpur PWSS 3. Piarapur PWSS 4. Krishnarampur PWSS 5. Jangalpara PWSS 6. Masat PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000938/2023-2024 | 108/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
1687 | Hooghly Division | Chandannagar Sub-Division | Providing 107 nos. tap connection at Mirzapur and bajitpur mouza of Baidyapur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000084/2022-2023 | 215/chan | 13/04/2022 | 20 | M/S RAJKUMAR KHAN | 4.99 | 0 | 100
1688 | Hooghly Division | Chandannagar Sub-Division | Providing 112 nos. tap connection at Nagadipara and Paschim para Habitation of TALPUR water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL HABITATION" | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000085/2022-2023 | 216/chan | 13/04/2022 | 20 | SWASTIK ENTERPRISE | 4.99 | 4.69 | 0
1689 | Hooghly Division | Chandannagar Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR JANGIPARA ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00668/2024-2025 | BP-2024-25-500 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 13.12 | 0 | 0
1690 | Hooghly Division | Chandannagar Sub-Division | Augmentation of DWIPA Water Supply Scheme with Construction of 600 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS, Switch room, Boundary wall,Rising Main,FHTC Work,Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000046/2022-2023 | 830/Hug | 20/04/2022 | 1078 | P.B. ENTERPRISE (PINTU BHADURI) | 724.25 | 685.83 | 80
1691 | Hooghly Division | Chandannagar Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at DWIPA PWSS (3rd & 4th Tube Well Site) of Chandannagar Sub-Division under Hooghly Division, PHE Dte. SL NO - 12 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000346/2022-2023 | 1999/HUG | 12/09/2022 | 45 | P.B. ENTERPRISE (PINTU BHADURI) | 26 | 23.08 | 0
1692 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of DWIPA PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000477/2021-2022 | 169/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 3.99 | 0
1693 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Dwipa PWSS, Enayetpur PWSS, Haripal zone-I PWSS, Haripal zone-II PWSS, Olipur zone-I PWSS, Olipur zone-II PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000972/2023-2024 | 301/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
1694 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000029/2022-2023 | 1125/2/HUG | 06/06/2022 | 0 | Resource Division | 11.52 | 0 | 0
1695 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000139/2022-2023 | 2686/6/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0
1696 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000150/2022-2023 | 01/08/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
1697 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000154/2021-2022 | 423/5/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
1698 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000236/2022-2023 | 109/ 9/Hug | 10/01/2023 | 0 | Resource Division | 34.08 | 0 | 0
1699 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000294/2023-2024 | 1383/40/Hug | 15/05/2023 | 0 | Resource Division | 11.38 | 0 | 0
1700 | Electrical | Chandannagar Sub-Division | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00904/2022-2023 | 183 | 10/03/2023 | 0 | WBSEDCL | 0.65 | 0 | 0
1701 | Electrical | Chandannagar Sub-Division | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00905/2022-2023 | 183 | 10/03/2023 | 0 | WBSEDCL | 3.08 | 0 | 0
1702 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dwipa water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000208/2022-2023 | 835/ED | 14/02/2023 | 90 | M/S PS & ASSOCIATES | 21.49 | 21.44 | 0
1703 | Hooghly Division | Chandannagar Sub-Division | Providing connection in leftout portion of beraberi mouza under Beraberi water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000052/2024-2025 | 2341/HUG | 19/06/2024 | 30 | MAA TARA CONSTRUCTION | 31.82 | 0 | 0
1704 | Hooghly Division | Chandannagar Sub-Division | Augmentation of BERABARI Water Supply Scheme with Construction of 600 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS(S-2) & Functional Household tap Connection within Chak Kalikabari, Beraberi, Jampukur, Madhusudanpur, Khaser Bheri & Khagragachhi Mouza, Switch room, Boundary wall, Rising Main, Repairing of existing Switch Rooms at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000139/2022-2023 | 1383/Hug | 07/07/2022 | 300 | S & P ENTERPRISE | 461.01 | 460.96 | 50
1705 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system including road restoration Work at Baje Melia & Hijli Mouzas under Beraberi Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000304/2024-2025 | 3675/HUG | 13/11/2024 | 45 | M/S BISWAS CONSTRUCTION | 42.93 | 0 | 0
1706 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation Beraberi PWSS under Chandannagar Sub Division , PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000476/2021-2022 | 168/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.13 | 0
1707 | Hooghly Division | Chandannagar Sub-Division | Augmentation of BERABARI Water Supply Scheme with Laying Distribution System (S-1) & Functional Household Tap Connection at Baje Melia & Hijli Mouzas, Construction of Switch room at Proposed T.W Site, Boundary wall at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000682/2022-2023 | 1583/HUG | 02/08/2022 | 75 | M/S BISWAS CONSTRUCTION | 246.26 | 204.24 | 50
1708 | Hooghly Division | Chandannagar Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BERABERI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000751/2023-2024 | 386/HUG | 08/02/2024 | 60 | BHATTACHARJEE CONSTRUCTION | 15.56 | 13.47 | 100
1709 | Hooghly Division | Chandannagar Sub-Division | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 15.97 | 100
1710 | Hooghly Division | Chandannagar Sub-Division | Laying DI pipe and orther allied work for BERABERI PWSS UNDER singur block under chandannagar subdivision of of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001641/2024-2025 | 3618/HUG | 05/11/2024 | 241 | DAFFODIL | 72.7 | 0 | 80
1711 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000026/2022-2023 | 1125/7/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0
1712 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000038/2023-2024 | 1235/Hug | 28/04/2023 | 0 | Resource Division | 223.26 | 0 | 0
1713 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000146/2022-2023 | 2686/13/Hug | 01/12/2022 | 0 | Resource Division | 0.35 | 0 | 0
1714 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000147/2021-2022 | 157/4/Hug | 24/01/2022 | 0 | Resource Division | 2.58 | 0 | 0
1715 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000151/2021-2022 | 423/3/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
1716 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000151/2022-2023 | 01/09/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
1717 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000299/2023-2024 | 1383/43/Hug | 15/05/2023 | 0 | Resource Division | 7.81 | 0 | 0
1718 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000466/2023-2024 | 3058/Hug | 11/10/2023 | 0 | Resource Division | 30.27 | 0 | 0
1719 | Electrical | Chandannagar Sub-Division | Quotation bill for New Connection at Beraberi W/S. Sch. PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00012/2022-2023 | BP-2022-23-111 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.54 | 0 | 0
1720 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Beraberi W/S Sch. , T/W No. - V [SM/09984] , Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503614887, dt. - 12/04/2024, Application No. - 5004104119 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00188/2024-2025 | 75 | 18/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
1721 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2022-2023 | 1918/ED | 21/11/2022 | 90 | GLACIER ENGINEERING CO. | 10.67 | 10.38 | 0
1722 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001275/2022-2023 | 1792/ED | 02/11/2022 | 90 | ALPHA ENTERPRISE | 10.67 | 10.38 | 99
1723 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001361/2022-2023 | 1548/ED | 20/09/2022 | 649 | PERFECT AIRCONDITION | 9.66 | 9.4 | 99
1724 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. V, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002478/2023-2024 | 338/ED | 21/02/2024 | 540 | DEY ENTERPRISE | 10.41 | 10.13 | 90
1725 | Electrical | Chandannagar Sub-Division | Electricity Bill New Connection | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002508/2022-2023 |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.03 | 0 | 0
1726 | Electrical | Chandannagar Sub-Division | New Connection of Electricity | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002509/2022-2023 |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
1727 | Electrical | Chandannagar Sub-Division | New Connection | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002536/2022-2023 | 80 | 16/09/2022 | 0 | WBSEDCL | 6.36 | 0 | 0
1728 | Central Drilling | Chandannagar Sub-Division | FUEL CHARGES FOR CAR NO - WB-04H-6870 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00023/2023-2024 | BP-2023-24-13 | 24/04/2023 | 0 | MIRA SERVICE STATION | 0.19 | 0 | 0
1729 | Central Drilling | Chandannagar Sub-Division | SUPPLY 7 DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKKS FOR CONSTRUCTION OF TUBE WELL aUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000083/2022-2023 | 372/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.62 | 0
1730 | Central Drilling | Chandannagar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000084/2022-2023 | 371/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.55 | 0
1731 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-II, HARTIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000085/2022-2023 | 370/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.75 | 0
1732 | Central Drilling | Chandannagar Sub-Division | SUPPLY & DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2022-2023 | 369/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.6 | 0
1733 | Central Drilling | Chandannagar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITHJ OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2022-2023 | 368/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.62 | 0
1734 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000088/2022-2023 | 367/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.78 | 0
1735 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLINGCREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000107/2022-2023 | 374/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.75 | 0
1736 | Central Drilling | Chandannagar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000108/2022-2023 | 375/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.7 | 0
1737 | Central Drilling | Chandannagar Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000109/2022-2023 | 376/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.6 | 0
1738 | Central Drilling | Chandannagar Sub-Division | CONTINUATION FOR HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000360/2022-2023 | 35/CMSD-II | 10/02/2023 | 15 | ASHUTOSH PAL | 0.29 | 0.29 | 0
1739 | Hooghly Division | Chinsuria Sub-Division | Protection Work at H/W & 2ND T.W Site for HASAMPUR W/S under Chinsurah Sub - Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000370/2023-2024 | 2460/HUG | 12/08/2023 | 60 | CHAKRABORTY ENTERPRISE | 35.44 | 30.86 | 100
1740 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 229.04 | 30
1741 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000117/2023-2024 | 1264/12/HUG | 03/05/2023 | 0 | Resource Division | 7.36 | 0 | 0
1742 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000231/2023-2024 | 1386/10/Hug | 15/05/2023 | 0 | Resource Division | 20.6 | 0 | 0
1743 | Electrical | Chinsuria Sub-Division | Add. Electric quot. of WBSEDCL for New service Connection of Barul T/W-I W/S scheme under Electrical Division PHE Dte. (SM/12246) App. No- 5003997215 Ref. Id- 503556940 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02093/2024-2025 | 539 | 29/10/2024 | 0 | WBSEDCL | 1.34 | 0 | 0
1744 | Electrical | Chinsuria Sub-Division | Barul PH__II Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05989/2023-2024 | 726 | 05/02/2024 | 0 | WBSEDCL | 4.11 | 0 | 0
1745 | Electrical | Chinsuria Sub-Division | Barul PH__I Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05990/2023-2024 | 727 | 05/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
1746 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Barul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000076/2022-2023 | 3458/ED | 30/12/2022 | 1095 | T S CONSTRUCTION | 20.35 | 0 | 65
1747 | Hooghly Division | Chandannagar Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00737/2023-2024 |  | 06/11/2023 | 0 | AATISH KUMAR SHAW | 0.8 | 0 | 0
1748 | Hooghly Division | Chandannagar Sub-Division | "RAMBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 150 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000476/2022-2023 | 2559/HUG | 25/11/2022 | 1103 | BAPPADITYA BANERJEE | 230.53 | 186.6 | 45
1749 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of RAMBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000663/2022-2023 | 159/HUG | 16/01/2023 | 45 | SAMIRON GHOSH | 28.9 | 28.86 | 100
1750 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of RAMBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000712/2022-2023 | 449/HUG | 16/02/2023 | 60 | RITAM ENTERPRISE | 12.29 | 12.29 | 50
1751 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000210/2022-2023 | 109/ 20/Hug | 10/01/2023 | 0 | Resource Division | 10.76 | 0 | 0
1752 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000273/2022-2023 | 902/14/Hug | 27/03/2023 | 0 | Resource Division | 5.33 | 0 | 0
1753 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000292/2023-2024 | 1383/38/Hug | 15/05/2023 | 0 | Resource Division | 5.43 | 0 | 0
1754 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme, PH No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03687/2023-2024 | 229 | 01/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0
1755 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03688/2023-2024 | 230 | 01/09/2023 | 0 | WBSEDCL | 9.37 | 0 | 0
1756 | Electrical | Chandannagar Sub-Division | Revised Quotation Bill for New Service Connection at Rambati W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04076/2023-2024 | 345 | 11/10/2023 | 0 | WBSEDCL | 0 | 0 | 0
1757 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rambati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000092/2022-2023 | 3474/ED | 30/12/2022 | 90 | S.G. TECHNICAL SERVICES | 20.35 | 17.05 | 90
1758 | Electrical | Chandannagar Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle - II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000285/2024-2025 | 2871/HMSD | 04/06/2024 | 182 | DEBASHISH GHOSH | 0.86 | 0.12 | 0
1759 | Hooghly Division | Arambug Sub-Division | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 4th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000124/2022-2023 | 1274/HUG | 23/06/2022 | 30 | KAMIRUL SK AND CO | 9.96 | 9.27 | 100
1760 | Hooghly Division | Arambug Sub-Division | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 5th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000125/2022-2023 | 1275/HUG | 23/06/2022 | 30 | KAMIRUL SK AND CO | 9.96 | 8.84 | 100
1761 | Hooghly Division | Arambug Sub-Division | Providing 155 nos Functional Household Tap Connection (FHTC) within the command area of JAGATPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000444/2021-2022 | 462/Hug | 10/03/2022 | 15 | M/S TANISA ENTERPRISE | 11.7 | 11.58 | 0
1762 | Hooghly Division | Arambug Sub-Division | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000885/2020-2021 | 467/HUG | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 0.97 | 100
1763 | Hooghly Division | Arambug Sub-Division | Providing 1487 nos F.H.T.C. in the villages of Sudarsan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba Dadpur] | Assistant Engineer | Junior Engineer (Civill) | ORD/000886/2020-2021 | 242/HUG | 02/02/2021 | 40 | M/S BISWAS CONSTRUCTION | 69.94 | 13.94 | 0
1764 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM in BELUN PWSS, Block-PANDUA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 06 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000374/2022-2023 | 2087/HUG | 21/09/2022 | 30 | BAKSHI ENTERPRISE | 24.77 | 24.76 | 0
1765 | Hooghly Division | Chinsuria Sub-Division | Laying of pipe line within left out portion for Providing Functional Household Tap Connection (FHTC) under JJM in BELUN PWSS, Block-PANDUA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 07 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000375/2022-2023 | 2088/HUG | 21/09/2022 | 30 | TANISA ENTERPRISE | 26.3 | 20.62 | 80
1766 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00088/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.42 | 0 | 0
1767 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00218/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.58 | 0 | 0
1768 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00415/2023-2024 | BP-2023-24-340 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.2 | 0 | 0
1769 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000134/2023-2024 | 1385/5/Hug | 15/05/2023 | 0 | Resource Division | 0.46 | 0 | 0
1770 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1771 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Antpukur of Rajhat PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000049/2024-2025 | 552/CH | 14/06/2024 | 7 | M/S BIMAL DAS AND CO. | 1.81 | 1.79 | 80
1772 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation RAJHAT Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000079/2024-2025 | 694/CH | 09/08/2024 | 7 | APEX ENGINEERING | 2.71 | 0 | 0
1773 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of RAJHAT W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000100/2023-2024 | 1419/Hug | 17/05/2023 | 45 | BOSE ENTERPRISE (RATUL BOSE) | 40.33 | 33.37 | 80
1774 | Hooghly Division | Chinsuria Sub-Division | Laying of Pipe Line for necessary interconnection with T.W.& Distribution System For RAJHAT Water Supply Scheme under CHINSURAH Sub-Division of HOOGHLY DIVISION P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000134/2023-2024 | 1476/HUG | 19/05/2023 | 45 | R.K. TRADERS | 29.66 | 29.65 | 100
1775 | Hooghly Division | Chinsuria Sub-Division | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000441/2021-2022 | 459/Hug | 10/03/2022 | 25 | MAHARAJA CONSTRUCTION CO. | 24.32 | 22.43 | 100
1776 | Hooghly Division | Chinsuria Sub-Division | Inter connection work of Rising main from Tube Well no. 6 to existing distribution system at Gotu of Rajhat W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000704/2024-2025 | 58/CH | 10/01/2025 | 5 | M/S BIMAL DAS AND CO. | 0.93 | 0 | 50
1777 | Hooghly Division | Chinsuria Sub-Division | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Rajhat Zone-II W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000771/2023-2024 | 129/CH | 16/02/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 4.94 | 4.94 | 15
1778 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar Babnan Z-I PWSS 2.Uttar Babnan Z-II PWSS 3. Rajhat PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000778/2023-2024 | 147/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.48 | 0.48 | 30
1779 | Hooghly Division | Chinsuria Sub-Division | Diversion of Laying of Distribution Pipeline for Re-construction of Bridge by I & W Dept. at Chatimtala under Rajhat W/S Scheme under Chinsurah Sub Division Of Hooghly Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000791/2023-2024 | 541/HUG | 20/02/2024 | 15 | MINTU CHAKRABORTY | 3.41 | 0 | 0
1780 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in RAJHAT GP of POLBA-DADPUR Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000913/2023-2024 | 246/CH | 12/03/2024 | 30 | M/S BIMAL DAS AND CO. | 4.98 | 4.79 | 100
1781 | Hooghly Division | Chinsuria Sub-Division | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of RAJHAT (Z-II) Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001843/2024-2025 | 220/CH | 19/02/2025 | 30 | MAA JAGADHATRI CONSTRUCTION | 4.63 | 0 | 0
1782 | Hooghly Division | Chinsuria Sub-Division | Repairing of existing Switch room(3.0 M X3.6M)& Boundary wall at existing 2nd T.W Site of RAJHAT (Z-II) Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001845/2024-2025 | 222/CH | 19/02/2025 | 30 | MAA JAGADHATRI CONSTRUCTION | 3.28 | 0 | 0
1783 | Hooghly Division | Chinsuria Sub-Division | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of RAJHAT ZONE-I Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001955/2024-2025 | 277/CH | 20/02/2025 | 10 | MAA JAGADHATRI CONSTRUCTION | 4.66 | 0 | 0
1784 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection at Rajhat w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00841/2022-2023 | 173 | 28/02/2023 | 0 | WBSEDCL | 7.44 | 0 | 0
1785 | Electrical | Chinsuria Sub-Division | Quotation bill for New service connection at Rajhat W/S. Sch Z-I, PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00851/2022-2023 | 173 | 28/02/2023 | 0 | WBSEDCL | 19.98 | 0 | 0
1786 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-I, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000234/2022-2023 | 865/ED | 14/02/2023 | 90 | DIPA CHHETRI | 10.17 | 10.16 | 100
1787 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000835/2023-2024 | 959/HMSD | 20/04/2023 | 30 | SANJIB PRADHAN | 0.39 | 0.39 | 1
1788 | Electrical | Chinsuria Sub-Division | Car hiring and fuel bill for car no. WB02AB3954 from 01.07.2023 to 31.07.2023. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000836/2023-2024 | 363//AE-I/ED | 29/05/2023 | 31 | TRIDIP SARKAR | 0.38 | 0.36 | 1
1789 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100
1790 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of AMDOBA Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000534/2022-2023 | 2735/HUG | 07/12/2022 | 480 | DREAM INFRASTRUCTURE | 4.83 | 3.24 | 60
1791 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area of AMDOBA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000658/2022-2023 | 155/HUG | 16/01/2023 | 50 | AICH CONSTRUCTION | 59.77 | 56.29 | 100
1792 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00297/2023-2024 | BP-2023-24-248 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.82 | 0 | 0
1793 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000156/2023-2024 | 1385/27/Hug | 15/05/2023 | 0 | Resource Division | 0.18 | 0 | 0
1794 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1795 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00090/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.61 | 0 | 0
1796 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00217/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.68 | 0 | 0
1797 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00414/2023-2024 | BP-2023-24-339 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.38 | 0 | 0
1798 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000129/2023-2024 | 1385/Hug | 15/05/2023 | 0 | Resource Division | 0.4 | 0 | 0
1799 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1800 | Hooghly Division | Arambug Sub-Division | Bhabapur Mini PWSS | Assistant Engineer | Arambag Block Junior Engineer (Civill) | BILL/00772/2024-2025 |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0
1801 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | RTOR000181/2023-2024 | 1385/52/Hug | 15/05/2023 | 0 | Resource Division | 0.59 | 0 | 0
1802 | Hooghly Division | Chandannagar Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00345/2023-2024 | BP-2023-24-281 | 16/08/2023 | 0 | GOUR KUMAR DAS | 0.77 | 0 | 0
1803 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of SRIPATIPUR ZONE-II Piped Water Supply Scheme with Construction of switch room, LDS, Boundary Wall, LDS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. Block-SINGUR, District- Hooghly.[AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000018/2023-2024 | 1063/HUG | 12/04/2023 | 90 | SATYA NARAYAN BISWAS | 215.71 | 171.28 | 50
1804 | Hooghly Division | Chandannagar Sub-Division | Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of boundary wall at Proposed H.W site, Rising Main, FHTC For AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000120/2023-2024 | 1470/HUG | 19/05/2023 | 958 | SOUMYADIP DE | 181.5 | 82.92 | 70
1805 | Hooghly Division | Chandannagar Sub-Division | Construction of 400 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of boundary wall at Proposed H.W site, Rising Main, FHTC For AUGMENTATION of SRIPATIPUR ZONE-II Piped Water Supply Schem under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000151/2023-2024 | 1555/HUG | 26/05/2023 | 270 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 227.21 | 40.02 | 20
1806 | Hooghly Division | Chandannagar Sub-Division | Route survey Design drawing & DPR preparation of Sripatipur PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000168/2022-2023 | 263/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.8 | 0
1807 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of SRIPATIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000204/2023-2024 | 1819/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 80.54 | 45
1808 | Hooghly Division | Chandannagar Sub-Division | :Estimate for Supply fitting and fixing of sluice valve for Sripatipur Zone-II Water Supply Scheme Under Chandannagar SubDivision,P.H.E Dte . | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000257/2025-2026 | 905/CHAN | 21/07/2025 | 15 | MAA TARA CONSTRUCTION | 4.92 | 0 | 50
1809 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at old 1st tubewell site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000286/2025-2026 | 919/CHAN | 21/07/2025 | 20 | M/S T.K.B. CONSTRUCTION | 4.18 | 0 | 0
1810 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at old 2nd site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000287/2025-2026 | 920/CHAN | 21/07/2025 | 20 | M/S T.K.B. CONSTRUCTION | 2.09 | 0 | 0
1811 | Hooghly Division | Chandannagar Sub-Division | Providing FHTC for the leftout portion of Sripatipur Mouza of SRIPATIPUR ZONE 1 Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000358/2024-2025 | 3666/HUG | 13/11/2024 | 322 | TRIYA CONSTRUCTION | 36.22 | 0 | 100
1812 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme with Construction of Switch Room, Boundary Wall, LDS, under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. Block-SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000802/2022-2023 | 953/HUG | 30/03/2023 | 90 | MALLIKA ENTERPRISE | 156.56 | 144.41 | 100
1813 | Hooghly Division | Chandannagar Sub-Division | Construction of approach road at head work site of Sripatipur zone-I water supply scheme under Chandannagar Sub-Division P.H.E. Dte.(Part-B) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002213/2024-2025 | 195/Chan | 12/02/2025 | 20 | SOUMYADIP DE | 3.95 | 0 | 0
1814 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000144/2022-2023 | 2686/11/Hug | 01/12/2022 | 0 | Resource Division | 0.35 | 0 | 0
1815 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000207/2022-2023 | 109/7/Hug | 10/01/2023 | 0 | Resource Division | 20.06 | 0 | 0
1816 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000277/2023-2024 | 1383/27/Hug | 15/05/2023 | 0 | Resource Division | 20.33 | 0 | 0
1817 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur W/S Scheme,Zone-I,TW No-I Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03763/2023-2024 | 262 | 05/09/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
1818 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for sripatipur W/S Scheme,Zone-I,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03764/2023-2024 | 261 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
1819 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur w/s scheme,Zone-II,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03765/2023-2024 | 260 | 05/09/2023 | 0 | WBSEDCL | 6.19 | 0 | 0
1820 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur w/s Scheme,Z-I,TW No-3 Block-Haripal,District-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03886/2023-2024 | 299 | 22/09/2023 | 0 | WBSEDCL | 2.5 | 0 | 0
1821 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Sripatipur PWSS, Zone-II, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04486/2023-2024 | 531 | 15/12/2023 | 0 | WBSEDCL | 3.22 | 0 | 0
1822 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sripatipur water supply scheme TW No I II III IV and V, Block Haripal, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000230/2022-2023 | 861/ED | 14/02/2023 | 884 | DEY ENTERPRISE | 53.74 | 52.19 | 65
1823 | Hooghly Division | Chandannagar Sub-Division | Repairing of pump house at 1St and 2nd TW site of Ramnarayanpur PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000291/2025-2026 | 924/CHAN | 21/07/2025 | 20 | BAPPADITYA BANERJEE | 4.38 | 0 | 50
1824 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Samanta Para of Ramnarayanpur PWSS under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000380/2023-2024 | 389/Chan | 09/06/2023 | 15 | KALYAN BANERJEE | 0.93 | 0.92 | 100
1825 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Ketera Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000586/2022-2023 | 2845/HUG | 16/12/2022 | 741 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 22.7 | 12.58 | 100
1826 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Gayeshpur & Bishnubati Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte.1 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2022-2023 | 2846/HUG | 16/12/2022 | 30 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 31.27 | 30.56 | 0
1827 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Gure & Makrar Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000588/2022-2023 | 2847/HUG | 16/12/2022 | 30 | ARATI ENGINEERING | 34.16 | 34.12 | 100
1828 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within Ramnarayanpur Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000778/2022-2023 | 790/HUG | 20/03/2023 | 30 | AHS R INFRA PRIVATE LIMITED | 25.02 | 21.17 | 100
1829 | Hooghly Division | Chandannagar Sub-Division | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Ramnarayanpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000856/2023-2024 | 728/HUG | 05/03/2024 | 45 | SWASTIK ENTERPRISE | 33.9 | 17.91 | 80
1830 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00291/2023-2024 | BP-2023-24-242 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.98 | 0 | 0
1831 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1832 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00296/2023-2024 | BP-2023-24-247 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.69 | 0 | 0
1833 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000151/2023-2024 | 1385/22/Hug | 15/05/2023 | 0 | Resource Division | 0.36 | 0 | 0
1834 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1835 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2025-2026 | 486/CH | 04/04/2025 | 10 | BIMAL KUMAR HALDER | 4.53 | 0 | 100
1836 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of SAPTAGRAM PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000031/2023-2024 | 1131/HUG | 19/04/2023 | 30 | SWARNA ENTERPRISE | 24.19 | 12.67 | 98
1837 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system, FHTC of SAPTAGRAM W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2023-2024 | 1340/HUG | 11/05/2023 | 30 | SWARNA ENTERPRISE | 21.02 | 6.26 | 100
1838 | Hooghly Division | Chinsuria Sub-Division | Construction of 2nos. 3.6 mtr x3.0 mtr Switch Room with Additional Plinth Height, With Sanitary and Water Supply arrangement at Proposed T/W Sites for Saptagram Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at Chinsurah Mogra Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000853/2023-2024 | 736/HUG | 05/03/2024 | 45 | M/S BIMAL DAS AND CO. | 11.17 | 0 | 50
1839 | Hooghly Division | Chinsuria Sub-Division | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Saptagram W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000855/2023-2024 | 737/HUG | 05/03/2024 | 30 | TAPAS ADHYA | 19.53 | 18.89 | 100
1840 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Mithapukur for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001038/2023-2024 | 280/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.97 | 0.97 | 80
1841 | Hooghly Division | Chinsuria Sub-Division | Laying HDPE pipeline for proiving FHTC at different placess at Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001039/2023-2024 | 281/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.96 | 0.96 | 80
1842 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Choto Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001040/2023-2024 | 282/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.96 | 0.96 | 80
1843 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Bara Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001041/2023-2024 | 283/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.97 | 0.97 | 80
1844 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of Switch room at PH-2 of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002010/2024-2025 | 296/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 1.33 | 0 | 100
1845 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000351/2023-2024 | 3004/4/Hug | 05/10/2023 | 0 | Resource Division | 36.39 | 0 | 0
1846 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - I (Dingalghat, bansberia),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643287, dt. - 10-05-2024, Application No. - 5004179261 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00455/2024-2025 | 123 | 17/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
1847 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - II (Chotokhejuria),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643407, dt. - 10-05-2024, Application No. - 5004179275 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00458/2024-2025 | 126 | 17/05/2024 | 0 | WBSEDCL | 5.49 | 0 | 0
1848 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Saptagram w/s scheme, P.H No.- IV, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000314/2022-2023 | 490/HMSD | 02/03/2023 | 30 | M.S.C. ENTERPRISE | 2.49 | 2.47 | 0
1849 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAPTAGRAM PIPED W/S SCHEME, T.W. No. V & VI, Block: Chinsurah Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000352/2024-2025 | 1457/ED | 25/07/2024 | 90 | D. K. ELECTRIC | 22.19 | 5.5 | 70
1850 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saptagram water supply scheme, T.W. No. IV, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001248/2022-2023 | 1318/ED | 17/08/2022 | 90 | M.S.C. ENTERPRISE | 7.28 | 7.28 | 0
1851 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00295/2023-2024 | BP-2023-24-246 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.62 | 0 | 0
1852 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000159/2023-2024 | 1385/30/Hug | 15/05/2023 | 0 | Resource Division | 0.43 | 0 | 0
1853 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1854 | Hooghly Division | Chinsuria Sub-Division | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000326/2023-2024 | 2409/HUG | 11/08/2023 | 30 | OSMAN SEKH | 32.34 | 15 | 100
1855 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under CHINSURAH-MOGRA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000342/2023-2024 | 2427/HUG | 11/08/2023 | 30 | SWASTIK ENTERPRISE | 42.74 | 41.58 | 95
1856 | Hooghly Division | Chinsuria Sub-Division | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of KULIHANDA Piped Water Supply Scheme Under Hooghly Division P.H.E. Dte. within Chinsurah Mogra Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000691/2022-2023 | 327/HUG | 03/02/2023 | 1063 | PREMANANDA ROY BISWAS | 121.55 | 83.44 | 80
1857 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kulihanda[SM/13345] W/S Sch., T/W No. - VII, Sukantanagar, Dt. - Hooghly, Ref. Id. - 503611685, Dt. - 8/04/2024, Application No. - 5004102924 under Pipulpati CCC, WBSEDCL | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00137/2024-2025 | 55 | 12/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
1858 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kulihanda W/S (Aug.)[SM/13345] Scheme, T/W No. - VIII,(Adarsha Nagar, Panditjir Dokan) under Bandel CCC, WBSEDCL, Ref. Id. - 503647843, Dt. - 17-05-2024, Application No. - 5004191804 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00514/2024-2025 | 177 | 30/05/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
1859 | Electrical | Chinsuria Sub-Division | Quotation bill for New Service Connection Kulihanda W/S. Sch. pH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00855/2022-2023 | 175 | 28/02/2023 | 0 | WBSEDCL | 4.33 | 0 | 0
1860 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kulihanda W/S. Sch. TW-VI | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04243/2023-2024 | 420 | 10/11/2023 | 0 | WBSEDCL | 5.1 | 0 | 0
1861 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000162/2022-2023 | 3497/ED | 30/12/2022 | 90 | H.K.DAS & CO. | 10.82 | 10.79 | 100
1862 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No. VI, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000855/2023-2024 | 3529/ED | 18/08/2023 | 90 | N.S. TRADING | 10.56 | 10.27 | 90
1863 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda W/S. Sch. TW-IV, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001136/2022-2023 | 1037/ED | 28/06/2022 | 90 | STANDARD ELECTRICALS | 10.23 | 10.21 | 0
1864 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car/Ambassador (BS-IV) for official use of the Chief Engineer (Electrical/Mechanical) Southern Zone, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001170/2023-2024 | 1072/HMSD | 11/05/2023 | 365 | ORIENTAL ENGINEERING CO. | 0.95 | 1.32 | 80
1865 | Hooghly Division | Arambug Sub-Division | GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000052/2023-2024 | 1520/HUG | 23/05/2023 | 954 | BAPPADITYA BANERJEE | 500 | 295.72 | 20
1866 | Hooghly Division | Arambug Sub-Division | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000311/2024-2025 | 3687/HUG | 14/11/2024 | 331 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0
1867 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000360/2023-2024 | 2452/HUG | 12/08/2023 | 60 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 16.55 | 0 | 0
1868 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2023-2024 | 595/HUG | 22/02/2024 | 393 | BAPPADITYA BANERJEE | 31.58 | 0 | 50
1869 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000052/2023-2024 | 1234/23/Hug | 28/04/2023 | 0 | Resource Division | 70.25 | 0 | 0
1870 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000161/2023-2024 | 1385/32/Hug | 15/05/2023 | 0 | Resource Division | 11.27 | 0 | 0
1871 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000418/2023-2024 | 3057/41/Hug | 11/10/2023 | 0 | Resource Division | 11.27 | 0 | 0
1872 | Electrical | Arambug Sub-Division | Quotation of new Service Connection for Gobindanagar Water supply Scheme,Zone-II,PH No-I Block-Arambag Dist-hooghly under Electrical Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04022/2023-2024 | 314 | 03/10/2023 | 0 | WBSEDCL | 4.73 | 0 | 0
1873 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000173/2022-2023 | 766/ED | 09/02/2023 | 90 | BARISAL TRADING CO. | 20.5 | 0 | 0
1874 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No. III, Block: Goghat-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002472/2023-2024 | 333/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
1875 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 120.14 | 30
1876 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
1877 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000168/2023-2024 | 1385/39/Hug | 15/05/2023 | 0 | Resource Division | 4.96 | 0 | 0
1878 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000428/2023-2024 | 3057/36/Hug | 11/10/2023 | 0 | Resource Division | 4.96 | 0 | 0
1879 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-II,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/14684) Application No-5004136393 Reference Id-503627261. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00327/2024-2025 | 96 | 06/05/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
1880 | Electrical | Arambug Sub-Division | Quotation App. No.-5004182874 SM/14684 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00466/2024-2025 | 117 | 17/05/2024 | 0 | WBSEDCL | 13.85 | 0 | 0
1881 | Electrical | Arambug Sub-Division | Additional Quotation for Shantipur w/s Scheme,Zone-II,PH no-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte,(SM/14684) Application No-100000124534 Reference Id-860319604 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02603/2024-2025 | 636 | 18/12/2024 | 0 | WBSEDCL | 0.91 | 0 | 0
1882 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000182/2022-2023 | 775/ED | 09/02/2023 | 996 | A.G. ENTERPRISE | 20.26 | 0 | 40
1883 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000400/2024-2025 | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0
1884 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RADHABALLAVPUR Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000428/2024-2025 | 3787/HUG | 25/11/2024 | 30 | SUDIPTA SINHA | 16.07 | 0 | 0
1885 | Hooghly Division | Arambug Sub-Division | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 201.51 | 45
1886 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0
1887 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
1888 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000072/2023-2024 | 1234/36/Hug | 28/04/2023 | 0 | Resource Division | 29.41 | 0 | 0
1889 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000185/2023-2024 | 1385/56/Hug | 15/05/2023 | 0 | Resource Division | 13.04 | 0 | 0
1890 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000222/2022-2023 | 127/23/Hug | 13/01/2023 | 0 | Resource Division | 29.92 | 0 | 0
1891 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000470/2023-2024 | 3057/14/Hug | 11/10/2023 | 0 | Resource Division | 13.04 | 0 | 0
1892 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04564/2023-2024 | 573 | 27/12/2023 | 0 | WBSEDCL | 11.45 | 0 | 0
1893 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04565/2023-2024 | 572 | 27/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0
1894 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RADHABALLAVPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000156/2024-2025 | 1179/ED | 14/06/2024 | 90 | BIJAN ENTERPRISE | 10.7 | 0 | 0
1895 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000179/2022-2023 | 772/ED | 09/02/2023 | 90 | BIJAN ENTERPRISE | 20.26 | 0 | 0
1896 | Hooghly Division | Chinsuria Sub-Division | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 553.91 | 20
1897 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000323/2023-2024 | 2407/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 44.87 | 40
1898 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 14.09 | 20
1899 | Hooghly Division | Chinsuria Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-I) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000332/2023-2024 | 2416/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 53.78 | 8.6 | 28
1900 | Hooghly Division | Chinsuria Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-II) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000333/2023-2024 | 2417/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.06 | 8.6 | 30
1901 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000126/2023-2024 | 1264/21/HUG | 03/05/2023 | 0 | Resource Division | 33.14 | 0 | 0
1902 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000239/2023-2024 | 1386/18/Hug | 15/05/2023 | 0 | Resource Division | 31.19 | 0 | 0
1903 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000508/2023-2024 | 3059/13/Hug | 11/10/2023 | 0 | Resource Division | 31.19 | 0 | 0
1904 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dhasghara W/S. Sch. Z-I, TW-II & Z-ii, TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04947/2023-2024 | 676 & 677 | 18/01/2024 | 0 | WBSEDCL | 12.17 | 0 | 0
1905 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05345/2023-2024 | 701 | 22/01/2024 | 0 | WBSEDCL | 12.21 | 0 | 0
1906 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05358/2023-2024 | 700 | 22/01/2024 | 0 | WBSEDCL | 9.7 | 0 | 0
1907 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dashghara water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000252/2022-2023 | 919/ED | 22/02/2023 | 90 | H.K.DAS & CO. | 43.01 | 18.12 | 35
1908 | Hooghly Division | Srirampur Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC For Development of JANGALPARA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000110/2023-2024 | 1439/HUG | 18/05/2023 | 45 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 35.13 | 24.27 | 20
1909 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000324/2023-2024 | 1384/22/Hug | 15/05/2023 | 0 | Resource Division | 2.77 | 0 | 0
1910 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection at Jangalpara W/S. Sch. PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00727/2023-2024 | 34 | 12/05/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
1911 | Electrical | Srirampur Sub-Division | New service connection charges for Jangalpara w/s scheme, PH No.-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01159/2023-2024 | 87 | 12/07/2023 | 0 | WBSEDCL | 0.53 | 0 | 0
1912 | Electrical | Srirampur Sub-Division | New service connection charges for Jangalpara w/s scheme, PH No.-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01160/2023-2024 | 85 | 12/07/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
1913 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangalpara water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001149/2022-2023 | 1501/ED | 28/03/2023 | 338 | INDRANI ENTERPRISE | 10.75 | 10.44 | 75
1914 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000029/2023-2024 | 1129/HUG | 19/04/2023 | 45 | M/S SHIVAM UDYOG | 54.23 | 38.37 | 97
1915 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2023-2024 | 1341/HUG | 11/05/2023 | 45 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 19.81 | 75
1916 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000071/2023-2024 | 1234/35/Hug | 28/04/2023 | 0 | Resource Division | 19.68 | 0 | 0
1917 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000537/2023-2024 | 3059/32/Hug | 11/10/2023 | 0 | Resource Division | 14.49 | 0 | 0
1918 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Augmentation of Dharampur W/S Sch.[SM/15891], T/W No. - II, South Simla, Block - Chinsurah-Mogra Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599481, Dt. - 22-03-2024, Application No. - 5004078318 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00014/2024-2025 | 15 | 04/04/2024 | 0 | WBSEDCL | 7.75 | 0 | 0
1919 | Electrical | Chinsuria Sub-Division | Supply of Fuel for 1(one) no Diesel Luxury Taxi on contract Carriage for the Office of the assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of March 2024. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00164/2024-2025 |  | 12/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1920 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of Submersible Pumping machinery and other Electrical/mechanical equipments etc. including allied works for Dharampur w/s scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00872/2022-2023 | 178 | 02/03/2023 | 0 | H.K.DAS & CO. | 4.32 | 0 | 0
1921 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for DHARAMPUR w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00874/2022-2023 | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 2.72 | 0 | 0
1922 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of Automatic Chlorinator for Dharampur water supply scheme, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00876/2022-2023 | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.76 | 0 | 0
1923 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dharampur W/S Sch. , T/W No. -I (Aug.), Block - Chinsurah-Mogra, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03784/2023-2024 | 282 | 13/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
1924 | Electrical | Chinsuria Sub-Division | Hire Charges Bill for official use office of the Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000987/2023-2024 | 958/HmSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0.39 | 1
1925 | Electrical | Chinsuria Sub-Division | Car Hire Charges Bill for official use of the Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001026/2023-2024 | 958,HMSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0.79 | 50
1926 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 1.57 | 15
1927 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Dharampur water supply scheme, T.W. No. I & II, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001357/2023-2024 | 4693/ED | 08/12/2023 | 90 | BISALAXMI ENTERPRISE | 21.99 | 21.97 | 49
1928 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KANPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000107/2023-2024 | 1427/HUG | 17/05/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 0 | 0
1929 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Kanpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000142/2023-2024 | 1495/HUG | 22/05/2023 | 30 | SONAR BANGLA ENTERPRISE | 11.78 | 0 | 0
1930 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir for KANPUR PWSS Under Arambagh Sub Division Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000384/2024-2025 | 3778/HUG | 25/11/2024 | 40 | MAA JAGADHATRI CONSTRUCTION | 10.4 | 0 | 100
1931 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001151/2022-2023 | 1503/ED | 28/03/2023 | 90 | BISALAXMI ENTERPRISE | 10.73 | 0 | 0
1932 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000140/2023-2024 | 1493/HUG | 22/05/2023 | 30 | SHREEOM ENTERPRISE | 12.1 | 0 | 0
1933 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000091/2023-2024 | 1263/6/Hug | 03/05/2023 | 0 | Resource Division | 9.76 | 0 | 0
1934 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000242/2022-2023 | 127/07/Hug | 13/01/2023 | 0 | Resource Division | 11.35 | 0 | 0
1935 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dakshin Rasulpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001147/2022-2023 | 1499/ED | 28/03/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 0 | 0
1936 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000119/2023-2024 | 1461/HUG | 18/05/2023 | 30 | S. B. CONSTRUCTION | 11.97 | 0 | 0
1937 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000450/2024-2025 | 4081/HUG | 19/12/2024 | 90 | R.K. TRADERS | 20.96 | 0 | 0
1938 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BHANGAMORA PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000773/2022-2023 | 744/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 11.36 | 100
1939 | Hooghly Division | Arambug Sub-Division | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Bhangamora W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001050/2023-2024 | 471/Arg | 05/07/2023 | 15 | MAYA CONSTRUCTION | 0.97 | 0.97 | 100
1940 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Bhangamora W/S. Sch. TW-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03828/2023-2024 | 391 | 03/11/2023 | 0 | WBSEDCL | 7.9 | 0 | 0
1941 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhangamora water supply scheme, T.W. No. I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001145/2022-2023 | 1497/ED | 28/03/2023 | 90 | KAMAKHYA ENTERPRISE | 10.69 | 0 | 0
1942 | Hooghly Division | Chandannagar Sub-Division | Restoration work for the damages Chandannagar Nasibpur Road to Vhadreswar Station road | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01130/2023-2024 | BP-2023-24-853 | 21/02/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 43.24 | 0 | 0
1943 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000054/2023-2024 | 1235/4/Hug | 28/04/2023 | 0 | Resource Division | 34.06 | 0 | 0
1944 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati w/s sch. (Zone - I), T/W -II, dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03626/2023-2024 | 223 | 28/08/2023 | 0 | WBSEDCL | 5.21 | 0 | 0
1945 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati W/s Scheme, Zone - I, T/W - I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04124/2023-2024 | 380 | 25/10/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
1946 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bighati W/S. Sch. TW-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04242/2023-2024 | 423 | 10/11/2023 | 0 | WBSEDCL | 5.25 | 0 | 0
1947 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 20.23 | 80
1948 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Khanakul 2 Block Junior Engineer | RTOR000087/2023-2024 | 1263/2/Hug | 03/05/2023 | 0 | Resource Division | 24.41 | 0 | 0
1949 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Khanakul 2 Block Junior Engineer | RTOR000139/2023-2024 | 1385/10/Hug | 15/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
1950 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Khanakul 2 Block Junior Engineer | RTOR000409/2023-2024 | 3057/59/Hug | 11/10/2023 | 0 | Resource Division | 0.76 | 0 | 0
1951 | Electrical | Arambug Sub-Division | Quotation of new service Connection for Naopara w/s Scheme,PH No-I Block-Khanakul-II, Dist-Hooghly under ED,PHE Dte(SM/16237) Application No-5004015680 Reference Id-503563156 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/06072/2023-2024 | 751 | 16/02/2024 | 0 | WBSEDCL | 0.2 | 0 | 0
1952 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NAOPARA MINI W/S SCHEME, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000168/2024-2025 | 1191/ED | 14/06/2024 | 90 | MAA TARA CONSTRUCTION | 7.52 | 7.23 | 30
1953 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of boundary wall at 3rd Tube well Site of HAZIPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000449/2024-2025 | 4082/HUG | 19/12/2024 | 90 | DAS TRADING | 21.34 | 0 | 0
1954 | Electrical | Arambug Sub-Division | Supply, Delivery & Installation of submersible Pumping Machinery & other allied electrical/mechanical equipments etc. incliding allied works for Hazipur W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | ORD/000522/2021-2022 | 555/ED | 23/03/2022 | 90 | GLACIER ENGINEERING CO. | 6.62 | 0 | 60
1955 | Hooghly Division | Chinsuria Sub-Division | BALIDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block DHANIAKHALI, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2023-2024 | 1363/HUG | 12/05/2023 | 90 | MA KANKALI ENTERPRISE | 85.78 | 85.65 | 92
1956 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Chautara PWSS 2. Hasnan PWSS 3. Bhatua PWSS 4. Balidaha PWSS 5. Dalimba PWSS 6. Simla PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000776/2023-2024 | 142/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 30
1957 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000264/2023-2024 | 1386/43/Hug | 15/05/2023 | 0 | Resource Division | 2.02 | 0 | 0
1958 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000362/2023-2024 | 3004/16/Hug | 05/10/2023 | 0 | Resource Division | 14.45 | 0 | 0
1959 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Balidaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05064/2023-2024 | 682 | 19/01/2024 | 0 | WBSEDCL | 3.71 | 0 | 0
1960 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balidaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000067/2023-2024 | 1922/ED | 15/05/2023 | 90 | D. K. ELECTRIC | 22.6 | 11.01 | 50
1961 | Hooghly Division | Chandannagar Sub-Division | Surging/Development of old tubewell using suitable air compressor to increase the yield at different Water Supply Scheme within Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. (Baruipara 5 Tube Well, Bandipur 3rd Tube Well) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000313/2025-2026 | 958/CHAN | 23/07/2025 | 15 | G. T. AGRO CENTRE | 1.47 | 0 | 100
1962 | Hooghly Division | Chandannagar Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BARUIPARA PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000344/2023-2024 | 2433/HUG | 11/08/2023 | 90 | MALLIKA ENTERPRISE | 95.97 | 95.95 | 50
1963 | Hooghly Division | Chandannagar Sub-Division | Laying of rising main for Interconnection of Laying Distribution System & 7 th Tubewell Including Protection Work of BARUIPARA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000388/2022-2023 | 2141/HUG | 26/09/2022 | 20 | AMBIAN INFRASTRUTTURE | 5.97 | 5.96 | 0
1964 | Hooghly Division | Chandannagar Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of BARUIPARA PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000479/2024-2025 | 4070/HUG | 19/12/2024 | 90 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.04 | 0 | 0
1965 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000400/2024-2025 | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0
1966 | Hooghly Division | Arambug Sub-Division | MAHISGOT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000782/2022-2023 | 861/HUG | 24/03/2023 | 270 | M/S R.M. CONSTRUCTION | 221.92 | 69.65 | 15
1967 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000045/2023-2024 | 1234/18/Hug | 28/04/2023 | 0 | Resource Division | 9.11 | 0 | 0
1968 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000481/2023-2024 | 3057/7/Hug | 11/10/2023 | 0 | Resource Division | 4.35 | 0 | 0
1969 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Mahisgot W/S. Sch. PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06151/2023-2024 | 794 | 22/02/2024 | 0 | WBSEDCL | 20.71 | 0 | 0
1970 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mahishgot water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000082/2023-2024 | 1999/ED | 19/05/2023 | 958 | AMITAVA CHAKRABORTY | 20.29 | 0 | 30
1971 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000222/2024-2025 | 3434/HUG | 03/10/2024 | 360 | DIBYENDU DHARA | 47.26 | 0 | 50
1972 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of POL W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000248/2024-2025 | 3527/HUG | 22/10/2024 | 221 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 32.12 | 0 | 50
1973 | Hooghly Division | Arambug Sub-Division | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 298.46 | 45
1974 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
1975 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000495/2023-2024 | 3057/2/Hug | 11/10/2023 | 0 | Resource Division | 19.44 | 0 | 0
1976 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037073/Quot/03 Reference ID- 503576717 SM Code- 18310 | Assistant Engineer | Junior Engineer (Civill) | BILL/06217/2023-2024 | 820 | 01/03/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1977 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036811/Quot/03 Reference ID- 503576702 SM Code- 18310 | Assistant Engineer | Junior Engineer (Civill) | BILL/06218/2023-2024 | 821 | 01/03/2024 | 0 | WBSEDCL | 3.87 | 0 | 0
1978 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for POL water supply scheme, T.W. No.- I, II & III, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000813/2023-2024 | 3158/ED | 27/07/2023 | 90 | DAS ENTERPRISE | 30.48 | 0 | 0
1979 | Hooghly Division | Chinsuria Sub-Division | Pandua Kulti Road Restoration | Assistant Engineer (Civil) |  | BILL/00670/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 19.73 | 0 | 0
1980 | Hooghly Division | Chinsuria Sub-Division | Feeder road from STKK | Assistant Engineer (Civil) |  | BILL/00673/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.3 | 0 | 0
1981 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR NAKSA DIGSUI INCHURA ROAD | Assistant Engineer (Civil) |  | BILL/00674/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 24.45 | 0 | 0
1982 | Hooghly Division | Chinsuria Sub-Division | Balagarh Inchura Road Restoration | Assistant Engineer (Civil) |  | BILL/00675/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.53 | 0 | 0
1983 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR G.T.ROAD TO SARAI LINK ROAD ROAD | Assistant Engineer (Civil) |  | BILL/00676/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.96 | 0 | 0
1984 | Hooghly Division | Chinsuria Sub-Division | jeerat feeder road STKK to Balagarh | Assistant Engineer (Civil) |  | BILL/00677/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 1.05 | 0 | 0
1985 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR SINGUR UGLY ROAD | Assistant Engineer (Civil) |  | BILL/00678/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 21.76 | 0 | 0
1986 | Hooghly Division | Chinsuria Sub-Division | feeder road from STKK to Balagarh | Assistant Engineer (Civil) |  | BILL/00680/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 6.58 | 0 | 0
1987 | Hooghly Division | Chinsuria Sub-Division | link road from STKK to Borail | Assistant Engineer (Civil) |  | BILL/00682/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.85 | 0 | 0
1988 | Hooghly Division | Chinsuria Sub-Division | Tamba Ilchoba Road Restoration | Assistant Engineer (Civil) |  | BILL/00685/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 9.39 | 0 | 0
1989 | Hooghly Division | Chinsuria Sub-Division | Tamba Kamarpara Road Restoration | Assistant Engineer (Civil) |  | BILL/00687/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.81 | 0 | 0
1990 | Hooghly Division | Chinsuria Sub-Division | Feeder road from STKK to Khamargachi | Assistant Engineer (Civil) |  | BILL/00688/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.03 | 0 | 0
1991 | Hooghly Division | Chinsuria Sub-Division | Feeder road from STKK to Sripur Bazar Road | Assistant Engineer (Civil) |  | BILL/00689/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.27 | 0 | 0
1992 | Hooghly Division | Chinsuria Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD PANDUA ROAD | Assistant Engineer (Civil) |  | BILL/00690/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.96 | 0 | 0
1993 | Hooghly Division | Chinsuria Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD PANDUA KANTAI ROAD | Assistant Engineer (Civil) |  | BILL/00691/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.18 | 0 | 0
1994 | Hooghly Division | Chinsuria Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD RAHIMPUR KALNA ROAD | Assistant Engineer (Civil) |  | BILL/00692/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.15 | 0 | 0
1995 | Hooghly Division | Chinsuria Sub-Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Pandua Block in Hooghly District with three months trial run & subsequent O&M for one year.. | Assistant Engineer (Civil) |  | ORD/000594/2023-2024 | 3309/HUG | 10/11/2023 | 783 | ECO PROTECTIONENGINEERS PVT LTD. | 19490.9 | 3306.97 | 25
1996 | Hooghly Division | Chinsuria Sub-Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh Block in Hooghly District with three months trial run & subsequent O&M for one year. | Assistant Engineer (Civil) |  | ORD/000595/2023-2024 | 3310/HUG | 10/11/2023 | 783 | ECO PROTECTIONENGINEERS PVT LTD. | 11029.1 | 1717.6 | 35
1997 | Hooghly Division | Chinsuria Sub-Division | Construction of 16.75 m X 12 m Pumphouse including plinth protection and surface drain at Pandua IBS-I site ofSurface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000605/2023-2024 | 3347/HUG | 17/11/2023 | 180 | MS PRADIP KUMAR PAL | 64.72 | 0 | 0
1998 | Hooghly Division | Chinsuria Sub-Division | Construction of 16.75 m X 12 m Pumphouse including plinth protection and surface drain at Pandua IBS-II site ofSurface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000606/2023-2024 | 3348/HUG | 17/11/2023 | 180 | R.G. INFRASTRUCTURE | 64.76 | 0 | 0
1999 | Hooghly Division | Chinsuria Sub-Division | Construction of C.W.R. (Clear water Reservoir) of capacity 350 Cu.m / 77000 Gallons & allied Work at Pandua IBS-I site of Surface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000607/2023-2024 | 3349/HUG | 17/11/2023 | 180 | MS PRADIP KUMAR PAL | 37.76 | 0 | 0
2000 | Hooghly Division | Chinsuria Sub-Division | Construction of C.W.R. (Clear water Reservoir) of capacity 450 Cu.m / 9900 Gallons & allied Work at Pandua IBS-II site of Surface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000608/2023-2024 | 3350/HUG | 17/11/2023 | 180 | R.G. INFRASTRUCTURE | 47.67 | 0 | 0
2001 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000546/2023-2024 | 3059/23/Hug | 11/10/2023 | 0 | Resource Division | 638.35 | 0 | 0
2002 | Electrical | Chinsuria Sub-Division | Supply, delivery, installation & Commissioning of Electro Mechanical machinery for Intermediate Pumping Station (IPS-I) to be installed at Boinchi Gram and Intermediate Pumping Station (IPS-2) to be installed at Damdama Gram under Balagarh-Pandua Surface Based Pipe Water Supply Scheme, in the Dist. of Hooghly under Electrical Division, P.H.E, Dte. | Assistant Engineer (Civil) |  | ORD/000007/2025-2026 | 660/ED | 24/04/2025 | 30 | M/S S.S. ENTERPRISE | 234.37 | 0 | 0
2003 | Hooghly Division | Arambug Sub-Division | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 103.17 | 30
2004 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of BULUNDI W/S Scheme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001532/2024-2025 | 3617/HUG | 05/11/2024 | 180 | S & P ENTERPRISE | 48.46 | 0 | 70
2005 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000411/2023-2024 | 3057/46/Hug | 11/10/2023 | 0 | Resource Division | 15.4 | 0 | 0
2006 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182766 Reference Id-503644453. | Assistant Engineer | Junior Engineer (Civill) | BILL/00447/2024-2025 | 121 | 17/05/2024 | 0 | WBSEDCL | 4.54 | 0 | 0
2007 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme, PH No-III Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182716 Reference Id-503644451. | Assistant Engineer | Junior Engineer (Civill) | BILL/00448/2024-2025 | 119 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
2008 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme,PH No-IV Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004416593 Reference Id-503753758 | Assistant Engineer | Junior Engineer (Civill) | BILL/01984/2024-2025 | 475 | 01/10/2024 | 0 | WBSEDCL | 7.6 | 0 | 0
2009 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004415806 Reference Id-503753690 | Assistant Engineer | Junior Engineer (Civill) | BILL/01985/2024-2025 | 476 | 01/10/2024 | 0 | WBSEDCL | 8.08 | 0 | 0
2010 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000130/2024-2025 | 1155/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0
2011 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000131/2024-2025 | 1156/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0
2012 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balundi water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000912/2023-2024 | 3583/ED | 28/08/2023 | 90 | M/S G P ENTERPRISE | 21.47 | 0 | 0
2013 | Hooghly Division | Srirampur Sub-Division | Bilaspur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House, 450 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, DiSt- Hooghly under Hooghly Divn.PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2022-2023 | 639/Hug | 01/04/2022 | 1117 | PRADIP KUMAR ADHYA | 447.88 | 421.2 | 90
2014 | Hooghly Division | Srirampur Sub-Division | Bilaspur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (New Scheme) (2nd Call) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2022-2023 | 755/Hug | 11/04/2022 | 12 | S. HATI | 507.65 | 507.48 | 99
2015 | Hooghly Division | Srirampur Sub-Division | Construction of Protection Wall at O.H.R. Site from Flood Water for Bilaspur Zone-I Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000111/2022-2023 | 449/SER | 31/05/2022 | 45 | PRADIP KUMAR ADHYA | 4.99 | 4.97 | 0
2016 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Bilaspur & Guti-Atra mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000191/2024-2025 | 534/SER | 17/09/2024 | 7 | ASHA ENTERPRISE | 4.97 | 4.95 | 99
2017 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Guti-Atra & Singti mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000194/2024-2025 | 537/SER | 17/09/2024 | 7 | ASHA ENTERPRISE | 4.97 | 4.97 | 99
2018 | Hooghly Division | Srirampur Sub-Division | Sinking of 2 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 5th Tube Well Site of BILASPUR W/S Scheme & 3rd Tube Well Site of JANAI W/S Scheme(ZONE-I) under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000252/2024-2025 | 3523/HUG | 22/10/2024 | 102 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 29.4 | 3.74 | 50
2019 | Hooghly Division | Srirampur Sub-Division | Protection works and other allied works at Head Work Site & 2nd Tube Well Site of Bilaspur Zone-II under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000442/2024-2025 | 4044/HUG | 19/12/2024 | 90 | M/S. S.G. CONSTRUCTION | 30.66 | 0 | 0
2020 | Hooghly Division | Srirampur Sub-Division | Laying of leftout pipeline and providing leftout FHTC and construction of Drain connecting to nearest Drain Culvert at Head work site,Land Development at 3rd Tubwell Site,Construction of Toilet ,Septic tank,soak well ,Plumbing work at 2nd Tubewell site at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000465/2024-2025 | 4047/HUG | 19/12/2024 | 90 | PRADIP KUMAR ADHYA | 40.81 | 0 | 0
2021 | Hooghly Division | Srirampur Sub-Division | Construction of balance portion of Boundary Wall, Land Development, Pathway, Drain at H/W Site & 2nd T/W Site and Other allied works at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000662/2023-2024 | 3561/HUG | 06/12/2023 | 60 | PRADIP KUMAR ADHYA | 51.59 | 50.49 | 80
2022 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000780/2023-2024 | 537/HUG | 20/02/2024 | 285 | SRI KRISHNA ENTERPRISE | 12.1 | 6.3 | 60
2023 | Hooghly Division | Srirampur Sub-Division | Balance LDS and Other works within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000784/2023-2024 | 531/HUG | 20/02/2024 | 15 | GOURI ENTERPRISE | 13.52 | 13.35 | 99
2024 | Hooghly Division | Srirampur Sub-Division | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000805/2023-2024 | 589/HUG | 22/02/2024 | 587 | ROY ENTERPRISE | 13.53 | 6.72 | 99
2025 | Hooghly Division | Srirampur Sub-Division | Laying of Balance portion of Additional Pipeline including other allied works at Borhal Mouza in Bilaspur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000806/2023-2024 | 590/HUG | 22/02/2024 | 120 | BAKSHI ENTERPRISE | 17.55 | 10.02 | 75
2026 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Borhal Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000852/2023-2024 | 734/HUG | 05/03/2024 | 120 | SRI KRISHNA ENTERPRISE | 18.31 | 16.73 | 90
2027 | Hooghly Division | Srirampur Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Paschim Gobindapur mouza of Bilaspur Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000858/2023-2024 | 740/HUG | 05/03/2024 | 60 | RAJU CONSTRUCTION | 32.26 | 0 | 20
2028 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of Pashpur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001255/2024-2025 | 55/SER | 20/01/2025 | 7 | ROY ENTERPRISE | 5 | 0 | 0
2029 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of Ranjapur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001256/2024-2025 | 56/SER | 20/01/2025 | 7 | ROY ENTERPRISE | 5 | 0 | 0
2030 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000001/2022-2023 | 986/Hug | 19/05/2022 | 0 | Resource Division | 33.77 | 0 | 0
2031 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000002/2022-2023 | 987/Hug | 19/05/2022 | 0 | Resource Division | 9.33 | 0 | 0
2032 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000015/2023-2024 | 1107/3/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0
2033 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000261/2022-2023 | 610/Hug | 02/03/2023 | 0 | Resource Division | 39.18 | 0 | 0
2034 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000313/2023-2024 | 1384/10/Hug | 15/05/2023 | 0 | Resource Division | 38.51 | 0 | 0
2035 | Hooghly Division | Srirampur Sub-Division | BIG DIA TUBE WELL | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001840/2021-2022 |  | 19/01/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0
2036 | Hooghly Division | Srirampur Sub-Division | BIG DIA TUBE WELL | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001841/2021-2022 |  | 19/01/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0
2037 | Hooghly Division | Srirampur Sub-Division | Central Drilling Payment | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002416/2021-2022 | C022228292462 | 09/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0
2038 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bilaspur PWSS Zone-II, P.H. No.-III, Hooghly. Application No. 5004065667 Ref ID: 503592945 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00111/2024-2025 | 45 | 09/04/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
2039 | Electrical | Srirampur Sub-Division | Fuel Charge | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00783/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.17 | 0 | 0
2040 | Electrical | Srirampur Sub-Division | Fuel Charge | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00784/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0
2041 | Electrical | Srirampur Sub-Division | car hire charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00785/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.15 | 0 | 0
2042 | Electrical | Srirampur Sub-Division | fuel charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00786/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.07 | 0 | 0
2043 | Electrical | Srirampur Sub-Division | Hire Charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00787/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.18 | 0 | 0
2044 | Electrical | Srirampur Sub-Division | Fuel Charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00788/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0
2045 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bilaspur water supply scheme Zone-I, T.W. No. II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00856/2022-2023 |  | 27/02/2023 | 0 | A.S. ENTERPRISE | 10.23 | 0 | 0
2046 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-II, TW-I, Dist- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2022-2023 | 779/ED | 05/05/2022 | 90 | H.K.DAS & CO. | 10.5 | 10.5 | 0
2047 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M allied works for Bilaspur W/S. Sch. Hooghly Z-II, TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000361/2022-2023 | 780/,ED | 05/05/2022 | 90 | TAMAL ENTERPRISE | 10.55 | 10.51 | 5
2048 | Electrical | Srirampur Sub-Division | Supply & installation of LED board and outside display board for depicting details of pump/valve operators at Zone-I, P.H. No.I & II of Bilashpur w/s scheme, Dist.-Hooghly under ED, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000362/2022-2023 | 2410/HMSD | 30/12/2022 | 10 | DIPA CHHETRI | 0.84 | 0.84 | 0
2049 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Bilaspur W/S. Sch. TW- II, Z-I, Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000862/2022-2023 | 913 /ED | 07/06/2022 | 90 | A.S. ENTERPRISE | 10.48 | 10.23 | 0
2050 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-I, TW-I, Dist- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001165/2021-2022 | 778/ED | 05/02/2022 | 90 | M/S DAS ENTERPRISE | 10.52 | 10.26 | 0
2051 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone-II, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002578/2023-2024 | 454/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 65
2052 | Electrical | Srirampur Sub-Division | Electric Supply | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001992/2022-2023 | 13 | 04/07/2022 | 0 | WBSEDCL | 19.89 | 0 | 0
2053 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE WITHIN JANGIPARA BLOCK UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000171/2021-2022 | 1013/CDD | 15/12/2021 | 30 | PADMA ENGINEERING & CO. | 12.61 | 10.54 | 0
2054 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY WITHIN GHATAL BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000172/2021-2022 | 479/ CDD | 07/09/2021 | 30 | PADMA ENGINEERING & CO. | 14.74 | 11.14 | 0
2055 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY JOHN-1500-III RIG MACHINE UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000173/2021-2022 | 476 /CDD | 06/09/2021 | 30 | PADMA ENGINEERING & CO. | 14.74 | 11.18 | 0
2056 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000174/2021-2022 | 1015/CDD | 15/12/2021 | 30 | PADMA ENGINEERING & CO. | 12.61 | 11.16 | 0
2057 | Central Drilling | Srirampur Sub-Division | ADDITIONAL DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III AT BILASPUR ZONE-I, TW-I WITHIN JANGIPARA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000175/2021-2022 | 07/CMSD-I | 04/01/2022 | 10 | PADMA ENGINEERING & CO. | 0.76 | 0.58 | 0
2058 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BHABANIPUR CHAR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000188/2022-2023 | 1655/Hug | 16/08/2022 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 5.19 | 5.18 | 0
2059 | Hooghly Division | Chinsuria Sub-Division | Providing 1350 nos Functional Household Tap Connection (FHTC) within the Bhabanipur Char Mouza of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000452/2021-2022 | 470/Hug | 10/03/2022 | 60 | MALLIKA ENTERPRISE | 62.56 | 62.61 | 0
2060 | Hooghly Division | Chinsuria Sub-Division | Providing 350 nos Functional Household Tap Connection (FHTC) within the Durllabhpur, Gournagar & Raninagar Mouzas of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000453/2021-2022 | 471/Hug | 10/03/2022 | 60 | BOSE ENTERPRISE (RATUL BOSE) | 17.42 | 16.63 | 0
2061 | Hooghly Division | Chandannagar Sub-Division | Augmentation of PASCHIM GOPINATHPUR Water Supply Scheme with Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS, Rising Main, Construction of Switch Room (5.40 m x 3.60 m ), FHTC Work, Repairing of 2 Nos. existing Switch Room (3.6 m x 3.0m), Boundary Wall at O.H.R Site, Boundary wall at 2nd & 3 rd Tube well at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000047/2022-2023 | 831/Hug | 20/04/2022 | 300 | M/S S.S. ENTERPRISE | 464.29 | 399.84 | 100
2062 | Hooghly Division | Chandannagar Sub-Division | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000088/2022-2023 | 220/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.98 | 4.72 | 100
2063 | Hooghly Division | Chandannagar Sub-Division | Damage road repairing at different location at Panchgachia mouza under Paschim Gopinathpur PWSS under Haripal block of the Chandannagar sub division under Chandannagar Sub division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000296/2025-2026 | 929/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.98 | 0 | 0
2064 | Hooghly Division | Chandannagar Sub-Division | Damage road repairing at different location at Sodpur mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000303/2025-2026 | 936/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.96 | 0 | 0
2065 | Hooghly Division | Chandannagar Sub-Division | Damage road repairing at different location at Mora mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000304/2025-2026 | 937/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.97 | 0 | 0
2066 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Paschim Gopinathpur PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000475/2021-2022 | 167/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.77 | 3.7 | 0
2067 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000031/2022-2023 | 1125/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2068 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000039/2022-2023 | 1370/Hug | 06/07/2022 | 0 | Resource Division | 101.79 | 0 | 0
2069 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000142/2022-2023 | 2686/9/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0
2070 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000144/2021-2022 | 157/11/Hug | 24/01/2022 | 0 | Resource Division | 1.03 | 0 | 0
2071 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000149/2022-2023 | 01/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
2072 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000153/2021-2022 | 423/4/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
2073 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000212/2023-2024 | 1383/15/Hug | 15/05/2023 | 0 | Resource Division | 2.43 | 0 | 0
2074 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000235/2022-2023 | 109/8/Hug | 10/01/2023 | 0 | Resource Division | 45.2 | 0 | 0
2075 | Electrical | Chandannagar Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Auf. of Paschim Gopinathpur W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00059/2022-2023 | 121 | 28/12/2022 | 0 | WBSEDCL | 2.54 | 0 | 0
2076 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Paschin Gopinathpur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00906/2022-2023 | 184 | 10/03/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
2077 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000056/2022-2023 | 2047/ED | 01/12/2022 | 90 | MAHADEV ENTERPRISE | 10.17 | 10.16 | 30
2078 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000254/2022-2023 | 921/ED | 22/02/2023 | 90 | MOITRA ENGINEERING CO. | 10.68 | 10.38 | 0
2079 | Central Drilling | Chandannagar Sub-Division | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000103/2022-2023 | 390/CMSD-II(D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 2.1 | 1.76 | 0
2080 | Central Drilling | Chandannagar Sub-Division | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CNSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000104/2022-2023 | 389/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 2.91 | 2.09 | 0
2081 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000105/2022-2023 | 387/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 3.14 | 2.97 | 0
2082 | Central Drilling | Chandannagar Sub-Division | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT , CDD, PHR DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000106/2022-2023 | 388/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 2.44 | 2.44 | 0
2083 | Central Drilling | Chandannagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well(250mm x 200mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Paschim Gopinathpur WS Scheme TW-I , Haripal Block under Hooghly District , CDD,PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000280/2022-2023 | 1130/CDD | 04/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 11.28 | 9.94 | 0
2084 | Central Drilling | Chandannagar Sub-Division | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000293/2022-2023 | 440/CMSD-II | 12/09/2022 | 15 | M/S S.K.GHOSH & CO. | 3.06 | 1.43 | 0
2085 | Hooghly Division |  | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-II PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000104/2023-2024 | 1424/HUG | 17/05/2023 | 45 | RANA ENTERPRISE | 23.85 | 20.43 | 100
2086 | Hooghly Division |  | Protection works and other allied works at Head Work Site of PURBA THAKURANICHAK under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000467/2024-2025 | 4049/HUG | 19/12/2024 | 90 | M/S. R. M. CONSTRUCTION | 23.91 | 0 | 0
2087 | Hooghly Division |  | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000591/2023-2024 | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0
2088 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000644/2023-2024 | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0
2089 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PURBA THAKURANICHAK PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000372/2024-2025 | 1455/ED | 25/07/2024 | 90 | M.S. ENTERPRISE | 22.21 | 0 | 0
2090 | Hooghly Division | Srirampur Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD KALACHARA BHAGABATIPUR ROAD | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00684/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 96.95 | 0 | 0
2091 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT BHAGABATIPUR Zone-I HW SITE AND 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | ORD/000135/2024-2025 | 424/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 95
2092 | Hooghly Division | Srirampur Sub-Division | BHAGABATIPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | ORD/000280/2023-2024 | 2320/HUG | 04/08/2023 | 662 | S GHOSH AND ASSOCIATES PVT LTD. | 570.37 | 42.94 | 20
2093 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bhagabatipur-I PWSS 2. Bhagabatipur-II PWSS 3. Jagmohanpur PWSS 4. Bandhpur PWSS 5. Haripur PWSS 6. Pairagacha PWSS | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | ORD/000940/2023-2024 | 110/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
2094 | Hooghly Division | Srirampur Sub-Division | BHAGABATIPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | ORD/001026/2023-2024 | 2021/HUG | 11/07/2023 | 633 | TIRUPATI ENTERPRISES | 498.14 | 305.03 | 30
2095 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | RTOR000503/2023-2024 | 3060/6/Hug | 11/10/2023 | 0 | Resource Division | 26.05 | 0 | 0
2096 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-II, Hooghly. Application No. 5004042700 Ref ID: 503581618 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00119/2024-2025 | 44 | 09/04/2024 | 0 | WBSEDCL | 10.61 | 0 | 0
2097 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004066730 Ref ID: 503597305 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00236/2024-2025 | 87 | 23/04/2024 | 0 | WBSEDCL | 4.55 | 0 | 0
2098 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-I, Hooghly. Application No. 5004034017 Ref ID: 503576013 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00237/2024-2025 | 86 | 23/04/2024 | 0 | WBSEDCL | 5.36 | 0 | 0
2099 | Electrical | Srirampur Sub-Division | Quotation for new service connection of Bhogatipur W/S. Sch. PH-I | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/06052/2023-2024 | 739 | 08/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0
2100 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, Zone - I, T.W. No. I & II and Zone - II, T.W. No. I & II, Block: Chanditala-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | ORD/000940/2023-2024 | 3619/ED | 29/08/2023 | 90 | M/S BIPUL BANERJEE | 46.53 | 33.79 | 60
2101 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 3057/53/Hug | 11/10/2023 | 0 | Resource Division | 1.82 | 0 | 0
2102 | Electrical |  | Quotation of New Service Connection for Gopaldaha w/s Scheme,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/19015) Application No-5004148688, Reference Id-503632547 |  |  | BILL/00414/2024-2025 | 100 | 06/05/2024 | 0 | WBSEDCL | 12.59 | 0 | 0
2103 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopaldaha water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001654/2023-2024 | 05/ED | 02/01/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 20.49 | 7.46 | 20
2104 | Hooghly Division |  | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underKhanakul I & II &Goghat I & II Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/000162/2024-2025 | 2831/HUG | 09/08/2024 | 15 | HORIZEN | 1.6 | 0 | 100
2105 | Hooghly Division |  | Construction of 2 nos new Pump House, Repairing and Renovation of Store cum Office room, Boundary wall of Khanakul PWSS under Arambagh Sub Division, PHE Dte. (2nd Call of WBPHE/EE/20/HUG/2024-25; SL-3) |  |  | ORD/000273/2025-2026 | 1495/HUG | 11/06/2025 | 60 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 23.44 | 0 | 100
2106 | Hooghly Division |  | Augmentation of KHANAKUL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] |  |  | ORD/000304/2023-2024 | 2368/HUG | 08/08/2023 | 601 | M/S. NANDY ENTERPRISE | 382.9 | 19.26 | 20
2107 | Hooghly Division |  | Augmentation of KHANAKUL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] |  |  | ORD/000317/2023-2024 | 2392/HUG | 10/08/2023 | 270 | SUBHANKAR BANERJEE | 387.3 | 43.69 | 15
2108 | Hooghly Division |  | Sinking of 3rd tube-well by D.R. Rig method , Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000812/2023-2024 | 592/HUG | 22/02/2024 | 60 | TOTON MONDAL | 29.75 | 0 | 0
2109 | Hooghly Division |  | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000813/2023-2024 | 596/HUG | 22/02/2024 | 540 | ANIRUDDHA FARUQUE | 29.6 | 13.16 | 50
2110 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos |  |  | ORD/002646/2024-2025 | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
2111 | Electrical |  | Quotation money deposition for new service connection at Khanakul W/S Zone- I ,T.W No.-I , Hooghly APP. No.- 5004036875 SM/18645 |  |  | BILL/06213/2023-2024 | 824 | 01/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
2112 | Electrical |  | Quotation money deposition for new service connection at khanakul w/s scheme, zone-II, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036737/Quot/03 Reference ID- 503576720 SM Code- 18645 |  |  | BILL/06214/2023-2024 | 823 | 01/03/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
2113 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000157/2024-2025 | 1180/ED | 14/06/2024 | 382 | M/S A.K BANERJEE | 10.73 | 0 | 50
2114 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000158/2024-2025 | 1181/ED | 14/06/2024 | 630 | M/S A.K BANERJEE | 10.74 | 0 | 10
2115 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Khanakul water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000929/2023-2024 | 3600/ED | 28/08/2023 | 90 | M/S S.R. ENTERPRISE | 21.49 | 0 | 0
2116 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 27.43 | 30
2117 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0
2118 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR I GP of DHANIAKHALI Block. |  |  | ORD/000915/2023-2024 | 250/CH | 12/03/2024 | 30 | SRI KRISHNA ENTERPRISE | 4.99 | 3.29 | 70
2119 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR II GP of DHANIAKHALI Block. |  |  | ORD/000916/2023-2024 | 251/CH | 12/03/2024 | 30 | JOY GURU ENTERPRISE | 4.99 | 1.31 | 100
2120 | Hooghly Division |  | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB DIVISION UNDER HOOGHLY DIVISION, PHE DTE. |  |  | ORD/001462/2024-2025 | 125/CH | 29/01/2025 | 10 | RAJMAHAL ENTERPRISE | 4.85 | 0 | 0
2121 | Hooghly Division |  | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. |  |  | ORD/001841/2024-2025 | 218/CH | 19/02/2025 | 30 | RAJMAHAL ENTERPRISE | 3.25 | 0 | 0
2122 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001247/2023-2024 | 4497/ED | 23/11/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0
2123 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0
2124 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 10.87 | 60
2125 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Musuria village under Balagrh Block, Akna village of Chinsurah Magra Block and Benabharui village of Chinsurah Magra Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000984/2023-2024 | 258/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100
2126 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at 2nd TW Site (PH-2) of Ektarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at BALAGARH Block |  |  | ORD/001853/2024-2025 | 232/CH | 19/02/2025 | 25 | MAA BUNAMATA ENTERPRISE | 2.99 | 0 | 100
2127 | Electrical |  | Quotation for new service connection for source Augmentation of EKTARPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18935), Reference Id- 503777877 Application no- 5004449206 |  |  | BILL/02273/2024-2025 | BP-24-25-581 | 19/11/2024 | 0 | WBSEDCL | 11.08 | 0 | 0
2128 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001208/2023-2024 | 4486/ED | 23/11/2023 | 90 | CINZANO | 21.5 | 0 | 0
2129 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000578/2023-2024 | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 60
2130 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Darbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001881/2024-2025 | 244/CH | 19/02/2025 | 10 | SUNITI MAIRA | 2.72 | 0 | 0
2131 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001910/2024-2025 | 261/CH | 20/02/2025 | 10 | BASU & SONS | 4.75 | 0 | 0
2132 | Hooghly Division |  | Repairing & Renovation of Switch room and Store Room at H/W Site Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001911/2024-2025 | 262/CH | 20/02/2025 | 10 | BASU & SONS | 2.85 | 0 | 0
2133 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001212/2023-2024 | 4490/ED | 23/11/2023 | 647 | M/S S.R. ENTERPRISE | 21.81 | 0 | 90
2134 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 60
2135 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 29.56 | 40
2136 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Chapta PWSS 2. Haral PWSS 3. Namajgram PWSS 4. Rameswerpur PWSS 5. Depara PWSS 6. Sripur Pandua PWSS |  |  | ORD/000828/2023-2024 | 206/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
2137 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Chapta PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001860/2024-2025 | 240/CH | 19/02/2025 | 10 | R.K. TRADERS | 4.79 | 0 | 0
2138 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Chapta PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001909/2024-2025 | 259/CH | 20/02/2025 | 10 | R.K. TRADERS | 2.23 | 0 | 0
2139 | Electrical |  | Quotation for new service connection for source Augmentation of CHAPTA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18940), Reference Id- 503729663 Application no- 5004376500 |  |  | BILL/01968/2024-2025 | 473 | 01/10/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
2140 | Electrical |  | Quotation for new service connection for source Augmentation of Chapta Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18940), Reference Id- 503751380 Application no- 5004412432 |  |  | BILL/02292/2024-2025 | BP-24-25-593 | 21/11/2024 | 0 | WBSEDCL | 8.08 | 0 | 0
2141 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001213/2023-2024 | 4491/ED | 23/11/2023 | 770 | MAA KALI ENTERPRISE | 21.49 | 0 | 50
2142 | Hooghly Division | Arambug Sub-Division | Augmentation of DIHIBATPUR Piped Water Supply Scheme with Sinking of 3 Nos. Tube Well within ZONE-I & II, Construction of 300 cum capacity RCC OHR in ZONE-I & Construction of 250 cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW site, LDS, Rising Main, FHTC, construction of 1 No. switch-room & boundary wall in ZONE-I & construction of 2 Nos. switch-room & 3 nos boundary wall , LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000288/2023-2024 | 2340/HUG | 07/08/2023 | 817 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 869.52 | 113.96 | 30
2143 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DIHIBATPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000807/2023-2024 | 597/HUG | 22/02/2024 | 60 | AMBIAN INFRASTRUCTURE | 29.67 | 0 | 0
2144 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Dihibatpur T/W-VI W/S scheme under Electrical Division PHE Dte. (SM/18670) | Assistant Engineer | Junior Engineer (Civill) | BILL/01615/2024-2025 | 373 | 12/08/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
2145 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VI, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000159/2024-2025 | 1182/ED | 14/06/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 10.73 | 0 | 0
2146 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VII, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000160/2024-2025 | 1183/ED | 14/06/2024 | 90 | STANDARD ELECTRICALS | 10.75 | 0 | 0
2147 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dihibatpur water supply scheme, T.W. No.- I, II & III, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000843/2023-2024 | 3411/ED | 10/08/2023 | 90 | B.T. PROJECT PVT. LTD. | 32.89 | 0 | 0
2148 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibatpur water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002469/2023-2024 | 330/ED | 21/02/2024 | 90 | AMIT DAS | 10.72 | 0 | 0
2149 | Hooghly Division |  | Laying HDPE pipeline at Dunlop of KEOTA Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000072/2024-2025 | 630/CH | 15/07/2024 | 10 | BIMAL KUMAR HALDER | 4.85 | 4.84 | 55
2150 | Hooghly Division |  | Laying of pipe line for improvement of water supply in distribution system at Keota & Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. |  |  | ORD/000516/2023-2024 | 823/CH | 31/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.96 | 0.96 | 80
2151 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 20
2152 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 50
2153 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of KEOTA Piped Water Supply Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001279/2023-2024 | 4519/ED | 23/11/2023 | 90 | SUJOY RANJAN BHOWMICK | 10.74 | 0 | 0
2154 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 20
2155 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.72 | 50
2156 | Hooghly Division |  | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP II GP of DHNIAKHALI Block. |  |  | ORD/000914/2023-2024 | 249/CH | 12/03/2024 | 30 | M/S MANGALCHANDI CONSTRUCTION | 4.98 | 0 | 89
2157 | Hooghly Division |  | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/001550/2024-2025 | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0
2158 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HASAMPUR Piped Water Supply Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001288/2023-2024 | 4520/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0
2159 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0
2160 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 80
2161 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Jamgram PWSS 2. Pandua Z-I PWSS 3. Pandua Z-II PWSS 4. Pandua Z-III PWSS 5. Shibrai PWSS |  |  | ORD/000829/2023-2024 | 207/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.79 | 0.79 | 50
2162 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Benipukur Mini PWSS 2. Baro Nekua Mini PWSS 3. Muragacha (Bakulia) Mini PWSS 4. Arji Aschitpur Mini PWSS 5. Jamgram Mondalai Arsenic PWSS 6. Illampur Arsenic PWSS |  |  | ORD/000832/2023-2024 | 210/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 45
2163 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jamgram village under Pandua Block, Mandalai village of Pandua Block and Sadhat village of Pandua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/000988/2023-2024 | 262/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100
2164 | Hooghly Division |  | Repairing & Renovation of Switch room and Store room at H/W Site of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001874/2024-2025 | 242/CH | 19/02/2025 | 10 | M/S BIMAL DAS AND CO. | 3.07 | 0 | 0
2165 | Hooghly Division |  | Repairing & Renovation of Switch room at PH-2 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001914/2024-2025 | 265/CH | 20/02/2025 | 10 | M/S BIMAL DAS AND CO. | 1.56 | 0 | 0
2166 | Hooghly Division |  | Repairing & Renovation of Switch room at PH-3 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001924/2024-2025 | 273/CH | 20/02/2025 | 10 | M/S BIMAL DAS AND CO. | 1.4 | 0 | 0
2167 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001264/2023-2024 | 4509/ED | 23/11/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 0
2168 | Hooghly Division |  | Preparation of DPR for Augmentation HANRAL Z-II Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. |  |  | ORD/000076/2024-2025 | 691/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.03 | 0 | 0
2169 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0
2170 | Hooghly Division |  | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Rashulpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. |  |  | ORD/000886/2023-2024 | 810/HUG | 11/03/2024 | 30 | M/S BIMAL DAS AND CO. | 9.01 | 8.94 | 80
2171 | Hooghly Division |  | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Maheswarpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. |  |  | ORD/000887/2023-2024 | 811/HUG | 11/03/2024 | 30 | M/S BIMAL DAS AND CO. | 9.75 | 9.69 | 80
2172 | Electrical |  | Quotation for new service connection for Hanral (S.Aug) T.W. - I [SM/18948] (Sekendarpur), Block - Polba-Dadpur, Dt. - Hooghly under WBSEDCL, Dadpur CCC, Ref. Id. -503739105, Dt. - 21-11-2024, Application No. - 5004394547 |  |  | BILL/02479/2024-2025 | 617 | 05/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
2173 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HANRAL Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001267/2023-2024 | 4512/ED | 23/11/2023 | 630 | KUSHANI ENTERPRISE | 10.74 | 0 | 30
2174 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-II, T.W. No. III, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001951/2023-2024 | 90/ED | 10/01/2024 | 540 | WIZARDTECH SOLUTION | 10.68 | 0 | 90
2175 | Hooghly Division | Arambug Sub-Division | Providing 720 nos FHTC in Bali Village under Bali PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000075/2020-2021 | 1540/Hug | 24/11/2020 | 181 | S.K. GHOSH | 31.88 | 63.75 | 100
2176 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000851/2021-2022 |  | 21/09/2021 | 0 | M/S SHIVAM UDYOG | 16.72 | 0 | 0
2177 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001914/2020-2021 |  | 15/02/2021 | 0 | S.K. GHOSH | 32 | 0 | 0
2178 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001917/2020-2021 |  | 15/02/2021 | 0 | M/S SHIVAM UDYOG | 17 | 0 | 0
2179 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
2180 | Hooghly Division | Arambug Sub-Division | Providing 1650 nos F.H.T.C. in Harishchak village of Harishchak and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000925/2020-2021 | 1688/HUG | 17/12/2020 | 40 | P.B. ENTERPRISE (PINTU BHADURI) | 77.54 | 0 | 0
2181 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000018/2021-2022 |  | 12/04/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 3.02 | 0 | 0
2182 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001920/2020-2021 |  | 15/02/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 77 | 0 | 0
2183 | Hooghly Division | Arambug Sub-Division | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Arandi Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000271/2021-2022 | 425/HUG | 01/12/2021 | 30 | M/S R K ENTERPRISE | 18.18 | 18.16 | 100
2184 | Hooghly Division | Arambug Sub-Division | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000336/2021-2022 | 13/Hug | 04/01/2022 | 20 | MS CHANDIMATA CONSTRUCTION | 13.37 | 13.35 | 100
2185 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001896/2020-2021 |  | 15/02/2021 | 0 | M/S RAJKUMAR KHAN | 27 | 0 | 0
2186 | Hooghly Division | Srirampur Sub-Division | Construction of One No. 3.60 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for ANTPUR W/S Scheme under Serampore Sub-Division of Hooghly Division,P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000350/2022-2023 | 537/SER | 08/09/2022 | 60 | BAKSHI ENTERPRISE | 2.65 | 2.53 | 0
2187 | Hooghly Division | Srirampur Sub-Division | Construction of Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ANTPUR Piped Water Supply Scheme under Hooghly Division P.HE Dte. within Jangipara Block, Serampore Sub Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000641/2022-2023 | 98/HUG | 10/01/2023 | 150 | SHREEOM ENTERPRISE | 4.59 | 4.2 | 99
2188 | Hooghly Division | Srirampur Sub-Division | Repairing of Switch Room & Boundary Wall at Existing TW sites of ANTPUR PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000930/2023-2024 | 986/HUG | 16/03/2024 | 30 | SUNITI MAIRA | 6.18 | 0 | 0
2189 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Antpur PWSS P.H. No.-IV, Hooghly. Application No. 5004065652 Ref ID: 503592944 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00120/2024-2025 | 42 | 09/04/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
2190 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Antpur (Aug) water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002564/2022-2023 | 1321/ED | 17/08/2022 | 90 | M/S, GHOSH ENTERPRISE | 10.28 | 9.91 | 75
2191 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ANTPUR PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002583/2023-2024 | 458/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
2192 | Central Drilling | Srirampur Sub-Division | Supply & Delivery of consumables at site for construction of TW at ANTPUR PWSS under CDD, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000027/2022-2023 | 179/CMSD-I(D) | 10/06/2022 | 15 | S B S ENTERPRISE | 1.5 | 1.45 | 100
2193 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ANTPUR PWSS, JAIGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000032/2022-2023 | 177/CMSD-I (D) | 10/06/2022 | 15 | M/S S.K.GHOSH & CO. | 4.38 | 3.91 | 90
2194 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT ANTPUR PWSS, JANGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000033/2022-2023 | 180/CMSD-I(D) | 10/06/2022 | 15 | M/S S.K.GHOSH & CO. | 2.9 | 2.75 | 100
2195 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERIALS (250MM DIA CD) CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBEWELL ANTPUR, UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000363/2022-2023 | 114/CMSD-I | 06/05/2022 | 15 | ASHUTOSH DAS & CO | 3.87 | 3.78 | 0
2196 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000367/2022-2023 | 377/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 0.11 | 0
2197 | Hooghly Division | Chinsuria Sub-Division | 1ST Continuation of Engagement of 2 nos Valve operators for the period from 01/07/2023 to 31/08/2023 for Dharampur & Uttarchandannagar W/S Scheme under Chinshurah Sub - Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000392/2023-2024 | 571/CH | 30/06/2023 | 124 | SOUMYADIP DE | 0.71 | 0 | 0
2198 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in CHINSURAH-MOGRA Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000918/2023-2024 | 253/CH | 12/03/2024 | 30 | BIMAL KUMAR HALDER | 4.99 | 0 | 75
2199 | Hooghly Division | Srirampur Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00274/2023-2024 | BP-2023-24-233 | 31/07/2023 | 0 | AATISH KUMAR SHAW | 0.39 | 0 | 0
2200 | Hooghly Division | Srirampur Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement at ProposedT/W Site of JANGIPARA ZONE-III W/S Scheme under SERAMPORE Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000008/2023-2024 | 1021/HUG | 06/04/2023 | 30 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 5.56 | 5.36 | 100
2201 | Hooghly Division | Srirampur Sub-Division | Repairing & Renovation of existing room for Chemical test of drinking water at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000023/2025-2026 | 266/SER | 03/04/2025 | 10 | MAA TARA CONSTRUCTION | 4.99 | 0 | 99
2202 | Hooghly Division | Srirampur Sub-Division | AUGMENTATION of JANGIPARA ZONE-I Piped Water Supply Scheme with LDS, Rising Main, Repairing of Switch Room, Boundary wall of ZONE-I under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000089/2023-2024 | 1353/HUG | 12/05/2023 | 965 | ASIA CONSTRUCTION | 350.59 | 155.1 | 60
2203 | Hooghly Division | Srirampur Sub-Division | Construction of 700 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & FHTC For AUGMENTATION Of JANGIPARA ZONE-I Piped Water Supply Scheme under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000090/2023-2024 | 1354/HUG | 12/05/2023 | 873 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 275.31 | 75.34 | 35
2204 | Hooghly Division | Srirampur Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving : ¦data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe : Water Supply Scheme under Chanditala I& Il & Jangipara Block (Part-l) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000178/2024-2025 | 3211/HUG | 12/09/2024 | 15 | TECHVISION | 4.2 | 0 | 80
2205 | Hooghly Division | Srirampur Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under JANGIPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000183/2024-2025 | 519/SER | 11/09/2024 | 5 | TOTON MONDAL | 4.77 | 4.72 | 95
2206 | Hooghly Division | Srirampur Sub-Division | AUGMENTATION of JANGIPARA ZONE-II Piped Water Supply Scheme with LDS,Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under JANGIPARA BlockWithin Serampore Sub-Division Of Hooghly Division P.H.E Dte., District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000320/2023-2024 | 2410/HUG | 11/08/2023 | 600 | BALAJI UDDYOG | 291.59 | 77.8 | 60
2207 | Hooghly Division | Srirampur Sub-Division | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000425/2024-2025 | 3522/HUG | 22/10/2024 | 316 | WATER TECH | 29.57 | 0 | 45
2208 | Hooghly Division | Srirampur Sub-Division | Augmentation of JANGIPARA (ZONE-III) Water Supply Scheme with LDS,FHTC, Rising Main at JANGIPARA Block Under Serampore Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000444/2022-2023 | 2481/HUG | 21/11/2022 | 40 | MAA TARA CONSTRUCTION | 118.54 | 113.92 | 60
2209 | Hooghly Division | Srirampur Sub-Division | Sinking of `Two Nos Big Dia Tube Well (250 mm X 150 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at JANGIPARA ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000451/2022-2023 | 2501/HUG | 22/11/2022 | 830 | GLOBAL CONSTRUCTION | 20.07 | 0 | 50
2210 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Jangipara (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000473/2021-2022 | 365/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.91 | 4.93 | 0
2211 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Jangipara (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000474/2021-2022 | 366/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 2.06 | 0
2212 | Hooghly Division | Srirampur Sub-Division | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of JANGIPARA Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000756/2023-2024 | 447/HUG | 15/02/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 31.62 | 0 | 20
2213 | Hooghly Division | Srirampur Sub-Division | Sinking of additional tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Anarbati mouza of Jangipara Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000866/2023-2024 | 748/HUG | 05/03/2024 | 60 | BANSBERIA CONSTRUCTION CO. | 31.77 | 0 | 70
2214 | Hooghly Division | Srirampur Sub-Division | Laying of 225 MM & 250 MM pipeline by HDD process under Jangipara Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000868/2023-2024 | 743/HUG | 05/03/2024 | 347 | ASIA CONSTRUCTION | 88.55 | 0 | 87
2215 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000006/2022-2023 | 1122/3/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2216 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000038/2022-2023 | 1291/1/Hug | 24/06/2022 | 0 | Resource Division | 9.24 | 0 | 0
2217 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000124/2022-2023 | 2210/3/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
2218 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000162/2022-2023 | 79/6/Hug | 06/01/2023 | 0 | Resource Division | 8.04 | 0 | 0
2219 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000305/2023-2024 | 1384/2/Hug | 15/05/2023 | 0 | Resource Division | 35.97 | 0 | 0
2220 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00801/2022-2023 | 164 | 21/02/2023 | 0 | WBSEDCL | 7.85 | 0 | 0
2221 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00802/2022-2023 | 164 | 21/02/2023 | 0 | WBSEDCL | 2.77 | 0 | 0
2222 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangipara water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000217/2022-2023 | 843/ED | 14/02/2023 | 90 | R.M.D TRADING. | 21.82 | 21.44 | 30
2223 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000390/2024-2025 | 1474/ED | 25/07/2024 | 90 | SARVATAH PROJECTS PRIVATE LIMITED | 11.1 | 0 | 0
2224 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002579/2023-2024 | 455/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 60
2225 | Central Drilling | Srirampur Sub-Division | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT JANGIPARA PWSS Z-II, HOOGHLY DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000223/2022-2023 | 550/CMSD-I | 11/11/2022 | 3 | CHANDA ENTERPRISE | 0.43 | 0.43 | 0
2226 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-II) W/S SCH, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000281/2022-2023 | 1373/CDD | 24/11/2022 | 30 | CHANDA ENTERPRISE | 12.87 | 12.07 | 0
2227 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-III), HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000282/2022-2023 | 1560/CDD | 08/12/2022 | 30 | C.M. ENTERPRISE | 12.48 | 10.49 | 0
2228 | Central Drilling | Srirampur Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT JANGIPARA PWSS, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000310/2022-2023 | 578/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.95 | 0
2229 | Hooghly Division | Arambug Sub-Division | SUBMISSION OF QUOTATION BILL FOR THE WBSEDCL BILL RAISED BY THE EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00368/2022-2023 | BP-2022-23-644 | 25/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0
2230 | Hooghly Division | Arambug Sub-Division | Augmentation of KAKNAN (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room & Boundary Wall of 3rd T.W Site at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000095/2022-2023 | 1086/Hug | 02/06/2022 | 30 | SWASTIK ENTERPRISE | 66.2 | 49.6 | 50
2231 | Hooghly Division | Arambug Sub-Division | Augmentation of KAKNAN (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, of Switch room, Boundary wall, existing OHR at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000192/2022-2023 | 963//Hug | 17/05/2022 | 60 | UNIQUE AGENCY | 166.37 | 165.74 | 100
2232 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at KAKNAN (ZONE-II) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 10 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000345/2022-2023 | 1958/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.41 | 100
2233 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of KAKNAN Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000381/2021-2022 | 612/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 3.16 | 100
2234 | Hooghly Division | Arambug Sub-Division | Construction of Drain, Internal Road & Land Development works at Head Work site of Kaknan W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000437/2022-2023 | 728/Arg | 29/09/2022 | 926 | UNIQUE AGENCY | 3.81 | 0 | 100
2235 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000023/2022-2023 | 1124/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2236 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000047/2022-2023 | 1590/2/Hug | 03/08/2022 | 0 | Resource Division | 6.15 | 0 | 0
2237 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000106/2022-2023 | 1773/40/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0
2238 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000143/2023-2024 | 1385/13/Hug | 15/05/2023 | 0 | Resource Division | 1.79 | 0 | 0
2239 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000163/2021-2022 | 424/4/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0
2240 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Kaknan W/S. Sch. TW-III Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00938/2022-2023 |  | 13/03/2023 | 0 | WBSEDCL | 3.65 | 0 | 0
2241 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kaknan water supply scheme, T.W. No.- I, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000287/2022-2023 | 937/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 10.38 | 83
2242 | Hooghly Division | Srirampur Sub-Division | Laying Distribution of left out portion of pipeline to restore the water supply at Kharsarai Functional Hosuehold Tap Connection at Kharsarai Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000025/2024-2025 | 2224/HUG | 10/06/2024 | 30 | ARATI ENGINEERING | 14.18 | 13.75 | 100
2243 | Hooghly Division | Srirampur Sub-Division | Sinking of I(One) No Big dia tube well (300 mmx200mm) with supply of PVC Pipe and strainer and having depth upto 150M of Kharsarai W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000145/2022-2023 | 1416/HUG | 12/07/2022 | 30 | B.R SUPPLIERS | 9.8 | 9.47 | 100
2244 | Hooghly Division | Srirampur Sub-Division | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000228/2021-2022 | 1867/Hug | 07/10/2021 | 30 | R.K. TRADERS | 6.22 | 0 | 100
2245 | Hooghly Division | Srirampur Sub-Division | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000233/2021-2022 | 1918/HUg | 27/10/2021 | 30 | R.K. TRADERS | 6.22 | 6.2 | 100
2246 | Hooghly Division | Srirampur Sub-Division | Augmentation of Kharsari Piped WS scheme with LDS Rising main Construction of switch room without w/s & toilet construction repairing of boundary wall switch room with FHTC work at Chanditala II Block of Hooghly Dist under Hooghly Divn PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2022-2023 | 638/HUG | 01/04/2022 | 180 | M/S S.G. CONSTRUCTION | 166.73 | 163.66 | 80
2247 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000394/2021-2022 | 287/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.8 | 2.8 | 100
2248 | Hooghly Division | Srirampur Sub-Division | Painting of OHR, Construction of Guard Wall with Boundary Wall, Pathwaty, Drain at Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000848/2023-2024 | 732/HUG | 05/03/2024 | 60 | M/S ATANU DAS | 20.89 | 15.67 | 80
2249 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000008/2022-2023 | 1122/5/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2250 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000156/2021-2022 | 422/1/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0
2251 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000308/2023-2024 | 1384/5/Hug | 15/05/2023 | 0 | Resource Division | 10.71 | 0 | 0
2252 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM in ITAGARH PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 04 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2022-2023 | 2085/HUG | 21/09/2022 | 30 | SWARNA ENTERPRISE | 11.4 | 9.87 | 0
2253 | Hooghly Division | Chinsuria Sub-Division | Providing 385 nos Functional Household Tap Connection (FHTC) within the Bhalki & Malancha Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000454/2021-2022 | 472/Hug | 10/03/2022 | 20 | SURAJIT SINGHA RAY | 19.2 | 17.71 | 0
2254 | Hooghly Division | Chinsuria Sub-Division | Providing 615 nos Functional Household Tap Connection (FHTC) within the Itagarh & Sargaria Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000455/2021-2022 | 473/Hug | 10/03/2022 | 30 | THREE MAA ENTERPRISE | 30.63 | 29.03 | 0
2255 | Hooghly Division | Chinsuria Sub-Division | Laying HDPE pipe and allied repairing works of Itagarh water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000509/2023-2024 | 815/CH | 31/08/2023 | 15 | GHOSH CONSTRUCTION | 0.94 | 0.93 | 95
2256 | Hooghly Division | Chinsuria Sub-Division | Providing 881 nos Functional Household Tap Connection (FHTC) within the Dakshin Darshan, Pakri & Shibrai Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000450/2021-2022 | 468/Hug | 10/03/2022 | 40 | SOUMYADIP DE | 44.14 | 28.92 | 0
2257 | Hooghly Division | Chinsuria Sub-Division | Providing 489 nos Functional Household Tap Connection (FHTC) within the Bejpara, Radhanagar & Uttar Darshan Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000451/2021-2022 | 469/Hug | 10/03/2022 | 30 | TAPAS ADHYA | 24.49 | 19.93 | 0
2258 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) of Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001917/2024-2025 | 268/CH | 20/02/2025 | 10 | R.K. TRADERS | 4.82 | 0 | 0
2259 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001918/2024-2025 | 269/CH | 20/02/2025 | 10 | AYUSH ENTERPRISE | 3.18 | 0 | 0
2260 | Hooghly Division | Chinsuria Sub-Division | Providing 800 nos F.H.T.C. in Kola and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah-Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000009/2021-2022 | 940/Hug | 06/05/2021 | 30 | PRASUN ENTERPRISE (PRASUN BISWAS) | 39.21 | 6.16 | 0
2261 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of KOLA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000033/2023-2024 | 1133/HUG | 19/04/2023 | 30 | ROY ENTERPRISE | 33.33 | 32.86 | 100
2262 | Hooghly Division | Chinsuria Sub-Division | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of KOLA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000358/2021-2022 | 119/Hug | 19/01/2022 | 60 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 67.95 | 63.78 | 0
2263 | Hooghly Division | Chinsuria Sub-Division | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of KOLA & HARAL ZONE-II Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000439/2021-2022 | 457/Hug | 10/03/2022 | 20 | ARATI ENGINEERING | 19.29 | 18.63 | 0
2264 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000121/2022-2023 | 289/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 4.99 | 0 | 0
2265 | Hooghly Division | Chinsuria Sub-Division | Providing 40 nos. Functional House Hold Connection (FHTC) within the Command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000121/2022-2023 | 461/CH | 31/05/2022 | 20 | CREATION CONSTRUCTION | 4.3 | 4.28 | 0
2266 | Hooghly Division | Chinsuria Sub-Division | Providing 1961 nos Functional Household Tap Connection (FHTC) within the command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000275/2021-2022 | 2129/Hug | 01/12/2021 | 50 | CREATION CONSTRUCTION | 80.54 | 80.53 | 0
2267 | Hooghly Division | Chinsuria Sub-Division | Providing Functional House hold tap connection (FHTC) under JJM within left out portion at Basudevbati PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000459/2024-2025 | 4046/HUG | 19/12/2024 | 90 | S.B. ENTERPRISE | 5.59 | 0 | 50
2268 | Hooghly Division | Chinsuria Sub-Division | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of BASUDEBBATI PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000736/2023-2024 | 28/CH | 05/01/2024 | 15 | M/S BIMAL DAS AND CO. | 4.35 | 4.34 | 50
2269 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BHASTARA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000417/2022-2023 | 2277/HUG | 19/10/2022 | 50 | SATYA NARAYAN BISWAS | 56.36 | 48.47 | 0
2270 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000013/2022-2023 | 1123/2/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0
2271 | Hooghly Division | Chinsuria Sub-Division | RESTORATION COST FOR PIPE LAYING WORK BALAGARH INCHURA ROAD | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00182/2024-2025 | BP-2024-25-96 | 02/05/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33.75 | 0 | 0
2272 | Hooghly Division | Chinsuria Sub-Division | Restoration Balagarh Inchura Road | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/01809/2023-2024 | BP-2024-25-1 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33 | 0 | 0
2273 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bankipur, Jasra, Somra &Baligari Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000026/2022-2023 | 1272/Hug | 23/06/2022 | 40 | S AND P CONSTRUCTION | 50.86 | 50.04 | 0
2274 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Masara,Debipur, Belgachhi, Muragari,Rajaipur,Kanpara, Bhelurgari,Kolara & Sukharia Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000027/2022-2023 | 728/Hug | 07/04/2022 | 40 | JAI BHARAT COMMERCIAL CORPORATION | 50.33 | 49.09 | 0
2275 | Hooghly Division | Chinsuria Sub-Division | Functional Household Tap Connection (FHTC) under JJM in SOMRA PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000369/2022-2023 | 2082/HUG | 21/09/2022 | 45 | M/S T.K.B. CONSTRUCTION | 53.89 | 53.8 | 0
2276 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000012/2022-2023 | 1123/1/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0
2277 | Hooghly Division | Chinsuria Sub-Division | ROAD RESTORATION PAYMENT TO PWD FOR BHASTARA MAJINAN ROAD | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00669/2024-2025 | 1234 | 27/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 17.55 | 0 | 0
2278 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 258.06 | 30
2279 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000120/2023-2024 | 1264/15/HUG | 03/05/2023 | 0 | Resource Division | 32.44 | 0 | 0
2280 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000241/2023-2024 | 1386/20/Hug | 15/05/2023 | 0 | Resource Division | 15.66 | 0 | 0
2281 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000515/2023-2024 | 3059/10/Hug | 11/10/2023 | 0 | Resource Division | 15.66 | 0 | 0
2282 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05066/2023-2024 | 680 | 19/01/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
2283 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05713/2023-2024 | 706 | 25/01/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
2284 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khajurdaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000159/2022-2023 | 3495/ED | 30/12/2022 | 1555 | AHALYA ENGINEERING WORKS | 20.35 | 16.81 | 40
2285 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0
2286 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0
2287 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 245.84 | 50
2288 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2289 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000081/2023-2024 | 1234/41/Hug | 28/04/2023 | 0 | Resource Division | 47.19 | 0 | 0
2290 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000180/2023-2024 | 1385/51/Hug | 15/05/2023 | 0 | Resource Division | 19.76 | 0 | 0
2291 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000468/2023-2024 | 3057/16/Hug | 11/10/2023 | 0 | Resource Division | 19.76 | 0 | 0
2292 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Natibpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004216541 Reference ID- 503658560 SM Code-12235 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01652/2024-2025 | 410 | 21/08/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
2293 | Electrical | Arambug Sub-Division | Quotation Money depostion for new service connection at Natibpur pwss, P.H No-I, Dist- Hooghly uned ED, PHED. App. No.-5004020953 SM/12235 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02301/2024-2025 | BP-24-25-598 | 21/11/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
2294 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Natibpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000089/2022-2023 | 3471/ED | 30/12/2022 | 913 | BARMAN ROY TRADERS | 21.9 | 0 | 40
2295 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NATIBPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000167/2024-2025 | 1190/ED | 14/06/2024 | 90 | BARMAN ROY TRADERS | 10.47 | 0 | 0
2296 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 358.92 | 30
2297 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000124/2023-2024 | 1264/19/HUG | 03/05/2023 | 0 | Resource Division | 34.53 | 0 | 0
2298 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000528/2023-2024 | 3059/35/Hug | 11/10/2023 | 0 | Resource Division | 22.49 | 0 | 0
2299 | Electrical | Chinsuria Sub-Division | Durgapur PH__II Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00456/2024-2025 |  | 14/05/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
2300 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06044/2023-2024 | 743 | 08/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
2301 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06045/2023-2024 | 744 | 08/02/2024 | 0 | WBSEDCL | 14.44 | 0 | 0
2302 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamalpur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000149/2022-2023 | 3492/ED | 30/12/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.6 | 0 | 0
2303 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme with Repairing of Switch Room & Boundary wall, Construction Of Switch Room, Boundary Wall & LDS, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block-CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000006/2023-2024 | 1016/HUG | 06/04/2023 | 90 | M/S T.K.B. CONSTRUCTION | 128.94 | 105.86 | 100
2304 | Hooghly Division | Chinsuria Sub-Division | Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, Rising Main, FHTC For AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000103/2023-2024 | 1421/Hug | 17/05/2023 | 685 | SUBHANKAR GUHA | 166.98 | 51.52 | 30
2305 | Hooghly Division | Chinsuria Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MADHUSUDANPUR PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 08 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000342/2022-2023 | 1956/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 11.23 | 25
2306 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Madhusudanpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000542/2021-2022 | 133/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 2.96 | 0
2307 | Hooghly Division | Chinsuria Sub-Division | Providing Functional House hold tap connection (FHTC) under JJM within Digirpara & Naapara of Madhusudanpur PWSS under Chinsurah Mogra Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001844/2024-2025 | 221/CH | 19/02/2025 | 30 | M/S T.K.B. CONSTRUCTION | 4.29 | 0 | 0
2308 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000016/2022-2023 | 1123/4/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0
2309 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000113/2022-2023 | 1991/2/HUG | 12/09/2022 | 0 | Resource Division | 21.16 | 0 | 0
2310 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000128/2022-2023 | 2211/2/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
2311 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000235/2023-2024 | 1386/14/Hug | 15/05/2023 | 0 | Resource Division | 11.35 | 0 | 0
2312 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Madhusudanpur(S.Aug.) W/S Sch. , T/W No. -III (Nr. Tissu Bus stand) [SM/11167] under Mogra CCC, WBSEDCL, Ref Id. - 503586680, Dt. - 16/04/2024, Application No. - 5004053256, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00192/2024-2025 | 80 | 19/04/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
2313 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Madhusudanpur water supply scheme TW No I Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000218/2022-2023 | 850/ED | 14/02/2023 | 567 | AMIT DAS | 10.75 | 10.45 | 90
2314 | Hooghly Division | Arambug Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, ARAMBAGH SUB-DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00228/2022-2023 | BP-2022-23-547 | 21/02/2023 | 0 | M/S PRADYUT KUMAR HAZRA | 1.15 | 0 | 0
2315 | Hooghly Division | Arambug Sub-Division | Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS within Sekati(Part) Mouza for Augmentation of Bhadur (Zone-II) Water Supply Scheme at Goghat-I Block under Armabag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000160/2022-2023 | 1422/Hug | 12/07/2022 | 1025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 98.87 | 46.61 | 50
2316 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection in BHADUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6M X 3.0M Switch Room & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 4 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000233/2022-2023 | 1782/HUG | 30/08/2022 | 45 | THREE MAA ENTERPRISE | 78.11 | 53.97 | 75
2317 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I].(Bhadur Part-A) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000239/2022-2023 | 334/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 3.6 | 0
2318 | Hooghly Division | Arambug Sub-Division | Additional survey work for preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. (Bhadur Part-B) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000240/2022-2023 | 335/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0.46 | 0
2319 | Hooghly Division | Arambug Sub-Division | Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work for Augmentation of BHADUR (ZONE-II) Water Supply Scheme at Goghat-I Block under Armabag Sub- Division of Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000386/2023-2024 | 2568/HUG | 24/08/2023 | 45 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.91 | 0 | 0
2320 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.42 | 100
2321 | Hooghly Division | Arambug Sub-Division | Laying Distribution System of BHADUR (Zone-II) Piped Water Supply Scheme within Bhadur, Mandalganti & Adra Mouza including Repairing of existing Switch rooms, Boundary walls of BHADUR (Zone-I & Zone-II) Water Supply Scheme at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000464/2022-2023 | 2525/HUG | 23/11/2022 | 45 | M/S S & P CONSTRUCTION | 85 | 68.89 | 95
2322 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at Head Work Site of BHADUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000476/2024-2025 | 4055/HUG | 19/12/2024 | 90 | AYUSH ENTERPRISE | 23.83 | 0 | 0
2323 | Hooghly Division | Arambug Sub-Division | Augmentation of BHADUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under Arambagh Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000619/2022-2023 | 43/HUG | 04/01/2023 | 300 | TITAS CONSTRUCTION | 411.57 | 185.87 | 55
2324 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000018/2023-2024 | 1106/5/HUG | 17/04/2023 | 0 | Resource Division | 23.22 | 0 | 0
2325 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000024/2023-2024 | 1234/5/Hug | 28/04/2023 | 0 | Resource Division | 3.72 | 0 | 0
2326 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000051/2022-2023 | 1590/3/Hug | 03/08/2022 | 0 | Resource Division | 15.4 | 0 | 0
2327 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000057/2022-2023 | 1688/4/HUG | 22/08/2022 | 0 | Resource Division | 120.14 | 0 | 0
2328 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000079/2022-2023 | 1773/13/Hug | 29/08/2022 | 0 | Resource Division | 1.03 | 0 | 0
2329 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000118/2022-2023 | 2211/3/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
2330 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000145/2023-2024 | 1385/15/Hug | 15/05/2023 | 0 | Resource Division | 14.32 | 0 | 0
2331 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000278/2022-2023 | 1105/5/Hug | 17/04/2023 | 0 | Resource Division | 86.37 | 0 | 0
2332 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000330/2023-2024 | 2607/3/Hug | 29/08/2023 | 0 | Resource Division | 18.58 | 0 | 0
2333 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000372/2023-2024 | 3002/3/Hug | 05/10/2023 | 0 | Resource Division | 20.89 | 0 | 0
2334 | Electrical | Arambug Sub-Division | Additional Quotation of Bhadur w/s Scheme,Zone-I,PH No-3 Block-Goghat-I Dist-Hooghly under Electrical division,PHE Dte.(SM/11463) Reference Id-860301435 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00622/2024-2025 | 183 | 03/06/2024 | 0 | WBSEDCL | 1.61 | 0 | 0
2335 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhadur w/s scheme,zone-II,TW No-II Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02129/2023-2024 | 119 | 20/07/2023 | 0 | WBSEDCL | 2.8 | 0 | 0
2336 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhadur w/s Scheme,Zone-I,TW No-III Dist-Hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02130/2023-2024 | 116 | 20/07/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
2337 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhadur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000200/2022-2023 | 827/ED | 14/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 21.95 | 21.82 | 20
2338 | Central Drilling | Arambug Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Bhadur W/S Scheme (Z-II, TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000466/2022-2023 | 2298/CDD | 30/03/2023 | 30 | CHANDA ENTERPRISE | 30.35 | 18.99 | 31
2339 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00354/2023-2024 | BP-2023-24-293 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.12 | 0 | 0
2340 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | RTOR000283/2023-2024 | 1386/54/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0
2341 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
2342 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
2343 | Hooghly Division | Chinsuria Sub-Division | xxx | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00351/2023-2024 |  | 17/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.77 | 0 | 0
2344 | Hooghly Division | Chinsuria Sub-Division | Bhabapur Mini PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00772/2024-2025 |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0
2345 | Hooghly Division | Chinsuria Sub-Division | Implementation of single village Basantapur mini pipe water supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00902/2024-2025 |  | 27/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 1.54 | 0 | 0
2346 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | RTOR000246/2023-2024 | 1386/25/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0
2347 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
2348 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
2349 | Hooghly Division | Chinsuria Sub-Division | Withdrawing Existing C.I Pipes & Specials & Laying CI/DI Pipes & Specials for Rising main pipeline for AMODGHATA W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000251/2022-2023 | 717 CH | 23/08/2022 | 15 | SHREEOM ENTERPRISE | 1.77 | 1.75 | 0
2350 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of AMODGHATA W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000254/2022-2023 | 721/CH | 23/08/2022 | 45 | S B ENTERPRISE | 4.97 | 4.94 | 0
2351 | Hooghly Division | Chinsuria Sub-Division | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of AMODGHATA Piped Water Supply Scheme Under Hooghly Division P.H.E Dte within Chinsurah Mogra Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000688/2022-2023 | 283/HUG | 01/02/2023 | 90 | R.K. TRADERS | 115.44 | 98.11 | 75
2352 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Amodghata PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000803/2023-2024 | 146/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 50
2353 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection at Amodghata w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00840/2022-2023 | 174 | 28/02/2023 | 0 | WBSEDCL | 7.19 | 0 | 0
2354 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000236/2022-2023 | 867/ED | 14/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 10.81 | 100
2355 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000278/2022-2023 | 945/ED | 22/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 0 | 0
2356 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Amodghata W/S. Sch. TW- IV, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000870/2022-2023 | 1547/ED | 20/09/2022 | 90 | BISALAXMI ENTERPRISE | 9.64 | 9.63 | 99
2357 | Hooghly Division | Chandannagar Sub-Division | BAHIRKHANDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] [2nd Call of WBPHE/EE/51/HUG/2022-23(Sl No. 3)] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000171/2023-2024 | 1670/HUG | 08/06/2023 | 938 | DIPTI TRADERS | 948.76 | 786.93 | 96
2358 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000070/2023-2024 | 1235/11/Hug | 28/04/2023 | 0 | Resource Division | 85.79 | 0 | 0
2359 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000203/2023-2024 | 1383/6/Hug | 15/05/2023 | 0 | Resource Division | 22.24 | 0 | 0
2360 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000415/2023-2024 | 3058/25/Hug | 11/10/2023 | 0 | Resource Division | 14.85 | 0 | 0
2361 | Electrical | Chandannagar Sub-Division | new service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02600/2023-2024 | 164 | 03/08/2023 | 0 | WBSEDCL | 1.7 | 0 | 0
2362 | Electrical | Chandannagar Sub-Division | new service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02602/2023-2024 | 165 | 03/08/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
2363 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Bahir Khanda w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/13404) Application No-5003976156 Reference Id-503538913 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06473/2023-2024 | 900 | 19/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0
2364 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bahirkhanda water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000126/2022-2023 | 3481/ED | 30/12/2022 | 60 | S.M. ELECTRICALS | 21.48 | 21.44 | 60
2365 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bahir Khanda water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002482/2023-2024 | 342/ED | 21/02/2024 | 90 | JOYSHREE CONCERN | 10.58 | 10.36 | 20
2366 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00289/2023-2024 | BP-2023-24-240 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.72 | 0 | 0
2367 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000177/2023-2024 | 1385/48/Hug | 15/05/2023 | 0 | Resource Division | 0.56 | 0 | 0
2368 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
2369 | Hooghly Division | Howrah Mechanical Sub-Division | BINAGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000264/2023-2024 | 2238/HUG | 01/08/2023 | 552 | SIBSANKAR CHOWDHURY | 672.18 | 201.3 | 30
2370 | Hooghly Division | Howrah Mechanical Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Binagram 1st T/W site & Naita 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000283/2024-2025 | 922/Chan | 19/07/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
2371 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | RTOR000079/2023-2024 | 1235/15/Hug | 28/04/2023 | 0 | Resource Division | 47.05 | 0 | 0
2372 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | RTOR000199/2023-2024 | 1383/2/Hug | 15/05/2023 | 0 | Resource Division | 16.44 | 0 | 0
2373 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | RTOR000388/2023-2024 | 3058/24/Hug | 11/10/2023 | 0 | Resource Division | 14.55 | 0 | 0
2374 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/04599/2023-2024 | 605 | 03/01/2024 | 0 | WBSEDCL | 20.72 | 0 | 0
2375 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/04607/2023-2024 | 606 | 03/01/2024 | 0 | WBSEDCL | 7.72 | 0 | 0
2376 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Binagram water supply scheme, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000183/2022-2023 | 776/ED | 09/02/2023 | 90 | STANDARD ELECTRICALS | 22.4 | 13.05 | 50
2377 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 551.22 | 15
2378 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000107/2023-2024 | 1264/3/HUG | 03/05/2023 | 0 | Resource Division | 12.22 | 0 | 0
2379 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000224/2023-2024 | 1386/3/Hug | 15/05/2023 | 0 | Resource Division | 21.59 | 0 | 0
2380 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000487/2023-2024 | 3059/20/Hug | 11/10/2023 | 0 | Resource Division | 21.59 | 0 | 0
2381 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Ghatampur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04322/2023-2024 | 430,431,432,433 | 21/11/2023 | 0 | WBSEDCL | 15.55 | 0 | 0
2382 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000185/2022-2023 | 778/ED | 09/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.74 | 23.17 | 97
2383 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No. III & IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000878/2023-2024 | 3451/ED | 11/08/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.25 | 22.19 | 97
2384 | Hooghly Division | Chandannagar Sub-Division | BIGHATI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under SINGUR Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2023-2024 | 1061/HUG | 12/04/2023 | 270 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 422.23 | 314.67 | 100
2385 | Hooghly Division | Chandannagar Sub-Division | Sinking of 1no. tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at BIGHAT ZONE - II Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000057/2024-2025 | 2367/HUG | 21/06/2024 | 539 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 31.59 | 8.19 | 100
2386 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000051/2023-2024 | 1235/5/Hug | 28/04/2023 | 0 | Resource Division | 54.25 | 0 | 0
2387 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000219/2023-2024 | 1383/21/Hug | 15/05/2023 | 0 | Resource Division | 9.73 | 0 | 0
2388 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000424/2023-2024 | 3058/23/Hug | 11/10/2023 | 0 | Resource Division | 9.73 | 0 | 0
2389 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati W/S Sch., Zone- II, T/W No. - III, Block - Singur, [SM/15249], under WBSEDCL, Khalisani CCC, Ref ID- 503803673, Dt. - 26-11-2024, Application No. - 5004481450, | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02526/2024-2025 | 608 | 05/12/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
2390 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL security deposit for Bighati PWSS, TW No.- II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04478/2023-2024 | 524 | 13/12/2023 | 0 | WBSEDCL | 4.06 | 0 | 0
2391 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 12.76 | 80
2392 | Hooghly Division | Srirampur Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Development of BORHAL (ZONE-I)W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000111/2023-2024 | 1440/HUG | 18/05/2023 | 45 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 31.23 | 17.63 | 25
2393 | Hooghly Division | Srirampur Sub-Division | Estimate of development at 3rd T/W site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001260/2024-2025 | 60/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 3.5 | 0 | 0
2394 | Hooghly Division | Srirampur Sub-Division | Estimate of Development of 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001261/2024-2025 | 61/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 2.75 | 0 | 0
2395 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Borhal w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004065635 Reference ID- 503592946 SM Code- 16449 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00487/2024-2025 | 146 | 22/05/2024 | 0 | WBSEDCL | 4.57 | 0 | 0
2396 | Electrical | Srirampur Sub-Division | Borhal Z-I P H NO-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02294/2023-2024 | 145 | 26/07/2023 | 0 | WBSEDCL | 4.55 | 0 | 0
2397 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-I) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000015/2023-2024 | 1631/ED | 11/04/2023 | 90 | S.S. ENTERPRISES | 23.3 | 11.35 | 85
2398 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 45
2399 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MORHAL PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002882/2023-2024 | 457/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 65
2400 | Central Drilling | Srirampur Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I), Jangipara block under hooghly District, CDD PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000457/2022-2023 | 2330/CDD | 30/03/2023 | 30 | C.M. ENTERPRISE | 22.68 | 10.58 | 47
2401 | Central Drilling | Srirampur Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 180 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I, TW-I), Jangipara block under hooghly District, CDD PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000458/2022-2023 | 1995/CDD | 07/02/2023 | 30 | UTTAM KUMAR CHATTERJEE | 12.54 | 10.58 | 100
2402 | Hooghly Division | Srirampur Sub-Division | GOPALPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000375/2023-2024 | 2496/HUG | 17/08/2023 | 807 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 416.93 | 196.95 | 85
2403 | Hooghly Division | Srirampur Sub-Division | GOPALPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000376/2023-2024 | 2497/HUG | 17/08/2023 | 776 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 498.12 | 320.97 | 80
2404 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000035/2023-2024 | 1236/2/Hug | 28/04/2023 | 0 | Resource Division | 56.85 | 0 | 0
2405 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000323/2023-2024 | 1384/20/Hug | 15/05/2023 | 0 | Resource Division | 19.32 | 0 | 0
2406 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000332/2023-2024 | 3005/4/Hug | 05/10/2023 | 0 | Resource Division | 4.3 | 0 | 0
2407 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000527/2023-2024 | 3060/11/Hug | 11/10/2023 | 0 | Resource Division | 17.72 | 0 | 0
2408 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04451/2023-2024 | 509 | 08/12/2023 | 0 | WBSEDCL | 10.63 | 0 | 0
2409 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04452/2023-2024 | 510 | 08/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
2410 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur Piped W/S. Sch. Z-II, PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04579/2023-2024 | 577 | 27/12/2023 | 0 | WBSEDCL | 7.27 | 0 | 0
2411 | Electrical | Srirampur Sub-Division | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. I & II Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000010/2023-2024 | 1626/ED | 11/04/2023 | 810 | UNITED ENTERPRISE | 21.83 | 0 | 80
2412 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. III & IV, Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000880/2023-2024 | 3453/ED | 11/08/2023 | 90 | DAS ENTERPRISE | 21.49 | 18.65 | 50
2413 | Hooghly Division | Arambug Sub-Division | PAYMENT TO ELECTRICAL DIVISION, PHE DTE.FOR THE PAYMENT TO WBSEDCL | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00490/2023-2024 | BP-2023-24-390 | 19/09/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.9 | 0 | 0
2414 | Hooghly Division | Arambug Sub-Division | PAYMENT TO EXECUTIVE ENGINEER,ELECTRICAL DIVISION, PHE DTE. FOR WBSEDCL AT MALAYPUR WATER SUPPLY SCHEME. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00534/2023-2024 | BP-2023-24-438 | 06/10/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 4.78 | 0 | 0
2415 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of MALAYPUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000221/2022-2023 | 363/Arg | 19/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.29 | 4.28 | 0
2416 | Hooghly Division | Arambug Sub-Division | MALAYPUR Piped Water Supply Scheme with LDS, FHTC, & Construction of 750 cum capacity OHR with 20 m. staging height including Soil Investigation work at ARAMBAG Block under ARAMBAG Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000407/2022-2023 | 2179/HUG | 29/09/2022 | 1082 | M/S PRADYUT KUMAR HAZRA | 663.67 | 542.86 | 90
2417 | Hooghly Division | Arambug Sub-Division | Construction of1 no.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site For AUGMENTATION of MALAYPPURW/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000411/2024-2025 | 3785/HUG | 25/11/2024 | 60 | SRI KRISHNA ENTERPRISE | 10.78 | 0 | 0
2418 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000931/2023-2024 | 987/HUG | 16/03/2024 | 30 | BIBHUTI SHAW | 46.75 | 0 | 0
2419 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000006/2023-2024 | 1106/HUG | 17/04/2023 | 0 | Resource Division | 22.16 | 0 | 0
2420 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000022/2022-2023 | 1124/3/HUG | 06/06/2022 | 0 | Resource Division | 9.24 | 0 | 0
2421 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000023/2023-2024 | 1234/4/Hug | 28/04/2023 | 0 | Resource Division | 58.72 | 0 | 0
2422 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000067/2022-2023 | 1773/1/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
2423 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000148/2023-2024 | 1385/19/Hug | 15/05/2023 | 0 | Resource Division | 17.82 | 0 | 0
2424 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Malaypur water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000288/2022-2023 | 938/ED | 22/02/2023 | 875 | MAHADEV ENTERPRISE | 21.42 | 21.12 | 40
2425 | Central Drilling | Arambug Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme (T/W I & II). Arambag Block under Hooghly District, Central Drilling Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000034/2023-2024 | 17/CDD | 04/04/2023 | 30 | ASHUTOSH DAS & CO | 22.26 | 19.63 | 50
2426 | Central Drilling | Arambug Sub-Division | Hiring of diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the Calcutta Mechanical Sub Division-I, P.H.Engineering Dte. under CMSD-II(D), CDD, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000048/2023-2024 | 217/CMSD-II(D) | 26/09/2023 | 92 | SUJATA BHOWMICK | 0.44 | 1.12 | 33
2427 | Central Drilling | Arambug Sub-Division | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000055/2024-2025 | 379/CMSD-I | 24/12/2024 | 33 | SIDDHARTHA CHATTERJEE | 0.16 | 0 | 0
2428 | Central Drilling | Arambug Sub-Division | Continuation for hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000145/2023-2024 | 120/S&WSD | 31/10/2023 | 61 | ASHUTOSH DAS & CO | 0.29 | 0.54 | 15
2429 | Central Drilling | Arambug Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Malaypur W/S Scheme (TW-I), under Hooghly District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000189/2023-2024 | 1434/CDD | 29/09/2023 | 30 | ASHUTOSH DAS & CO | 10.74 | 9.06 | 100
2430 | Central Drilling | Arambug Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 180 Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme Arambagh Block under Hooghly District, Central Drilling Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000484/2022-2023 | 2002/CDD | 09/02/2023 | 30 | M/S SAIKAT ENTERPRISE | 12.54 | 10.63 | 100
2431 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 0 | 100
2432 | Hooghly Division | Chandannagar Sub-Division | Sinking of tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of KULTEGHORI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000381/2023-2024 | 2516/HUG | 18/08/2023 | 941 | SHREE JAGANNATH ENTERPRISE | 32.57 | 1.95 | 40
2433 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000296/2023-2024 | 1383/39/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0
2434 | Electrical | Chandannagar Sub-Division | Quotation money deposition for new service connection at Kulteghori w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004314314 Reference ID- 503702908 SM Code- 16564 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01407/2024-2025 | 349 | 31/07/2024 | 0 | WBSEDCL | 24.36 | 0 | 0
2435 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kulteghori (Aug.) water supply scheme, T.W. No. I, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000077/2023-2024 | 1933/ED | 15/05/2023 | 90 | DAS ENTERPRISE | 11.48 | 0 | 30
2436 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions at Itkhola for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000035/2024-2025 | 537/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 2.81 | 2.81 | 100
2437 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Payan majipara for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000036/2024-2025 | 538/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 100
2438 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC at the left out portions of Priyanagar for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000037/2024-2025 | 539/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 85
2439 | Hooghly Division | Chinsuria Sub-Division | Repairing Of Switch Room, Boundary wall for Badinan W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000061/2024-2025 | 2408/HUG | 26/06/2024 | 30 | GHOSH CONSTRUCTION | 7.86 | 7.83 | 100
2440 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation Hanral Z-I Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000075/2024-2025 | 690/CH | 09/08/2024 | 7 | APEX ENGINEERING | 3.88 | 0 | 0
2441 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of BADINAN W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000082/2023-2024 | 1337/HUG | 11/05/2023 | 45 | BAKSHI ENTERPRISE | 40.42 | 35.48 | 45
2442 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at BADINAN W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000603/2023-2024 | 3318/HUG | 10/11/2023 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.88 | 13.06 | 100
2443 | Hooghly Division | Chinsuria Sub-Division | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No.- 4 of Badinan W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000739/2024-2025 | 65/CH | 10/01/2025 | 5 | BIMAL KUMAR HALDER | 0.97 | 0 | 0
2444 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 0 | 65
2445 | Electrical | Chinsuria Sub-Division | Additional Quotation for new service connection at Badinan w/s sch. , P.H. No. III, Dist -Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00750/2023-2024 | 37 | 15/05/2023 | 0 | WBSEDCL | 0.48 | 0 | 0
2446 | Electrical | Chinsuria Sub-Division | Quatation bill for New service connection at Aug. of Badinan w/s scheme, P.H No.-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00871/2022-2023 | 176 | 02/03/2023 | 0 | WBSEDCL | 4.74 | 0 | 0
2447 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Badinan W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04640/2023-2024 | 632 | 08/01/2024 | 0 | WBSEDCL | 5.16 | 0 | 0
2448 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000012/2023-2024 | 1628/ED | 11/04/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 11.4 | 99
2449 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Badinan water supply scheme, T.W. No. III, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000124/2022-2023 | 3480/ED | 30/12/2022 | 90 | INDIA ENTERPRISE | 10.64 | 10.3 | 90
2450 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000864/2023-2024 | 3436/ED | 11/08/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 0
2451 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000007/2024-2025 | 420/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.73 | 0.73 | 100
2452 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000008/2024-2025 | 421/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100
2453 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000009/2024-2025 | 422/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100
2454 | Hooghly Division | Chandannagar Sub-Division | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at kharda-apurbapur Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000065/2024-2025 | 2506/HUG | 03/07/2024 | 45 | KALPATARU ENTERPRISE | 37.6 | 3.71 | 50
2455 | Hooghly Division | Chandannagar Sub-Division | KHORDAAPURBAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000180/2023-2024 | 1686/HUG | 08/06/2023 | 90 | SATYA NARAYAN BISWAS | 146.57 | 110.2 | 60
2456 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Khordaapurbapur 1st T/W site & Kamarkundu (Zone-1) 1st T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000292/2024-2025 | 928/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0.38 | 100
2457 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - II, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503678884, dt. - 26-06-2024, Application No. - 5004264232. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00977/2024-2025 | 260 | 03/07/2024 | 0 | WBSEDCL | 13.18 | 0 | 0
2458 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503675586, dt. - 26-06-2024, Application No. - 5004257575. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00978/2024-2025 | 261 | 03/07/2024 | 0 | WBSEDCL | 14.47 | 0 | 0
2459 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Khordaa purbapur water supply scheme, T.W. No. I, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000072/2023-2024 | 1928/ED | 15/05/2023 | 655 | TAMAL ENTERPRISE | 11.65 | 9.05 | 50
2460 | Hooghly Division | Srirampur Sub-Division | Construction of Shed on open terrace of Existing Laboratory building at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000024/2025-2026 | 267/SER | 03/04/2025 | 10 | MAA TARA CONSTRUCTION | 4.93 | 0 | 0
2461 | Hooghly Division | Srirampur Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & other works at Chandrahati mouza of HIJALI Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000032/2025-2026 | 1055/HUG | 24/04/2025 | 60 | R.K. TRADERS | 27.87 | 0 | 0
2462 | Hooghly Division | Srirampur Sub-Division | HIJALI Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000265/2023-2024 | 2239/HUG | 01/08/2023 | 571 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 350.15 | 145.76 | 10
2463 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bilaspur-I PWSS 2. Bilaspur-II PWSS 3. Hijli PWSS 4. Jaganathpur PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000945/2023-2024 | 115/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.64 | 0.64 | 80
2464 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000036/2023-2024 | 1236/3/Hug | 28/04/2023 | 0 | Resource Division | 5.49 | 0 | 0
2465 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000315/2023-2024 | 1384/12/Hug | 15/05/2023 | 0 | Resource Division | 5.49 | 0 | 0
2466 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000499/2023-2024 | 3060/9/Hug | 11/10/2023 | 0 | Resource Division | 5.49 | 0 | 0
2467 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Hijali W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/04588/2023-2024 | 595 | 29/12/2023 | 0 | WBSEDCL | 6.03 | 0 | 0
2468 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Hijali W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/04648/2023-2024 | 633 | 08/01/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
2469 | Electrical | Srirampur Sub-Division | Shifting of 11KV HTOH line at Hijali pump house No.-1 Application ID: 100000103017 Ref ID: 860295257 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/06502/2023-2024 | 899 | 19/03/2024 | 0 | WBSEDCL | 6.79 | 0 | 0
2470 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hijali water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000069/2023-2024 | 1925/ED | 15/05/2023 | 90 | GLACIER ENGINEERING CO. | 23.4 | 21 | 25
2471 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DANTRA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000193/2023-2024 | 1776/HUG | 15/06/2023 | 45 | VAIDIK CONSTRUCTION | 11.42 | 0 | 70
2472 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at MAHISHGOT ZONE I (2Nos.), UDAYPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000227/2024-2025 | 3437/HUG | 03/10/2024 | 90 | SAHA CONSTRUCTION AND CO | 47.26 | 0 | 0
2473 | Hooghly Division | Arambug Sub-Division | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 258.22 | 45
2474 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2475 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000391/2023-2024 | 3057/56/Hug | 11/10/2023 | 0 | Resource Division | 19.7 | 0 | 0
2476 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037021/Quot/03 Reference ID- 503576711 SM Code- 18308 | Assistant Engineer | Junior Engineer (Civill) | BILL/06215/2023-2024 | 818 | 03/03/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
2477 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036968/Quot/03 Reference ID- 503576706 SM Code- 18308 | Assistant Engineer | Junior Engineer (Civill) | BILL/06216/2023-2024 | 819 | 01/03/2024 | 0 | WBSEDCL | 11.54 | 0 | 0
2478 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Udaypur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000817/2023-2024 | 3162/ED | 27/07/2023 | 90 | DEBJYOTI BASU | 21.36 | 0 | 0
2479 | Hooghly Division | Arambug Sub-Division | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 202.35 | 45
2480 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000842/2023-2024 | 722/HUG | 05/03/2024 | 60 | ANIRUDDHA FARUQUE | 48.17 | 26.24 | 100
2481 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2482 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000479/2023-2024 | 3057/8/Hug | 11/10/2023 | 0 | Resource Division | 11.45 | 0 | 0
2483 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for UDNA w/s Scheme, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18309) Application No-5004114171 Reference Id-503617472 | Assistant Engineer | Junior Engineer (Civill) | BILL/00233/2024-2025 | 83 | 22/04/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
2484 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for UDNA water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000814/2023-2024 | 3159/ED | 27/07/2023 | 90 | MAA KALI ENTERPRISE | 20.23 | 14.81 | 100
2485 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Udna water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002471/2023-2024 | 332/ED | 21/02/2024 | 90 | MAA KALI ENTERPRISE | 21.44 | 15.9 | 20
2486 | Hooghly Division | Srirampur Sub-Division | JAGANNATHBATI Piped Water Supply Scheme with Sinking of tubewell, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000012/2023-2024 | 1042/Hug | 10/04/2023 | 997 | M/S SHIVAM UDYOG | 212.99 | 97.79 | 30
2487 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHBATI HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000149/2024-2025 | 432/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.36 | 0.36 | 95
2488 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000318/2023-2024 | 1384/15/Hug | 15/05/2023 | 0 | Resource Division | 4.88 | 0 | 0
2489 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000340/2023-2024 | 3005/13/Hug | 05/10/2023 | 0 | Resource Division | 4.88 | 0 | 0
2490 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000548/2023-2024 | 3060/7/Hug | 11/10/2023 | 0 | Resource Division | 4.88 | 0 | 0
2491 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004146914 Reference ID- 503632742 SM Code- 17176 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00437/2024-2025 | 128 | 17/05/2024 | 0 | WBSEDCL | 3.91 | 0 | 0
2492 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004146792 Reference ID- 503632743 SM Code- 17176 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00444/2024-2025 | 133 | 17/05/2024 | 0 | WBSEDCL | 9.39 | 0 | 0
2493 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathbati water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000051/2023-2024 | 1795/ED | 24/04/2023 | 799 | AHALYA ENGINEERING WORKS | 20.26 | 14.32 | 60
2494 | Hooghly Division | Chinsuria Sub-Division | Providing 1599 nos F.H.T.C. in Bahadurpur, Belmuri,Manikpur, Radha Ballabhpur & Uttar Mogalpur Village of Bahadurpur and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2021-2022 | 933/Hug | 06/05/2021 | 40 | ORIENT CONSTRUCTION | 92.76 | 69.85 | 100
2495 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000340/2023-2024 | 2430/HUG | 11/08/2023 | 30 | MUKHERJEE AND CO | 39.91 | 39.29 | 98
2496 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000080/2021-2022 | 2097/20/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
2497 | Hooghly Division | Chinsuria Sub-Division | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000290/2021-2022 | 2201/Hug | 14/12/2021 | 30 | SARKAR CONSTRUCTION | 18.07 | 0 | 100
2498 | Hooghly Division | Chinsuria Sub-Division | Providing 90 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000335/2021-2022 | 12/Hug | 04/01/2022 | 30 | BIMAL KUMAR HALDER | 16.49 | 0 | 100
2499 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Gouribati PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000406/2022-2023 | 509/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 2.93 | 2.93 | 0
2500 | Hooghly Division | Chandannagar Sub-Division | "GAURIBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 250 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000475/2022-2023 | 2558/HUG | 25/11/2022 | 1102 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 305.74 | 230.46 | 30
2501 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of GAURIBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000660/2022-2023 | 157/HUG | 16/01/2023 | 45 | SAMIRON GHOSH | 28.9 | 25.39 | 100
2502 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of GAURIBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000710/2022-2023 | 447/HUG | 16/02/2023 | 60 | AMBIAN INFRASTRUTTURE | 12.23 | 12.23 | 100
2503 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000213/2022-2023 | 109/ 21/Hug | 10/01/2023 | 0 | Resource Division | 22.52 | 0 | 0
2504 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000216/2023-2024 | 1383/18/Hug | 15/05/2023 | 0 | Resource Division | 8.44 | 0 | 0
2505 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000272/2022-2023 | 902/8/Hug | 27/03/2023 | 0 | Resource Division | 8.54 | 0 | 0
2506 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000421/2023-2024 | 3058/37/Hug | 11/10/2023 | 0 | Resource Division | 8.29 | 0 | 0
2507 | Electrical | Chandannagar Sub-Division | Quation Money for Gauribati w/s scheme P.H.No-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02005/2023-2024 | 104 | 19/07/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
2508 | Electrical | Chandannagar Sub-Division | Gauribati water supply scheme,PHNo-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02305/2023-2024 | 140 | 25/07/2023 | 0 | WBSEDCL | 3.83 | 0 | 0
2509 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gouribati W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/05984/2023-2024 | 733 | 05/02/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
2510 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gauribati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000081/2022-2023 | 3463/ED | 30/12/2022 | 90 | POLYCON ENGINEERS | 22.28 | 22.27 | 100
2511 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gouribati water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002481/2023-2024 | 341/ED | 21/02/2024 | 90 | J.K. ENGINEERING CO. | 10.74 | 7.71 | 40
2512 | Hooghly Division | Arambug Sub-Division | Augmentation of SHYAMPUR Piped Water Supply Scheme with Sinking of 3 Nos. tube-well within ZONE-I, II & III, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I, LDS, FHTC, construction of switch-rooms & boundary walls in ZONE-II, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & LDS, RISING MAIN, FHTC, construction of switch-rooms & boundary walls in ZONE-III under PURSURAH Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000275/2023-2024 | 2292/HUG | 03/08/2023 | 823 | SIBSANKAR CHOWDHURY | 745.98 | 247.41 | 45
2513 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SHYAMPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000377/2024-2025 | 3719/HUG | 19/11/2024 | 60 | SIBSANKAR CHOWDHURY | 51.74 | 0 | 0
2514 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New Connection of Shyampur T/W-IV W/S scheme under ED PHE Dte (SM/18347) | Assistant Engineer | Junior Engineer (Civill) | BILL/01356/2024-2025 | 338 | 30/07/2024 | 0 | WBSEDCL | 4.57 | 0 | 0
2515 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Shyampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18347) | Assistant Engineer | Junior Engineer (Civill) | BILL/01613/2024-2025 | 372 | 12/08/2024 | 0 | WBSEDCL | 26.41 | 0 | 0
2516 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, T.W. No. V, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000165/2024-2025 | 1187/ED | 14/06/2024 | 90 | COOLING CARE CENTER | 10.74 | 0 | 0
2517 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyampur water supply scheme, T.W. No.- I, II, III & IV, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000820/2023-2024 | 3174/ED | 28/07/2023 | 644 | H.K.DAS & CO. | 43.01 | 2.77 | 25
2518 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1107/5/HUG | 17/04/2023 | 0 | Resource Division | 3.08 | 0 | 0
2519 | Electrical |  | Quotation bill for new service connection charges at Panchghara PWSS P.H. No.-IV, Hooghly. Application No. 5004090927 Ref ID: 503606723 |  |  | BILL/00486/2024-2025 | 148 | 22/05/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
2520 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Panchghora water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000993/2023-2024 | 3789/ED | 26/09/2023 | 90 | SRI KRISHNA NIRMAN | 10.74 | 10.67 | 80
2521 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PANCHGHORA PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002577/2023-2024 | 453/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 65
2522 | Hooghly Division |  | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0
2523 | Hooghly Division |  | MAYAPUR Piped Water Supply Scheme with Sinking of tube-well, Rising Main & construction of boundary walls at different TW site under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] |  |  | ORD/000507/2023-2024 | 2916/HUG | 22/09/2023 | 542 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 72.39 | 0 | 35
2524 | Hooghly Division |  | Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & Providing FHTC IN MAYAPUR Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] |  |  | ORD/000592/2023-2024 | 3187/HUG | 30/10/2023 | 429 | DHIRENDRA ENGINEERING & CONSTRUCTION | 212.41 | 0 | 0
2525 | Hooghly Division |  | Laying Distribution System of proposed pipe line& construction of switch-rooms at different TW site of MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] |  |  | ORD/000593/2023-2024 | 3302/Hug | 10/11/2023 | 120 | EQUIPMENTS AND SPARES AGENCIES | 197.56 | 95.62 | 30
2526 | Hooghly Division |  | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000931/2023-2024 | 987/HUG | 16/03/2024 | 30 | BIBHUTI SHAW | 46.75 | 0 | 0
2527 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000447/2023-2024 | 3057/26/Hug | 11/10/2023 | 0 | Resource Division | 14.6 | 0 | 0
2528 | Electrical |  | Quotation of New Service Connection for Mayapur w/s Scheme, PH No-II Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte. |  |  | BILL/00428/2024-2025 | 131 | 17/05/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
2529 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. I, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000177/2024-2025 | 1201/ED | 14/06/2024 | 90 | WIZARDTECH SOLUTION | 10.75 | 0 | 0
2530 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. II, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000185/2024-2025 | 1202/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0
2531 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000186/2024-2025 | 1203/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0
2532 | Hooghly Division |  | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion at Hatpukur Bakultala & Gopinathpara of MANDARAN PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. |  |  | ORD/000043/2024-2025 | 545/CH | 14/06/2024 | 7 | M/S SHIVAM UDYOG | 4.33 | 4.09 | 100
2533 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000581/2023-2024 | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 20
2534 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000617/2023-2024 | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 0 | 20
2535 | Hooghly Division |  | Repairing & Renovation of Switch Room Including Boundary Wall At Head Work Site Of Mandaran Water Supply Scheme Under Pandua Block Of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/001846/2024-2025 | 223/CH | 19/02/2025 | 30 | GHOSH CONSTRUCTION | 4.65 | 0 | 0
2536 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001251/2023-2024 | 4500/ED | 23/11/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 21.71 | 0 | 0
2537 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0
2538 | Hooghly Division | Arambug Sub-Division | TIROL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2023-2024 | 2338/HUG | 07/08/2023 | 878 | MINTU CHAKRABORTY | 737.4 | 452.1 | 50
2539 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd and 4th tube-well by D.R. Rig method, Construction of 2 nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at TIROL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000786/2023-2024 | 539/HUG | 20/02/2024 | 404 | MINTU CHAKRABORTY | 59.45 | 19.73 | 50
2540 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000465/2023-2024 | 3057/18/Hug | 11/10/2023 | 0 | Resource Division | 19.1 | 0 | 0
2541 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme,Z-I,PH No-III Block-Arambag Dist-Hooghly under Electrical Division, PHE Dte.(SM/18668) Application No-5004097240 Reference Id-503608902 | Assistant Engineer | Junior Engineer (Civill) | BILL/00082/2024-2025 | 37 | 09/04/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
2542 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18668) Application No-5004138271, Reference Id-503628273 | Assistant Engineer | Junior Engineer (Civill) | BILL/00416/2024-2025 | 94 | 06/05/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
2543 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I, PH No-4 Block-Arambag, Dist-Hooghly Under Electrical division, PHE Dte.(SM/18668) Application No-5004256486, Reference Id-503674894. | Assistant Engineer | Junior Engineer (Civill) | BILL/00976/2024-2025 | 255 | 03/07/2024 | 0 | WBSEDCL | 5.29 | 0 | 0
2544 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for BALIGARI Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000239/2024-2025 | 3474/HUG | 04/10/2024 | 60 | DIPTI TRADERS | 53.05 | 0 | 0
2545 | Hooghly Division | Chandannagar Sub-Division | BALIGARI (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR at ZONE-I & Construction of 300 cum capacity RCC OHR at ZONE-II with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000282/2023-2024 | 2337/HUG | 07/08/2023 | 872 | DIPTI TRADERS | 963.28 | 648.11 | 5
2546 | Hooghly Division | Chandannagar Sub-Division | Road restoration at Madpur under Baligori PWSS under Chandannagar Sub-Division P.H.E. Dte. (Part C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000307/2025-2026 | 940/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 4.91 | 0 | 100
2547 | Hooghly Division | Chandannagar Sub-Division | Construction of Boundary Wall at H/W site & Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Talpur Mouza of Baligari water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000859/2023-2024 | 730/HUG | 05/03/2024 | 60 | DAS CONSTRUCTION | 47.63 | 44.24 | 100
2548 | Hooghly Division | Chandannagar Sub-Division | Sinking of1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NANDANBATI Mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001761/2024-2025 | 184/HUG | 24/01/2025 | 60 | SPG ENTERPRISES | 26.58 | 0 | 0
2549 | Hooghly Division | Chandannagar Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for BAIDYAPUR mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002388/2024-2025 | 801/HUG | 25/03/2025 | 60 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 26.48 | 0 | 0
2550 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000434/2023-2024 | 3058/3/Hug | 11/10/2023 | 0 | Resource Division | 9.82 | 0 | 0
2551 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04416/2023-2024 | 494 | 07/12/2023 | 0 | WBSEDCL | 12.83 | 0 | 0
2552 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04643/2023-2024 | 627 | 08/01/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
2553 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04644/2023-2024 | 626 | 08/01/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
2554 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligori W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04646/2023-2024 | 628 | 08/01/2024 | 0 | WBSEDCL | 9.44 | 0 | 0
2555 | Electrical | Chandannagar Sub-Division | Additional Quotation Charge for Effecting New PHE Connection at PHE-2, Baligori, Monoharpur | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04853/2023-2024 | 674 | 17/01/2024 | 0 | WBSEDCL | 1.12 | 0 | 0
2556 | Electrical | Chandannagar Sub-Division | Quotation bill for new service connection at Baligori water supply scheme, Zone-I, P.H. No.-I, Hooghly Application No.- 100000101765 Referance ID: 860294205 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06261/2023-2024 | 860 | 11/03/2024 | 0 | WBSEDCL | 0.47 | 0 | 0
2557 | Electrical | Chandannagar Sub-Division | Additional quotation for effecting new service connection of Baligori Zone-II, P.H. No.-I Ref ID: 860293430 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06485/2023-2024 | 898 | 19/03/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
2558 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000849/2023-2024 | 3417/ED | 10/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 19.8 | 90
2559 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000850/2023-2024 | 3418/ED | 10/08/2023 | 90 | BINAPANI ENTERPRISE | 21.36 | 20.72 | 30
2560 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000871/2023-2024 | 3444/ED | 11/08/2023 | 90 | BINAPANI ENTERPRISE | 21.38 | 0 | 0
2561 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000872/2023-2024 | 3445/ED | 11/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 0 | 0
2562 | Hooghly Division |  | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for CHINRA ZONE-IIPiped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000288/2024-2025 | 3669/HUG | 13/11/2024 | 45 | MAYA CONSTRUCTION | 26.56 | 0 | 0
2563 | Hooghly Division |  | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. |  |  | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 224.24 | 50
2564 | Hooghly Division |  | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000849/2023-2024 | 726/HUG | 05/03/2024 | 366 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 0 | 75
2565 | Hooghly Division |  | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Chinra Zone-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. |  |  | ORD/001574/2023-2024 | 1460/HUG | 18/05/2023 | 30 | GLOBAL CONSTRUCTION | 11.78 | 0 | 0
2566 | Hooghly Division |  | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2567 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's |  |  | ORD/002745/2024-2025 | 1153/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
2568 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000423/2023-2024 | 3057/37/Hug | 11/10/2023 | 0 | Resource Division | 22.02 | 0 | 0
2569 | Electrical |  | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- 2, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004136093 Reference ID- 503627504 SM Code- 18772 |  |  | BILL/00530/2024-2025 | 180 | 30/05/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
2570 | Electrical |  | Quotation of New Service Connection for Chinra w/s Scheme, Zone-II,TW No-III Block-Khanakul-II Dist-Hooghly under Electrical Division Phe Dte.(SM/18772) Application No-5004383077 Reference Id-503732160 |  |  | BILL/01928/2024-2025 | 454 | 10/09/2024 | 0 | WBSEDCL | 3.57 | 0 | 0
2571 | Electrical |  | Quotation of New Service Connection for Chinra w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/18772) Application No-5003988265 Reference Id-503547190 |  |  | BILL/06060/2023-2024 | 759 | 16/02/2024 | 0 | WBSEDCL | 6.73 | 0 | 0
2572 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000147/2024-2025 | 1170/ED | 14/06/2024 | 90 | ANJAN ENTERPRISE | 10.71 | 0 | 0
2573 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000148/2024-2025 | 1171/ED | 14/06/2024 | 90 | R.K.ENTERPRISE | 10.74 | 0 | 0
2574 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000932/2023-2024 | 3611/ED | 29/08/2023 | 682 | MAHADEV ENTERPRISE | 22.26 | 2.84 | 30
2575 | Hooghly Division | Srirampur Sub-Division | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000100/2020-2021 | 1686/Hug | 17/12/2020 | 182 | S & P CONSTRUCTION | 24.9 | 24.9 | 98
2576 | Hooghly Division | Srirampur Sub-Division | Partial Modification & Extension of HDPE Water Distribution Line at Jangalsufi village of Borhal (Zone-I) & its adjoining mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000245/2022-2023 | 448/Ser | 31/05/2022 | 15 | ARUN SEAL AND CO. | 4.85 | 4.85 | 100
2577 | Hooghly Division | Srirampur Sub-Division | Estimate of Construction of Boundary Wall at 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001262/2024-2025 | 62/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 5 | 0 | 0
2578 | Hooghly Division | Srirampur Sub-Division | Estimate of Construction of Boundary Wall at 3rd T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001291/2024-2025 | 63/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 5 | 0 | 0
2579 | Hooghly Division | Srirampur Sub-Division | COLLECTION DATA FOR FHTC IN BORHAL | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001324/2020-2021 |  | 08/12/2020 | 0 | ARUN SEAL AND CO. | 2.15 | 0 | 0
2580 | Hooghly Division | Chinsuria Sub-Division | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000321/2020-2021 | 393/Hug | 15/02/2021 | 50 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 60.72 | 0
2581 | Hooghly Division | Chinsuria Sub-Division | Providing 253 nos F.H.T.C. in Gangarampur Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000322/2020-2021 | 394/Hug | 15/02/2021 | 20 | K. JAGADHATRY & CO. | 13.2 | 12.85 | 0
2582 | Hooghly Division | Chinsuria Sub-Division | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000910/2020-2021 | 393/HUG | 15/02/2021 | 50 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 21.9 | 100
2583 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000169/2021-2022 | 428/3-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0
2584 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000931/2021-2022 |  | 24/09/2021 | 0 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 41.41 | 0 | 0
2585 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000944/2021-2022 |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 7.39 | 0 | 0
2586 | Hooghly Division | Arambug Sub-Division | Providing 90 nos Functional Household Tap Connection (FHTC) within Jaykrishnapur & Dhulepur Village of Jaykrishnapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000015/2022-2023 | 716/Hug | 07/04/2022 | 20 | SADHUKHAN ENTERPRISE | 4.26 | 0 | 0
2587 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000112/2021-2022 | 2096/32/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
2588 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001891/2020-2021 |  | 29/01/2021 | 0 | BANBERIA CONSTRUCTION CO. | 60 | 0 | 0
2589 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
2590 | Hooghly Division | Arambug Sub-Division | Providing 220 nos F.H.T.C. in Mathura village of Jaykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2020-2021 | 243/Hug | 02/02/2021 | 20 | R AND D TRADERS | 10.05 | 0 | 0
2591 | Hooghly Division | Arambug Sub-Division | Providing 220 nos FHTC Mathura village of Joukrishnapur and its Adj. Mouzas PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000755/2020-2021 | 1440/Hug. | 02/02/2021 | 45 | R AND D TRADERS | 10.01 | 10.01 | 0
2592 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at old 1st tubewell site of Santoshpur PWSS Scheme under Chandannagar Sub-Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000435/2025-2026 | 1075/CHAN | 31/07/2025 | 20 | M/S RAJKUMAR KHAN | 4.18 | 0 | 0
2593 | Hooghly Division | Chandannagar Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of SANTOSHPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2024-2025 | 4074/HUG | 19/12/2024 | 90 | RAJ CONSTRUCTION | 9.25 | 0 | 0
2594 | Hooghly Division | Chandannagar Sub-Division | Sinking of tube-well by D.R. Rig method at SANTOSHPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000783/2023-2024 | 538/HUG | 20/02/2024 | 30 | ANIRUDDHA FARUQUE | 15.99 | 13.57 | 100
2595 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000036/2021-2022 | 2098/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
2596 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000128/2021-2022 | 2197/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
2597 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000133/2022-2023 | 2686/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0
2598 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001045/2021-2022 |  | 30/09/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.36 | 0 | 0
2599 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001094/2021-2022 |  | 06/10/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 8.41 | 0 | 0
2600 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001909/2020-2021 |  | 15/02/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 78 | 0 | 0
2601 | Hooghly Division | Chandannagar Sub-Division | ... | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/003237/2020-2021 | 844327 | 08/03/2021 | 0 | HOOGHLY ZILLA PARISHAD | 7.8 | 0 | 0
2602 | Hooghly Division | Chandannagar Sub-Division | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of MADPUR Water Supply Scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000078/2022-2023 | 209/chan | 13/04/2022 | 30 | M/S RAJKUMAR KHAN | 4.99 | 1.99 | 100
2603 | Hooghly Division | Chandannagar Sub-Division | Providing 132 nos. tap connection at Madpur mouza, Maheshpur mouza, Radhanagar mouza and Nandanbati mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000089/2022-2023 | 221/chan | 13/04/2022 | 20 | M/S RAJKUMAR KHAN | 4.99 | 5.13 | 100
2604 | Hooghly Division | Chandannagar Sub-Division | Providing 130 nos. tap connection at Bagbari mouza, Kanaipur mouza, Nazirpur mouza and sardarpur mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000408/2021-2022 | 15/chan | 05/01/2022 | 20 | M/S RAJKUMAR KHAN | 5 | 10.06 | 100
2605 | Hooghly Division | Chandannagar Sub-Division | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Madpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000854/2023-2024 | 727/HUG | 05/03/2024 | 30 | BAKSHI ENTERPRISE | 9.55 | 9.38 | 100
2606 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000032/2022-2023 | 1125/5/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2607 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002292/2020-2021 |  | 15/03/2021 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 25 | 0 | 0
2608 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002293/2020-2021 |  | 15/03/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 10.5 | 0 | 0
2609 | Hooghly Division | Arambug Sub-Division | Providing 887 nos FHTC in Jaysinghachak & Pandugram village of Arandi PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000073/2020-2021 | 1539/Hug | 24/11/2020 | 181 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 38.52 | 29.23 | 100
2610 | Hooghly Division | Arambug Sub-Division | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000336/2021-2022 | 13/Hug | 04/01/2022 | 20 | MS CHANDIMATA CONSTRUCTION | 13.37 | 0 | 100
2611 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000020/2021-2022 |  | 12/04/2021 | 0 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 2.71 | 0 | 0
2612 | Hooghly Division | Arambug Sub-Division | FHTC WORKS | Assistant Engineer | Junior Engineer (Civill) | VCH/001351/2020-2021 |  | 15/12/2020 | 0 | TITAS CONSTRUCTION | 22.3 | 0 | 0
2613 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001899/2020-2021 |  | 15/02/2021 | 0 | TITAS CONSTRUCTION | 14.09 | 0 | 0
2614 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
2615 | Hooghly Division | Chinsuria Sub-Division | Providing 1439 nos F.H.T.C. in Chanparai and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000302/2020-2021 | 380/Hug | 15/02/2021 | 40 | RAJ CONSTRUCTION | 74.99 | 70.99 | 100
2616 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000071/2021-2022 | 2097/11/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
2617 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001027/2021-2022 |  | 30/09/2021 | 0 | RAJ CONSTRUCTION | 40.07 | 0 | 0
2618 | Central Drilling | Chinsuria Sub-Division | Fuel charges for car no. WB-25H-5187 for the month of JANUARY 2023 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00127/2022-2023 | BP-2022-23-345 | 02/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0
2619 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000016/2021-2022 | 248/CMSD-II (D) | 24/08/2021 | 30 | S B S ENTERPRISE | 2.88 | 0.12 | 100
2620 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS (200 CM PIPE & 200 MM RMS FILTER)CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2021-2022 | 249/CMSD-II (D) | 24/08/2021 | 30 | S B S ENTERPRISE | 4.85 | 1.63 | 100
2621 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2021-2022 | 255/CMSD-II (D) | 24/08/2021 | 15 | S B S ENTERPRISE | 4.86 | 1.69 | 100
2622 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT DHARAMPUR W/S SCH TW-I (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000039/2021-2022 | 234/CMSD-II (D) | 23/08/2021 | 30 | S B S ENTERPRISE | 0.96 | 0.71 | 100
2623 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS ATDHARAMPUR W/S SCH TW-I (REPLACEMENT) & UDANG W/S SCG TW-I HW SITE (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000041/2021-2022 | 236/CMSD-II (D) | 23/08/2021 | 30 | S B S ENTERPRISE | 0.85 | 0.43 | 100
2624 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000077/2021-2022 | 351/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 4.17 | 4.17 | 100
2625 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG M/C IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000080/2021-2022 | 350/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 4.86 | 3.3 | 100
2626 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS:12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000081/2021-2022 | 352/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 2.38 | 1.95 | 100
2627 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF GRAVELS & BENTONITE POWDER AT SITE FOR CONSTRUCTION OF TUBE WELL AT DHARAMPUR TW-I (REPLACEMENT TUBE WELL) HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2021-2022 | 222/CMSD-II (D) | 17/08/2021 | 15 | S B S ENTERPRISE | 0.89 | 0.35 | 100
2628 | Hooghly Division | Arambug Sub-Division | Providing 800 nos Functional Household Tap Connection (FHTC) within the command area of BHANGAMORA Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000310/2021-2022 | 2229/Hug | 15/12/2021 | 60 | BIMAL KUMAR HALDER | 40.78 | 38.51 | 100
2629 | Electrical | Chinsuria Sub-Division | Replacement of some electrical accessories, voltage correcting device and other allied works for Pandua water supply scheme, Zone-III, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000317/2022-2023 | 493/HMSD | 02/03/2023 | 30 | KARUNAMOY ENGINEERING | 3.06 | 3.06 | 0
2630 | Central Drilling | Chinsuria Sub-Division | PROVIDING PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000177/2022-2023 | 328/CMSD-I | 15/07/2022 | 10 | INDRANI ENTERPRISE | 0.93 | 0.73 | 100
2631 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN PANDUA, SUTAHATA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000178/2022-2023 | 223/CMSD-I | 20/06/2022 | 15 | INDRANI ENTERPRISE | 4.98 | 4.98 | 100
2632 | Central Drilling | Chinsuria Sub-Division | PROVIDING BENTONITE POWDER SODIUM BASED WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000179/2022-2023 | 329/CMSD-I | 15/07/2022 | 10 | INDRANI ENTERPRISE | 0.97 | 0.73 | 100
2633 | Central Drilling | Chinsuria Sub-Division | SINKING OF 200 MM X 100 MM DIA TUBE WELL WITH OTHER WOORKS AT SITE IN PANDUA, GHATAL BLOCK UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000180/2022-2023 | 396/CMSD-I | 05/08/2022 | 15 | INDRANI ENTERPRISE | 5 | 4.92 | 100
2634 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000030/2023-2024 | 1130/HUG | 19/04/2023 | 45 | BAKSHI ENTERPRISE | 40.32 | 16.69 | 30
2635 | Hooghly Division | Chinsuria Sub-Division | Providing 70 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-II) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000275/2022-2023 | 730/CH | 26/08/2022 | 15 | BIMAL KUMAR HALDER | 4.96 | 4.96 | 100
2636 | Hooghly Division | Chinsuria Sub-Division | Providing of 87 nos Functional House Hold Tap Connection Within Debanandapur Mouza of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000419/2021-2022 | 91/CH | 03/02/2022 | 25 | BIMAL KUMAR HALDER | 4.99 | 4.57 | 100
2637 | Hooghly Division | Chinsuria Sub-Division | Providing 80 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-I) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000720/2022-2023 | 756/Ch | 05/09/2022 | 15 | BIMAL KUMAR HALDER | 4.97 | 4.79 | 100
2638 | Hooghly Division | Arambug Sub-Division | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000363/2021-2022 | 124/Hug | 19/01/2022 | 15 | SADHUKHAN ENTERPRISE | 3.79 | 3.78 | 100
2639 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000018/2021-2022 | 2096/15/Hug | 26/11/2021 | 0 | Resource Division | 0.82 | 0 | 0
2640 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000522/2021-2022 |  | 23/07/2021 | 0 | M/S T.K.B. CONSTRUCTION | 13.44 | 0 | 0
2641 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000524/2021-2022 |  | 23/07/2021 | 0 | DILIP KUMAR GHOSH | 13.44 | 0 | 0
2642 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000595/2021-2022 |  | 17/08/2021 | 0 | M/S T.K.B. CONSTRUCTION | 5.51 | 0 | 0
2643 | Hooghly Division | Arambug Sub-Division | Placement of Fund | Assistant Engineer | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
2644 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002631/2020-2021 |  | 19/03/2021 | 0 | DILIP KUMAR GHOSH | 15 | 0 | 0
2645 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Chanparui Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000006/2025-2026 | 488/CH | 04/04/2025 | 10 | RAJ CONSTRUCTION | 4.79 | 0 | 0
2646 | Hooghly Division | Chinsuria Sub-Division | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Chanparai Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000008/2025-2026 | 490/CH | 04/04/2025 | 10 | RAJ CONSTRUCTION | 1.97 | 0 | 0
2647 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe line for inter connection between T.W & Distribution System for Augmentation of CHANPARAI Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within CHINSURAH-MOGRA Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000135/2023-2024 | 1477/HUG | 19/05/2023 | 45 | SRI KRISHNA ENTERPRISE | 11.81 | 11.25 | 100
2648 | Hooghly Division | Chinsuria Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at CHANPARAI PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 03 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000351/2022-2023 | 2009/HUG | 13/09/2022 | 45 | OSMAN SEKH | 22.63 | 11.03 | 0
2649 | Hooghly Division | Chinsuria Sub-Division | Augmentation of CHANPARAI Water Supply Scheme with LDS, FHTC, Rising Main at CHINSURAH MOGRA Block of Chinsurah Sub-Division under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000405/2022-2023 | 2178/HUG | 29/09/2022 | 75 | RAJ CONSTRUCTION | 251.9 | 230.86 | 10
2650 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Chanparai Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000464/2021-2022 | 128/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 3.38 | 0
2651 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000004/2023-2024 | 1105/Hug | 17/04/2023 | 0 | Resource Division | 7.86 | 0 | 0
2652 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000011/2022-2023 | 1123/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0
2653 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000115/2022-2023 | 1991/1/HUG | 12/09/2022 | 0 | Resource Division | 7.86 | 0 | 0
2654 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT CHANPARAI W/S SCH., P.H. NO. - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00782/2023-2024 | 53 | 31/05/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
2655 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanparai water supply scheme, T.W. No.- I, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000203/2022-2023 | 830/ED | 14/02/2023 | 259 | NITESH MANAGEMENT | 10.73 | 10.4 | 97
2656 | Hooghly Division | Chinsuria Sub-Division | Pawan Ochai Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00495/2023-2024 | BP-2023-24-396 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 6.79 | 0 | 0
2657 | Hooghly Division | Chinsuria Sub-Division | Pandua Polba Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00496/2023-2024 | BP-2023-24-397 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 33.08 | 0 | 0
2658 | Hooghly Division | Chinsuria Sub-Division | Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00683/2023-2024 | BP-2023-24-591 | 16/11/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 93 | 0 | 0
2659 | Hooghly Division | Chinsuria Sub-Division | Laying C.I/D.I pipes & specials for interconnection between T.W No. -I & II with distribution pipe line at Polba (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000041/2024-2025 | 543/CH | 18/06/2024 | 7 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.66 | 2.59 | 50
2660 | Hooghly Division | Chinsuria Sub-Division | Augmentation of POLBA (ZONE-II) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000213/2022-2023 | 1718/Hug | 24/08/2022 | 40 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 110.96 | 102.3 | 85
2661 | Hooghly Division | Chinsuria Sub-Division | Augmentation of POLBA (ZONE-I) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. SL NO - 04 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000250/2022-2023 | 1885/HUG | 01/09/2022 | 90 | P.B. ENTERPRISE (PINTU BHADURI) | 411.46 | 392.41 | 65
2662 | Hooghly Division | Chinsuria Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000271/2024-2025 | 930/CH | 05/11/2024 | 5 | R.K. TRADERS | 4.85 | 4.68 | 90
2663 | Hooghly Division | Chinsuria Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000272/2024-2025 | 934/CH | 11/11/2024 | 5 | TAPAS ADHYA | 2.12 | 2.12 | 90
2664 | Hooghly Division | Chinsuria Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of 450 cum capacity of POLBA Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 02 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000284/2022-2023 | 1905/HUG | 05/09/2022 | 30 | M/S T.K.B. CONSTRUCTION | 9.49 | 9.49 | 0
2665 | Hooghly Division | Chinsuria Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at POLBA (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 04 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000352/2022-2023 | 2010/HUG | 13/09/2022 | 45 | OSMAN SEKH | 22.63 | 21.12 | 0
2666 | Hooghly Division | Chinsuria Sub-Division | Repairing Of Switch Room, Boundary wall for Augemntation Of POLBA ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000364/2023-2024 | 2455/HUG | 12/08/2023 | 45 | SUDIPTA DAS | 9.47 | 18.87 | 100
2667 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000543/2021-2022 | 143/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.76 | 0
2668 | Hooghly Division | Chinsuria Sub-Division | Additional Survey Work for Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000544/2021-2022 | 144/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0.4 | 0
2669 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site Of POLBA ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000706/2022-2023 | 443/HUG | 16/02/2023 | 60 | MAA JAGADHATRI CONSTRUCTION | 12.24 | 12.24 | 55
2670 | Hooghly Division | Chinsuria Sub-Division | Construction of Guard Room at Polba (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000772/2023-2024 | 128/CH | 16/02/2024 | 15 | MAA BUNAMATA ENTERPRISE | 3.76 | 3.75 | 15
2671 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DADPUR GP of POLBA-DADPUR Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000923/2023-2024 | 243/CH | 12/03/2024 | 30 | SHREEOM ENTERPRISE | 4.98 | 1.31 | 70
2672 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in POLBA GP of POLBA-DADPUR Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000925/2023-2024 | 245/CH | 12/03/2024 | 30 | R.K. TRADERS | 4.98 | 4.96 | 75
2673 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Birpala village under Polba Dadpur Block, Gopalnagar village of Polba Dadpur Block and Kasemaligar village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000990/2023-2024 | 264/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2674 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sonatikri village under Polba Dadpur Block, Banshdarun village of Polba Dadpur Block and Arzi Jatchandi village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000992/2023-2024 | 266/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2675 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Banseya village under Polba Dadpur Block, Barunanpara village of Polba Dadpur Block and Ramnagar Bheri village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000993/2023-2024 | 267/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2676 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Dubir Bheri village under Polba Dadpur Block, Dakshin Babnan village of Polba Dadpur Block and Chanda village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000994/2023-2024 | 268/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2677 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Khurigachi village under Polba Dadpur Block, Musar village of Polba Dadpur Block and Nonadanga village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000995/2023-2024 | 269/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2678 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Meghsar village under Polba Dadpur Block, Baral Malimpur village of Polba Dadpur Block and Sangrampur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000996/2023-2024 | 270/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
2679 | Hooghly Division | Chinsuria Sub-Division | Providing Functional House hold tap connection (FHTC) under JJM within left out mouzas/habitations of differet PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001852/2024-2025 | 231/CH | 19/02/2025 | 10 | M/S BIMAL DAS AND CO. | 2.86 | 0 | 0
2680 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 No. tube-well, Rising Main for inter connection between T.W & Distribution, construction of boundary wall at PUINAN mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002927/2024-2025 | 4144/HUG | 24/12/2024 | 30 | BANSBERIA CONSTRUCTION CO. | 20.34 | 0 | 0
2681 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall at GOSWAMIMALIPARA mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002928/2024-2025 | 4145/HUG | 24/12/2024 | 45 | BANSBERIA CONSTRUCTION CO. | 26.48 | 0 | 0
2682 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000001/2023-2024 | 1105/4/Hug | 17/04/2023 | 0 | Resource Division | 14.69 | 0 | 0
2683 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000112/2022-2023 | 1991/3/HUG | 12/09/2022 | 0 | Resource Division | 20.25 | 0 | 0
2684 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000259/2023-2024 | 1386/38/Hug | 15/05/2023 | 0 | Resource Division | 0.98 | 0 | 0
2685 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000539/2023-2024 | 3059/30/Hug | 11/10/2023 | 0 | Resource Division | 24.79 | 0 | 0
2686 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Polba[SM/10468] W/S Sch. , Zone - I, T/W No. - IV, (Nr. Kasundipara primary school), Block - Polba-Dadpur, under Polba CCC, WBSEDCL, Ref. Id. - 503595736, Dt. - 05/04/2024, Application No. - 5004071216, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00121/2024-2025 | 35 | 09/04/2024 | 0 | WBSEDCL | 7.13 | 0 | 0
2687 | Electrical | Chinsuria Sub-Division | Quotation bill for security money of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00799/2022-2023 | 163 | 20/02/2023 | 0 | WBSEDCL | 2.81 | 0 | 0
2688 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charges of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00800/2022-2023 | 163 | 20/02/2023 | 0 | WBSEDCL | 12.44 | 0 | 0
2689 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Polba water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000221/2022-2023 | 852/ED | 14/02/2023 | 90 | S.P. CONSTRUCTION | 21.49 | 20.78 | 98
2690 | Hooghly Division | Arambug Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00739/2023-2024 |  | 06/11/2023 | 0 | GOUR KUMAR DAS | 0.76 | 0 | 0
2691 | Hooghly Division | Arambug Sub-Division | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-II) with Laying Distribution System, Construction of switch room & boundary wall at proposed 3rd TW site and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000053/2022-2023 | 853/Hug | 25/04/2022 | 45 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 104.29 | 31.67 | 80
2692 | Hooghly Division | Arambug Sub-Division | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-I) with Laying Distribution System, repairing of existing OHR, switch rooms & boundary wall and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000114/2022-2023 | 1150/Hug | 09/06/2022 | 1218 | TITAS CONSTRUCTION | 231.61 | 144.09 | 80
2693 | Hooghly Division | Arambug Sub-Division | Route survey Design drawing & DPR preparation of Kamarkundu Zone- I, II & III PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000177/2022-2023 | 271/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.97 | 4.93 | 100
2694 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 11.91 | 70
2695 | Hooghly Division | Arambug Sub-Division | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir of KAMARPUKUR Water Supply Scheme under Arambagh Sub - Division, P.H.E. Dte., Hooghly. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000308/2024-2025 | 3677/HUG | 13/11/2024 | 60 | ZEST INFRACON | 28.14 | 0 | 0
2696 | Hooghly Division | Arambug Sub-Division | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Chandannagar Sub-Division Office under Chandannagar Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000321/2021-2022 | 2110/hug | 30/11/2021 | 121 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0
2697 | Hooghly Division | Arambug Sub-Division | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000327/2021-2022 | 2105/Hug | 29/11/2021 | 121 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0
2698 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of KAMARPUKUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000383/2021-2022 | 614/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.61 | 3.62 | 0
2699 | Hooghly Division | Arambug Sub-Division | Repairing of Rising Main due to Construction of Box Culvert by PWD and laying D.I pipes & specials for Rising Main pipe line for KAMARPUKUR Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. [Block-Goghat-II] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000432/2022-2023 | 733/Arg | 29/09/2022 | 20 | DHIRENDRA ENGINEERING & CONSTRUCTION | 4.17 | 4.15 | 0
2700 | Hooghly Division | Arambug Sub-Division | Additional pipeline due to shifting of 3rd Tubewell site under Augmentation of Kamarpukur Zone-II water supply scheme under Goghat- II block of Arambagh Sub-Division, Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000744/2023-2024 | 379/HUG | 08/02/2024 | 203 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.75 | 17.75 | 100
2701 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000024/2022-2023 | 1124/5/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0
2702 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000048/2022-2023 | 1590/6/Hug | 03/08/2022 | 0 | Resource Division | 18.45 | 0 | 0
2703 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000094/2022-2023 | 1773/28/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
2704 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000179/2022-2023 | 79/20/Hug | 06/01/2023 | 0 | Resource Division | 1.78 | 0 | 0
2705 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000189/2023-2024 | 1385/60/Hug | 15/05/2023 | 0 | Resource Division | 9.22 | 0 | 0
2706 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kamarpukur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000219/2022-2023 | 844/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 0 | 35
2707 | Hooghly Division | Srirampur Sub-Division | Estimate for Reconstruction of boundary wall, Internal Pathway and allied works Head Works Site of Seakhala under Chanditala Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000014/2025-2026 | 285/SER | 17/04/2025 | 25 | M/S RAJKUMAR KHAN | 4.68 | 0 | 92
2708 | Hooghly Division | Srirampur Sub-Division | Piped water supply scheme at CHANDITALA PANCHGHORA NANDANKANAN area under Chanditala - II block of Hooghly Division. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000029/2024-2025 | 2286/HUG | 14/06/2024 | 60 | AMBIAN INFRASTRUCTURE | 42.77 | 0 | 0
2709 | Hooghly Division | Srirampur Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at 3rd TW sites for CHANDITALA (PIARAPUR) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000051/2024-2025 | 2340/HUG | 19/06/2024 | 339 | MS PRADIP KUMAR PAL | 27.85 | 0 | 55
2710 | Hooghly Division | Srirampur Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system,For AUGMENTATION OF of CHANDITALA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000117/2023-2024 | 1446/HUG | 18/05/2023 | 30 | SB ASSOCIATES | 31.08 | 14.8 | 70
2711 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT CHANDITALA PWSS NEAR EKLAKI UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000148/2024-2025 | 431/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.36 | 0.35 | 95
2712 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000150/2022-2023 | 1421/Hug | 12/07/2022 | 45 | S.B. ASSOCIATES | 78.39 | 17.33 | 20
2713 | Hooghly Division | Srirampur Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA I & SERAMPORE-UTTARPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000181/2024-2025 | 517/SER | 11/09/2024 | 5 | JOY GURU ENTERPRISE | 3.53 | 6.99 | 95
2714 | Hooghly Division | Srirampur Sub-Division | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA II Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000182/2024-2025 | 518/SER | 11/09/2024 | 5 | TOTON MONDAL | 4.15 | 4.12 | 95
2715 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-I) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000184/2024-2025 | 522/SER | 12/09/2024 | 5 | TOTON MONDAL | 4.93 | 4.93 | 95
2716 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-II) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000185/2024-2025 | 523/SER | 12/09/2024 | 5 | TOTON MONDAL | 4.93 | 4.93 | 95
2717 | Hooghly Division | Srirampur Sub-Division | Construction of Switch Room,Boundary wall,and rising main with interconnection atChanditalaW/s Scheme(Zone 1)Beledanga,Chanditala-II Block under Hooghly Division PHE Dte.Source Augmentation. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000267/2024-2025 | 3614/HUG | 05/11/2024 | 60 | S D ENTERPRISE | 25.82 | 0 | 0
2718 | Hooghly Division | Srirampur Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Chanditala I & II & Jangipara Block (Phase-III) in the District of Hooghly under Serampore Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000346/2024-2025 | 644/SER | 05/11/2024 | 15 | TECHVISION | 4.94 | 0 | 0
2719 | Hooghly Division | Srirampur Sub-Division | Sinking of 01 nos. (size 100 X 40 mm dia) 154.0 Mtr. Deep, Indian Mark-II Tube well with PVC pipe & Strainer near Chanditala Police Station under Chanditala Water Supply Scheme of Hooghly Division. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000348/2025-2026 | 539/SER | 29/08/2025 | 10 | PANKAJ KUMAR MANNA | 0.99 | 0 | 0
2720 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala - II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000425/2022-2023 | 1421/HUG | 12/07/2022 | 45 | S.B. ASSOCIATES | 78.39 | 44.01 | 0
2721 | Hooghly Division | Srirampur Sub-Division | Construction of Boundary wall,Toilet,Plumbing arrangement,Path way and repairing of Existing Pump House at Pump house No 12ofChanditala water Supply Scheme under Serampur SubDivision;of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000437/2024-2025 | 4041/HUG | 19/12/2024 | 90 | TOTON MONDAL | 10.75 | 0 | 0
2722 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Chanditala (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000471/2021-2022 | 363/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.33 | 0
2723 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Chanditala (Zone-III & IV) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000472/2021-2022 | 364/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.56 | 3.55 | 0
2724 | Hooghly Division | Srirampur Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at CHANDITALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000494/2021-2022 | 622/Hug | 31/03/2022 | 122 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0
2725 | Hooghly Division | Srirampur Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SEAKHALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000495/2021-2022 | 623/Hug | 31/03/2022 | 122 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0
2726 | Hooghly Division | Srirampur Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 23.09 | 40
2727 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Garalgacha and Krishnapur Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Garalgacha) at Chanditala-II Block under Serampore Sub-Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000620/2022-2023 | 1539/HUG | 27/07/2022 | 60 | DAS TRADING | 86.11 | 64.06 | 100
2728 | Hooghly Division | Srirampur Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 28.3 | 100
2729 | Hooghly Division | Srirampur Sub-Division | Laying of Balance pipeline and allied works due to road widening work at Chanditala W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000664/2023-2024 | 3562/HUG | 05/12/2023 | 30 | P. B. ENTERPRISE(PINTU BHADURI) | 43.61 | 40.54 | 60
2730 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-III) Water Supply Scheme with LDS within Eklakhi and part of Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000674/2022-2023 | 1420/HUG | 12/07/2022 | 45 | BIMAL KUMAR HALDER | 56.66 | 54.61 | 99
2731 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Barijhati & Bledanga Mouza & Functional Household tap Connection & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000678/2022-2023 | 1538/HUG | 27/07/2022 | 45 | M/S SHIVAM UDYOG | 56.4 | 40.37 | 100
2732 | Hooghly Division | Srirampur Sub-Division | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNARAMPUR (CHANDITALA) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000892/2023-2024 | 816/HUG | 11/03/2024 | 60 | CHAKRABORTY ENTERPRISE | 31.68 | 6.15 | 78
2733 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Chanditala Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6M X 3.0M ) and Boundary Wall at 10th T.W Site & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000894/2022-2023 | 1418/HUG | 12/07/2022 | 45 | EVEREST CONSULTANT SERVICES (SUBRATA KUNDU) | 73.77 | 38.85 | 0
2734 | Hooghly Division | Srirampur Sub-Division | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Barijhati and Thero Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Barijhati) at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000895/2022-2023 | 1419/HUG | 12/07/2022 | 45 | CHAKRABORTTI ENTERPRISE | 88.54 | 66.85 | 0
2735 | Hooghly Division | Srirampur Sub-Division | Estimate for construction of 2 nos Toilets at Piarapur Pump House No-2 and Krishnarampur Pump Hose No-2 under Chanditala PWSS under Serampore Sub - Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001302/2024-2025 | 74/SER | 20/01/2025 | 10 | M/S RAJKUMAR KHAN | 3.91 | 0 | 50
2736 | Hooghly Division | Srirampur Sub-Division | Estimate for jack pushing of Road due to interconnection of Existing pipeline to 3rd Pump House of Krishnarampur mouza under Chanditala W/S Supply scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001304/2024-2025 | 76/SER | 20/01/2025 | 10 | CHAKRABORTY ENTERPRISE | 3.93 | 0 | 0
2737 | Hooghly Division | Srirampur Sub-Division | Balance works for laying of water supply pipeline by HDD process under Chanditala Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002253/2024-2025 | 652/HUG | 10/03/2025 | 30 | M/S SHIVAM UDYOG | 35.39 | 0 | 0
2738 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000005/2022-2023 | 1122/2/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
2739 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000037/2022-2023 | 1291/2/Hug | 24/06/2022 | 0 | Resource Division | 9.24 | 0 | 0
2740 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000122/2022-2023 | 2210/1/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
2741 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000322/2023-2024 | 1384/19/Hug | 15/05/2023 | 0 | Resource Division | 18.64 | 0 | 0
2742 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00031/2024-2025 | 19 | 05/04/2024 | 0 | WBSEDCL | 6.27 | 0 | 0
2743 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Chanditala PWSS Zone-I, P.H. No.-V, Hooghly. Application No. 5004085765 Ref ID: 503603819 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00032/2024-2025 | 20 | 05/04/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
2744 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- III, T.W. NO- III, Dist.-Hooghly under PHE Dte. Application No- 5004091705 Reference ID- 503606735 SM Code- 10338 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00161/2024-2025 | 70 | 16/04/2024 | 0 | WBSEDCL | 8.21 | 0 | 0
2745 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00485/2024-2025 | 152 | 22/05/2024 | 0 | WBSEDCL | 3.84 | 0 | 0
2746 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection of WBSEDC at Chanditalaw/s scheme, T.W. No.-XII | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00777/2022-2023 | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0
2747 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection of WBSEDC at Chanditala w/s scheme, T.W. No.-XI | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00778/2022-2023 | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0
2748 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chanditala water supply scheme, T.W. No. X, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000101/2022-2023 | 3529/ED | 30/12/2022 | 90 | BISALAXMI ENTERPRISE | 10.66 | 10.65 | 0
2749 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanditala water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000202/2022-2023 | 829/ED | 14/02/2023 | 687 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 19.69 | 95
2750 | Electrical | Srirampur Sub-Division | Augumention of Electro Mechanical Equipments and other electro mechanical accessories at Pump House under Barijhati GP and Garalgacha Gram Panchayet of Chanditala - II Block, Dist-Hooghly under Electrical Divisio, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001480/2023-2024 | 4892/ED | 27/12/2023 | 90 | D. K. ELECTRIC | 31.09 | 30.98 | 100
2751 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XII & XIII, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002504/2023-2024 | 420/ED | 29/02/2024 | 564 | DEY ENTERPRISE | 20.85 | 10.14 | 40
2752 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XIV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002576/2023-2024 | 452/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 65
2753 | Electrical | Srirampur Sub-Division | Quatation Bill for Chanditala W/S. Sch. PH-X | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | VCH/002744/2022-2023 |  | 16/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0
2754 | Electrical | Srirampur Sub-Division | Quotation bill for Chanditala W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | VCH/002752/2022-2023 | 109 | 18/11/2022 | 0 | WBSEDCL | 0.66 | 0 | 0
2755 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000079/2022-2023 | 236/CMSD-II(D) | 20/05/2022 | 15 | S B S ENTERPRISE | 3.98 | 3.2 | 0
2756 | Central Drilling | Srirampur Sub-Division | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II(D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000080/2022-2023 | 235/CMSD-II(D) | 20/05/2022 | 15 | S B S ENTERPRISE | 2.79 | 2.79 | 0
2757 | Central Drilling | Srirampur Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000081/2022-2023 | 238/CMSD-II(D) | 20/05/2022 | 15 | M/S S.K.GHOSH & CO. | 1.97 | 1.71 | 0
2758 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OGF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR CHANDITALA W/S SCHEME CHANDITALA -II BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000082/2022-2023 | 232/CMSD-II (D) | 20/05/2022 | 15 | S B S ENTERPRISE | 2.4 | 2.26 | 0
2759 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDITALA PWSS, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000270/2022-2023 | 1374/CDD | 24/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 12.9 | 11.13 | 0
2760 | Central Drilling | Srirampur Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAP (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE SUPERINTENDING ENGINEER, M/E, PMU WBDWSIP UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000313/2022-2023 | 261/CMSD-I | 27/06/2022 | 15 | SIDDHARTHA CHATTERJEE | 0.9 | 1.49 | 0
2761 | Central Drilling | Srirampur Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBEWELL AT CHANDITALA, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000319/2022-2023 | 508/CMSDII | 11/11/2022 | 7 | SUBHRA ENTERPRISE | 0.98 | 0.9 | 0
2762 | Central Drilling | Srirampur Sub-Division | Providing drilling crew and other works for construction of TW (300mm x 200mm x 210 mtr. depth) by utilising Departmental machineries for Chanditala PWSS under Hooghly District, CDD, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000333/2022-2023 | 1561/CDD | 08/12/2022 | 30 | SUBHRA ENTERPRISE | 12.67 | 10.2 | 0
2763 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 320.3 | 30
2764 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000116/2023-2024 | 1264/11/HUG | 03/05/2023 | 0 | Resource Division | 24.6 | 0 | 0
2765 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000529/2023-2024 | 3059/7/Hug | 11/10/2023 | 0 | Resource Division | 14.89 | 0 | 0
2766 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05715/2023-2024 | 704 | 25/01/2024 | 0 | WBSEDCL | 5.78 | 0 | 0
2767 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05718/2023-2024 | 705 | 25/01/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
2768 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rudrani water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000093/2022-2023 | 3475/ED | 30/12/2022 | 90 | INDTECH ASSOCIATES. | 21.42 | 0 | 0
2769 | Hooghly Division | Chinsuria Sub-Division | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 93.02 | 20
2770 | Hooghly Division | Chinsuria Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 25.04 | 20
2771 | Hooghly Division | Chinsuria Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for GURBARI Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000335/2023-2024 | 2422/HUG | 11/08/2023 | 90 | GEE BEE NIRMAN CO PRIVATE LIMITED | 51.96 | 0 | 0
2772 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000128/2023-2024 | 1264/23/HUG | 03/05/2023 | 0 | Resource Division | 12.17 | 0 | 0
2773 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000266/2023-2024 | 1386/45/Hug | 15/05/2023 | 0 | Resource Division | 17.02 | 0 | 0
2774 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000521/2023-2024 | 3059/38/Hug | 11/10/2023 | 0 | Resource Division | 17.02 | 0 | 0
2775 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Gurbari W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05065/2023-2024 | 681 | 19/01/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
2776 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gurbari water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000082/2022-2023 | 3464/ED | 30/12/2022 | 90 | A.G. ENTERPRISE | 21.58 | 0 | 0
2777 | Hooghly Division | Arambug Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00375/2023-2024 |  | 22/08/2023 | 0 | AATISH KUMAR SHAW | 0.4 | 0 | 0
2778 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Mandra Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000244/2022-2023 | 365/Arg | 19/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.64 | 3.59 | 0
2779 | Hooghly Division | Arambug Sub-Division | Augmentation of MANDRA Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under Arambagh Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000404/2022-2023 | 2173/HUG | 28/09/2022 | 1009 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 404.56 | 351.98 | 60
2780 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at 3rd & 4th TubeWell Site of MANDRA under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000466/2024-2025 | 4048/HUG | 19/12/2024 | 90 | MUNSHI TAJUDDIN | 15.5 | 0 | 0
2781 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of MANDRA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000665/2022-2023 | 160/HUG | 16/01/2023 | 45 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 28.39 | 0 | 0
2782 | Hooghly Division | Arambug Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of Mandra Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000705/2022-2023 | 442/HUG | 16/02/2023 | 60 | BENGAL TRADERS | 12.32 | 12.32 | 100
2783 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
2784 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000007/2023-2024 | 1106/1/HUG | 17/04/2023 | 0 | Resource Division | 13.56 | 0 | 0
2785 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000058/2022-2023 | 1688/3/HUG | 22/08/2022 | 0 | Resource Division | 11.15 | 0 | 0
2786 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000086/2022-2023 | 1773/20/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
2787 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000120/2022-2023 | 2209/3/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
2788 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000194/2023-2024 | 1385/65/Hug | 15/05/2023 | 0 | Resource Division | 13.13 | 0 | 0
2789 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000257/2022-2023 | 127/16/Hug | 13/01/2023 | 0 | Resource Division | 10.67 | 0 | 0
2790 | Electrical | Arambug Sub-Division | New Service Connection at Mandara W/S. Sch. PH-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00725/2023-2024 | 15 | 24/04/2023 | 0 | WBSEDCL | 9.72 | 0 | 0
2791 | Electrical | Arambug Sub-Division | New service connection of WBSEDCL for Mandra w/s scheme | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00798/2022-2023 | 161 | 16/02/2023 | 0 | WBSEDCL | 0.31 | 0 | 0
2792 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Mandara W/S. Sch. PH-IV | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01284/2022-2023 | 190 | 16/03/2023 | 0 | WBSEDCL | 2.76 | 0 | 0
2793 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mandra water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000038/2023-2024 | 1715/ED | 18/04/2023 | 90 | M/S A.K BANERJEE | 21.89 | 21.66 | 75
2794 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. V, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000128/2024-2025 | 1153/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
2795 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. VI, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000129/2024-2025 | 1154/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
2796 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ATGHARA PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000175/2024-2025 | 1199/ED | 14/06/2024 | 90 | EMCON | 10.74 | 0 | 0
2797 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIESFOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000348/2022-2023 | 1679/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 0 | 0
2798 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000351/2022-2023 | 1678/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 0 | 0
2799 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-III, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000369/2022-2023 | 1678/ CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 10.73 | 0
2800 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREQW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-IV, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000370/2022-2023 | 1679/ CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 9.51 | 0
2801 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for PURUSHOTTAMPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000399/2024-2025 | 3779/HUG | 25/11/2024 | 362 | WATER TECH | 50.34 | 0 | 30
2802 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000193/2022-2023 | 109/3/Hug | 10/01/2023 | 0 | Resource Division | 44.45 | 0 | 0
2803 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000455/2023-2024 | 3058/31/Hug | 11/10/2023 | 0 | Resource Division | 10.44 | 0 | 0
2804 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection at Purushottampur W/S Sch. , T/W No. - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04126/2023-2024 | 381 | 25/10/2023 | 0 | WBSEDCL | 2.72 | 0 | 0
2805 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Purushattampur W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04244/2023-2024 | 413 | 10/11/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
2806 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purushottampur water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000166/2022-2023 | 3500/ED | 30/12/2022 | 90 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 21.49 | 19.47 | 80
2807 | Hooghly Division | Hooghly Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/00081/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 215.31 | 0 | 0
2808 | Hooghly Division | Hooghly Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/00222/2023-2024 | BP-2023-24-211 | 14/07/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 232.26 | 0 | 0
2809 | Hooghly Division | Hooghly Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/00352/2023-2024 | BP-2023-24-295 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 206.54 | 0 | 0
2810 | Hooghly Division | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL - II BLOCK UNDER HOOGHLY DISTRICT (TSM/020222) | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | ORD/000024/2023-2024 | 1104/HUG | 17/04/2023 | 150 | RAJMAHAL ENTERPRISE | 41.84 | 32.87 | 70
2811 | Hooghly Division | Hooghly Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Muragari Mini PWSS 2. Charsundalpur Mini PWSS 3. Digra Mini PWSS 4. Rampur Mini PWSS 5. Naopara Mini PWSS 6. Telinipara Mini PWSS | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | ORD/000831/2023-2024 | 209/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 45
2812 | Hooghly Division | Hooghly Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | RTOR000270/2023-2024 | 1386/49/Hug | 15/05/2023 | 0 | Resource Division | 10.2 | 0 | 0
2813 | Electrical | Hooghly Division | Mini Piped water Supply Scheme | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
2814 | Electrical | Hooghly Division | Mini piped Water Supply scheme | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
2815 | Hooghly Division | Arambug Sub-Division | Augmentation of BARADANGAL ZONE-I Water Supply Scheme with Laying Distribution System including providing Functional Household Tap Connection (FHTC) at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000216/2022-2023 | 1702/Hug | 22/08/2022 | 60 | M/S CARE | 193.77 | 181.56 | 99
2816 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000241/2022-2023 | 337/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 3.98 | 0
2817 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir Of BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000362/2023-2024 | 2454/HUG | 12/08/2023 | 60 | TANISA ENTERPRISE | 7.86 | 7.65 | 95
2818 | Hooghly Division | Arambug Sub-Division | Additional work for Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. Part-B | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000391/2022-2023 | 624/Arg | 01/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.3 | 1.3 | 0
2819 | Hooghly Division | Arambug Sub-Division | Augmentation of BARADANGAL ZONE-II PWSS with LDS, FHTC, Rising Main and Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000581/2022-2023 | 2827/HUG | 15/12/2022 | 204 | JAHANGIR ALAM | 266.1 | 161.13 | 60
2820 | Hooghly Division | Arambug Sub-Division | Construction of 2 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000788/2023-2024 | 540/HUG | 20/02/2024 | 425 | DIAMOND ENGINEERS CO OP AND CONSTRUCTION SOCIETY LTD | 27.35 | 16.36 | 70
2821 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000027/2023-2024 | 1234/8/Hug | 28/04/2023 | 0 | Resource Division | 26.55 | 0 | 0
2822 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000069/2022-2023 | 1773/3/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
2823 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000191/2023-2024 | 1385/62/Hug | 15/05/2023 | 0 | Resource Division | 6.84 | 0 | 0
2824 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-I Dist-Hooghly under ED, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01917/2023-2024 | 91 | 13/07/2023 | 0 | WBSEDCL | 5.05 | 0 | 0
2825 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-II District-Hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01918/2023-2024 | 92 | 13/07/2023 | 0 | WBSEDCL | 4.6 | 0 | 0
2826 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baradangal water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000198/2022-2023 | 825/ED | 14/02/2023 | 926 | OSMAN SEKH | 21.5 | 1.75 | 70
2827 | Central Drilling | Arambug Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Baradangal W/S Scheme (Z-II, TW-I&II), Arambag block under hooghly District, CDD PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000459/2022-2023 | 2329/CDD | 30/03/2023 | 30 | ASHUTOSH DAS & CO | 22.73 | 18.83 | 100
2828 | Hooghly Division | Chinsuria Sub-Division | Providing 1338 nos F.H.T.C. in Dwarpara, Beleswar& Basna Village of Ektarpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000006/2021-2022 | 937/Hug | 06/05/2021 | 40 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 77.59 | 75.44 | 100
2829 | Hooghly Division | Chinsuria Sub-Division | Providing 310 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000357/2021-2022 | 118/Hug | 19/01/2022 | 20 | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.53 | 21.77 | 100
2830 | Hooghly Division | Chinsuria Sub-Division | Providing 780 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000440/2021-2022 | 458/Hug | 10/03/2022 | 40 | MAA TARA CONSTRUCTION | 52.71 | 44.22 | 100
2831 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000061/2021-2022 | 2097/1/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
2832 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001049/2021-2022 |  | 30/09/2021 | 0 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 27.03 | 0 | 0
2833 | Hooghly Division | Chinsuria Sub-Division | COLLECTION OF DATA FOR FHTC OF DIGSUI HEORA W/S/S | Assistant Engineer (Civil) |  | VCH/001325/2020-2021 |  | 08/12/2020 | 0 | R AND D TRADERS | 4.98 | 0 | 0
2834 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under PANDUA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000346/2023-2024 | 2429/HUG | 11/08/2023 | 30 | GHOSH CONSTRUCTION | 42.89 | 0 | 80
2835 | Hooghly Division | Chinsuria Sub-Division | Making Interconnection from newly bored tube well to existing Over Head Reservoir at Pandua under Pandua Zone-I Water Supply Scheme Under Chinsurah Subdivision under Hooghly division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000520/2023-2024 | 816/CH | 31/08/2023 | 15 | JOY GURU ENTERPRISE | 0.7 | 0.7 | 90
2836 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 79.33 | 50
2837 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2838 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | RTOR000086/2023-2024 | 1263/1/Hug | 03/05/2023 | 0 | Resource Division | 41.15 | 0 | 0
2839 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | RTOR000167/2023-2024 | 1385/38/Hug | 15/05/2023 | 0 | Resource Division | 12.02 | 0 | 0
2840 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | RTOR000385/2023-2024 | 3057/Hug | 11/10/2023 | 0 | Resource Division | 12.02 | 0 | 0
2841 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/sScheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical division,PHE Dte.(SM/13322). Application No-5004325249, Reference Id-503707789 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/01406/2024-2025 | 350 | 31/07/2024 | 0 | WBSEDCL | 7.6 | 0 | 0
2842 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-II,Ph No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13322) Application No-5004011194 Reference Id-503561404 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/06480/2023-2024 | 901 | 19/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
2843 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/000189/2022-2023 | 782/ED | 09/02/2023 | 90 | S.G. TECHNICAL SERVICES | 20.49 | 0 | 0
2844 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 230.57 | 30
2845 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 11.01 | 70
2846 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
2847 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000063/2023-2024 | 1234/30/Hug | 28/04/2023 | 0 | Resource Division | 25.45 | 0 | 0
2848 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000493/2023-2024 | 3057/60/Hug | 11/10/2023 | 0 | Resource Division | 13.4 | 0 | 0
2849 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Selampur w/s Scheme,Zone-II,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/14685) Application No-5004431262 Reference Id-503764740 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02058/2024-2025 | 537 | 28/10/2024 | 0 | WBSEDCL | 4.39 | 0 | 0
2850 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034192 Reference Id-503574969. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06201/2023-2024 | 810 | 28/02/2024 | 0 | WBSEDCL | 4.41 | 0 | 0
2851 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034199 Reference Id-503574970 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06202/2023-2024 | 809 | 28/02/2024 | 0 | WBSEDCL | 4.48 | 0 | 0
2852 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000140/2024-2025 | 1166/ED | 14/06/2024 | 474 | S.S. ENTERPRISES | 10.95 | 0 | 0
2853 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000181/2022-2023 | 774/ED | 09/02/2023 | 965 | S S ENTERPRISES | 22.09 | 17.9 | 10
2854 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00292/2023-2024 | BP-2023-24-243 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.46 | 0 | 0
2855 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
2856 | Hooghly Division | Chinsuria Sub-Division | Augmentation of HARIT Piped Water Supply Scheme with Sinking of Tube-Well, LDS, Rising Main, FHTC, construction of switch-rooms , boundary walls& Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site under POLBA-DADPUR Block, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000701/2022-2023 | 379/HUG | 09/02/2023 | 90 | DAS ENTERPRISE (SAMIR DAS) | 238.76 | 218.37 | 92
2857 | Hooghly Division | Chinsuria Sub-Division | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in HARIT GP of POLBA-DADPUR Block | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000924/2023-2024 | 244/CH | 12/03/2024 | 30 | BASU & SONS | 4.98 | 4.97 | 75
2858 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Kelor Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001042/2023-2024 | 284/CH | 14/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.97 | 100
2859 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Majher Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001043/2023-2024 | 287/CH | 15/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.98 | 85
2860 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Ichapur of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001044/2023-2024 | 288/CH | 15/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.82 | 0.79 | 95
2861 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000106/2023-2024 | 1264/1/HUG | 03/05/2023 | 0 | Resource Division | 39.48 | 0 | 0
2862 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000198/2022-2023 | 226/5/Hug | 24/01/2023 | 0 | Resource Division | 39.48 | 0 | 0
2863 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000276/2023-2024 | 1386/51/Hug | 15/05/2023 | 0 | Resource Division | 6.49 | 0 | 0
2864 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Harit water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000214/2022-2023 | 841/ED | 14/02/2023 | 90 | DEBJYOTI BASU | 21.49 | 10.41 | 50
2865 | Hooghly Division | Arambug Sub-Division | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000159/2023-2024 | 1602/HUG | 01/06/2023 | 1035 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 311.49 | 65
2866 | Hooghly Division | Arambug Sub-Division | Horizontal Auger boring with water jet system Including Approach Road at GOBINDANAGAR ZONE-I, KUMURSA, KOTA, RAGHUBATI & SUNIA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000693/2023-2024 | 3592/HUG | 05/12/2023 | 30 | P. B. ENTERPRISE(PINTU BHADURI) | 7.29 | 7.05 | 100
2867 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000050/2023-2024 | 1234/22/Hug | 28/04/2023 | 0 | Resource Division | 9.97 | 0 | 0
2868 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000169/2023-2024 | 1385/40/Hug | 15/05/2023 | 0 | Resource Division | 11.06 | 0 | 0
2869 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000430/2023-2024 | 3057/35/Hug | 11/10/2023 | 0 | Resource Division | 11.06 | 0 | 0
2870 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gobindanagar W/S. Sch. Z-I, PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04149/2023-2024 | 393 | 03/11/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
2871 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-I,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/15247) Application No-5004049800, Reference Id-503584072 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06239/2023-2024 | 839 | 01/03/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
2872 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000280/2022-2023 | 930/ED | 22/02/2023 | 90 | T S CONSTRUCTION | 20.5 | 19.86 | 25
2873 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000879/2023-2024 | 3452/ED | 11/08/2023 | 90 | PERFECT AIRCONDITION | 20.49 | 0 | 0
2874 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0
2875 | Hooghly Division | Arambug Sub-Division | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 286.56 | 30
2876 | Hooghly Division | Arambug Sub-Division | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 0 | 70
2877 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0
2878 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000062/2023-2024 | 1234/29/Hug | 28/04/2023 | 0 | Resource Division | 40.15 | 0 | 0
2879 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000405/2023-2024 | 3057/48/Hug | 11/10/2023 | 0 | Resource Division | 14.49 | 0 | 0
2880 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I, PH No-I Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004151889 Reference Id-503633694 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00412/2024-2025 | 95 | 06/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
2881 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I,PH No-II,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004294581 Reference Id-503691996 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01172/2024-2025 | 312 | 22/07/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
2882 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000139/2024-2025 | 1165/ED | 14/06/2024 | 90 | ANUPAMA ENGINEERING WORKS | 10.75 | 0 | 0
2883 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000281/2022-2023 | 931/ED | 22/02/2023 | 769 | GHOSE ENGINEERING SYNDICATE | 22.1 | 0.46 | 30
2884 | Hooghly Division | Arambug Sub-Division | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000164/2023-2024 | 1618/Hug | 02/06/2023 | 270 | M/S RAJKUMAR KHAN | 246.71 | 13.25 | 15
2885 | Hooghly Division | Arambug Sub-Division | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000179/2023-2024 | 1618/hug | 02/06/2023 | 270 | M/S RAJKUMAR KHAN | 246.71 | 56.24 | 20
2886 | Hooghly Division | Arambug Sub-Division | Laying of Additional Pipeline for MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block Arambagh. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000230/2024-2025 | 3439/HUG | 03/10/2024 | 30 | DILIP KUMAR GHOSH | 54.57 | 0 | 0
2887 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0
2888 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000041/2023-2024 | 1234/14/Hug | 28/04/2023 | 0 | Resource Division | 25.34 | 0 | 0
2889 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000186/2023-2024 | 1385/57/Hug | 15/05/2023 | 0 | Resource Division | 2.68 | 0 | 0
2890 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000472/2023-2024 | 3057/12/Hug | 11/10/2023 | 0 | Resource Division | 6.12 | 0 | 0
2891 | Electrical | Arambug Sub-Division | Quotation for New Service Connection at Mayapur W/S. Sch. Z=II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04611/2023-2024 | 610 | 04/01/2024 | 0 | WBSEDCL | 6.44 | 0 | 0
2892 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000025/2023-2024 | 1702/ED | 18/04/2023 | 90 | NUPUR CHANDRA HALDER | 20.8 | 0 | 0
2893 | Hooghly Division | Chandannagar Sub-Division | SIBRAMBATI ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000277/2023-2024 | 2296/HUG | 03/08/2023 | 270 | M/S BISWAS CONSTRUCTION | 551.83 | 139.35 | 40
2894 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Shibrambati (Zone-1) 1st T/W site & Shibrambati (Zone-1) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000287/2024-2025 | 926/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
2895 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach Road at SIBRAMBATI ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000590/2023-2024 | 3232/HUG | 03/11/2023 | 30 | M/S BISWAS CONSTRUCTION | 20.63 | 20.63 | 100
2896 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000792/2023-2024 | 152/Chan | 16/02/2024 | 15 | TECHVISION | 0.84 | 0.84 | 98
2897 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000794/2023-2024 | 153/Chan | 16/02/2024 | 15 | TECHVISION | 0.73 | 0.73 | 98
2898 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000797/2023-2024 | 154/Chan | 16/02/2024 | 15 | TECHVISION | 0.96 | 0.96 | 98
2899 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-D). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000798/2023-2024 | 155/Chan | 16/02/2024 | 15 | TECHVISION | 0.78 | 0.78 | 98
2900 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000057/2023-2024 | 1235/6/Hug | 28/04/2023 | 0 | Resource Division | 36.75 | 0 | 0
2901 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000269/2022-2023 | 902/6/Hug | 27/03/2023 | 0 | Resource Division | 7.76 | 0 | 0
2902 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000427/2023-2024 | 3058/20/Hug | 11/10/2023 | 0 | Resource Division | 15.5 | 0 | 0
2903 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati water supply Scheme [SM/15889],Zone - I, T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503588850, Dt. - 11-03-2024, Application No. - 5004057590 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06274/2023-2024 | 882 | 13/03/2024 | 0 | WBSEDCL | 5.7 | 0 | 0
2904 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati W/S Sch., (Zone - I), T/W No. - II,[SM/15889] Block - Singur under Singur CCC, WBSEDCL, Ref. Id. - 503591781, Dt. - 12-03-2024, Application No. - 5004061900 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06469/2023-2024 | 893 | 18/03/2024 | 0 | WBSEDCL | 6.69 | 0 | 0
2905 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sibrambati water supply scheme, Zone-I, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001359/2023-2024 | 4695/ED | 08/12/2023 | 540 | A.K. ENTERPRISE | 22.43 | 16.25 | 70
2906 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000128/2023-2024 | 1471/HUG | 19/05/2023 | 30 | S.B. ASSOCIATES | 11.81 | 0 | 0
2907 | Hooghly Division | Arambug Sub-Division | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PRATAPNAGAR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000502/2023-2024 | 2862/HUG | 20/09/2023 | 360 | B.R SUPPLIERS | 22.63 | 11.04 | 60
2908 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000095/2023-2024 | 1263/10/Hug | 03/05/2023 | 0 | Resource Division | 11.38 | 0 | 0
2909 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000247/2022-2023 | 127/19/Hug | 13/01/2023 | 0 | Resource Division | 11.5 | 0 | 0
2910 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pratapnagar w/s Scheme,PH No-3, Block-Arambag, Dist-Hooghly under Electrical division,PHE Dte.(SM/15807) Application No-5004254598 Reference Id-503673919 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00850/2024-2025 | 248 | 24/06/2024 | 0 | WBSEDCL | 7.9 | 0 | 0
2911 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Pratapnagar water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000021/2023-2024 | 1698/ED | 18/04/2023 | 989 | GOENKA ENTERPRISE | 20.5 | 15.17 | 10
2912 | Hooghly Division | Chinsuria Sub-Division | Laying of HDPE Pipe by HDD Process from Spandan Electronics at Magra Ganj towards Natungram Shib Manidr via Rathtala Suriya Sangha Club at Mogra-Gurap (23 No.) Road within KOLA PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000038/2023-2024 | 1161/HUG | 20/04/2023 | 45 | MAA TARA CONSTRUCTION | 96.46 | 76.91 | 50
2913 | Hooghly Division | Arambug Sub-Division | ARUNDA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000269/2023-2024 | 2280/HUG | 03/08/2023 | 270 | M/S. NANDY ENTERPRISE | 501.51 | 0 | 25
2914 | Hooghly Division | Arambug Sub-Division | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000849/2023-2024 | 726/HUG | 05/03/2024 | 366 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 9.57 | 75
2915 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)- 1 no?s (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no?s (3) ARUNDA PWSS (Z-I)- 4 no?s (4) ARUNDA PWSS (Z-II)- 5 no?s (5) POL PWSS ? 2no?s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002744/2024-2025 | 1152/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
2916 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000066/2023-2024 | 1234/33/Hug | 28/04/2023 | 0 | Resource Division | 25.46 | 0 | 0
2917 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000132/2023-2024 | 1385/3/Hug | 15/05/2023 | 0 | Resource Division | 12.79 | 0 | 0
2918 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000387/2023-2024 | 3057/58/Hug | 11/10/2023 | 0 | Resource Division | 11.7 | 0 | 0
2919 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-III Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460458 Reference Id-503787369 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02276/2024-2025 | BP-24-25-579 | 19/11/2024 | 0 | WBSEDCL | 4.06 | 0 | 0
2920 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460466 Reference Id-503787366 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02592/2024-2025 | 628 | 18/12/2024 | 0 | WBSEDCL | 5.68 | 0 | 0
2921 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000151/2024-2025 | 1174/ED | 14/06/2024 | 90 | BARISAL TRADING CO. | 10.74 | 0 | 0
2922 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000152/2024-2025 | 1175/ED | 14/06/2024 | 90 | S.M. ELECTRICALS | 10.74 | 0 | 0
2923 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0
2924 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-II) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001143/2022-2023 | 1495/ED | 28/03/2023 | 90 | BARISAL TRADING CO. | 21.49 | 0 | 0
2925 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000001/2024-2025 | 412/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.73 | 0.73 | 100
2926 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2024-2025 | 413/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100
2927 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000003/2024-2025 | 414/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100
2928 | Hooghly Division | Chandannagar Sub-Division | BHANDARDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000094/2023-2024 | 1518/HUG | 23/05/2023 | 90 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 91.84 | 89.89 | 100
2929 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000392/2023-2024 | 3058/10/Hug | 11/10/2023 | 0 | Resource Division | 22.67 | 0 | 0
2930 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bhandardaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04169/2023-2024 | 408 | 09/11/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
2931 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000004/2024-2025 | 416/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.93 | 0.93 | 100
2932 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000005/2024-2025 | 417/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100
2933 | Hooghly Division | Chandannagar Sub-Division | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000006/2024-2025 | 419/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100
2934 | Hooghly Division | Chandannagar Sub-Division | KALACHHARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000132/2023-2024 | 1484/HUG | 19/05/2023 | 425 | CONCORD PROJECTS PRIVATE LIMITED | 82.76 | 79.78 | 15
2935 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Rajballavbati PWSS, Kalachara PWSS, Paschim Narayanpur PWSS, Mahistikari Z-I PWSS, Mahistikari Z-II PWSS, Parjana PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000977/2023-2024 | 305/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
2936 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000205/2023-2024 | 1383/8/Hug | 15/05/2023 | 0 | Resource Division | 1.8 | 0 | 0
2937 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection at Kalachara W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04668/2023-2024 | 649 | 10/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0
2938 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalachhara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000070/2023-2024 | 1926/ED | 15/05/2023 | 90 | S.G. TECHNICAL SERVICES | 22.6 | 10.77 | 25
2939 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
2940 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) |  | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 16.41 | 100
2941 | Hooghly Division | Chandannagar Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NAWPARA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000236/2024-2025 | 3471/HUG | 04/10/2024 | 454 | DIPTI TRADERS | 26.55 | 0 | 60
2942 | Hooghly Division | Chandannagar Sub-Division | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NAWPARA Water Supply Scheme at SINGUR Block under Chandannagar Sub- Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000274/2023-2024 | 2294/HUG | 03/08/2023 | 785 | DIPTI TRADERS | 757.77 | 598.38 | 87
2943 | Hooghly Division | Chandannagar Sub-Division | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 12.32 | 100
2944 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000194/2022-2023 | 109/4/Hug | 10/01/2023 | 0 | Resource Division | 52 | 0 | 0
2945 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000390/2023-2024 | 3058/6/Hug | 11/10/2023 | 0 | Resource Division | 17.71 | 0 | 0
2946 | Electrical | Chandannagar Sub-Division | Quotation for service connection for Nawpara W/S Sch. , T/W -I, Block - Singur | Assistant Engineer (Civil) |  | BILL/02064/2023-2024 | 111 | 19/07/2023 | 0 | WBSEDCL | 2.63 | 0 | 0
2947 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Nawpara W/S. Sch. TW-II | Assistant Engineer (Civil) |  | BILL/04503/2023-2024 | 547 | 19/12/2023 | 0 | WBSEDCL | 15.9 | 0 | 0
2948 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawpara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000810/2023-2024 | 3063/ED | 12/07/2023 | 90 | POLYCON ENGINEERS | 21.71 | 21.69 | 92
2949 | Hooghly Division | Chandannagar Sub-Division | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2023-2024 | 1041/Hug | 10/04/2023 | 792 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 429.8 | 60
2950 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte. (Baichipota Z-I PWSS, Baichipota Z-II PWSS, Kharda Apurbapur PWSS, Baruipara PWSS, Sripatipur PWSS, Paschim Gopinathpur PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000976/2023-2024 | 304/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
2951 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000060/2023-2024 | 1235/9/Hug | 28/04/2023 | 0 | Resource Division | 13.03 | 0 | 0
2952 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000264/2022-2023 | 902/2/Hug | 27/03/2023 | 0 | Resource Division | 10.56 | 0 | 0
2953 | Electrical | Chandannagar Sub-Division | Additional Quotation for new service connection at Bainchipota[SM/17289] W/S Sch., Zone - I, T/W No. - II under Nasibpur CCC, WBSEDCL, Ref. Id. - 860298080, Dt. - 23/04/2024, Application ID. - 100000106100 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00330/2024-2025 | 98 | 06/05/2024 | 0 | WBSEDCL | 0.25 | 0 | 0
2954 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Boinchipota W/s sch. , T/W - I, Block- Singur, Dist. -hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02062/2023-2024 | 110 | 19/07/2023 | 0 | WBSEDCL | 3.99 | 0 | 0
2955 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Boinchipota W/S Sch,, Zone - I. T/W No. - II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04125/2023-2024 | 382 | 25/10/2023 | 0 | WBSEDCL | 2.44 | 0 | 0
2956 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000053/2023-2024 | 1797/ED | 24/04/2023 | 360 | MITRA ASSOCIATES | 20.2 | 19.88 | 97
2957 | Hooghly Division |  | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at MAHISHGOT ZONE I (2Nos.), UDAYPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000227/2024-2025 | 3437/HUG | 03/10/2024 | 90 | SAHA CONSTRUCTION AND CO | 47.26 | 0 | 0
2958 | Hooghly Division |  | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte |  |  | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 359.39 | 45
2959 | Hooghly Division |  | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
2960 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000441/2023-2024 | 3057/29/Hug | 11/10/2023 | 0 | Resource Division | 16.38 | 0 | 0
2961 | Electrical |  | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - I |  |  | BILL/04366/2023-2024 | 457 | 01/12/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
2962 | Electrical |  | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - II |  |  | BILL/04367/2023-2024 | 458 | 01/12/2023 | 0 | WBSEDCL | 6.15 | 0 | 0
2963 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall & Pathway Development of Rajhat(Z-I) at H/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000122/2022-2023 | 462/CH | 31/05/2022 | 40 | S. G. ENTERPRISE | 3.36 | 0 | 0
2964 | Hooghly Division | Chinsuria Sub-Division | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000207/2021-2022 | 1676/Hug | 13/09/2021 | 40 | M/S BUILDWELL | 59.06 | 27.65 | 0
2965 | Hooghly Division | Chinsuria Sub-Division | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat Zone-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000291/2021-2022 | 2202/Hug | 14/12/2021 | 20 | GHOSH CONSTRUCTION | 13.02 | 13.02 | 0
2966 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under POLBA-DADPUR Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000341/2023-2024 | 2431/HUG | 11/08/2023 | 30 | DILIP KUMAR GHOSH | 42.76 | 41.91 | 95
2967 | Hooghly Division | Chinsuria Sub-Division | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & HARAL ZONE-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000438/2021-2022 | 456/Hug | 10/03/2022 | 30 | M/S S.C CIVIL ENTERPRISE | 31.96 | 31.4 | 0
2968 | Hooghly Division | Chinsuria Sub-Division | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000546/2021-2022 | 1676/HUG | 13/09/2021 | 40 | M/S BUILDWELL | 59.06 | 31.4 | 100
2969 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of RAJHAT Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000889/2022-2023 | 1509/Hug | 22/07/2022 | 20 | GHOSH CONSTRUCTION | 20.38 | 19.74 | 100
2970 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS. DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-I) POLBA DADPUR BLOCK HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000001/2022-2023 | 301/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 5.74 | 0
2971 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2022-2023 | 89/CMSD-I (D) | 19/04/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.99 | 0
2972 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2022-2023 | 90/ CMSD-I (D) | 19/04/2022 | 15 | C.M. ENTERPRISE | 5 | 4.07 | 0
2973 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELLIN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000005/2022-2023 | 88/CMSD-I (D) | 18/04/2022 | 15 | C.M. ENTERPRISE | 5 | 4.69 | 0
2974 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000006/2022-2023 | 87/CMSD-I (D) | 18/04/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.55 | 0
2975 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCH (Z-II), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000009/2022-2023 | 303/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 3.45 | 0
2976 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-II) POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000022/2022-2023 | 303/ CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 2.21 | 0
2977 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I), POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000149/2022-2023 | 138/S&WSD | 12/08/2022 | 15 | TAMAL ENTERPRISE | 5 | 4.55 | 0
2978 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000150/2022-2023 | 139/S&WSD | 12/08/2022 | 15 | DEY ENTERPRISE | 4.99 | 2.83 | 0
2979 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000151/2022-2023 | 137/S&WSD | 12/08/2022 | 15 | TAMAL ENTERPRISE | 3.92 | 3.74 | 0
2980 | Central Drilling | Chinsuria Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000173/2022-2023 | 483/CMSD-I | 23/09/2022 | 10 | SUJATA BHOWMICK | 0.86 | 1.69 | 0
2981 | Central Drilling | Chinsuria Sub-Division | PROCVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000204/2022-2023 | 142/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 5 | 4.78 | 0
2982 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLT DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000205/2022-2023 | 141/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 4.98 | 3.69 | 0
2983 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000206/2022-2023 | 140/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 3.91 | 3.8 | 0
2984 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, (300MM DIA) CONFORMING TO IS: 12818:2010 AND OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2022-2023 | 476/CMSD-II | 11/10/2022 | 7 | TAMAL ENTERPRISE | 0.53 | 0.51 | 0
2985 | Central Drilling | Chinsuria Sub-Division | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.29 | 0
2986 | Central Drilling | Chinsuria Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2022-2023 | 483/CMSD-I (RA-VI & F) | 23/09/2022 | 15 | SUJATA BHOWMICK | 0.39 | 0.39 | 0
2987 | Hooghly Division |  | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under BALAGARH Block of Chinsurah Sub Division under Hooghly Division PHE Dte. |  |  | ORD/000268/2024-2025 | 927/CH | 05/11/2024 | 5 | MAA BUNAMATA ENTERPRISE | 3.7 | 0.98 | 90
2988 | Hooghly Division |  | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir, Switch Room & Boundary wall of SRIPUR BALAGARH Water Supply Scheme under Chinsurah Sub - Division, P.H.E. Dte., Hooghly |  |  | ORD/000309/2024-2025 | 3678/HUG | 13/11/2024 | 160 | DIPTI TRADERS | 29.54 | 0 | 100
2989 | Hooghly Division |  | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000576/2023-2024 | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0
2990 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000610/2023-2024 | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 14.86 | 60
2991 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001205/2023-2024 | 4483/ED | 23/11/2023 | 90 | M/S A.K BANERJEE | 21.49 | 0 | 0
2992 | Hooghly Division |  | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for AUGMENTATION Of BALIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000125/2025-2026 | 1479/HUG | 10/06/2025 | 45 | TANISA ENTERPRISE | 26.56 | 0 | 0
2993 | Hooghly Division |  | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of BALIPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000126/2025-2026 | 1480/HUG | 10/06/2025 | 60 | DAS ENTERPRISE (SAMIR DAS) | 52.97 | 0 | 0
2994 | Hooghly Division |  | Sinking of Tube-Well, Laying Distribution System, Laying Rising Main, Providing FHTC, Construction of Switch-Rooms & Boundary Walls at different TW site For Augmentation of BALIPUR ZONE-I(B) under Arambagh SubDivision of Hooghly Division P.H.E Dte. Block- Khanakul-I, District:- Hooghly |  |  | ORD/000388/2023-2024 | 2591/HUG | 28/08/2023 | 90 | M/S R.M. CONSTRUCTION | 308.46 | 148.3 | 45
2995 | Hooghly Division |  | Augmentation of BALIPUR ZONE-II Piped Water Supply Scheme with LDS, FHTC, Repairing of Switch Rooms, Boundary walls at different TW site, under Hooghly Division P.H.E Dte.Block- KHANAKUL-I , District:- Hooghly |  |  | ORD/000390/2023-2024 | 2597/HUG | 29/08/2023 | 630 | DHIRENDRA ENGINEERING & CONSTRUCTION | 172.47 | 133.75 | 75
2996 | Hooghly Division |  | Augmentation of BALIPUR ZONE-I(A) Piped Water Supply Scheme with LDS, FHTC, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, under KHANAKUL-I Block, District:- Hooghly. |  |  | ORD/000393/2023-2024 | 2600/HUG | 29/08/2023 | 90 | M/S R K ENTERPRISE | 267.18 | 101.47 | 55
2997 | Hooghly Division |  | Sinking of 1 No. Replacement tube-well at Balipur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000701/2025-2026 | 2309/HUG | 02/09/2025 | 30 | OSMAN SEKH | 15.48 | 0 | 0
2998 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000181/2022-2023 | 79/17/Hug | 06/01/2023 | 0 | Resource Division | 56.05 | 0 | 0
2999 | Electrical |  | Quotation of New Service Connection for Balipur w/s Scheme, Zone-I,TW No-III Block-Khanakul-I,Dist-Hooghly under Electrical Division PHE Dte. |  |  | BILL/03702/2023-2024 | 232 | 01/09/2023 | 0 | WBSEDCL | 3.1 | 0 | 0
3000 | Electrical |  | Quotation of New Service Connection for Balipur w/s scheme,zone-I,TW no-3, Block-khanakul-I,Dist-Hooghly under Electrical Division PHE Dte |  |  | BILL/03885/2023-2024 | 297 | 21/09/2023 | 0 | WBSEDCL | 10.61 | 0 | 0
3001 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Balipur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000934/2023-2024 | 3613/ED | 29/08/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.72 | 18.17 | 30
3002 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
3003 | Hooghly Division | Arambug Sub-Division | PURBBA KRISHNAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION, Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000177/2023-2024 | 1682/HUG | 08/06/2023 | 270 | M/S R K ENTERPRISE | 442.41 | 71.31 | 10
3004 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000048/2023-2024 | 1234/20/Hug | 28/04/2023 | 0 | Resource Division | 40.63 | 0 | 0
3005 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000164/2023-2024 | 1385/35/Hug | 15/05/2023 | 0 | Resource Division | 8.34 | 0 | 0
3006 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000437/2023-2024 | 3057/31/Hug | 11/10/2023 | 0 | Resource Division | 8.34 | 0 | 0
3007 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-II,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208366 Reference Id-503655425. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00671/2024-2025 | 203 | 10/06/2024 | 0 | WBSEDCL | 3.71 | 0 | 0
3008 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-I,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208398 Reference Id-503655423. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00672/2024-2025 | 202 | 10/06/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
3009 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purbba Krishnapur water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000044/2023-2024 | 1730/ED | 19/04/2023 | 804 | CINZANO | 20.96 | 0 | 50
3010 | Hooghly Division | Chandannagar Sub-Division | NASIBPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000174/2023-2024 | 1679/HUG | 08/06/2023 | 938 | BAPPADITYA BANERJEE | 499.98 | 218.29 | 60
3011 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 15.95 | 100
3012 | Hooghly Division | Chandannagar Sub-Division | Horizontal road crossing by trenchless method along CN Road(PWD) for NASIBPUR pwss under Chandannagar Sub Division,Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000241/2024-2025 | 3476/HUG | 04/10/2024 | 335 | BAPPADITYA BANERJEE | 56.52 | 0 | 80
3013 | Hooghly Division | Chandannagar Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of NASIBPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000745/2023-2024 | 384/HUG | 08/02/2024 | 60 | M/S ALPHA CONSTRUCTION | 15.5 | 13.39 | 100
3014 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Nasibpur PWSS, Bhandardaha PWSS, Ganderpukur PWSS, Bighati zone-I PWSS, Gopalnagar PWSS, Bahirkhanda PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000971/2023-2024 | 300/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
3015 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000042/2023-2024 | 1235/2/Hug | 28/04/2023 | 0 | Resource Division | 69.72 | 0 | 0
3016 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000268/2022-2023 | 902/5/Hug | 27/03/2023 | 0 | Resource Division | 15.17 | 0 | 0
3017 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000275/2023-2024 | 1383/26/Hug | 15/05/2023 | 0 | Resource Division | 15.17 | 0 | 0
3018 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000431/2023-2024 | 3058/13/Hug | 11/10/2023 | 0 | Resource Division | 15.17 | 0 | 0
3019 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nasibpur W/s Sch.,H/W Site(T/W No. - I), Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01922/2023-2024 | 89 | 12/07/2023 | 0 | WBSEDCL | 3.56 | 0 | 0
3020 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Nasibpur PWSS, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04482/2023-2024 | 527 | 14/12/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
3021 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nasibpur water supply Scheme [SM/17627], T/W No. - III, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. Id. - 503584530, Dt. - 07-03-2024, Application No. - 5004050532 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06277/2023-2024 | 872 | 13/03/2024 | 0 | WBSEDCL | 2.63 | 0 | 0
3022 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000043/2023-2024 | 1729/ED | 19/04/2023 | 90 | ANIK & CO. | 20.5 | 9.97 | 45
3023 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002477/2023-2024 | 337/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 10.35 | 100
3024 | Hooghly Division |  | Balance LDS and other allied works within left out habitation of various Mouzas in Borhal (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000785/2023-2024 | 532/HUG | 20/02/2024 | 15 | MA CONSTRUCTION | 16.06 | 16.06 | 80
3025 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kumarbazar village under Antpur PWSS (2 nos.) 2. Paschim Durgapur village under Borhal PWSS (2 nos.) 3. Ilampur village under Borhal PWSS (2 nos.) |  |  | ORD/000960/2023-2024 | 172/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 80
3026 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Dakshin Dilakash village under Borhal PWSS (2 nos.) 2. Mandaran Dilakash village under Borhal PWSS (2 nos.) 3. Khurigachhi village under Borhal PWSS (2 nos.) |  |  | ORD/000962/2023-2024 | 173/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 80
3027 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kulakash village under Borhal PWSS (2 nos.) 2. Kandar Panagar village under Borhal PWSS (2 nos.) 3. Paschim Gobindapur village under Borhal PWSS (2 nos.) |  |  | ORD/000963/2023-2024 | 174/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 80
3028 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Nikash village under Borhal PWSS (2 nos.) 2. Borhal under Borhal PWSS (2 nos.) 3. Satghara village under Borhal PWSS (2 nos.) |  |  | ORD/000964/2023-2024 | 175/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 80
3029 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mathurabati village under Borhal PWSS (2 nos.) 2. Masinan village under Radhanagar PWSS (2 nos.) 3. Kuliara village under Morhal PWSS (2 nos.) |  |  | ORD/000965/2023-2024 | 176/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 80
3030 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 45
3031 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 40
3032 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Abdulpur PWSS 2. Bhabanipur PWSS 3. Dumurdaha PWSS 4. Guptipara PWSS 5. Itagarh PWSS 6. Kamarpara PWSS |  |  | ORD/000818/2023-2024 | 196/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3033 | Hooghly Division |  | Inter connection work of Rising main from newly bored 2nd Tube Well to OHR of Abdulpur W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000880/2023-2024 | 214/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.87 | 0.86 | 50
3034 | Hooghly Division |  | Repairing & Renovation of Boundary Wall, Switch Room and Land Development at PH-II Site of Abdulpur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002014/2024-2025 | 302/CH | 20/02/2025 | 10 | M/S. R. M. CONSTRUCTION | 3.48 | 0 | 0
3035 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001255/2023-2024 | 4503/ED | 23/11/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.72 | 0 | 0
3036 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000578/2023-2024 | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 60
3037 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001861/2024-2025 | 241/CH | 19/02/2025 | 10 | M/S SHIVAM UDYOG | 4.84 | 0 | 0
3038 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001883/2024-2025 | 245/CH | 19/02/2025 | 10 | M/S SHIVAM UDYOG | 2.62 | 0 | 0
3039 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001913/2024-2025 | 264/CH | 20/02/2025 | 10 | M/S SHIVAM UDYOG | 4.49 | 0 | 0
3040 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001922/2024-2025 | 272/CH | 20/02/2025 | 10 | M/S SHIVAM UDYOG | 3.18 | 0 | 0
3041 | Electrical |  | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- II in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503697548, Application no- 5004304981 |  |  | BILL/01373/2024-2025 | 337 | 30/07/2024 | 0 | WBSEDCL | 3.93 | 0 | 0
3042 | Electrical |  | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- I in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503705756, Application no- 5004321019 |  |  | BILL/01632/2024-2025 | 374 | 12/08/2024 | 0 | WBSEDCL | 23.02 | 0 | 0
3043 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001211/2023-2024 | 4489/ED | 23/11/2023 | 495 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.49 | 0 | 80
3044 | Hooghly Division |  | Repair and Renovation Works of R.C.C. Elevated Reservoir , Bounary Wall of DIHIBAYRA PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000383/2024-2025 | 3777/HUG | 25/11/2024 | 40 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 12.75 | 0 | 0
3045 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos |  |  | ORD/002647/2024-2025 | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
3046 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Dihibayra w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001527/2021-2022 | 544/HMSD | 17/03/2022 | 30 | WIZARDTECH SOLUTION | 2.36 | 2.36 | 100
3047 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibayra water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001532/2021-2022 | 471_ED | 10/03/2022 | 90 | T S CONSTRUCTION | 6.4 | 6.4 | 50
3048 | Hooghly Division |  | Laying HDPE Pipeline From existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000033/2024-2025 | 535/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.83 | 4.82 | 80
3049 | Hooghly Division |  | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000042/2024-2025 | 544/CH | 18/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.43 | 4.43 | 80
3050 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 80
3051 | Hooghly Division |  | Inter connection work of Rising main from newly bored Tube Well to existing Distribution Main of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000689/2023-2024 | 1111/CH | 15/12/2023 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.89 | 100
3052 | Hooghly Division |  | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000690/2023-2024 | 1112/CH | 15/12/2023 | 10 | MAA BUNAMATA ENTERPRISE | 0.94 | 0.94 | 100
3053 | Hooghly Division |  | Carriage for Chlorine From Polba Store to different Pump Houses at Pandua & Balagarh Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000691/2023-2024 | 1113/CH | 15/12/2023 | 7 | MAA BUNAMATA ENTERPRISE | 0.53 | 0.53 | 100
3054 | Hooghly Division |  | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000734/2023-2024 | 26/CH | 05/01/2024 | 15 | MAA BUNAMATA ENTERPRISE | 1.93 | 1.93 | 60
3055 | Hooghly Division |  | Providing FHTC at the left out portions of Ramnagar of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/001032/2023-2024 | 275/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 80
3056 | Hooghly Division |  | Providing FHTC at the left out portions of Nayasarai of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/001033/2023-2024 | 276/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 80
3057 | Electrical |  | Quotation for new service connection for source Augmentation of DUMURDHA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18942), Reference Id- 503718763 Application no- 5004350181 |  |  | BILL/01798/2024-2025 | 425 | 01/10/2024 | 0 | WBSEDCL | 8.83 | 0 | 0
3058 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001261/2023-2024 | 4506/ED | 23/11/2023 | 495 | INDTECH ASSOCIATES. | 10.76 | 0 | 80
3059 | Hooghly Division | Arambug Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for GHOLDIGRUI ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000291/2024-2025 | 3670/HUG | 13/11/2024 | 414 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 26.4 | 0 | 0
3060 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000810/2023-2024 | 591/HUG | 22/02/2024 | 679 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.57 | 13.75 | 70
3061 | Hooghly Division | Arambug Sub-Division | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000885/2023-2024 | 809/HUG | 11/03/2024 | 661 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.59 | 13.44 | 70
3062 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000089/2023-2024 | 1263/4/Hug | 03/05/2023 | 0 | Resource Division | 13.62 | 0 | 0
3063 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000229/2022-2023 | 127/09/Hug | 13/01/2023 | 0 | Resource Division | 22.34 | 0 | 0
3064 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000467/2023-2024 | 3057/17/Hug | 11/10/2023 | 0 | Resource Division | 15.63 | 0 | 0
3065 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gholdhuguri W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02139/2023-2024 | 123 | 20/07/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
3066 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Gholedigrui w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004475357 Reference ID- 503799179 SM Code- 13334 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02304/2024-2025 | BP-24-25-596 | 21/11/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
3067 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Zone-I PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02733/2023-2024 | 171 | 10/08/2023 | 0 | WBSEDCL | 5.99 | 0 | 0
3068 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000186/2022-2023 | 779/ED | 09/02/2023 | 90 | TRIO CONCERN | 22.03 | 22 | 75
3069 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002467/2023-2024 | 328/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
3070 | Hooghly Division | Arambug Sub-Division | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 152 Nos FHTC out of 304 Nos FHTC within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 707651.50(50% of Rs. 1415303.00) | Assistant Engineer | Junior Engineer (Civill) | ORD/000243/2021-2022 | 1965/Hug | 02/11/2021 | 30 | GHOSH ENTERPRISE | 11.32 | 5.43 | 0
3071 | Hooghly Division | Arambug Sub-Division | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of PROTAPNAGAR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000341/2021-2022 | 18/Hug | 04/01/2022 | 30 | SURAJIT SINGHA RAY | 12.56 | 12.21 | 0
3072 | Hooghly Division | Arambug Sub-Division | Providing FHTC for Pratapnagar PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000503/2021-2022 | 525/Arg. | 30/11/2021 | 45 | BENGAL TRADERS | 4.84 | 4.84 | 0
3073 | Hooghly Division | Arambug Sub-Division | Providing 304 nos FHTC for Pratapnagar PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000509/2021-2022 | 1998/Hug. | 12/11/2021 | 35 | MESSRS FREEDOM CONSTRUCTION | 5.58 | 5.58 | 0
3074 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000123/2021-2022 | 2196/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0
3075 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000006/2021-2022 |  | 12/04/2021 | 0 | MONDAL PRECESSION PVT LTD. | 22.48 | 0 | 0
3076 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001091/2021-2022 |  | 05/10/2021 | 0 | MONDAL PRECESSION PVT LTD. | 40.25 | 0 | 0
3077 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002100/2021-2022 |  | 28/01/2022 | 0 | MESSRS. FREEDOM CONSTRUCTION | 5.58 | 0 | 0
3078 | Hooghly Division |  | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] |  |  | ORD/000268/2020-2021 | 262/Hug | 03/02/2021 | 20 | K JAGADHATRY & CO | 13.62 | 3.85 | 0
3079 | Hooghly Division |  | Providing 200 nos F.H.T.C. in Patna Bhairabpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] |  |  | ORD/000269/2020-2021 | 263/Hug | 03/02/2021 | 20 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 14.3 | 11.55 | 85
3080 | Hooghly Division |  | FHTC |  |  | VCH/000588/2021-2022 |  | 16/08/2021 | 0 | PRADIP KUMAR ADHYA | 59.27 | 0 | 0
3081 | Hooghly Division |  | FHTC |  |  | VCH/000934/2021-2022 |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 4.01 | 0 | 0
3082 | Hooghly Division |  | FHTC |  |  | VCH/000936/2021-2022 |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 4.01 | 0 | 0
3083 | Hooghly Division |  | FHTC |  |  | VCH/000938/2021-2022 |  | 24/09/2021 | 0 | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.55 | 0 | 0
3084 | Hooghly Division |  | FHTC |  |  | VCH/001050/2021-2022 |  | 30/09/2021 | 0 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 4.5 | 0 | 0
3085 | Hooghly Division |  | FHTC |  |  | VCH/001925/2020-2021 |  | 15/02/2021 | 0 | ASHOK GHOSH & BROTHERS | 20 | 0 | 0
3086 | Hooghly Division | Chandannagar Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PASCHIM JAYKRISHNAPUR Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000131/2023-2024 | 1474/HUG | 19/05/2023 | 30 | S.B. ENTERPRISE | 11.8 | 9.82 | 80
3087 | Hooghly Division | Chandannagar Sub-Division | Repairing of boundary wall at 2nd site of Paschim Joykrishnapur zone 1 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000309/2025-2026 | 942/CHAN | 21/07/2025 | 20 | MAHAMAYA CONSTRUCTION | 2.08 | 0 | 0
3088 | Hooghly Division | Chandannagar Sub-Division | Providing1527 nos F.H.T.C. in Chaitanyapur, Chak Ananta,Kulubati Bhagabatipur & Radha Krishnapur Village of Paschim Joykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000567/2021-2022 | 944/HUG | 06/05/2021 | 40 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.35 | 13.56 | 100
3089 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Gouribati 3rd T/W site & Paschim Joykrishnapur (Zone-1) 3rd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000935/2023-2024 | 280/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100
3090 | Hooghly Division | Chandannagar Sub-Division | Reparing of Damage Pipeline at Paschim Jaykrishnapur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000951/2023-2024 | 289/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.57 | 0.57 | 100
3091 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Paschim Jaykrishnapur PWSS, Kaikala PWSS, Bandipur PWSS, Bamonjol PWSS, Binagram PWSS, Rambati PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000979/2023-2024 | 307/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
3092 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001044/2021-2022 |  | 30/09/2021 | 0 | UNIQUE AGENCY | 41.52 | 0 | 0
3093 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001053/2021-2022 |  | 30/09/2021 | 0 | UNIQUE AGENCY | 43.59 | 0 | 0
3094 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001102/2021-2022 |  | 08/11/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 7.95 | 0 | 0
3095 | Hooghly Division | Chandannagar Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
3096 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002614/2020-2021 |  | 19/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 31 | 0 | 0
3097 | Hooghly Division | Arambug Sub-Division | Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Gobindapur, Patul & Khanakul W/S Scheme for the period of 01.09.21 to 31.08.22 under Arambagh Sub- Division P.H.E Dte. SL-54 | Assistant Engineer | Junior Engineer (Civill) | ORD/000177/2021-2022 | 1603/Hug | 03/09/2021 | 363 | M/S PRADYUT KUMAR HAZRA | 9.37 | 0 | 0
3098 | Hooghly Division | Arambug Sub-Division | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of Gobindapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000272/2021-2022 | 2126/Hug | 01/12/2021 | 30 | M/S T.K.B. CONSTRUCTION | 13.29 | 15.71 | 100
3099 | Hooghly Division | Arambug Sub-Division | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mollah Para, Malik Para Habitation of Maikhanda Village under Gobindapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-I] [ 2nd Call] | Assistant Engineer | Junior Engineer (Civill) | ORD/000516/2021-2022 | 174/Arg | 21/03/2022 | 30 | BAKSHI ENTERPRISE | 4.69 | 4.57 | 100
3100 | Hooghly Division | Arambug Sub-Division | Providing 1207 nos F.H.T.C. in Gobindapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000887/2020-2021 | 406/HUG | 15/02/2021 | 30 | M/S R.K. CHOUDHURI | 62.52 | 0.62 | 100
3101 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000026/2021-2022 | 2096/23/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
3102 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002094/2021-2022 |  | 27/01/2022 | 0 | M/S T.K.B. CONSTRUCTION | 0 | 0 | 0
3103 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002576/2020-2021 |  | 19/03/2021 | 0 | M/S R.K. CHOUDHURI | 40 | 0 | 0
3104 | Hooghly Division | Chinsuria Sub-Division | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000330/2020-2021 | 402/Hug | 15/02/2021 | 30 | ARUN SEAL AND CO. | 24.94 | 15.13 | 100
3105 | Hooghly Division | Chinsuria Sub-Division | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000876/2020-2021 | 402/HUG | 15/02/2021 | 30 | ARUN SEAL AND CO. | 6.69 | 6.69 | 100
3106 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000064/2021-2022 | 2097/4/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
3107 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000858/2021-2022 |  | 21/09/2021 | 0 | ARUN SEAL AND CO. | 15.14 | 0 | 0
3108 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection at Subhaspally of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000306/2023-2024 | 693/CH | 27/07/2023 | 15 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100
3109 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection at Natunpara Talpukur of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000307/2023-2024 | 694/CH | 27/07/2023 | 15 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100
3110 | Hooghly Division | Chinsuria Sub-Division | Connecting Rising main From Newly Bored Tube Well at Jatileswer Tala to the Existing distribution system and allied works of Naldanga water supply scheme under Chinsurah Sub Division undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000510/2023-2024 | 817/CH | 31/08/2023 | 15 | R.K. TRADERS | 0.98 | 0.96 | 80
3111 | Hooghly Division | Chinsuria Sub-Division | Laying distribution of Pipeline and allied works at Jatileswar Tala, Natun Para, Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000511/2023-2024 | 818/CH | 31/08/2023 | 15 | R.K. TRADERS | 0.96 | 0.96 | 80
3112 | Hooghly Division | Chinsuria Sub-Division | Connecting Rising main with Existing distribution system and allied works at Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000513/2023-2024 | 821/CH | 31/08/2023 | 15 | R.K. TRADERS | 1 | 1 | 80
3113 | Hooghly Division | Chinsuria Sub-Division | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system at 4TH TW Site of Naldanga W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000590/2021-2022 | 598/CH | 14/12/2021 | 25 | R.K. TRADERS | 4.05 | 1.31 | 100
3114 | Hooghly Division | Chinsuria Sub-Division | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001030/2022-2023 |  | 20/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.2 | 0 | 0
3115 | Hooghly Division | Chinsuria Sub-Division | Laying of HDPE Pipe by HDD Process & Open cut method including restoration work at Mohanad Bandel Road within MEGHSAR PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 09 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000377/2022-2023 | 2090/HUG | 21/09/2022 | 45 | M/S BISWAS CONSTRUCTION | 87.34 | 99.97 | 80
3116 | Hooghly Division | Chinsuria Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00367/2022-2023 | BP-2022-23-630 | 22/03/2023 | 0 | AATISH KUMAR SHAW | 0.4 | 0 | 0
3117 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bainchi Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000021/2022-2023 | 722/Hug | 07/04/2022 | 40 | TOTON MONDAL | 50.96 | 50.95 | 0
3118 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Batika & Chau Bera Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000022/2022-2023 | 723/Hug | 07/04/2022 | 40 | M/S ASHA CONSTRUCTION. | 48.21 | 43.01 | 0
3119 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BAINCHI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000415/2022-2023 | 2275/HUG | 19/10/2022 | 40 | M/S T.K.B. CONSTRUCTION | 45.7 | 45.54 | 0
3120 | Hooghly Division | Chinsuria Sub-Division | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000740/2022-2023 | 613/HUG | 02/03/2023 | 270 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 0 | 0
3121 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000017/2022-2023 | 1123/5/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0
3122 | Hooghly Division | Howrah Mechanical Sub-Division | Road Restoration | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00684/2023-2024 | BP-2023-24-589 | 16/11/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13 | 0 | 0
3123 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 44.35 | 100
3124 | Hooghly Division | Howrah Mechanical Sub-Division | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part I) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2025-2026 | 861/CHAN | 22/07/2025 | 20 | MAA TARA CONSTRUCTION | 4.89 | 0 | 50
3125 | Hooghly Division | Howrah Mechanical Sub-Division | Augmentation of OLIPUR (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS & Functional Household Tap Connection, Construction of 4 Nos.Switch Room(1No. 5.4 M x 3.6M & 3Nos. 3.6 M x 3.0M) & 3 Nos. Boundary Wall at 2nd T.W Site, Proposed T.W Site, O.H.R Site, Laying Rising Main, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000214/2022-2023 | 1719/Hug | 24/08/2022 | 1012 | S & P ENTERPRISE | 758.77 | 727.35 | 90
3126 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000225/2022-2023 | 264/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.93 | 3.86 | 0
3127 | Hooghly Division | Howrah Mechanical Sub-Division | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000226/2022-2023 | 265/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.02 | 0
3128 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for OLIPUR ZONE-II Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000237/2024-2025 | 3472/HUG | 04/10/2024 | 60 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 26.54 | 0 | 0
3129 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for OLIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000238/2024-2025 | 3473/HUG | 04/10/2024 | 343 | RAJMAHAL ENTERPRISE | 26.48 | 0 | 80
3130 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of Four Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at OLIPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000449/2022-2023 | 2500/HUG | 22/11/2022 | 45 | M/S SYCHROTECH INDUSTRY | 55.58 | 0 | 0
3131 | Hooghly Division | Howrah Mechanical Sub-Division | Repairing of 5.4 mtr. x 3.4 mtr. size existing pump house of Olipur PWSS under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000594/2021-2022 | 535/CHAN | 12/11/2021 | 30 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 3.43 | 0
3132 | Hooghly Division | Howrah Mechanical Sub-Division | Repairing of 5.4 mtr x 3.6 mtr. size existing pump house of Olipur PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000595/2021-2022 | 535/CHAN | 15/11/2021 | 30 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 0 | 0
3133 | Hooghly Division | Howrah Mechanical Sub-Division | Balance Laying of Pipeline of Purba Narayanpur Mouzas (JL - 80) of Olipur Zone - II water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002243/2024-2025 | 647/HUG | 10/03/2025 | 30 | T.K. INTERNATIONAL | 9.66 | 0 | 0
3134 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000028/2022-2023 | 1125/1/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0
3135 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000143/2022-2023 | 2686/10/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0
3136 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000146/2021-2022 | 157/10/Hug | 24/01/2022 | 0 | Resource Division | 1.55 | 0 | 0
3137 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000149/2021-2022 | 423/1/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
3138 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000153/2022-2023 | 01/10/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
3139 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000282/2023-2024 | 1383/29/Hug | 15/05/2023 | 0 | Resource Division | 10.61 | 0 | 0
3140 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000326/2023-2024 | 1782/Hug | 15/06/2023 | 0 | Resource Division | 158.24 | 0 | 0
3141 | Hooghly Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | RTOR000327/2023-2024 | 2502/Hug | 17/08/2023 | 0 | Resource Division | 10.8 | 0 | 0
3142 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Oilipur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00055/2023-2024 | 03 | 13/04/2023 | 0 | WBSEDCL | 0.96 | 0 | 0
3143 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Aug. of Olipur W/S. Sch. Z-I & II, PH-III & I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01882/2022-2023 | 220 | 27/03/2023 | 0 | WBSEDCL | 4.54 | 0 | 0
3144 | Electrical | Howrah Mechanical Sub-Division | QUOTATION for new Service Connection of Olipur W/S Scheme ,Zone-I,PH No-I, Block-Haripal,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02000/2023-2024 | 101 | 19/07/2023 | 0 | WBSEDCL | 3.26 | 0 | 0
3145 | Electrical | Howrah Mechanical Sub-Division | Quotation for New Service Connection of Olipur W/S Scheme ,Zone-I,PH No-II District-Hooghly under ED,PHE DTe | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02001/2023-2024 | 100 | 19/07/2023 | 0 | WBSEDCL | 1.93 | 0 | 0
3146 | Electrical | Howrah Mechanical Sub-Division | New service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02598/2023-2024 | 163 | 03/08/2023 | 0 | WBSEDCL | 11.4 | 0 | 0
3147 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Olipur water supply scheme, T.W. No.- I, II, III & IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000039/2023-2024 | 1716/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 42.97 | 42.53 | 45
3148 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for OLIPUR water supply scheme, Zone-II, TW No. IV, Block: Haripal, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/003079/2024-2025 | 477/ED | 18/03/2025 | 90 | SUBHRA ENTERPRISE | 11.3 | 0 | 0
3149 | Hooghly Division | Chandannagar Sub-Division | Construction of 300 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-I) Water Supply Scheme & Laying Rising Main, at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000135/2022-2023 | 1284/Hug | 23/06/2022 | 1043 | ARUN SEAL AND CO. | 96.23 | 76.33 | 40
3150 | Hooghly Division | Chandannagar Sub-Division | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-II) Water Supply Scheme with & Laying Rising Main at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000137/2022-2023 | 1346/Hug | 29/06/2022 | 300 | DAS ENTERPRISE (SAMIR DAS) | 110.01 | 109.92 | 45
3151 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000228/2022-2023 | 273/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.76 | 3.23 | 0
3152 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - II PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000229/2022-2023 | 274/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.15 | 3.15 | 0
3153 | Hooghly Division | Chandannagar Sub-Division | Augmentation of SALEPURDUTTAPUR (ZONE-I)Water Supply Scheme with LDS & Functional Household tap Connection, Construction of 1 No. Switch Room(3.6 M X 3.0M)& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakeswar Block under Chandannagar Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000338/2022-2023 | 1952/HUG | 07/09/2022 | 847 | UNIQUE AGENCY | 288.28 | 275.2 | 100
3154 | Hooghly Division | Chandannagar Sub-Division | Augmentation of SALEPUR-DUTTAPUR (ZONE - II) Water Supply Scheme with LDS & Functional Household Tap Connection, Construction of 1 No. Switch Room (3.6 M X 3.0 M) & Boundary Wall at 2nd T.W. Site, Proposed T.W. Site & O.H.R. Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakswar Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000414/2022-2023 | 2236/Hug | 13/10/2022 | 90 | S & P ENTERPRISE | 476.56 | 470.01 | 50
3155 | Hooghly Division | Chandannagar Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000457/2022-2023 | 2508/HUG | 22/11/2022 | 30 | SPG ENTERPRISES | 13.82 | 12.23 | 0
3156 | Hooghly Division | Chandannagar Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000458/2022-2023 | 2509/HUG | 22/11/2022 | 30 | SPG ENTERPRISES | 13.82 | 13 | 0
3157 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000061/2022-2023 | 1690/HUG | 22/08/2022 | 0 | Resource Division | 93.17 | 0 | 0
3158 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000138/2022-2023 | 2686/5/Hug | 01/12/2022 | 0 | Resource Division | 0.32 | 0 | 0
3159 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000297/2023-2024 | 1383/41/Hug | 15/05/2023 | 0 | Resource Division | 5.14 | 0 | 0
3160 | Electrical | Chandannagar Sub-Division | Augmentation Of Solepur-Duttapur Water Supply Scheme. TW-3, Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01909/2022-2023 | 248 | 30/03/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
3161 | Electrical | Chandannagar Sub-Division | Quation Money for Salepur Duttapur PH No-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02007/2023-2024 | 102 | 19/07/2023 | 0 | WBSEDCL | 3.35 | 0 | 0
3162 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Salepur Duttapur water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000226/2022-2023 | 857/ED | 14/02/2023 | 90 | ALPHA ENTERPRISE | 21.49 | 21.44 | 45
3163 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 467.08 | 30
3164 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000123/2023-2024 | 1264/18/HUG | 03/05/2023 | 0 | Resource Division | 15.5 | 0 | 0
3165 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000226/2023-2024 | 1386/5/Hug | 15/05/2023 | 0 | Resource Division | 11.59 | 0 | 0
3166 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05060/2023-2024 | 685 | 19/01/2024 | 0 | WBSEDCL | 11.72 | 0 | 0
3167 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05061/2023-2024 | 684 | 19/01/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
3168 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kanajoli water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000156/2022-2023 | 3493/ED | 30/12/2022 | 90 | CHATTERJEE BROTHERS | 20.25 | 16.41 | 35
3169 | Hooghly Division | Chinsuria Sub-Division | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 328.47 | 30
3170 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000118/2023-2024 | 1264/13/HUG | 03/05/2023 | 0 | Resource Division | 16.96 | 0 | 0
3171 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000249/2023-2024 | 1386/28/Hug | 15/05/2023 | 0 | Resource Division | 22.55 | 0 | 0
3172 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000531/2023-2024 | 3059/6/Hug | 11/10/2023 | 0 | Resource Division | 22.55 | 0 | 0
3173 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Chalua w/s Scheme,PH No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12257) Application No-5003977943 Reference Id-503540606 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06103/2023-2024 | 763 | 16/02/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
3174 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Chalua w/s Scheme,TW No-I,Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte.(SM/12257) Application No-5003977900 Reference Id-503540601 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06104/2023-2024 | 764 | 16/02/2024 | 0 | WBSEDCL | 4.74 | 0 | 0
3175 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chalua water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000079/2022-2023 | 3461/ED | 30/12/2022 | 90 | M/S P.P. ELECTRICALS | 22.94 | 0 | 0
3176 | Hooghly Division | Srirampur Sub-Division | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 283.71 | 9
3177 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | RTOR000034/2023-2024 | 1236/1/Hug | 28/04/2023 | 0 | Resource Division | 28.77 | 0 | 0
3178 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | RTOR000319/2023-2024 | 1384/16/Hug | 15/05/2023 | 0 | Resource Division | 16.88 | 0 | 0
3179 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | RTOR000524/2023-2024 | 3060/15/Hug | 11/10/2023 | 0 | Resource Division | 16.88 | 0 | 0
3180 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Dudhkalmi PWSS P.H. No.-II, Hooghly. Application No. 5004031077 Ref ID: 503576014 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/00039/2024-2025 | 24 | 05/04/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
3181 | Electrical | Srirampur Sub-Division | Dudhkalmi w/s scheme,P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/04509/2023-2024 | 559 | 21/12/2023 | 0 | WBSEDCL | 5.64 | 0 | 0
3182 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dudhkalmi water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000144/2022-2023 | 3488/ED | 30/12/2022 | 90 | S.P. CONSTRUCTION | 21.37 | 0 | 0
3183 | Hooghly Division | Chinsuria Sub-Division | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 311.42 | 15
3184 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000108/2023-2024 | 1264/2/HUG | 03/05/2023 | 0 | Resource Division | 4.63 | 0 | 0
3185 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000221/2023-2024 | 1386/Hug | 15/05/2023 | 0 | Resource Division | 11.38 | 0 | 0
3186 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000484/2023-2024 | 3059/22/Hug | 11/10/2023 | 0 | Resource Division | 0.47 | 0 | 0
3187 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dalimba W/S Sch., T/W No. - I, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03783/2023-2024 | 283 | 13/09/2023 | 0 | WBSEDCL | 4.85 | 0 | 0
3188 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dalimba W/S Sch., T/W No. - II, Block - Polba-Dadpur, Dist. - Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04077/2023-2024 | 350 | 11/10/2023 | 0 | WBSEDCL | 3.11 | 0 | 0
3189 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dalimba water supply scheme, T.W. No.- I & II, Block: Polba - Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000142/2022-2023 | 3487/ED | 30/12/2022 | 810 | A.K. ENTERPRISE | 20.38 | 16.47 | 90
3190 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of AIMA CHAPSARA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. [2nd Call of WBPHE/EE/35/HUG/2022-23, Sl No-1] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000048/2023-2024 | 1200/HUG | 26/04/2023 | 45 | PRASUN ENTERPRISE (PRASUN BISWAS) | 28.83 | 27.45 | 100
3191 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Ayma Chapsara H/W site & Kamarkundu (Zone-VI) 3rd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000284/2024-2025 | 924/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
3192 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for AIMACHAPSARA Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000338/2023-2024 | 2423/HUG | 11/08/2023 | 568 | AMBIAN INFRASTRUCTURE | 41.36 | 3.9 | 50
3193 | Hooghly Division | Chandannagar Sub-Division | AIMA CHAPSARA Piped Water Supply Scheme with Laying Distribution System, FHTC & Construction of 300 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL BLOCK under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000485/2022-2023 | 2896/HUG | 22/12/2022 | 970 | PRASUN ENTERPRISE (PRASUN BISWAS) | 370.57 | 100.09 | 20
3194 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of AIMA CHAPSARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000750/2022-2023 | 651/Hug | 10/03/2023 | 60 | KAPTON | 12.29 | 12.29 | 100
3195 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000073/2023-2024 | 1235/13/Hug | 28/04/2023 | 0 | Resource Division | 59.23 | 0 | 0
3196 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000275/2022-2023 | 902/9/Hug | 27/03/2023 | 0 | Resource Division | 9.01 | 0 | 0
3197 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000291/2023-2024 | 1383/37/Hug | 15/05/2023 | 0 | Resource Division | 9.17 | 0 | 0
3198 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxuary Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00957/2024-2025 | 266 | 03/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
3199 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte Car No.- WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01156/2024-2025 | 281 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
3200 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte 01/07/2024 to 31/07/2024 WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01639/2024-2025 | 412 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
3201 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.- WB-15C-5554 From 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01995/2024-2025 | 468 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
3202 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02106/2024-2025 | 549 | 30/10/2024 | 0 | DILIP KUMAR GHOSH | 0.08 | 0 | 0
3203 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01.09.2024 to 30.09.2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02107/2024-2025 | 550 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0
3204 | Electrical | Chandannagar Sub-Division | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02471/2024-2025 | 623 | 18/12/2024 | 0 | DILIP KUMAR GHOSH | 0.02 | 0 | 0
3205 | Electrical | Chandannagar Sub-Division | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01/10/2024 to 31/10/2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02472/2024-2025 | 619 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
3206 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04474/2023-2024 | 526 | 14/12/2023 | 0 | WBSEDCL | 8.35 | 0 | 0
3207 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04475/2023-2024 | 525 | 14/12/2023 | 0 | WBSEDCL | 2.72 | 0 | 0
3208 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Aima Chapsara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000074/2022-2023 | 3456/ED | 30/12/2022 | 90 | TAMAL ENTERPRISE | 21.5 | 21.46 | 30
3209 | Electrical | Chandannagar Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000515/2024-2025 | 1645/AE-II/ED | 29/07/2024 | 184 | DILIP KUMAR GHOSH | 0.87 | 0.58 | 0
3210 | Electrical | Chandannagar Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/003371/2023-2024 | 218_AE-II_ED | 20/02/2024 | 182 | DILIP KUMAR GHOSH | 0.86 | 0.44 | 0
3211 | Hooghly Division | Arambug Sub-Division | Providing 1319 nos Functional Household Tap Connection (FHTC) within Haraditya & Shyamgram Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000055/2022-2023 | 884/HUG | 29/04/2022 | 40 | ANUP PAUL | 62.53 | 54.75 | 0
3212 | Hooghly Division | Arambug Sub-Division | Providing 1301 nos Functional Household Tap Connection (FHTC) within Amgaon, Birati & Chhandra Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000056/2022-2023 | 885/HUG | 29/04/2022 | 40 | PREMANANDA ROY BISWAS | 58.31 | 58.24 | 0
3213 | Hooghly Division | Arambug Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARADITYA PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000106/2023-2024 | 1426/HUG | 17/05/2023 | 45 | GANESH RAY | 37.07 | 0 | 0
3214 | Hooghly Division | Arambug Sub-Division | Preparation & Improvement of foundation due to continuous comprehensive seepage after starting of excavation for raft foundation at Head Work Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000434/2022-2023 | 739/Arg | 29/09/2022 | 30 | ANUP PAUL | 1.48 | 0 | 0
3215 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000538/2022-2023 | 2739/HUG | 07/12/2022 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 4.87 | 4.87 | 100
3216 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | RTOR000135/2023-2024 | 1385/6/Hug | 15/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
3217 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 225.15 | 50
3218 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000842/2023-2024 | 722/HUG | 05/03/2024 | 60 | ANIRUDDHA FARUQUE | 48.17 | 13.6 | 100
3219 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
3220 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002746/2024-2025 | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
3221 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000080/2023-2024 | 1234/40/Hug | 28/04/2023 | 0 | Resource Division | 120.19 | 0 | 0
3222 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000173/2023-2024 | 1385/44/Hug | 15/05/2023 | 0 | Resource Division | 12.89 | 0 | 0
3223 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000483/2023-2024 | 3057/5/Hug | 11/10/2023 | 0 | Resource Division | 12.89 | 0 | 0
3224 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13762). Application No-5004034769 Reference Id-503576011 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00150/2024-2025 | 53 | 12/04/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
3225 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13762) Application no-5004034787 Reference Id-503576010 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00440/2024-2025 | 127 | 17/05/2024 | 0 | WBSEDCL | 6.13 | 0 | 0
3226 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Hirapur w/s scheme, Zone- II, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004210670 Reference ID- 503656455 SM Code- 13762 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00820/2024-2025 | 222 | 18/06/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
3227 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000150/2024-2025 | 1173/ED | 14/06/2024 | 90 | PS & ASSOCIATES | 10.75 | 0 | 50
3228 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000187/2022-2023 | 780/ED | 09/02/2023 | 873 | M.D ENTERPRISE | 20.49 | 0 | 10
3229 | Hooghly Division | Arambug Sub-Division | Providing 1591 nos Functional Household Tap Connection (FHTC) within Benga & Batanal Mouza of Batanal(Zone-I) Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000057/2022-2023 | 886 | 29/04/2022 | 50 | M/S PRADYUT KUMAR HAZRA | 75.31 | 73.68 | 98
3230 | Hooghly Division | Srirampur Sub-Division | Repairing of Damaged Road due to FHTC Works at Ranibazar & Lohagacchi mouzas of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000204/2024-2025 | 549/SER | 19/09/2024 | 7 | TOTON MONDAL | 4.99 | 0 | 98
3231 | Hooghly Division | Srirampur Sub-Division | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000906/2023-2024 | 829/HUG | 11/03/2024 | 30 | SURAJIT SINGHA RAY | 30.4 | 30.4 | 99
3232 | Hooghly Division | Srirampur Sub-Division | Providing 1250 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Antpur Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000913/2020-2021 | 466/HUG | 26/02/2021 | 1039 | GHOSH CONCERN | 96.72 | 4.55 | 72
3233 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Lohagachhi village under Antpur PWSS (2 nos.) 2. Ranibazar village under Antpur PWSS (2 nos.) 3. Anarbati village under Antpur PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000957/2023-2024 | 170/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 80
3234 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Raipur village under Antpur PWSS (2 nos.) 2. Atpur village under Antpur PWSS (2 nos.) 3. Palgachha village under Antpur PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000959/2023-2024 | 171/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 80
3235 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | RTOR000155/2023-2024 | 1385/26/Hug | 15/05/2023 | 0 | Resource Division | 0.23 | 0 | 0
3236 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00359/2023-2024 | BP-2023-24-299 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.91 | 0 | 0
3237 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
3238 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
3239 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00294/2023-2024 | BP-2023-24-245 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.52 | 0 | 0
3240 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
3241 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000272/2023-2024 | 1383/24/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0
3242 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00083/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.54 | 0 | 0
3243 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00214/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.82 | 0 | 0
3244 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00411/2023-2024 | BP-2023-24-336 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.34 | 0 | 0
3245 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000137/2023-2024 | 1385/8/Hug | 15/05/2023 | 0 | Resource Division | 0.52 | 0 | 0
3246 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
3247 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | BILL/00355/2023-2024 | BP-2023-24-294 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.83 | 0 | 0
3248 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
3249 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
3250 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00290/2023-2024 | BP-2023-24-241 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.09 | 0 | 0
3251 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000131/2023-2024 | 1385/2/Hug | 15/05/2023 | 0 | Resource Division | 0.39 | 0 | 0
3252 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
3253 | Hooghly Division | Chandannagar Sub-Division | PARJANA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000102/2023-2024 | 1406/Hug | 17/05/2023 | 270 | S & P ENTERPRISE | 659.08 | 451.88 | 50
3254 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Barakamalpur (Z-4) 1st T/W site & Parjana 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000282/2024-2025 | 921/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 100
3255 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000196/2022-2023 | 109/ 11/Hug | 10/01/2023 | 0 | Resource Division | 11.55 | 0 | 0
3256 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000209/2023-2024 | 1383/12/Hug | 15/05/2023 | 0 | Resource Division | 14.48 | 0 | 0
3257 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000277/2022-2023 | 902/10/Hug | 27/03/2023 | 0 | Resource Division | 14.48 | 0 | 0
3258 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000386/2023-2024 | 3058/28/Hug | 11/10/2023 | 0 | Resource Division | 14.48 | 0 | 0
3259 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05964/2023-2024 | 721 | 31/01/2024 | 0 | WBSEDCL | 8.41 | 0 | 0
3260 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05965/2023-2024 | 722 | 31/01/2024 | 0 | WBSEDCL | 7.3 | 0 | 0
3261 | Electrical | Chandannagar Sub-Division | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Parjana water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000178/2022-2023 | 771/ED | 09/02/2023 | 90 | WEST BENGAL ENGINEERING CO. | 32.05 | 20.58 | 30
3262 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of AMODGHATAPWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000027/2023-2024 | 1128/HUG | 19/04/2023 | 30 | ASIT KUMAR KHAMRUI | 27.23 | 21.72 | 55
3263 | Hooghly Division | Chinsuria Sub-Division | Providing 232 nos Functional Household Tap Connection (FHTC) within the command area of Amodghata Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000569/2021-2022 | 2001/HUG | 12/11/2021 | 30 | R.K. TRADERS | 10.07 | 10.03 | 0
3264 | Hooghly Division | Chinsuria Sub-Division | REFAITPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000748/2022-2023 | 684/Hug | 10/03/2023 | 270 | SATYA NARAYAN BISWAS | 261.02 | 157.29 | 40
3265 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Gurbari PWSS 2. Lokabati PWSS 3. Bishnupur PWSS 4. Kamalpur PWSS 5. Refaitpur Z-I PWSS 6. Barul PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000773/2023-2024 | 139/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
3266 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000293/2023-2024 | 1386/56/Hug | 15/05/2023 | 0 | Resource Division | 6.75 | 0 | 0
3267 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000532/2023-2024 | 3059/34/Hug | 11/10/2023 | 0 | Resource Division | 6.75 | 0 | 0
3268 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Refaitpur W/S Sch., Zone - I, T/w No. - I, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03782/2023-2024 | 305 | 26/09/2023 | 0 | WBSEDCL | 6.1 | 0 | 0
3269 | Electrical | Chinsuria Sub-Division | Quotattion for new service connection at Refaitpur W/S Sch., Zon - I, T/W -II, Block - Chinsurah-Mogra, Dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03980/2023-2024 | 315 | 03/10/2023 | 0 | WBSEDCL | 13.11 | 0 | 0
3270 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Refaitpur W/S. Sch. TW- I & II, & Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04136/2023-2024 | 388&389 | 02/11/2023 | 0 | WBSEDCL | 11.2 | 0 | 0
3271 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2022-2023 | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 19.09 | 90
3272 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Dashghara PWSS 2. Patul PWSS 3. Durgapur PWSS 4. Khajurdaha PWSS 5. Refaitpur Z-II PWSS 6. Kalora PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000774/2023-2024 | 140/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 30
3273 | Hooghly Division | Chinsuria Sub-Division | REFAITPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000810/2022-2023 | 975/Hug | 31/03/2023 | 270 | DAS ENTERPRISE (SAMIR DAS) | 244.77 | 177.94 | 30
3274 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Refaitpur Z-II PWSS 2. Sankhangar Chakbasberia PWSS 3. Basudebbati PWSS 4. Dantra PWSS 5. Goswami Malipara PWSS 6. Amra PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000822/2023-2024 | 200/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3275 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000522/2023-2024 | 3059/9/Hug | 11/10/2023 | 0 | Resource Division | 9.67 | 0 | 0
3276 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000232/2022-2023 | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 19.92 | 90
3277 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Santoshpur Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within Tarakeswar Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000078/2023-2024 | 1312/HUG | 10/05/2023 | 30 | SRI KRISHNA ENTERPRISE | 11.78 | 3.57 | 40
3278 | Hooghly Division | Howrah Mechanical Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SANTOSHPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000768/2022-2023 | 751/HUG | 15/03/2023 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0
3279 | Electrical | Howrah Mechanical Sub-Division | Quotation money deposition for new service connection at Santoshpur w/s scheme, P.H. No.-3, Dist.-Hooghly under PHE Dte. Application No- 5004085290 Reference ID- 503609191 SM Code- 15793 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/00439/2024-2025 | 129 | 17/05/2024 | 0 | WBSEDCL | 6.12 | 0 | 0
3280 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Santoshpur water supply scheme, T.W. No. I, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000007/2023-2024 | 1623/ED | 11/04/2023 | 720 | UNIVERSAL ENTERPRISES | 10.75 | 0 | 100
3281 | Hooghly Division | Howrah Mechanical Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAMONJOL Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000129/2023-2024 | 1472/HUG | 19/05/2023 | 30 | GOURI ENTERPRISE | 11.8 | 11.12 | 100
3282 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection of Bamonjol W/S Scheme(Aug) TW No-3 District-Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01998/2023-2024 | 113 | 19/07/2023 | 0 | WBSEDCL | 0.79 | 0 | 0
3283 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamonjol water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000013/2023-2024 | 1629/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 11.05 | 40
3284 | Hooghly Division |  | Providing1670 nos F.H.T.C. in Sarkhola, Hanral,Mogalpur,Kantul, Anantapur,Krishnapur, Shrirampur,Kantagare & Sekendarpur Village of Hanral Zone-I and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] |  |  | ORD/000007/2021-2022 | 938/Hug | 06/05/2021 | 40 | M/S S.S. ENTERPRISE | 96.09 | 77.65 | 100
3285 | Hooghly Division |  | Providing 1507 nos F.H.T.C. in Samsara, Hodla,Aima,Kharsat, Rasulpur,Khidirpur, Dakshin Dadpur,Maheshwarpur& Tamila Village of Hanral Zone-II and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] |  |  | ORD/000080/2021-2022 | 1146/Hug | 29/06/2021 | 40 | LOKENIRMAN | 87 | 87 | 100
3286 | Hooghly Division |  | Providing 390 nos Functional Household Tap Connection (FHTC) within the command area of HANRAL & DWARBASINI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000442/2021-2022 | 460/Hug | 10/03/2022 | 25 | M/S R.M. CONSTRUCTION | 28.34 | 26.75 | 100
3287 | Hooghly Division |  | FHTC |  |  | VCH/000943/2021-2022 |  | 24/09/2021 | 0 | LOKENIRMAN | 28.24 | 0 | 0
3288 | Hooghly Division |  | FHTC |  |  | VCH/001048/2021-2022 |  | 30/09/2021 | 0 | M/S S.S. ENTERPRISE | 26.38 | 0 | 0
3289 | Central Drilling |  | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000158/2022-2023 | 293/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 9.23 | 100
3290 | Central Drilling |  | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000161/2022-2023 | 292/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 5.2 | 90
3291 | Central Drilling |  | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-II) PWSS, BLOCK - POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. |  |  | ORD/000212/2022-2023 | 519/CMSD-I | 21/10/2022 | 3 | DEV ENTERPRISE | 0.32 | 0 | 100
3292 | Central Drilling |  | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-I) PWSS, BLOCK- POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. |  |  | ORD/000214/2022-2023 | 491/CMSD-I | 28/09/2022 | 7 | DEV ENTERPRISE | 0.32 | 0 | 100
3293 | Hooghly Division | Srirampur Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC of KRISHNARAMPUR W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000044/2023-2024 | 1172/HUG | 20/04/2023 | 45 | TAPAS ADHYA | 63.38 | 51.97 | 35
3294 | Hooghly Division | Srirampur Sub-Division | Estimate for Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of Krishnarampur Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001292/2024-2025 | 64/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 4.42 | 0 | 0
3295 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000325/2023-2024 | 1384/21/Hug | 15/05/2023 | 0 | Resource Division | 8.93 | 0 | 0
3296 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Krishnarampur PWSS P.H. No.-IV, Hooghly. Application No. 5004062824 Ref ID: 503597308 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00117/2024-2025 | 43 | 09/04/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
3297 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection at Krishnarampur W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00726/2023-2024 | 31 | 12/05/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
3298 | Electrical | Srirampur Sub-Division | New service connection charges for Krishnarampur w/s scheme, PH No.-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01161/2023-2024 | 86 | 12/07/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
3299 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnarampur water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000019/2023-2024 | 1635/ED | 11/04/2023 | 90 | D.S. ENTERPRISE | 11.41 | 11.13 | 70
3300 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNARAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000174/2024-2025 | 1198/ED | 14/06/2024 | 322 | P.P. CONCERN | 10.75 | 0 | 75
3301 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KRISHNARAMPUR W/S SCH, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000378/2022-2023 | 1999/CDD | 08/02/2023 | 30 | UNIVERSAL ENTERPRISES | 12.65 | 11 | 0
3302 | Hooghly Division | Arambug Sub-Division | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of SABALSINGHAPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000114/2023-2024 | 1443/HUG | 18/05/2023 | 390 | KARALI MOHAN KHAMRUI | 31.29 | 31.26 | 94
3303 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of SABALSINGHAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000453/2024-2025 | 4078/HUG | 19/12/2024 | 90 | CHAKRABORTY ENTERPRISE | 14.1 | 0 | 0
3304 | Hooghly Division | Arambug Sub-Division | Protection works and other allied works at 2nd TubeWell Sites of Soaluk & Sabalsinghapur Water Supply Scheme under Arambagh Sub Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000473/2024-2025 | 4052/HUG | 19/12/2024 | 90 | TANISA ENTERPRISE | 15.54 | 0 | 0
3305 | Hooghly Division | Arambug Sub-Division | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000893/2022-2023 | 1413/Hug | 12/07/2022 | 30 | SUBHAJIT BISWAS | 7.88 | 7.32 | 0
3306 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-IV, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235292 Reference ID- 503666262 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00817/2024-2025 | 221 | 18/06/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
3307 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00818/2024-2025 | 220 | 18/06/2024 | 0 | WBSEDCL | 5.73 | 0 | 0
3308 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-II, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004234490 Reference ID- 503666255 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00819/2024-2025 | 219 | 18/06/2024 | 0 | WBSEDCL | 7.27 | 0 | 0
3309 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-III | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00893/2022-2023 | 180 | 09/03/2023 | 0 | WBSEDCL | 2.81 | 0 | 0
3310 | Electrical | Arambug Sub-Division | "Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-IV Hooghly" | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00895/2022-2023 | 180 | 09/03/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
3311 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sabalsinghapur water supply scheme, T.W. No. III, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000869/2023-2024 | 3442/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 10.74 | 10.66 | 25
3312 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/001074/2023-2024 | 4190/ED | 01/11/2023 | 90 | D. K. ELECTRIC | 10.83 | 10.75 | 40
3313 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/002102/2022-2023 | 2048/ED | 01/12/2022 | 90 | BOSE & CHATTERJEE INDUSTRIES | 10.57 | 0 | 0
3314 | Hooghly Division | Srirampur Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system & FHTC For Development of ANIYA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000113/2023-2024 | 1442/HUG | 18/05/2023 | 30 | M/S KAMALA ENTERPRISE | 26.42 | 14.91 | 80
3315 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000311/2023-2024 | 1384/8/Hug | 16/05/2023 | 0 | Resource Division | 1.23 | 0 | 0
3316 | Electrical | Srirampur Sub-Division | Aniya water supply scheme,P H No-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02293/2023-2024 | 142 | 25/07/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
3317 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Aniya water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000011/2023-2024 | 1627/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 11.11 | 85
3318 | Central Drilling | Srirampur Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS.) BY UTILISING DEPARTMENTAL RIG MACHINERIES FOR ANIYA SCHEME (P/H-3), CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CENTRAL DRILLING DIVISION , PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000032/2023-2024 | 872/CDD | 11/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 10.73 | 10.41 | 100
3319 | Central Drilling | Srirampur Sub-Division | Additional work for construction of tube well at Aniya PWSS TW-I, Chanditala-I Block, Hooghly District by utilizing skilled departmental crew and departmental mechaneries CDD, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000197/2023-2024 | 193/CMSD-II | 26/07/2023 | 10 | UTTAM KUMAR CHATTERJEE | 0.67 | 0.69 | 100
3320 | Hooghly Division | Chinsuria Sub-Division | Horizontal Auger boring with water jet system including Protection Work at Patna Bhairabpur W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000305/2024-2025 | 3676/HUG | 13/11/2024 | 30 | SAMRAT CONSTRUCTION | 8.16 | 0 | 0
3321 | Hooghly Division | Chinsuria Sub-Division | Maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000732/2023-2024 | 24/CH | 05/01/2024 | 15 | SUNITI MAIRA | 4.47 | 0 | 50
3322 | Hooghly Division | Chinsuria Sub-Division | Laying of pipe line and other necessary maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000733/2023-2024 | 25/CH | 05/01/2024 | 15 | SUNITI MAIRA | 4.67 | 4.54 | 50
3323 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 65
3324 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000356/2023-2024 | 3004/Hug | 05/10/2023 | 0 | Resource Division | 1.5 | 0 | 0
3325 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000541/2023-2024 | 3059/28/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0
3326 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Patna Bhirabpur W/S Sch. T/W - I (Aug.), Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03755/2023-2024 | 259 | 05/09/2023 | 0 | WBSEDCL | 5.61 | 0 | 0
3327 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patna Bhairavpur water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000020/2023-2024 | 1636/ED | 11/04/2023 | 90 | DIPA CHHETRI | 11.5 | 11.47 | 90
3328 | Hooghly Division | Arambug Sub-Division | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 176.39 | 30
3329 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) MAYAPUR PWSS (Z-II)- 1no¿s (2) BALUNDI PWSS - 4no¿s (3) BHALIA PWSS (Z-I)- 2 no¿s (4) BHALIA PWSS (Z-II)- 1 no¿s (5) DAHARKUNDU PWSS (Z-I)- 2 no¿s, (6) DAHARKUNDU PWSS (Z-II)- 2 no¿s, (7) GOBINDANAGAR PWSS(Z-I) ¿2 no¿s | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002742/2024-2025 | 1150/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0
3330 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000044/2023-2024 | 1234/17/Hug | 28/04/2023 | 0 | Resource Division | 42.83 | 0 | 0
3331 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000476/2023-2024 | 3057/10/Hug | 11/10/2023 | 0 | Resource Division | 13.55 | 0 | 0
3332 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Dahar Kundu W/S. Sch.TW-I, Z-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04583/2023-2024 | 588 | 28/12/2023 | 0 | WBSEDCL | 6.53 | 0 | 0
3333 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-II,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/15913) Application No-5004015927 Reference Id-503563368 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06064/2023-2024 | 754 | 16/02/2024 | 0 | WBSEDCL | 16.1 | 0 | 0
3334 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DAHARKUNDU PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000204/2024-2025 | 1160/ED | 14/06/2024 | 90 | B.P. TRADING CORPORATION | 10.75 | 0 | 0
3335 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-II, T.W. No.- I & II, Block: Armbag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000310/2022-2023 | 1240/ED | 06/03/2023 | 787 | ALPHA ENTERPRISE | 20.47 | 0 | 30
3336 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARALPWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2023-2024 | 1134/HUG | 19/04/2023 | 30 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.97 | 14.95 | 100
3337 | Hooghly Division | Chinsuria Sub-Division | Sinking of tube-well, LDS, Rising Main, Connection with Existing FHTC, construction of switch-room & boundary wall & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones for Augmentation of HANRAL Piped Water Supply Scheme under POLBA DADPUR Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000178/2023-2024 | 1683/HUG | 08/06/2023 | 180 | ASIA CONSTRUCTION | 503.22 | 116.17 | 45
3338 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000279/2023-2024 | 1386/52/Hug | 15/05/2023 | 0 | Resource Division | 1.23 | 0 | 0
3339 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT HANRAL W/S SCHEME, T/W NO. - III, DIST. - HOOGHLY | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00762/2023-2024 | 45 | 23/05/2023 | 0 | WBSEDCL | 10.88 | 0 | 0
3340 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Hanral W/S. Sch. PH-III, Z-I Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00894/2022-2023 | 179 | 09/03/2023 | 0 | WBSEDCL | 2.86 | 0 | 0
3341 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hanral W/S Sch., Zone -I, T/W No. - III [SM/16119] under SM/Dadpur, WBSEDCL, Ref Id. - 503657583, dt. - 25-06-2024, Application No. - 5004214131 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00969/2024-2025 | 256 | 03/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
3342 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-I, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001374/2022-2023 | 969/ED | 25/02/2023 | 90 | TRIDENT ENTERPRISE | 11.08 | 2.93 | 90
3343 | Hooghly Division | Chinsuria Sub-Division | KALORA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000243/2023-2024 | 2098/HUG | 19/07/2023 | 90 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 98.59 | 18.07 | 20
3344 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000225/2023-2024 | 1386/4/Hug | 15/05/2023 | 0 | Resource Division | 3.22 | 0 | 0
3345 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000365/2023-2024 | 3004/13/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0
3346 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000526/2023-2024 | 3059/8/Hug | 11/10/2023 | 0 | Resource Division | 3.22 | 0 | 0
3347 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kalora W/S Sch.,Near Majhar, [SM/18099], T/W No. - I, Block - Polba-Dadpur under Bandel CCC, WBSEDCL | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06246/2023-2024 | 850 | 07/03/2024 | 0 | WBSEDCL | 10.7 | 0 | 0
3348 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalora water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000071/2023-2024 | 1927/ED | 15/05/2023 | 90 | MAA KALI ENTERPRISE | 22.96 | 11.19 | 50
3349 | Hooghly Division | Chinsuria Sub-Division | Ground Water based BARAMALLIKPUR Piped Water Supply Scheme in Dhaniakhali Block under Chinsurah Sub-Division P.H.E. Dte. District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | ORD/000097/2023-2024 | 1364/HUG | 12/05/2023 | 90 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.69 | 31.77 | 98
3350 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar HazipurMini PWSS 2. Bara Mallikpur Mini PWSS 3. Sripala Mini PWSS 4. Alasin Mini PWSS 5. Chautpur Mini PWSS 6. Jangalpur Mini PWSS | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | ORD/000998/2023-2024 | 272/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100
3351 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | RTOR000265/2023-2024 | 1386/44/Hug | 15/05/2023 | 0 | Resource Division | 0.59 | 0 | 0
3352 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basa Mallikpur mini piped W/S. Sch. | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | BILL/04337/2023-2024 | 452 | 29/11/2023 | 0 | WBSEDCL | 0.32 | 0 | 0
3353 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bara Mallikpur Mini Piped W/S Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | ORD/001696/2023-2024 | 5175/ED | 28/12/2023 | 90 | RISHAV ENTERPRISE | 7.25 | 7.25 | 55
3354 | Hooghly Division | Srirampur Sub-Division | MUNDALIKA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000276/2023-2024 | 2295/HUG | 03/08/2023 | 727 | GHOSH CONCERN | 585.3 | 228.02 | 50
3355 | Hooghly Division | Srirampur Sub-Division | MUNDALIKA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000278/2023-2024 | 2293/HUG | 03/08/2023 | 821 | JAL PRAVAHIKA PVT. LTD | 608.12 | 201.6 | 20
3356 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000333/2023-2024 | 3005/1/Hug | 05/10/2023 | 0 | Resource Division | 65.04 | 0 | 0
3357 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000514/2023-2024 | 3060/10/Hug | 11/10/2023 | 0 | Resource Division | 27.04 | 0 | 0
3358 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04645/2023-2024 | 622 | 08/01/2024 | 0 | WBSEDCL | 12.14 | 0 | 0
3359 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04647/2023-2024 | 623 | 08/01/2024 | 0 | WBSEDCL | 8.9 | 0 | 0
3360 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04688/2023-2024 | 664 | 11/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
3361 | Electrical | Srirampur Sub-Division | Quotation for New service connection at Mundalika W/S. Sch.Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06222/2023-2024 | 826 | 01/03/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
3362 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mundalika water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000821/2023-2024 | 3176/ED | 28/07/2023 | 613 | R.N.S. TRADING | 43.65 | 0 | 10
3363 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Naita PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000411/2022-2023 | 513/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 5.15 | 5.15 | 0
3364 | Hooghly Division | Chandannagar Sub-Division | "NAITA" Piped Water Supply Scheme With LDS, FHTC & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000473/2022-2023 | 2546/HUG | 24/11/2022 | 180 | SIBSANKAR CHOWDHURY | 504.76 | 241.93 | 65
3365 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of NAITA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000661/2022-2023 | 158/HUG | 16/01/2023 | 45 | M/S SYCHROTECH INDUSTRY | 28.77 | 0 | 0
3366 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of NAITA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000752/2022-2023 | 653/Hug | 10/03/2023 | 60 | GOURI ENTERPRISE | 12.25 | 12.25 | 50
3367 | Hooghly Division | Chandannagar Sub-Division | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 31.65 | 100
3368 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000219/2022-2023 | 109/ 24/Hug | 10/01/2023 | 0 | Resource Division | 40.3 | 0 | 0
3369 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000274/2022-2023 | 902/11/Hug | 27/03/2023 | 0 | Resource Division | 13.29 | 0 | 0
3370 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000289/2023-2024 | 1383/35/Hug | 15/05/2023 | 0 | Resource Division | 4.49 | 0 | 0
3371 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000368/2023-2024 | 3003/Hug | 05/10/2023 | 0 | Resource Division | 41.04 | 0 | 0
3372 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000449/2023-2024 | 3058/36/Hug | 11/10/2023 | 0 | Resource Division | 13.24 | 0 | 0
3373 | Electrical | Chandannagar Sub-Division | Naita w/s scheme,P H No -I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03902/2023-2024 | 307 | 26/09/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
3374 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for NAITA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004032139 Ref. ID- 503573584 SM/11291 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06195/2023-2024 | 803 | 27/02/2024 | 0 | WBSEDCL | 6.57 | 0 | 0
3375 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Naita water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000088/2022-2023 | 3470/ED | 30/12/2022 | 810 | GOENKA ENTERPRISE | 21.49 | 15.43 | 70
3376 | Central Drilling | Chandannagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x180 Mtrs.) byn utilising departmental rig machineries for naita W/S Scheme (TW-I & II), Tarakeswar Block under Hooghly District, CDD, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000030/2023-2024 | 873/CDD | 11/07/2023 | 30 | CHANDA ENTERPRISE | 24.62 | 11.57 | 50
3377 | Hooghly Division | Chandannagar Sub-Division | DIARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000173/2023-2024 | 1678/HUG | 08/06/2023 | 938 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 451.08 | 180.65 | 60
3378 | Hooghly Division | Chandannagar Sub-Division | Horizontal road crossing by trenchless method across BTC Road (PWD) at yuger more & allied works in Diara pwss under Chandannagar Sub-Division, of Hooghly Division P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000225/2024-2025 | 3433/HUG | 03/10/2024 | 335 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 11.39 | 0 | 80
3379 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000046/2023-2024 | 1235/3/Hug | 28/04/2023 | 0 | Resource Division | 33.96 | 0 | 0
3380 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000214/2023-2024 | 1383/16/Hug | 15/05/2023 | 0 | Resource Division | 3.01 | 0 | 0
3381 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000267/2022-2023 | 902/4/Hug | 27/03/2023 | 0 | Resource Division | 14.2 | 0 | 0
3382 | Electrical | Chandannagar Sub-Division | Quotation New Service Connection for Diara Water Supply Scheme, Block - Singur, Dist - hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02761/2023-2024 | 172 | 10/08/2023 | 0 | WBSEDCL | 3.96 | 0 | 0
3383 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Diara W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05922/2023-2024 | 714 | 29/01/2024 | 0 | WBSEDCL | 8.07 | 0 | 0
3384 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000234/2024-2025 | 3469/HUG | 04/10/2024 | 90 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0
3385 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof MADHABPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000256/2024-2025 | 3526/HUG | 22/10/2024 | 30 | GITA ENTERPRISE | 31.35 | 0 | 0
3386 | Hooghly Division | Arambug Sub-Division | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 294.27 | 30
3387 | Hooghly Division | Arambug Sub-Division | Horizontal Auger boring with water jet system & other ancillary works at Madhabpur Water Suply Scheme under Serampur Sub Division of Hooghly Division PHE Dte, | Assistant Engineer | Junior Engineer (Civill) | ORD/001837/2024-2025 | 333/HUG | 05/02/2025 | 60 | ARUN SEAL AND CO. | 28.35 | 0 | 0
3388 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000497/2023-2024 | 3057/1/Hug | 11/10/2023 | 0 | Resource Division | 17.17 | 0 | 0
3389 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Madhabpur W/S. Sch. TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04165/2023-2024 | 399 | 09/11/2023 | 0 | WBSEDCL | 3.86 | 0 | 0
3390 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Madhabpur PWSS, TW - II | Assistant Engineer | Junior Engineer (Civill) | BILL/04371/2023-2024 | 463 | 01/12/2023 | 0 | WBSEDCL | 8.57 | 0 | 0
3391 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MADHABPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000134/2024-2025 | 1159/ED | 14/06/2024 | 90 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0
3392 | Electrical | Arambug Sub-Division | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.12.2023 to 31.05.2024. | Assistant Engineer | Junior Engineer (Civill) | ORD/001947/2023-2024 | 876/AE-I/ED | 23/11/2023 | 182 | TRIDIP SARKAR | 0.87 | 2.4 | 10
3393 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KUMURSA Piped Water Supply Scheme underARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2024-2025 | 3463/HUG | 04/10/2024 | 60 | P. B. ENTERPRISE(PINTU BHADURI) | 53.64 | 0 | 0
3394 | Hooghly Division | Arambug Sub-Division | KUMURSA Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block, District:-Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000259/2023-2024 | 2213/Hug | 28/07/2023 | 978 | P.B. ENTERPRISE (PINTU BHADURI) | 660.63 | 421.28 | 80
3395 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002743/2024-2025 | 1151/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0
3396 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000435/2023-2024 | 3057/32/Hug | 11/10/2023 | 0 | Resource Division | 15.03 | 0 | 0
3397 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000549/2023-2024 | 3616/Hug | 06/12/2023 | 0 | Resource Division | 20.86 | 0 | 0
3398 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kumursa w/s Scheme,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18307) Application No-5004423612 Reference Id-503761600 | Assistant Engineer | Junior Engineer (Civill) | BILL/02034/2024-2025 | 513 | 21/10/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
3399 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Kumursha W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/04410/2023-2024 | 488 | 06/12/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
3400 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000234/2024-2025 | 3469/HUG | 04/10/2024 | 90 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0
3401 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELALPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000255/2024-2025 | 3525/HUG | 22/10/2024 | 30 | GITA ENTERPRISE | 31.35 | 0 | 0
3402 | Hooghly Division | Arambug Sub-Division | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 298.71 | 30
3403 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002743/2024-2025 | 1151/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0
3404 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000398/2023-2024 | 3057/52/Hug | 11/10/2023 | 0 | Resource Division | 3.38 | 0 | 0
3405 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selalpur w/s Scheme,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18596) Application No-5004135212, Reference Id-503626837 | Assistant Engineer | Junior Engineer (Civill) | BILL/00415/2024-2025 | 99 | 06/05/2024 | 0 | WBSEDCL | 7.66 | 0 | 0
3406 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Selalpur W/S. Sch. TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04166/2023-2024 | 400 | 09/11/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
3407 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELALPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000132/2024-2025 | 1157/ED | 14/06/2024 | 90 | M/S DILIP MITRA | 10.74 | 0 | 0
3408 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selalpur water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000915/2023-2024 | 3586/ED | 28/08/2023 | 551 | M/S DILIP MITRA | 21.5 | 14.35 | 30
3409 | Hooghly Division | Srirampur Sub-Division | PAYMENT TO ROAD RESTORATION TO PWD JANGIPARA GANGADHARPUR ROAD | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00686/2024-2025 | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.35 | 0 | 0
3410 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT GANGADHARPUR Z-I HW SITE AND Zone-II HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000136/2024-2025 | 425/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.68 | 95
3411 | Hooghly Division | Srirampur Sub-Division | Construction of 200 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Gangadharpur Zone - II under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000302/2024-2025 | 3674/HUG | 13/11/2024 | 45 | TOTON MONDAL | 81.06 | 0 | 0
3412 | Hooghly Division | Srirampur Sub-Division | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 469.55 | 9
3413 | Hooghly Division | Srirampur Sub-Division | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001443/2023-2024 | 116/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100
3414 | Hooghly Division | Srirampur Sub-Division | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001444/2023-2024 | 117/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100
3415 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000337/2023-2024 | 3005/10/Hug | 05/10/2023 | 0 | Resource Division | 25.89 | 0 | 0
3416 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000517/2023-2024 | 3060/5/Hug | 11/10/2023 | 0 | Resource Division | 25.93 | 0 | 0
3417 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Gangadharpur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004064346 Ref ID: 503597306 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00036/2024-2025 | 22 | 05/04/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
3418 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of November, 2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00836/2024-2025 | 237 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0
3419 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of December, 2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00837/2024-2025 | 238 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
3420 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of January,2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00838/2024-2025 | 233 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
3421 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.05.2024 to 31.05.2024 WB-02AT-8617 Bill No : 0239 Bill Date : 31/05/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00852/2024-2025 | 253 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
3422 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.04.2024 to 30.04.2024 WB-02AT-8617 Bill No : 0100 Bill Date : 30/04/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00853/2024-2025 | 250 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
3423 | Electrical | Srirampur Sub-Division | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/03/2024 to 31/03/2024 Bill No.- 1469 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01398/2024-2025 | 353 | 31/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
3424 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.07.2024 to 31.07.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01962/2024-2025 | 463 | 13/09/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
3425 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No. WB-11C-1616 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02101/2024-2025 | 563 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
3426 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.09.2024 to 30.09.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02102/2024-2025 | 564 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.15 | 0 | 0
3427 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No. WB-02AT-8617 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02302/2024-2025 | 605 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.06 | 0 | 0
3428 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charge at Gangadharpur, Zone-II, P.H. No.-II, District-Hooghly Application No.- 5004481099 Ref No.: 503803227 Scheme Code: SM/18623 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02309/2024-2025 | 611 | 05/12/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
3429 | Electrical | Srirampur Sub-Division | Gangadharpur w/s scheme,P H No 1 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04510/2023-2024 | 560 | 21/12/2023 | 0 | WBSEDCL | 3.67 | 0 | 0
3430 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Gangadharpur w/s scheme, Zone-II, PH No.-I, Hooghly. Application No.- 5004040971 Ref ID: 503579949 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06456/2023-2024 | 885 | 15/03/2024 | 0 | WBSEDCL | 5.59 | 0 | 0
3431 | Electrical | Srirampur Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000229/2024-2025 | 3054/HMSD | 20/06/2024 | 184 | SIDDHARTHA CHATTERJEE. | 0.87 | 0.17 | 0
3432 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000919/2023-2024 | 3590/ED | 28/08/2023 | 90 | GOENKA ENTERPRISE | 21.37 | 15.91 | 60
3433 | Electrical | Srirampur Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003200/2023-2024 | 2502_/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 0.43 | 0
3434 | Hooghly Division |  | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. |  |  | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 208.21 | 50
3435 | Hooghly Division |  | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
3436 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s |  |  | ORD/002746/2024-2025 | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
3437 | Hooghly Division |  | Material Requisition To Resource Division |  |  | RTOR000443/2023-2024 | 3057/28/Hug | 11/10/2023 | 0 | Resource Division | 16.38 | 0 | 0
3438 | Electrical |  | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008503 Reference Id-503559062 |  |  | BILL/06458/2023-2024 | 884 | 15/03/2024 | 0 | WBSEDCL | 8.68 | 0 | 0
3439 | Electrical |  | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008491 Reference Id-503559063 |  |  | BILL/06459/2023-2024 | 883 | 15/03/2024 | 0 | WBSEDCL | 4.21 | 0 | 0
3440 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000142/2024-2025 | 1168/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 0 | 0
3441 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000933/2023-2024 | 3612/ED | 29/08/2023 | 642 | TRIO CONCERN | 17.37 | 10.61 | 15
3442 | Hooghly Division | Chinsuria Sub-Division | Providing 1380 nos Functional Household Tap Connection (FHTC) within the command area of Puinan Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000276/2021-2022 | 2130/Hug | 01/12/2021 | 40 | TOTON MONDAL | 57.38 | 51.7 | 100
3443 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000034/2022-2023 | 1123/7/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0
3444 | Hooghly Division | Chinsuria Sub-Division | Providing 569 nos F.H.T.C. in Char Sundalpur & Abdulpur Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000296/2020-2021 | 374/Hug | 15/02/2021 | 30 | TAPAS ADHYA | 29.72 | 27.34 | 100
3445 | Hooghly Division | Chinsuria Sub-Division | Providing 446 nos F.H.T.C. in Kamardanga Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000297/2020-2021 | 375/Hug | 15/02/2021 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 23.29 | 16.02 | 100
3446 | Hooghly Division | Chinsuria Sub-Division | Laying of C.I/D.I pipes & specials for Rising main Pipeline inbetween T.W No.-I & II to O.H.R. including Bypass arrangement & interconnection with distribution system for Abdulpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000420/2021-2022 | 90/CH | 03/02/2022 | 25 | ARUN SEAL AND CO. | 2.36 | 1.8 | 100
3447 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000063/2021-2022 | 2097/3/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
3448 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000836/2021-2022 |  | 21/09/2021 | 0 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 15.6 | 0 | 0
3449 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000849/2021-2022 |  | 21/09/2021 | 0 | TAPAS ADHYA | 11.3 | 0 | 0
3450 | Central Drilling | Chinsuria Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Abdulpur W/S Scheme, Balagarh block under hooghly District, CDD PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000482/2022-2023 | 2342/CDD | 31/03/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 10.28 | 100
3451 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dumurdaha dham & Aschitpur Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000023/2022-2023 | 724/Hug | 07/04/2022 | 40 | MS PRADIP KUMAR PAL | 51.01 | 49.54 | 0
3452 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dadpur, Kamalpur, Sija & Ramnagar Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000024/2022-2023 | 725/Hug | 07/04/2022 | 40 | DAS ENTERPRISE (SAMIR DAS) | 51.08 | 50.37 | 0
3453 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of DUMURDAHA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000416/2022-2023 | 2276/HUG | 19/10/2022 | 15 | TAPAS ADHYA | 10.76 | 10.75 | 0
3454 | Hooghly Division | Chinsuria Sub-Division | Repairing of Existing O.H.R at H/W site of Dumurdaha Zone- II Water supply scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Balagarh, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000796/2023-2024 | 536/HUG | 20/02/2024 | 45 | DAS ENTERPRISE (SAMIR DAS) | 8.36 | 8.03 | 100
3455 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000015/2022-2023 | 1123/3/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0
3456 | Central Drilling | Chinsuria Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mmx200mmx150Mtrs) by utilisiling departmental rig machineries for Durmurdaha W/S Scheme, balagarh Block under Hooghly Division, CDD, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000027/2023-2024 | 62/CDD | 06/04/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 9.95 | 100
3457 | Central Drilling | Chinsuria Sub-Division | Hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000098/2023-2024 | 209/CMSD-II(D) | 25/08/2023 | 122 | SIDDHARTHA CHATTERJEE | 0.94 | 0.88 | 0
3458 | Central Drilling | Chinsuria Sub-Division | Hiring of diesel drive motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000502/2022-2023 | 45/CMSD-II(D) | 27/02/2023 | 181 | SIDDHARTHA CHATTERJEE | 0.9 | 0 | 0
3459 | Hooghly Division | Srirampur Sub-Division | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 29.61 | 9
3460 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000032/2023-2024 | 1236/Hug | 28/04/2023 | 0 | Resource Division | 25.53 | 0 | 0
3461 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000303/2023-2024 | 1384/Hug | 15/05/2023 | 0 | Resource Division | 13.1 | 0 | 0
3462 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000475/2023-2024 | 3060/Hug | 11/10/2023 | 0 | Resource Division | 12.43 | 0 | 0
3463 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jogmohanpur w/s scheme, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5003805642 Reference ID- 503409286 SM Code- 17632 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01403/2024-2025 | 347 | 31/07/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
3464 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Jagmohanpur w/s scheme, P.H. No.-I, Dist: Hooghly. Application No.-5004024656 Ref ID: 503569651 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/06264/2023-2024 | 863 | 12/03/2024 | 0 | WBSEDCL | 7.56 | 0 | 0
3465 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagmohanpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000052/2023-2024 | 1796/ED | 24/04/2023 | 648 | MASSK ENGINEERING WORKS. | 20.35 | 6.65 | 75
3466 | Hooghly Division |  | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000576/2023-2024 | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0
3467 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000610/2023-2024 | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 0 | 60
3468 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Natunchar Krishnabati Mini PWSS 2. Charkrishnabti Mini PWSS 3. Guptipara Char Mini PWSS 4. Rampur Mini PWSS 5. Raninagar Mini PWSS 6. Basantapur Mini PWSS |  |  | ORD/000830/2023-2024 | 208/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 45
3469 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001206/2023-2024 | 4484/ED | 23/11/2023 | 90 | A.S. ENTERPRISE | 21.82 | 0 | 0
3470 | Hooghly Division | Arambug Sub-Division | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000223/2023-2024 | 2035/HUG | 12/07/2023 | 270 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 36.04 | 60
3471 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for GHOLDIGRUI ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2024-2025 | 3668/HUG | 13/11/2024 | 414 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 52.78 | 0 | 0
3472 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000376/2023-2024 | 3002/5/Hug | 05/10/2023 | 0 | Resource Division | 54.23 | 0 | 0
3473 | Electrical | Arambug Sub-Division | Electric quot for Ghol Digrui Zone-II T/W-I W/S scheme | Assistant Engineer | Junior Engineer (Civill) | BILL/02719/2023-2024 | 166 | 04/08/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
3474 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Z-II, TW-II | Assistant Engineer | Junior Engineer (Civill) | BILL/03827/2023-2024 | 285 | 18/09/2023 | 0 | WBSEDCL | 3.29 | 0 | 0
3475 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000815/2023-2024 | 3160/ED | 27/07/2023 | 90 | DIPALI CONSTRUCTION | 21.49 | 21.46 | 30
3476 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002468/2023-2024 | 329/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
3477 | Hooghly Division |  | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 7.08 | 40
3478 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 14.02 | 100
3479 | Electrical |  | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004485180 Reference ID- 503806101 SM Code- 18967 v |  |  | BILL/02480/2024-2025 | 615 | 04/12/2024 | 0 | WBSEDCL | 10.74 | 0 | 0
3480 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001295/2023-2024 | 4527/ED | 23/11/2023 | 525 | DEBJYOTI BASU | 10.75 | 10.43 | 75
3481 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 60
3482 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000580/2023-2024 | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0
3483 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 13.22 | 40
3484 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000616/2023-2024 | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 12.85 | 75
3485 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001915/2024-2025 | 266/CH | 20/02/2025 | 10 | GHOSH CONSTRUCTION | 4.53 | 0 | 0
3486 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001952/2024-2025 | 274/CH | 20/02/2025 | 10 | GHOSH CONSTRUCTION | 2.58 | 0 | 0
3487 | Electrical |  | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802582 Application no- 5004479726 |  |  | BILL/02527/2024-2025 | 602 | 05/12/2024 | 0 | WBSEDCL | 19.9 | 0 | 0
3488 | Electrical |  | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802583 Application no- 5004479665 |  |  | BILL/02528/2024-2025 | 612 | 05/12/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
3489 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001243/2023-2024 | 4493/ED | 23/11/2023 | 90 | M.S. ENTERPRISE | 21.51 | 0 | 0
3490 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 40
3491 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001253/2023-2024 | 4502/ED | 23/11/2023 | 90 | DIPA CHHETRI | 11.05 | 0 | 0
3492 | Hooghly Division | Arambug Sub-Division | Augmentation of SRIRAMPUR Piped Water Supply Scheme with Sinking of 2 Nos. tube-well within ZONE-II, Construction of 600cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW sites of ZONE-I, LDS, FHTC in ZONE-I & construction of 2 Nos. switch-room & 2 Nos boundary wall, LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000289/2023-2024 | 2339/HUG | 07/08/2023 | 782 | M/S PRADYUT KUMAR HAZRA | 812.72 | 180.61 | 20
3493 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SRIRAMPUR Piped Water Supply Scheme under ARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000379/2024-2025 | 3774/HUG | 25/11/2024 | 60 | M/S SHIVAM UDYOG | 51.47 | 0 | 0
3494 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
3495 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Srirampur T/W-II W/S scheme under Electrical Division PHE Dte. (SM/18643) | Assistant Engineer | Junior Engineer (Civill) | BILL/02653/2024-2025 | 637 | 18/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
3496 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIRAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000163/2024-2025 | 1186/ED | 14/06/2024 | 90 | SOMNATH ENTERPRISE | 10.66 | 0 | 0
3497 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Srirampur water supply scheme, Zone-I, T.W. No. I and Zone-II, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001990/2023-2024 | 118/ED | 15/01/2024 | 90 | PRADIP KUMAR DHABAL | 21.51 | 0 | 0
3498 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000581/2023-2024 | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 11.16 | 20
3499 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000617/2023-2024 | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 17.31 | 20
3500 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 13.65 | 30
3501 | Hooghly Division |  | Reparing & Washing of Existing Ferrule and Laying of HDPE Pipeline From existing Distribution System for providing FHTC of Debanandapur W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. |  |  | ORD/000770/2023-2024 | 127/CH | 16/02/2024 | 15 | BIMAL KUMAR HALDER | 2.16 | 2.16 | 45
3502 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Debanandapur PWSS 2. Digsui Heora Z-I PWSS 3. Digsui Heora Z-II PWSS 4. Keota PWSS 5. Saptagram PWSS 6. Chanparui PWSS |  |  | ORD/000820/2023-2024 | 198/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3503 | Hooghly Division |  | Laying C.I/D.I & HDPE pipes & specials for rising main & interconnection of Tube well No. 7 & Distribution line at Lal Baba Asram of Debanandapur W/S under Chinsurah Sub - Division P.H.E. Dte. |  |  | ORD/000857/2025-2026 | 2833/HUG | 17/11/2025 | 60 | BIMAL KUMAR HALDER | 15.19 | 0 | 0
3504 | Hooghly Division |  | Repairing & Renovation of Switch room and Store room at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002011/2024-2025 | 297/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 3.41 | 0 | 100
3505 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002013/2024-2025 | 301/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 2.58 | 0 | 100
3506 | Electrical |  | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - I, (Near Sarat Library ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045949, Reference No. - 503581960 |  |  | BILL/06237/2023-2024 | 836 | 04/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
3507 | Electrical |  | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - II, (Manaspur near Lalbaba Ashram ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045960, Reference No. - 503581923 |  |  | BILL/06238/2023-2024 | 840 | 04/03/2024 | 0 | WBSEDCL | 20.45 | 0 | 0
3508 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001249/2023-2024 | 4498/ED | 23/11/2023 | 90 | R.N.S. TRADING | 22.03 | 10.67 | 40
3509 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000581/2023-2024 | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 20
3510 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000617/2023-2024 | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 0 | 20
3511 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Natagarh PWSS 2. Natunchar Krishnabati PWSS 3. Somra PWSS 4. Sripur Balagarh PWSS 5. Amodghata PWSS 6. Dharampur PWSS |  |  | ORD/000819/2023-2024 | 197/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3512 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002003/2024-2025 | 287/CH | 20/02/2025 | 10 | SOMNATH ADHYA | 3.03 | 0 | 0
3513 | Hooghly Division |  | Repairing & Renovation of Switch Room and Store Room at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002004/2024-2025 | 288/CH | 20/02/2025 | 10 | SOMNATH ADHYA | 3.42 | 0 | 0
3514 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001250/2023-2024 | 4499/ED | 23/11/2023 | 90 | R.M.D TRADING. | 22.05 | 0 | 0
3515 | Hooghly Division | Arambug Sub-Division | RASULPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000256/2023-2024 | 2188/HUG | 26/07/2023 | 796 | KHAN ENTERPRISE | 741.7 | 0 | 5
3516 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of RASULPUR, SHYAMBALLAVPUR , DIHIBAGNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000264/2024-2025 | 3531/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.49 | 0 | 0
3517 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RASULPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000289/2024-2025 | 3654/HUG | 13/11/2024 | 90 | BAKSHI ENTERPRISE | 16.15 | 0 | 0
3518 | Hooghly Division | Arambug Sub-Division | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0
3519 | Hooghly Division | Arambug Sub-Division | Sinking of 2 Nos. Additional tube-well at Rasulpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/002250/2024-2025 | 651/HUG | 10/03/2025 | 30 | AUXILIARY TUBEWELL DRILLERS | 29.39 | 0 | 0
3520 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Pursurah Block Junior Engineer | RTOR000400/2023-2024 | 3057/51/Hug | 11/10/2023 | 0 | Resource Division | 19.68 | 0 | 0
3521 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000161/2024-2025 | 1184/ED | 14/06/2024 | 90 | RISHAV ENTERPRISE | 10.75 | 0 | 0
3522 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000162/2024-2025 | 1185/ED | 14/06/2024 | 90 | M/S, GHOSH ENTERPRISE | 10.73 | 0 | 0
3523 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 35
3524 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0
3525 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 26.43 | 60
3526 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001858/2024-2025 | 237/CH | 19/02/2025 | 10 | TOTON MONDAL | 4.6 | 0 | 100
3527 | Hooghly Division |  | Repairing & Renovation of Switch room and Store Room at H/W Site Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001906/2024-2025 | 256/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 3.06 | 0 | 100
3528 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001907/2024-2025 | 257/CH | 20/02/2025 | 10 | TOTON MONDAL | 2.58 | 0 | 100
3529 | Electrical |  | Quotation for new service connection for source Augmentation of BELUN Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18936 ), Reference Id- 503802585 Application no- 5004479701 |  |  | BILL/02529/2024-2025 | 613 | 05/12/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
3530 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001209/2023-2024 | 4487/ED | 23/11/2023 | 709 | C.M.S. ENGINEERING CONCERN | 21.64 | 2.79 | 50
3531 | Hooghly Division |  | Providing FHTC at the left out portions of Different area for proiving FHTC in Kulihanda, Naldanga & Debanandapur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000038/2024-2025 | 540/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.85 | 4.85 | 80
3532 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 20
3533 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 50
3534 | Hooghly Division |  | Providing and installation of 150 mm x 100 mm dia. tubewell by Rig Bored system with Switch Room and allied works at Madrasi Para Under Naldanga Piped Water Supply Scheme In Chinsurah Sub-Division Of Hooghly Division, P.H.E. Dte |  |  | ORD/000669/2023-2024 | 3564/HUG | 05/12/2023 | 30 | SOUMYADIP DE | 16.51 | 12.95 | 50
3535 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Kola PWSS 2. Kulihanda PWSS 3. Madhusudanpur PWSS 4. Naldanga PWSS 5. Raghunathpur PWSS 6. Refaitpur Z-I PWSS |  |  | ORD/000821/2023-2024 | 199/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3536 | Hooghly Division |  | Construction of approach Road for Head Works site of NALDANGA piped water supply scheme in JJM under Chinsurah-Mogra Block. |  |  | ORD/002387/2024-2025 | 376/CH | 04/03/2025 | 7 | DUTTA CONSTRUCTION | 0.94 | 0 | 0
3537 | Electrical |  | Quotation for new service connection at Naldanga(S.Aug.) [SM/18954], T/W NO. - I, under Pipulpati CCC, WBSEDCL, Ref. Id. - 503644538, dt.- 14-05-2024, Application No. - 5004183039 |  |  | BILL/00539/2024-2025 | 181 | 30/05/2024 | 0 | WBSEDCL | 8.65 | 0 | 0
3538 | Electrical |  | Quotation for additional quotation for Naldanga(S.Aug.) W/s Sch., T.W. No. - VII [SM/18954], Ref Id- 860316928, Application Id. - 100000122348, dt. - 30-10-2024 |  |  | BILL/02128/2024-2025 | 567 | 13/11/2024 | 0 | WBSEDCL | 0.81 | 0 | 0
3539 | Electrical |  | Quotation for new service connection at Naldanga (Source Aug.) water supply Scheme [SM/18954], T/W No. - VI(Mini), Block - Chinsurah-Mogra, under Bandel CCC, WBSEDCL, Ref. Id. - 503582004, Dt. - 29-02-2024, Application No. - 5004045934 |  |  | BILL/06281/2023-2024 | 878 | 13/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
3540 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NALDANGA MINI W/S SCHEME, Block: Chinsura Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000169/2024-2025 | 1192/ED | 14/06/2024 | 90 | TULIP ENTERPRISE | 7.53 | 7.41 | 95
3541 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Naldanga w/s scheme, T.W No. V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001171/2023-2024 | 4444/ED | 17/11/2023 | 90 | MOITRA ENGINEERING CO. | 10.92 | 9.97 | 90
3542 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of NALDANGA piped W/S Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001278/2023-2024 | 4518/ED | 23/11/2023 | 90 | SUBHRA ENTERPRISE | 21.49 | 8.24 | 70
3543 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangment , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of GANESHBATI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000194/2023-2024 | 1779/HUG | 15/06/2023 | 30 | ROY ENTERPRISE | 12.01 | 0 | 0
3544 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir of GANESHBATI PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000293/2024-2025 | 3672/HUG | 13/11/2024 | 40 | TAPAS ADHYA | 12.36 | 0 | 0
3545 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100
3546 | Hooghly Division | Arambug Sub-Division | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at GANESHBATI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000745/2022-2023 | 656/HUG | 09/03/2023 | 45 | R CONSTRUCTION | 22.63 | 13.05 | 0
3547 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000249/2022-2023 | 1263/14/Hug | 03/05/2023 | 0 | Resource Division | 11.5 | 0 | 0
3548 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ganeshbati W/S Scheme(Aug) TW No-4 District-Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00754/2023-2024 | 42 | 17/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
3549 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Ganeshbati water supply scheme, T.W. No. I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001148/2022-2023 | 1500/ED | 28/03/2023 | 826 | ASHUTOSH DAS & CO. | 21.49 | 0 | 30
3550 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 80
3551 | Hooghly Division |  | Construction of Store room for temporary Chlorine and maintenance material storage For Pandua Block under Chinsurah Sub-Division under Hooghly Division, PHE Dte.under Chinsurah Sub Division of Hooghly Division PHE Dte. |  |  | ORD/001036/2023-2024 | 286/CH | 15/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 30
3552 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001856/2024-2025 | 235/CH | 19/02/2025 | 10 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 4.49 | 0 | 0
3553 | Hooghly Division |  | Repairing & Renovation of Switch room at PH-II of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001857/2024-2025 | 236/CH | 19/02/2025 | 10 | AYUSH ENTERPRISE | 1.36 | 0 | 0
3554 | Hooghly Division |  | Laying CI/DI pipes and specials for connection of proposed TW with existing rising main pipeline for Source AUGMENTATION Of Aymanababpur Piped Water Supply Scheme underPandua Block, District:- Hooghly |  |  | ORD/002143/2024-2025 | 357/CH | 28/02/2025 | 7 | M/S KAMALA ENTERPRISE | 1 | 0 | 0
3555 | Electrical |  | Quotation for new service connection for source Augmentation of AYMA NABABPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18941), Reference Id- 503802584 Application no- 5004479744 |  |  | BILL/02530/2024-2025 | 603 | 05/12/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
3556 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001259/2023-2024 | 4505/ED | 23/11/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 0
3557 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0
3558 | Hooghly Division |  | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Sudarshan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. |  |  | ORD/000804/2023-2024 | 148/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 50
3559 | Hooghly Division |  | Replacement of damaged pipe line with HDPE & CI/DI pipeline and Shifting House Connection from existing main to new main for smooth operation of water supply at Sudarshan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/001833/2024-2025 | 330/HUG | 05/02/2025 | 30 | RAJ CONSTRUCTION | 7.01 | 0 | 0
3560 | Electrical |  | Quotation for new service connection at Sudarshan Water Supply Scheme [SM/18949](S.Aug.),T.W. No. - III, sarangpur, Block - Polba-Dadpur, Dt. - Hooghly, under Polba CCC, Ref. Id. - 503787954, Application No. - 5004461023, Dt.-11-11-2024 |  |  | BILL/02277/2024-2025 | BP-24-25-582 | 19/11/2024 | 0 | WBSEDCL | 6.27 | 0 | 0
3561 | Hooghly Division | Srirampur Sub-Division | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) |  | ORD/000355/2020-2021 | 467/Hug | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 60.54 | 100
3562 | Hooghly Division | Srirampur Sub-Division | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) |  | ORD/000885/2020-2021 | 467/HUG | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 0 | 100
3563 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) |  | RTOR000010/2022-2023 | 1122/7/HUG | 06/06/2022 | 0 | Resource Division | 6.16 | 0 | 0
3564 | Hooghly Division | Srirampur Sub-Division | FHTC | Assistant Engineer (Civil) |  | VCH/002242/2020-2021 |  | 15/03/2021 | 0 | MLG CONSTRUCTION | 35 | 0 | 0
3565 | Hooghly Division | Srirampur Sub-Division | Placement of Fund | Assistant Engineer (Civil) |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
3566 | Hooghly Division | Chinsuria Sub-Division | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of DIGSUI HOERA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000359/2021-2022 | 120/Hug | 19/01/2022 | 30 | DAS TRADING | 41.69 | 29.43 | 100
3567 | Hooghly Division | Arambug Sub-Division | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of KISHORPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000443/2021-2022 | 461/Hug | 10/03/2022 | 30 | MS CHANDIMATA CONSTRUCTION | 26.43 | 25.98 | 0
3568 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000011/2021-2022 |  | 12/04/2021 | 0 | DULAL CHANDRA ROY | 2.67 | 0 | 0
3569 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000515/2021-2022 |  | 23/07/2021 | 0 | DULAL CHANDRA ROY | 21.01 | 0 | 0
3570 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000838/2021-2022 |  | 21/09/2021 | 0 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.08 | 0 | 0
3571 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001100/2021-2022 |  | 08/11/2021 | 0 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0
3572 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/001104/2021-2022 |  | 08/11/2021 | 0 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0
3573 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000019/2021-2022 |  | 12/04/2021 | 0 | TITAS CONSTRUCTION | 8.56 | 0 | 0
3574 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000520/2021-2022 |  | 23/07/2021 | 0 | TITAS CONSTRUCTION | 12.14 | 0 | 0
3575 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002246/2020-2021 |  | 15/03/2021 | 0 | TITAS CONSTRUCTION | 68 | 0 | 0
3576 | Hooghly Division | Arambug Sub-Division | Providing 575 nos Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000246/2021-2022 | 1997/Hug | 12/11/2021 | 40 | STP ENTERPRISE | 31.38 | 28.46 | 0
3577 | Hooghly Division | Arambug Sub-Division | Providing 650 nos Functional Household Tap Connection (FHTC) within the command area of SABALSINGHAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000342/2021-2022 | 19/Hug | 04/01/2022 | 60 | M/S R.K. CHOUDHURI | 26.47 | 0 | 0
3578 | Hooghly Division | Arambug Sub-Division | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000347/2021-2022 | 527/Arg | 30/11/2021 | 30 | P.K. GHOSH & CO. | 4.7 | 0 | 0
3579 | Hooghly Division | Arambug Sub-Division | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000540/2021-2022 | 527/ARG | 15/02/2022 | 30 | P.K. GHOSH & CO. | 4.79 | 4.79 | 0
3580 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000027/2021-2022 |  | 12/04/2021 | 0 | TITAS CONSTRUCTION | 8.56 | 0 | 0
3581 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000541/2021-2022 |  | 23/07/2021 | 0 | TITAS CONSTRUCTION | 12.14 | 0 | 0
3582 | Hooghly Division | Chandannagar Sub-Division | Providing 122 nos F.H.T.C. & extension of pipe line in left out portion of Dilalpur village of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000275/2020-2021 | 322/Hug | 11/02/2021 | 20 | BANERJEE CONSTRUCTION | 25.9 | 31.83 | 100
3583 | Hooghly Division | Chandannagar Sub-Division | Providing 158 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2020-2021 | 468/Hug | 26/02/2021 | 20 | MINTU CHAKRABORTY | 19.87 | 14.82 | 100
3584 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000004/2021-2022 |  | 06/04/2021 | 0 | BANERJEE CONSTRUCTION | 6.85 | 0 | 0
3585 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000010/2021-2022 |  | 12/04/2021 | 0 | BANERJEE CONSTRUCTION | 11.71 | 0 | 0
3586 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001889/2020-2021 |  | 29/01/2021 | 0 | MINTU CHAKRABORTY | 26.7 | 0 | 0
3587 | Hooghly Division | Chandannagar Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002298/2020-2021 |  | 15/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 35 | 0 | 0
3588 | Hooghly Division | Chandannagar Sub-Division | Placement of Fund | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0
3589 | Hooghly Division | Chinsuria Sub-Division | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2020-2021 | 1682/Hug | 17/12/2020 | 182 | TIRUPATI ENTERPRISE | 53.57 | 60.66 | 100
3590 | Hooghly Division | Chinsuria Sub-Division | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of PAUNAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000447/2021-2022 | 465/Hug | 10/03/2022 | 20 | SAMRAT CONSTRUCTION | 19.02 | 0 | 100
3591 | Hooghly Division | Chinsuria Sub-Division | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000882/2020-2021 | 1682HUG. | 17/12/2020 | 40 | TIRUPATI ENTERPRISES | 11 | 11 | 100
3592 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000586/2021-2022 |  | 17/08/2021 | 0 | TIRUPATI ENTERPRISE | 30.33 | 0 | 0
3593 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/000856/2021-2022 |  | 21/09/2021 | 0 | M/S S.G. CONSTRUCTION | 8.61 | 0 | 0
3594 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001911/2020-2021 |  | 15/02/2021 | 0 | M/S S.G. CONSTRUCTION | 47 | 0 | 0
3595 | Hooghly Division | Arambug Sub-Division | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Anandapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000270/2021-2022 | 2124/Hug | 01/12/2021 | 30 | GHOSH CONSTRUCTION | 12.06 | 10.04 | 0
3596 | Hooghly Division | Arambug Sub-Division | Providing 285 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000344/2021-2022 | 21/Hug | 04/01/2022 | 30 | ARATI ENGINEERING | 11.81 | 0 | 0
3597 | Hooghly Division | Arambug Sub-Division | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mohanpur Village under Anandapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Goghat-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000349/2021-2022 | 526/Arg | 30/11/2021 | 30 | M/S TANISHA ENTERPRISE | 4.7 | 4.81 | 0
3598 | Hooghly Division | Arambug Sub-Division | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000362/2021-2022 | 123/Hug | 19/01/2022 | 25 | M/S ROY CONSTRUCTION AND CO. | 14.88 | 0 | 100
3599 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000014/2021-2022 | 2096/11/Hug | 26/11/2021 | 0 | Resource Division | 0.82 | 0 | 0
3600 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000024/2021-2022 |  | 12/04/2021 | 0 | R AND D TRADERS | 1.5 | 0 | 0
3601 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000025/2021-2022 |  | 12/04/2021 | 0 | M/S R.M. CONSTRUCTION | 2.96 | 0 | 0
3602 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000589/2021-2022 |  | 17/08/2021 | 0 | M/S R.M. CONSTRUCTION | 14.97 | 0 | 0
3603 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/000590/2021-2022 |  | 17/08/2021 | 0 | ARATI ENGINEERING | 10.31 | 0 | 0
3604 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002258/2020-2021 |  | 15/03/2021 | 0 | R AND D TRADERS | 5 | 0 | 0
3605 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002621/2020-2021 |  | 19/03/2021 | 0 | M/S R.M. CONSTRUCTION | 18 | 0 | 0
3606 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall & Pathway Development of RAJHAT (Z-II) at 3rd T/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000276/2022-2023 | 731/CH | 26/08/2022 | 30 | SURAJ ENTERPRISE | 4.85 | 4.42 | 100
3607 | Hooghly Division | Chinsuria Sub-Division | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000467/2021-2022 | 621/CH | 20/12/2021 | 25 | BIMAL KUMAR HALDER | 4.16 | 0.86 | 100
3608 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000468/2021-2022 | 622/CH | 20/12/2021 | 40 | SURAJ ENTERPRISE | 2.44 | 2.44 | 100
3609 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000348/2023-2024 | 3004/10/Hug | 05/10/2023 | 0 | Resource Division | 2.86 | 0 | 0
3610 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipment etc. including allied works for Rajhat W/S. Sch. Z-II, TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000026/2022-2023 | 1036/ED | 28/06/2022 | 99 | INDIA ENTERPRISE | 9.21 | 9.21 | 100
3611 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-II, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000235/2022-2023 | 866/ED | 14/02/2023 | 90 | KUSHANI ENTERPRISE | 10.17 | 10.17 | 100
3612 | Electrical | Chinsuria Sub-Division | Supply & installation of LED board at Zone-II, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000600/2022-2023 | 2348/HMSD | 20/12/2022 | 10 | SUDHIKSHA CONSTRUCTION | 0.79 | 0.79 | 0
3613 | Electrical | Chinsuria Sub-Division | "Hire Charges Bill of V.No.- WB07J-3173 01.03.23 to 14.05.23" with fuel bill | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002170/2022-2023 | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.62 | 0 | 1
3614 | Electrical | Chinsuria Sub-Division | 'Hire Charges Bill of V.No.- WB07J-317301.03.23 to 14.05.23' with fuel bill | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002176/2022-2023 | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.63 | 0.63 | 1
3615 | Electrical | Chinsuria Sub-Division | Electric Supply | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | VCH/001993/2022-2023 | 14 | 07/07/2022 | 0 | WBSEDCL | 4.53 | 0 | 0
3616 | Hooghly Division | Chandannagar Sub-Division | WBSEDCL | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00029/2022-2023 | BP-2022-23-414 | 20/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0
3617 | Hooghly Division | Chandannagar Sub-Division | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR THE CHANDANPUR W/S/S | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00057/2022-2023 |  | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0
3618 | Hooghly Division | Chandannagar Sub-Division | PAYMENT IN RESPECT OF WBSEDCL TO THE ELECTRICAL DIVISION, PHE DTE. FOR THE CHANDANPUR W/S/SCH | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00122/2023-2024 | BP-2023-24-98 | 26/05/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 19.19 | 0 | 0
3619 | Hooghly Division | Chandannagar Sub-Division | PAYMENT FOR QUOTATION BILL TO WBSEDCL FOR CHANDANPUR WATER SUPPLY SCHEME UNDER CHANDANNAGORE SUB-DIVISION, PHE DTE. BILL WAS ALREADY SUBMITTED BY THE EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00140/2022-2023 | BP-2022-23-471 | 18/01/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 2.4 | 0 | 0
3620 | Hooghly Division | Chandannagar Sub-Division | Way leave Facility Charges | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00199/2022-2023 | BP-2022-23-529 | 02/02/2023 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.78 | 0 | 0
3621 | Hooghly Division | Chandannagar Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00258/2022-2023 | BP-2022-23-570 | 03/03/2023 | 0 | GOUR KUMAR DAS | 1.29 | 0 | 0
3622 | Hooghly Division | Chandannagar Sub-Division | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000088/2022-2023 | 220/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.98 | 0 | 100
3623 | Hooghly Division | Chandannagar Sub-Division | Construction of 1 no. 250 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials, and Soil Investigation works for construction of OHR and Laying Distribution System, Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work, Construction of 1 No 5.9 M X 4.1 M Switch Room with Sanitary and Water Supply Arrangements, Construction of 1 no 4.10M x 3.5M Switch Room without Sanitary & Water Supply arrangement at 2nd T/W Site including Providing 1105 nos, FHTC in Chandanpur Water Supply Scheme of HARIPAL BLOCK under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000186/2022-2023 | 1606/Hug | 05/08/2022 | 791 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 278.64 | 234.7 | 70
3624 | Hooghly Division | Chandannagar Sub-Division | Jack pushing / Horizontal direct drilling along Railway land and below Railway track for laying 600 mm dia M.S Casing Pipe,150 mm dia M.S Carrier Pipe through in between Mast no 40/1057-40/29 & 49/29A-40/30A on HWH-BWN (Chord) Section Chandanpur to Porabazar Station for Chandanpur Piped Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000343/2023-2024 | 2432/HUG | 11/08/2023 | 60 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 37.98 | 37.82 | 98
3625 | Hooghly Division | Chandannagar Sub-Division | Laying Extra D.I Pipe for Interconnection Between OHR, Head work T.W &, 2nd t.w & allied works for Chandandanpur W/S Scheme under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000349/2023-2024 | 2441/HUG | 12/08/2023 | 445 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 56.42 | 25.62 | 52
3626 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000041/2022-2023 | 1370/4/Hug | 06/07/2022 | 0 | Resource Division | 24.77 | 0 | 0
3627 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000234/2022-2023 | 109/ 17/Hug | 10/01/2023 | 0 | Resource Division | 23.6 | 0 | 0
3628 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000271/2023-2024 | 1383/23/Hug | 15/05/2023 | 0 | Resource Division | 3.45 | 0 | 0
3629 | Hooghly Division | Chandannagar Sub-Division | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | VCH/001031/2022-2023 | C092248441540 | 27/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.43 | 0 | 0
3630 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000242/2022-2023 | 2044/ED | 01/12/2022 | 90 | R.N.S. TRADING | 10.29 | 0 | 0
3631 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001223/2022-2023 | 1319/ED | 17/08/2022 | 90 | ANJAN ENTERPRISE | 9.78 | 0 | 100
3632 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BANDIPUR W/S SCHEME (TW-II), HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000143/2022-2023 | 300/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 12.84 | 11.6 | 100
3633 | Central Drilling | Chandannagar Sub-Division | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR CHANDANPUR W/S SCHEME TARAKESWAR BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000215/2021-2022 | 1295/CDD | 17/02/2022 | 30 | C.M. ENTERPRISE | 11.21 | 10.17 | 100
3634 | Central Drilling | Chandannagar Sub-Division | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING RIG MACHINE FOR CHANDANPUR W/S SCHEME UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000257/2021-2022 | 1294/CDD | 17/02/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.2 | 90
3635 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000367/2022-2023 | 377/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.63 | 0
3636 | Hooghly Division | Arambug Sub-Division | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000099/2022-2023 | 1088/HUG | 03/06/2022 | 30 | BRISTI CONSTRUCTION | 30.74 | 23.5 | 100
3637 | Hooghly Division | Arambug Sub-Division | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kapsit Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000232/2021-2022 | 1917/Hug | 27/10/2021 | 30 | S AND P CONSTRUCTION | 16.75 | 0 | 100
3638 | Hooghly Division | Arambug Sub-Division | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000446/2021-2022 | 464/Hug | 10/03/2022 | 20 | KOUSIK MONDAL | 12.26 | 12.14 | 30
3639 | Hooghly Division | Arambug Sub-Division | Providing 280 Nos FHTC TAP Connection For Kapsit PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000507/2021-2022 | 1917/Hug. | 27/10/2021 | 30 | M/S S & P CONSTRUCTION | 16.74 | 16.74 | 100
3640 | Hooghly Division | Arambug Sub-Division | Construction of Boundary wall, Pathway & Land development at the Head Work site of Kapsit W/S Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000933/2020-2021 | 1536/HUG | 24/11/2020 | 1451 | KAPTON | 13.57 | 0 | 100
3641 | Hooghly Division | Arambug Sub-Division | FHTC | Assistant Engineer | Junior Engineer (Civill) | VCH/002097/2021-2022 |  | 28/01/2022 | 0 | S AND P CONSTRUCTION | 16.74 | 0 | 0
3642 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of SAPTAGRAM W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000269/2022-2023 | 724/CH | 23/08/2022 | 45 | SRI KRISHNA ENTERPRISE | 4.97 | 4.97 | 100
3643 | Hooghly Division | Chinsuria Sub-Division | Providing 1600 nos Functional Household Tap Connection (FHTC) within the command area of Saptagram Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000547/2021-2022 | 1674/HUG | 13/09/2021 | 40 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 73.56 | 29.38 | 100
3644 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of SAPTAGRAM Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000616/2022-2023 | 2936/HUG | 28/12/2022 | 50 | STP ENTERPRISE | 48.34 | 43.73 | 90
3645 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000030/2022-2023 | 178/CMSD-I (D) | 10/06/2022 | 15 | S B S ENTERPRISE | 3.88 | 3.73 | 100
3646 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000031/2022-2023 | 176/CMSD-I (D) | 10/06/2022 | 15 | S B S ENTERPRISE | 4.85 | 4.36 | 100
3647 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000034/2022-2023 | 181/CMSD-I (D) | 20/06/2022 | 15 | M/S PRACHI ENGINEERING | 1.88 | 1.77 | 100
3648 | Central Drilling | Chinsuria Sub-Division | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT IIEST TW-I, SHIBPUR, HOWRAH DISTRICT BY UTILISING SKIILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000365/2022-2023 | 111/CMSD-I | 29/04/2022 | 15 | ASHUTOSH DAS & CO | 0.93 | 0.93 | 0
3649 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT HARIPAL (Z-I) PWSS, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000404/2022-2023 | 574/CMSD-I (D) (P-II) | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.7 | 0.06 | 0
3650 | Central Drilling | Chinsuria Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.15 | 0
3651 | Hooghly Division | Arambug Sub-Division | Repairing of Concrete Road damaged due to Laying Distribution System and Interconnection Pipeline with other allied works of SAIDPUR Zone-II Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000026/2023-2024 | 1126/HUG | 19/04/2023 | 30 | MINTU CHAKRABORTY | 35.76 | 0 | 0
3652 | Hooghly Division | Arambug Sub-Division | Augmentation of Saidpur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 600 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (2nd Call) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000051/2022-2023 | 1182/Hug | 15/06/2022 | 1200 | BANSBERIA CONSTRUCTION CO. | 600.84 | 551.71 | 92
3653 | Hooghly Division | Arambug Sub-Division | Augmentation of Saidpur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000094/2022-2023 | 1020/Hug | 27/05/2022 | 365 | MINTU CHAKRABORTY | 602.3 | 511.77 | 75
3654 | Hooghly Division | Arambug Sub-Division | Interconnection of T.W. III with LDS for AUGMENTATION of SAIDPUR ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-Arambagh, District:- Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000167/2024-2025 | 2417/HUG | 26/06/2024 | 30 | MINTU CHAKRABORTY | 25.39 | 0 | 0
3655 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0
3656 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SAIDPUR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000175/2024-2025 | 3185/HUG | 11/09/2024 | 30 | B.K ENTERPRISE | 32.31 | 0 | 0
3657 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-A) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000222/2022-2023 | 407/Arg | 07/06/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 6.85 | 0
3658 | Hooghly Division | Arambug Sub-Division | Additional survey work for preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-B) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000223/2022-2023 | 408/Arg | 07/06/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.17 | 0 | 0
3659 | Hooghly Division | Arambug Sub-Division | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000224/2024-2025 | 3435/HUG | 03/10/2024 | 90 | T.K. INTERNATIONAL | 47.2 | 0 | 0
3660 | Hooghly Division | Arambug Sub-Division | 1ST CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Arambag Sub-Division Office under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000330/2021-2022 | 2088/Hug | 25/11/2021 | 121 | PEACOCK SECURITY SERVICE | 3.38 | 0 | 0
3661 | Hooghly Division | Arambug Sub-Division | 1ST CONTINUATION ORDER FOR Deployment of 2 (two) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Kamarpukur Bunglow under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000331/2021-2022 | 2089/Hug | 25/11/2021 | 121 | PEACOCK SECURITY SERVICE | 1.69 | 0 | 0
3662 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at SAIDPUR (ZONE-I) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL - 09 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000344/2022-2023 | 1957/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.33 | 0
3663 | Hooghly Division | Arambug Sub-Division | Construction of approach road at 3rd Tube Well Site of Saidpur Zone-I Piped Water Supply Scheme under Arambagh Sub-Division , P.H.E.Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000368/2022-2023 | 614/Arg | 31/08/2022 | 20 | M/S KHAMRUI CONSTRUCTION | 1.42 | 1.37 | 0
3664 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SAIDPUR ZONE-II PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000454/2022-2023 | 2505/HUG | 22/11/2022 | 30 | OSMAN SEKH | 12.72 | 12.45 | 100
3665 | Hooghly Division | Arambug Sub-Division | Repairing of existing Switch Rooms and Construction of Boundary Wall with Internal Pathway and Drain at H/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000483/2024-2025 | 4147/HUG | 26/12/2024 | 90 | BANSBERIA CONSTRUCTION CO. | 48.83 | 0 | 0
3666 | Hooghly Division | Arambug Sub-Division | Repairing of existing Switch Rooms and Construction of Boundary Wall for HW & 2nd TW Site with Construction of Toilet at 2nd T/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000484/2024-2025 | 4148/HUG | 26/12/2024 | 90 | TANISA ENTERPRISE | 49.97 | 0 | 0
3667 | Hooghly Division | Arambug Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SODEPUR Water Supply Scheme under Arambag Sub-Division, under Hooghly Division, PHE Dte.. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000498/2021-2022 | 626/Hug | 31/03/2022 | 122 | PEACOCK SECURITY SERVICE | 4.26 | 0 | 0
3668 | Hooghly Division | Arambug Sub-Division | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components ofSrirumpore, Shyampur & Saidpur (Zone-I & II) W/S Scheme for the period of 01.12.22 to 31.12.22 under Arambag Sub- Division P.H.E Dte. SL-37 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000521/2022-2023 | 2614/HUG | 30/11/2022 | 31 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 0.83 | 0 | 0
3669 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000021/2022-2023 | 1124/2/HUG | 06/06/2022 | 0 | Resource Division | 9.24 | 0 | 0
3670 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000046/2022-2023 | 1590/1/Hug | 03/08/2022 | 0 | Resource Division | 24.64 | 0 | 0
3671 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000107/2022-2023 | 1773/41/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0
3672 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000188/2023-2024 | 1385/59/Hug | 15/05/2023 | 0 | Resource Division | 39.55 | 0 | 0
3673 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000256/2022-2023 | 127/27/Hug | 13/01/2023 | 0 | Resource Division | 39.26 | 0 | 0
3674 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Saidpur W/S. Sch. Z-II, PH-III & II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01883/2022-2023 | 218 | 27/03/2023 | 0 | WBSEDCL | 15.33 | 0 | 0
3675 | Electrical | Arambug Sub-Division | Power Connection for Saidpur W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000002/2022-2023 | 5003400960/Quot/03 | 11/07/2022 | 365 | WBSEDCL | 13.34 | 0 | 0
3676 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Saidpur water supply scheme Zone I TW No I and Zone II TW No I Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000225/2022-2023 | 856/ED | 14/02/2023 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.48 | 20.91 | 65
3677 | Electrical | Arambug Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. including allied works for Saidpur W/S. Sch. Z-I, TW-III. Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001142/2022-2023 | 1038/ED | 28/06/2022 | 90 | P.K. ENGINEERING | 10.19 | 9.86 | 0
3678 | Electrical | Arambug Sub-Division | Electric Supply | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | VCH/001994/2022-2023 | 15 | 15/07/2022 | 0 | WBSEDCL | 13.34 | 0 | 0
3679 | Central Drilling | Arambug Sub-Division | SINKING OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR SAIDPUR W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000212/2021-2022 | 1297/CDD | 17/02/2022 | 30 | PADMA ENGINEERING & CO. | 14.58 | 11.25 | 0
3680 | Central Drilling | Arambug Sub-Division | DEFIXING, DISMOUNTING AND DISMANTLING THE MUD PUMP OIL CHAMBER, FLUID CHAMBER, PTO FOR RIG MACHINE JOHN/DR/1000 (MUD PUMP) UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000272/2021-2022 | 141/CMSD-I | 23/08/2021 | 7 | PADMA ENGINEERING & CO. | 0.11 | 0.11 | 0
3681 | Central Drilling | Arambug Sub-Division | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 2.39 | 0
3682 | Hooghly Division | Srirampur Sub-Division | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Shyamsundarpur & Kalyanbati Mouza, Repairing of existing OHR, Switch Rooms (H/W & 2ND T.W Site) & Construction of Boundary wall at H/W Site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000044/2022-2023 | 828/Hug | 20/04/2022 | 60 | ARUN SEAL AND CO. | 155.99 | 149.62 | 30
3683 | Hooghly Division | Srirampur Sub-Division | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Construction of boundary wall at 2nd TW site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000045/2022-2023 | 829/Hug | 20/04/2022 | 30 | DAS ENTERPRISE (SAMIR DAS) | 84.14 | 80.13 | 30
3684 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Aniya Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000395/2021-2022 | 288/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 3.22 | 3.19 | 100
3685 | Hooghly Division | Srirampur Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Seakhala PWSS 2. Aniya PWSS 3. Dudhkalmi PWSS 4. Nababpur PWSS 5. Gangadharpur PWSS 6. Kumirmora PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000939/2023-2024 | 109/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 80
3686 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000003/2022-2023 | 1122/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0
3687 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000036/2022-2023 | 1291/Hug | 24/06/2022 | 0 | Resource Division | 6.16 | 0 | 0
3688 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000063/2022-2023 | 1689/HUG | 22/08/2022 | 0 | Resource Division | 0.87 | 0 | 0
3689 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000121/2022-2023 | 2210/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
3690 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000159/2021-2022 | 422/4/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0
3691 | Hooghly Division | Arambug Sub-Division | Tantisal W/S scheme with LDS Rising mainFHTC workPump House(5.9mx4.1m) with sanitary w/s arrangementsPump house(4.1mx3.5m)450 cum capacityOHR with20 mtr. staging height including soil investigation at Khanakul-IBlockin ArambaghSub-Divn, Dist-Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000003/2022-2023 | 640/Hug | 01/04/2022 | 12 | PRASUN ENTERPRISE (PRASUN BISWAS) | 464.21 | 376.55 | 25
3692 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at H/W SITE OF TANTISAL PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 11 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000355/2022-2023 | 2013/HUG | 13/09/2022 | 30 | PRASUN ENTERPRISE (PRASUN BISWAS) | 11.75 | 10.45 | 0
3693 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000076/2023-2024 | 1234/38/Hug | 28/04/2023 | 0 | Resource Division | 17.89 | 0 | 0
3694 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000154/2023-2024 | 1385/25/Hug | 15/05/2023 | 0 | Resource Division | 17.73 | 0 | 0
3695 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000413/2023-2024 | 3057/44/Hug | 11/10/2023 | 0 | Resource Division | 17.73 | 0 | 0
3696 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Tantisal W/S Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01894/2022-2023 | 226 | 29/03/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
3697 | Electrical | Arambug Sub-Division | Quotation for New Service Connection for Tantisal water Supply Scheme,TW No-II, Block-Khanakul-I,Dist-Hooghly under ED PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03620/2023-2024 | 221 | 25/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
3698 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Tantisal water supply scheme, T.W. No. I & II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000103/2022-2023 | 3478/ED | 30/12/2022 | 90 | GHOSE ENGINEERING SYNDICATE | 22.37 | 21.99 | 60
3699 | Central Drilling | Arambug Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for tantisal W/S Scheme (TW-I), Khanakul-II block under hooghly District, CDD PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000019/2023-2024 | 11/CDD | 04/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 11.14 | 10.4 | 100
3700 | Hooghly Division | Arambug Sub-Division | Augmentation of ANUR (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room, Boundary Wall of 3rd T.W. Site at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000096/2022-2023 | 1087/Hug | 02/06/2022 | 40 | M/S SHIVAM UDYOG | 81.78 | 69.32 | 100
3701 | Hooghly Division | Arambug Sub-Division | Sinking of I (one) No Big dia tube well (250 mm X150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 4th TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000143/2022-2023 | 1414/HUG | 12/07/2022 | 30 | OSMAN SEKH | 8.6 | 8.44 | 100
3702 | Hooghly Division | Arambug Sub-Division | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof ANUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000172/2024-2025 | 3168/HUG | 10/09/2024 | 30 | KALPATARU ENTERPRISE | 32.25 | 0 | 0
3703 | Hooghly Division | Arambug Sub-Division | Augmentation of ANUR (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Repairing of Switch room, Boundary wall, existing OHR at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000185/2022-2023 | 1600/Hug | 04/08/2022 | 75 | SIBSANKAR CHOWDHURY | 200.45 | 127.81 | 40
3704 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of ANUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000379/2021-2022 | 610/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.48 | 3.48 | 100
3705 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SAOTA PWSS- 3nos (2) ANUR PWSS- 3nos (3) Badanganj PWSS (Z- I)- 4nos (4) Badanganj PWSS (Z- II)-4nos | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000416/2024-2025 | 808/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100
3706 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000445/2024-2025 | 4086/HUG | 19/12/2024 | 90 | DHIRENDRA ENGINEERING & CONSTRUCTION | 9.58 | 0 | 0
3707 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ANUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000453/2022-2023 | 2503/HUG | 22/11/2022 | 30 | M/S SHIVAM UDYOG | 12.72 | 10.81 | 0
3708 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000049/2022-2023 | 1590/4/Hug | 03/08/2022 | 0 | Resource Division | 18.48 | 0 | 0
3709 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000089/2022-2023 | 1773/23/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
3710 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000149/2023-2024 | 1385/20/Hug | 15/05/2023 | 0 | Resource Division | 2.3 | 0 | 0
3711 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000160/2021-2022 | 424/1/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0
3712 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at kamarpukur,Anur w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004182874 Reference ID- 503645387 SM Code- 09698 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00484/2024-2025 | 147 | 22/05/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
3713 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Annur W/S. Sch. Z-II, PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00912/2022-2023 | 186 | 13/03/2023 | 0 | WBSEDCL | 4.44 | 0 | 0
3714 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000194/2022-2023 | 820/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 10.75 | 0
3715 | Hooghly Division | Chandannagar Sub-Division | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, Rising Main, FHTC For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000091/2023-2024 | 1355/HUG | 12/05/2023 | 720 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 419.11 | 90.43 | 60
3716 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of BARAKAMALPUR (ZONE-I) Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000092/2023-2024 | 1356/HUG | 12/05/2023 | 904 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 310.94 | 42.31 | 80
3717 | Hooghly Division | Chandannagar Sub-Division | Route survey Design drawing & DPR preparation of Barakamalpur Zone- I & II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000171/2022-2023 | 266/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.98 | 4.98 | 0
3718 | Hooghly Division | Chandannagar Sub-Division | Route survey Design drawing & DPR preparation of Barakamalpur Zone- III & IV PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000173/2022-2023 | 267/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.71 | 4.69 | 0
3719 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.85 | 100
3720 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system including Laying of additional pipe line at molla-simla & pahalanpur mouza For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. Block SINGUR, District-Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000303/2024-2025 | 3661/HUG | 13/11/2024 | 180 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 59.69 | 5.35 | 70
3721 | Hooghly Division | Chandannagar Sub-Division | Construction of 900 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, LDS, Rising Main, FHTC & Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000316/2023-2024 | 2391/HUG | 10/08/2023 | 869 | P.B. ENTERPRISE (PINTU BHADURI) | 1034.2 | 312.15 | 15
3722 | Hooghly Division | Chandannagar Sub-Division | Horizontal road crossing by trenchless method & parallel shifting of distribution pipe line at Ghanashyampur, Kamarkundu, Bora telermore, Sheetpara -Borai Beside NH12 Within Kamarpukur & Barakamalpur PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000462/2022-2023 | 2523/HUG | 23/11/2022 | 30 | SURAJIT SINGHA RAY | 25.39 | 25.37 | 0
3723 | Hooghly Division | Chandannagar Sub-Division | Balance Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme underChandannagarSub-Division of Hooghly Division P.HE Dte. Block SINGUR,District:-Hooghly[AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000503/2023-2024 | 2902/HUG | 21/09/2023 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 96.84 | 96.75 | 100
3724 | Hooghly Division | Chandannagar Sub-Division | Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000538/2023-2024 | 3105/HUG | 13/10/2023 | 597 | T.K. INTERNATIONAL | 54.41 | 36.42 | 75
3725 | Hooghly Division | Chandannagar Sub-Division | Laying D.I Pipe& HDPE Pipe For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000547/2023-2024 | 3117/HUG | 16/10/2023 | 90 | SURAJIT SINGHA RAY | 91.89 | 91.72 | 80
3726 | Hooghly Division | Chandannagar Sub-Division | Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III)PipedWater Supply Scheme under ChandannagarSub-Division of Hooghly Division P.HEDte.Block SINGUR, District:-Hooghly[AUGMENTATIONSCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000550/2023-2024 | 3153/HUG | 17/10/2023 | 90 | M/S KAUSAR CONSTRUCTION | 93.46 | 93.41 | 100
3727 | Hooghly Division | Chandannagar Sub-Division | Laying of UPVC pipe for crossing through culvert below National Highway - 2 including repairing of damage AC pipe for providing water supply at BORAI under BoraKamalpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000617/2022-2023 | 214/chan | 13/04/2022 | 15 | G.K ENTERPRISE (GOUR KUMAR DAS) | 1.7 | 1.7 | 0
3728 | Hooghly Division | Chandannagar Sub-Division | AUGMENTATION of BARAKAMALPUR (ZONE-IV) Piped Water Supply Scheme with LDS, FHTC, Sinking of Tube Well & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000789/2022-2023 | 889/HUG | 27/03/2023 | 717 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 98.75 | 0 | 50
3729 | Hooghly Division | Chandannagar Sub-Division | Withdrawing & relaying of distribution main at H/W site of Bora -Kamalpur (Zone - II) W/S Scheme under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000865/2023-2024 | 758/HUG | 05/03/2024 | 15 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.98 | 2.97 | 100
3730 | Hooghly Division | Chandannagar Sub-Division | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 15.88 | 100
3731 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000145/2022-2023 | 2686/12/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0
3732 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000189/2022-2023 | 79/14/Hug | 06/01/2023 | 0 | Resource Division | 320.94 | 0 | 0
3733 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000213/2023-2024 | 1383/16/Hug | 15/05/2023 | 0 | Resource Division | 77.76 | 0 | 0
3734 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000270/2022-2023 | 902/7/Hug | 27/03/2023 | 0 | Resource Division | 34.55 | 0 | 0
3735 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Barakamalpur W/S Sch.[SM/12369], Zone - IV, T/W No. - I, (Gobindapur Dulepara), Block - Singur, Dt. - Hooghly under Nasibpur CCC, WBSEDCL, Ref. Id. - 503600456, Dated - 22-03-2024, Application No. - 5004079502 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00012/2024-2025 | 12 | 04/04/2024 | 0 | WBSEDCL | 2.81 | 0 | 0
3736 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for Barakamalpur , Zone - III, T/W - I, Block Singur, Dist - hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02760/2023-2024 | 173 | 10/08/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
3737 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Barakamalpur W/S Sch., Zone - II, T/W - III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04127/2023-2024 | 385 | 25/10/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
3738 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-II, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04131/2023-2024 | 384 | 25/10/2023 | 0 | WBSEDCL | 5.89 | 0 | 0
3739 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04170/2023-2024 | 404 | 09/11/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
3740 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04171/2023-2024 | 403 | 09/11/2023 | 0 | WBSEDCL | 3.93 | 0 | 0
3741 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Bora Kamalpur PWSS, Zone-II, TW - VI | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04483/2023-2024 | 532 | 15/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
3742 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-I, TW-I & TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04690/2023-2024 | 665 & 666 | 11/01/2024 | 0 | WBSEDCL | 10.85 | 0 | 0
3743 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04855/2023-2024 | 766 | 16/02/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
3744 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05993/2023-2024 | 805 | 27/02/2024 | 0 | WBSEDCL | 5.78 | 0 | 0
3745 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for BARAKAMALPUR water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001365/2022-2023 | 1371/ED | 14/03/2023 | 365 | M/S S.S. ENTERPRISE | 130.31 | 98.37 | 70
3746 | Hooghly Division | Chinsuria Sub-Division | Shifting House Connection from existing main to new main and allied works from Bispara to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000030/2024-2025 | 532/CH | 14/06/2024 | 7 | R.K. TRADERS | 4.85 | 0 | 75
3747 | Hooghly Division | Chinsuria Sub-Division | Shifting House Connection from existing main to new main and allied works from Kuntighat More of Bispara of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000039/2024-2025 | 541/CH | 14/06/2024 | 7 | R.K. TRADERS | 4.84 | 0 | 75
3748 | Hooghly Division | Chinsuria Sub-Division | Shifting HDPE pipeline and allied works from Kuntighat to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000040/2024-2025 | 542/CH | 14/06/2024 | 7 | R.K. TRADERS | 3.15 | 0 | 75
3749 | Hooghly Division | Chinsuria Sub-Division | Special Repairing, maintenance work of damaged R.C.C. Elevated Reservoir of Capacity 1,36,200 litre of Raghunathpur & Damra Water Supply Scheme under Chinsurah Sub - Division of Hooghly Division, P.H.E. Dte. SL NO - 03 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000285/2022-2023 | 1906/HUG | 05/09/2022 | 45 | M/S SHIVAM UDYOG | 25.15 | 25.12 | 0
3750 | Hooghly Division | Chinsuria Sub-Division | Dismantaling of old damaged Switch room at Ragunathpur 3rd Tube well site of Agumentation of Raghunathpur W/S Scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000303/2023-2024 | 690/CH | 27/07/2023 | 10 | SRI KRISHNA ENTERPRISE | 0.31 | 0.31 | 100
3751 | Hooghly Division | Chinsuria Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RAGHUNATHPUR(Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 01 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000339/2022-2023 | 1953/HUG | 07/09/2022 | 45 | ARUN SEAL AND CO. | 23.79 | 23 | 0
3752 | Hooghly Division | Chinsuria Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RGHUNATHPUR(Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 02 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000340/2022-2023 | 1954/HUG | 07/09/2022 | 45 | DAS ENTERPRISE (SAMIR DAS) | 23.78 | 22.92 | 0
3753 | Hooghly Division | Chinsuria Sub-Division | Augmentation of Raghunathpur (ZONE-II) with LDS, FHTC, Laying Rising Main & Interconnection with Distribution system at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division P.H.E Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000384/2022-2023 | 1572/HUG | 01/08/2022 | 40 | DAS ENTERPRISE (SAMIR DAS) | 96.59 | 87.61 | 50
3754 | Hooghly Division | Chinsuria Sub-Division | Augmentation of Raghunathpur (ZONE-I) with LDS, FHTC, Rising Main & Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000403/2022-2023 | 2172/HUG | 28/09/2022 | 1380 | PRADIP KUMAR ADHYA | 433.19 | 235.24 | 55
3755 | Hooghly Division | Chinsuria Sub-Division | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.12.2022 to 31.12.2022 under Chinsurah Sub- Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000494/2022-2023 | 2593/HUG | 30/11/2022 | 31 | M/S BISWAS CONSTRUCTION | 0.49 | 0 | 0
3756 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Raghunathpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000565/2021-2022 | 129/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.13 | 4.12 | 0
3757 | Hooghly Division | Chinsuria Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of RAGHUNATHPUR Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000600/2023-2024 | 3315/HUG | 10/11/2023 | 45 | DIBYENDU DHARA | 8.56 | 7.98 | 65
3758 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000707/2022-2023 | 444/HUG | 16/02/2023 | 45 | SHREEOM ENTERPRISE | 6.29 | 6.29 | 0
3759 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000708/2022-2023 | 445/HUG | 16/02/2023 | 60 | DAS TRADING | 12.25 | 12.25 | 100
3760 | Hooghly Division | Chinsuria Sub-Division | 3rd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.01.23 to 31.08.22 under Chinsurah Sub- Division P.H.E Dte. SL-15 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000817/2022-2023 | 2974/HUG | 30/12/2022 | 243 | M/S BISWAS CONSTRUCTION | 3.96 | 0 | 0
3761 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000125/2022-2023 | 2211/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
3762 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000230/2022-2023 | 226/8/Hug | 24/01/2023 | 0 | Resource Division | 59.6 | 0 | 0
3763 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000284/2023-2024 | 1383/31/Hug | 15/05/2023 | 0 | Resource Division | 17.69 | 0 | 0
3764 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00777/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 6.07 | 0 | 0
3765 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00778/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 5.95 | 0 | 0
3766 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00780/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 8.32 | 0 | 0
3767 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00781/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 2.64 | 0 | 0
3768 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Raghunathpur water supply scheme TW No I II III and IV, Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000224/2022-2023 | 855/ED | 14/02/2023 | 90 | D. K. ELECTRIC | 42.97 | 42.89 | 95
3769 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 0 | 90
3770 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002165/2022-2023 | 2382/HMSD | 27/12/2022 | 121 | BHOLA DEY | 1.11 | 1.11 | 1
3771 | Central Drilling | Chinsuria Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000121/2022-2023 | 289/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.73 | 0
3772 | Central Drilling | Chinsuria Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000122/2022-2023 | 288/CDD | 01/06/2022 | 15 | C.M. ENTERPRISE | 3.07 | 2.9 | 0
3773 | Central Drilling | Chinsuria Sub-Division | SUPPLY & DELIVERY CONSUMBLES SITE FOR CONSTRUCTION OF TUBE WELL AT RAGHUNATHPUR W/S SCH TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000123/2022-2023 | 290/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 2.45 | 2.4 | 0
3774 | Hooghly Division | Chandannagar Sub-Division | Road Restoration of Anandanagar Health Centre Road | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01810/2023-2024 | BP-2024-25-2 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 11.11 | 0 | 0
3775 | Hooghly Division | Chandannagar Sub-Division | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed 3rd TW site at Nanda Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000029/2025-2026 | 1174/HUG | 02/05/2025 | 90 | PRASUN ENTERPRISE (PRASUN BISWAS) | 30.43 | 0 | 0
3776 | Hooghly Division | Chandannagar Sub-Division | Laying balance pipeline and other allied works at NANDA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000030/2025-2026 | 1175/HUG | 02/05/2025 | 60 | PRASUN ENTERPRISE (PRASUN BISWAS) | 44.68 | 0 | 0
3777 | Hooghly Division | Chandannagar Sub-Division | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 16.06 | 100
3778 | Hooghly Division | Chandannagar Sub-Division | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NANDA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000746/2022-2023 | 682/HUG | 10/03/2023 | 902 | PRASUN ENTERPRISE (PRASUN BISWAS) | 614.2 | 328.83 | 85
3779 | Hooghly Division | Chandannagar Sub-Division | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.14 | 100
3780 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000040/2023-2024 | 1235/1/Hug | 28/04/2023 | 0 | Resource Division | 75.7 | 0 | 0
3781 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000192/2022-2023 | 109/2/Hug | 10/01/2023 | 0 | Resource Division | 65.22 | 0 | 0
3782 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000263/2022-2023 | 902/1/Hug | 27/03/2023 | 0 | Resource Division | 14.85 | 0 | 0
3783 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000383/2023-2024 | 3058/2/Hug | 11/10/2023 | 0 | Resource Division | 14.85 | 0 | 0
3784 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for Nanda W/s Sch., H/W Site(T/W No.- I), Dist - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01921/2023-2024 | 88 | 12/07/2023 | 0 | WBSEDCL | 7.92 | 0 | 0
3785 | Electrical | Chandannagar Sub-Division | Additional Quotation for Nanda W/S Sch., T/W no. - I, Block - Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02869/2023-2024 | 196 | 17/08/2023 | 0 | WBSEDCL | 0.43 | 0 | 0
3786 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nanda W/S Sch., T/W No. - II, District - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03889/2023-2024 | 301 | 22/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
3787 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nanda water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000165/2022-2023 | 3499/ED | 30/12/2022 | 90 | RAJIB COMPANY | 21.48 | 21.45 | 95
3788 | Hooghly Division | Arambug Sub-Division | Laying Distribution main by HDD process with HDPE pipe at Mayapur Z1, Kelepara, Krishnanagar Z1 & Z2 W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000228/2024-2025 | 3438/HUG | 03/10/2024 | 360 | MS PRADIP KUMAR PAL | 15.93 | 0 | 40
3789 | Hooghly Division | Arambug Sub-Division | KELEPARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000262/2023-2024 | 2236/HUG | 01/08/2023 | 270 | M/S R K ENTERPRISE | 502.36 | 87.56 | 10
3790 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000227/2022-2023 | 127/33/Hug | 13/01/2023 | 0 | Resource Division | 40.69 | 0 | 0
3791 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000450/2023-2024 | 3057/24/Hug | 11/10/2023 | 0 | Resource Division | 10.79 | 0 | 0
3792 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Kelepara T/W-II W/S scheme under Electrical Division PHE Dte. (SM/12232) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01616/2024-2025 | 375 | 12/08/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
3793 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kelepara water supply scheme, T.W. No.- I & II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000158/2022-2023 | 3494/ED | 30/12/2022 | 900 | PADMA ENGINEERING CO. | 20.47 | 0 | 30
3794 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KELEPARA PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000164/2024-2025 | 1188/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0
3795 | Hooghly Division | Hooghly Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/00080/2022-2023 | BP-2022-23-434 | 30/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 151.83 | 0 | 0
3796 | Hooghly Division | Hooghly Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | RTOR000230/2023-2024 | 1386/9/Hug | 15/05/2023 | 0 | Resource Division | 6.78 | 0 | 0
3797 | Hooghly Division | Hooghly Division | MINI WATER SUPPLY SCHEME | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | VCH/000966/2022-2023 |  | 13/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 786.94 | 0 | 0
3798 | Hooghly Division | Hooghly Division | REQUISITION FOR SAJAL GRAM | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | VCH/001007/2022-2023 |  | 15/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 350.65 | 0 | 0
3799 | Hooghly Division | Hooghly Division | REQUISITION FOR SAJAL GRAM | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | VCH/001042/2022-2023 | C092250848485 | 28/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 350.65 | 0 | 0
3800 | Hooghly Division | Srirampur Sub-Division | BISHNUPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000775/2022-2023 | 749/Hug | 15/03/2023 | 749 | TOTON MONDAL | 232.56 | 158.88 | 92
3801 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000173/2022-2023 | 792/2/Hug | 06/01/2023 | 0 | Resource Division | 2.91 | 0 | 0
3802 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000309/2023-2024 | 1384/6/Hug | 16/05/2023 | 0 | Resource Division | 2.91 | 0 | 0
3803 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | RTOR000496/2023-2024 | 3060/16/Hug | 11/10/2023 | 0 | Resource Division | 2.91 | 0 | 0
3804 | Electrical | Srirampur Sub-Division | Bishnupur water supply scheme, P H No -I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/02286/2023-2024 | 141 | 25/07/2023 | 0 | WBSEDCL | 3.39 | 0 | 0
3805 | Electrical | Srirampur Sub-Division | Bishnupur water supply scheme,PH No-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/02310/2023-2024 | 144 | 26/07/2023 | 0 | WBSEDCL | 2.89 | 0 | 0
3806 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000138/2022-2023 | 3486/ED | 30/12/2022 | 90 | BARMAN ROY TRADERS | 20.46 | 19.87 | 85
3807 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000172/2024-2025 | 1195/ED | 14/06/2024 | 706 | MAA KALI ENTERPRISE | 10.7 | 0 | 40
3808 | Hooghly Division | Srirampur Sub-Division | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000139/2024-2025 | 427/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 95
3809 | Hooghly Division | Srirampur Sub-Division | JAGANNATHPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000263/2023-2024 | 2237/HUG | 01/08/2023 | 548 | SIBSANKAR CHOWDHURY | 584.82 | 224.7 | 40
3810 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000171/2022-2023 | 79/5/Hug | 06/01/2023 | 0 | Resource Division | 13.26 | 0 | 0
3811 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000314/2023-2024 | 1384/11/Hug | 15/05/2023 | 0 | Resource Division | 13.26 | 0 | 0
3812 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000505/2023-2024 | 3060/18/Hug | 11/10/2023 | 0 | Resource Division | 13.26 | 0 | 0
3813 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Jagannathpur W/S. Sch.PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04609/2023-2024 | 607 | 04/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
3814 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Jagganathpur W/S. Sch. PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04639/2023-2024 | 621 | 08/01/2024 | 0 | WBSEDCL | 6.73 | 0 | 0
3815 | Electrical | Srirampur Sub-Division | Quotation Bill for Suplimentary Quotation for NSC Jagannathpur W/S. Sch PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05298/2023-2024 | 695 | 22/01/2024 | 0 | WBSEDCL | 0.06 | 0 | 0
3816 | Electrical | Srirampur Sub-Division | Quotation for New service connection at Jagannathpur W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06221/2023-2024 | 825 | 01/03/2024 | 0 | WBSEDCL | 10.23 | 0 | 0
3817 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathpur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000148/2022-2023 | 3491/ED | 30/12/2022 | 848 | BISALAXMI ENTERPRISE | 20.31 | 17.69 | 50
3818 | Hooghly Division | Arambug Sub-Division | Construction of supporting arrangement for LDS and allied works of GHORADAHA Piped Water Supply Scheme under Arambag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000060/2024-2025 | 2407/HUG | 26/06/2024 | 270 | DILIP KUMAR GHOSH | 17.92 | 0 | 75
3819 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of Ghoradaha Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000100/2022-2023 | 390/Arg | 31/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.34 | 0
3820 | Hooghly Division | Arambug Sub-Division | Laying of Additional pipe line for Augmentation of GHORADAHA water Supply Scheme under, Arambagh Sub Division,of Hooghly Division PHE Dte. (Khanakul - II Block) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000306/2024-2025 | 3662/HUG | 13/11/2024 | 270 | M/S T.K.B. CONSTRUCTION | 79.95 | 0 | 50
3821 | Hooghly Division | Arambug Sub-Division | Augmentation of GHORADAHA Piped Water Supply Scheme by Sinking of 2 Nos. Tube well, Laying Distribution System, Construction of 2 Nos. Switch Room at 3rd & 4th Tubewell site and Boundary wall at 2nd, 3rd & 4th Tubewell site under Arambag Sub-Division of Hooghly Division PHE Dte. within Khanakul - II Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000702/2022-2023 | 396/HUG | 10/02/2023 | 90 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 202.79 | 137.89 | 20
3822 | Hooghly Division | Arambug Sub-Division | Augmentation of GHORADAHA Piped Water Supply Scheme with Construction of Boundary wall at 1st T.W Site, Repairing of Switch room, Laying of Rising main with necessary interconnection with T.W. & Distribution System & Functional Household tap Connection under Arambag SUb-Division of Hooghly Division, PHE Dte. within Khanakul -II Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000716/2022-2023 | 493/HUG | 20/02/2023 | 90 | DILIP KUMAR GHOSH | 149.07 | 110.91 | 25
3823 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000029/2023-2024 | 1234/10/Hug | 28/04/2023 | 0 | Resource Division | 17.59 | 0 | 0
3824 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000150/2023-2024 | 1385/21/Hug | 15/05/2023 | 0 | Resource Division | 19.81 | 0 | 0
3825 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03627/2023-2024 | 220 | 25/08/2023 | 0 | WBSEDCL | 6.53 | 0 | 0
3826 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04140/2023-2024 | 390 | 02/11/2023 | 0 | WBSEDCL | 8.75 | 0 | 0
3827 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000212/2022-2023 | 839/ED | 14/02/2023 | 838 | M/S S R ENTERPRISE | 21.49 | 11.63 | 15
3828 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000337/2023-2024 | 2420/HUG | 11/08/2023 | 60 | M/S T.K.B. CONSTRUCTION | 41.15 | 18.21 | 70
3829 | Hooghly Division | Chandannagar Sub-Division | SIRAZPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 350 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000486/2022-2023 | 2897/HUG | 22/12/2022 | 180 | PRASUN ENTERPRISE (PRASUN BISWAS) | 489.75 | 163.38 | 19
3830 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach Road at SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000505/2023-2024 | 2903/HUG | 21/09/2023 | 30 | M/S T.K.B. CONSTRUCTION | 13.8 | 4.14 | 50
3831 | Hooghly Division | Chandannagar Sub-Division | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of SIRAZPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000670/2022-2023 | 164/HUG | 16/01/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 28.19 | 28.13 | 100
3832 | Hooghly Division | Chandannagar Sub-Division | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of SIRAZPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000709/2022-2023 | 446/HUG | 16/02/2023 | 60 | M/S T.K.B. CONSTRUCTION | 12.21 | 12.21 | 85
3833 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Sirazpur 2nd T/W site & Kolachora PWSS under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000933/2023-2024 | 279/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100
3834 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000225/2022-2023 | 109/ 14/Hug | 10/01/2023 | 0 | Resource Division | 58.72 | 0 | 0
3835 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000271/2022-2023 | 902/13/Hug | 27/03/2023 | 0 | Resource Division | 12.82 | 0 | 0
3836 | Electrical | Chandannagar Sub-Division | Quotation for new service connection of Sirazpur w/s scheme,PH No-I Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02002/2023-2024 | 112 | 19/07/2023 | 0 | WBSEDCL | 5.08 | 0 | 0
3837 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Uttar Sirazpur W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04327/2023-2024 | 443 | 24/11/2023 | 0 | WBSEDCL | 5.56 | 0 | 0
3838 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sirazpur water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000121/2022-2023 | 3477/ED | 30/12/2022 | 90 | DIPALI CONSTRUCTION | 21.47 | 21.09 | 30
3839 | Hooghly Division | Chinsuria Sub-Division | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Sripur Balagar Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000292/2021-2022 | 2203/Hug | 14/12/2021 | 60 | MALLIKA ENTERPRISE | 46.52 | 30.15 | 0
3840 | Hooghly Division | Arambug Sub-Division | Bhabapur Mini PWSS | Assistant Engineer | Arambag Block Junior Engineer (Civill) | BILL/00772/2024-2025 |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0
3841 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | RTOR000183/2023-2024 | 1385/54/Hug | 15/05/2023 | 0 | Resource Division | 0.48 | 0 | 0
3842 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Cheragram Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000563/2021-2022 | 146/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.48 | 4.44 | 0
3843 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 no. 300 X200 mm dia Replacement Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Cheragram W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000670/2023-2024 | 3593/HUG | 05/12/2023 | 30 | OSMAN SEKH | 16.05 | 0 | 100
3844 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation in ZONE-I & II, Sinking of tube-well, LDS, Rising Main, FHTC, construction of switch-room & boundary wall in ZONE-I & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones, LDS, Rising Main, FHTC in ZONE-II for Augmentation of CHERAGRAM Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000724/2022-2023 | 561/HUG | 27/02/2023 | 795 | TAPU SAHA | 543.92 | 410.67 | 98
3845 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001550/2024-2025 | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0
3846 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000233/2022-2023 | 226/4/Hug | 24/01/2023 | 0 | Resource Division | 20.31 | 0 | 0
3847 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000234/2023-2024 | 1386/13/Hug | 15/05/2023 | 0 | Resource Division | 13.66 | 0 | 0
3848 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000534/2023-2024 | 3059/33/Hug | 11/10/2023 | 0 | Resource Division | 13.66 | 0 | 0
3849 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Cheragram W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05063/2023-2024 | 683 | 19/01/2024 | 0 | WBSEDCL | 13.03 | 0 | 0
3850 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Cheragram water supply scheme, T.W. No.- I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000204/2022-2023 | 831/ED | 14/02/2023 | 90 | INDRAJIT MITRA | 10.98 | 10.68 | 57
3851 | Hooghly Division | Chinsuria Sub-Division | Regarding damage of PMGSY Road | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00361/2024-2025 | BP-2024-25-294 | 10/07/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9.93 | 0 | 0
3852 | Hooghly Division | Chinsuria Sub-Division | DAMAGED PIPELINE OF PMGSY ROAD FROM RUHIA TO MAJINAN VIA SHIBAICHANDI RAILWAY STATION UNDER DHANIAKHALI BLOCK | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00932/2023-2024 | BP-2023-24-677 | 22/12/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.58 | 0 | 0
3853 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION Of SIBAICHANDI ZONE-II Piped Water Supply Scheme with LDS, Rising Main& construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000054/2023-2024 | 1219/HUG | 27/04/2023 | 60 | SK MAIDUL ISLAM | 54.16 | 53.97 | 95
3854 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC (At ZONE-I & ZONE-II), construction of boundary wall at Proposed TW site OF ZONE-I For AUGMENTATION of SIBAICHANDI ZONE-I & ZONE-II Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000055/2023-2024 | 1220/HUG | 27/04/2023 | 363 | R. CONSTRUCTION | 82.07 | 72.08 | 96
3855 | Hooghly Division | Chinsuria Sub-Division | Laying Pipeline in uncovered areas and providing FHTC at the left out portions of Sibachandi (Zone-I & Zone-II) Piped Water Supply Scheme under Dhaniakhali-II Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000055/2024-2025 | 2365/HUG | 21/06/2024 | 285 | MAA JAGADHATRI CONSTRUCTION | 9.77 | 7.81 | 80
3856 | Hooghly Division | Chinsuria Sub-Division | Construction of 2 Nos. switch-room at different TW site of SIBAICHANDI Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000083/2023-2024 | 1343/HUG | 11/05/2023 | 45 | SUDIPTA DAS | 12.29 | 12.29 | 95
3857 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION Of SIBAICHANDI ZONE-I Piped Water Supply Scheme with LDS, Rising Main & construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000196/2023-2024 | 1787/HUG | 16/06/2023 | 90 | M/S BISWAS CONSTRUCTION | 138.84 | 94.78 | 30
3858 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Sibaichandi Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000421/2021-2022 | 92/CH | 03/02/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.07 | 4.02 | 0
3859 | Hooghly Division | Chinsuria Sub-Division | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000493/2021-2022 | 621/Hug | 31/03/2022 | 122 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.26 | 0 | 0
3860 | Hooghly Division | Chinsuria Sub-Division | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at SHIBAICHANDI W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000602/2023-2024 | 3317/HUG | 10/11/2023 | 30 | B.K ENTERPRISE | 14.48 | 14.42 | 95
3861 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 14.62 | 80
3862 | Hooghly Division | Chinsuria Sub-Division | Laying Pipeline in left out portions including Repairing of RCC OHR, Switch Room, Boundary Wall, Pathway etc. of Sibaichandi Zone-I Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000789/2023-2024 | 534/HUG | 20/02/2024 | 30 | M/S BISWAS CONSTRUCTION | 32.28 | 0 | 0
3863 | Hooghly Division | Chinsuria Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sibaichandi PWSS 2. Srikrishnapur PWSS 3. Aymanbabpur PWSS 4. Baichi PWSS 5. Balun PWSS 6. Dwarbasini PWSS | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000827/2023-2024 | 205/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 50
3864 | Hooghly Division | Chinsuria Sub-Division | Laying Balance pipeline within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000846/2023-2024 | 3563/HUG | 05/12/2023 | 30 | MUKHERJEE AND CO | 43.92 | 41.46 | 95
3865 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000082/2023-2024 | 1264/24/HUG | 03/05/2023 | 0 | Resource Division | 33.5 | 0 | 0
3866 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000126/2022-2023 | 2209/1/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
3867 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000302/2023-2024 | 1386/58/Hug | 15/05/2023 | 0 | Resource Division | 12.71 | 0 | 0
3868 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Sibaichandi W/S. Sch. TW-I & II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/03758/2023-2024 | 250, 251 | 05/09/2023 | 0 | WBSEDCL | 27.99 | 0 | 0
3869 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Sibaichandi TW-I & II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/03788/2023-2024 | 309 & 310 | 27/09/2023 | 0 | WBSEDCL | 4.03 | 0 | 0
3870 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sibaichandi water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000227/2022-2023 | 858/ED | 14/02/2023 | 90 | ANJAN ENTERPRISE | 21.45 | 19.65 | 45
3871 | Hooghly Division | Chinsuria Sub-Division | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report For AUGMENTATION of SRIKRISHNAPUR ZONE-II & its adjoining moujas water supply Scheme within DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division, P.H.E.Dte. Dist. Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000023/2023-2024 | 1103/HUG | 17/04/2023 | 728 | M/S SHIVAM UDYOG | 93.02 | 37.97 | 70
3872 | Hooghly Division | Chinsuria Sub-Division | Preparation of DPR for Augmentation of Srikrishnapur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000564/2021-2022 | 145/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.73 | 0
3873 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (ZONE-I) Piped Water Supply Scheme with Laying Distribution System Within Dasghara G.P., providing FHTC & repairing of of 272 cum capacity RCC OHR, Boundary Wall, Switch Room at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000595/2022-2023 | 2854/HUG | 16/12/2022 | 60 | SWASTIK ENTERPRISE | 72.14 | 67.11 | 75
3874 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Mouza(Part), providing FHTC & repairing of of Switch Room (3.6 M x 3.0M) & Boundary wall at existing 2nd T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000596/2022-2023 | 2855/HUG | 16/12/2022 | 60 | DAS TRADING | 78.15 | 67.56 | 75
3875 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Zone-I (North), providng FHTC & Construction of 3.6m x3.0 m Switch Room at Zone-II at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000597/2022-2023 | 2856/HUG12 | 16/12/2022 | 60 | DILIP KUMAR GHOSH | 68.2 | 59.71 | 80
3876 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS within South East, providing FHTC & Construction of Boundary Wall, Internal Pathway at 2nd TW Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000598/2022-2023 | 2857/HUG | 16/12/2022 | 60 | MS PRADIP KUMAR PAL | 77.87 | 62.03 | 100
3877 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS Within West portion, providing FHTC & Construction of Boundary Wall, Internal Pathway at H/W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000599/2022-2023 | 2858/HUG | 16/12/2022 | 60 | SAMRAT CONSTRUCTION | 87.74 | 61.98 | 20
3878 | Hooghly Division | Chinsuria Sub-Division | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with Laying Distribution System Within South West, providing FHTC & Construction of 1 No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements at Head Work Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000604/2022-2023 | 2890/HUG | 22/12/2022 | 60 | G.S CONSTRUCTION AND CO. | 61.25 | 55.58 | 67
3879 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 28.69 | 80
3880 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000232/2022-2023 | 226/9/Hug | 24/01/2023 | 0 | Resource Division | 33.67 | 0 | 0
3881 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | RTOR000295/2023-2024 | 1386/57/Hug | 15/05/2023 | 0 | Resource Division | 13.9 | 0 | 0
3882 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02593/2023-2024 | 156 | 03/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0
3883 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02594/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
3884 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charge at Srikrishnapur w/s scheme, T.W. No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02726/2023-2024 | 181 | 11/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
3885 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Srikrishnapur water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000229/2022-2023 | 860/ED | 14/02/2023 | 90 | ASHUTOSH DAS & CO. | 21.49 | 20.91 | 50
3886 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car (BS-IV) for the Official us of the Executive Engineer, Electrical Division PHED wef 01.06.23 to 30.11.23 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001022/2023-2024 | 363_AE-I_ED | 29/05/2023 | 365 | TRIDIP SARKAR | 5 | 1.19 | 40
3887 | Hooghly Division | Chinsuria Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer (Civil) | Chinsurah Block Junior Engineer (Civill) | BILL/00092/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.32 | 0 | 0
3888 | Hooghly Division | Chinsuria Sub-Division | Uttar Hazipur Mini PWSS | Assistant Engineer (Civil) | Chinsurah Block Junior Engineer (Civill) | BILL/00387/2023-2024 | BP-2023-24-330 | 29/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.62 | 0 | 0
3889 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil) | Chinsurah Block Junior Engineer (Civill) | BILL/01594/2024-2025 | 377 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 8.49 | 0 | 0
3890 | Hooghly Division | Arambug Sub-Division | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00085/2022-2023 |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.6 | 0 | 0
3891 | Hooghly Division | Arambug Sub-Division | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00216/2023-2024 |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 34 | 0 | 0
3892 | Hooghly Division | Arambug Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/00413/2023-2024 | BP-2023-24-338 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.41 | 0 | 0
3893 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | RTOR000182/2023-2024 | 1385/53/Hug | 15/05/2023 | 0 | Resource Division | 0.6 | 0 | 0
3894 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
3895 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection at Roypara ( Mirdanga) village of Guptipara 1 No. Gram Panchyet under Guptipara W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000308/2023-2024 | 691/CH | 27/07/2023 | 15 | MAA BUNAMATA ENTERPRISE | 0.97 | 0.97 | 100
3896 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under BALAGARH Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000345/2023-2024 | 2428/HUG | 11/08/2023 | 30 | SB ASSOCIATES | 42.72 | 38.01 | 85
3897 | Hooghly Division | Chinsuria Sub-Division | Providing 700 nos Functional Household Tap Connection (FHTC) within the command area of GUPTIPARA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000428/2022-2023 | 2363/HUG | 07/11/2022 | 35 | ARUN SEAL AND CO. | 41.06 | 41.02 | 0
3898 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000029/2023-2024 | 1129/HUG | 19/04/2023 | 45 | M/S SHIVAM UDYOG | 54.23 | 0 | 97
3899 | Hooghly Division | Chinsuria Sub-Division | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2023-2024 | 1341/HUG | 11/05/2023 | 45 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 0 | 75
3900 | Hooghly Division | Chinsuria Sub-Division | Rising Main in between 4th T.W to OHR Bypass arrangement and interconnection with Distribution System for DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000253/2022-2023 | 720/CH | 23/08/2022 | 15 | SOUMYADIP DE | 3.71 | 3.27 | 0
3901 | Hooghly Division | Chinsuria Sub-Division | Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO -02 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000370/2022-2023 | 2083/HUG | 21/09/2022 | 30 | M/S RAJKUMAR KHAN | 16.76 | 16.44 | 0
3902 | Hooghly Division | Chinsuria Sub-Division | Laying of Pipe line within left out portion for providing Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 03 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000371/2022-2023 | 2084/HUG | 21/09/2022 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.05 | 16.52 | 0
3903 | Hooghly Division | Chinsuria Sub-Division | Connection of replacement T.W. with existing rising main pipe line at head works site for Dharampur W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000718/2022-2023 | 12B/CH | 06/01/2023 | 15 | M/S BIMAL DAS AND CO. | 0.97 | 0.96 | 0
3904 | Hooghly Division | Chinsuria Sub-Division | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 65
3905 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Chatterjee Bagan of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001045/2023-2024 | 289/CH | 15/03/2024 | 7 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 80
3906 | Hooghly Division | Chinsuria Sub-Division | Providing FHTC in rest out portion of at Maynadanga of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001046/2023-2024 | 290/CH | 15/03/2024 | 7 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 80
3907 | Hooghly Division | Arambug Sub-Division | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of Chingra Zone-I Piped Water Supply Scheme under Khanakul-II Block of ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000299/2024-2025 | 3658/HUG | 13/11/2024 | 212 | M/S KAUSAR CONSTRUCTION | 16.1 | 0 | 50
3908 | Hooghly Division | Arambug Sub-Division | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 77.58 | 50
3909 | Hooghly Division | Arambug Sub-Division | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0
3910 | Hooghly Division | Arambug Sub-Division | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002745/2024-2025 | 1153/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0
3911 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000078/2023-2024 | 1234/39/Hug | 28/04/2023 | 0 | Resource Division | 14.42 | 0 | 0
3912 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000174/2023-2024 | 1385/45/Hug | 15/05/2023 | 0 | Resource Division | 8.35 | 0 | 0
3913 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000414/2023-2024 | 3059/43/Hug | 11/10/2023 | 0 | Resource Division | 8.35 | 0 | 0
3914 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- I, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004201533 Reference ID- 503652893 SM Code- 13325 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00821/2024-2025 | 223 | 18/06/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
3915 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Chinra w/s Scheme,Zone-I,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325) Application No-5004308863 Reference Id-503700260 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02035/2024-2025 | 510 | 21/10/2024 | 0 | WBSEDCL | 3.75 | 0 | 0
3916 | Electrical | Arambug Sub-Division | Quotation for Shifting Existing LT Structure at Chinra w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325).Application No-100000121107 Reference Id-860315657 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02094/2024-2025 | 548 | 30/10/2024 | 0 | WBSEDCL | 0.63 | 0 | 0
3917 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000146/2024-2025 | 1169/ED | 14/06/2024 | 90 | GOENKA ENTERPRISE | 10.74 | 0 | 0
3918 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000184/2022-2023 | 777/ED | 09/02/2023 | 898 | GOENKA ENTERPRISE | 20.48 | 10.43 | 10
3919 | Hooghly Division | Chandannagar Sub-Division | BADE DIGARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under HARIPAL Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000019/2023-2024 | 1062/HUG | 12/04/2023 | 811 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 423.74 | 268.74 | 25
3920 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Culvert, Approach Road at BADE DIGHARIA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000527/2023-2024 | 3006/HUG | 05/10/2023 | 60 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 11.3 | 11.18 | 100
3921 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR preparation of Bade Digharia PWSS under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000634/2023-2024 | 521/Chan | 12/10/2023 | 15 | APEX ENGINEERING | 4.19 | 4.19 | 100
3922 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Bade Digaria PWSS, Bhagabatipur PWSS, Sirazpur PWSS, Harat PWSS, panrra PWSS, Malia PWSS) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000978/2023-2024 | 306/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
3923 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000197/2022-2023 | 109/ 12/Hug | 10/01/2023 | 0 | Resource Division | 3.49 | 0 | 0
3924 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000217/2023-2024 | 1383/19/Hug | 15/05/2023 | 0 | Resource Division | 10.26 | 0 | 0
3925 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000276/2022-2023 | 902/12/Hug | 27/03/2023 | 0 | Resource Division | 10.26 | 0 | 0
3926 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000459/2023-2024 | 3058/27/Hug | 11/10/2023 | 0 | Resource Division | 10.26 | 0 | 0
3927 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection of Bade Digaria W/S scheme,TW No-I, Block-Haripal, District- Hooghly under ED ,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01982/2023-2024 | 98 | 17/07/2023 | 0 | WBSEDCL | 3.05 | 0 | 0
3928 | Electrical | Chandannagar Sub-Division | Quotation for new Service Connection of Bade Digaria w/s Scheme, TW No-II, Block- Haripal, District- Hooghly under ED ,PHE DTE | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01983/2023-2024 | 99 | 17/07/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
3929 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000170/2022-2023 | 559/ED | 02/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 0 | 0
3930 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000171/2022-2023 | 764/ED | 09/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 21.33 | 40
3931 | Hooghly Division | Chandannagar Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at MALIA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-17] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000050/2023-2024 | 1202/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 11.93 | 0
3932 | Hooghly Division | Chandannagar Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of MALIA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000130/2023-2024 | 1473/HUG | 19/05/2023 | 30 | SUDIPTA SINHA | 11.92 | 10.71 | 98
3933 | Electrical | Chandannagar Sub-Division | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00870/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0
3934 | Electrical | Chandannagar Sub-Division | Supply & delivery of submersible pumping machinery for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00873/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0
3935 | Electrical | Chandannagar Sub-Division | Supply & installation of MCC Panel & allied works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00875/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 2.7 | 0 | 0
3936 | Electrical | Chandannagar Sub-Division | Supply & delivery of electro-mechanical equipments and installation of submersible pumping machinery & other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00877/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.72 | 0 | 0
3937 | Electrical | Chandannagar Sub-Division | Supply ,delivery & installation of Actuator operated butterfly valve for for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00878/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1 | 0 | 0
3938 | Electrical | Chandannagar Sub-Division | Supply ,delivery & installation of Voltage correcting device and other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00879/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1.7 | 0 | 0
3939 | Electrical | Chandannagar Sub-Division | Supply & installation of Automatic Chlorinator at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00880/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.71 | 0 | 0
3940 | Electrical | Chandannagar Sub-Division | Internal electrification and works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00881/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.59 | 0 | 0
3941 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection of Malia W/S Scheme(Aug) T.W No-4 District-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01997/2023-2024 | 114 | 19/07/2023 | 0 | WBSEDCL | 2.28 | 0 | 0
3942 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Malia water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000002/2023-2024 | 1618/ED | 11/04/2023 | 90 | A.S. ENTERPRISE | 10.71 | 10.69 | 50
3943 | Electrical | Chandannagar Sub-Division | Supply, Installation of MCC panel & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000187/2020-2021 | 503/HMSD | 12/03/2021 | 90 | DEY ENTERPRISE | 2.7 | 2.7 | 0
3944 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of voltage correcting device & other allied works for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000188/2020-2021 | 322/HMSD | 15/02/2021 | 90 | DEY ENTERPRISE | 1.7 | 1.7 | 0
3945 | Electrical | Chandannagar Sub-Division | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001224/2021-2022 | 863/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.51 | 0.51 | 0
3946 | Electrical | Chandannagar Sub-Division | Supply & Delivery of electro-mechanical equipments & Installation of S/P/M & other allied works for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001225/2021-2022 | 864/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.72 | 0.72 | 0
3947 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of actuor operated butterfly valve for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001226/2021-2022 | 865/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 1 | 1 | 0
3948 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of automatic chlorinator for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001227/2021-2022 | 862/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.71 | 0.71 | 0
3949 | Electrical | Chandannagar Sub-Division | Internal Electrification & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001228/2021-2022 | 861/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.59 | 0.59 | 0
3950 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000077/2023-2024 | 1311/HUG | 10/05/2023 | 510 | MUNSHI TAJUDDIN | 11.82 | 10.42 | 90
3951 | Hooghly Division | Arambug Sub-Division | Construction of Boundary wall, land development, Internal Pathway at Head Work site of Shyamballavpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000294/2019-2020 | 208/HUG | 04/02/2020 | 30 | MOHANLAL CHATTERJEE | 15.28 | 0 | 0
3952 | Hooghly Division | Arambug Sub-Division | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at SHYAMBALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000743/2022-2023 | 654/HUG | 09/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 9.65 | 0
3953 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Shyamballavpur w/s Scheme,TW No-3,Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02132/2023-2024 | 122 | 20/07/2023 | 0 | WBSEDCL | 4.38 | 0 | 0
3954 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyamballavpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000008/2023-2024 | 1624/ED | 11/04/2023 | 90 | S.G.-ENTERPRISE | 10.73 | 10.64 | 40
3955 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000074/2023-2024 | 1235/12/Hug | 28/04/2023 | 0 | Resource Division | 58.83 | 0 | 0
3956 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000274/2023-2024 | 1383/25/Hug | 15/05/2023 | 0 | Resource Division | 5.09 | 0 | 0
3957 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Mahishtikari W/S. Sch. TW-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04167/2023-2024 | 406 | 09/11/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
3958 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Mahishtikri W/S. Sch. TW-I, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04168/2023-2024 | 407 | 09/11/2023 | 0 | WBSEDCL | 3.04 | 0 | 0
3959 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-I) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000042/2023-2024 | 1728/ED | 19/04/2023 | 866 | MENAKA ENTERPRISE | 20.26 | 19.47 | 30
3960 | Hooghly Division | Chandannagar Sub-Division | Horizontal Auger boring with water jet system Including Approach road with culvert at MAHISHTIKRI (ZONE-I & ZONE-II) under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000028/2024-2025 | 2285/HUG | 14/06/2024 | 30 | MAA TARA CONSTRUCTION | 4.82 | 0 | 100
3961 | Hooghly Division | Chandannagar Sub-Division | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Maheshtikri Zone 2 PWSS under Chandannagar Sub-Division Phe Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000932/2023-2024 | 278/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.84 | 100
3962 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000300/2023-2024 | 1383/44/Hug | 15/05/2023 | 0 | Resource Division | 3.76 | 0 | 0
3963 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000453/2023-2024 | 3058/18/Hug | 11/10/2023 | 0 | Resource Division | 3.76 | 0 | 0
3964 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection Charge for Mahishtikri w/s Scheme,Zone-2,TW No-I Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03761/2023-2024 | 264 | 07/09/2023 | 0 | WBSEDCL | 9.89 | 0 | 0
3965 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Mahistikri w/s Scheme,Zone-2,TW No-2 Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03762/2023-2024 | 263 | 07/09/2023 | 0 | WBSEDCL | 3.24 | 0 | 0
3966 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-II) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000024/2023-2024 | 1701/ED | 18/04/2023 | 90 | DEBJYOTI BASU | 20.5 | 0 | 60
3967 | Hooghly Division | Arambug Sub-Division | GOPALBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000138/2023-2024 | 1491/HUG | 22/05/2023 | 955 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 339.91 | 74.04 | 30
3968 | Hooghly Division | Arambug Sub-Division | Laying of Additional Pipeline for GOPALBATI Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000229/2024-2025 | 3431/HUG | 03/10/2024 | 182 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 23.25 | 0 | 15
3969 | Hooghly Division | Arambug Sub-Division | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000311/2024-2025 | 3687/HUG | 14/11/2024 | 331 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0
3970 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000049/2023-2024 | 1234/21/Hug | 28/04/2023 | 0 | Resource Division | 19.42 | 0 | 0
3971 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000163/2023-2024 | 1385/34/Hug | 15/05/2023 | 0 | Resource Division | 6.52 | 0 | 0
3972 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | RTOR000422/2023-2024 | 3057/39/Hug | 11/10/2023 | 0 | Resource Division | 6.52 | 0 | 0
3973 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gopalbati w/s Scheme,PH No-II,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/16756) Application No-5004475080 Reference Id-503799042 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02474/2024-2025 | 618 | 05/12/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
3974 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gopalbati W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04409/2023-2024 | 487 | 06/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
3975 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gopalbati water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000056/2023-2024 | 1800/ED | 24/04/2023 | 708 | KAMAKHYA ENTERPRISE | 20.26 | 0 | 30
3976 | Hooghly Division |  | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000576/2023-2024 | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0
3977 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000610/2023-2024 | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 28.58 | 60
3978 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land Development at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002005/2024-2025 | 289/CH | 20/02/2025 | 10 | TAPAS ADHYA | 4.29 | 0 | 0
3979 | Hooghly Division |  | Repairing & Renovation of Switch Room and Store Room at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002006/2024-2025 | 290/CH | 20/02/2025 | 10 | TAPAS ADHYA | 3.17 | 0 | 0
3980 | Electrical |  | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18934), Reference Id- 503795724 Application no- 5004470487 |  |  | BILL/02293/2024-2025 | BP-24-25-594 | 21/11/2024 | 0 | WBSEDCL | 7.02 | 0 | 0
3981 | Electrical |  | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHEDte. ( SM/18934), Reference Id- 503814971 Application no- 5004498167 |  |  | BILL/02600/2024-2025 | 631 | 18/12/2024 | 0 | WBSEDCL | 6.54 | 0 | 0
3982 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME Block- Balagarh, District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001207/2023-2024 | 4485/ED | 23/11/2023 | 770 | BARISAL TRADING CO. | 21.49 | 0 | 25
3983 | Hooghly Division | Chinsuria Sub-Division | Providing 1350 nos F.H.T.C. in Talchinan- Sanihati, Popai & Dhanijpur Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000019/2021-2022 | 957/Hug | 10/05/2021 | 40 | MINTU CHAKRABORTY | 61.16 | 52.83 | 100
3984 | Hooghly Division | Chinsuria Sub-Division | Providing 12 Nos. House Connection Within Goswami Malipara & It¿s Adjoining mouzas W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000118/2022-2023 | 400/CH | 06/05/2022 | 15 | MINTU CHAKRABORTY | 4.74 | 4.73 | 100
3985 | Hooghly Division | Chinsuria Sub-Division | Construction of Boundary Wall, Pathway & Repairing of Switch room at Head Works site & 2nd T/W Site of PAUNAN W/S Scheme under Chinsurah Sub-Division under Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000237/2021-2022 | 1922/Hug | 27/10/2021 | 40 | M/S S.G. CONSTRUCTION | 26.25 | 12.44 | 100
3986 | Hooghly Division | Chinsuria Sub-Division | Providing 1963 nos F.H.T.C. in Hadilpur, Bali Kukhari, Mirkhila, Chaupala & Goswami Malipara Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000289/2020-2021 | 364/Hug | 15/02/2021 | 30 | MINTU CHAKRABORTY | 92.96 | 5.85 | 100
3987 | Hooghly Division | Chinsuria Sub-Division | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Goswami Malipara Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000297/2021-2022 | 2208/Hug | 14/12/2021 | 20 | M/S KAMALA ENTERPRISE | 13.84 | 13.37 | 100
3988 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due to laying of pipe line at Choska Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000420/2023-2024 | 756/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.91 | 97
3989 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due to laying of pipe line at Dengor para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000422/2023-2024 | 757/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.85 | 97
3990 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Gosai para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000423/2023-2024 | 759/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 97
3991 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000425/2023-2024 | 760/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.9 | 0.9 | 97
3992 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000427/2023-2024 | 762/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.8 | 1.52 | 97
3993 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due to laying of pipe line at Kallyandanga of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000428/2023-2024 | 763/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.9 | 97
3994 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Bhagarpar of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000431/2023-2024 | 764/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.89 | 0.89 | 97
3995 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000432/2023-2024 | 770/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.89 | 0.85 | 97
3996 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due to laying of pipe line at Kolor Par of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000433/2023-2024 | 771/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.9 | 97
3997 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Kalyan danga Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000434/2023-2024 | 772/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 97
3998 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000435/2023-2024 | 773/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.84 | 1.67 | 97
3999 | Hooghly Division | Chinsuria Sub-Division | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000436/2023-2024 | 777/CH | 21/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.52 | 0.49 | 97
4000 | Hooghly Division | Chinsuria Sub-Division | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Goswami Malipara PWSS, Block POLBA DADPUR under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000582/2022-2023 | 2841/HUG | 16/12/2022 | 30 | BOSE ENTERPRISE (RATUL BOSE) | 29.55 | 29.52 | 40
4001 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001127/2021-2022 |  | 16/11/2021 | 0 | MINTU CHAKRABORTY | 28.28 | 0 | 0
4002 | Hooghly Division | Chinsuria Sub-Division | Providing 513 nos F.H.T.C. in Kamarpara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000020/2021-2022 | 958/Hug | 10/05/2021 | 30 | SWASTIK ENTERPRISE | 26.53 | 26.5 | 100
4003 | Hooghly Division | Chinsuria Sub-Division | Providing 85 nos Functional Household Tap Connection (FHTC) within the command area of Kamarpara Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000343/2021-2022 | 20/Hug | 04/01/2022 | 20 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 6.07 | 5.92 | 100
4004 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000002/2021-2022 | 1968/HUG | 03/11/2021 | 0 | Resource Division | 9.31 | 0 | 0
4005 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000062/2021-2022 | 2097/2/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0
4006 | Hooghly Division | Chinsuria Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000171/2021-2022 | 428/4-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0
4007 | Hooghly Division | Chinsuria Sub-Division | FHTC | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001026/2021-2022 |  | 30/09/2021 | 0 | SWASTIK ENTERPRISE | 13 | 0 | 0
4008 | Hooghly Division | Srirampur Sub-Division | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000268/2020-2021 | 262/Hug | 03/02/2021 | 20 | K JAGADHATRY & CO | 13.62 | 8.38 | 0
4009 | Hooghly Division | Srirampur Sub-Division | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000284/2020-2021 | 331/Hug | 11/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 16.31 | 100
4010 | Hooghly Division | Srirampur Sub-Division | Providing 375 nos Functional Household Tap Connection (FHTC) within the command area of BORHAL(ZONE-I) Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000361/2021-2022 | 122/Hug | 19/01/2022 | 25 | K. JAGADHATRY & CO. | 15.98 | 15.98 | 100
4011 | Hooghly Division | Srirampur Sub-Division | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000881/2020-2021 | 1686/Hug. | 17/12/2020 | 40 | S & P ENTERPRISE | 103.59 | 17.89 | 98
4012 | Hooghly Division | Srirampur Sub-Division | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00738/2023-2024 |  | 06/11/2023 | 0 | P. B. ENTERPRISE(PINTU BHADURI) | 1.02 | 0 | 0
4013 | Hooghly Division | Srirampur Sub-Division | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at 2nd TW sites for PURBA TAJPUR (ZONE-I) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000050/2024-2025 | 2339/HUG | 19/06/2024 | 60 | TAPAS ADHYA | 28.13 | 0 | 0
4014 | Hooghly Division | Srirampur Sub-Division | Preparation of DPR for Augmentation of Purba Tajpur Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000154/2022-2023 | 482/SER | 14/07/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.85 | 2.85 | 0
4015 | Hooghly Division | Srirampur Sub-Division | Augmentation of PURBATAJPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000187/2022-2023 | 1609/Hug | 05/08/2022 | 40 | MS CHANDIMATA CONSTRUCTION | 76.17 | 74.19 | 98
4016 | Hooghly Division | Srirampur Sub-Division | Augmentation of PURBATAJPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000465/2022-2023 | 2526/HUG | 23/11/2022 | 40 | BIMAL KUMAR HALDER | 76.75 | 67.85 | 98
4017 | Hooghly Division | Srirampur Sub-Division | Sinking of 1 no 300 X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of PURBATAJPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000669/2022-2023 | 163/HUG | 16/01/2023 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 100
4018 | Hooghly Division | Srirampur Sub-Division | Left out pipeline to restore the water supply and development of head work site at Purbatajpur Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000896/2023-2024 | 824/HUG | 11/03/2024 | 30 | DAS CONSTRUCTION | 22.87 | 22.33 | 95
4019 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000013/2023-2024 | 1107/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0
4020 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | RTOR000312/2023-2024 | 1384/9/Hug | 15/05/2023 | 0 | Resource Division | 10.9 | 0 | 0
4021 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.02.2024 to 29.02.2024 WB19J-7094 SM Code- 11465 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00717/2024-2025 | 229 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0
4022 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.01.2024 to 31.01.2024 WB19J-7094 SM Code- 11465 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00719/2024-2025 | 228 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
4023 | Electrical | Srirampur Sub-Division | Purba Tajpur w/s scheme, P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04329/2023-2024 | 442 | 24/11/2023 | 0 | WBSEDCL | 5.52 | 0 | 0
4024 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Tajpur water supply scheme TW No I Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000223/2022-2023 | 854/ED | 14/02/2023 | 90 | A.K. SIKDAR | 10.72 | 10.67 | 99
4025 | Electrical | Srirampur Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001009/2023-2024 | 2502/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 1.16 | 15
4026 | Hooghly Division | Arambug Sub-Division | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply & Sanitation arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of RAJHATO Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Khanakul-II Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000124/2023-2024 | 1458/HUG | 18/05/2023 | 30 | BENGAL TRADERS | 10.29 | 10.28 | 100
4027 | Hooghly Division | Arambug Sub-Division | Augmentation of RAJHATO Water Supply Scheme with LDS, Switch room, Boundary wall,Rising Main,FHTC Work, of existing Switch Rooms& Boundary Wall at Khanakul-II Block. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000190/2022-2023 | 826//Hug | 20/04/2022 | 1261 | M/S PRADYUT KUMAR HAZRA | 404.28 | 365.14 | 80
4028 | Hooghly Division | Arambug Sub-Division | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 13.73 | 70
4029 | Hooghly Division | Arambug Sub-Division | Preparation of DPR for Augmentation of RAJHATO Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000382/2021-2022 | 613/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.79 | 3.78 | 100
4030 | Hooghly Division | Arambug Sub-Division | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall of RAJHATO PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000448/2024-2025 | 4083/HUG | 19/12/2024 | 90 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 21.43 | 0 | 0
4031 | Hooghly Division | Arambug Sub-Division | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at RAJHATO PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000455/2022-2023 | 2506/HUG | 22/11/2022 | 45 | OSMAN SEKH | 22.53 | 22.24 | 100
4032 | Hooghly Division | Arambug Sub-Division | Supply of UPVC Pipe for TW-III of RAJHATO Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000910/2022-2023 | 209/Arg | 31/03/2023 | 15 | OSMAN SEKH | 0.69 | 0.69 | 100
4033 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000045/2022-2023 | 1590/Hug | 03/08/2022 | 0 | Resource Division | 24.64 | 0 | 0
4034 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000075/2022-2023 | 1773/9/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0
4035 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000142/2023-2024 | 1385/14/Hug | 15/05/2023 | 0 | Resource Division | 0.2 | 0 | 0
4036 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000161/2021-2022 | 424/2/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0
4037 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000177/2022-2023 | 79/23/Hug | 06/01/2023 | 0 | Resource Division | 26.55 | 0 | 0
4038 | Electrical | Arambug Sub-Division | Quotation bill for New Service connection of Rajhato w/s scheme,TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00731/2023-2024 | 20 | 04/05/2023 | 0 | WBSEDCL | 2.22 | 0 | 0
4039 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Rajhato(Aug) w/s Scheme, PH No-2 District-Hooghly Under Electrical division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01162/2023-2024 | 84 | 10/07/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
4040 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Rajhato water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000289/2022-2023 | 939/ED | 22/02/2023 | 90 | MAA KALI ENTERPRISE | 21.48 | 21.31 | 60
4041 | Central Drilling | Arambug Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150mtrs Depth ) by utilising Departmental Machineries for Rajhato W/S Scheme ,Arambag Block under hooghly District ,CDD,PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000005/2023-2024 | 61/CDD | 06/04/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 10.14 | 100
4042 | Central Drilling | Arambug Sub-Division | SUPPLY AND DELIVERY OF TENT FOR DRILLING WORK AT RAJHATO PWSS UNDER CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000190/2022-2023 | 255/CMSD-I | 23/06/2022 | 15 | M/S S.K.GHOSH & CO. | 4.56 | 0 | 100
4043 | Central Drilling | Arambug Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000216/2021-2022 | 55/CMSD-II (D) | 31/01/2022 | 7 | ASHUTOSH PAL | 0.86 | 0 | 64
4044 | Central Drilling | Arambug Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION-I, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000217/2021-2022 | 67/CMSD-I (D) | 22/03/2022 | 7 | SUJATA BHOWMICK | 0.87 | 0 | 67
4045 | Central Drilling | Arambug Sub-Division | MISCELLANEOUS REPAIRING OF MUD PUMP ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000241/2021-2022 | 634/CMSD-II (D) | 23/12/2021 | 15 | M/S B.P.TRADING CORPORATION | 3.28 | 3.22 | 100
4046 | Central Drilling | Arambug Sub-Division | Supply & Delivery of Tent for Drilling work at Rajhato PWSS, Dist Hooghly and other PWSS under CDD, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000306/2022-2023 | 336/CMSD-I(D) | 18/07/2022 | 15 | M/S S.K.GHOSH & CO. | 4.37 | 4.37 | 100
4047 | Central Drilling | Arambug Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCHEME (TW0II) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000393/2022-2023 | 1077/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 4.28 | 0
4048 | Central Drilling | Arambug Sub-Division | CONTINGENCY BILL | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | VCH/000150/2022-2023 | BP-2022-23-41 | 15/07/2022 | 0 | ASHUTOSH PAL | 0.29 | 0 | 0
4049 | Central Drilling | Arambug Sub-Division | CONTINGENCY BILL | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | VCH/000151/2022-2023 | BP-2022-23-40 | 15/07/2022 | 0 | SUJATA BHOWMICK | 0.14 | 0 | 0
4050 | Hooghly Division | Chandannagar Sub-Division | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR AUGMENTATION OF CHAMPDANGA W/S/S | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00056/2022-2023 | BP-2022-23-413 | 20/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0
4051 | Hooghly Division | Chandannagar Sub-Division | Augmentation of CHAMPADANGA Water Supply Scheme with Laying Distribution System within MOKTARPUR & LASKARPUR Mouza, Construction of Switch room & Boundary wall for Proposed Switch Room-IV, Repairing of existing Switch Room-III & Boundary Wall & FHTC Work within MOKTARPUR & LASKARPUR Mouza at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000049/2022-2023 | 833/Hug | 20/04/2022 | 1076 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 348.19 | 277.19 | 100
4052 | Hooghly Division | Chandannagar Sub-Division | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at TARAKESWAR Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000086/2022-2023 | 218/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.97 | 4.97 | 0
4053 | Hooghly Division | Chandannagar Sub-Division | Route Survey, Design Drawing & DPR Preparation of Champadanga PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000224/2022-2023 | 261/CHAN | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.96 | 4.96 | 0
4054 | Hooghly Division | Chandannagar Sub-Division | Necessary Maintenance Work for Improvement of water supply in distribution system at Laskarpur & Muktarpur mouza under Champadanda Water Supply Scheme under Chandannagar Sub - Division P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000229/2025-2026 | 877/CHAN | 21/07/2025 | 20 | ASHA ENTERPRISE | 1.49 | 0 | 100
4055 | Hooghly Division | Chandannagar Sub-Division | Laying of HDPE distribution pipe due to widening & construction of 4-lane of champadanga-Chanditala road under WBHDCL for providing water supply at Champadanga water supply scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000359/2022-2023 | 208/HUG | 13/04/2022 | 15 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.67 | 4.65 | 0
4056 | Hooghly Division | Chandannagar Sub-Division | Shifting of UVPC Pipe Line & Allied works for new culvert construction of irrigation at Laskarpur mouza under Champadanga Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000456/2025-2026 | 1004/Chan | 30/07/2025 | 10 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 0.96 | 0 | 0
4057 | Hooghly Division | Chandannagar Sub-Division | Augmentation of CHAMPADANGA Water Supply Scheme with Construction of 750 cum capacity OHR with 20 mtr. staging height including Soil Investigation work , Laying Distribution System Within CHAMPADANGA & SACHAK Mouza, Construction of Switch rooms at Proposed Pump House-V, Boundary wall at Proposed 5th T.W Site, Rising Main, FHTC Work, Repairing of existing Switch Rooms & Boundary Wall of Existing T.W-1 & 2 at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000499/2022-2023 | 1151/HUG | 09/06/2022 | 1327 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 687.43 | 585.19 | 95
4058 | Hooghly Division | Chandannagar Sub-Division | Horizontal road crossing by trenchless method at Champadanga Pairadinghi kalitala Node(538-541), Champadanga Kalitala Node(256-260), Champadanga Mansatala Node(159-170),DVC Santhashitala(Hanuman Temple) Node(135-138),Muktarpur Electric substation Node(232-234) beside SH 15 & SH 12 under Chandannagar Sub-Division. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000651/2023-2024 | 3481/HUG | 29/11/2023 | 45 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 12.41 | 24.8 | 100
4059 | Hooghly Division | Chandannagar Sub-Division | Left OutPortion of LDS AND FHTC Work of champadanga Water Supply Scheme under mouza champadanga and sachak Under chandannagar Sub-Division of Hooghly Division,P.H.E Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000656/2023-2024 | 3522/HUG | 30/11/2023 | 747 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 96.7 | 25.04 | 95
4060 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part A). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000705/2023-2024 | 934/Chan | 30/11/2023 | 15 | AMBIAN INFRASTRUCTURE | 0.91 | 0.7 | 100
4061 | Hooghly Division | Chandannagar Sub-Division | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part B). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000718/2023-2024 | 935/Chan | 30/11/2023 | 15 | AMBIAN INFRASTRUCTURE | 0.63 | 0.57 | 100
4062 | Hooghly Division | Chandannagar Sub-Division | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000966/2023-2024 | 294/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.99 | 0 | 99
4063 | Hooghly Division | Chandannagar Sub-Division | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000967/2023-2024 | 295/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.95 | 0 | 95
4064 | Hooghly Division | Chandannagar Sub-Division | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000968/2023-2024 | 298/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.98 | 0 | 99
4065 | Hooghly Division | Chandannagar Sub-Division | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Champadanga PWSS, Naita PWSS, Purbaramnagar PWSS, Ramnaryanpur PWSS, Salepur-Duttapur zone-I PWSS, Salepur-Duttapur zone-II PWSS). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000973/2023-2024 | 302/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100
4066 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000043/2022-2023 | 1370/2/Hug | 06/07/2022 | 0 | Resource Division | 133.19 | 0 | 0
4067 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000136/2022-2023 | 2686/3/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0
4068 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000152/2022-2023 | 01/01/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0
4069 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000155/2021-2022 | 423/6/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0
4070 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000208/2022-2023 | 109/ 18/Hug | 10/01/2023 | 0 | Resource Division | 96.26 | 0 | 0
4071 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | RTOR000278/2023-2024 | 1383/28/Hug | 15/05/2023 | 0 | Resource Division | 5.78 | 0 | 0
4072 | Electrical | Chandannagar Sub-Division | Augmentation Of Champadanga Water Supply Scheme TW-4 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01908/2022-2023 | 250, 251 | 31/03/2023 | 0 | WBSEDCL | 6.95 | 0 | 0
4073 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000237/2022-2023 | 868/ED | 14/02/2023 | 745 | STANDARD ELECTRICALS | 21.96 | 21.95 | 95
4074 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000279/2022-2023 | 946/ED | 22/02/2023 | 90 | STANDARD ELECTRICALS | 21.96 | 0 | 0
4075 | Central Drilling | Chandannagar Sub-Division | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, , Central Drilling Division, P.H.E. Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000034/2024-2025 | 188/S&WSD | 25/09/2024 | 182 | SUJIT DAS | 0.86 | 1.12 | 0
4076 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000207/2022-2023 | 381/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.34 | 3.16 | 0
4077 | Central Drilling | Chandannagar Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSUMBLES OF TUBEWELL AT AUG. OF CHAMPADANGA PWSS, TARAKESSWAR BLOCK, HOOGHLY BLOCK UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000209/2022-2023 | 383/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.68 | 2.64 | 0
4078 | Central Drilling | Chandannagar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000210/2022-2023 | 382/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.31 | 0
4079 | Central Drilling | Chandannagar Sub-Division | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROADS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT CHAMPADANGAPWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000211/2022-2023 | 464/CMSD-II | 27/09/2022 | 7 | C.M. ENTERPRISE | 0.26 | 0.25 | 0
4080 | Central Drilling | Chandannagar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAMPADANGA UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000330/2022-2023 | 1677/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 11.34 | 9.18 | 0
4081 | Central Drilling | Chandannagar Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAMPADANGA, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000342/2022-2023 | 575/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.86 | 0
4082 | Central Drilling | Chandannagar Sub-Division | Hiring of Diesel Driven Motor Vab (BS-III & Above) (Non AC) hiving contract carriage permit along with driven for office of the Calcutta Mechanical Sub Division -I, PHE Dte. under CMSD-II (D), CDD, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000425/2022-2023 | 40/CMSD-II(D) | 16/02/2023 | 150 | SUJATA BHOWMICK | 0.87 | 2.28 | 51
4083 | Hooghly Division | Arambug Sub-Division | GHAR GOHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2023-2024 | 3183/HUG | 30/10/2023 | 720 | DAS TRADING | 194.07 | 109.72 | 30
4084 | Hooghly Division | Arambug Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Civill) | RTOR000426/2023-2024 | 3057/38/Hug | 11/10/2023 | 0 | Resource Division | 3.29 | 0 | 0
4085 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-I Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282705 Reference Id-503686110 | Assistant Engineer | Junior Engineer (Civill) | BILL/01152/2024-2025 | 285 | 09/07/2024 | 0 | WBSEDCL | 5.39 | 0 | 0
4086 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282784 Reference Id-503686105 | Assistant Engineer | Junior Engineer (Civill) | BILL/01153/2024-2025 | 286 | 09/07/2024 | 0 | WBSEDCL | 6.42 | 0 | 0
4087 | Electrical | Arambug Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Officical use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000284/2024-2025 | 2870/HMSD | 04/06/2024 | 182 | BHOLA DEY | 0.86 | 0 | 0
4088 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghar Gohal water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001984/2023-2024 | 116/ED | 15/01/2024 | 531 | GLACIER ENGINEERING CO. | 21.1 | 0 | 30
4089 | Hooghly Division |  | Replacement of damaged AC pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Khayramari Char of Bhawanipur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000034/2024-2025 | 536/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 2.51 | 2.51 | 90
4090 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 0 | 30
4091 | Hooghly Division |  | Repairing & Renovation of Boundary Wall and Land Development At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/001963/2024-2025 | 285/CH | 20/02/2025 | 10 | MAA BUNAMATA ENTERPRISE | 3.85 | 0 | 100
4092 | Hooghly Division |  | Repairing & Renovation of Boundary Wall extensions, Switch Room & IP Room At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002009/2024-2025 | 295/CH | 20/02/2025 | 10 | MAA BUNAMATA ENTERPRISE | 4.49 | 0 | 100
4093 | Hooghly Division |  | Repairing & Renovation of Boundary Wall, Switch Room and Land Development At PH-II Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. |  |  | ORD/002015/2024-2025 | 303/CH | 20/02/2025 | 10 | SWARNA ENTERPRISE | 2.15 | 0 | 0
4094 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001246/2023-2024 | 4496/ED | 23/11/2023 | 90 | PERPETUAL ENTERPRISE | 21.7 | 0 | 0
4095 | Hooghly Division | Chinsuria Sub-Division | MINI PIPED WATER SUPPLY SCHEME | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/00357/2023-2024 | BP-2023-24-297 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.23 | 0 | 0
4096 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
4097 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
4098 | Hooghly Division |  | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Ser Gram of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000046/2024-2025 | 549/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 5 | 4.99 | 80
4099 | Hooghly Division |  | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Tin MandirTala of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000047/2024-2025 | 550/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.97 | 4.97 | 80
4100 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 45
4101 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 28.08 | 25
4102 | Electrical |  | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - III, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619158, Dt. - 13-05-2024, Application No. - 5004116682 |  |  | BILL/00450/2024-2025 | 124 | 17/05/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
4103 | Electrical |  | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - IV, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619159, Dt. - 13-05-2024, Application No. - 5004116723 |  |  | BILL/00451/2024-2025 | 122 | 17/05/2024 | 0 | WBSEDCL | 6.36 | 0 | 0
4104 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of PUINAN piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001276/2023-2024 | 4516/ED | 23/11/2023 | 90 | SUTRADHAR TRADERS | 21.47 | 6.16 | 30
4105 | Hooghly Division | Srirampur Sub-Division | KOTALPUR (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR At ZONE-I & Construction of 300 cum capacity RCC OHR At ZONE-II with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site of ZONE-I & ZONE-II under Serampore Sub-Division of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000281/2023-2024 | 2321/HUG | 04/08/2023 | 1732 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 1457.97 | 364.27 | 45
4106 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000343/2023-2024 | 3005/17/Hug | 05/10/2023 | 0 | Resource Division | 71.65 | 0 | 0
4107 | Hooghly Division | Srirampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000530/2023-2024 | 3060/2/Hug | 11/10/2023 | 0 | Resource Division | 31.37 | 0 | 0
4108 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-II, PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04442/2023-2024 | 519A | 11/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
4109 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04587/2023-2024 | 596 | 29/12/2023 | 0 | WBSEDCL | 0.74 | 0 | 0
4110 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04589/2023-2024 | 597 | 29/12/2023 | 0 | WBSEDCL | 5.03 | 0 | 0
4111 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04636/2023-2024 | 625 | 08/01/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
4112 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04637/2023-2024 | 624 | 08/01/2024 | 0 | WBSEDCL | 7.5 | 0 | 0
4113 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000847/2023-2024 | 3415/ED | 10/08/2023 | 90 | A.S. ENTERPRISE | 20.34 | 14.41 | 60
4114 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000848/2023-2024 | 3416/ED | 10/08/2023 | 90 | P.K. ENGINEERING | 22.13 | 0 | 0
4115 | Hooghly Division |  | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000450/2024-2025 | 4081/HUG | 19/12/2024 | 90 | R.K. TRADERS | 20.96 | 0 | 0
4116 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 14.3 | 60
4117 | Hooghly Division |  | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000716/2023-2024 | 3352/HUG | 17/11/2023 | 778 | A.R. CONSTRUCTION | 35.75 | 0 | 20
4118 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SAOTA Piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001291/2023-2024 | 4523/ED | 23/11/2023 | 90 | TRIO CONCERN | 21.48 | 0 | 0
4119 | Hooghly Division | Chandannagar Sub-Division | PAYMENT FOR ROAD RESTORATION | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00265/2024-2025 | BP-2024-25-186 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.78 | 0 | 0
4120 | Hooghly Division | Chandannagar Sub-Division | BALARAMBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000284/2023-2024 | 2334/HUG | 07/08/2023 | 686 | SAMIRON GHOSH | 782.6 | 616.94 | 100
4121 | Hooghly Division | Chandannagar Sub-Division | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BALARAMBATI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000529/2023-2024 | 3008/HUG | 05/10/2023 | 60 | S.K ENTERPRISE | 33.79 | 60.79 | 100
4122 | Hooghly Division | Chandannagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | RTOR000436/2023-2024 | 3058/4/Hug | 11/10/2023 | 0 | Resource Division | 20.62 | 0 | 0
4123 | Electrical | Chandannagar Sub-Division | Qoutation for new service connection at Balarambati W/S Sch., Head works Site, (T/W No - I), Dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03703/2023-2024 | 233 | 01/09/2023 | 0 | WBSEDCL | 3.21 | 0 | 0
4124 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Balarambati W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05924/2023-2024 | 715 | 29/01/2024 | 0 | WBSEDCL | 6.84 | 0 | 0
4125 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Balarambati W/S Sch., T/W No. - III, [SM/18657], Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503584700, Dt. - 12-03-2024, Application No. - 5004050064 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06470/2023-2024 | 894 | 18/03/2024 | 0 | WBSEDCL | 5.07 | 0 | 0
4126 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balarambati water supply scheme, T.W. No. I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000842/2023-2024 | 3410/ED | 10/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 32.24 | 0 | 80
4127 | Hooghly Division |  | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000597/2023-2024 | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 32
4128 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) |  |  | ORD/000646/2023-2024 | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 12.28 | 20
4129 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of GOURHATI piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001293/2023-2024 | 4525/ED | 23/11/2023 | 90 | UNIVERSAL ENTERPRISES | 21.49 | 0 | 0
4130 | Hooghly Division |  | Repairing & Renovation of Switch room at PH-3 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/000001/2025-2026 | 483/CH | 04/04/2025 | 10 | TOTON MONDAL | 1.4 | 0 | 100
4131 | Hooghly Division |  | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/000003/2025-2026 | 485/CH | 04/04/2025 | 10 | JOY GURU ENTERPRISE | 1.72 | 0 | 100
4132 | Hooghly Division |  | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0
4133 | Hooghly Division |  | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 80
4134 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001859/2024-2025 | 238/CH | 19/02/2025 | 10 | JOY GURU ENTERPRISE | 4.78 | 0 | 100
4135 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Pandua Z-III PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001921/2024-2025 | 271/CH | 20/02/2025 | 10 | TOTON MONDAL | 3.38 | 0 | 100
4136 | Hooghly Division |  | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001953/2024-2025 | 275/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 4.78 | 0 | 100
4137 | Hooghly Division |  | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001956/2024-2025 | 278/CH | 20/02/2025 | 10 | TOTON MONDAL | 2.84 | 0 | 100
4138 | Hooghly Division |  | Repairing & Renovation of Switch room at PH-2 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001957/2024-2025 | 279/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 2.23 | 0 | 100
4139 | Hooghly Division |  | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001959/2024-2025 | 281/CH | 20/02/2025 | 10 | TOTON MONDAL | 3.18 | 0 | 100
4140 | Hooghly Division |  | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block |  |  | ORD/001961/2024-2025 | 283/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 2.9 | 0 | 100
4141 | Hooghly Division |  | Emargency replacement of valves and allied works at Pandua Water Supply Scheme under Pandua Block under Chinsurah sub-division under Hooghly Division, PHE Dte. |  |  | ORD/002016/2024-2025 | 304/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 3.26 | 0 | 100
4142 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001265/2023-2024 | 4510/ED | 23/11/2023 | 90 | INDIA ENTERPRISE | 21.48 | 0 | 0
Total | [10 empty] | 430133.63 | 78560.78