## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 05 nos, (Rangametya, Kuladabar, Burat, Deulberia, Murgathol ) Total House Hold - 520 |  | Junior Engineer | ORD/000056/2020-2021 | 464/BQA | 05/02/2021 | 30 | MUNMUN UPADHYAY | 36.86 | 0 | 0
2 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 nos, (Chandra, Benagoria) Total House Hold - 143 |  | Junior Engineer | ORD/000057/2020-2021 | 465/BQA | 05/02/2021 | 30 | ROY CHOWDHURY ENTERPRISE | 9.76 | 2.64 | 0
3 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 27.5 | 0
4 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 03 nos, ( Ampahari, Gopinathpur, Chakchaki,) Total House Hold - 518 |  | Junior Engineer | ORD/000206/2020-2021 | 678/BQA | 19/02/2021 | 30 | SUMITA UPADHYAY | 36.78 | 0 | 0
5 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- Murgathol (Part) Total House Hold - 67 nos |  | Junior Engineer | ORD/000246/2022-2023 | 250/KSD | 12/07/2022 | 15 | TARINI CHARAN UPADHYAY | 3.37 | 3.36 | 0
6 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Burat mouza & Dismantling & reconstruction of concrete for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHIRA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte |  | Junior Engineer | ORD/000280/2022-2023 | 350/KSD | 16/08/2022 | 20 | MUNMUN UPADHYAY | 4.92 | 4.91 | 0
7 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - JOREHERA, No. of Mouza :- 01 no., (Burat), Total House Hold- 80 nos. |  | Junior Engineer | ORD/000499/2021-2022 | 248/BSD | 15/03/2022 | 10 | TARINI CHARAN UPADHYAY | 4.5 | 4.5 | 0
8 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Radhaballav more to Ampahari Village to increase water pressure at Ampahari mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jorehira (Zone - B) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000744/2022-2023 | 632/BQA | 24/03/2023 | 45 | SWAPAN KUMAR DE | 17.25 | 0 | 15
9 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
10 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 135 | Assistant Engineer | Junior Engineer | ORD/000005/2020-2021 | 606/BQA | 10/02/2021 | 30 | M/S SACHHIDANANDA MAZUMDAR | 10.28 | 0 | 0
11 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 530 | Assistant Engineer | Junior Engineer | ORD/000006/2020-2021 | 607/BQA | 10/02/2021 | 30 | PARTHA PRATIM CHATAIT | 40.66 | 1.72 | 0
12 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 45 | UNICON INDIA | 317.75 | 0 | 100
13 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 60. | Assistant Engineer | Junior Engineer | ORD/000145/2020-2021 | 24/VSD | 20/01/2021 | 30 | TAPAS KUMAR HAZRA | 4.81 | 0 | 0
14 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 62. | Assistant Engineer | Junior Engineer | ORD/000146/2020-2021 | 25/VSD | 20/01/2021 | 30 | BIT ENTERPRISE | 4.82 | 0 | 0
15 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SOMSAR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Somsar, No. of Mouza :- 01 no. i.e. (Somsar-02), Total House Hold - 1058 | Assistant Engineer | Junior Engineer | VCH/002454/2021-2022 | FHTC/1 | 01/02/2022 | 0 | M/S K.B.CONSTRUCTION | 13.26 | 0 | 0
16 | Bankura Division | Brishnupur Sub-Division | Additional work by laying of new HDPE pipeline of uncover area in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA from Nayer culvert to Gur hati Mansa tala via Pathar Pukur within Radhanagar W/S Scheme zone - ll under Bishnupur Sub - Division of Bankura Division, PHE Dte. sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002971/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 4.53 | 0 | 0
17 | Bankura Division | Brishnupur Sub-Division | Additional work by laying of new HDPE pipeline of uncover area in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Beside of Joykrishnapur village and Joykrishnapur coliny para within Radhanagar W/S Scheme zone - ll under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002972/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 4.24 | 0 | 0
18 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.22 | 0
19 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No. of Mouza :- 02 no, Arrah (Part), Khudrabanagram Total House Hold - 383. | Assistant Engineer | Junior Engineer | VCH/002452/2021-2022 | FHTC/1 | 01/02/2022 | 0 | NAYAN BARDHAN | 28.49 | 0 | 0
20 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
21 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | VCH/003048/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 59.46 | 0 | 0
22 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 3,( Housibad, Parulia(Part), Jaljalia banshal,) Total House Hold - 436 | Assistant Engineer | Junior Engineer | ORD/000054/2020-2021 | 461/BQA | 05/02/2021 | 1791 | APEX ENTERPRISE | 36.37 | 5.97 | 20
23 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 3,( Kalipur, Parulia(Part), Biskodar,) Total House Hold - 437 | Assistant Engineer | Junior Engineer | ORD/000055/2020-2021 | 462/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 36.36 | 13.43 | 20
24 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part), Total House Hold - 75 (Sl No of Work- 08) | Assistant Engineer | Junior Engineer | ORD/000139/2020-2021 | 100/ BSD | 12/02/2021 | 20 | SANDHYA DEY | 4.75 | 5.09 | 0
25 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Tilabani More to Arjunda village to increase pressure in Arjunda (65) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2022-2023 | 1683/BQA | 27/07/2022 | 30 | GON ASSOCIATES | 5.44 | 5.02 | 0
26 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Basudebpur (79) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2022-2023 | 1691/BQA | 27/07/2022 | 30 | SANJOY PATRA | 7.96 | 5.89 | 0
27 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70) & Jamdahara (71) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2020-2021 | 168/BQA | 18/01/2021 | 30 | SANJOY PATRA | 26.31 | 7.94 | 0
28 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tilabani (72), Dhanga Dungri (74) & Mirgi (75) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000111/2020-2021 | 169/BQA | 18/01/2021 | 30 | SANJOY PATRA | 28.38 | 9.71 | 0
29 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Basudebpur (79), Jhat Pukhuria (80) & Patasimul (143) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2020-2021 | 170/BQA | 18/01/2021 | 30 | SANJOY PATRA | 27.11 | 5.83 | 0
30 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 100 | 0
31 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70), Jamdahara (71), Tilabani (72), Dhanga Dungri (74), Mirgi (75), Basudebpur (79), Jhat Pukhuria (80) & Patasimul (143) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000512/2020-2021 | 310/KSD | 29/12/2020 | 61 | SANJOY PATRA | 0.38 | 0 | 0
32 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jhatpukhuria(80) mouza by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 28) | Assistant Engineer | Junior Engineer | ORD/000697/2021-2022 | 89/KSD | 09/03/2022 | 7 | SANJOY PATRA | 1.84 | 0 | 0
33 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora G.P - chandar Name of Village - Kadakuli man para . Total House Hold - 70 Tender No - 04/20-21/EE/BQA W/O NO - 556/BSD dt. 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000606/2021-2022 | FHTC/15 | 05/05/2021 | 0 | GON ASSOCIATES | 4.24 | 0 | 0
34 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kodalia(PART-B), Total House Hold -429 | Assistant Engineer | Junior Engineer | VCH/002486/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 7.18 | 0 | 0
35 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003050/2021-2022 | FHTC/28 | 28/03/2022 | 0 | DEBAKI RANJAN SARKAR | 0.84 | 0 | 0
36 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, ( Simla, Bank simul, Nekrakuada ) Total House Hold - 499 | Assistant Engineer | Junior Engineer | VCH/003100/2021-2022 | FHTC/28 | 28/03/2022 | 0 | M/S TARUN KUMAR PATRA | 37.54 | 0 | 0
37 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43, Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 130 |  | Junior Engineer | ORD/000021/2020-2021 | 617/BQA | 10/02/2021 | 30 | I.R.CONSTRUCTION | 9.86 | 18.8 | 0
38 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 |  | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 28.91 | 17.17 | 95
39 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 05, (Kesekol (PART), Domanbandhi, Kumuria, Tilabedia & Kamladanga), Total House Hold - 516 |  | Junior Engineer | ORD/000066/2020-2021 | 469/BQA | 05/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.2 | 0 | 100
40 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 01, (Kesekol (PART), Total House Hold - 517 ( Sl .No.- 20 ) |  | Junior Engineer | ORD/000176/2020-2021 | 719/BQA | 19/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.25 | 0 | 100
41 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 30 | NAYAN BARDHAN | 14.75 | 3.38 | 0
42 | Bankura Division | Bankura Sadar Sub-Division | Extension of UPVC distribution of Cherabastar (Zone - K) to cover Sapagara village under Bankura I, II & Barjora Block water supply scheme (BRGF Phase - I) project under Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001136/2021-2022 | FHTC/23 | 23/07/2021 | 0 | SUBHADIP KOLEY | 4.72 | 0 | 0
43 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , |  | Junior Engineer | VCH/001133/2021-2022 | FHTC/23 | 23/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0
44 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Purandarpur & Kanchanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001134/2021-2022 | FHTC/23 | 23/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.35 | 0 | 0
45 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) & KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Bankura- II, Name of OHR- 1) Tilabedia, 2) Khyerkanali, No. of Mouza :- 25 nos (Mouladanga, Mithila, Jagannathbati, raghunathpur, Manoharpur, Mohanpur, Kesekol, Domanbandhi, Kumuria, Tilabedia, Kamladanga, Bambanpur, Nabada, Sibarampur, Churamonipur, Khyerkanali, Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalaphar, Kaljuri, Muraboni & Rasiknagarpur), Total House Hold = 3931 nos. |  | Junior Engineer | VCH/001337/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 1.24 | 0 | 0
46 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kesiakole Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block |  | Junior Engineer | VCH/001479/2021-2022 |  | 08/10/2021 | 0 | PARAMESWAR CHOWDHURY | 3.95 | 0 | 0
47 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 |  | Junior Engineer | VCH/001487/2021-2022 | FHTC/03 | 03/11/2021 | 0 | BEAUTY CHATTERJEE | 7.46 | 0 | 0
48 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., |  | Junior Engineer | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0
49 | Bankura Division | Bankura Sadar Sub-Division | Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | VCH/002299/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0
50 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 07 ( Duldihi, Kamlagora, Kalapathar, Rangameta, Basulitara, Jambedia, & Anandapur). Total House Hold - 696 | Assistant Engineer | Junior Engineer | ORD/000493/2022-2023 | 372/BQA | 23/02/2023 | 768 | TAPAS KUMAR HAZRA | 41.95 | 17.27 | 51
51 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme Kushtora ZONE- W under Bankura - l - ll & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - B Block - Bankura -l, name of OHR - Kushtora ZONE- W . - No.of Mouza :- 01 no., (Poryasol) Total House Hold - 50. | Assistant Engineer | Junior Engineer | VCH/002993/2021-2022 | FHTC/22 | 22/03/2022 | 0 | KHAN ENTERPRISE | 2.75 | 0 | 0
52 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme Kustora ZONE- W under Bankura - l - ll & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - A Block - Bankura -l, name of OHR - Kushtora ZONE- W . - No.of Mouza :- 01 no., (Poryasol) Total House Hold - 60. | Assistant Engineer | Junior Engineer | VCH/002994/2021-2022 | FHTC/22 | 22/03/2022 | 0 | KHAN ENTERPRISE | 4.24 | 0 | 0
53 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Kherkanali No.of Mouza :- 01 nos. ( Kaljuri)Total House Hold -120 nos. |  | Junior Engineer | ORD/000011/2022-2023 | 895/BQA | 14/04/2022 | 30 | MOHAN KUMAR ROY | 14.36 | 0 | 0
54 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 20.48 | 0
55 | Bankura Division | Bankura Sadar Sub-Division | Additional UPVC Pipe Line for increasing pressure in existing distribution pipe line of Belboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000382/2021-2022 | 989/ BSD | 25/11/2021 | 15 | M/S TARUN KUMAR PATRA | 2.11 | 0 | 0
56 | Bankura Division | Bankura Sadar Sub-Division | Restoration of concrete road at Belboni, Agya Nandapur & Kaljuri mouzas for construction and commissioning of "FHTC" (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000383/2021-2022 | 990/ BSD | 25/11/2021 | 15 | M/S TARUN KUMAR PATRA | 4.94 | 0 | 0
57 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 83.12 | 0
58 | Bankura Division | Bankura Sadar Sub-Division | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. , |  | Junior Engineer | VCH/001595/2021-2022 | FHTC/08 | 08/10/2021 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.14 | 0 | 0
59 | Bankura Division | Bankura Sadar Sub-Division | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. ( month of July - 2021) |  | Junior Engineer | VCH/001596/2021-2022 | FHTC/08 | 08/10/2021 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.99 | 0 | 0
60 | Bankura Division | Bankura Sadar Sub-Division | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. (month of July - 2021 to Sep 2021) |  | Junior Engineer | VCH/001597/2021-2022 | FHTC/08 | 08/10/2021 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.13 | 0 | 0
61 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line to increase pressure at nabanda mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000448/2022-2023 | 621/BSD | 16/08/2022 | 21 | KOUSHIK GUPTA KABIRAJ | 2.13 | 0 | 100
62 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Khyarkanali village to makurgram chatarkanali main road to increase pressure to kaljuri mouza of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. TSM/010428. |  | Junior Engineer | ORD/000498/2022-2023 | 376/BQA | 23/02/2023 | 45 | MOHAN KUMAR ROY | 2.4 | 0 | 100
63 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  | Junior Engineer | VCH/001590/2021-2022 | FHTC/08 | 08/10/2021 | 0 | KASTURI ROY | 2.17 | 0 | 0
64 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No.- 11), |  | Junior Engineer | VCH/001591/2021-2022 | FHTC/08 | 08/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.94 | 0 | 0
65 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 10), |  | Junior Engineer | VCH/001592/2021-2022 | FHTC/08 | 08/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.96 | 0 | 0
66 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Koskunda), |  | Junior Engineer | VCH/001593/2021-2022 | FHTC/08 | 08/10/2021 | 0 | ASHISH KUMAR SAMANTA | 4.03 | 0 | 0
67 | Bankura Division | Bankura Sadar Sub-Division | Festival bonus for laboratory personnel engaged through NGO |  | Junior Engineer | VCH/001598/2021-2022 | FHTC/08 | 08/10/2021 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.14 | 0 | 0
68 | Bankura Division | Bankura Sadar Sub-Division | Prayer for release fund for laboratory personal's for the month of Aug 2021 to Sep 2021 |  | Junior Engineer | VCH/001599/2021-2022 | FHTC/08 | 08/10/2021 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.66 | 0 | 0
69 | Bankura Division | Bankura Sadar Sub-Division | Prayer for release fund for laboratory personal's for the month of May 2021 to Aug 2021 |  | Junior Engineer | VCH/001600/2021-2022 | FHTC/08 | 08/10/2021 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.12 | 0 | 0
70 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 68 (Sl No of Work- 11) |  | Junior Engineer | VCH/001594/2021-2022 | FHTC/08 | 08/10/2021 | 0 | PRABIR BARDHAN | 0.77 | 0 | 0
71 | Bankura Division | Bankura Sadar Sub-Division | Prayer for release fund for laboratory personal's for the month of June 2021 to Aug 2021 |  | Junior Engineer | VCH/001601/2021-2022 | FHTC/08 | 08/10/2021 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.99 | 0 | 0
72 | Bankura Division | Bankura Sadar Sub-Division | Prayer for release fund for laboratory personal's for the month of April 2016 to jUNE 2021 , |  | Junior Engineer | VCH/001602/2021-2022 | FHTC/08 | 08/10/2021 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.99 | 0 | 0
73 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 13), |  | Junior Engineer | VCH/001635/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 3.63 | 0 | 0
74 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 12) |  | Junior Engineer | VCH/001785/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0
75 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 ( PART-B House Hold - 1284) |  | Junior Engineer | ORD/000063/2021-2022 | 2197/BQA | 25/08/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 112.13 | 0 | 0
76 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | ORD/000064/2021-2022 | 2198/BQA | 25/08/2021 | 30 | M/S TARUN KUMAR PATRA | 112.13 | 0 | 0
77 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Sanabandh), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Sanabandh) Total House Hold - 937 nos. |  | Junior Engineer | VCH/002685/2021-2022 | FHTC/2 | 02/03/2022 | 0 | NEW STAR CONSTRUCTION | 45.07 | 0 | 0
78 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE, GI & MS pipe line from Air valve of Saulia OHR Rising main (Near Talanda village) to Gopinath pur Mouza to increase pressure along with all allied works of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000138/2022-2023 | 565/BSD | 29/07/2022 | 30 | TARINI CHARAN UPADHYAY | 4.79 | 0 | 50
79 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 22.33 | 0
80 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456 |  | Junior Engineer | ORD/000265/2020-2021 | 2064/BQA | 29/12/2020 | 30 | MUNMUN UPADHYAY | 36.39 | 0 | 0
81 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 02 (Brindabanpur & Kodma), Total House Hold -470 |  | Junior Engineer | ORD/000266/2020-2021 | 2065/BQA | 29/12/2020 | 30 | SIB SANKAR CHOWDHURY | 37.54 | 0 | 0
82 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 02 (Talanda, Harishpur), Total House Hold -130 |  | Junior Engineer | ORD/000267/2020-2021 | 2066/BQA | 29/12/2020 | 30 | I.R.CONSTRUCTION | 10.4 | 0 | 0
83 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) , Name of mouza -Kodma , (Part-B) |  | Junior Engineer | ORD/000351/2021-2022 | 679/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 2.66 | 0 | 0
84 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) , Name of mouza -Kodma , (Part-A) |  | Junior Engineer | ORD/000352/2021-2022 | 676/ BSD | 11/06/2021 | 10 | SIB SANKAR CHOWDHURY | 4.35 | 0 | 0
85 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Harishpur & Mathur Beria mouzas of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000517/2021-2022 | 240/BSD | 15/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.88 | 0 | 0
86 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Brindabonpur mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000522/2021-2022 | 208/BSD | 11/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.98 | 0 | 0
87 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 09) |  | Junior Engineer | VCH/001009/2021-2022 |  | 14/09/2021 | 0 | MUNMUN UPADHYAY | 4.83 | 0 | 0
88 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 07) |  | Junior Engineer | VCH/001010/2021-2022 |  | 14/09/2021 | 0 | TARINI CHARAN UPADHYAY | 3.57 | 0 | 0
89 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Harishpur & Mathur Beria mouzas of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  | Junior Engineer | VCH/001236/2022-2023 | FHTC/28 | 28/09/2022 | 0 | SIB SANKAR CHOWDHURY | 4.83 | 0 | 0
90 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001608/2021-2022 | FHTC/07 | 07/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.95 | 0 | 0
91 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) , Dharmapur (133) Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura Under Jal Swapna & Jal Jeevan Mission Programme., |  | Junior Engineer | VCH/001609/2021-2022 | FHTC/07 | 07/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.98 | 0 | 0
92 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) |  | Junior Engineer | VCH/002310/2021-2022 | FHTC/20 | 20/01/2022 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 16.51 | 0 | 0
93 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 05(Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurdanga), Total House Hold -451 ( Sl .No.- 14) |  | Junior Engineer | ORD/000167/2020-2021 | 713/BQA | 19/02/2021 | 30 | SIB SANKAR CHOWDHURY | 41.68 | 0 | 0
94 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 ( Srikrishnapur, Gangabundh, Saulia), Total House Hold -467 ( Sl .No.- 15) |  | Junior Engineer | ORD/000168/2020-2021 | 714/BQA | 19/02/2021 | 30 | SIB SANKAR CHOWDHURY | 43.23 | 68.35 | 0
95 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 02 ( Mathurberia,Rajmadhabpur), Total House Hold -138 ( Sl .No.- 16) |  | Junior Engineer | ORD/000170/2020-2021 | 715/BQA | 19/02/2021 | 30 | I.R.CONSTRUCTION | 12.82 | 0 | 0
96 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Ganga Bandh mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000520/2021-2022 | 233/BSD | 15/03/2022 | 10 | SIB SANKAR CHOWDHURY | 2.8 | 2.77 | 0
97 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000521/2021-2022 | 210/BSD | 11/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.99 | 0 | 0
98 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633' |  | Junior Engineer | VCH/000216/2022-2023 | FHTC/08 | 08/04/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 8.22 | 0 | 0
99 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605' |  | Junior Engineer | VCH/000217/2022-2023 | FHTC/08 | 08/04/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 6.47 | 0 | 0
100 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576' |  | Junior Engineer | VCH/000218/2022-2023 | FHTC/08 | 08/04/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 12.5 | 0 | 0
101 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 04 |  | Junior Engineer | VCH/001241/2022-2023 | FHTC/28 | 28/09/2022 | 0 | SIB SANKAR CHOWDHURY | 4.94 | 0 | 0
102 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
103 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. |  | Junior Engineer | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0
104 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 45 | UNICON INDIA | 317.75 | 0 | 100
105 | Bankura Division | Brishnupur Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001011/2021-2022 | FHTC/23 | 23/11/2021 | 0 | MUNMUN UPADHYAY | 3.97 | 0 | 0
106 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 03 nos, ( Ampahari, Gopinathpur, Chakchaki,) Total House Hold - 518 | Assistant Engineer | Junior Engineer | VCH/001489/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SUMITA UPADHYAY | 32.36 | 0 | 0
107 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, Khyerkanali (PART-1) Total House Hold - 145 | Assistant Engineer | Junior Engineer | VCH/001514/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PRADIP CHAKRABORTY | 11.26 | 0 | 0
108 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 | Assistant Engineer | Junior Engineer | VCH/001750/2021-2022 | FHTC/23 | 23/11/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 74.71 | 0 | 0
109 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Kendboni to Lapuria Village & Garakusum village to increase presure in Lapuria & Garakusum mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (ZONE-P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000136/2022-2023 | 472/BSD | 06/06/2022 | 15 | ASHIS KUMAR SAMANTA | 4.95 | 0 | 0
110 | Bankura Division | Bankura Sadar Sub-Division | "Name of Work: Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 02, (Karanjora, Lapuria (PART)), Total House Hold - 606" |  | Junior Engineer | ORD/000319/2020-2021 | 1369/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.67 | 0 | 100
111 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" |  | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 0 | 0
112 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line to increase pressure at lapuria mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000436/2022-2023 | 622/BSD | 16/08/2022 | 21 | ASHIS KUMAR SAMANTA | 3.76 | 0 | 100
113 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001334/2021-2022 |  | 28/09/2021 | 0 | SOUMITRA BHATTACHARYA | 4.51 | 0 | 0
114 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001336/2021-2022 |  | 28/09/2021 | 0 | SOUMITRA BHATTACHARYA | 4.66 | 0 | 0
115 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Kotasol (108) , Chiltere (109) & Jhola (110) mouza by retrofitting zone - ll piped water supply for Chiltore & its adjoining mouzas at block - Sarenga dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. ( MB No - 3909) |  | Junior Engineer | VCH/001573/2020-2021 | FHTC/280 | 12/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 33.72 | 0 | 0
116 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
117 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001991/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
118 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001993/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.26 | 0 | 0
119 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001994/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
120 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001996/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
121 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001998/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
122 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-3,(Nabanda, Kantapahari(Part) Haridi) Total House Hold - 402 |  | Junior Engineer | ORD/000037/2020-2021 | 639/BQA | 10/02/2021 | 30 | SOUMITRA BHATTACHARYA | 33.83 | 0 | 0
123 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-2,(Karkari, Kantapahari(Part) ) Total House Hold - 402 |  | Junior Engineer | ORD/000038/2020-2021 | 640/BQA | 10/02/2021 | 30 | M/S BIPUL BANERJEE | 33.79 | 0 | 0
124 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-2,(Karkari, Kantapahari(Part) ) Total House Hold - 402 |  | Junior Engineer | VCH/000470/2022-2023 | FHTC/16 | 16/06/2022 | 0 | M/S BIPUL BANERJEE | 25.53 | 0 | 0
125 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash (Zone - B) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur Name of OHR - Gumut No.of Mouza :- 02 nos, Beliara - 66, Dejjat - 66 Total House Hold - 977 |  | Junior Engineer | VCH/002688/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PARAMESWAR CHOWDHURY | 60.61 | 0 | 0
126 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 278 Nos.' |  | Junior Engineer | VCH/002692/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SRIKANTA MONDAL | 10.55 | 0 | 0
127 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Rajsol (41) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - B Sl no - 17 |  | Junior Engineer | VCH/002695/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S TARUN KUMAR PATRA | 2.11 | 0 | 0
128 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002723/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 0.51 | 0 | 0
129 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Naria (29) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002725/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 0.45 | 0 | 0
130 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 03 nos, (Brindajam, Simulbedia, Dhatala) Total House Hold -384 |  | Junior Engineer | ORD/000025/2021-2022 | 1800/BQA | 09/07/2021 | 30 | GOUTAM BHOUMIK | 25.05 | 4.5 | 0
131 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 02 nos, (Moyragora, Jaynagar) Total House Hold - 146 |  | Junior Engineer | ORD/000026/2021-2022 | 1801/BQA | 09/07/2021 | 30 | M/S BANERJEE & BANERJEE | 10.14 | 0 | 0
132 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 01 no, (Hatjore) Total House Hold - 149 |  | Junior Engineer | ORD/000046/2021-2022 | 1802/BQA | 09/07/2021 | 30 | GOUTAM GHOSH | 10.74 | 0 | 0
133 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 04 nos, (Kaminbedia, Sihikapahari, Dubra, Tilna) Total House Hold - 429 |  | Junior Engineer | ORD/000056/2021-2022 | 1932/BQA | 28/07/2021 | 30 | PARAMESWAR CHOWDHURY | 28.35 | 0 | 0
134 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :-Hatjore Total House Hold :- 15 nos. |  | Junior Engineer | ORD/000207/2022-2023 | 343/KSD | 16/08/2022 | 20 | GOUTAM GHOSH | 1.08 | 1.08 | 0
135 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe line to cover Hatjor mouza for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILNA (Zone- E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000294/2021-2022 | 960/ BSD | 29/10/2021 | 15 | GOUTAM GHOSH | 2.18 | 0 | 0
136 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 53.39 | 0
137 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction of concrete at Brindajam, Simulbedia, Dhatala for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000450/2022-2023 | 351/KSD | 16/08/2022 | 20 | GOUTAM BHOWMIK | 1.31 | 1.11 | 0
138 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, Name of Mouza :- Moyragora, Total House Hold :- 09 nos |  | Junior Engineer | ORD/000513/2022-2023 | 253/KSD | 12/07/2022 | 15 | M/S BANERJEE & BANERJEE | 3.22 | 1.77 | 0
139 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 02 nos, (Moyragora, Jaynagar) Total House Hold - 146 |  | Junior Engineer | VCH/000221/2022-2023 | FHTC/08 | 08/04/2022 | 0 | M/S BANERJEE & BANERJEE | 3.99 | 0 | 0
140 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (115 out of 714), House Hold - 115 |  | Junior Engineer | VCH/002381/2021-2022 | FHTC/19 | 19/02/2022 | 0 | PRASANTA BHUIN | 8.81 | 0 | 0
141 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Arrah (Part), Khudrabanagram mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandyagal (Zone-F ) under Chhatna Block Saltora-Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/002382/2021-2022 | FHTC/19 | 19/02/2022 | 0 | NAYAN BARDHAN | 4.99 | 0 | 0
142 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madandihi (101) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) |  | Junior Engineer | VCH/002383/2021-2022 | FHTC/19 | 19/02/2022 | 0 | BISWAJIT LAI | 3.86 | 0 | 0
143 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 ,Gadardihi (PART-B ), Total House Hold - 115 |  | Junior Engineer | VCH/002607/2021-2022 | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.34 | 0 | 0
144 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-E), Total House Hold - 114 |  | Junior Engineer | VCH/002608/2021-2022 | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.08 | 0 | 0
145 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 2 nos, Dhapali, Laxmanpur, Total House Hold -341 . |  | Junior Engineer | VCH/002610/2021-2022 | FHTC/26 | 26/02/2022 | 0 | ASHOKE KUMAR DEY | 19.25 | 0 | 0
146 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe 15 mm NB pvC 9schedule 80/20 mm OD HDPE (pE 100,Ph 16) toRetrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilbaid(Zone- F) under Saltora Block under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002611/2021-2022 | FHTC/26 | 26/02/2022 | 0 | MANAS DEY | 4.79 | 0 | 0
147 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 ( Chhendua, Chamkara, Fengabasa, Purandihi, Amlatara, Kumidya, Penchaldihi, Siarbada & Deba) Total House Hold - 994 |  | Junior Engineer | ORD/000375/2020-2021 | 207/BQA | 19/01/2021 | 30 | SWAPAN KUMAR UPADHYAY | 70.51 | 0 | 100
148 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Rangamati), Total House Hold- 43 nos. |  | Junior Engineer | ORD/000659/2021-2022 | 219/BSD | 11/03/2022 | 10 | GOURANGA NANDI | 2.16 | 2.15 | 0
149 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Debo & Purundi mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol (Zone- V) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000700/2021-2022 | 823/BSD | 06/08/2021 | 15 | SWAPAN KUMAR UPADHYAY | 4.84 | 2.41 | 0
150 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Fengabasa & Amlatora mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol (Zone- V) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000797/2021-2022 | 824/BSD | 06/08/2021 | 15 | TARINI CHARAN UPADHYAY | 4.84 | 0 | 35
151 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001606/2021-2022 | FHTC/07 | 07/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.11 | 0 | 0
152 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Kaliapathar (89) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001607/2021-2022 | FHTC/07 | 07/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.26 | 0 | 0
153 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001608/2021-2022 | FHTC/07 | 07/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.95 | 0 | 0
154 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Arkama (124) & Hazamdihi (233) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001658/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UNITED TRADERS | 4.76 | 0 | 0
155 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SOMSAR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Somsar, No. of Mouza :- 01 no. i.e. (Somsar-02), Total House Hold - 1058, |  | Junior Engineer | VCH/001659/2021-2022 | FHTC/28 | 28/10/2021 | 0 | M/S K.B.CONSTRUCTION | 42.97 | 0 | 0
156 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Routara (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, No.of Mouza :- 02 (Routara,Bagjada ) Total House Hold - 533., |  | Junior Engineer | VCH/001660/2021-2022 | FHTC/28 | 28/10/2021 | 0 | SUBHENDU SEKHAR GORAI | 20.58 | 0 | 0
157 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
158 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 |  | Junior Engineer | VCH/003099/2021-2022 | FHTC/30 | 30/03/2022 | 0 | MUNMUN UPADHYAY | 35.35 | 0 | 0
159 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576" | Assistant Engineer | Junior Engineer | ORD/000317/2020-2021 | 1367/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0
160 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633" | Assistant Engineer | Junior Engineer | ORD/000318/2020-2021 | 1368/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.68 | 0 | 0
161 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line to increase pressure at teleghra'banki,narrah karmakarpara,sayanipara, adra,paschim ratanpur & sibrampur tantipara for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) & CHERABASTA (ZONE-K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2022-2023 | 609/BSD | 16/08/2022 | 21 | COSMIC CONSTRUCTION | 4.99 | 0 | 0
162 | Bankura Division | Bankura Sadar Sub-Division | Road restoration works at Khyarkanali, Belboni, Cherabasta, Uparbandh, Sirsara, Banki, Pratappur, Sendra & Narrah mouzas of Bankura-II block under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000673/2023-2024 | 810/BSD | 10/08/2023 | 7 | TARUN KUMAR BHATTACHARYYA | 0.95 | 0 | 100
163 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to Cover Pratappur , Balarampur, Telegarah, Chapatara & Sendra Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000848/2021-2022 |  | 01/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.59 | 0 | 0
164 | Bankura Division | Bankura Sadar Sub-Division | Engagement of Computer Operator (Category - A) for office work of the Assistant Engineer, Bankura Sadar Sub - Division PHE Dte. of 01.08.20 to 31.07.21 ( 12 months) (Dec 20 & Jan - 2021) | Assistant Engineer | Junior Engineer | VCH/001564/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | ABHIJIT MALAKAR | 0.34 | 0 | 0
165 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Superinteding Engineer, PIU Bankura, WBDWSIP P.H.E. Dte. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Dec 20 & Jan - 2021) | Assistant Engineer | Junior Engineer | VCH/001565/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | M/S BHATTACHARJEE & CO , | 0.36 | 0 | 0
166 | Bankura Division | Bankura Sadar Sub-Division | Engagement of one(1) no qualified computer operator ( Category-A) in computer application (one year) for office of the Assistant Engineer, RWS Bankura Sub - Division PHE Dte. (01.08.20 to 31.07.21 ( 12 months) | Assistant Engineer | Junior Engineer | VCH/001566/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | BANASRI KUNDU | 0.73 | 0 | 0
167 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Jan - 2021) | Assistant Engineer | Junior Engineer | VCH/001567/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | RAJU DUTTA | 0.18 | 0 | 0
168 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 06 nos, (Akurbad, Banki, Matranga, Pratappur, Balarampur & Teleghra.) Total House Hold - 1209. | Assistant Engineer | Junior Engineer | VCH/001345/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
169 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576" | Assistant Engineer | Junior Engineer | VCH/001390/2020-2021 |  | 01/03/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 28.72 | 0 | 0
170 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 ( MB No - 3993)" | Assistant Engineer | Junior Engineer | VCH/001423/2020-2021 |  | 01/03/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 38.44 | 0 | 0
171 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) | Assistant Engineer | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
172 | Bankura Division | Bankura Sadar Sub-Division | " Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 . ( MB No - 3775)" | Assistant Engineer | Junior Engineer | VCH/001549/2020-2021 | FHTC/283 | 22/02/2021 | 0 | AJIT KUMAR PAUL | 10.59 | 0 | 0
173 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Executive Engineer, Bankura Division, P.H.E. Dte.. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Jan - 2021) | Assistant Engineer | Junior Engineer | VCH/001568/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | RAJESH SHARMA | 0.18 | 0 | 0
174 | Bankura Division | Bankura Sadar Sub-Division | Engagement of one(1) no qualified computer operator ( Category-C) in computer application for Account Section of office of the Executive Engineer, Bankura Division PHE Dte. ( 01/03/20 to 28/02/21) (Jan - 2021) | Assistant Engineer | Junior Engineer | VCH/001569/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 0 | SIMA GORAI | 0.14 | 0 | 0
175 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Bangaria & Hirakon mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001918/2020-2021 | FHTC/294 | 01/03/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.31 | 0 | 0
176 | Bankura Division | Bankura Sadar Sub-Division | " Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 . ( MB No - 3775)" | Assistant Engineer | Junior Engineer | VCH/001550/2020-2021 | FHTC/283 | 22/02/2021 | 0 | TAPAS DEY | 10.63 | 0 | 0
177 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (252) , Labdapara (265) & Birkham (266) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3952) | Assistant Engineer | Junior Engineer | VCH/001551/2020-2021 | FHTC/283 | 22/02/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 3.7 | 0 | 0
178 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A ( MB No - 3951) | Assistant Engineer | Junior Engineer | VCH/001554/2020-2021 | FHTC/283 | 22/02/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 3.18 | 0 | 0
179 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B ( MB No - 3951) | Assistant Engineer | Junior Engineer | VCH/001555/2020-2021 | FHTC/283 | 22/02/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 3.34 | 0 | 0
180 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part -A ( MB No - 3952) | Assistant Engineer | Junior Engineer | VCH/001556/2020-2021 | FHTC/283 | 22/02/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.51 | 0 | 0
181 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part -B ( MB No - 3952) | Assistant Engineer | Junior Engineer | VCH/001557/2020-2021 | FHTC/283 | 22/02/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.72 | 0 | 0
182 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 |  | Junior Engineer | ORD/000027/2020-2021 | 629/BQA | 10/02/2021 | 30 | SUBHENDU SEKHAR GORAI | 18.25 | 32.65 | 0
183 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Guniada (1) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000131/2020-2021 | 188/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 27.87 | 25.34 | 90
184 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Sonadaha(part), Total House Hold -137" |  | Junior Engineer | ORD/000335/2020-2021 | 1704/BQA | 08/12/2020 | 30 | TARINI CHARAN UPADHYAY | 9.72 | 14.8 | 0
185 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06, Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah (PART), Total House Hold - 528." |  | Junior Engineer | ORD/000345/2020-2021 | 1770/BQA | 09/12/2020 | 30 | SWAPAN KUMAR CHANDRA | 37.21 | 0 | 100
186 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Narrah (Part) mouza for construction and commissioning of "FHTC" (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000374/2021-2022 | 988/ BSD | 25/11/2021 | 15 | ALOK ENTERPRISE | 1.61 | 0 | 0
187 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 01 , Narrah(PART), Total House Hold - 528." |  | Junior Engineer | ORD/000395/2020-2021 | 1554/BQA | 18/11/2020 | 30 | J. D. J. ENTERPRISE | 37.68 | 0 | 100
188 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATERKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chaterkanali, No. of Mouza :- 01 no. Narra, Total House Hold- 60 nos. |  | Junior Engineer | ORD/001031/2021-2022 | 260/BSD | 15/03/2022 | 10 | M/S TARUN KUMAR PATRA | 4.46 | 0 | 100
189 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban, No.of Mouza :- 1, Kumirdoha (PART) Total House Hold - 65. , |  | Junior Engineer | VCH/000267/2021-2022 | FHTC/12 | 23/04/2021 | 0 | PRASANTA BHUIN | 3.88 | 0 | 0
190 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Maliara, Kotulpur, Kanchanpur , Dadhimukha, , No Of Mouzas-68 , Total House Hold - 14124. |  | Junior Engineer | VCH/000272/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS DEY | 2.23 | 0 | 0
191 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06 nos, (Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah), Total House Hold - 1056. |  | Junior Engineer | VCH/001347/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
192 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 04 nos, (Talandanga, Upar Narrah, Chhatarkanali, Rampur, ), Total House Hold - 530 |  | Junior Engineer | VCH/001420/2020-2021 |  | 01/03/2021 | 0 | M/S TARUN KUMAR PATRA | 31.8 | 0 | 0
193 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 01 , Narrah(PART), Total House Hold - 528. ( MB No - 3994)" |  | Junior Engineer | VCH/001429/2020-2021 |  | 01/03/2021 | 0 | J. D. J. ENTERPRISE | 25.6 | 0 | 0
194 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 12 Nos. ( Helna, Fagua kanali, Dumuria, Chaturdihi, Chattardihi, Paharia, Baikudihi, Kankardihi, Jethia, Dalpur, Krishnanagar & Manjura. ) Total House Hold - 1063 |  | Junior Engineer | ORD/000042/2020-2021 | 644/BQA | 10/02/2021 | 300 | GOPAL CHANDRA CHOUDHURY | 92.19 | 0 | 0
195 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000114/2020-2021 | 172/BQA | 18/02/2021 | 30 | GANESH ROY | 18.65 | 25.24 | 0
196 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Manjura mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000564/2021-2022 | 838/BSD | 18/08/2021 | 15 | SUBHADIP KOLEY | 4.52 | 3.92 | 0
197 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malcharar (100) mouzas zone - 0 (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte part - B |  | Junior Engineer | VCH/001245/2021-2022 | FHTC/25 | 25/08/2021 | 0 | TAPAN KUMAR MANDAL | 3.32 | 0 | 0
198 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001250/2021-2022 | FHTC/13 | 13/08/2021 | 0 | UNITED TRADERS | 3.36 | 0 | 0
199 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - barjora G.P chandar, Name of OHR - Lobason bauri para, chandar shib Total House Hold - 50 no - 03. |  | Junior Engineer | VCH/001256/2021-2022 | FHTC/02 | 02/08/2021 | 0 | M/S PAUL BROTHERS | 4.27 | 0 | 0
200 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (FunCtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dangalan, No. of Mouza :- 09 nos. i.e. Banki-85, Chotogobindapur-86, Adilpur-87 & Haldi-83, Mandra-88, Berghosh-84, Dangalan-91, Musarbar-92 & Ashwinpur-93, Total House Hold - 2639 | Assistant Engineer | Junior Engineer | ORD/000302/2021-2022 | 3349/BQA | 30/12/2021 | 60 | J. D. J. ENTERPRISE | 206.26 | 48 | 65
201 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2021-2022 | 481/BQA | 04/03/2022 | 0 | Resource Division | 14.51 | 0 | 0
202 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (FunCtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dangalan, No. of Mouza :- 09 nos. i.e. Banki-85, Chotogobindapur-86, Adilpur-87 & Haldi-83, Mandra-88, Berghosh-84, Dangalan-91, Musarbar-92 & Ashwinpur-93, Total House Hold - 2639 | Assistant Engineer | Junior Engineer | VCH/001245/2022-2023 | FHTC/29 | 29/09/2022 | 0 | J. D. J. ENTERPRISE | 77 | 0 | 0
203 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Heyatnagar, No. of Mouza :- 8 nos. i.e. Srikara-31, Padua-11, Adpara Kumrul-12, Sripur-26, Heyatnagar-27, Maheshpur-28, Meral-29 & Chakmeral-30, Total House Hold - 2465 | Assistant Engineer | Junior Engineer | VCH/002445/2021-2022 | FHTC/18 | 18/02/2022 | 0 | JAYANTA KUMAR MONDAL | 140.85 | 0 | 0
204 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002453/2021-2022 | FHTC/15 | 15/02/2022 | 0 | PARAMESWAR CHOWDHURY | 3.19 | 0 | 0
205 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas, | Assistant Engineer | Junior Engineer | VCH/002455/2021-2022 | FHTC/15 | 15/02/2022 | 0 | SUMITA UPADHYAY | 4.89 | 0 | 0
206 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
207 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Heyatnagar, No. of Mouza :- 8 nos. i.e. Srikara-31, Padua-11, Adpara Kumrul-12, Sripur-26, Heyatnagar-27, Maheshpur-28, Meral-29 & Chakmeral-30, Total House Hold - 2465 | Assistant Engineer | Junior Engineer | VCH/002865/2021-2022 | FHTC/15 | 15/03/2022 | 0 | JAYANTA KUMAR MONDAL | 31.74 | 0 | 0
208 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2021-2022 | 2769/BQA | 08/11/2021 | 30 | SUBHADIP KOLEY | 42.21 | 0 | 0
209 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) | Assistant Engineer | Junior Engineer | ORD/000594/2021-2022 | 797/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.31 | 0 | 0
210 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000457/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.27 | 0 | 0
211 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
212 | Bankura Division | Khatra Sub-Division | Reconstruction concrete at Jolhari mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001501/2022-2023 | FHTC/27 | 27/12/2022 | 0 | TAPAS KUMBHAKAR | 4.31 | 0 | 0
213 | Bankura Division | Khatra Sub-Division | Supplying laying by UPVC pipe for distribution network along with ancillary works at village karbhanga due to strengthening widening of Sarenga Chowrasta more to Goaltore Road under Gargaria Zone -B water supply scheme (BRGF phase -I) part - B under Jal Swapna & Jal Jeevan Mission Programme under Bankura Khatra Sub - Division of Bankura Division, PHE Dte. sl no 14 | Assistant Engineer | Junior Engineer | VCH/001503/2021-2022 |  | 22/11/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.87 | 0 | 0
214 | Bankura Division | Khatra Sub-Division | Laying Extra 15 mm NB PVC (schedule 80) /20 mm OD HDPE Pipe to cover Paharghata, Begdiha, Hapania mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- d) under Saltora- Block saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002761/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SIB SANKAR CHOWDHURY | 5 | 0 | 0
215 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002762/2021-2022 | FHTC/4 | 04/03/2022 | 0 | MUNMUN UPADHYAY | 34.71 | 0 | 0
216 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC pipe line to cover Jiakanali ( 274) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - IIA (Baragari) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002766/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU BANERJEE | 3.83 | 0 | 0
217 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC pipe line to cover Jiakanali ( 274) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - IIA (Baragari) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. part - A | Assistant Engineer | Junior Engineer | VCH/002767/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU BANERJEE | 4.91 | 0 | 0
218 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Dhadanga (97 ) & Haludkanali (102) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- O (Madandihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 15 | Assistant Engineer | Junior Engineer | VCH/002769/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU BANERJEE | 3.35 | 0 | 0
219 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Dhadanga (97 ) & Haludkanali (102) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- O (Madandihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - B sl no - 16 | Assistant Engineer | Junior Engineer | VCH/002771/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU BANERJEE | 3.47 | 0 | 0
220 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to increase pressure at Asna (287) mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Garharya (Zone - B) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002905/2021-2022 | FHTC/21 | 21/03/2022 | 0 | PRADYUMNA KOLEY | 4.87 | 0 | 0
221 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to increase pressure at Baligura (286), Chhotagarra ( 288) & Chingra ( 292) mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Garharya (Zone - B) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002906/2021-2022 | FHTC/21 | 21/03/2022 | 0 | PRADYUMNA KOLEY | 4.92 | 0 | 0
222 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhengasole W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Dhengasole, No. of Mouza :- 05 nos. i.e. Dadasbari- 98, Jharia- 122, Bankati-123, Baraamlai-124 & Pedda-125, Total House Hold - 638 | Assistant Engineer | Junior Engineer | ORD/000197/2021-2022 | 3027/BQA | 29/11/2021 | 30 | BRINDABAN KONAR | 77.15 | 23.25 | 0
223 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. | Assistant Engineer | Junior Engineer | VCH/000661/2022-2023 | FHTC/27 | 27/09/2022 | 0 | S K FAZLUL ALAM | 4.81 | 0 | 0
224 | Bankura Division | Brishnupur Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply scheme for KANKI & its adjoining mouzas under Chhatna Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR:- Kanki, No.of Mouza :- 05 (Rajadal Bongaon Bikpur, Murgaboni & Kanki). Total House Hold - 438 nos. | Assistant Engineer | Junior Engineer | VCH/000884/2022-2023 | FHTC/23 | 23/09/2022 | 0 | TAPAN KUMAR MANDAL | 7.26 | 0 | 0
225 | Bankura Division | Brishnupur Sub-Division | Preparation of Detailed Project Report for Augmentation of Mukundapur Piped Water Supply Scheme, Block : Raipur, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/001198/2022-2023 | FHTC/30 | 30/09/2022 | 0 | SIRCON ENGINEERING SERVICES | 3.55 | 0 | 0
226 | Bankura Division | Brishnupur Sub-Division | Laying extra HDPE Pipe Line from OHR zone - ll to Dehulka village to increase water pressure for 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - l) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001199/2022-2023 | FHTC/30 | 30/09/2022 | 0 | DAUD ALI KHAN | 4.92 | 0 | 0
227 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | Assistant Engineer | Junior Engineer | VCH/001228/2022-2023 | FHTC/27 | 27/09/2022 | 0 | SAMIRUDDIN KHAN | 4.97 | 0 | 0
228 | Bankura Division | Brishnupur Sub-Division | Water supply arrangement at different Anganwari Center laying pipe line & installation SSP under Lurka Zone -A | Assistant Engineer | Junior Engineer | VCH/001243/2022-2023 | FHTC/23 | 23/09/2022 | 0 | M/S ABU KADER KHAN | 3.14 | 0 | 0
229 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line to cover Harishpur & Mathur Beria mouzas of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 09 | Assistant Engineer | Junior Engineer | VCH/001236/2022-2023 | FHTC/28 | 28/09/2022 | 0 | SIB SANKAR CHOWDHURY | 4.83 | 0 | 0
230 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001237/2022-2023 | FHTC/23 | 23/09/2022 | 0 | GON ASSOCIATES | 7.66 | 0 | 0
231 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 04 | Assistant Engineer | Junior Engineer | VCH/001241/2022-2023 | FHTC/28 | 28/09/2022 | 0 | SIB SANKAR CHOWDHURY | 4.94 | 0 | 0
232 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line to cover Brindabonpur mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001242/2022-2023 | FHTC/28 | 28/09/2022 | 0 | SIB SANKAR CHOWDHURY | 4.98 | 0 | 0
233 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | ORD/000255/2021-2022 | 3149/BQA | 15/12/2021 | 60 | KHAN ENTERPRISE | 219.37 | 13.79 | 0
234 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Functional House Hold Tap Connection)' for extra house hold and repairing and maintenance work in connection with Jal Jeevan Mission (JJM) of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 1 no. i.e. Abdulpur - 53 Total House Hold - 6. | Assistant Engineer | Junior Engineer | ORD/000647/2022-2023 | 46/VSD | 10/03/2023 | 25 | MOHAN KUMAR ROY | 0.96 | 0.96 | 100
235 | Bankura Division | Brishnupur Sub-Division | Supplying laying by UPVC pipe dor distribution network along with ancillary works at village khaterpahri due to strengthening - widening of Sarenga Chowrasta more to Goaltore road by PWD roads dte. under water supply scheme for Gargaria zone - B water supply scheme ( BRGF ph - l ) under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000468/2022-2023 | FHTC/16 | 16/06/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.8 | 0 | 0
236 | Bankura Division | Brishnupur Sub-Division | Supplying laying by UPVC pipe dor distribution network along with ancillary works at village Baragarra due to strengthening - widening of Sarenga Chowrasta more to Goaltore road by PWD roads dte. under water supply scheme for Gargaria zone - B water supply scheme ( BRGF ph - l ) under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000469/2022-2023 | FHTC/16 | 16/06/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.26 | 0 | 0
237 | Bankura Division | Brishnupur Sub-Division | Reconstruction concrete at Jolhari mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001501/2022-2023 | FHTC/27 | 27/12/2022 | 0 | TAPAS KUMBHAKAR | 4.31 | 0 | 0
238 | Bankura Division | Brishnupur Sub-Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui - 118) of Akui (Zone - A) under Indas Block under Bishnupur Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | VCH/002387/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 120.91 | 0 | 0
239 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 09 nos, (Kamalpur, Gopalpur), Total House Hold - 381 nos | Assistant Engineer | Junior Engineer | VCH/002776/2021-2022 | FHTC/4 | 04/03/2022 | 0 | BIJOY KOLEY | 22.62 | 0 | 0
240 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC Pipe Line to Cover Narrah (Part) mouza for construction and commissioning of 'FHTC' (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | VCH/002782/2021-2022 | FHTC/4 | 04/03/2022 | 0 | ALOK ENTERPRISE | 1.61 | 0 | 0
241 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in , Santor (95) & Birsinghapur (97) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household -25 | Assistant Engineer | Junior Engineer | ORD/000039/2023-2024 | 801/BQA | 11/04/2023 | 90 | JAI BHARAT COMMERCIAL CORPORATION | 5.69 | 5.55 | 100
242 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household - 2267 nos. | Assistant Engineer | Junior Engineer | ORD/000406/2021-2022 | 319/BQA | 22/02/2022 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 121.49 | 121.47 | 100
243 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-02( Napra(Part-B) , Bagulia ), Total House Hold -323 | Assistant Engineer | Junior Engineer | ORD/000462/2020-2021 | 858/BQA | 25/02/2021 | 30 | SARKAR CONSTRUCTION | 27.85 | 0 | 0
244 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2021-2022 | 88/BSD | 28/01/2022 | 60 | TAPAS DEY | 0.76 | 0.76 | 0
245 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2021-2022 | 450/BQA | 03/03/2022 | 0 | Resource Division | 12.47 | 0 | 0
246 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54) Angadpur (85) Bhaluka (86) Karra (87) Hemchabad (88) Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina Gobindarampur (126), Ramar Gram (127) & Hatiband (128) mouzas by retrofitting Bikrampur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1510 nos. | Assistant Engineer | Junior Engineer | ORD/000319/2021-2022 | 3370/BQA | 31/12/2021 | 1552 | M/S TARUN KUMAR PATRA | 75.2 | 34.02 | 0
247 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina Gobindarampur (126), Ramar Gram (127) & Hatiband (128) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Bikrampur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000887/2021-2022 | 93/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.5 | 0.28 | 0
248 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2021-2022 | 569/BQA | 17/03/2022 | 0 | Resource Division | 9.3 | 0 | 0
249 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1422 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2021-2022 | 436/BQA | 03/03/2022 | 1673 | GOUTAM BHOWMIK | 89.6 | 41.32 | 62
250 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2021-2022 | 101/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.47 | 0.28 | 0
251 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000032/2021-2022 | 572/BQA | 17/03/2022 | 0 | Resource Division | 8.76 | 0 | 0
252 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, ( Simla, Bank simul, Nekrakuada ) Total House Hold - 499 | Assistant Engineer | Junior Engineer | ORD/000035/2020-2021 | 637/BQA | 10/02/2021 | 30 | M/S TARUN KUMAR PATRA | 37.55 | 0 | 0
253 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 2, ( (Subarda, Shalchura ) Total House Hold - 496 | Assistant Engineer | Junior Engineer | ORD/000036/2020-2021 | 638/BQA | 10/02/2021 | 30 | UNIVERSAL CONSTRUCTION | 37.1 | 0 | 0
254 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) | Assistant Engineer | Junior Engineer | ORD/000175/2020-2021 | 718/BQA | 19/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.42 | 25.08 | 0
255 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Simla, Bank simul mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000231/2021-2022 | 932/BSD | 04/10/2021 | 15 | M/S TARUN KUMAR PATRA | 4.79 | 0 | 0
256 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Simla, Bank simul mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000232/2021-2022 | 933/BSD | 04/10/2021 | 15 | M/S TARUN KUMAR PATRA | 4.11 | 0 | 0
257 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 278 Nos.' | Assistant Engineer | Junior Engineer | VCH/002692/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SRIKANTA MONDAL | 10.55 | 0 | 0
258 | Bankura Division | Bankura Sadar Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban, Hapania, Jorehira, Kalipur, Tilna No. of Mouza :- 97 no. , Total House Hold - 15305 nos. | Assistant Engineer | Junior Engineer | VCH/002965/2021-2022 | FHTC/26 | 25/03/2022 | 0 | TECHVISION | 4.85 | 0 | 0
259 | Bankura Division | Bankura Sadar Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban, Hapania, Jorehira, Kalipur, Tilna No. of Mouza :- 35 no. , Total House Hold - 3284 nos. | Assistant Engineer | Junior Engineer | VCH/002966/2021-2022 | FHTC/26 | 25/03/2022 | 0 | TECHVISION | 1.04 | 0 | 0
260 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. | Assistant Engineer | Junior Engineer | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0
261 | Bankura Division | Brishnupur Sub-Division | "Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Somsar W/S Scheme (BRGF Ph-I) Block- Indas under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block -Bishnupur, Name of OHR -Dhengasole, No. of Mouza :- 3 nos. i.e. (i) Bhagabatipur J.L No-01, (ii) Palashdanga J.L No-03, (iii) Kumna JL No-04. Total House Hold - 518 SM/10041 " | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1354/BQA | 02/06/2023 | 60 | S B ASSOCIATES | 71.74 | 71.72 | 91
262 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Somsar W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Naldanga No. of Mouza :- 01 no. mouzas (i.e. Palashdanga 03) , Total House Hold - 70 | Assistant Engineer | Junior Engineer | ORD/001110/2022-2023 | 137/VSD | 12/05/2022 | 21 | AJIT KUMAR DUTTA | 4.54 | 4.48 | 85
263 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Somsar W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Naldanga No. of Mouza :- 01 no. mouzas (i.e. Palashdanga 03) , Total House Hold - 75 | Assistant Engineer | Junior Engineer | ORD/001111/2022-2023 | 137A/VSD | 12/05/2022 | 21 | SANU KARMAKAR | 4.81 | 4.48 | 85
264 | Bankura Division | Bankura Sadar Sub-Division | Bankura-Saltora Road from Ch:39.474 km to 44.800 km, Permanent Restoration of Road for the purpose of " Laying of pippeline from Lapahari to Murlu Village via Subdar more under Augmentation of Saltora water supply schemes" under Bankura Highway Division in the district of Bankura. | Assistant Engineer | Junior Engineer | BILL/00085/2025-2026 |  | 09/04/2025 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 24.18 | 0 | 0
265 | Bankura Division | Bankura Sadar Sub-Division | SHIFTING 4 NOS POLE AT LEDAPALADH ALONG SALTORA G. GHATI ROAD OF SALTORA CUSTOMER CARE CENTER. | Assistant Engineer | Junior Engineer | BILL/00255/2025-2026 | 4215/1 | 16/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.97 | 0 | 0
266 | Bankura Division | Bankura Sadar Sub-Division | Gangajalghati-Saltora Road from Ch. 9.60 km to Ch. 12.50 km & Ch. 19.30 km to Ch. 21.90 km - Permanent restoration work due to laying of PHE pipeline for under Bankura Highway Division in the district Bankura. | Assistant Engineer | Junior Engineer | BILL/01926/2024-2025 |  | 17/03/2025 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 17.86 | 0 | 0
267 | Bankura Division | Bankura Sadar Sub-Division | Construction of CWR (250 CUM CAPACITY) with plinth protection and other allied works for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. (For Zone -I) | Assistant Engineer | Junior Engineer | ORD/000068/2022-2023 | 1696/BQA | 28/07/2022 | 60 | SAIKAT CHOWDHURY | 50.47 | 39.45 | 90
268 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing at Anandapur Intake Site for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS Under Satora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Intake Site) | Assistant Engineer | Junior Engineer | ORD/000068/2025-2026 | 1008/BQA | 25/04/2025 | 90 | GOUTAM GHOSH | 32.15 | 0 | 0
269 | Bankura Division | Bankura Sadar Sub-Division | Laying of different dia DI (k9) rising main including all allied works for Augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2022-2023 | 1698/BQA | 28/07/2022 | 1618 | GOUTAM BHATTACHRYYA | 87.82 | 0 | 25
270 | Bankura Division | Bankura Sadar Sub-Division | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/05/2024 to 31/05/2024 (31 Days). | Assistant Engineer | Junior Engineer | ORD/000111/2024-2025 | 533/BSD | 30/04/2024 | 31 | GOUTAM GHOSH | 0.15 | 0.39 | 0
271 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Bamuntore pump house to Narayanpur more to Iswada village for water supply arrangement at Narayanpur & Iswada village under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000276/2022-2023 | 08/BQA | 03/01/2023 | 45 | RAHUL CHATERJEE | 8.95 | 8.88 | 0
272 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Narayanpur mouza under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000374/2022-2023 | 51/BQA | 05/01/2023 | 45 | SWAPAN KUMAR CHANDRA | 3.59 | 3.59 | 100
273 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to cover Iswada mouza under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2022-2023 | 52/BQA | 05/01/2023 | 45 | S K FAZLUL ALAM | 4.88 | 4.88 | 80
274 | Bankura Division | Bankura Sadar Sub-Division | Construction and commission of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr as per approved drawing & Laying DI (K7) & HDPE pipe line for distribution system including Providing FHTC for Augmentation of sub Surface Water Based Water Supply scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division. PHE Dte. (For Zone -I) | Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 1195/BQA | 22/05/2023 | 270 | SIB SANKAR CHOWDHURY | 391.5 | 76.17 | 19
275 | Bankura Division | Bankura Sadar Sub-Division | CONSTRUCTION, COMMISSIONING OF RCC OVERHEAD RESEVOR OF CAPACITY 550CUM AND STAGING HEIGHT 20 MTR. AS PER APPROVE DRAWING AND LAYING D.I(K-7) AND H.D.P.E PIPE LENGTH FOR DISTIBUTION SYSTEM INCLUDING PROVING FHTC FOR AUGMENTATION OF SUB-SURFACE WATER BASED WATER PIPE LINE SYSTEM FOR SALTORA PWSS.(FOR ZONE-II) | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 1257/BQA | 26/05/2023 | 936 | DEBAKI RANJAN SARKAR | 647.6 | 0 | 0
276 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 07 no. 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well & Supplying Laying 100 mm dia G.I connecting Main including supply and Erecting of 40 mm dia G I Pipe for Guard pilling from River bed T/W to Manifold for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000466/2021-2022 | 784/BQA | 31/03/2022 | 30 | GOPAL CHANDRA CHOWDHURY | 57.75 | 52.65 | 0
277 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 10/08/2023 to 09/02/2024 (184 Days). | Assistant Engineer | Junior Engineer | ORD/000621/2023-2024 | 807/BSD | 10/08/2023 | 184 | GOUTAM GHOSH | 0.87 | 2.42 | 0
278 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (250 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte (Zone- I) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000641/2022-2023 | 580/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
279 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (550 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte (Zone- II) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000642/2022-2023 | 581/BQA | 17/03/2023 | 930 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
280 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of CWR (250 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. (Head Work Site) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000643/2022-2023 | 582/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
281 | Bankura Division | Bankura Sadar Sub-Division | 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for inspection of JJM works across Bankura district of Deputy Superintending Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/10/2023 to 31/03/2024 (183 Days). | Assistant Engineer | Junior Engineer | ORD/000719/2023-2024 | 1016/BSD | 29/09/2023 | 183 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.2 | 100
282 | Bankura Division | Bankura Sadar Sub-Division | Continuation for Supply of 01 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for official use of the Assistant Engineer, Bankura Head Quarter under Bankura Division P.H.E. Dte. for the period from 01/12/2022 to 30/11/2023 (One Year) | Assistant Engineer | Junior Engineer | ORD/001176/2022-2023 | 10\BQA(H.Q.) | 28/11/2022 | 365 | MITALI CHHATAIT PARAMANIK | 1.73 | 0 | 0
283 | Bankura Division | Bankura Sadar Sub-Division | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/06/2024 to 30/06/2024 (30 Days). | Assistant Engineer | Junior Engineer | ORD/001334/2024-2025 | 607/BSD | 28/05/2024 | 30 | GOUTAM GHOSH | 0.14 | 0.39 | 0
284 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing at Saltora Z-I OHR Site for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS Under Satora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Z- I) | Assistant Engineer | Junior Engineer | ORD/001411/2024-2025 | 28/BQA | 02/01/2025 | 454 | KABISH KUMAR GHOSH | 36.78 | 0 | 1
285 | Bankura Division | Bankura Sadar Sub-Division | Supply of fitting including carriage and delivary at site for Augmentation of sub surface water based water supply scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001439/2023-2024 | 692/BQA | 27/02/2024 | 30 | APEX ENTERPRISE | 30.63 | 30.63 | 20
286 | Bankura Division | Bankura Sadar Sub-Division | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 10/02/2024 to 31/03/2024 (51 Days). | Assistant Engineer | Junior Engineer | ORD/001451/2023-2024 | 249/BSD | 09/02/2024 | 51 | GOUTAM GHOSH | 0.24 | 0.64 | 0
287 | Bankura Division | Bankura Sadar Sub-Division | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for inspection of JJM works across Bankura district of Deputy Superintending Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2024 to 30/09/2024 (183 Days). | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 472\BSD | 28/03/2024 | 183 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.31 | 0
288 | Bankura Division | Bankura Sadar Sub-Division | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/04/2024 to 30/04/2024 (30 Days). | Assistant Engineer | Junior Engineer | ORD/001562/2023-2024 | 473/BSD | 28/03/2024 | 30 | GOUTAM GHOSH | 0.14 | 0.37 | 0
289 | Bankura Division | Bankura Sadar Sub-Division | Continuation for Supply of 01 (One) No. Diesel/ LPG/ CNG driven Luxury Taxi / Bolero/ Scorpio on hire basis for official use of the Assistant Engineer, Bankura Head Quarter under Bankura Division P.H.E. Dte. for the period from 01/12/2023 to 30/11/2024 (One Year) | Assistant Engineer | Junior Engineer | ORD/001627/2023-2024 | 55\BQA(H.Q.) | 29/11/2023 | 366 | MITALI CHHATAIT PARAMANIK | 1.74 | 0 | 0
290 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2022-2023 | 1953/BQA | 19/09/2022 | 0 | Resource Division | 39.9 | 0 | 0
291 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2025-2026 | 2146/BQA | 29/10/2025 | 0 | Resource Division | 25.55 | 0 | 0
292 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000047/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 232.29 | 0 | 0
293 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 120KVA to 155 KVA at 11KV having Consumer ID : 942304500 at the premises at Anandapur, Saltora water supply scheme(Intake), Bankura. | Assistant Engineer | Junior Engineer | BILL/00956/2024-2025 | BP-2024-25-237 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.17 | 0 | 0
294 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 60KVA to 98 KVA at 11KV having Consumer ID : 942304600 at the premises at Biharinath, Saltora, Bankura. | Assistant Engineer | Junior Engineer | BILL/00957/2024-2025 | BP-2024-25-238 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0
295 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing and installation of High Lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist : Bankura. | Assistant Engineer | Junior Engineer | ORD/000614/2023-2024 | 2070/BMD | 12/09/2023 | 180 | DAS ENTERPRISE | 303.87 | 222.57 | 40
296 | Bankura Division | Khatra Sub-Division | New service connection at Simlapal CWR-II & OHR site of Simlapal piped water supply scheme of Simlapal block under Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00713/2024-2025 | BP-243/2024-25 | 28/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.01 | 0 | 0
297 | Bankura Division | Khatra Sub-Division | Load extended service connection at CWR Site of Simlapal Piped Water Supply Scheme (Consumer Id-942308000) of Simlapal Block under Bankura Division,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00985/2024-2025 | BP-326/2024-25 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.6 | 0 | 0
298 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline at different mouzas for Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿of Augmentation of Simlapal PWSS Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 827/BQA | 17/04/2023 | 836 | M/S TARUN KUMAR PATRA | 49.22 | 47.8 | 95
299 | Bankura Division | Khatra Sub-Division | Work Order for Soil Investigation work for the proposed construction of RCC Over Head Reservoir of capacity 400 CuM, stagging height 20.00 Mtr. for Augmentation of Simlapal water supply scheme (JJM) under Khatra Sub- Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000101/2022-2023 | 132/KSD | 21/04/2022 | 15 | M/S JAI KISHAN AGRO SCIENCE | 1.85 | 1.85 | 0
300 | Bankura Division | Khatra Sub-Division | Construction of 400 Cum. Capacity R.C.C. OHR (based on Departmental Design) with 20 mtr. staging height and Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 1188/BQA | 22/05/2023 | 590 | SIB SANKAR CHOWDHURY | 183.3 | 114.97 | 80
301 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Augmentation of Simlapal Piped Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Total House Hold - 3489 Nos.) | Assistant Engineer | Junior Engineer | ORD/000241/2022-2023 | 2112/BQA | 03/11/2022 | 881 | M/S TARUN KUMAR PATRA | 366.97 | 294.07 | 80
302 | Bankura Division | Khatra Sub-Division | Construction of Office Cum Operater room and room for WBSEDCLwith allied works for Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2024-2025 | 2340/BQA | 09/09/2024 | 124 | UTTAM KUMAR SINHAMAHAPATRA | 10.54 | 10.03 | 90
303 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Augmentation of Simlapal Piped Water Supply Scheme, Block : Simlapal, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000528/2021-2022 | 668/KSD | 24/09/2021 | 20 | LEMNISCATE | 3.76 | 3.67 | 0
304 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall with allied Works at Head Work site for Augmentation of Simlapal Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2022-2023 | 491/BQA | 13/03/2023 | 45 | GOUTAM MUKHERJEE | 27.05 | 16.55 | 60
305 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2022-2023 | 2282/BQA | 30/11/2022 | 0 | Resource Division | 80.24 | 0 | 0
306 | Bankura Division | Khatra Sub-Division | Construction and commissioning of Clear Water Reservoir (100 CUM Capacity) at Over Head Reservoir site and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2022-2023 | 283/BQA | 13/02/2023 | 721 | SUBHADIP KOLEY | 34.03 | 29.02 | 50
307 | Bankura Division | Khatra Sub-Division | Construction and commissioning of Clear Water Reservoir (100 CUM Capacity) at Over Head Reservoir site and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2022-2023 | 284/BQA | 13/02/2023 | 1397 | SAIKAT CHOWDHURY | 34.03 | 26.42 | 60
308 | Bankura Division | Khatra Sub-Division | Construction of High lift Pump House / Panel Room / Sub-Station building with sanitary & water supply arrangement and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 485/BQA | 13/03/2023 | 135 | UTTAM KUMAR SINHAMAHAPATRA | 28.83 | 28.81 | 60
309 | Bankura Division | Khatra Sub-Division | Construction of High lift Pump House / Panel Room / Sub-Station building with sanitary & water supply arrangement and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 486/BQA | 13/03/2023 | 382 | M/S SUPRIYA CHATTERJEE | 28.8 | 28.79 | 65
310 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal under Khatra Sub division under Bankura Division, PHE Dte. Location of site: (1) Near Simlapal Party Office, (2) Near Simlapal Sabji Market & (3) Near Simlapal PWD Office. | Assistant Engineer | Junior Engineer | ORD/000879/2023-2024 | 3007/BQA | 03/11/2023 | 165 | M/S TARUN KUMAR PATRA | 20.46 | 19.5 | 90
311 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
312 | Bankura Division | RWS Bankura Sub-Division | New Service connection at Mini Piped w/s scheme at village Chattabaid, P.o-Chakaltore under Bankura Mechanical Division PHE Dte. |  | Junior Engineer | BILL/00821/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
313 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
314 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
315 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
316 | Bankura Division | Bankura Sadar Sub-Division | Makarkendi, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00767/2022-2023 |  | 15/03/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
317 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
318 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 52.12 | 48
319 | Bankura Division | Brishnupur Sub-Division | (site - Nijchak, Deshra, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00294/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
320 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
321 | Bankura Division | Brishnupur Sub-Division | Quatation bill Jaykrishnapur, Bishnu Mandi, Sihar Kotulpur | Assistant Engineer | Junior Engineer | BILL/00678/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
322 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
323 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
324 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
325 | Bankura Division | Brishnupur Sub-Division | Panahar Koalpara, Kotulpur | Assistant Engineer | Junior Engineer | BILL/00681/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
326 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
327 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27 | 48
328 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
329 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
330 | Bankura Division | Bankura Sadar Sub-Division | New connection at rahir, Jhantipahari, PHE Dte. of the Executive Engineer, Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02647/2023-2024 | FHTC/03 | 20/03/2024 | 0 | JHANTIPAHARI CCC | 0.13 | 0 | 0
331 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30.5 | 48
332 | Bankura Division | Brishnupur Sub-Division | (site - Dingal, lowgram, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00290/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
333 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
334 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
335 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
336 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
337 | Bankura Division | Bankura Sadar Sub-Division | Quotation of WBSEDCL for the scheme of SM/10931 | Assistant Engineer | Junior Engineer | BILL/00850/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
338 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45.97 | 48
339 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
340 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
341 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
342 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
343 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
344 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
345 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
346 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
347 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Benakali. | Assistant Engineer | Junior Engineer | BILL/01576/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0
348 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.6 | 48
349 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
350 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
351 | Bankura Division | Bankura Sadar Sub-Division | New Service connection at Kustore | Assistant Engineer | Junior Engineer | BILL/01405/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
352 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.5 | 48
353 | Bankura Division | RWS Bankura Sub-Division | New Connection at Gholkuri,Ranibandh |  | Junior Engineer | BILL/00325/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
354 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
355 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
356 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 48
357 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
358 | Bankura Division | Brishnupur Sub-Division | New Connection at Kendgare,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00484/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
359 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
360 | Bankura Division | Brishnupur Sub-Division | New Service Connection for Mini Piped water supply Scheme at Muktapur, G.p-Hamirpur block-Patrasayer under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02575/2023-2024 | FHTC/03 | 12/03/2024 | 0 | PATRASAYER CCC | 0.43 | 0 | 0
361 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
362 | Bankura Division | Brishnupur Sub-Division | (site - Eneyetchak, Deshra, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00291/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
363 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
364 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
365 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at ENEYETCHAK | Assistant Engineer | Junior Engineer | BILL/01267/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
366 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
367 | Bankura Division | RWS Bankura Sub-Division | New Connection at Churamonipur, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00425/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
368 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
369 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
370 | Bankura Division | RWS Bankura Sub-Division | New Connection at Ghagar, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00423/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
371 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
372 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
373 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
374 | Bankura Division | RWS Bankura Sub-Division | New Connection at Balarampur, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00436/2023-2024 | BP-147/2024-25 | 03/07/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
375 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
376 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
377 | Bankura Division | RWS Bankura Sub-Division | New Connection at Brahmandhara, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00440/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
378 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
379 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
380 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for mini water supply scheme at Paharberia, Bamuntore under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00825/2023-2024 | FHTC/09 | 07/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
381 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
382 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
383 | Bankura Division | RWS Bankura Sub-Division | New service connection for Baliguma Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00182/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
384 | Bankura Division | RWS Bankura Sub-Division | New Connection at Baliguma Block-Sarenga in connection with 431 mini PWSS under BMSD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00273/2023-2024 | FHTC/06 | 07/06/2023 | 0 | SARENGA CCC | 0.11 | 0 | 0
385 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
386 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
387 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 48
388 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Balguma Village (SM/11129), (2) Mini Piped Water Supply Scheme for Dhepua Village (SM/11130) and (3) Mini Piped Water Supply Scheme for Raghunathpur Village (SM/11132) | Assistant Engineer | Junior Engineer | ORD/002001/2024-2025 | 201\KSD | 10/03/2025 | 10 | PRADYUMNA KOLEY | 0.45 | 0 | 90
389 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
390 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Nadusenera Bansidi | Assistant Engineer | Junior Engineer | BILL/01031/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
391 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
392 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
393 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
394 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
395 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
396 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Lego, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00278/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
397 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
398 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
399 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
400 | Bankura Division | Bankura Sadar Sub-Division | New connecion at vill-Bhurrudanga p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02601/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
401 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
402 | Bankura Division | Bankura Sadar Sub-Division | New connecion at vill-Blmrrudanga p.o-Jhilimili(Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02599/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
403 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
404 | Bankura Division | Bankura Sadar Sub-Division | New connection at vill-Kasakend p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02592/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
405 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45 | 48
406 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 48 | 48
407 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
408 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Uttar Kendbona | Assistant Engineer | Junior Engineer | BILL/01034/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
409 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
410 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
411 | Bankura Division | Brishnupur Sub-Division | svs single phase connection for Grambera village | Assistant Engineer | Junior Engineer | BILL/00042/2024-2025 | FHTC/04 | 29/04/2024 | 0 | PATRASAYER CCC | 2.33 | 0 | 0
412 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
413 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
414 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
415 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Rampur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00285/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
416 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
417 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
418 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at RAMPUR | Assistant Engineer | Junior Engineer | BILL/01258/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
419 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
420 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 06 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 2148/BQA | 14/11/2022 | 30 | M/S TARUN KUMAR PATRA | 85.81 | 72.26 | 100
421 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 06 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000247/2022-2023 | 2149/BQA | 14/11/2022 | 30 | GOPAL CHANDRA CHOWDHURY | 85.9 | 71.36 | 0
422 | Bankura Division | Bankura Sadar Sub-Division | Construction of common manifold and Sinking of 03 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000248/2022-2023 | 2150/BQA | 14/11/2022 | 45 | SIB SANKAR CHOWDHURY | 42.96 | 42.74 | 20
423 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhadaspur Khas (10), Jahur Bana (102), Fatepur (103) & Amjhor (104) mouzas of Saltora Block including laying of 400 mm dia MS Rising main from manifold to CWR at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF Ph - I Project) under Jal Jeevan Mission Programme under Bankura Division, P.H.E. Dte.Block - Saltora, No. of OHR:- 1No. No.of Mouza :- 4, Total House Hold- 258 Nos. | Assistant Engineer | Junior Engineer | ORD/000684/2022-2023 | 585/BQA | 20/03/2023 | 90 | TAPAS KUMBHAKAR | 53.41 | 49.12 | 90
424 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 04 (Four) nos. 200 mm dia. X 16.0 Mtr. depth Vertical River Bed Tube Well and supplying & laying of 150 mm dia MS collecting line with other allied works from riverbed to manifold at Kukhrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, P.H.E. Dte. under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | ORD/001463/2024-2025 | 84/BQA | 06/01/2025 | 134 | SINGHA ENTERPRISE | 29.1 | 0 | 1
425 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pumping machineries with other electro-mechanical accessories for 4 nos vertical tubewell at Intake Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 147/BMD | 30/04/2025 | 90 | ORIENTAL ENGINEERING CO. | 27.6 | 0 | 100
426 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, Delivery and installation of Voltage Correction device and allied works for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 784/BMD | 20/08/2024 | 240 | DAS ENTERPRISE | 29.99 | 0 | 80
427 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work-Providing and Installation of Low lift pumping machineries and other electro-mechanical accessories for Augmentation of source by sinking of river bed Tube well including connecting line & M.S. Rising main at Kukrakuri in the river bed of Damodar and providing FHTC for Saltora Chhatna water supply scheme (BRGF Phase-I) under Jal Jeevan Mission under Bankura Mechanical Division PHE Dte. Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 341/BMD | 03/03/2023 | 184 | ORIENTAL ENGINEERING CO. | 99.53 | 89.03 | 100
428 | Bankura Division | Bankura Sadar Sub-Division | Laying DI (K7) & UPVC pipe line for distribution system with FHTC for the proposed Augmentation of Piped Water Supply Scheme for Kenjakura and its adjoining mouzas (JJM Revision) under Bankura Sadar Sub - Division, PHE Dte. (Part - A) & Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/10/2012) for Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas(JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000221/2022-2023 | 1972/BQA | 22/09/2022 | 1286 | M/S TARUN KUMAR PATRA | 343.73 | 138.48 | 70
429 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2022-2023 | 357/BSD | 13/04/2022 | 15 | MABCO CONSULTANT | 1.83 | 1.85 | 0
430 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas(JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000426/2023-2024 | 2009/BQA | 19/07/2023 | 956 | M/S TARUN KUMAR PATRA | 176.63 | 0 | 40
431 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe line,special repairing and ¿FHTC (Functional House Hold Tap Connection) at manoharpur village under KENJAKURA W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000694/2022-2023 | 616/BQA | 23/03/2023 | 45 | JAGADISH BANERJEE | 2.22 | 2.21 | 20
432 | Bankura Division | Bankura Sadar Sub-Division | Continuation for Diesel Ambassador Car equivalent luxury Car / Bolero / Scrpio etc. having license for contract carriage permit from the Regional Transport Authority for office use of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/12/2022 to 31/05/2023) | Assistant Engineer | Junior Engineer | ORD/000981/2022-2023 | 751/BSD | 28/11/2022 | 181 | GOURANGA NANDI | 0.86 | 2.39 | 100
433 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000026/2022-2023 | 2146/BQA | 11/11/2022 | 0 | Resource Division | 54.83 | 0 | 0
434 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000067/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 40.87 | 0 | 0
435 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Kenjakura augmentation site at Bankura-I block under BMD PHE Dte.(SM/09877) | Assistant Engineer | Junior Engineer | BILL/01337/2024-2025 | BP-2024-25-355 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0
436 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of piped water supply scheme for Kenjakura its adjoining mouzas (JJM Revision) under Bankura Mechanical Division PHE Dte Bankura-I Block- Dist -Bankura. | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 1170/BMD | 01/06/2023 | 180 | M/S SOMA ENTERPRISES | 64.3 | 51.14 | 8
437 | Bankura Division | Bankura Sadar Sub-Division | Payment to Rail | Assistant Engineer | Junior Engineer | BILL/00020/2023-2024 | FHTC/17 | 17/04/2023 | 0 | SOUTH EASTERN RAILWAY | 5.87 | 0 | 0
438 | Bankura Division | Bankura Sadar Sub-Division | Laying DI (K7) & UPVC pipe line for distribution system & Construction and commissioning of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- 1/OHR/7/2012 (Sheet 1 &2)with 20 mtr staging height including foundation, pipeline connection and cost of pipes , specials etc.and allied works for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura PART -A and Construction and commissioning of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- 1/OHR/7/2012 (Sheet 1 &2)with 20 mtr staging height including foundation, pipeline connection and cost of pipes , specials etc.and allied works for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura PART - B | Assistant Engineer | Junior Engineer | ORD/000077/2022-2023 | 1989/BQA | 27/09/2022 | 1187 | PARAMESWAR CHOWDHURY | 193.56 | 49.22 | 60
439 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 236/6 -7) in between Rly. Station Bikna-Nabanda Rly. station in Katnar mouza, P.S. Bankura,by Jack Pushing method with 300 mm (OD) Spirally welded MS Casing Pipe with 100 mm dia. MS carrier pipe under Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2025-2026 | 1294/BQA | 17/06/2025 | 45 | PARAMESWAR CHOWDHURY | 48.84 | 0 | 5
440 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Augmentation for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for 03 nos. Mouzas of proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura. Block - Bankura- II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :- 03 nos, Bikna (235), Kuraria (254), Katnar (255). | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 519/BSD | 12/06/2023 | 60 | TAPAS DEY | 0.45 | 0.24 | 100
441 | Bankura Division | Bankura Sadar Sub-Division | Laying Rising Main DI (K9) pipe & construction of CWR (50 CUM CAPACITY) with plinth protection for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura ( Single compartment , Size of Compartment -Length 5mtr , Width-5mtr , Depth -2.5 mtr ) ( Sl.No-04) | Assistant Engineer | Junior Engineer | ORD/000445/2021-2022 | 525/BQA | 10/03/2022 | 315 | SAIKAT CHOWDHURY | 13.71 | 6.7 | 51
442 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 300 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Bikna and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2022-2023 | 359/BSD | 13/04/2022 | 15 | ASIS ENTERPRISE | 1.85 | 1.73 | 100
443 | Bankura Division | Bankura Sadar Sub-Division | Road Crossing work by verious dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Bikna Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001266/2023-2024 | 693/BQA | 28/02/2024 | 45 | PARAMESWAR CHOWDHURY | 34.8 | 29.28 | 85
444 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Augmentation works for Bikna and its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 860/BMD | 29/08/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.19 | 0 | 0
445 | Bankura Division | Bankura Sadar Sub-Division | Cannel/Drain Crossing work near Kuraria Smasan Kali Mandir by 150 mm dia MS carrier pipe & 300 mm dia MS casing pipe by Jack pushing method, inetrconnection of MS carrier pipe with HDPE pipeline including fabrication of MS pipe & allied works for Augmentation of Bikna Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001699/2024-2025 | 388/BQA | 07/02/2025 | 60 | PARAMESWAR CHOWDHURY | 34.68 | 0 | 1
446 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE (Balardihi Patra Para) HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00160/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | KHATRA CCC | 0.12 | 0 | 0
447 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43.5 | 48
448 | Bankura Mechanical | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | Assistant Engineer | Junior Engineer | BILL/01671/2023-2024 |  | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
449 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
450 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
451 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi , Binadpur Araldihi | Assistant Engineer | Junior Engineer | BILL/01033/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
452 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
453 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30.5 | 48
454 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
455 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi,Kumirpaar Hatagram | Assistant Engineer | Junior Engineer | BILL/01028/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
456 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
457 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
458 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Digrya site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00183/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
459 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
460 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
461 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 41 | 48
462 | Bankura Division | Brishnupur Sub-Division | Payment for Wayleave Facility Charge of [SM/12418] HIRAPUR PIPED WATER SUPPLY SCHEME [Node No- 1 to 2] under Joypur Block. Application ID: ER-HWH-2025-WL-51. | Assistant Engineer | Junior Engineer | BILL/00898/2025-2026 | 4215/1 | 16/09/2025 | 0 | EASTERN RAILWAY | 4.94 | 0 | 0
463 | Bankura Division | Brishnupur Sub-Division | Hirapur to Dighpur (WB-03-36) of Scheme Name Hirapur PWSS (SM/12418) | Assistant Engineer | Junior Engineer | BILL/02023/2024-2025 |  | 25/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 4.72 | 0 | 0
464 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 191.13 | 6
465 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
466 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 8.77 | 0 | 0
467 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000044/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 130.53 | 0 | 0
468 | Bankura Mechanical | Brishnupur Sub-Division | Hirapur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01548/2023-2024 | BP-2023-24-107 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.45 | 0 | 0
469 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Hirapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000188/2025-2026 | 460/BMD | 10/06/2025 | 90 | KASHINATH DEY | 11.69 | 0 | 0
470 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR KOT MADAN MOHANPUR VILLAGE (Dahala Karapara) HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00161/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | KHATRA CCC | 0.12 | 0 | 0
471 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 48 | 48
472 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
473 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Amdangra Nabadeulvira | Assistant Engineer | Junior Engineer | BILL/00525/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
474 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
475 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
476 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
477 | Bankura Division | Brishnupur Sub-Division | New Connection at Gosaigram,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00476/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
478 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
479 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31.61 | 48
480 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
481 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
482 | Bankura Division | Brishnupur Sub-Division | New service connection for mini water supply scheme at Dhuma piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02748/2023-2024 | FHTC/03 | 27/03/2024 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
483 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18.6 | 48
484 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for choto Bankadaha | Assistant Engineer | Junior Engineer | BILL/00043/2024-2025 | FHTC/04 | 29/04/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
485 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
486 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 16 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002200/2024-2025 | 579/A/VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 2.41 | 0 | 0
487 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Bagsara site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00199/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
488 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
489 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
490 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 44 | 48
491 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Chandabil site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00191/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
492 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
493 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
494 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38 | 48
495 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
496 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
497 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
498 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
499 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
500 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22 | 48
501 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Tella Paharkole Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00153/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
502 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Tella Paharkole Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00173/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
503 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
504 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
505 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
506 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
507 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
508 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Karamara Village (SM/11014), (2) Mini Piped Water Supply Scheme for Chaturikalapathar Village (SM/13268), (3) Mini Piped Water Supply Scheme for Chaturi Village (SM/11010), (4) Mini Piped Water Supply Scheme for Manhara Village (SM/11019) and (5) Mini Piped Water Supply Scheme for Turubandh Village (SM/13272) |  | Junior Engineer | ORD/001994/2024-2025 | 194\KSD | 10/03/2025 | 10 | SANDHYA DEY | 0.75 | 0 | 90
509 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 73.64 | 55
510 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000071/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 9.03 | 0 | 0
511 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATSOLE TW-1(JL NO-68, PLOT-159/188LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00017/2024-2025 | BP-2024-25-27 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.15 | 0 | 0
512 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATSOLE TW-2 (JL NO-68, PLOT-159/188) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00024/2024-2025 | BP-2024-25-28 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0
513 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Patsol Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000062/2025-2026 | 401/BMD | 04/06/2025 | 90 | S.DUTTA | 15.08 | 0 | 0
514 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-4B) (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000324/2022-2023 | 186/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.43 | 3.43 | 0
515 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
516 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 250 m³ capacity R.C.C OHR(based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2023-2024 | 2364/BQA | 14/08/2023 | 270 | MANJAR ALI KHAN | 407 | 35.5 | 35
517 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 442/BQA | 06/03/2023 | 90 | EDER ALI KHAN | 8.65 | 0 | 0
518 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 443/BQA | 06/03/2023 | 90 | SOMENATH ACHARYYA | 4.63 | 0 | 0
519 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000572/2022-2023 | 444/BQA | 06/03/2023 | 45 | SOMENATH ACHARYYA | 19.54 | 0 | 0
520 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000576/2022-2023 | 445/BQA | 06/03/2023 | 90 | MOHAMMAD HASAN KHAN | 8.64 | 0 | 0
521 | Bankura Division | Khatra Sub-Division | Work Order Installation of scheme information board for 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- IV/B Water supply scheme (SM/14091), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- V/A Water supply scheme (SM/15009), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- V/B Water supply scheme (SM/16935), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VI Water supply scheme (SM/16260),1 no. site of Sub surface water based Pirrabakra pipe water supply scheme (SM/18042) and 1 no. site of Proposed sub surface water based Khayerbani pipe water supply scheme (SM/18040) within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001910/2024-2025 | 154\KSD | 07/03/2025 | 10 | TAPAN KUMAR MANDAL | 0.9 | 0 | 90
522 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 2.26 | 0 | 0
523 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000206/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 14.2 | 0 | 0
524 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 1124/BMD | 24/05/2023 | 30 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0
525 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 193.75 | 55
526 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 4.39 | 0 | 0
527 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2024-2025 | 2945/BQA | 21/11/2024 | 0 | Resource Division | 8.46 | 0 | 0
528 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 14.56 | 0 | 0
529 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for GOALA DANGA water supply scheme under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | BILL/00016/2024-2025 | BP-2024-25-32 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.63 | 0 | 0
530 | Bankura Mechanical | Brishnupur Sub-Division | Goala Danga Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01614/2023-2024 | BP-2023-24-142 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.78 | 0 | 0
531 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Goala Danga Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 233/BMD | 14/05/2025 | 90 | M/S BIPUL BANERJEE | 10.88 | 0 | 0
532 | Bankura Division | Brishnupur Sub-Division | Balance Ancillary Work for ¿Kubirbandh¿ and ¿Chakai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000422/2025-2026 | 1989/BQA | 16/09/2025 | 180 | PRINCE INDUSTRIES (INDIA) | 130.51 | 0 | 15
533 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR CHAKAI & KUBIRBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 2336/BQA | 14/08/2023 | 999 | PRINCE INDUTRIES (INDIA) | 1048.51 | 118.79 | 73
534 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000026/2024-2025 | 713/BQA | 13/03/2025 | 0 | Resource Division | 11.49 | 0 | 0
535 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 26.25 | 0 | 0
536 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Kubir Bandh Zone-II TW1 Water supply scheme of sonamukhi Block under Bankura Mechanical Division PHE DTE.(SM/14008) | Assistant Engineer | Junior Engineer | BILL/01179/2024-2025 | BP-2024-25-306 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.7 | 0 | 0
537 | Bankura Mechanical | Brishnupur Sub-Division | Kubir Bandh Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01666/2023-2024 | BP-2023-24-183 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.51 | 0 | 0
538 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone- II) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 655/BMD | 17/04/2023 | 180 | UNITED TRADERS | 31.37 | 13.99 | 45
539 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000427/2023-2024 | 1687/BMD | 27/07/2023 | 180 | PRADIP KUMAR DHABAL | 36.76 | 19.54 | 53
540 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 276.29 | 55
541 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000061/2023-2024 | 2527/BQA | 08/09/2023 | 0 | Resource Division | 10.29 | 0 | 0
542 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 23 | 0 | 0
543 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Kushawdip (T/W-II) water supply scheme at patrasayer block under BMD PHE Dte.(SM/15266) | Assistant Engineer | Junior Engineer | BILL/01472/2024-2025 | BP-2024-25-356 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0
544 | Bankura Mechanical | Brishnupur Sub-Division | Kushadwip Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01655/2023-2024 | BP-2023-24-181 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.42 | 0 | 0
545 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Mukundapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000021/2025-2026 | 232/BMD | 14/05/2025 | 90 | ABHIJIT MUKHERJEE | 11.53 | 0 | 0
546 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Kushadwip Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000140/2025-2026 | 435/BMD | 10/06/2025 | 90 | M/S DAS AND SARKAR ENTERPRISE | 11.74 | 0 | 0
547 | Bankura Division | Brishnupur Sub-Division | Repair estimate of PMGSY Road Damaged by PHE Department. ( Name of Scheme : Lankajol PWSS, Sm code - SM/15022, First Installment i.e-50% ) | Assistant Engineer | Junior Engineer | BILL/01378/2024-2025 | BP-444/2024-25 | 24/12/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 5.56 | 0 | 0
548 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 249.09 | 55
549 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 15.68 | 0 | 0
550 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000089/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 69.06 | 0 | 0
551 | Bankura Mechanical | Brishnupur Sub-Division | Lankajol Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01509/2023-2024 | BP-2023-24-95 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0
552 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Lankajol Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000152/2025-2026 | 447/BMD | 10/06/2025 | 90 | PRADIP KUMAR DHABAL | 11.84 | 0 | 0
553 | Bankura Division | Brishnupur Sub-Division | Gopinathpur to Aswinkota ( WB-03-432) of Scheme Name Narayanpur PWSS (SM/14178) | Assistant Engineer | Junior Engineer | BILL/02021/2024-2025 |  | 25/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 13.86 | 0 | 0
554 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 152.61 | 55
555 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Pratappur Piped Water Supply Scheme (SM/15019), 2 nos. sites of Narayanpur Piped Water Supply Scheme (SM/14178) & 2 nos. sites of Lankajol Piped Water Supply Scheme (SM/15022) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001879/2024-2025 | 557/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 100
556 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 12.2 | 0 | 0
557 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000092/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 48.16 | 0 | 0
558 | Bankura Mechanical | Brishnupur Sub-Division | Narayanpur | Assistant Engineer | Junior Engineer | BILL/01505/2023-2024 | BP-2023-24-101 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.1 | 0 | 0
559 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Narayanpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 445/BMD | 10/06/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 11.87 | 0 | 0
560 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no. 43 Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Mamudpur-124 & Bagalpur-128 , Total House Hold - 304 (304 out 549) | Assistant Engineer | Junior Engineer | ORD/000089/2021-2022 | 2527/BQA | 23/09/2021 | 30 | OSMAN SEKH | 25.6 | 0 | 0
561 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no. 43 Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Barabaikunthapur-125 & Habispur-127 , Total House Hold - 245 (245 out of 549) | Assistant Engineer | Junior Engineer | ORD/000091/2021-2022 | 2528/BQA | 23/09/2021 | 30 | TAPAN KUMAR MANDAL | 20.5 | 0 | 0
562 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal (Zone-B) W/S Scheme (BRGF phase-I project) for 02 nos. mouzas (Mamudpur - 124 & Bagalpur - 128) of left out householed 76 nos. within Indas Block under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 2 nos. i.e. Mamudpur - 124 & Bagalpur - 128, Total House Hold - 76 (left out) | Assistant Engineer | Junior Engineer | ORD/000473/2021-2022 | 43/VSD | 22/02/2022 | 30 | OSMAN SEKH | 4.34 | 3.75 | 0
563 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Indas, Name of OHR - Rol, No. of Mouza :- 2 nos. i.e. Rol-07 & Chichinga-08, Total House Hold - 1421 | Assistant Engineer | Junior Engineer | VCH/002337/2021-2022 | FHTC/25 | 25/01/2022 | 0 | CREATION CONSTRUCTION | 64.49 | 0 | 0
564 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456 | Assistant Engineer | Junior Engineer | VCH/002338/2021-2022 | FHTC/25 | 25/01/2022 | 0 | MUNMUN UPADHYAY | 2.86 | 0 | 0
565 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipeline to cover Bhelaidiha (81) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002339/2021-2022 | FHTC/28 | 28/01/2022 | 0 | BEAUTY CHATTERJEE | 4.49 | 0 | 0
566 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipeline to cover Husumdanga (83) & Bhogra (84) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002340/2021-2022 | FHTC/28 | 28/01/2022 | 0 | BEAUTY CHATTERJEE | 3.23 | 0 | 0
567 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 | Assistant Engineer | Junior Engineer | VCH/002341/2021-2022 | FHTC/25 | 25/01/2022 | 0 | NAYAN BARDHAN | 1.3 | 0 | 0
568 | Bankura Division | Brishnupur Sub-Division | Work Order for Household survey in different mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) & Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) | Assistant Engineer | Junior Engineer | VCH/002342/2021-2022 | FHTC/25 | 25/01/2022 | 0 | TAPAS DEY | 3.77 | 0 | 0
569 | Bankura Division | Brishnupur Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of Mouza- Paschim Brindabanpur | Assistant Engineer | Junior Engineer | VCH/002343/2021-2022 | FHTC/25 | 25/01/2022 | 0 | M/S SUPRIYA CHATTERJEE | 4.84 | 0 | 0
570 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 | Assistant Engineer | Junior Engineer | VCH/002344/2021-2022 | FHTC/25 | 25/01/2022 | 0 | AMIYA KUMAR BIT | 35.44 | 0 | 0
571 | Bankura Division | Khatra Sub-Division | " Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345) and Janapara (356) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 359 Nos." |  | Junior Engineer | ORD/000117/2021-2022 | 2770/BQA | 08/11/2021 | 30 | BIJOY KOLEY | 16.44 | 2.39 | 0
572 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chandpara (357) and Bamandiha (358) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 369 Nos." |  | Junior Engineer | ORD/000118/2021-2022 | 2771/BQA | 08/11/2021 | 30 | ASHOKE KUMAR DEY | 16.6 | 4.22 | 0
573 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 278 Nos." |  | Junior Engineer | ORD/000119/2021-2022 | 2772/BQA | 08/11/2021 | 30 | SRIKANTA MONDAL | 13.54 | 2.58 | 0
574 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 182 Nos." |  | Junior Engineer | ORD/000120/2021-2022 | 2773/BQA | 08/11/2021 | 30 | GON ASSOCIATES | 9.74 | 0 | 0
575 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works at culvert portion from Gargaria village more to Taldiha village more [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000131/2022-2023 | 300/KSD | 26/07/2022 | 10 | UTTAM KUMAR SINHAMAHAPATRA | 4.93 | 4.9 | 0
576 | Bankura Division | Khatra Sub-Division | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 45 | NAYAN BARDHAN | 49.26 | 6.68 | 0
577 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of UPVC pipe for Distribution Main along with allied works for culvert crossing from Debgram village to Brahamandiha village [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 33) |  | Junior Engineer | ORD/000568/2021-2022 | 763/BQA | 28/03/2022 | 15 | UNITED TRADERS | 4.84 | 4.82 | 0
578 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) |  | Junior Engineer | ORD/000589/2021-2022 | 793/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.4 | 0 | 0
579 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Makarkol (365) & Jukhanala (366) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 27) |  | Junior Engineer | ORD/000622/2021-2022 | 757/BQA | 28/03/2022 | 10 | SRIKANTA MONDAL | 1.08 | 0 | 0
580 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/000459/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.38 | 0 | 0
581 | Bankura Division | Khatra Sub-Division | Household survey in Mamra, baradhara, kukrakhondar tusarkanti hanspatha rmouzas under Pasola zone -A to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 17 |  | Junior Engineer | VCH/000465/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.26 | 0 | 0
582 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Makarkol (365) & Jukhanala (366) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 27) |  | Junior Engineer | VCH/001308/2022-2023 | FHTC/20 | 20/10/2022 | 0 | SRIKANTA MONDAL | 1.12 | 0 | 0
583 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 279 Nos. |  | Junior Engineer | VCH/002625/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 11.3 | 0 | 0
584 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002627/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAS GHOSH | 12.24 | 0 | 0
585 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 |  | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
586 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Chandpara (357 ) & Bamandiha ( 258) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Garharya (Zone - B) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002932/2021-2022 | FHTC/22 | 22/03/2022 | 0 | SANDHYA DEY | 3.02 | 0 | 0
587 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe line to cover Taldiha (345) & Janapara (356) mouzas construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Retrofitting of water supply scheme for Gargarya zone - A under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  | Junior Engineer | VCH/002943/2021-2022 | FHTC/23 | 23/03/2022 | 0 | BIJOY KOLEY | 4.06 | 0 | 0
588 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Saburbandh & Adjoining Mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000367/2023-2024 | 2029/BQA | 24/07/2023 | 892 | PRINCE INDUTRIES (INDIA) | 158.22 | 86.21 | 100
589 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Division, PHE Dte. Block - Saltora, No. of Mouza :- 01 nos. Rajpura, Total House Hold :-35 nos. | Assistant Engineer | Junior Engineer | ORD/000674/2023-2024 | 811/BSD | 10/08/2023 | 15 | TAPAN KUMAR UPADHYAY | 0.87 | 0.87 | 87
590 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Division, PHE Dte. Block - Saltora, No. of Mouza :- 1 no., kesarkundi, Total House Hold :-30 nos. | Assistant Engineer | Junior Engineer | ORD/000676/2023-2024 | 812/BSD | 10/08/2023 | 15 | TAPAN KUMAR UPADHYAY | 0.93 | 0.93 | 80
591 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division,of Bankura Division PHE Dte. Block - Saltora, Name of OHR - Saburbandh, No. of Mouza :- 01 no., Rajpura (Part), Total House Hold :-17 nos. | Assistant Engineer | Junior Engineer | ORD/000680/2023-2024 | 813/BSD | 10/08/2023 | 15 | TAPAN KUMAR UPADHYAY | 0.86 | 0.84 | 70
592 | Bankura Division | Bankura Sadar Sub-Division | Construction of valve chamber at Rajpura, Keserkundi, Salbedia, Krishnapur mouza) of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000708/2023-2024 | 818/BSD | 10/08/2023 | 10 | TAPAN KUMAR UPADHYAY | 0.84 | 0.84 | 86
593 | Bankura Division | Bankura Sadar Sub-Division | Dismentling & reconstruction of concrete at Iswada mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000718/2023-2024 | 821/BSD | 11/08/2023 | 10 | SK FAZLUL ALAM | 0.96 | 0.94 | 85
594 | Bankura Division | Bankura Sadar Sub-Division | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000721/2023-2024 | 822/BSD | 11/08/2023 | 15 | SONU SINGH | 0.95 | 0.95 | 100
595 | Bankura Division | Bankura Sadar Sub-Division | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 823/BSD | 11/08/2023 | 15 | ABDUL AZID KHAN | 0.92 | 0.92 | 100
596 | Bankura Division | Bankura Sadar Sub-Division | Construction of concrete to cover the pipeline from pump house to Keser Kundi for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saltora block of Saburbandh W/S Scheme under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 824\BSD | 11/08/2023 | 15 | M/S S.M ENTERPRISE | 0.95 | 0.89 | 100
597 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 02 no., (Iswada, Narayanpur), Total House Hold - 35 nos, (Part- A). | Assistant Engineer | Junior Engineer | ORD/001041/2023-2024 | 1144/BSD | 22/11/2023 | 618 | GON ASSOCIATES | 0.91 | 0 | 95
598 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 02 no., (Iswada, Narayanpur), Total House Hold - 35 nos, (Part- B). | Assistant Engineer | Junior Engineer | ORD/001042/2023-2024 | 1145/BSD | 22/11/2023 | 618 | GON ASSOCIATES | 0.87 | 0 | 95
599 | Bankura Division | Bankura Sadar Sub-Division | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/001045/2023-2024 | 1146/BSD | 22/11/2023 | 15 | SOURASIS KARAK | 0.95 | 0 | 100
600 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Saburbandh & Adjoining Mouzas Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001368/2024-2025 | 3131/BQA | 19/12/2024 | 90 | AMITAVA CHAKRABORTY | 58.46 | 0 | 0
601 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000090/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.7 | 0 | 0
602 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000261/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.7 | 0 | 0
603 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram , Total House Hold - 275 nos. | Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 673/BQA | 28/03/2023 | 1010 | MUNMUN UPADHYAY | 96.68 | 28.12 | 35
604 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Nabagram (Zone-K) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2023-2024 | 2974/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.08 | 1.47 | 100
605 | Bankura Division | Bankura Sadar Sub-Division | Crossing major PMGSY Road by different dia MS pipe by trench less Technologies i.e Jack Pushing method with MS Carrier pipe and all alled works near Metyala Village at Saluni-Kamalpur Road under Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001396/2024-2025 | 43/BQA | 02/01/2025 | 45 | MUNMUN UPADHYAY | 4.61 | 0 | 10
606 | Bankura Division | Bankura Sadar Sub-Division | Construction of Guard Room & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001407/2024-2025 | 49/BQA | 02/01/2025 | 90 | LABIR MIRSHAD KHAN | 5.33 | 0 | 2
607 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000092/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.72 | 0 | 0
608 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000264/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
609 | Bankura Division | Bankura Sadar Sub-Division | Road Crossing work by verious dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Saulia (Zone- G) Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2025-2026 | 1021/BQA | 25/04/2025 | 60 | SIBSANKAR CHOWDHURY | 30.95 | 0 | 0
610 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House at Saulia, including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Saulia (Zone- G) Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000196/2024-2025 | 1865/BQA | 12/07/2024 | 538 | MANAS DEY | 30.88 | 0 | 5
611 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platform of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Saulia (Zone - G) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2023-2024 | 2090/BQA | 27/07/2023 | 270 | SIB SANKAR CHOWDHURY | 328.41 | 0 | 60
612 | Bankura Division | Bankura Sadar Sub-Division | inking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) & Bypass pipe line arrangemet from tube well to inlet pipe of OHR at Saulia (Zone - G) OHR site under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and Jal Swapna Fund) | Assistant Engineer | Junior Engineer | ORD/000697/2023-2024 | 2655/BQA | 21/09/2023 | 45 | SAMIRUDDIN KHAN | 11.39 | 8.24 | 100
613 | Bankura Division | Bankura Sadar Sub-Division | upport service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Saulia (Zone- G) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2023-2024 | 433/BQA | 08/02/2024 | 30 | LEMNISCATE | 3.39 | 0 | 100
614 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000078/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.82 | 0 | 0
615 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000231/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.82 | 0 | 0
616 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00160/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
617 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for Saulia (Zone -G) water supply scheme at head works site Barjora block under BMD,PHE Dte.(SM/16960) | Assistant Engineer | Junior Engineer | BILL/00348/2024-2025 | BP-2024-25-170 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.51 | 0 | 0
618 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Saulia (Zone-G) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 503/BMD | 09/07/2024 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 13.19 | 0 | 0
619 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Saulia ( Zone-G) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000303/2023-2024 | 1406/BMD | 18/07/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.3 | 61.78 | 75
620 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- II at Tail End site of Augmentation works for Saulia (Zone-G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000314/2024-2025 | 855/BMD | 29/08/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 19.1 | 0 | 0
621 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall and High lift Pump House at OHR Site under Augmentation of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000351/2024-2025 | 2346/BQA | 09/09/2024 | 320 | PRADIP PATRA | 31.2 | 0 | 100
622 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000380/2023-2024 | 2041/BQA | 24/07/2023 | 887 | PRADIP RAJAK | 383.03 | 133.87 | 51
623 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Bonkati (Zone- R) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2023-2024 | 453/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 1.7 | 0 | 100
624 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000084/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.71 | 0 | 0
625 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000244/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.71 | 0 | 0
626 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00148/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
627 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01611/2023-2024 | BP-2023-24-137 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.75 | 0 | 0
628 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Bankati (Zone-R ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000009/2025-2026 | 144/BMD | 30/04/2025 | 90 | EASTERN INDIA SALES & SERVICE | 20.27 | 0 | 0
629 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Bonkati (Zone R) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000524/2023-2024 | 1888/BMD | 17/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 52.37 | 64
630 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of KALYANI and adjoining mouzas W/S Scheme (Zone - A) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000295/2023-2024 | 1913/BQA | 13/07/2023 | 1084 | GOUTAM BHOWMIK | 143.3 | 111.41 | 90
631 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000076/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1 | 0 | 0
632 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000227/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1 | 0 | 0
633 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-A) and Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000609/2023-2024 | 2083/BMD | 12/09/2023 | 120 | P.K. ENGINEERING | 71.94 | 59.66 | 60
634 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHANSIMLA PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 1196/BQA | 22/05/2023 | 955 | SINGHA ENTERPRISE | 138.96 | 68.93 | 90
635 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000027/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 11.52 | 0 | 0
636 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Dhansimla TW-1 | Assistant Engineer | Junior Engineer | BILL/00027/2024-2025 | BP-2024-25-17 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.53 | 0 | 0
637 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Dhansimla T/W-II water supply under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00030/2024-2025 | BP-2024-25-18 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.07 | 0 | 0
638 | Bankura Mechanical | Brishnupur Sub-Division | Additional Quotation payment for diversion of HTOH line due to objection of local people for effecting of new connection at Dhansimla T/W-II | Assistant Engineer | Junior Engineer | BILL/00729/2024-2025 | BP-2024-25-212 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0
639 | Bankura Mechanical | Brishnupur Sub-Division | Dhan Simla Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01516/2023-2024 | BP-2023-24-113 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.04 | 0 | 0
640 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Dhansimla piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000423/2023-2024 | 1685/BMD | 27/07/2023 | 1080 | PRADIP KUMAR DHABAL | 37.28 | 17.48 | 46
641 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AMRUL ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000323/2023-2024 | 1927/BQA | 13/07/2023 | 990 | PRINCE INDUTRIES (INDIA) | 171.45 | 98.48 | 80
642 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Amrul (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001377/2024-2025 | 18/BQA | 02/01/2025 | 394 | MRITYUNJOY HAZRA | 12.96 | 0 | 85
643 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00181/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
644 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AMRUL ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00432/2024-2025 | BP-2024-25-103 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
645 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Mahespur (Amrul Zone-B) | Assistant Engineer | Junior Engineer | BILL/01332/2024-2025 | BP-2024-25-339 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0
646 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01619/2023-2024 | BP-2023-24-158 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
647 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Amrul (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 1697/BMD | 28/07/2023 | 720 | WEST BENGAL ENGINEERING CO. | 73.36 | 0 | 40
648 | Bankura Division | Bankura Sadar Sub-Division | Construction 100 Cum. Clear Water Reservoir for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000691/2023-2024 | 2637/BQA | 21/09/2023 | 641 | NAYAN BARDHAN | 23.64 | 0 | 10
649 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000692/2023-2024 | 2638/BQA | 21/09/2023 | 90 | MA USHA CONSTRUCTION CO. | 11.58 | 0 | 0
650 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline and Construction & commissioning of ?FHTC (Functional House Hold Tap Connection)? for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000765/2023-2024 | 2868/BQA | 11/10/2023 | 165 | BEAUTY CHATTERJEE | 41.67 | 11.56 | 20
651 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline and Construction & commissioning of ?FHTC (Functional House Hold Tap Connection)? for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000766/2023-2024 | 2869/BQA | 11/10/2023 | 45 | BIJOY KOLEY | 41.67 | 13.04 | 20
652 | Bankura Division | Bankura Sadar Sub-Division | Laying Rising Main for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000767/2023-2024 | 2873/BQA | 11/10/2023 | 45 | SONU SINGH | 5.02 | 0 | 0
653 | Bankura Division | Bankura Sadar Sub-Division | Laying Rising Mainfor sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 2874/BQA | 11/10/2023 | 45 | DURGADAS SINGHA | 5.02 | 0 | 0
654 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000790/2023-2024 | 2870/BQA | 11/10/2023 | 45 | TAPAS KUMBHAKAR | 28.41 | 10.74 | 20
655 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000791/2023-2024 | 2871/BQA | 11/10/2023 | 629 | JAGADISH BANERJEE | 28.41 | 9.01 | 21
656 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 2872/BQA | 11/10/2023 | 315 | TAPAN KUMAR UPADHYAY | 28.41 | 9.18 | 20
657 | Bankura Division | Bankura Sadar Sub-Division | Construction of 200 Cum. OHR for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2023-2024 | 2947/BQA | 30/10/2023 | 884 | ANWESHA CONSTRUCTION | 78.68 | 0 | 1
658 | Bankura Division | Bankura Sadar Sub-Division | Route Survey Preparation of DPR for piped water supply scheme for uncover mouzas of Ramjibanpur (JL No- 85), Pabra (86) & Niamatpur (JL No- 92) Block- Saltora under Jal Jeevan Misson (JJM) of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000853/2023-2024 | 2979/BQA | 31/10/2023 | 30 | LEMNISCATE | 2.75 | 0 | 100
659 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary Wall with ancillary works at OHR site for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000860/2023-2024 | 2639/BQA | 21/09/2023 | 923 | ASHIS PAL | 12.71 | 9.93 | 5
660 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000893/2023-2024 | 3044/BQA | 06/11/2023 | 30 | K S GROUP | 0.56 | 0 | 100
661 | Bankura Division | Bankura Sadar Sub-Division | Balance Work of Soil investigation work for construction of OHR (200 cum capacity) under proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District- Bankura under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001601/2023-2024 | 421/BSD | 18/03/2024 | 10 | K S GROUP | 0.94 | 0.94 | 100
662 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 80.61 | 0 | 0
663 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 7.04 | 0 | 0
664 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000149/2023-2024 | 3467/BQA | 20/12/2023 | 0 | Resource Division | 12.07 | 0 | 0
665 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000267/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 7.04 | 0 | 0
666 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00196/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
667 | Bankura Mechanical | Bankura Sadar Sub-Division | New 3 phase service connection for Pabra w/s Scheme | Assistant Engineer | Junior Engineer | BILL/00728/2024-2025 | BP-2024-25-210 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0
668 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation work of 06 nos OHR under Saltora-Chhatna Water scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 155/BMD | 30/04/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 29.72 | 0 | 0
669 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Pabra under Water Supply Scheme Block- Saltora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000446/2023-2024 | 1774/BMD | 01/08/2023 | 60 | ABHIJIT MUKHERJEE | 46.8 | 32.3 | 37
670 | Bankura Division | Brishnupur Sub-Division | Laying of distribution system, Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold and Repairing and Renovation of RCC Elevated Over Head Reservoir of 90 cum capacity with staging height 20 m and other allied works in connection with Jal Jeevan Mission (JJM) of Panchal Zone-I W/S Scheme within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Sonamukhi, Location of OHR :-Jamdoba No. of Mouzas Covered :- 3 nos., Name of Mouzas & JL No.:-Jamdoba (154), Ichharia (155), Bhabanipur (165) Total No. House Hold:-12 | Assistant Engineer | Junior Engineer | ORD/000796/2022-2023 | 679/BQA | 28/03/2023 | 270 | SOUMITRA KUMAR DAS | 22.93 | 22.91 | 95
671 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House, including plinth protection, Ramp etc of departmental design & drawing in connection with Jal Jeevan Mission (JJM) for Augmentation of MALIARA (Zone - A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000347/2024-2025 | 2341/BQA | 09/09/2024 | 450 | ASHOK KUMAR DEY | 17 | 0 | 0
672 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of MALIARA (Zone - A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000509/2023-2024 | 2360/BQA | 14/08/2023 | 810 | SWAPAN KUMAR UPADHYAY | 294.78 | 49.87 | 46
673 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001175/2023-2024 | 426/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.62 | 0 | 100
674 | Bankura Division | Bankura Sadar Sub-Division | Continuation for hiring car equivalewnt to Motor Cab & Maruti Omni (Standard) with Mass emission standard of BS-III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer ,Bankura Sadar Sub-Division , P.H.E Dte. with effect from (01/01/2024 to 30/06/2024) (Six Months) | Assistant Engineer | Junior Engineer | ORD/001219/2023-2024 | 3538/BQA | 29/12/2023 | 183 | GOURANGA NANDI | 0.87 | 2.39 | 100
675 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000095/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.47 | 0 | 0
676 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000269/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.47 | 0 | 0
677 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00139/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
678 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Maliara (Zone-A) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 500/BMD | 09/07/2024 | 120 | SUTRADHAR TRADERS | 13.17 | 0 | 0
679 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Maliara ( Zone-A) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1404/BMD | 18/07/2023 | 851 | B T PROJECTS PRIVATE LIMITED | 82.62 | 51.28 | 73
680 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000821/2023-2024 | 2930/BQA | 26/10/2023 | 798 | SHANTA COLIBRI (INDIA) PVT LTD | 320.93 | 95.17 | 32
681 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (300 CUM CAPACITY) under Augmentation of Sonadaha (Zone- Q) under Bankura- I, II & Barjora W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000885/2023-2024 | 3036/BQA | 06/11/2023 | 30 | K S GROUP | 0.49 | 0.49 | 100
682 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Sonadaha (Zone- Q) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001199/2023-2024 | 452/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 1.08 | 0 | 100
683 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall, High lift Pump House, Laying Rising Main under Augmentation of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001341/2024-2025 | 3180/BQA | 24/12/2024 | 463 | JAGADISH BANERJEE | 43.62 | 0 | 70
684 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000098/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.23 | 0 | 0
685 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000274/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
686 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00138/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
687 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Sonadaha water supply scheme at Bankura -II block under BMD PHE Dte.(SM/17240) | Assistant Engineer | Junior Engineer | BILL/01338/2024-2025 | BP-2024-25-338 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.02 | 0 | 0
688 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Sonadaha (Zone-Q) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000525/2023-2024 | 1889/BMD | 17/08/2023 | 1032 | PREMNATH MITRA | 81.81 | 0 | 65
689 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Sonadaha( Zone-Q) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000166/2024-2025 | 508/BMD | 09/07/2024 | 120 | M/S BIPUL BANERJEE | 8.77 | 5.34 | 60
690 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division | Assistant Engineer | Junior Engineer | ORD/000394/2023-2024 | 2054/BQA | 24/07/2023 | 708 | SAIKAT CHOWDHURY | 86.91 | 30.42 | 26
691 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for ANCHURI (Zone- T2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2023-2024 | 3040/BQA | 06/11/2023 | 30 | K S GROUP | 0.58 | 0 | 100
692 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001204/2023-2024 | 457/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 3.85 | 0 | 100
693 | Bankura Division | Bankura Sadar Sub-Division | Barbed wire Fencing works at ANCHURI (Zone - T-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001481/2023-2024 | 207/BSD | 02/02/2024 | 10 | SANTI RANJAN MANDAL | 0.85 | 0.85 | 100
694 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000099/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.54 | 0 | 0
695 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000276/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.54 | 0 | 0
696 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00150/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
697 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Anchuri augmentation at Kasiadoba,Bankura-I block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01489/2024-2025 | BP-2024-25-378 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0
698 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Anchuri (Zone-T ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 145/BMD | 30/04/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 0
699 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Achuri (Zone-T) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 1468/BMD | 18/07/2023 | 600 | ABHIJIT MUKHERJEE | 81.82 | 57.08 | 76
700 | Bankura Division | Brishnupur Sub-Division | Additional sinking of 1 no 300mm X 200mm X 165m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Morar Zone-B of Bishnupur Block (JJM) under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000263/2025-2026 | 1541/BQA | 14/07/2025 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.02 | 0 | 0
701 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF MORAR ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 2037/BQA | 24/07/2023 | 810 | M/S D.PALIT & CO. | 159.64 | 90.12 | 80
702 | Bankura Division | Brishnupur Sub-Division | Renovation of RCC Elevated Over Head Reservoir of 550 cum capacity with staging height 20 m and other allied works Augmentation of Chakuparsole Zone-B & Morar Zone-B Water Supply Scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000416/2025-2026 | 1968/BQA | 15/09/2025 | 90 | ASHIS PAL | 11.9 | 0 | 0
703 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Morar (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001363/2024-2025 | 3125/BQA | 19/12/2024 | 90 | TAPAS DEY | 12.93 | 0 | 0
704 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Chuamasina Zone-B Water Supply Scheme (SM/17427), 2 nos. sites of Augmentation of Morar Zone-A Water Supply Scheme (SM/17237) & 1 no. sites of Augmentation of Morar Zone-B Water Supply Scheme (SM/17243) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001805/2024-2025 | 534/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.75 | 0 | 0
705 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Morar Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00165/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
706 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Marar Zone-B TW-II Mouza Agunkumari ,Block Bishnupur.SM/17243 | Assistant Engineer | Junior Engineer | BILL/01094/2024-2025 | BP-2024-25-249 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0
707 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-B TW-III Mouza Belsulia.SM-17243 | Assistant Engineer | Junior Engineer | BILL/01140/2024-2025 | BP-2024-25-286 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.33 | 0 | 0
708 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-B TW-I Mouza Chandabila .Block Bishnupur SM-17243 | Assistant Engineer | Junior Engineer | BILL/01144/2024-2025 | BP-2024-25-287 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.23 | 0 | 0
709 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HSC pumping machineries with allied work for Augmentation of Marar Zone-B and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission programme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000267/2024-2025 | 775/BMD | 20/08/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 44.9 | 0 | 0
710 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 1711/BMD | 28/07/2023 | 900 | M.S. ENTERPRISE | 95.96 | 72.81 | 81
711 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Bakshibandh (Zone ¿ J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2024-2025 | 2436/BQA | 25/09/2024 | 30 | CARTO | 2.21 | 0 | 80
712 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Boxibandh (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Boxibandh, Total House Hold - 621 nos. | Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 586/BQA | 20/03/2023 | 1108 | M/S TARUN KUMAR PATRA | 90.34 | 10.3 | 12
713 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000106/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.86 | 0 | 0
714 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000288/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.86 | 0 | 0
715 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block - Barjora, Name of OHR - BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone - IV), No. of Mouza :- 06 nos., Name of mouza:- (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), No. of Household-1690 nos | Assistant Engineer | Junior Engineer | ORD/000811/2022-2023 | 714/BQA | 30/03/2023 | 90 | ASHIS PAL | 31.43 | 31.43 | 100
716 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 03 (Three) no. 200 mm X 165 mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 715/BQA | 30/03/2023 | 45 | GANESH ROY | 12.95 | 8.34 | 90
717 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block - Barjora, Name of OHR - BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone - IV), No. of Mouza :- 06 nos., Name of mouza:- (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), No. of Household- 200 nos | Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 716/BQA | 30/03/2023 | 90 | MOHAN KUMAR ROY | 43.66 | 18.04 | 90
718 | Bankura Division | Bankura Sadar Sub-Division | 100 mm dia & 150 mm dia MS delivery main connecting line from 2 (two) nos Vertical Tube Well to CWR & CWR to OHR Inlet pipe ,1 (one) nos Vertical Tube Well to Distribution pipe in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 717/BQA | 30/03/2023 | 90 | SANDHYA DEY | 4.95 | 0 | 22
719 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001188/2023-2024 | 440/BQA | 08/02/2024 | 30 | LEMNISCATE | 2 | 0 | 100
720 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe line, Construction of Pump House cum chlorine room, Construction of Pump House & Toilet at head work site & Boundary wall under Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/001394/2024-2025 | 41/BQA | 02/01/2025 | 90 | PRAVAT SARKAR | 56.51 | 0 | 0
721 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000134/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.18 | 0 | 0
722 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000251/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.18 | 0 | 0
723 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | Assistant Engineer | Junior Engineer | BILL/00158/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
724 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail End at GOPBANDHI, Saharjora for Augmentation works under BARJORA (ZONE -IV) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000183/2024-2025 | 578/BMD | 24/07/2024 | 120 | NUPUR CHANDRA HALDER | 13.15 | 0 | 0
725 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IV) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1402/BMD | 18/07/2023 | 60 | WEST BENGAL ENGINEERING CO. | 81.8 | 54.19 | 55
726 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) ( Zone IV) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001037/2023-2024 | 2969/BMD | 29/02/2024 | 725 | M/S S.G. ENTERPRISE | 27.54 | 0 | 99
727 | Bankura Division | Khatra Sub-Division | Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-F (Masanjhar) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000068/2024-2025 | 1503/BQA | 18/06/2024 | 228 | RUFIKUL MONDAL | 19.6 | 4.36 | 50
728 | Bankura Division | Khatra Sub-Division | Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Masanjhar (Zone- F) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2023-2024 | 1355/BQA | 02/06/2023 | 486 | GOURANGA CHATTERJEE | 48.69 | 48.68 | 30
729 | Bankura Division | Khatra Sub-Division | Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Masanjhar (Zone- F) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2023-2024 | 1360/BQA | 02/06/2023 | 668 | EARTH MOVING (INDIA) | 48.69 | 47.17 | 20
730 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000842/2023-2024 | 2968/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.39 | 2.03 | 95
731 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000167/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.82 | 0 | 0
732 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00206/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
733 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Masanjhar (Zone F) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 251/BMD | 14/05/2025 | 90 | NUPUR CHANDRA HALDER | 28.18 | 0 | 0
734 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DWARIKA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2023-2024 | 2323/BQA | 14/08/2023 | 871 | DEBAKI RANJAN SARKAR | 631.76 | 219.97 | 87
735 | Bankura Division | Brishnupur Sub-Division | Preparation of Detailed Project Report for Proposed ground water based Dwarika pipe water supply scheme, under Bankura Division Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 485/BQA | 09/02/2024 | 150 | ROY CHOWDHURY ASSOCIATES | 3.09 | 3.09 | 90
736 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Jamuna Band Pipe Water Supply Scheme (SM/18037) & 2 nos. sites of Dwarika Pipe Water Supply Scheme (SM/17224) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001811/2024-2025 | 537/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.6 | 0 | 0
737 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 18.58 | 0 | 0
738 | Bankura Mechanical | Brishnupur Sub-Division | Dwarika Pipe Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01610/2023-2024 | BP-2023-24-136 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.76 | 0 | 0
739 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed ground water based Dwarika piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001082/2023-2024 | 3060/BMD | 12/03/2024 | 835 | RAJIB COMPANY | 44.62 | 7.42 | 55
740 | Bankura Division | RWS Bankura Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-B (Tilaboni) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2022-2023 | 566/BQA | 17/03/2023 | 45 | M/S SUPRIYA CHATTERJEE | 61.85 | 61.4 | 100
741 | Bankura Division | RWS Bankura Sub-Division | Laying HDPE pipeline, Construction and Commissioning of FHTC (Functional House Hold Tap Connection), Construction of platform with all allied works of Zone-B (Tilabani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 401/BQA | 07/02/2024 | 754 | M/S PARAMESWAR CHOWDHURY | 54.4 | 36.43 | 87
742 | Bankura Division | RWS Bankura Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.59 | 0 | 0
743 | Bankura Division | RWS Bankura Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000296/2023-2024 | 738/BQA | 01/03/2024 | 0 | Resource Division | 25.98 | 0 | 0
744 | Bankura Mechanical | RWS Bankura Sub-Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00204/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
745 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Tilaboni (Zone B ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 254/BMD | 14/05/2025 | 90 | S.P. CONSTRUCTION | 28.43 | 0 | 0
746 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PANCHAL ZONE-II PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000409/2023-2024 | 2094/BQA | 27/07/2023 | 1162 | M/S D.PALIT & CO. | 138.26 | 71.7 | 80
747 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Rampur Water Supply Scheme (SM/09454 ), 3 nos. sites of Augmentation of Panchal Zone-I Water Supply Scheme (SM/17233) & Augmentation of Panchal Zone-II Water Supply Scheme (SM/17423) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001890/2024-2025 | 568/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
748 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | BILL/00025/2024-2025 |  | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0
749 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | BILL/00026/2024-2025 | 1 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0
750 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Panchal Zone-II Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00187/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
751 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Sukhsayer water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00380/2024-2025 | BP-2024-25-85 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0
752 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal water supply scheme under Bankura Mechanical Division PHE Dte.(SM-17423) | Assistant Engineer | Junior Engineer | BILL/00417/2024-2025 | BP-2024-25-97 | 04/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0 | 0 | 0
753 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Panchal (Zone-II) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1789/BMD | 01/08/2023 | 1080 | TAPAN KUMAR SARKAR | 41.85 | 16.61 | 40
754 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House with all allied works at Dadhimukha (Zone- D), OHR Site under Augmentation of Dadhimukha Water Supply Scheme under Jal Jeevan Mission (JJM) under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000176/2024-2025 | 1851/BQA | 12/07/2024 | 308 | SAYED PAHALOWAN | 18.37 | 0 | 100
755 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000491/2023-2024 | 2343/BQA | 14/08/2023 | 969 | SINGHA ENTERPRISE | 179.63 | 90.76 | 75
756 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Dadhimukha (Zone- D) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001178/2023-2024 | 430/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.69 | 0 | 100
757 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Godardihi (Zone- E) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001179/2023-2024 | 431/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.31 | 0 | 100
758 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low Lift Pump House and Boundary Wall at Asnasole Mouza and Boundary Wall at Rautara Mouza under Augmentation of Dadhimukha (Zone- D) Water Supply Scheme. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001404/2024-2025 | 47/BQA | 02/01/2025 | 90 | SOUHARDYA BUSINESSLINE | 22.87 | 0 | 0
759 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000121/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.39 | 0 | 0
760 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000270/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.39 | 0 | 0
761 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00135/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
762 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for at Rautara tail end T/W under Dadhimukha (zone-D) water supply scheme Barjora block under BMD,PHE Dte.(SM/17424 ) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00347/2024-2025 | 12 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
763 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement Service connection charge for Dadhimukha (zone-D) OHR site water supply scheme Barjora block under BMD,PHE Dte.(SM/17424 ) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/02192/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0
764 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation works at Rautara Pump house (Tail End) under Dadhimukha (Zone -D) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000154/2024-2025 | 497/BMD | 09/07/2024 | 480 | GOENKA ENTERPRISE | 23.1 | 9.32 | 30
765 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Dadhimukha ( Zone-D) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000455/2023-2024 | 1781/BMD | 01/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 30
766 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHAKUPARSOLE ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 2050/BQA | 24/07/2023 | 979 | PRINCE INDUTRIES (INDIA) | 201.42 | 117.33 | 90
767 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Chakuparsole (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001352/2024-2025 | 3169/BQA | 24/12/2024 | 90 | SUBHAJIT BANERJEE | 25.94 | 0 | 0
768 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chakuparsole Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00169/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
769 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Mouza-Dihar. of Aug of Prakash zone-A w/s scheme.SM/17222. | Assistant Engineer | Junior Engineer | BILL/00645/2026-2027 |  | 17/06/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.93 | 0 | 0
770 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new serrvice connection at Chak Uparsole Z-A TW-II JL 135 Mouza Bhaluka.SM -17425 | Assistant Engineer | Junior Engineer | BILL/01142/2024-2025 | BP-2024-25-282 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.43 | 0 | 0
771 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chakuparsole zone-A ,Mouza - Baramara. GP-Bankadaha.SM-17425 | Assistant Engineer | Junior Engineer | BILL/01173/2024-2025 | BP-2024-25-295 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.65 | 0 | 0
772 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Chak Uparsole Z-A Mouza -Majuria. Block -Bishnupur.SM-17425 | Assistant Engineer | Junior Engineer | BILL/01184/2024-2025 | BP-2024-25-296 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.29 | 0 | 0
773 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Hetagora of Chakuparsole Zone-A w/s scheme .SM/17425 | Assistant Engineer | Junior Engineer | BILL/01655/2024-2025 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.55 | 0 | 0
774 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW I to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000141/2024-2025 | 484/BMD | 09/07/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 40.43 | 24.39 | 100
775 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chakuparsole (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000518/2023-2024 | 1883/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 71.39 | 0 | 75
776 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set and other allied works at Prakash Zone-A & Chakuparsol Zone-A water supply scheme under Bishnupur Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2025-2026 | 640/BMD | 11/07/2025 | 90 | MIK ENTERPRISES | 20.18 | 0 | 0
777 | Bankura Division | Bankura Sadar Sub-Division | Regarding permission and revision of estimate of permanent restroration work for the purpose of leakage repairing works on Rangamati-Asuria-Dejuri Road | Assistant Engineer | Junior Engineer | BILL/00620/2023-2024 | FHTC/11 | 09/11/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.23 | 0 | 0
778 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-III) | Assistant Engineer | Junior Engineer | ORD/000432/2023-2024 | 2266/BQA | 01/08/2023 | 270 | SIB SANKAR CHOWDHURY | 255.5 | 111.58 | 50
779 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House, 450 cum OHR along with soil investigation work, boundary wall and laying of rising main under Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III) | Assistant Engineer | Junior Engineer | ORD/000535/2025-2026 | 2154/BQA | 30/10/2025 | 90 | CHAKRABORTTI ENTERPRISE | 166.89 | 0 | 0
780 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001187/2023-2024 | 439/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.54 | 0 | 100
781 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000122/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.54 | 0 | 0
782 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000268/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.54 | 0 | 0
783 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | Assistant Engineer | Junior Engineer | BILL/00157/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
784 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Hatasuria OHR site under Barjora (Zone-III) water supply scheme (left out mouza of Barjora) , Barjora block under BMD, PHE Dte. (SM/17428) | Assistant Engineer | Junior Engineer | BILL/01335/2024-2025 | BP-2024-25-334 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.75 | 0 | 0
785 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail end site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) ( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 498/BMD | 09/07/2024 | 120 | S.DUTTA | 13.17 | 5.03 | 38
786 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 120 | SINHA ELECTRICALS | 11.28 | 0 | 0
787 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 1401/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.83 | 61.51 | 48
788 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF ROL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000402/2023-2024 | 2087/BQA | 27/07/2023 | 614 | S.N POLYMERS PVT LTD | 107.14 | 61.59 | 50
789 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Augmentation of Rol Zone-A Water Supply Scheme (SM/17693) & 3 nos. sites of Augmentation of Rol Zone-B Water Supply Scheme (SM/17683) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001820/2024-2025 | 541/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
790 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Rol Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00182/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
791 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for ROLL ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00433/2024-2025 | BP-2024-25-106 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
792 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000377/2023-2024 | 1703/BMD | 28/07/2023 | 611 | M/S BIPUL BANERJEE | 39.07 | 19.6 | 50
793 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 2346/BQA | 14/08/2023 | 810 | SWAPAN KUMAR UPADHYAY | 214.79 | 103.11 | 50
794 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Joykrishnapur (Zone- I) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001183/2023-2024 | 435/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.85 | 0 | 100
795 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000127/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.54 | 0 | 0
796 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000259/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.54 | 0 | 0
797 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00159/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
798 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Joykrishnapur (Zone-I) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 501/BMD | 09/07/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 13.36 | 0 | 0
799 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joykrisnapur ( Zone-I) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000300/2023-2024 | 1403/BMD | 18/07/2023 | 60 | M/S SOMA ENTERPRISES | 81.75 | 66.22 | 35
800 | Bankura Division | Bankura Sadar Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS PROPOSED GROUND WATER BASED JHATIBONI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- ONDA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 1916/BQA | 13/07/2023 | 1173 | APEX ENTERPRISE | 221.76 | 77.7 | 40
801 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (150 CUM CAPACITY) under Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2023-2024 | 3047/BQA | 06/11/2023 | 30 | K S GROUP | 0.57 | 0 | 100
802 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Jhatibone (JL No- 270) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001088/2021-2022 | 282\BSD | 21/03/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.46 | 3.46 | 98
803 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 1.42 | 0 | 0
804 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000124/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.91 | 0 | 0
805 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000263/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.91 | 0 | 0
806 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for shifting of 11KV HTOH at Jhatiboni ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00287/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0
807 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | Assistant Engineer | Junior Engineer | BILL/01607/2023-2024 | BP-2023-24-134 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.73 | 0 | 0
808 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000124/2024-2025 | 1072/BMSD | 05/07/2024 | 60 | M/S DE ENGINEERING CONCERN | 4.37 | 0 | 0
809 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000443/2023-2024 | 1772/BMD | 01/08/2023 | 720 | INDRAJIT MITRA | 36.9 | 18.79 | 90
810 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 26 Nos (Part- A) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 652/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.97 | 0.97 | 100
811 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- B) | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 653/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.94 | 0.94 | 100
812 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- C) | Assistant Engineer | Junior Engineer | ORD/000297/2024-2025 | 654/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.96 | 0.96 | 100
813 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- D) | Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 655/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.96 | 0.96 | 100
814 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- E) | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 656/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.96 | 0.96 | 100
815 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1956/BQA | 18/07/2023 | 944 | SUBHADIP KOLEY | 110.17 | 69.22 | 100
816 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low Lift Pump House and Boundary Wall under Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001399/2024-2025 | 44/BQA | 02/01/2025 | 545 | M/S KHAN ENTERPRISE | 28.99 | 0 | 1
817 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000118/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.86 | 0 | 0
818 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000278/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.86 | 0 | 0
819 | Bankura Division | Bankura Sadar Sub-Division | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 14 Nos (Part- F) | Assistant Engineer | Junior Engineer | ORD/000302/2024-2025 | 657/BSD | 10/06/2024 | 207 | PRADYUMNA KOLEY | 0.65 | 0.65 | 100
820 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 02 (Two) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001389/2024-2025 | 36/BQA | 02/01/2025 | 375 | SUBHADIP KOLE | 22.11 | 0 | 1
821 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur (Zone-B) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 1994/BMD | 28/08/2023 | 120 | UNITED TRADERS | 46.43 | 29.8 | 80
822 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Radhanagar Zone - I Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/000361/2025-2026 | 1802/BQA | 19/08/2025 | 90 | JAMIRUL CONSTRUCTION | 12.72 | 0 | 0
823 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RADHANAGAR ZONE-I PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000379/2023-2024 | 2040/BQA | 24/07/2023 | 891 | SIB SANKAR CHOWDHURY | 221.76 | 94.79 | 90
824 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 1 no. sites of Augmentation of Radhanagar Zone-I Water Supply Scheme (SM/17690) & 2 nos. sites of Augmentation of Radhanagar Zone-II Water Supply Scheme (SM/17691) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001810/2024-2025 | 536/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.45 | 0 | 0
825 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00162/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
826 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Sarada Pally (Bankati) of Radhanagar Zone-I ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00294/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
827 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Swasan of Radhanagar Zone-I ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00295/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.85 | 0 | 0
828 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for Kankila OHR of Radhanagar w/s scheme. | Assistant Engineer | Junior Engineer | BILL/00536/2024-2025 | 1 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0
829 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR, CWR and Tail end site for Augmentation of Radhanagar (Zone I) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000120/2024-2025 | 430/BMD | 27/06/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 61.72 | 17.33 | 100
830 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineryes with allied works for Augmentation of Radhanagar Zone-I Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 863/BMD | 29/08/2024 | 480 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 20.86 | 0 | 50
831 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-I) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000373/2023-2024 | 1701/BMD | 28/07/2023 | 704 | TAPAN KUMAR SARKAR | 40.91 | 22.96 | 82
832 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Hatirampur Canal Bridge to Baharamuri village with all allied works of Zone-Q (Jambedia) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2024-2025 | 2326/BQA | 06/09/2024 | 320 | AKRAM BHANGI | 3.34 | 0 | 90
833 | Bankura Division | Khatra Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-Q (Jambedia) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000817/2022-2023 | 722/BQA | 30/03/2023 | 90 | SHYAMAL KUMAR DAS | 38.54 | 33.88 | 80
834 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000174/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
835 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Jambedia (Zone Q) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000051/2025-2026 | 250/BMD | 14/05/2025 | 90 | JAL PRAVAHIKA PVT LTD | 25.68 | 0 | 0
836 | Bankura Division | Khatra Sub-Division | New service connection for Keshia, Jl-241,plot-72,Kadra (Zone-G) Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00129/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | KHATRA CCC | 0.46 | 0 | 0
837 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline with all allied works of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000193/2024-2025 | 2134/BQA | 07/08/2024 | 451 | TAPAN KUMAR MANDAL | 26.97 | 0 | 90
838 | Bankura Division | Khatra Sub-Division | Construction of Pump House with ancillary works for newly constructed Tubewell site (Location- Kesia High School) of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000284/2024-2025 | 2177/BQA | 12/08/2024 | 172 | SAIMUDDIN MOLLAH | 6.22 | 2.76 | 70
839 | Bankura Division | Khatra Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-G (Kadra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000802/2022-2023 | 721/BQA | 30/03/2023 | 978 | MUNMUN UPADHYAY | 80.93 | 63.77 | 80
840 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Augmentation of Zone-G (Kadra) Water Supply Scheme (SM/17433), 1 no. site of Augmentation of Zone-H (Arkama) Water Supply Scheme ( SM/17254), 1 no. site of Augmentation of Baragari (Zone- IIA) Water Supply Scheme (SM/17711), 1 no. site of Augmentation of Zone-IIB (Hetiasol) Water Supply Scheme (SM/17430), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- I/A Water supply scheme (SM/15007), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- I/B Water supply scheme (SM/15001) within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001908/2024-2025 | 152\KSD | 07/03/2025 | 10 | BIKASH MANDAL | 0.9 | 0 | 90
841 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000168/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
842 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Kadra (Zone G) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000042/2025-2026 | 246/BMD | 14/05/2025 | 90 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0
843 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kadra (Zone- G) ( Boosting at Tail end) under Khatra-Hirbandh-Ranibandh Water Supply Scheme piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000168/2024-2025 | 510/BMD | 09/07/2024 | 719 | RAJIB COMPANY | 13.22 | 0 | 75
844 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Basantapur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00197/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
845 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
846 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
847 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 41 | 48
848 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from T02-Banskopa to Jugda under Taldangra Block in the District of Bankura ,Vide Package No- WB-03-435, Road Length-11.49 Km.( Augmentation of water supply scheme for Pathardoba (Zone-B) under Simlapal water supply scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01459/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.2 | 0 | 0
849 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Balarampur - Ramboni under Simlapal Block in the District of Bankura ,Vide Package No- WB-03-188, Road Length-5.702 Km. ( Augmentation of water supply scheme for Pathardoba (Zone-B) under Simlapal water supply scheme (BRGF Ph-l) | Assistant Engineer | Junior Engineer | BILL/01467/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.47 | 0 | 0
850 | Bankura Division | Khatra Sub-Division | Repair and maintenance work of the road from T03-Bagakhnila under Simlapal Block in the district of Bankura vide package No. WB-03-193, Road length - 2.64 Km. (Augmentation of Water Supply Scheme of Pathardoba Zone-B under Simlapal Water Supply Scheme BRGF Phase-I) | Assistant Engineer | Junior Engineer | BILL/01468/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.89 | 0 | 0
851 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room, Boundary Wall and laying distribution pipeline for providing FHTC, Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Pathardoba, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000256/2025-2026 | 1505/BQA | 08/07/2025 | 185 | APEX ENTERPRISE | 156.89 | 0 | 0
852 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000832/2023-2024 | 2958/BQA | 31/10/2023 | 30 | GEO SOLUTION | 3.54 | 3.53 | 96
853 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001611/2024-2025 | 311/BQA | 28/01/2025 | 210 | M/S PARAMESWAR CHOWDHURY | 104.47 | 0 | 0
854 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System other work at Pathardoba Zone -A water supply scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000192/2025-2026 | 637/BMD | 11/07/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 15.72 | 0 | 0
855 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement and installation od new charger panel and other allied works for Augmentation for PATHARDOBA ZONE -B water supply scheme under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000274/2024-2025 | 779/BMD | 20/08/2024 | 371 | M/S BIPUL BANERJEE | 18.58 | 0 | 55
856 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-B and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000994/2023-2024 | 2854/BMD | 09/02/2024 | 545 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 134.65 | 89.23 | 65
857 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Lo49-Kharjuria to MDR under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-478, Road Length-1.099 Km. ( Augmentation of water supply scheme for Parsola (Zone-B) under Simlapal water supply scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01460/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.26 | 0 | 0
858 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Parsola Zone - B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2024-2025 | 1490/BQA | 18/06/2024 | 30 | MESAURE LAND | 1.26 | 1.21 | 90
859 | Bankura Division | Khatra Sub-Division | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR and road crossing of distribution pipeline at different location by trenchless technologies with other allied works of Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2025-2026 | 1315/BQA | 17/06/2025 | 184 | APEX ENTERPRISE | 42.63 | 0 | 0
860 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001619/2024-2025 | 242/BQA | 21/01/2025 | 465 | NAYAN BARDHAN | 133.96 | 0 | 15
861 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/18893], 2 nos. site of Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/18895], 1 nos. site of Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/18892] and 2 nos. site of Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC) [SM/10294] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001928/2024-2025 | 172\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
862 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 200 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Parsola, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001971/2024-2025 | 667/BQA | 12/03/2025 | 265 | PRADIP PATRA | 11.21 | 0 | 70
863 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of water supply scheme for Parsola Zone-B and its adjoining mouzas under simlapal water (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000991/2023-2024 | 2851/BMD | 09/02/2024 | 518 | QUAZI NOZRUL ISLAM | 102.52 | 0 | 40
864 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from T07-Topubaip under Simlapal Block in the District of Bankura , Vide Package No- WB - 03-191 Road Length - 4.743Km. ( Augmentation of water supply scheme for Pathardoba (Zone-A) under Simlapal water supply scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01466/2024-2025 | BP/452/2024-25 | 20/01/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.57 | 0 | 0
865 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 500 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Pathardoba, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2025-2026 | 1287/BQA | 17/06/2025 | 90 | PARESH CHANDRA LAYEK | 18.76 | 0 | 0
866 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Pathardoba Zone - A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2024-2025 | 2434/BQA | 25/09/2024 | 30 | CARTO | 2.53 | 2.48 | 90
867 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001614/2024-2025 | 233/BQA | 20/01/2025 | 437 | GOPAL CHANDRA CHOWDHURY | 244.27 | 0 | 40
868 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01656/2023-2024 | BP-2023-24-172 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0
869 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-A and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000993/2023-2024 | 2853/BMD | 09/02/2024 | 720 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 135.08 | 114.91 | 70
870 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 48 | 48
871 | Bankura Division | RWS Bankura Sub-Division | New service connection for "kalipahari" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00067/2024-2025 | BP-38/2024-25 | 06/05/2024 | 0 | JHANTIPAHARI CCC | 0.12 | 0 | 0
872 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
873 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
874 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
875 | Bankura Division | Brishnupur Sub-Division | New Connection at Sapuradihi, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00295/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
876 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
877 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
878 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
879 | Bankura Division | Brishnupur Sub-Division | (site - Mukha, lowgram, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00289/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
880 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
881 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
882 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Mukha | Assistant Engineer | Junior Engineer | BILL/01255/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
883 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
884 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :Mangalda, Parasibonaa, Guniada, Malpara (Part), Harokbedya (Part) Total House Hold - 209 |  | Junior Engineer | ORD/000070/2020-2021 | 473/BQA | 05/02/2021 | 30 | NAYAN BARDHAN | 15.25 | 2.98 | 0
885 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe from Pinguri Village Hunuman mondir to Khatal Bagan Village for increase pressure of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000145/2022-2023 | 554/BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.94 | 0 | 0
886 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe from Pinguri village football ground to Pinguri Village Hunuman mondir for increase pressure of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000147/2022-2023 | 553/BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.93 | 0 | 0
887 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe from Maliara OHR site to Pinguri village football ground for increase pressure of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000148/2022-2023 | 552/BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.8 | 0 | 0
888 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 65 out of 921. |  | Junior Engineer | ORD/000151/2020-2021 | 59/VSD | 10/02/2021 | 21 | M/S SACHHIDANANDA MAZUMDAR | 4.85 | 7.42 | 0
889 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ), Total House Hold - 65 (Sl No of Work- 10) |  | Junior Engineer | ORD/000152/2020-2021 | 102/ BSD | 12/02/2021 | 20 | TAPAS KUMBHAKAR | 4.42 | 7.75 | 0
890 | Bankura Division | Bankura Sadar Sub-Division | Supply laying & fitting fixing of MS pipe line crossing at Tentulpoha jore & repairing of existing UPVC pipe connection for Tentulpoha village for Maliara (Zone -A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) |  | Junior Engineer | ORD/000303/2022-2023 | 557/BSD | 29/07/2022 | 30 | SAMIRUDDIN KHAN | 2.85 | 0 | 0
891 | Bankura Division | Bankura Sadar Sub-Division | Parallel pipe laying of HDPE pipe from Maliara OHR site to Pinguri village football ground for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000314/2022-2023 | 552/ BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.8 | 0 | 0
892 | Bankura Division | Bankura Sadar Sub-Division | Parallel pipe laying of HDPE pipe from Pinguri village football ground to Pinguri Village Hunuman mondir for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000315/2022-2023 | 553/BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.93 | 0 | 0
893 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 02 nos (Pinguri (Part-C) &Tentuldoha ), Total House Hold -249 |  | Junior Engineer | ORD/000401/2020-2021 | 861/BQA | 25/02/2021 | 30 | BEAUTY CHATTERJEE | 20.31 | 0 | 0
894 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01 no (Pinguri (Part-A ), Total House Hold -420 |  | Junior Engineer | ORD/000402/2020-2021 | 859/BQA | 25/02/2021 | 30 | SUBHANKAR BANERJEE | 34.11 | 0 | 0
895 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- -01 no (Pinguri (Part-B ), Total House Hold -330 |  | Junior Engineer | ORD/000403/2020-2021 | 860/BQA | 25/02/2021 | 30 | AJIT KUMAR PAUL | 26.91 | 0 | 0
896 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 1.63 | 0
897 | Bankura Division | Bankura Sadar Sub-Division | Extra retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) of Maliara (Zone- A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Total House Hold - 13 nos. Mouza- Pinguri & Kuldiha. |  | Junior Engineer | ORD/000827/2022-2023 | 217/BSD | 28/02/2023 | 15 | AJIT KUMAR PAUL | 0.95 | 0 | 0
898 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 |  | Junior Engineer | VCH/001487/2021-2022 | FHTC/03 | 03/11/2021 | 0 | BEAUTY CHATTERJEE | 7.46 | 0 | 0
899 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying by UPVC pipe for distribution network along with ancillary works at village karbhanga due to strengthening widening of Sarenga Chowrasta more to Goaltore Road under Gargaria Zone -B water supply scheme (BRGF phase -I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. sl no - 13 |  | Junior Engineer | VCH/001502/2021-2022 | FHTC/23 | 23/11/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.95 | 0 | 0
900 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
901 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha No.of Mouza :- 01 Bhangahira part Total House Hold - 27 |  | Junior Engineer | VCH/003109/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TAPAN KUMAR UPADHYAY | 2.11 | 0 | 0
902 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 30 | SUMITA UPADHYAY | 13.03 | 0.09 | 0
903 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | ORD/000094/2021-2022 | 2531/BQA | 23/09/2021 | 30 | ZAKIR HOSSAIN MONDAL | 46.02 | 0 | 0
904 | Bankura Division | Bankura Sadar Sub-Division | Household survey of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura- I, II & Barjora Block W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block - Bankura- II, Name of OHR - Maliara, Kotalpukur, Kanchanpur, Dadhimukha, Gadardihi, Talanjuri, Saulia, Joytunga & Joykrishnapur, No. of Mouza :- 141 nos, Total House Hold - 2427 nos. |  | Junior Engineer | ORD/000101/2023-2024 | 324/BSD | 06/04/2023 | 60 | TAPAS DEY | 0.81 | 0 | 100
905 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from S.P.N school to Barjora Maliara Main Road , Barjojora School Danga Prymary School to Dena Bank , Suman Tewary house to Barjora Maliara Main Road & Baltu Babar Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000277/2021-2022 | 885/ BSD | 08/09/2021 | 15 | ZAKIR HOSSAIN MONDAL | 4.98 | 0 | 0
906 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-C) , Total House Hold -175 |  | Junior Engineer | ORD/000404/2020-2021 | 862/BQA | 25/02/2021 | 30 | DAUD ALI KHAN | 15.18 | 0 | 0
907 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 30 | NAYAN BARDHAN | 14.75 | 0 | 0
908 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I Total House Hold -80 nos. (Part-B) |  | Junior Engineer | ORD/000432/2021-2022 | 177/BSD | 18/02/2022 | 10 | PRADIP CHAKRABORTY | 4.15 | 4.15 | 0
909 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I Total House Hold -85 nos.(Part-A) |  | Junior Engineer | ORD/000455/2021-2022 | 176/BSD | 18/02/2022 | 10 | ZAKIR HOSSAIN MONDAL | 4.52 | 0 | 0
910 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 |  | Junior Engineer | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SANJOY MONDAL | 4.55 | 0 | 0
911 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Maliara, Kotulpur, Kanchanpur , Dadhimukha, , No Of Mouzas-68 , Total House Hold - 14124. |  | Junior Engineer | VCH/001614/2020-2021 |  | 15/03/2021 | 0 | TAPAS DEY | 2.23 | 0 | 0
912 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  | Junior Engineer | VCH/002288/2021-2022 | FHTC/31 | 31/01/2022 | 0 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0
913 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | VCH/002289/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.1 | 0 | 0
914 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) |  | Junior Engineer | VCH/002374/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DAUD ALI KHAN | 4.26 | 0 | 0
915 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 01 no., (Pakhanna Pratap pur), Total House Hold - 402 nos |  | Junior Engineer | VCH/002375/2021-2022 | FHTC/19 | 19/02/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 24.08 | 0 | 0
916 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Barjora Forest Office to End of Forest colony of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | VCH/002376/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.77 | 0 | 0
917 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from End of Forest colony to Ramkrishna Mission Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | VCH/002377/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.78 | 0 | 0
918 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line near Ramkrishna Mission Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | VCH/002378/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.77 | 0 | 0
919 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | VCH/002379/2021-2022 | FHTC/19 | 19/02/2022 | 0 | PRADYUMNA KOLEY | 4.71 | 0 | 0
920 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Baharamuri (91) & Jibanpur (92) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2022-2023 | 1682/BQA | 27/07/2022 | 30 | SUBHADIP KOLEY | 9.22 | 8.66 | 0
921 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000084/2021-2022 | 2502/BQA | 23/09/2021 | 30 | MUNMUN UPADHYAY | 48.03 | 0 | 0
922 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000356/2020-2021 | 42/KSD | 15/01/2021 | 59 | TAPAS DEY | 0.28 | 0.25 | 0
923 | Bankura Division | Khatra Sub-Division | Laying Extra HDPE Pipe Line to Cover Chatraraj para,Garaipara,Napitpara & Mandalpara at Mouladanga mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2022-2023 | 626/BSD | 16/08/2022 | 21 | GOURANGA CHATTERJEE | 2.47 | 2.42 | 0
924 | Bankura Division | Khatra Sub-Division | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 30 | SOUMITRA BOSE | 23.15 | 0.2 | 0
925 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Radhanathpur (259) & Saluka (260) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) | Assistant Engineer | Junior Engineer | ORD/000644/2021-2022 | 106/KSD | 10/03/2022 | 10 | TARINI CHARAN UPADHYAY | 2.58 | 2.35 | 0
926 | Bankura Division | Khatra Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Jorehira, No. of Mouza:- 1 no., ( Parasia), Total House Hold -18 nos. (Sl. No. 04) | Assistant Engineer | Junior Engineer | VCH/001203/2022-2023 | FHTC/28 | 28/09/2022 | 0 | TAPAN KUMAR UPADHYAY | 1.39 | 0 | 0
927 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001482/2022-2023 | FHTC/20 | 20/12/2022 | 0 | MUNMUN UPADHYAY | 13.3 | 0 | 0
928 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Bankuradanga , Purusattam pur(PART-A) ,), Total House Hold -170 | Assistant Engineer | Junior Engineer | VCH/002612/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOUTAM GHOSH | 1.26 | 0 | 0
929 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- A), Total House Hold -175 | Assistant Engineer | Junior Engineer | VCH/002614/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOUTAM GHOSH | 1.38 | 0 | 0
930 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Paharbedia, Nangla, Bharatpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B). | Assistant Engineer | Junior Engineer | VCH/002615/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BHATTACHARYYA ENTERPRISE | 4.99 | 0 | 0
931 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Jhunjka mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A). | Assistant Engineer | Junior Engineer | VCH/002617/2021-2022 | FHTC/24 | 24/02/2022 | 0 | APEX ENTERPRISE | 4.99 | 0 | 0
932 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Paharbedia, Nangla, Bharatpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A). | Assistant Engineer | Junior Engineer | VCH/002618/2021-2022 | FHTC/24 | 24/02/2022 | 0 | APEX ENTERPRISE | 4.99 | 0 | 0
933 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC Pipe Line to Cover Ladna & Lapuria part mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kendboni (Zone- p) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002620/2021-2022 | FHTC/24 | 28/02/2022 | 0 | SOUMITRA BHATTACHARYA | 4.73 | 0 | 0
934 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC Pipe Line to Cover Karanjora & Lapuria part mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kendboni (Zone- p) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002621/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SOUMITRA BHATTACHARYA | 4.76 | 0 | 0
935 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 06 nos, (Agaya , Pachasimul, Mechabaid , Banjurya, Haridi, Tentulberia) Total House Hold - 436 | Assistant Engineer | Junior Engineer | VCH/002624/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SWAPAN KUMAR UPADHYAY | 27.06 | 0 | 0
936 | Bankura Division | Khatra Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Palsona more to Ramchandrapur High School under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Palsona & Ramchandrapur | Assistant Engineer | Junior Engineer | VCH/002656/2021-2022 | FHTC/10 | 10/02/2022 | 0 | RUFIKUL MONDAL | 4.8 | 0 | 0
937 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 01 no., (Radhakantapur), Total House Hold - 463 nos | Assistant Engineer | Junior Engineer | VCH/002799/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GANESH ROY | 26.6 | 0 | 0
938 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Bhedua (264) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone- IIA (Baragari) of Khatra - Hirbandh-Ranibandh water supply scheme (BRGF Ph-I) at Block- Khatra Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A Sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002967/2021-2022 |  | 25/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.36 | 0 | 0
939 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Maharadihi (215) & Dharampur (216) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - llA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003045/2021-2022 | FHTC/27 | 27/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.71 | 0 | 0
940 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Baragari (220) & Saluka (260) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - llA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003046/2021-2022 | FHTC/27 | 27/03/2022 | 0 | MUNMUN UPADHYAY | 3.37 | 0 | 0
941 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kasipur (230), Indkucha (231), Dhanara (234) Sabudad (253) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2020-2021 | 486/BQA | 05/02/2021 | 30 | EARTHMOVING (INDIA) | 36.37 | 0 | 0
942 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Nekrasonda (246), Dumuria (254), Dhargram (255) Sial Pahari (256) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2020-2021 | 487/BQA | 05/02/2021 | 30 | EARTHMOVING (INDIA) | 32.81 | 0 | 0
943 | Bankura Division | Khatra Sub-Division | Work Order for Laying UPVC pipeline to increase pressure in Dhargram (255) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 326/KSD | 01/08/2022 | 15 | S. B. CONSTRUCTION | 3.25 | 3.24 | 0
944 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Dungrikole village under Dhargram (255) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000135/2022-2023 | 304/KSD | 26/07/2022 | 10 | EARTH MOVING (INDIA) | 2.73 | 2.73 | 0
945 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1, Tilabaid (PART-B) Total House Hold - 75. (Sl No of Work- 17) | Assistant Engineer | Junior Engineer | ORD/000200/2020-2021 | 109/ BSD | 12/02/2021 | 20 | MRITYUNJOY HAZRA | 4.84 | 8.15 | 0
946 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kasipur (230), Indkucha (231), Dhanara (234), Nekra Sonda (246), Sabudad (253), Dumuria (254), Dhargram (255), Sial Pahari (256) & Dhabani (257) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 24) | Assistant Engineer | Junior Engineer | ORD/000528/2020-2021 | 326/KSD | 29/12/2020 | 61 | EARTH MOVING (INDIA) | 0.37 | 0.18 | 0
947 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Husumdanga More to Dighi village to increase pressure in Dhajamanipur (87) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2022-2023 | 918/BQA | 19/04/2022 | 30 | MAYA CONSTRUCTION | 10.09 | 0 | 0
948 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Baharamuri (91) & Jibanpur (92) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2022-2023 | 1682/BQA | 27/07/2022 | 30 | SUBHADIP KOLEY | 9.22 | 0 | 0
949 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2020-2021 | 474/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 23.18 | 3.53 | 0
950 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhajamanipur (87), Topabari (88), Kaliapathar (89) & Shyampur (90) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2020-2021 | 182/BQA | 18/01/2021 | 30 | SUBHADIP KOLEY | 21.98 | 0 | 60
951 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhajamanipur (87), Topabari (88), Kaliapathar (89) & Shyampur (90) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2020-2021 | 183/BQA | 18/01/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 26.73 | 0 | 0
952 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baharamuri (91) mouza by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2020-2021 | 192/BQA | 18/01/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 30.12 | 0 | 0
953 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000355/2020-2021 | 41/KSD | 15/01/2021 | 59 | TAPAS DEY | 0.38 | 0 | 0
954 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kaliapathar (89) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000675/2021-2022 | 645/KSD | 17/09/2021 | 15 | SUBHADIP KOLEY | 3.3 | 0 | 70
955 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SANJOY MONDAL | 4.55 | 0 | 0
956 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001023/2021-2022 |  | 16/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.95 | 0 | 0
957 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Kaliapathar (89) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001024/2021-2022 |  | 16/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.26 | 0 | 0
958 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001025/2021-2022 |  | 16/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.11 | 0 | 0
959 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140, | Assistant Engineer | Junior Engineer | VCH/001561/2021-2022 | FHTC/11 | 11/10/2021 | 0 | GANGADHAR MONDAL | 8.9 | 0 | 0
960 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., | Assistant Engineer | Junior Engineer | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0
961 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baharamuri (91) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A | Assistant Engineer | Junior Engineer | VCH/002985/2021-2022 | FHTC/24 | 24/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.62 | 0 | 0
962 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baharamuri (91) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002986/2021-2022 | FHTC/24 | 24/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.6 | 0 | 0
963 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87) & Kaliapathar (89) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002987/2021-2022 | FHTC/24 | 24/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.01 | 0 | 0
964 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jibanpur (92) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002988/2021-2022 | FHTC/24 | 24/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.72 | 0 | 0
965 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Manora (52) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2022-2023 | 1686/BQA | 27/07/2022 | 30 | MANAS DEY | 5.84 | 5.82 | 0
966 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuakana (63) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2020-2021 | 160/BQA | 18/01/2021 | 30 | SUBHADIP KOLEY | 10.98 | 0 | 0
967 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuakana (63) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2020-2021 | 159/BQA | 18/01/2021 | 30 | SUBHADIP KOLEY | 10.98 | 0 | 0
968 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhupur (62), Belkanlia (67) & Bauridihi (68) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2020-2021 | 161/BQA | 18/01/2021 | 30 | SUBHADIP KOLEY | 9.26 | 0 | 0
969 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuchu Dungri (61) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2020-2021 | 162/BQA | 18/01/2021 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 7.77 | 0 | 50
970 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sitarampur (59) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000105/2020-2021 | 163/BQA | 18/01/2021 | 30 | PRADIP CHAKRABORTY | 12.32 | 0 | 100
971 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57) & Chaka Doba (58) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2020-2021 | 164/BQA | 18/01/2021 | 30 | PRADIP CHAKRABORTY | 12.74 | 6.64 | 0
972 | Bankura Division | Khatra Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000229/2021-2022 | 716/KSD | 12/11/2021 | 15 | SUBHADIP KOLEY | 4.2 | 0 | 0
973 | Bankura Division | Khatra Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000230/2021-2022 | 717/KSD | 12/11/2021 | 15 | PRADYUMNA KOLEY | 3.47 | 0 | 0
974 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2020-2021 | 1773/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 17.57 | 1.25 | 20
975 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.43 | 0
976 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (68) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000509/2020-2021 | 307/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.25 | 0 | 0
977 | Bankura Division | Khatra Sub-Division | Household survey in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (68) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) | Assistant Engineer | Junior Engineer | VCH/001036/2021-2022 |  | 16/09/2021 | 0 | TAPAS DEY | 0.23 | 0 | 0
978 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuakana (63) mouzas by retrofitting zone - A (Bhuakana) of Khatra-Hirbandh-Ranibandh w/s scheme ( BRGF PH - I) at block - Hirbandh under Jal Jeeval Mission (JJM) and Jal Swapna & Jal Jeevan Mission programme under Khatra sub - Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001380/2020-2021 |  | 01/03/2021 | 0 | SUBHADIP KOLEY | 9.95 | 0 | 0
979 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhupur (62), Belkanlia (87) mouzas by retrofitting zone - A (Bhuakana) of Khatra-Hirbandh-Ranibandh w/s scheme ( BRGF PH - I) at block - Hirbandh under Jal Jeeval Mission (JJM) and Jal Swapna & Jal Jeevan Mission programme under Khatra sub - Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001381/2020-2021 |  | 01/03/2021 | 0 | SUBHADIP KOLEY | 8.52 | 0 | 0
980 | Bankura Division | Khatra Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
981 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002297/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SUBHANKAR BANERJEE | 7.61 | 0 | 0
982 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- Bhabanipur, Upargara ( Part ) Total House Hold- 128 | Assistant Engineer | Junior Engineer | VCH/002487/2021-2022 | FHTC/1 | 01/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 3.33 | 0 | 0
983 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Tapta (52) , Banshkhopa ( 53) Beoncha (115) Beliakala ( 116) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belatikri zone - B under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003047/2021-2022 | FHTC/26 | 26/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 3.8 | 0 | 0
984 | Bankura Division | Brishnupur Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. | Assistant Engineer | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 40.2 | 14.14 | 0
985 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 02 nos (Pinguri (Part-C) &Tentuldoha ), Total House Hold -249 | Assistant Engineer | Junior Engineer | ORD/000401/2020-2021 | 861/BQA | 25/02/2021 | 30 | BEAUTY CHATTERJEE | 20.31 | 36.91 | 0
986 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-D) , Total House Hold -173 | Assistant Engineer | Junior Engineer | ORD/000411/2020-2021 | 866/BQA | 25/02/2021 | 30 | GOUTAM GHOSH | 15.02 | 27.37 | 0
987 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} of Kotalpukur (Zone- B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001181/2021-2022 | FHTC/29 | 29/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 63.55 | 0 | 0
988 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) Mouza - Chakupasole 160 | Assistant Engineer | Junior Engineer | VCH/001473/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.16 | 0 | 0
989 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) Mouza -Asthasole 161 | Assistant Engineer | Junior Engineer | VCH/001474/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.84 | 0 | 0
990 | Bankura Division | Brishnupur Sub-Division | Supplying laying by UPVC pipe for distribution network along with ancillary works at village karbhanga due to strengthening widening of Sarenga Chowrasta more to Goaltore Road under Gargaria Zone -B water supply scheme (BRGF phase -I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. sl no - 13 | Assistant Engineer | Junior Engineer | VCH/001502/2021-2022 | FHTC/23 | 23/11/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.95 | 0 | 0
991 | Bankura Division | Brishnupur Sub-Division | Laying extra HDPE pipeline to cover Haludkanali (113) mouza for construction and commissioning of FHTC ( functional house hold tap connection) by retrofitting zone - P ( Nachna) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF PH - I) at block-Ranibandh dist - Bankura under jal jeevan mission programme under Khatra sub - Division PHE Dte. part A sl no - 08 | Assistant Engineer | Junior Engineer | VCH/001724/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PRADYUMNA KOLEY | 4.8 | 0 | 0
992 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurulpahari (238) AND Baurisol (240) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2020-2021 | 484/BQA | 05/02/2021 | 30 | EARTHMOVING (INDIA) | 36.45 | 0 | 0
993 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sindurpeti (239), Tiring (244), Parashi Danga (247), Khayerbani (248) Bagakhulia (249) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2020-2021 | 485/BQA | 05/02/2021 | 30 | EARTHMOVING (INDIA) | 38.55 | 0 | 0
994 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Bena (236) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000119/2022-2023 | 321/KSD | 01/08/2022 | 15 | S. B. CONSTRUCTION | 4.89 | 4.89 | 0
995 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Chaka (237) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000121/2022-2023 | 324/KSD | 01/08/2022 | 15 | EARTH MOVING (INDIA) | 3.99 | 3.99 | 0
996 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 23) | Assistant Engineer | Junior Engineer | ORD/000527/2020-2021 | 325/KSD | 29/12/2020 | 61 | EARTH MOVING (INDIA) | 0.37 | 0.28 | 0
997 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Mulbandh More to Aamdihi SSK to increase pressure in Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000658/2022-2023 | 511/BQA | 13/03/2023 | 45 | M/S SUPRIYA CHATTERJEE | 24.96 | 24.76 | 100
998 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Aamdihi SSK to Sindurpeti More to increase pressure in Sindurpeti (239) & Tiring (244) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 512/BQA | 13/03/2023 | 45 | GOURANGA CHATTERJEE | 33.16 | 25.84 | 100
999 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001732/2021-2022 | FHTC/23 | 23/11/2021 | 0 | M/S BIPUL BANERJEE | 24.12 | 0 | 0
1000 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 | Assistant Engineer | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
1001 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 289 |  | Junior Engineer | ORD/000012/2020-2021 | 613/BQA | 10/02/2021 | 30 | OSMAN SEKH | 18.09 | 14.12 | 0
1002 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 02 no., Majit ( Part), Singhir (Part), Total House Hold - 20 nos. |  | Junior Engineer | ORD/000042/2022-2023 | 462/BSD | 06/06/2022 | 10 | MD. AFSAR ALI | 1.66 | 1.62 | 0
1003 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000123/2020-2021 | 180/BQA | 18/01/2021 | 30 | PRADIP CHAKRABORTY | 10.08 | 0.3 | 0
1004 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-A), Total House Hold -343 |  | Junior Engineer | ORD/000223/2020-2021 | 2036/BQA | 29/12/2020 | 30 | SARKAR CONSTRUCTION | 30.62 | 0 | 0
1005 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-B),, Total House Hold -119 |  | Junior Engineer | ORD/000224/2020-2021 | 2037/BQA | 29/12/2020 | 30 | SANDHYA DEY | 10.58 | 0 | 0
1006 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-C) & PabayaTotal House Hold -119 |  | Junior Engineer | ORD/000225/2020-2021 | 2038/BQA | 29/12/2020 | 30 | ASHOKE KUMAR DEY | 10.65 | 0 | 0
1007 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Manjumara (Part-A), Total House Hold -125 |  | Junior Engineer | ORD/000226/2020-2021 | 2039/BQA | 29/12/2020 | 30 | TAPAN KUMAR SARKAR | 11.27 | 0 | 0
1008 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Manjumara (Part-B), Total House Hold -130 |  | Junior Engineer | ORD/000227/2020-2021 | 2040/BQA | 29/12/2020 | 30 | SUBHADIP KOLEY | 11.61 | 0 | 0
1009 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 02 Manjumara (Part-C),Monoharbati, Total House Hold -116 |  | Junior Engineer | ORD/000229/2020-2021 | 2041/BQA | 29/12/2020 | 30 | ASHOKE KUMAR DEY | 10.32 | 0 | 0
1010 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 2.76 | 0
1011 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Khejurbedia (7 anapara) to Khejurbedia village to increase pressure for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000528/2022-2023 | 627/BSD | 16/08/2022 | 21 | SONIA ENTERPRISE | 4.76 | 4.76 | 0
1012 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
1013 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhupur (62), Belkanlia (67) & Bauridihi (68) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002803/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHADIP KOLEY | 0.74 | 0 | 0
1014 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 | Assistant Engineer | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 0.11 | 0
1015 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000043/2020-2021 | 11/KSD | 14/01/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.01 | 0.26 | 25
1016 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Kankri Jharna More to Barikul Primary School to increase pressure in Barikul (179) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000061/2022-2023 | 1685/BQA | 27/07/2022 | 30 | APEX ENTERPRISE | 7.7 | 0.16 | 0
1017 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 5.07 | 0
1018 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) | Assistant Engineer | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 25.88 | 0
1019 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34), mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001453/2021-2022 |  | 08/10/2021 | 0 | ASOKE KUMAR SAHU | 2.98 | 0 | 0
1020 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001454/2021-2022 |  | 08/10/2021 | 0 | ASOKE KUMAR SAHU | 2.98 | 0 | 0
1021 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001455/2021-2022 |  | 08/10/2021 | 0 | ASOKE KUMAR SAHU | 3.64 | 0 | 0
1022 | Bankura Division | Khatra Sub-Division | Supply laying & fitting fixing of MS pipe line crossing at Tentulpoha jore & repairing of existing UPVC pipe connection for Tentulpoha village for Maliara (Zone -A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) | Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 557/BSD | 29/07/2022 | 30 | SAMIRUDDIN KHAN | 2.85 | 0.6 | 0
1023 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Mahaldanga (34) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000333/2021-2022 | 671/KSD | 29/09/2021 | 15 | ASOKE KUMAR SAHU | 4.98 | 0 | 0
1024 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000360/2020-2021 | 12/KSD | 14/01/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 3.93 | 0.32 | 25
1025 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000361/2020-2021 | 13/KSD | 14/01/2021 | 15 | UNITED TRADERS | 4.52 | 0.16 | 0
1026 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000362/2020-2021 | 14/KSD | 14/01/2021 | 15 | UNITED TRADERS | 4.39 | 0.13 | 0
1027 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001456/2021-2022 |  | 08/10/2021 | 0 | ASOKE KUMAR SAHU | 3.35 | 0 | 0
1028 | Bankura Division | Khatra Sub-Division | House hold survey different mouzas of Naria Zone -E OF Khatra-Hirbandh-Ranibandh w/s scheme at Hirbandh Block | Assistant Engineer | Junior Engineer | VCH/001736/2020-2021 |  | 19/03/2021 | 0 | TAPAS DEY | 0.39 | 0 | 0
1029 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000363/2020-2021 | 15/KSD | 14/01/2021 | 15 | UNITED TRADERS | 4.29 | 0.04 | 0
1030 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000364/2020-2021 | 16/KSD | 14/01/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.56 | 0.16 | 100
1031 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000365/2020-2021 | 17/KSD | 14/01/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.38 | 0.19 | 100
1032 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000366/2020-2021 | 18/KSD | 14/01/2021 | 15 | BEAUTY CHATTERJEE | 4.5 | 0.13 | 0
1033 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000367/2020-2021 | 19/KSD | 14/01/2021 | 15 | BEAUTY CHATTERJEE | 4.37 | 0.14 | 0
1034 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000368/2020-2021 | 20/KSD | 14/01/2021 | 15 | GOURANGA CHATTERJEE | 4.37 | 0.13 | 0
1035 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000369/2020-2021 | 21/KSD | 14/01/2021 | 15 | GOURANGA CHATTERJEE | 3.87 | 0.1 | 0
1036 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000370/2020-2021 | 22/KSD | 14/01/2021 | 15 | BIKASH MANDAL | 4.97 | 0.08 | 0
1037 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000371/2020-2021 | 23/KSD | 14/01/2021 | 15 | TAPAN KUMAR MANDAL | 4.99 | 0.49 | 0
1038 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000372/2020-2021 | 24/KSD | 14/01/2021 | 15 | SUNIL KUMAR MANDAL | 4.97 | 0.4 | 0
1039 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000373/2020-2021 | 25/KSD | 14/01/2021 | 15 | ASOKE KUMAR SAHU | 4.26 | 0 | 0
1040 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 16) | Assistant Engineer | Junior Engineer | ORD/000374/2020-2021 | 26/KSD | 14/01/2021 | 15 | ASOKE KUMAR SAHU | 4.12 | 0 | 0
1041 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 17) | Assistant Engineer | Junior Engineer | ORD/000376/2020-2021 | 27/KSD | 14/01/2021 | 15 | ASOKE KUMAR SAHU | 4.08 | 0 | 0
1042 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simul Kundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) | Assistant Engineer | Junior Engineer | ORD/000377/2020-2021 | 28/KSD | 14/01/2021 | 15 | SRIKANTA MONDAL | 4.99 | 0.12 | 0
1043 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) | Assistant Engineer | Junior Engineer | ORD/000388/2021-2022 | 771/KSD | 25/11/2021 | 15 | UNITED TRADERS | 2.5 | 0 | 0
1044 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000396/2021-2022 | 746/KSD | 18/11/2021 | 7 | SRIKANTA MONDAL | 1.99 | 0 | 0
1045 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 4.02 | 0
1046 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Shyamnagar (22) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000460/2020-2021 | 119/KSD | 11/02/2021 | 10 | BIKASH MANDAL | 2.7 | 0 | 0
1047 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000464/2021-2022 | 184/BSD | 18/02/2022 | 10 | GOURANGA CHATTERJEE | 3.5 | 3.47 | 0
1048 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000465/2021-2022 | 185/BSD | 18/02/2022 | 10 | M/S BANERJEE & BANERJEE | 3.48 | 3.48 | 0
1049 | Bankura Division | Khatra Sub-Division | Laying balance HDPE Pipe Line with in Pachirdang Village to increase pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000512/2022-2023 | 59/BSD | 24/01/2023 | 21 | M/S BANERJEE & BANERJEE | 0.96 | 0.8 | 0
1050 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000520/2020-2021 | 318/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.4 | 0 | 0
1051 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Shyamnagar (22) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000534/2021-2022 | 96/KSD | 10/03/2022 | 10 | SUNIL KUMAR MANDAL | 4.73 | 4.7 | 0
1052 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahamadanga (33) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/001048/2021-2022 | 743/KSD | 18/11/2021 | 7 | UNITED TRADERS | 1.27 | 0 | 0
1053 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover shyamnagar (22) mouza for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ retrofitting Zone - E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000333/2021-2022 |  | 11/05/2021 | 0 | BIKASH MANDAL | 2.53 | 0 | 0
1054 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Brahma Danga (33), mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000657/2022-2023 | FHTC/21 | 21/07/2022 | 0 | UNITED TRADERS | 1.27 | 0 | 0
1055 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Naria (29), Benagaria (30) & Hirakhon (31) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000669/2021-2022 |  | 16/07/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.24 | 0 | 0
1056 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000670/2021-2022 |  | 16/07/2021 | 0 | UNITED TRADERS | 3.36 | 0 | 0
1057 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in simulkundi (77) mouzas by retrofitting zone - E (Naria) of Khatra-Hirbandh-Ranibandh w/s scheme ( BRGF PH - I) at block - Hirbandh under Jal Jeeval Mission (JJM) and Jal Swapna & Jal Jeevan Mission programme under Khatra sub - Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001379/2020-2021 |  | 01/03/2021 | 0 | SRIKANTA MONDAL | 4.87 | 0 | 0
1058 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Buriam (112) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/001387/2021-2022 | FHTC/24 | 24/09/2021 | 0 | SUBHADIP KOLEY | 2.47 | 0 | 0
1059 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chanpasol (78) mouzas by Rectrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF Ph-I) at Block- Hirrbandh , Dist Bankura under Jal Swapna & Jal Jeevan misssion programme under Khatra Sub-Division of Bankura Division PHE Dte. (Part-D) Sl No-11 | Assistant Engineer | Junior Engineer | VCH/001579/2020-2021 |  | 15/03/2021 | 0 | GOURANGA CHATTERJEE | 3.61 | 0 | 0
1060 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chanpasol (78) mouzas by Rectrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF Ph-I) at Block- Hirrbandh , Dist Bankura under Jal Swapna & Jal Jeevan mission program me under Khatra Sub-Division of Bankura Division PHE Dte. (Part-C) Sl No-10 | Assistant Engineer | Junior Engineer | VCH/001580/2020-2021 |  | 15/03/2021 | 0 | GOURANGA CHATTERJEE | 4.03 | 0 | 0
1061 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl.No-8) | Assistant Engineer | Junior Engineer | VCH/001582/2020-2021 |  | 15/03/2021 | 0 | BEAUTY CHATTERJEE | 4.14 | 0 | 0
1062 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl.No-9) | Assistant Engineer | Junior Engineer | VCH/001583/2020-2021 |  | 15/03/2021 | 0 | BEAUTY CHATTERJEE | 4.16 | 0 | 0
1063 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 01 no, (Hatjore) Total House Hold - 149 | Assistant Engineer | Junior Engineer | VCH/002285/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOUTAM GHOSH | 10.74 | 0 | 0
1064 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Birbhandh (183) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) | Assistant Engineer | Junior Engineer | VCH/002436/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 3.56 | 0 | 0
1065 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Bhedua Purosatyampur, Narrah mouzas for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002879/2021-2022 |  | 16/03/2022 | 0 | SELCO | 3.61 | 0 | 0
1066 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. | Assistant Engineer | Junior Engineer | VCH/002880/2021-2022 |  | 16/03/2022 | 0 | DAUD ALI KHAN | 4.42 | 0 | 0
1067 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | VCH/002930/2021-2022 | FHTC/21 | 21/03/2022 | 0 | SRIKANTA MONDAL | 1.97 | 0 | 0
1068 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, sibrampur Total House Hold - 151 |  | Junior Engineer | ORD/000003/2021-2022 | 1409/BQA | 07/06/2021 | 30 | PRADIP CHAKRABORTY | 11.54 | 0 | 0
1069 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE- (I & II) W/S Scheme under Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 1 no., Bhangucha ( Part), Total House Hold- 47 nos. |  | Junior Engineer | ORD/000117/2022-2023 | 459/BSD | 06/06/2022 | 10 | PARESH CHANDRA LAYEK | 2.08 | 2.08 | 0
1070 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 25.11 | 0
1071 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 02 churamonipur & bambhanpur Total House Hold - 124 ( Sl .No.-23) |  | Junior Engineer | ORD/000179/2020-2021 | 721/BQA | 19/02/2021 | 30 | PRADIP CHAKRABORTY | 11.69 | 0 | 100
1072 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 Nabada Total House Hold -388 ( Sl .No.- 24) |  | Junior Engineer | ORD/000181/2020-2021 | 722/BQA | 19/02/2021 | 30 | ASHISH KUMAR SAMANTA | 46.34 | 0 | 100
1073 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" |  | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 1.23 | 0
1074 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Pradip mukherjee house to main road at mouladanga mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000401/2022-2023 | 625/BSD | 16/08/2022 | 21 | GOURANGA CHATTERJEE | 3.55 | 3.54 | 0
1075 | Bankura Division | Bankura Sadar Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub-Division, PHE Dte. Block - Barjora, OHR - Maliara, Kotalpukur, Kanchanpur, Dadhimukha |  | Junior Engineer | VCH/001330/2021-2022 | FHTC/23 | 23/11/2021 | 0 | TAPAS DEY | 1.82 | 0 | 0
1076 | Bankura Division | Bankura Sadar Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura sadar sub-division of Bankura division PHE Dte. block - Barjora , name of OHR - Godardihi, talanjuri , saulia, joytunga, joykrishnapur, no. of mouza - 73 total house hold - 11815 Sl no - - 02 |  | Junior Engineer | VCH/001332/2021-2022 | FHTC/23 | 23/11/2021 | 0 | TAPAS DEY | 1.16 | 0 | 0
1077 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Buriam (112) & Haludkanali (113) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 02 Nos. Total Household - 420 Nos. |  | Junior Engineer | VCH/001519/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SUBHADIP KOLEY | 27.61 | 0 | 0
1078 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban No. of Mouza :- 01 nos Asurabad (Part), Total House Hold- 140 |  | Junior Engineer | VCH/001862/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PARESH CHANDRA LAYEK | 9.4 | 0 | 0
1079 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
1080 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
1081 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 02 churamonipur & bambhanpur Total House Hold - 124 ( Sl .No.-23) |  | Junior Engineer | VCH/003108/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PRADIP CHAKRABORTY | 1.05 | 0 | 0
1082 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. | Assistant Engineer | Junior Engineer | ORD/000193/2020-2021 | 210/BQA | 19/01/2021 | 30 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0
1083 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- Kamalpur (part), Total House Hold :-90 nos. | Assistant Engineer | Junior Engineer | ORD/000227/2022-2023 | 248/KSD | 12/07/2022 | 15 | M/S TARUN KUMAR PATRA | 3.87 | 0 | 0
1084 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 06 nos, (Agaya , Pachasimul, Mechabaid , Banjurya, Haridi, Tentulberia) Total House Hold - 436 | Assistant Engineer | Junior Engineer | VCH/002624/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SWAPAN KUMAR UPADHYAY | 27.06 | 0 | 0
1085 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002627/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAS GHOSH | 12.24 | 0 | 0
1086 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamberia (179) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household - 160 Nos. | Assistant Engineer | Junior Engineer | VCH/002629/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAS GHOSH | 10.78 | 0 | 0
1087 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Kamalpur Mantumura for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chinabari zone - H under Bankura sadar sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002949/2021-2022 | FHTC/23 | 23/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.8 | 0 | 0
1088 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Kamalpur Mantumura for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chinabari zone - H under saltora - chhatna water supply scheme ( BRGF PH - I) Bankura sadar sub - Division of Bankura Division, PHE Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002950/2021-2022 | FHTC/23 | 23/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.78 | 0 | 0
1089 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. | Assistant Engineer | Junior Engineer | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0
1090 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000293/2020-2021 | 1416/BQA | 09/10/2020 | 30 | EARTHMOVING (INDIA) | 37.66 | 0 | 20
1091 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277) & Gopalpur (301) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2020-2021 | 1778/BQA | 09/12/2020 | 1574 | SIB SANKAR CHOWDHURY | 33.24 | 0 | 90
1092 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Raghunathpur (303) & Salbani (342) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2020-2021 | 1779/BQA | 09/12/2020 | 1696 | SIB SANKAR CHOWDHURY | 20.21 | 0 | 90
1093 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) & Salbani (342) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 34) | Assistant Engineer | Junior Engineer | ORD/000537/2020-2021 | 276/KSD | 10/12/2020 | 62 | SIB SANKAR CHOWDHURY | 0.27 | 0 | 90
1094 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277) & Gopalpur (301) mouzas under Dhanara G.P. for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001096/2021-2022 | 459\KSD | 11/05/2021 | 10 | SIBSANKAR CHOWDHURY | 4.34 | 0 | 0
1095 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2020-2021 | 474/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 23.18 | 39.07 | 0
1096 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Penchakola (298) & Dubli (299) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2020-2021 | 1417/BQA | 09/10/2020 | 30 | SIB SANKAR CHOWDHURY | 41.33 | 0 | 90
1097 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000295/2020-2021 | 1418/BQA | 09/10/2020 | 30 | SIB SANKAR CHOWDHURY | 39.24 | 0 | 90
1098 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Penchakola (298) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000447/2020-2021 | 112/KSD | 11/02/2021 | 10 | SIB SANKAR CHOWDHURY | 4.93 | 0 | 90
1099 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dubli (299) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000449/2020-2021 | 113/KSD | 11/02/2021 | 10 | SIB SANKAR CHOWDHURY | 4.24 | 0 | 0
1100 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Penchakola (298) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-05) | Assistant Engineer | Junior Engineer | VCH/001809/2020-2021 |  | 25/03/2021 | 0 | SIB SANKAR CHOWDHURY | 3.9 | 0 | 0
1101 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Dubli(299) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-06) | Assistant Engineer | Junior Engineer | VCH/001810/2020-2021 |  | 25/03/2021 | 0 | SIB SANKAR CHOWDHURY | 4.03 | 0 | 0
1102 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Kharsasuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurbada (360) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000450/2020-2021 | 114/KSD | 11/02/2021 | 10 | SIB SANKAR CHOWDHURY | 4.97 | 0 | 90
1103 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Penchakola (298), Dubli (299), Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 33) | Assistant Engineer | Junior Engineer | ORD/000536/2020-2021 | 275/KSD | 10/12/2020 | 62 | SIB SANKAR CHOWDHURY | 0.4 | 0 | 90
1104 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3907) | Assistant Engineer | Junior Engineer | VCH/001536/2020-2021 | FHTC/280 | 12/02/2021 | 0 | SIB SANKAR CHOWDHURY | 25.76 | 0 | 0
1105 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Kharkasuli (300) , Marosol(302) , Katalda(343) , Beherbani (344) , Thakurbada (360) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting JJM Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-07) | Assistant Engineer | Junior Engineer | VCH/001811/2020-2021 |  | 25/03/2021 | 0 | SIB SANKAR CHOWDHURY | 4.28 | 0 | 0
1106 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 05 Nos. Total Household - 853 Nos. " | Assistant Engineer | Junior Engineer | ORD/000039/2021-2022 | 1786/BQA | 09/07/2021 | 30 | PARTHA PRATIM CHATAIT | 56.47 | 11.12 | 0
1107 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 30 | SUMITA UPADHYAY | 13.03 | 10.04 | 0
1108 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pitadungri (275) Kuchiarmahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000083/2020-2021 | 488/BQA | 05/02/2021 | 30 | SWAPAN KUMAR UPADHYAY | 52.62 | 5.24 | 0
1109 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pita Dungri (275) & Kuchiar Mahar (276) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 27) | Assistant Engineer | Junior Engineer | ORD/000530/2020-2021 | 328/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.26 | 0.26 | 0
1110 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
1111 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Bhedua (264 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - llA (Baragari) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, sl no - 02 | Assistant Engineer | Junior Engineer | VCH/003070/2021-2022 | FHTC/29 | 29/03/2022 | 0 | SWAPAN KUMAR UPADHYAY | 2.91 | 0 | 0
1112 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pitadungri (275) Kuchiarmahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003102/2021-2022 | FHTC/30 | 30/03/2022 | 0 | SWAPAN KUMAR UPADHYAY | 47.33 | 0 | 0
1113 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kotalsol (108), Chiltore (109) & Jhola (110) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2020-2021 | 1413/BQA | 09/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 36.79 | 2.5 | 0
1114 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 30 | SUMITA UPADHYAY | 13.03 | 0.97 | 0
1115 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000291/2020-2021 | 1414/BQA | 09/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 34.86 | 0.69 | 0
1116 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 30) |  | Junior Engineer | ORD/000533/2020-2021 | 272/KSD | 10/12/2020 | 62 | SUBHADIP KOLEY | 0.3 | 0 | 0
1117 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) , Dharmapur (133) Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura Under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/001096/2021-2022 |  | 21/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.98 | 0 | 0
1118 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
1119 | Bankura Division | Khatra Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3944) |  | Junior Engineer | VCH/001529/2020-2021 | FHTC/260 | 04/02/2021 | 0 | M/S TARUN KUMAR PATRA | 22.67 | 0 | 0
1120 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001545/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRADYUMNA KOLEY | 2.81 | 0 | 0
1121 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10), |  | Junior Engineer | VCH/001546/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRADYUMNA KOLEY | 3.1 | 0 | 0
1122 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3955) |  | Junior Engineer | VCH/001552/2020-2021 | FHTC/283 | 22/02/2021 | 0 | SUMITA UPADHYAY | 20.58 | 0 | 0
1123 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000136/2020-2021 | 193/BQA | 18/01/2021 | 30 | PARAMESWAR CHOWDHURY | 43.02 | 78.7 | 0
1124 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 06 ( Kustora, Nekragori , Gangtara, Bhalukbasa, Hrtyasol & Patharkata ). Total House Hold - 819 |  | Junior Engineer | ORD/000194/2020-2021 | 209/BQA | 19/01/2021 | 30 | SABIR ALI KHAN | 71.28 | 0 | 95
1125 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 1.56 | 0
1126 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Beladi More to Hetyasole Village to increse pressure in Hetyasole mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000533/2021-2022 | 152/BSD | 16/02/2022 | 10 | SANDIP PATI | 1.95 | 1.95 | 0
1127 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Debedia Atchala to Salghata village to increase pressure in Debedia (86) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2022-2023 | 1687/BQA | 27/07/2022 | 30 | SUBHENDU SEKHAR GORAI | 8.34 | 0 | 0
1128 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :Mangalda, Parasibonaa, Guniada, Malpara (Part), Harokbedya (Part) Total House Hold - 209 | Assistant Engineer | Junior Engineer | ORD/000070/2020-2021 | 473/BQA | 05/02/2021 | 30 | NAYAN BARDHAN | 15.25 | 15.43 | 0
1129 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000169/2020-2021 | 88/KSD | 09/02/2021 | 15 | SUBHADIP KOLEY | 4.86 | 0.22 | 0
1130 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000171/2020-2021 | 89/KSD | 09/02/2021 | 15 | SUBHADIP KOLEY | 4.82 | 0.21 | 0
1131 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000173/2020-2021 | 90/KSD | 09/02/2021 | 15 | SUBHADIP KOLEY | 4.82 | 0.21 | 0
1132 | Bankura Division | Khatra Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) with Jal Jeevan Mission (JJM) | Assistant Engineer | Junior Engineer | VCH/001737/2020-2021 |  | 19/03/2021 | 0 | TAPAS DEY | 0.35 | 0 | 0
1133 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000177/2020-2021 | 91/KSD | 09/02/2021 | 15 | PRADYUMNA KOLEY | 4.69 | 0 | 0
1134 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) | Assistant Engineer | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 19.77 | 0
1135 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-E) (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000180/2020-2021 | 92/KSD | 09/02/2021 | 15 | PRADYUMNA KOLEY | 4.68 | 0.23 | 0
1136 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000183/2020-2021 | 93/KSD | 09/02/2021 | 15 | GOURANGA CHATTERJEE | 4.13 | 0 | 0
1137 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000184/2020-2021 | 94/KSD | 09/02/2021 | 15 | GOURANGA CHATTERJEE | 4 | 0 | 0
1138 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000215/2020-2021 | 95/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 4 | 0 | 0
1139 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhogra (84) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000218/2020-2021 | 96/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 3.94 | 0 | 0
1140 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhogra (84) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000220/2020-2021 | 97/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 3.81 | 0 | 0
1141 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhogra (84) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000222/2020-2021 | 98/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 3.73 | 0 | 0
1142 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Husumdanga (83) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000237/2020-2021 | 99/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 2.74 | 0 | 0
1143 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Husumdanga (83) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000255/2020-2021 | 100/KSD | 09/02/2021 | 15 | BEAUTY CHATTERJEE | 2.61 | 0 | 50
1144 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 16) | Assistant Engineer | Junior Engineer | ORD/000256/2020-2021 | 103/KSD | 09/02/2021 | 15 | GOURANGA CHATTERJEE | 4.19 | 0 | 0
1145 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 17) | Assistant Engineer | Junior Engineer | ORD/000257/2020-2021 | 104/KSD | 09/02/2021 | 15 | AJIT KUMAR PAUL | 4.15 | 0 | 0
1146 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 18) | Assistant Engineer | Junior Engineer | ORD/000258/2020-2021 | 105/KSD | 09/02/2021 | 15 | GOURANGA CHATTERJEE | 4.02 | 0 | 0
1147 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 19) | Assistant Engineer | Junior Engineer | ORD/000259/2020-2021 | 106/KSD | 09/02/2021 | 15 | AJIT KUMAR PAUL | 4.01 | 0 | 0
1148 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 747/KSD | 18/11/2021 | 15 | BEAUTY CHATTERJEE | 4.1 | 0 | 0
1149 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000353/2020-2021 | 101/KSD | 09/02/2021 | 15 | KOUSIK MONDAL | 4.56 | 0 | 0
1150 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000354/2020-2021 | 102/KSD | 09/02/2021 | 15 | KOUSIK MONDAL | 4.42 | 0 | 0
1151 | Bankura Division | Khatra Sub-Division | Replacing of damaged MS carrier pipe line of rising main of Joytunga (Zone- H) OHR at Rail way track crossing Chandar village (Bankura to sonamukhi Rail way line) along with allied works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 533/BSD | 28/07/2022 | 21 | ZAKIR HOSSAIN MONDAL | 3.08 | 2.99 | 0
1152 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000363/2021-2022 | 748/KSD | 18/11/2021 | 7 | KOUSIK MONDAL | 2.66 | 0 | 0
1153 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000370/2021-2022 | 744/KSD | 18/11/2021 | 7 | GOURANGA CHATTERJEE | 3.42 | 0 | 0
1154 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000470/2021-2022 | 814/KSD | 15/12/2021 | 15 | SUBHADIP KOLEY | 2.36 | 0 | 0
1155 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 07) | Assistant Engineer | Junior Engineer | ORD/000471/2021-2022 | 815/KSD | 15/12/2021 | 15 | PRADYUMNA KOLEY | 2.33 | 0 | 0
1156 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000472/2021-2022 | 766/KSD | 25/11/2021 | 7 | SUBHADIP KOLEY | 1.4 | 1.34 | 0
1157 | Bankura Division | Khatra Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 0.1 | 0
1158 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000521/2020-2021 | 319/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.38 | 0 | 0
1159 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) | Assistant Engineer | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.46 | 0.74 | 0
1160 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Bhelaidiha (81) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001026/2021-2022 |  | 16/09/2021 | 0 | BEAUTY CHATTERJEE | 4.49 | 0 | 0
1161 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Tentulia (27) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001027/2021-2022 |  | 16/09/2021 | 0 | GOURANGA CHATTERJEE | 2.17 | 0 | 0
1162 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Husumdanga (83) & Bhogra (84) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001028/2021-2022 |  | 16/09/2021 | 0 | BEAUTY CHATTERJEE | 3.23 | 0 | 0
1163 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
1164 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Tentulara-20 (53 out of 106), House Hold - 53 (Sl. No. 02) | Assistant Engineer | Junior Engineer | VCH/002317/2021-2022 | FHTC/20 | 20/01/2022 | 0 | MANORANJAN GHOSH | 4.14 | 0 | 0
1165 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Belut, Total House Hold - 65 nos. | Assistant Engineer | Junior Engineer | VCH/002811/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU SEKHAR GORAI | 3.65 | 0 | 0
1166 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhogra (84) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003041/2021-2022 | FHTC/27 | 27/03/2022 | 0 | BEAUTY CHATTERJEE | 1.33 | 0 | 0
1167 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas, (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IA). No.of Mouza :-06 (Tikargram , Kishoripur, Patharajuri , Gokulmathura, Joysinghapur, Paharpur ,) Total House Hold - 2158 | Assistant Engineer | Junior Engineer | ORD/000259/2021-2022 | 3168/BQA | 17/12/2021 | 60 | GOPAL CHANDRA CHOUDHURY | 127.31 | 41.08 | 0
1168 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas ((Tikargram , Kishoripur, Patharajuri , Gokulmathura, Joysinghapur, Paharpur ) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IA), No. of Mouza :-06 nos, (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur), Total House Hold - 2158 nos. | Assistant Engineer | Junior Engineer | VCH/000249/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.34 | 0 | 0
1169 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Manjumara (Part-B), Total House Hold -130 | Assistant Engineer | Junior Engineer | VCH/002734/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SUBHADIP KOLEY | 0.88 | 0 | 0
1170 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-C) , Total House Hold -118 ( Sl .No.- 03 ) | Assistant Engineer | Junior Engineer | VCH/002736/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SUBHADIP KOLEY | 0.82 | 0 | 0
1171 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-D) , Total House Hold -118 ( Sl .No.- 04 ) | Assistant Engineer | Junior Engineer | VCH/002737/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SANDHYA DEY | 1.12 | 0 | 0
1172 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe to cover Saburbandh mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 08 | Assistant Engineer | Junior Engineer | VCH/002819/2021-2022 | FHTC/9 | 09/03/2022 | 0 | RUFIKUL MONDAL | 4.98 | 0 | 0
1173 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 02 Manjumara (Part-C),Monoharbati, Total House Hold -116 | Assistant Engineer | Junior Engineer | VCH/002738/2021-2022 | FHTC/4 | 04/03/2022 | 0 | ASHOKE KUMAR DEY | 0.95 | 0 | 0
1174 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Dhwajmonipur (PART-A) , Total House Hold -123 ( Sl .No.- 05) | Assistant Engineer | Junior Engineer | VCH/002739/2021-2022 | FHTC/4 | 04/03/2022 | 0 | ASHOKE KUMAR DEY | 1.41 | 0 | 0
1175 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Dakaisini, Bansol, Dhwajmonipur (PART-B)), Total House Hold -120 ( Sl .No.- 6 ) | Assistant Engineer | Junior Engineer | VCH/002740/2021-2022 | FHTC/4 | 04/03/2022 | 0 | ASHOKE KUMAR DEY | 1.6 | 0 | 0
1176 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe line to cover Hatjor mouza for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILNA (Zone- E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002741/2021-2022 | FHTC/4 | 04/03/2022 | 0 | GOUTAM GHOSH | 2.18 | 0 | 0
1177 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03, Gouripur,Bonkati( part) & Ladadih (part ). Total House Hold - 396 | Assistant Engineer | Junior Engineer | VCH/002742/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SOUMITRA BOSE | 2.82 | 0 | 0
1178 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos (Kulpat Bonkati, Gourangadihi, Kesia & Ladadih (Part ). Total House Hold - 396' | Assistant Engineer | Junior Engineer | VCH/002743/2021-2022 | FHTC/4 | 04/03/2022 | 0 | BISWARUP BOSE | 3.52 | 0 | 0
1179 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- B), Total House Hold - 50. | Assistant Engineer | Junior Engineer | VCH/002744/2021-2022 | FHTC/4 | 04/03/2022 | 0 | TAPAN KUMAR UPADHYAY | 4.47 | 0 | 0
1180 | Bankura Division | Bankura Sadar Sub-Division | laying Extra UPVC pipeline to cover Tirsulia (66) Barkania (69) & Jamdahara ( 71) mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by retrofitting Zone-B (Tilaboni) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002751/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SANJOY PATRA | 2.98 | 0 | 0
1181 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Chingra (292) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone-B and its mouzas under Sarenga water supply scheme (BRGF Ph-I) at Block- Sarenga , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002752/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SUBHADIP KOLEY | 4.96 | 0 | 0
1182 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Chhotagarra (288) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone-B and its mouzas under Sarenga water supply scheme (BRGF Ph-I) at Block- Sarenga , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002753/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PRADYUMNA KOLEY | 4.97 | 0 | 0
1183 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhengasole W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Dhengasole, No. of Mouza :- 05 nos. i.e. Dadasbari- 98, Jharia- 122, Bankati-123, Baraamlai-124 & Pedda-125, Total House Hold - 638 | Assistant Engineer | Junior Engineer | VCH/002754/2021-2022 | FHTC/4 | 04/03/2022 | 0 | BRINDABAN KONAR | 41.76 | 0 | 0
1184 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 06 ( Kustora, Nekragori , Gangtara, Bhalukbasa, Hrtyasol & Patharkata ). Total House Hold - 819 | Assistant Engineer | Junior Engineer | VCH/002755/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SABIR ALI KHAN | 18.43 | 0 | 0
1185 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe line to cover Birkham (110) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - P (Nachna) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) at Block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A Sl no - 06 | Assistant Engineer | Junior Engineer | VCH/002816/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GANESH ROY | 3.44 | 0 | 0
1186 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe line to cover Birkham (110) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - P (Nachna) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) at Block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - B Sl no - 07 | Assistant Engineer | Junior Engineer | VCH/002817/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GANESH ROY | 2.93 | 0 | 0
1187 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete of Saburbandh mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002818/2021-2022 | FHTC/9 | 09/03/2022 | 0 | RUFIKUL MONDAL | 4.93 | 0 | 0
1188 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Bhedua (46) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- C (Biradihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Hirbandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A | Assistant Engineer | Junior Engineer | VCH/002820/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.75 | 0 | 0
1189 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Bhedua (46) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- C (Biradihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Hirbandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002821/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.57 | 0 | 0
1190 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Lutia (47) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- C (Biradihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Hirbandh under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002822/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.36 | 0 | 0
1191 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
1192 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Atasole (61 ) & Tamakhun (62) susnigeria (77) & Bikramdihi mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 12 | Assistant Engineer | Junior Engineer | VCH/002832/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.49 | 0 | 0
1193 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Burisol (39 ) & Mahespur (52) Deuli (53) & Chirkunkanali (54) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002833/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.98 | 0 | 0
1194 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE work to Sarari village under Barjora water supply scheme (including left out BRGF ph - l ) under BRGF ph - l within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Sl no - 04 zone - lll Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/003107/2021-2022 | FHTC/30 | 30/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.21 | 0 | 0
1195 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas, (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III). No.of Mouza :- 13 nos (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold - 2821 nos. | Assistant Engineer | Junior Engineer | ORD/000395/2021-2022 | 206/BQA | 01/02/2022 | 60 | M/S TARUN KUMAR PATRA | 151.26 | 0 | 0
1196 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 | Assistant Engineer | Junior Engineer | VCH/002745/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UNICON INDIA | 116.51 | 0 | 0
1197 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas under Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 7 Nos. Total Household:- 882 Nos. | Assistant Engineer | Junior Engineer | VCH/002808/2021-2022 | FHTC/5 | 05/03/2022 | 0 | EARTH MOVING (INDIA) | 51.48 | 0 | 0
1198 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Lutia (47) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- C (Biradihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Hirbandh under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002822/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.36 | 0 | 0
1199 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Bamni (42) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- C (Biradihi) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Hirbandh under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002823/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 3.41 | 0 | 0
1200 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 01 , Narrah(PART), Total House Hold - 528.' | Assistant Engineer | Junior Engineer | VCH/002824/2021-2022 | FHTC/9 | 09/03/2022 | 0 | J. D. J. ENTERPRISE | 4.61 | 0 | 0
1201 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe line to cover sanpura & Kalipahari mouza & Dismantling & reconstruction of concrete of Saburbandh mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jorehira ( zone - B) under Chhatna block of Saltora -chhatna water supply scheme (BRGF ph - l project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002825/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.27 | 0 | 0
1202 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Burisol (39 ) & Mahespur (52) Deuli (53) & Chirkunkanali (54) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002833/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.98 | 0 | 0
1203 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Bagdubi (56 ) Palash Bani (57) budh Khila (60) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 21 | Assistant Engineer | Junior Engineer | VCH/002834/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.79 | 0 | 0
1204 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Dhanara (36 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 04 | Assistant Engineer | Junior Engineer | VCH/002835/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.62 | 0 | 0
1205 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Ramdungri (35 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - B sl no - 03 | Assistant Engineer | Junior Engineer | VCH/002836/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.62 | 0 | 0
1206 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Ramdungri (35 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 02 | Assistant Engineer | Junior Engineer | VCH/002837/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.55 | 0 | 0
1207 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Routara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Routara (Zone - A) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003020/2021-2022 | FHTC/28 | 28/03/2022 | 0 | SUBHENDU SEKHAR GORAI | 4.89 | 0 | 0
1208 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas, (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III). No.of Mouza :- 13 nos (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold - 2821 nos. | Assistant Engineer | Junior Engineer | VCH/003101/2021-2022 | FHTC/28 | 28/03/2022 | 0 | M/S TARUN KUMAR PATRA | 151.09 | 0 | 0
1209 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Kunjapur-112 & Bahalalpur-114, Total House Hold - 852 | Assistant Engineer | Junior Engineer | ORD/000192/2021-2022 | 3005/BQA | 26/11/2021 | 30 | MITHU BUILDERS | 66.8 | 52.08 | 0
1210 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 01 no. i.e. Dighalgram-126, Total House Hold - 751 | Assistant Engineer | Junior Engineer | ORD/000171/2021-2022 | 2846/BQA | 16/11/2021 | 30 | AMIYA KUMAR BIT | 69.52 | 57.57 | 0
1211 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dhamur, No. of Mouza :- 09 nos. i.e. Shashpur-75, Narayanpur-82, Thakuranidighi-63, Dharmapur-64, Charigram-65, Baikunthapur-68, Manaharpur-74, Biharpuskarini-94 & Barajpota-95 , Total House Hold - 2264 | Assistant Engineer | Junior Engineer | ORD/000419/2021-2022 | 440/BQA | 03/03/2022 | 60 | PRINCE INDUTRIES (INDIA) | 140.28 | 136.12 | 0
1212 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2021-2022 | 474/BQA | 04/03/2022 | 0 | Resource Division | 13.92 | 0 | 0
1213 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ajodhya Zone W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Sancha, No. of Mouza :- 16 nos. i.e. Sancha - 6,Patalpur -8, Loharara - 9, Ajodhya -10, Damodarpur -7, Antare -11, Jangalmahal -12,Gobardhanpur -44, Banskopa - 46, Amral - 47, Muchdang -48, Kundohati - 49, Birra -50, Pikpara -57, Dharapati -58 & Pachim Nischintapur -59, Total House Hold - 3096 | Assistant Engineer | Junior Engineer | ORD/000026/2022-2023 | 1084/BQA | 12/05/2022 | 1420 | M/S TARUN KUMAR PATRA | 240.2 | 168.44 | 98
1214 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur , Harinagara , Raghunathpur,Bamandihi, Kamla,Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No. of Mouza :- 04 nos, (Ronalejora, Shyampur, Bhagabanpur, Raghunathpur), Total House Hold -580 nos | Assistant Engineer | Junior Engineer | ORD/000129/2021-2022 | 2794/BQA | 11/11/2021 | 30 | RANABIR CHATTERJEE | 34.39 | 34.24 | 0
1215 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos | Assistant Engineer | Junior Engineer | ORD/000130/2021-2022 | 2795/BQA | 11/11/2021 | 30 | RANABIR CHATTERJEE | 40.68 | 11.79 | 0
1216 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No.of Mouza :- 02 no., (Harinagara, Kamla), Total House Hold - 283 nos | Assistant Engineer | Junior Engineer | ORD/000131/2021-2022 | 2796/BQA | 11/11/2021 | 30 | SAIKAT CHOWDHURY | 16.55 | 0 | 0
1217 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No. of Mouza:- 01 no., (Krishnanagar ), Total House Hold -1227 nos | Assistant Engineer | Junior Engineer | ORD/000132/2021-2022 | 2797/BQA | 11/11/2021 | 30 | MUNMUN UPADHYAY | 72.28 | 0 | 0
1218 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No.of Mouza :- 01 no., (Bhairabpur (Paschim), Total House Hold -367 nos | Assistant Engineer | Junior Engineer | ORD/000133/2021-2022 | 2798/BQA | 11/11/2021 | 30 | BEAUTY CHATTERJEE | 21.6 | 0 | 0
1219 | Bankura Division | Bankura Sadar Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur , Harinagara , Raghunathpur,Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IB) | Assistant Engineer | Junior Engineer | ORD/000191/2022-2023 | 350/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.96 | 4.96 | 0
1220 | Bankura Division | Bankura Sadar Sub-Division | Additional pipe line laying at Bhairabpur Paschim mouza and providing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), Name of Mouza :- Bhairabpur (Paschim), Total House Hold - 10 nos | Assistant Engineer | Junior Engineer | ORD/000328/2022-2023 | 531/BSD | 28/07/2022 | 21 | BEAUTY CHATTERJEE | 4.1 | 4.1 | 0
1221 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at Ronalejora, Shyampur & Bhagabanpur mouza of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) | Assistant Engineer | Junior Engineer | ORD/000765/2022-2023 | 536/BSD | 28/07/2022 | 21 | RANABIR CHATTERJEE | 4.98 | 4.96 | 0
1222 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at Bilmalpur mouza of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) | Assistant Engineer | Junior Engineer | ORD/000766/2022-2023 | 537/BSD | 28/07/2022 | 21 | RANABIR CHATTERJEE | 4.8 | 4.77 | 0
1223 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to increase pressure at Haringara Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000232/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SAIKAT CHOWDHURY | 2.79 | 0 | 0
1224 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to increase pressure at Kotgram Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000233/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SAIKAT CHOWDHURY | 4.57 | 0 | 0
1225 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Ronalejora, shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, krishnanagar, Barjora W/S Scheme (left out mouzas of barjora BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, zone IB Name of OHR - no (direct supply) No. of Mouza :- 10 nos. . Total House Hold -3147 sl no - 15 | Assistant Engineer | Junior Engineer | VCH/000246/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.83 | 0 | 0
1226 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos | Assistant Engineer | Junior Engineer | VCH/000268/2022-2023 | FHTC/18 | 18/04/2022 | 0 | RANABIR CHATTERJEE | 25.21 | 0 | 0
1227 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 | Assistant Engineer | Junior Engineer | VCH/002745/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UNICON INDIA | 116.51 | 0 | 0
1228 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No. of Mouza:- 01 no., (Krishnanagar ), Total House Hold -1227 nos | Assistant Engineer | Junior Engineer | VCH/002868/2021-2022 | FHTC/15 | 15/03/2022 | 0 | MUNMUN UPADHYAY | 72.26 | 0 | 0
1229 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to increase pressure at Haringara Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002884/2021-2022 |  | 16/03/2022 | 0 | SAIKAT CHOWDHURY | 2.79 | 0 | 0
1230 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to increase pressure at Kotgram Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002885/2021-2022 |  | 16/03/2022 | 0 | SAIKAT CHOWDHURY | 4.57 | 0 | 0
1231 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Bhairabpur (paschim) of Barjora water supply scheme (left out mouzas of Barjora block under (BRGF ph - I project) block - Barjora under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- No (direct supply) Name of Mouza:-- 1 no., (Bhairabpur) (Paschim) sl No- 09 | Assistant Engineer | Junior Engineer | VCH/002940/2021-2022 | FHTC/23 | 23/03/2022 | 0 | BEAUTY CHATTERJEE | 4.72 | 0 | 0
1232 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Bhairabpur (Paschim) of Barjora W/S Scheme (left out mouzas of Barjora block under BRGF PH - I within Barjoa block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora Name of OHR- direct supply , Name of Mouza:-- 1 no., (BBhairabpur (Paschim), Total House Hold - 42 nos sl no - 01. | Assistant Engineer | Junior Engineer | VCH/002941/2021-2022 | FHTC/23 | 23/03/2022 | 0 | BEAUTY CHATTERJEE | 4.59 | 0 | 0
1233 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Babundihi main road towards Bilmalpur village to cover Bilmalpur mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Barjora water supply scheme (left out mouzas of barjora block under BRGF ph - l ) within Barjora block under Bankura sadar sub - Division of Bankura Division, PHE Dte. zone - IB sl no - 09 | Assistant Engineer | Junior Engineer | VCH/002970/2021-2022 | FHTC/26 | 25/03/2022 | 0 | RANABIR CHATTERJEE | 4.69 | 0 | 0
1234 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Jomadargram more to Babundihi Talpukur more to increse pressute in Bamandihi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte zone - IB sl no - 08 | Assistant Engineer | Junior Engineer | VCH/003068/2021-2022 | FHTC/30 | 30/03/2022 | 0 | RANABIR CHATTERJEE | 4.72 | 0 | 0
1235 | Bankura Division | Bankura Sadar Sub-Division | supply of sluice valve restruration of concrete road, construction of valve chamber with all allied work to Sarari village under Barjora water supply scheme (including left out BRGF ph - l ) under BRGF ph - l within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Sl no - 05 zone - lll | Assistant Engineer | Junior Engineer | VCH/003106/2021-2022 | FHTC/30 | 30/03/2022 | 0 | M/S TARUN KUMAR PATRA | 3.64 | 0 | 0
1236 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2021-2022 | 2495/BQA | 23/09/2021 | 30 | SOUMITRA BHATTACHARYA | 57.83 | 0 | 0
1237 | Bankura Division | Khatra Sub-Division | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 45 | NAYAN BARDHAN | 49.26 | 10.04 | 0
1238 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000582/2021-2022 | 788/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.33 | 0 | 0
1239 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline, construction of different dia valve chamber & other allied works to increase pressure at Sareskol (32) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2022-2023 | 507/BQA | 13/03/2023 | 45 | UTTAM KUMAR SINHAMAHAPATRA | 4.81 | 4.74 | 60
1240 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Sareskol (32), Jambani (33), Jhulisol (34) & Neturpur (44) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000698/2021-2022 | 97/KSD | 10/03/2022 | 10 | SOUMITRA BHATTACHARYA | 4.72 | 0 | 0
1241 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000454/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.3 | 0 | 0
1242 | Bankura Division | Khatra Sub-Division | Laying Extra 15 mm NB PVC (schedule 80) /20 mm OD HDPE Pipe to cover Paharghata, Begdiha, Hapania mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- d) under Saltora- Block saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002757/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SIB SANKAR CHOWDHURY | 4.96 | 0 | 0
1243 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002759/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SOUMITRA BHATTACHARYA | 43.3 | 0 | 0
1244 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) | Assistant Engineer | Junior Engineer | VCH/002763/2021-2022 | FHTC/4 | 04/03/2022 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 22.27 | 0 | 0
1245 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No.of Mouza :- 02 no., (Harinagara, Kamla), Total House Hold - 283 nos | Assistant Engineer | Junior Engineer | VCH/002765/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SAIKAT CHOWDHURY | 16.53 | 0 | 0
1246 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe line to Gangnala (230) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Phulberia & its mouzas at Block- Sarenga , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002768/2021-2022 | FHTC/4 | 04/03/2022 | 0 | TARINI CHARAN UPADHYAY | 2.45 | 0 | 0
1247 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
1248 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 05 Nos. Total Household - 853 Nos. " | Assistant Engineer | Junior Engineer | ORD/000039/2021-2022 | 1786/BQA | 09/07/2021 | 30 | PARTHA PRATIM CHATAIT | 56.47 | 1.58 | 0
1249 | Bankura Division | Khatra Sub-Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II). No. of Mouza :-03 nos (Kadasole, Kamarsol, Ghutgaria), Total House Hold -1874 nos. | Assistant Engineer | Junior Engineer | ORD/000039/2022-2023 | 1380/BQA | 27/06/2022 | 60 | SIB SANKAR CHOWDHURY | 212.38 | 44.97 | 15
1250 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000120/2022-2023 | 322/KSD | 01/08/2022 | 15 | D. S. ENTERPRISE | 3.93 | 3.93 | 0
1251 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipe to increase water pressure at Majit mouza for rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - (I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000130/2022-2023 | 470/BSD | 06/06/2022 | 15 | TAPAN KUMAR MANDAL | 4.98 | 4.98 | 0
1252 | Bankura Division | Khatra Sub-Division | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 45 | NAYAN BARDHAN | 49.26 | 7.73 | 0
1253 | Bankura Division | Khatra Sub-Division | Supply & delivery of portable multi parameter water quality testing device of the device of rural drinking water sources of 146 Nos. GP in Bankura District of west Bengal under PHE Dte | Assistant Engineer | Junior Engineer | VCH/002839/2021-2022 | FHTC/9 | 09/03/2022 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 13.33 | 0 | 0
1254 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180), Dhuliapur (177), Hariharpur (178), Tikarpara (182), Digpar (194), Kusmi (195) & Chakrasol (196) mouzas under Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 17 Nos. Total Household:- 2199 Nos. | Assistant Engineer | Junior Engineer | ORD/000315/2021-2022 | 08/BQA | 03/01/2022 | 60 | GOPAL CHANDRA CHOUDHURY | 148.6 | 148.36 | 0
1255 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" | Assistant Engineer | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 1.01 | 0
1256 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-IV )Total House Hold - 139." | Assistant Engineer | Junior Engineer | ORD/000336/2020-2021 | 1705/BQA | 08/12/2020 | 30 | SUDAM KUMAR DAS | 9.89 | 9.42 | 0
1257 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180), Dhuliapur (177), Hariharpur (178), Tikarpara (182), Digpar (194), Kusmi (195) & Chakrasol (196) mouzas under Baricha, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12) | Assistant Engineer | Junior Engineer | ORD/000596/2021-2022 | 798/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.73 | 0.73 | 0
1258 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) | Assistant Engineer | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.46 | 0 | 0
1259 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Baricha (180), Dhuliapur (177) & Hariharpur (178) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000649/2021-2022 | 754/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.95 | 0 | 0
1260 | Bankura Division | Khatra Sub-Division | laying Extra UPVC pipeline to cover Palashbani (148) mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by retrofitting Zone-B (Tilaboni) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002772/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SANJOY PATRA | 1.65 | 0 | 0
1261 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Manjumara (Part-A), Total House Hold -125 | Assistant Engineer | Junior Engineer | VCH/002774/2021-2022 | FHTC/5 | 05/03/2022 | 0 | TAPAN KUMAR SARKAR | 1.27 | 0 | 0
1262 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 03 nos. i.e. Abantika- 88 , Belthya- 89 & Deuli- 91, Total House Hold - 733 | Assistant Engineer | Junior Engineer | ORD/000136/2021-2022 | 2805/BQA | 11/11/2021 | 30 | S B ASSOCIATES | 63.17 | 0 | 0
1263 | Bankura Division | Brishnupur Sub-Division | Extra retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)' at Abantika mouza in connection with Jal Jeevan Mission (JJM) of Benda (BRGF ph - I project) W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2022-2023 | 319/VSD | 29/11/2022 | 15 | SANTANU GARAI | 0.95 | 0.95 | 100
1264 | Bankura Division | Brishnupur Sub-Division | Extra retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)' at Abantika, Bethya and Banamalipur mouza in connection with Jal Jeevan Mission (JJM) of Benda (BRGF ph - I project) W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000304/2022-2023 | 320/VSD | 29/11/2022 | 15 | AJIT KUMAR DUTTA | 0.96 | 0.95 | 0
1265 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 1.11 | 0 | 0
1266 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
1267 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Part - B | Assistant Engineer | Junior Engineer | VCH/002721/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.47 | 0 | 0
1268 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Part - A | Assistant Engineer | Junior Engineer | VCH/002722/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.46 | 0 | 0
1269 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhuchu Dungri (61) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002724/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 0.28 | 0 | 0
1270 | Bankura Division | Khatra Sub-Division | Work Order for Relaying of UPVC pipeline at Jamrepara (295) mouza for construction and commissioning of FHTC (due to damage done by PWD (Roads) Dte. for Strengthening - Widening of road from Pirorgari More to Brahamandiha) of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000127/2022-2023 | 272/KSD | 12/07/2022 | 10 | ASHIS PAL | 1.2 | 1.13 | 0
1271 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Agaya (350) & Ampata (351) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 3 Nos. Total Household:- 265 Nos. | Assistant Engineer | Junior Engineer | ORD/000198/2021-2022 | 3017/BQA | 29/11/2021 | 30 | SUBHADIP KOLEY | 11.23 | 2.32 | 0
1272 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamrepara (295) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 285 Nos. | Assistant Engineer | Junior Engineer | ORD/000199/2021-2022 | 3018/BQA | 29/11/2021 | 30 | ASHIS PAL | 12.79 | 1.61 | 0
1273 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debgram (296) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 201 Nos. | Assistant Engineer | Junior Engineer | ORD/000201/2021-2022 | 3019/BQA | 29/11/2021 | 30 | SANJOY MONDAL | 10.53 | 1.14 | 0
1274 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 279 Nos. | Assistant Engineer | Junior Engineer | ORD/000202/2021-2022 | 3020/BQA | 29/11/2021 | 30 | TAPAN KUMAR UPADHYAY | 12.6 | 1.23 | 0
1275 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Dangarpara (293), Jamrepara (295), Debgram (296), Agaya (350), Ampata (351) & Sitarampur (352) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000587/2021-2022 | 791/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.34 | 0 | 0
1276 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Jamrepara (295), Debgram (296), Agaya (350), Ampata (351) & Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000452/2022-2023 | FHTC/24 | 24/06/2022 | 0 | TAPAS DEY | 0.34 | 0 | 0
1277 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Agaya (350), Ampata (351) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000644/2022-2023 | FHTC/14 | 14/07/2022 | 0 | COSMIC CONSTRUCTION | 2.88 | 0 | 0
1278 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 | Assistant Engineer | Junior Engineer | VCH/002353/2021-2022 | FHTC/25 | 25/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0
1279 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
1280 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to increase pressure at Ampata (351) Chingra ( 292) mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Gargarya (Zone - A) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002907/2021-2022 | FHTC/21 | 21/03/2022 | 0 | PRADYUMNA KOLEY | 3.36 | 0 | 0
1281 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to increase pressure at Dangarpara (293) Agaya (350) mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Gargarya (Zone - A) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002908/2021-2022 | FHTC/21 | 21/03/2022 | 0 | PRADYUMNA KOLEY | 3.28 | 0 | 0
1282 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Debgram (296) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Gargarya zone - A under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002956/2021-2022 | FHTC/24 | 24/03/2022 | 0 | SANJOY MONDAL | 4.61 | 0 | 0
1283 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Sitarampur (352) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone- A and its adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) at Block- Sarenga Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002982/2021-2022 | FHTC/24 | 24/03/2022 | 0 | TAPAN KUMAR UPADHYAY | 0.94 | 0 | 0
1284 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Jamrepara (295) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Gargarya Zone - A and its adjoining mouza under Sarenga water supply shceme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B laying extra UPVC pipe line to cover Jamrepara (295) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Gargarya Zone - A and its adjoining mouza under Sarenga water supply shceme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B | Assistant Engineer | Junior Engineer | VCH/003076/2021-2022 | FHTC/29 | 29/03/2022 | 0 | ASHIS PAL | 2.01 | 0 | 0
1285 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gamidya (192), Amla Tara (196), Angaria (197), Madan Mohanpur (198), Kheruashol (199), Betajora (200), Bhaluk Khulya (201), Brindabanpur (202), Shirsha (203), Siara (204), Kundalia (205), Bhedua (206), Kunchi Shole (207), Ektarpur (208), Bhetiara (212) & Nanda Bhanga (213) mouzas by retrofitting Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1663 nos. | Assistant Engineer | Junior Engineer | ORD/000405/2021-2022 | 320/BQA | 22/02/2022 | 45 | APEX ENTERPRISE | 93.6 | 62.62 | 0
1286 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Gamidya (192), Amla Tara (196), Angaria (197), Madan Mohanpur (198), Kheruashol (199), Betajora (200), Bhaluk Khulya (201), Brindabanpur (202), Shirsha (203), Siara (204), Kundalia (205), Bhedua (206), Kunchi Shole (207), Ektarpur (208), Bhetiara (212) & Nanda Bhanga (213) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000903/2021-2022 | 99/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.55 | 0.36 | 0
1287 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000034/2021-2022 | 574/BQA | 17/03/2022 | 0 | Resource Division | 10.24 | 0 | 0
1288 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186) & Kenduadangri (187) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 4 Nos. Total Household:- 295 Nos. | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 887/BQA | 13/04/2022 | 30 | TAPAN KUMAR UPADHYAY | 16.71 | 16.37 | 100
1289 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000272/2021-2022 | 3181/BQA | 21/12/2021 | 30 | SANJOY PATRA | 87.36 | 0 | 100
1290 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Khamani (121) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 381 Nos. | Assistant Engineer | Junior Engineer | ORD/000460/2021-2022 | 674/BQA | 25/03/2022 | 30 | MAHARAJA CONSTRUCTION CO. | 23.78 | 21.16 | 95
1291 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nekrapahari (192), Amdiha (193) & Beruabaid (194) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 3 Nos. Total Household:- 158 Nos. | Assistant Engineer | Junior Engineer | ORD/000461/2021-2022 | 675/BQA | 25/03/2022 | 1103 | SHYAMAPADA DEY | 10.13 | 3.54 | 20
1292 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 18) | Assistant Engineer | Junior Engineer | ORD/000476/2021-2022 | 110/KSD | 10/03/2022 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.66 | 3.24 | 20
1293 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000004/2022-2023 | 1840/BQA | 29/08/2022 | 0 | Resource Division | 7.74 | 0 | 0
1294 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kuldiha (211) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 717 Nos. ( PART-A) | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 780/BQA | 31/03/2022 | 1463 | BISWARUP BOSE | 22.12 | 0 | 40
1295 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kuldiha (211) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 717 Nos. ( PART - B) | Assistant Engineer | Junior Engineer | ORD/000483/2021-2022 | 781/BQA | 31/03/2022 | 1463 | SHYAMAL KUMAR DAS | 22.12 | 0 | 40
1296 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Telijant (188) & Bhalukchira (189) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household:- 729 Nos. ( PART - A ) | Assistant Engineer | Junior Engineer | ORD/000484/2021-2022 | 782/BQA | 31/03/2022 | 30 | DAUD ALI KHAN | 22.5 | 22.05 | 0
1297 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Telijant (188) & Bhalukchira (189) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household:- 729 Nos. ( PART B ) | Assistant Engineer | Junior Engineer | ORD/000485/2021-2022 | 783/BQA | 31/03/2022 | 30 | MRITYUNJOY HAZRA | 22.5 | 21.92 | 0
1298 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of UPVC pipeline in Jangalkhas (126), Chottaamlatara(185), Baraamlatara(186), & Kenduadangri (187) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000660/2022-2023 | 505/BQA | 13/03/2023 | 45 | TAPAN KUMAR UPADHYAY | 5.13 | 5.1 | 100
1299 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), Bhalukchira (189), Nekrapahari (192), Amdiha (193), Beruabaid (194) & Kuldiha (211) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) | Assistant Engineer | Junior Engineer | ORD/000689/2021-2022 | 865/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.76 | 0.44 | 0
1300 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Amjhor village to Sarenga Netaji More due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | VCH/002954/2021-2022 | FHTC/23 | 23/03/2022 | 0 | EARTH MOVING (INDIA) | 24.89 | 0 | 0
1301 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | VCH/002961/2021-2022 | FHTC/26 | 25/03/2022 | 0 | SANJOY PATRA | 69.45 | 0 | 0
1302 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur (225), Indra (226), Khamarbere (227), Datina Purusottampur (230) & Bansh Danga (231) mouzas by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1450 Nos. (Out of 2901 Nos.) ( Part-B) | Assistant Engineer | Junior Engineer | ORD/000015/2022-2023 | 924/BQA | 21/04/2022 | 70 | PRINCE INDUTRIES (INDIA) | 64.88 | 63.56 | 100
1303 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur (225), Indra (226), Khamarbere (227), Datina Purusottampur (230) & Bansh Danga (231) mouzas by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1451 ( out of 2901 nos.) ( PART-A) | Assistant Engineer | Junior Engineer | ORD/000031/2022-2023 | 1147/BQA | 24/05/2022 | 60 | PARAMESWAR CHOWDHURY | 64.92 | 43.57 | 62
1304 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Gogra, Adhury mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Horaka (Zone - G) under Saltora Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2021-2022 | 1031/ BSD | 14/12/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.86 | 0 | 0
1305 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur (225), Indra (226), Khamarbere (227), Datina Purusottampur (230) & Bansh Danga (231) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000900/2021-2022 | 103/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.97 | 0.73 | 0
1306 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0
1307 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2021-2022 | 575/BQA | 17/03/2022 | 0 | Resource Division | 17.87 | 0 | 0
1308 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) | Assistant Engineer | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
1309 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 560 | Assistant Engineer | Junior Engineer | VCH/002323/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SIB SANKAR CHOWDHURY | 26.82 | 0 | 0
1310 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266) Chak Bagmari (267) Bagmari Maheshpur (268) Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (288), Mahish Doba (289), Bena Bandi (290) & Bhedua (291) mouzas by retrofitting Jamadhara and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1047 nos. | Assistant Engineer | Junior Engineer | ORD/000399/2021-2022 | 301/BQA | 18/02/2022 | 30 | M/S BIPUL BANERJEE | 70.8 | 36.33 | 0
1311 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (288), Mahish Doba (289), Bena Bandi (290) & Bhedua (291) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Jamadhara and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2021-2022 | 96/BSD | 28/01/2022 | 2 | TAPAS DEY | 0.35 | 0.19 | 0
1312 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2021-2022 | 570/BQA | 17/03/2022 | 0 | Resource Division | 6.45 | 0 | 0
1313 | Bankura Division | Khatra Sub-Division | New Service Connection at Solepanemara,Moshiara (pin-722136) OHR site of Hirbandh & adjoining Mouzas water supply scheme of Hirbandh block under Bankura Mechanical Division,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00632/2023-2024 | FHTC/08 | 14/08/2023 | 0 | HIRBANDH CCC | 0.29 | 0 | 0
1314 | Bankura Division | Khatra Sub-Division | Power Connection As OHR at Solepanemara of Executive Engineer Bankura Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/02372/2023-2024 | FHTC/01 | 15/01/2024 | 0 | HIRBANDH CCC | 15.13 | 0 | 0
1315 | Bankura Division | Khatra Sub-Division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height with allied works and Providing ¿FHTC (Functional House Hold Tap Connection)¿ of Improvement of Hirbandh and its adjoining mouzas water supply scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000052/2023-2024 | 900/BQA | 20/04/2023 | 708 | SUBHANKAR BANERJEE | 230.48 | 104.77 | 55
1316 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Mashiara ICDS centre to Jhapandihi village to increase pressure in Dharampur, Jhapandihi and Kendua village under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1951/BQA | 17/07/2023 | 45 | M/S GEMINI CONSTRUCTION | 33.82 | 33.74 | 100
1317 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of Sluice Valve of Augmentation works for balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 128/KSD | 25/05/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.95 | 0.95 | 20
1318 | Bankura Division | Khatra Sub-Division | Work Order for Special repairing of Rising Main pipeline near Amjhuri village under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 265/KSD | 24/08/2023 | 7 | CHANDANA BANERJEE | 0.55 | 0 | 0
1319 | Bankura Division | Khatra Sub-Division | Construction of boundary wall including construction of Path way at Over Head Reservoir Site for Improvement of Hirbandh & Its adjoining mouzas water supply scheme within Khatra Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000586/2022-2023 | 501/BQA | 13/03/2023 | 45 | M/S. AMAL KUMAR SARKAR | 18.03 | 17.86 | 100
1320 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000051/2023-2024 | 2412/BQA | 18/08/2023 | 0 | Resource Division | 11.02 | 0 | 0
1321 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000157/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 11.02 | 0 | 0
1322 | Bankura Division | Khatra Sub-Division | Balance work of DI distribution line at soul ponamara with ancillary works for improvement of Hirbandh and its adjoing mouzas water supply scheme under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003014/2021-2022 | FHTC/28 | 28/03/2022 | 0 | EARTH MOVING (INDIA) | 3.48 | 0 | 0
1323 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of pipeline of pumping delivery main and rising main by MS pipe with allied works and construction of drain at Hirbandh Pumping Station under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000885/2022-2023 | 45/KSD | 29/03/2023 | 7 | S. B. CONSTRUCTION | 0.57 | 0.55 | 90
1324 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of pipeline of pumping delivery main and rising main by MS pipe with allied works and construction of drain at Hirbandh Pumping Station under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000888/2022-2023 | 47/KSD | 29/03/2023 | 7 | S. B. CONSTRUCTION | 0.57 | 0.56 | 90
1325 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of pipeline of pumping delivery main and rising main by MS pipe with allied works and construction of drain at Hirbandh Pumping Station under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 48/KSD | 29/03/2023 | 7 | SRIJAN CONSTRUCTION | 0.29 | 0.29 | 45
1326 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room and Operator Room with sanitary arrangement and laying HDPE pipeline with all allied works under balance work of Improvement of Hirbandh & its adjoining mouzas Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001784/2024-2025 | 494/BQA | 25/02/2025 | 60 | SUBHANKAR BANERJEE | 38.23 | 0 | 0
1327 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing And Installation Of Pumping Machineries And Other Electro-Mechanical Accessories for Improvement of Hirbandh And Adjoining Mouzas Water supply Scheme. Block- Hirbandh, Dist- Bankura. | Assistant Engineer | Junior Engineer | ORD/000073/2021-2022 | 895/BMD | 27/07/2021 | 120 | M/S P.P ELECTRICALS | 36.91 | 36.91 | 0
1328 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- Upargara ( Part ) Total House Hold- 128 |  | Junior Engineer | ORD/000018/2020-2021 | 620/BQA | 10/02/2021 | 30 | SAIKAT CHOWDHURY | 11.44 | 0 | 0
1329 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 01 no (Jalhori ) Total House Hold-144 |  | Junior Engineer | ORD/000021/2021-2022 | 1794/BQA | 09/07/2021 | 30 | TAPAS KUMBHAKAR | 9.46 | 0 | 45
1330 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 nos ( Radhaballavpur, Rampur) Total House Hold- 140 |  | Junior Engineer | ORD/000022/2021-2022 | 1795/BQA | 09/07/2021 | 30 | RUFIKUL MONDAL | 8.41 | 0 | 0
1331 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 no, ( Namabad , Gopinathdihi) Total House Hold-141 |  | Junior Engineer | ORD/000023/2021-2022 | 1796/BQA | 09/07/2021 | 30 | ASHISH PAUL | 9.27 | 12.75 | 0
1332 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthal (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000046/2020-2021 | 455/BQA | 05/02/2021 | 30 | SAIKAT CHOWDHURY | 10.71 | 0 | 0
1333 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Kendbeda, Jamthol (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000047/2020-2021 | 456/BQA | 05/02/2021 | 30 | BASUDEB ACHARJEE | 10.72 | 0 | 100
1334 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Bhelani Total House Hold- 140 |  | Junior Engineer | ORD/000049/2020-2021 | 457/BQA | 05/02/2021 | 30 | TAPAS KUMBHAKAR | 10.58 | 0 | 0
1335 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 04 no [Narasole, Taljhoria, Khabanigoparpur (Part), Jhikuria] Total House Hold- 359 |  | Junior Engineer | ORD/000050/2021-2022 | 1961/BQA | 30/07/2021 | 30 | TAPAS KUMAR HAZRA | 25.15 | 0 | 0
1336 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthol (PART) ,Bhelani (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000051/2020-2021 | 458/BQA | 05/02/2021 | 30 | TAPAS KUMAR HAZRA | 10.62 | 0 | 0
1337 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 10 no, Khabanigoparpur (Part) Total House Hold-140 |  | Junior Engineer | ORD/000052/2021-2022 | 1931/BQA | 28/07/2021 | 30 | SRIKANTA MONDAL | 9.31 | 0 | 20
1338 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Asurabad (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000203/2020-2021 | 988/BQA | 26/02/2021 | 30 | PARESH CHANDRA LAYEK | 10.68 | 0 | 0
1339 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Asurabad (PART) ,Bhelani (PART) Jamthol (part) Total House Hold- 74 |  | Junior Engineer | ORD/000205/2020-2021 | 990/BQA | 26/02/2021 | 30 | M/S T.P. HAZRA & SONS | 9.9 | 0 | 0
1340 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction concrete at Jolhari mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000668/2021-2022 | 1041/BSD | 14/12/2021 | 15 | TAPAS KUMBHAKAR | 4.83 | 0 | 0
1341 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
1342 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no. 43Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Barabaikunthapur-125 & Habispur-127 , Total House Hold - 245 (245 out of 549) |  | Junior Engineer | VCH/002335/2021-2022 | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR MANDAL | 16.4 | 0 | 0
1343 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no. 43Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Mamudpur-124 & Bagalpur-128 , Total House Hold - 304 (304 out 549) |  | Junior Engineer | VCH/002336/2021-2022 | FHTC/25 | 25/01/2022 | 0 | OSMAN SEKH | 22.07 | 0 | 0
1344 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Indas, Name of OHR - Rol, No. of Mouza :- 2 nos. i.e. Rol-07 & Chichinga-08, Total House Hold - 1421 |  | Junior Engineer | VCH/002337/2021-2022 | FHTC/25 | 25/01/2022 | 0 | CREATION CONSTRUCTION | 64.49 | 0 | 0
1345 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover 15 mm NB PVC to cover Gopinathdihi, Namabad mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora - Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002900/2021-2022 | FHTC/17 | 17/03/2022 | 0 | ASHIS PAL | 2.43 | 0 | 0
1346 | Bankura Division | Khatra Sub-Division | Service connection charge for Shyamsundarpur (Zone IIA & IIB) water supply scheme at head works site Raipur block under BMD,PHE Dte.(SM/10296) | Assistant Engineer | Junior Engineer | BILL/00349/2024-2025 | BP-146/2024-25 | 03/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.92 | 0 | 0
1347 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road fiom L04O-Nischintapur to Kharda under Raipur Block in the District of Bankura ,Vide Package No-WB-03-669, Road Length"4 Km. (Shyamsundarpur (Zone - IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01432/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0
1348 | Bankura Division | Khatra Sub-Division | Repair ard Maintenance work of the Road from Lo3g-Kuchiapal to SH under Raipur Block in the District of Bankura ,Vide Package No-WB-03-654, Road Length4,g Km. (Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme(BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01433/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0
1349 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Magra to Ledra under Raipur Block in the District of Bankura,Vide Package No-WB-03-281, Road Length-11.9 Km.( Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01436/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 6.14 | 0 | 0
1350 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from KUCHIAPAL - L038 under Raipur Btock in the District of Bankura ,Vide Package No-WB-03-S7, Road Length-5.2 Km. (Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I). | Assistant Engineer | Junior Engineer | BILL/01437/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.94 | 0 | 0
1351 | Bankura Division | Khatra Sub-Division | Balance Work of Construction of High lift Pump House cum Panel Room cum Sub-Station building with sanitary & water supply arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000064/2024-2025 | 1519/BQA | 19/06/2024 | 621 | SUBHENDU SEKHAR GORAI | 19.03 | 0 | 81
1352 | Bankura Division | Khatra Sub-Division | Balance allied works of Shyamsundarpur (IIA & IIB) water supply scheme under Raipur water supply scheme (BRGF PH-I) under Khatra Sub-Division of BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 1811/BQA | 11/07/2024 | 120 | GOPAL CHANDRA CHOWDHURY | 216.03 | 175.4 | 85
1353 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000027/2022-2023 | 2283/BQA | 30/11/2022 | 0 | Resource Division | 1250.64 | 0 | 0
1354 | Bankura Division | Khatra Sub-Division | Sinking of 12 (Twelve) Nos. 200 mm dia. X 6.50 Mtr. depth horizontal river bed tube well, using MS "T", MS delivery main collecting line from river bed tube well to CWR incuding supply and erecting of guard piling etc. all complete, laying rising main using different dia D.I. - K9 pipes and providing ¿FHTC (Functional House Hold Tap Connection)¿ with all allied works for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division P.H.E. Dte. (Total Household : 5110 Nos.) | Assistant Engineer | Junior Engineer | ORD/000240/2022-2023 | 2111/BQA | 03/11/2022 | 1245 | GOPAL CHANDRA CHOWDHURY | 740.81 | 241.53 | 60
1355 | Bankura Division | Khatra Sub-Division | Construction of R.C.C. Clear water reservoir (C.W.R.) of capacity 200 M3 for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000470/2022-2023 | 285/BQA | 13/02/2023 | 90 | ASOKE KUMAR SAHU | 29.63 | 29.62 | 30
1356 | Bankura Division | Khatra Sub-Division | Construction of High lift Pump House cum Panel Room cum Sub-Station building with sanitary & water supply arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2022-2023 | 492/BQA | 13/03/2023 | 90 | SUBHENDU SEKHAR GORAI | 25.87 | 25.83 | 5
1357 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at Head Work Site for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2022-2023 | 493/BQA | 13/03/2023 | 90 | M/S S.M ENTERPRISE | 4.7 | 4.36 | 100
1358 | Bankura Division | Khatra Sub-Division | Construction of Operator cum Guard Room with water supply and sanitary arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000573/2022-2023 | 494/BQA | 13/03/2023 | 90 | KABISH KUMAR GHOSH | 5.52 | 5.11 | 100
1359 | Bankura Division | Khatra Sub-Division | Construction of Boundary wall, Approach road, Land Development with other allied works for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. (For Head Work site) | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 495/BQA | 13/03/2023 | 751 | D. S. ENTERPRISE | 29.02 | 8.21 | 82
1360 | Bankura Division | Khatra Sub-Division | Construction of Sub-Station Building with all allied works for balance work of Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001144/2023-2024 | 346/BQA | 05/02/2024 | 421 | GANGADHAR MONDAL | 18.99 | 0 | 83
1361 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 3 nos. site of Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme (SM/10296) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001934/2024-2025 | 177\KSD | 07/03/2025 | 10 | M/S ASHOK KUMAR DEY | 0.45 | 0 | 90
1362 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High Lift & Low Lift pumping machineries and other electro-mechanical accessories for Syamsundarpur (Zone-IIA & IIB) water supply scheme under Raipur water supply scheme (BRGF Ph-I) under JJM Programme under Bankura Mechanical Division PHE Dte. Block-Raipur, Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 951/BMD | 17/05/2023 | 866 | R.N.S. TRADING | 276.53 | 0 | 32
1363 | Bankura Division | RWS Bankura Sub-Division | New Connection at Asnasundarpur, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00432/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1364 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1365 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1366 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1367 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
1368 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Murkum C/o Sudip Saha ,Murkum Chhota Tung |  | Junior Engineer | BILL/00046/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
1369 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1370 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1371 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
1372 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Dhanjhar Village (SM/11112), (2) Mini Piped Water Supply Scheme for Birbandh Village (SM/11111), (3) Mini Piped Water Supply Scheme for Murkum Choto Tung Village (SM/11113), (4) Mini Piped Water Supply Scheme for Phuljhor Village (SM/11027), (5) Mini Piped Water Supply Scheme for Banpukuria Village (SM/11029) and (6) Mini Piped Water Supply Scheme for Gholkuri Village (SM/11031) |  | Junior Engineer | ORD/001991/2024-2025 | 191\KSD | 10/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 90
1373 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte C/o Sudip saha ,Goalmuri, Ranibandh |  | Junior Engineer | BILL/00038/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
1374 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1375 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1376 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
1377 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1378 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for mini water supply scheme at Krishnapur, Goswamidihi village under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00836/2023-2024 | FHTC/09 | 07/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
1379 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1380 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
1381 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1382 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for Rajpura Tiluri mini water supply scheme under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00837/2023-2024 | FHTC/09 | 19/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
1383 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1384 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 24 | 48
1385 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-42, Mouza-Chaturi,Kalapathar Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00278/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
1386 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-93, Mouza-Chaturi, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00280/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
1387 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1388 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1389 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
1390 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-60, Mouza-Karamara, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00282/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
1391 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1392 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1393 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 42.6 | 48
1394 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1395 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1396 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
1397 | Bankura Division | RWS Bankura Sub-Division | New Connection at Saharghati, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00415/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1398 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1399 | Bankura Division | RWS Bankura Sub-Division | New Connection at Jemuya, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00413/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1400 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 48
1401 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Jemua Village (SM/11081), (2) Mini Piped Water Supply Scheme for Mahishakanali Village (SM/11083), (3) Mini Piped Water Supply Scheme for Sushunia Village (SM/11034), (4) Mini Piped Water Supply Scheme for Tilabai Village (SM/11035), (5) Mini Piped Water Supply Scheme for Ghagar Village (SM/11050) and (6) Mini Piped Water Supply Scheme for Nabagram Village (SM/11052) |  | Junior Engineer | ORD/001997/2024-2025 | 197\KSD | 10/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 95
1402 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1403 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte Bankati, Ps-Khatra, Dist-Bankura |  | Junior Engineer | BILL/00773/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
1404 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1405 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
1406 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1407 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1408 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
1409 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1410 | Bankura Division | Khatra Sub-Division | New Connection at Machla, Taldangra,Pin-722102 PHE Dte | Assistant Engineer | Junior Engineer | BILL/00434/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1411 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1412 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
1413 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1414 | Bankura Division | Khatra Sub-Division | New Connection at Marasole, Taldangra,Pin-722102 PHE Dte | Assistant Engineer | Junior Engineer | BILL/00428/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1415 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1416 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
1417 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 48
1418 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1419 | Bankura Division | RWS Bankura Sub-Division | New Service Connection at Mini Piped w/s Scheme at Nischintapur Po-Jiarda under Bankura Mechanical Division PHE Dte |  | Junior Engineer | BILL/00812/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
1420 | Bankura Division | RWS Bankura Sub-Division | New Service connection at Mini Piped w/s scheme at Nischintapur under Bankura Mechanical Division PHE Dte |  | Junior Engineer | BILL/00820/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
1421 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1422 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
1423 | Bankura Division | Khatra Sub-Division | Quotation of WBSEDCL for the scheme of SM/11063 |  | Junior Engineer | BILL/00845/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.37 | 0 | 0
1424 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1425 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Nama Dudhiadoba Village (SM/11063), (2) Mini Piped Water Supply Scheme for Bamunpathri Village (SM/11070), (3) Mini Piped Water Supply Scheme for Barisol Village (SM/11062), (4) Mini Piped Water Supply Scheme for Bhaduldoba Village (SM/11065) and (5) Mini Piped Water Supply Scheme for Dudhiadoba Village (SM/11072) |  | Junior Engineer | ORD/002002/2024-2025 | 202\KSD | 10/03/2025 | 10 | SUBHADIP KOLE | 0.75 | 0 | 95
1426 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1427 | Bankura Division | Khatra Sub-Division | New service connection for Bhaduldoba Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00137/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
1428 | Bankura Division | Khatra Sub-Division | New Service Connection at Bhaduldoba, Simlapal Block, PHE Dte. |  | Junior Engineer | BILL/00320/2023-2024 | FHTC/04 | 29/04/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
1429 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1430 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1431 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
1432 | Bankura Division | Bankura Sadar Sub-Division | Quatation bill Salukgere, Gopinathpur, Kotulpur | Assistant Engineer | Junior Engineer | BILL/00670/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1433 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 42 | 48
1434 | Bankura Division | Brishnupur Sub-Division | (site - Shyampur, lowgram, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00288/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1435 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1436 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1437 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION SHYAMPUR | Assistant Engineer | Junior Engineer | BILL/01286/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1438 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
1439 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Adwaitabati, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00277/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1440 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1441 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1442 | Bankura Division | Brishnupur Sub-Division | quotation for new connection Adwaitabati | Assistant Engineer | Junior Engineer | BILL/01273/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1443 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
1444 | Bankura Division | Bankura Sadar Sub-Division | Construction and Commissioning of 'FHTC (Funtional House Hold Tap Connection) in mouzas of Rejuvenation of SARBERIA W/S Scheme ( Zone-I) (including Left out BRGF Mouzas] Block - Chhatna, Dist.- Bankura under JAL SWAPNA & Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 2032/BQA | 24/07/2023 | 981 | M/S TARUN KUMAR PATRA | 356.78 | 0 | 46
1445 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M Bg-. 218-2 /4) in between Rly. Station Bankura (BQA) & Onda Gram (ODM) Rly. station in Salghata mouza, P.S. Bankura,by Jack Pushing method with 400 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001958/2024-2025 | 684/BQA | 12/03/2025 | 60 | GOPAL CHANDRA CHOWDHURY | 59.97 | 0 | 100
1446 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.:BG- 245/17-19) in between Jhantipahari Rly. Station (JPH) & Chhatna Rly. station (CJN) , P.S.Chhatna ,by Jack Pushing method with 400 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Augmentation of Sarberia & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001967/2024-2025 | 687/BQA | 12/03/2025 | 60 | M/S TARUN KUMAR PATRA | 73.54 | 0 | 1
1447 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1448 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Tunamara Jiorda | Assistant Engineer | Junior Engineer | BILL/01032/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
1449 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1450 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.5 | 48
1451 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for various Anganwari Center's & School under Moynapur W/S Scheme Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2022-2023 | 136/VSD | 12/05/2022 | 15 | SWAPAN KUMAR DE | 0.49 | 0.49 | 0
1452 | Bankura Division | Brishnupur Sub-Division | Construction of 300 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for MOYNAPUR mouzas under MOYNAPUR W/S. scheme, at JOYPUR Block, Within BISHNUPUR Sub-Division,under BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2022-2023 | 2322/BQA | 08/12/2022 | 1110 | SANJOY PATRA | 82.13 | 78.3 | 95
1453 | Bankura Division | Brishnupur Sub-Division | Laying distribution system Augmentation of Moynapur Piped W/S. Scheme (JJM Revesion ) at Moynapur, Joypur Block under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000297/2022-2023 | 06/BQA | 03/01/2023 | 90 | S B ASSOCIATES | 80.46 | 71.03 | 0
1454 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 90 mtr long for Augmentation of Moynapur water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 67/BQA | 05/01/2023 | 30 | GOURANGA NANDI | 5.28 | 5.14 | 0
1455 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for augmentation of Moynapur W/S Scheme Block- Joypur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/008990 , AAFS Project Id :- PH212246951M000 Block -Joypur, Name of OHR -Moynapur, No. of Mouza :- 1 nos. i.e. Moynapur-J.L No-120. Total House Hold - 1224 | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 180/BQA | 30/01/2023 | 60 | TAPAN KUMAR MANDAL | 51.02 | 51.01 | 100
1456 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Chandar Rail line para, school , health center, Total House Hold -52. | Assistant Engineer | Junior Engineer | ORD/000471/2020-2021 | 10/BSD | 06/01/2021 | 21 | SANJOY MONDAL | 4.8 | 4.79 | 0
1457 | Bankura Division | Brishnupur Sub-Division | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Moynapur to accommodate FHTC under Jal Sapno Mission under Jaypur Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 1) [Estimated Cost Rs. Quotated Rate] | Assistant Engineer | Junior Engineer | ORD/000651/2021-2022 | 424/A/VSD | 23/09/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.51 | 2.51 | 0
1458 | Bankura Division | Brishnupur Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Moynapur W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) (Sl. No. 02) OHR Capacity- 300 m3 | Assistant Engineer | Junior Engineer | ORD/000654/2022-2023 | 145//VSD | 18/05/2022 | 15 | AGAC | 1.4 | 1.4 | 0
1459 | Bankura Division | Brishnupur Sub-Division | Providing FHTC, Sinking of 1 no Tubewell and Construction of Pump House for Augmentation of Moynapur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001364/2024-2025 | 3126/BQA | 19/12/2024 | 90 | SANJOY PATRA | 48.63 | 0 | 0
1460 | Bankura Division | Brishnupur Sub-Division | Supply of Various Type Materials for Construction of 300 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for MOYNAPUR mouzas under MOYNAPUR W/S. scheme, at JOYPUR Block, Within BISHNUPUR Sub-Division,under BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001149/2023-2024 | 354/BQA | 06/02/2024 | 30 | SANJOY PATRA | 6.02 | 5.99 | 75
1461 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of ground water based piped supply scheme for Moynapur to accommodate FSTC under Jal Swapna mission under Joypur Block in Bankura District under Bankura Mechanical Division, PHE Dte t: Bankura. | Assistant Engineer | Junior Engineer | ORD/000193/2023-2024 | 1016/BMD | 22/05/2023 | 1080 | KASHINATH DEY | 23.01 | 17.72 | 30
1462 | Bankura Division | Brishnupur Sub-Division | (site - Parbatipur pry school, gopinathpur, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00299/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1463 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1464 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1465 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at PARBATIPUR | Assistant Engineer | Junior Engineer | BILL/01252/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1466 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
1467 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Chaknayan, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00279/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1468 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1469 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1470 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at CHAKNAYAN | Assistant Engineer | Junior Engineer | BILL/01269/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1471 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 24 | 48
1472 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1473 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1474 | Bankura Division | Brishnupur Sub-Division | New Service connection for Mini water supply scheme at Ramnagar G.P- Hamirpur block-Patrasayer under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02589/2023-2024 | FHTC/03 | 12/03/2024 | 0 | PATRASAYER CCC | 0.44 | 0 | 0
1475 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
1476 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1477 | Bankura Division | Brishnupur Sub-Division | New Connection at Bhetia,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00478/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
1478 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1479 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
1480 | Bankura Division | RWS Bankura Sub-Division | New Connection at Jambedia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00419/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
1481 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1482 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Bankadaha village | Assistant Engineer | Junior Engineer | BILL/00044/2024-2025 | FHTC/04 | 29/04/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
1483 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1484 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1485 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
1486 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 15 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002206/2024-2025 | 582\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.41 | 0 | 0
1487 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Pirragora village | Assistant Engineer | Junior Engineer | BILL/00047/2024-2025 | FHTC/04 | 29/04/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
1488 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1489 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1490 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
1491 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 15 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002206/2024-2025 | 582\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.41 | 0 | 0
1492 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1493 | Bankura Division | Brishnupur Sub-Division | New Connection at Thakurhat,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00477/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
1494 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1495 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 44.6 | 48
1496 | Bankura Division | Brishnupur Sub-Division | New Connection at Hurhurjanagar, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00308/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
1497 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1498 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1499 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
1500 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RANIBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 2045/BQA | 24/07/2023 | 982 | PRINCE INDUTRIES (INDIA) | 587.96 | 357.64 | 73
1501 | Bankura Division | Brishnupur Sub-Division | Balance Ancillary Work for ¿Ranibandh¿ and ¿Dhulai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2025-2026 | 1990/BQA | 16/09/2025 | 180 | PRINCE INDUSTRIES (INDIA) | 194.43 | 0 | 15
1502 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2023-2024 | 2523/BQA | 08/09/2023 | 0 | Resource Division | 8.19 | 0 | 0
1503 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000080/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 79.07 | 0 | 0
1504 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Rani Bandh water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 875/BMD | 04/05/2023 | 1260 | TAPAN KUMAR SARKAR | 35.82 | 20.2 | 56
1505 | Bankura Mechanical | Brishnupur Sub-Division | Continuation Order for Trial run of operation and guarding of pumping machinery & other at Rani Bandh (P.H-I) water supply scheme under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001220/2025-2026 | 1798/BMSD | 29/10/2025 | 90 | TAPAN KUMAR SARKAR | 0.43 | 0 | 0
1506 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1507 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1508 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
1509 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 13 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002204/2024-2025 | 581\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 1.96 | 0 | 0
1510 | Bankura Division | Brishnupur Sub-Division | New service connection for Borajpota Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00131/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDUS CCC | 0.12 | 0 | 0
1511 | Bankura Division | Brishnupur Sub-Division | New Connection at Barajpota,Indus PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00315/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.11 | 0 | 0
1512 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1513 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1514 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 55 | 48
1515 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Parashe site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00175/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
1516 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1517 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1518 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 39 | 48
1519 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1520 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1521 | Bankura Division | Brishnupur Sub-Division | New service connection at Uttar Rupai Sayar (Bud Bud) Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02603/2023-2024 | FHTC/03 | 12/03/2024 | 0 | BUDBUD CCC | 0.14 | 0 | 0
1522 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
1523 | Bankura Division | Brishnupur Sub-Division | New service connection for "Saldaha" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00066/2024-2025 | BP-38/2024-25 | 06/05/2024 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
1524 | Bankura Division | Brishnupur Sub-Division | New Connection at Saldha, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00314/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
1525 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1526 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1527 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 54 | 48
1528 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
1529 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1530 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1531 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
1532 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/15005 ) | Assistant Engineer | Junior Engineer | BILL/00659/2024-2025 |  | 09/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 45.36 | 0 | 0
1533 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/15005 ) | Assistant Engineer | Junior Engineer | BILL/01242/2024-2025 | BP-226/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 45.36 | 0 | 0
1534 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 974/BQA | 28/04/2023 | 613 | S.N POLYMERS PVT LTD | 312.82 | 114.31 | 65
1535 | Bankura Division | Khatra Sub-Division | Work order for Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 1837/BQA | 12/07/2024 | 45 | SIBSANKAR CHOWDHURY | 14.17 | 14.1 | 80
1536 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-3A) (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000627/2022-2023 | 183/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.09 | 3.21 | 0
1537 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.) including by pass arrangement, construction of boundary wall and repairing of guard room for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- III/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001765/2024-2025 | 488/BQA | 25/02/2025 | 370 | TAPAS PAL | 24.51 | 0 | 100
1538 | Bankura Division | Khatra Sub-Division | Work Order for Emergency laying of pipeline from Rajapara More to Khatra Police Station (left side of the road) [due to construction of cement concrete road from Rajapara more to Khatra Puratan Bazar and Khatra Puratan Bazar to Kharban More (Partly renovation work of the Bituminous road)] to provide FHTC under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/A) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002284/2024-2025 | 58\KSD | 16/01/2025 | 10 | S.N POLYMERS PVT LTD | 5.63 | 0 | 95
1539 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 26 | 0 | 0
1540 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000203/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 15.88 | 0 | 0
1541 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000459/2023-2024 | 1785/BMD | 01/08/2023 | 60 | M/S DE ENGINEERING CONCERN | 2.39 | 0 | 0
1542 | Bankura Division | Khatra Sub-Division | Work Order for Emergency laying of pipeline from Rajapara More to Khatra Police Station (right side of the road) [due to construction of cement concrete road from Rajapara more to Khatra Puratan Bazar and Khatra Puratan Bazar to Kharban More (Partly renovation work of the Bituminous road)] to provide FHTC under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/A) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002285/2024-2025 | 59\KSD | 16/01/2025 | 10 | S.N POLYMERS PVT LTD | 5.46 | 0 | 95
1543 | Bankura Division | Khatra Sub-Division | Additional laying of pipeline for providing FHTC (Functional House Hold Tap Connection) for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- V/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2025-2026 | 1011/BQA | 25/04/2025 | 251 | SANJOY PATRA | 15.89 | 0 | 0
1544 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- V/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 1194/BQA | 22/05/2023 | 681 | SANJOY PATRA | 232.69 | 112.3 | 81
1545 | Bankura Division | Khatra Sub-Division | Work order for Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- V/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2024-2025 | 1838/BQA | 12/07/2024 | 45 | MOU CONSTRUCTION | 7.52 | 6.24 | 90
1546 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-5A) (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000630/2022-2023 | 187/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.53 | 3.26 | 0
1547 | Bankura Division | Khatra Sub-Division | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 16.10.2023 to 08.06.2024. | Assistant Engineer | Junior Engineer | ORD/001140/2023-2024 | 297\KSD | 05/10/2023 | 244 | RAJ KUMAR BAURI | 0.09 | 0.02 | 90
1548 | Bankura Division | Khatra Sub-Division | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 12.02.2023 to 13.10.2023. | Assistant Engineer | Junior Engineer | ORD/001184/2022-2023 | 18/KSD | 08/02/2023 | 365 | RAJ KUMAR BAURI | 0.09 | 0.09 | 90
1549 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 225 Cum., staging height 20 Mtr.) including by pass arrangement, guard room and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- V/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001766/2024-2025 | 489/BQA | 25/02/2025 | 243 | TAPAN KUMAR MANDAL | 11.03 | 0 | 0
1550 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000037/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 0.61 | 0 | 0
1551 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000207/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 8.8 | 0 | 0
1552 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000240/2023-2024 | 1125/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
1553 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 5.52 | 0 | 0
1554 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000086/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 31.95 | 0 | 0
1555 | Bankura Mechanical | Brishnupur Sub-Division | Jibta Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01501/2023-2024 | BP-2023-24-96 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.55 | 0 | 0
1556 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Jibta piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 771/BMD | 24/04/2023 | 738 | ABHIJIT MUKHERJEE | 31.26 | 13.14 | 64
1557 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RAMNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2023-2024 | 1972/BQA | 18/07/2023 | 1048 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 570.89 | 129.78 | 65
1558 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Ramnagar Piped Water Supply Scheme (SM/14005) & 3 nos. sites of Danna Piped Water Supply Scheme (SM/18302) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001884/2024-2025 | 562/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
1559 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000078/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 84.18 | 0 | 0
1560 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for RAMNAGAR water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00020/2024-2025 | BP-2024-25-31 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
1561 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Ramnagar (T/W-II) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/14005) | Assistant Engineer | Junior Engineer | BILL/01478/2024-2025 | BP-2024-25-358 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.29 | 0 | 0
1562 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Ramnagar Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000033/2025-2026 | 238/BMD | 14/05/2025 | 90 | UNITED TRADERS | 11.66 | 0 | 0
1563 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Ramnagar Piped water supply scheme Block : Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 770/BMD | 24/04/2023 | 1095 | RAJIB COMPANY | 46.94 | 18.92 | 80
1564 | Bankura Division | Brishnupur Sub-Division | Road Name: Prayagpur to 21L20 Package No: WB-03-774 Name of the Block: Sonamukhi Name of the District: Bankura Length of Road: 1.650 Km Damaged Length: 3080.000 m (Due to some portion Both Side Cutting) SM/14245 CHAKAI PWSS | Assistant Engineer | Junior Engineer | BILL/01249/2024-2025 | BP-437/2024-25 | 28/11/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 4.85 | 0 | 0
1565 | Bankura Division | Brishnupur Sub-Division | Road Name: L049-Paschimdubrajpur to Sitaljore Package No: WB-03-666 Name of the Block: Sonamukhi Name of the District: Bankura Length of Road: 1.180 Km Damaged Length: 300.000 m (Due to both side cutting) SM/14245 CHAKAI PWSS | Assistant Engineer | Junior Engineer | BILL/01250/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.58 | 0 | 0
1566 | Bankura Division | Brishnupur Sub-Division | Repair and Maintenance work of the Road from Palashdanga to T12 under Sonamukhi Block in the District to Bankura ,Vide Package No-WB-03-50, Road Length- 16.80 Km. Scheme code for i) chakai PWSS (ch-3000m to ch- 7100m)- SM/14245 ii) Birsinghapur pwss (ch- 9400m to 12100m)- SM/17223 iii) Dhulai PWSS (Ch-13100m to 16800m)- SM/18753 | Assistant Engineer | Junior Engineer | BILL/01251/2024-2025 | BP-439/2024-25 | 28/11/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 30.91 | 0 | 0
1567 | Bankura Division | Brishnupur Sub-Division | Balance Ancillary Work for ¿Kubirbandh¿ and ¿Chakai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000422/2025-2026 | 1989/BQA | 16/09/2025 | 180 | PRINCE INDUSTRIES (INDIA) | 130.51 | 0 | 15
1568 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR CHAKAI & KUBIRBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 2336/BQA | 14/08/2023 | 999 | PRINCE INDUTRIES (INDIA) | 1048.51 | 241.17 | 73
1569 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Chakai Piped Water Supply Scheme (SM/14245) & 3 nos. sites of Kubir Bandh Piped Water Supply Scheme (SM/14008) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001893/2024-2025 | 571/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
1570 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2024-2025 | 2944/BQA | 21/11/2024 | 0 | Resource Division | 4.83 | 0 | 0
1571 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 140.84 | 0 | 0
1572 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for CHAKAI (JL NO-23, PLOT-177) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00018/2024-2025 | BP-2024-25-26 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0
1573 | Bankura Mechanical | Brishnupur Sub-Division | Chakai Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01665/2023-2024 | BP-2023-24-192 | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0
1574 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Chakai Piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 768/BMD | 24/04/2023 | 1260 | GOENKA ENTERPRISE | 47 | 19.47 | 80
1575 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VI) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) Near Sahebbandh More & (2) Near Patpur village More | Assistant Engineer | Junior Engineer (Contractual) | ORD/000072/2025-2026 | 1069/BQA | 30/04/2025 | 246 | SWAPAN KUMAR CHANDRA | 14.38 | 0 | 50
1576 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VI/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000117/2023-2024 | 1199/BQA | 22/05/2023 | 955 | SABIR ALI KHAN | 174.78 | 70.65 | 65
1577 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline for Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VI Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000179/2024-2025 | 2136/BQA | 07/08/2024 | 60 | SUBHENDU BANERJEE | 9.92 | 9.55 | 80
1578 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-6) (Sl. No. 11) | Assistant Engineer | Junior Engineer (Contractual) | ORD/000631/2022-2023 | 189/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.18 | 2.95 | 0
1579 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 45 Cum., staging height 20 Mtr.) including by pass arrangement, guard room and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VI Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/002022/2024-2025 | 673/BQA | 12/03/2025 | 184 | SAKIYAR RAHAMAN MONDAL | 10.87 | 0 | 0
1580 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000039/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 36.3 | 0 | 0
1581 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000209/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 8.51 | 0 | 0
1582 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-6 of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000242/2023-2024 | 1127/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
1583 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House cum chlorine room and Sinking of 03 (Three) no. 200 mm X 165 mm dia.X 250 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000201/2024-2025 | 1889/BQA | 15/07/2024 | 625 | ASHIS KUMAR SAMANTA | 18.8 | 3.07 | 63
1584 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2024-2025 | 2345/BQA | 09/09/2024 | 266 | GANGADHAR MONDAL | 31.19 | 0 | 80
1585 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura-II, Name of OHR -KENDBONI (Zone - P), No. of Mouza :-12 nos mousas (Karanjora, Lapuria, Ladna, Garakusum, Mankanali , Khiraijur,Kendboni, Kantaboni, Mamurjuri, Dhansimul,, Sonamui & Malindasi), No. of Household, No. of Household- 200 nos. under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2023-2024 | 2007/BQA | 19/07/2023 | 987 | ASHIS KUMAR SAMANTA | 209.18 | 146.97 | 65
1586 | Bankura Division | Bankura Sadar Sub-Division | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at Dhan Simul (07), Baikunthapur (15), Arjunpur (42), Bhedua Purusottompur (264) & Chhatarkanali (268) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001059/2023-2024 | 1175/BSD | 22/11/2023 | 15 | TAPAS DEY | 0.69 | 0.68 | 100
1587 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kendboni (Zone- P) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001198/2023-2024 | 451/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 1.85 | 0 | 100
1588 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000083/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.54 | 0 | 0
1589 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000242/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.54 | 0 | 0
1590 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00147/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1591 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01612/2023-2024 | BP-2023-24-139 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
1592 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Kendboni (Zone-P) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 437/BMD | 10/06/2025 | 90 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 26.41 | 0 | 0
1593 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kendbani (Zone P) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000526/2023-2024 | 1890/BMD | 17/08/2023 | 853 | EASTERN INDIA SALES & SERVICE | 81.78 | 49.86 | 56
1594 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Zone-II Ekteswar) | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 1200/BQA | 22/05/2023 | 270 | SUBHANKAR BANERJEE | 155.66 | 106.87 | 92
1595 | Bankura Division | Bankura Sadar Sub-Division | Supplying fitting fixing of different dia. CIDF Sluice Valve & fittings & Construction of valve chamber in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR and adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2023-2024 | 515/BSD | 12/06/2023 | 15 | MANOJ GHOSAL | 0.89 | 0.89 | 22
1596 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001202/2023-2024 | 455/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 2.31 | 0 | 100
1597 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line for creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001318/2023-2024 | 15/BSD | 03/01/2024 | 10 | SUBHANKAR BANERJEE | 0.94 | 0.93 | 10
1598 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line (to increase pressure of Bejogram Mouza) from Chowmatha More to House of Rabi Lohar in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001323/2023-2024 | 32/BSD | 08/01/2024 | 10 | SUBHANKAR BANERJEE | 0.98 | 0.98 | 10
1599 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza) from House of Badal Mukherjee towards Chowmatha More in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001327/2023-2024 | 33/BSD | 08/01/2024 | 10 | SUBHANKAR BANERJEE | 1 | 1 | 10
1600 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000071/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.75 | 0 | 0
1601 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000222/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.75 | 0 | 0
1602 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza)from Lalbaba Ashram towards House of Badal Mukherjee in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001501/2023-2024 | 40/BSD | 10/01/2024 | 10 | SUBHANKAR BANERJEE | 1 | 0.96 | 10
1603 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza) from House of Kamarpara towards Lalbaba Ashram in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001502/2023-2024 | 41/BSD | 10/01/2024 | 10 | SUBHANKAR BANERJEE | 0.99 | 0.99 | 10
1604 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza)from house of Rabi Lohar towards Bejogram in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001503/2023-2024 | 42/BSD | 10/01/2024 | 10 | SUBHANKAR BANERJEE | 0.8 | 0.76 | 10
1605 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Kotalpukur (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 2089/BQA | 27/07/2023 | 889 | MUNMUN UPADHYAY | 249.33 | 145.87 | 70
1606 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001174/2023-2024 | 427/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.46 | 0 | 100
1607 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House of departmental design & drawing in connection with Jal Jeevan Mission (JJM)for Augmentation of Kotalpukur (Zone- B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001391/2024-2025 | 38/BQA | 02/01/2025 | 545 | MUNMUN UPADHYAY | 16.96 | 0 | 100
1608 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000073/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.43 | 0 | 0
1609 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000224/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.43 | 0 | 0
1610 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00141/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1611 | Bankura Mechanical | Bankura Sadar Sub-Division | Quotation Bill for New Service Connection at Kotalpukur (zone-B) Water supply scheme under Bankura Mechanical Division PHE DTE (scheme code: SM/16955) | Assistant Engineer | Junior Engineer | BILL/01254/2024-2025 | BP-2024-25-321 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0
1612 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for Augmentation works at OHR site under Kotalpukur (ZONE -B) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000374/2024-2025 | 1003/BMD | 24/09/2024 | 240 | KINGKINI TRADERS | 9.12 | 0 | 25
1613 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kotalpukur ( Zone B) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000519/2023-2024 | 1884/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69
1614 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of ¿FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhana Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Keshra, No. of Mouza :- 18 nos, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Shaldiha, Rampur, Lakshmishol, Khirshole, Chakta magara, Joytradihi, Pithabad, Bhandarber, Keshra, Mahishadanga, Hetatora, Baliguma), Total House Hold - 2926 nos. | Assistant Engineer | Junior Engineer | ORD/000248/2021-2022 | 3361/BQA | 31/12/2021 | 60 | M/S D.K.H CONSTRUCTION | 145.99 | 145.98 | 0
1615 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Bangora to vanderber to increase water pressure at Saldiha,Vanderber for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Keshra (Zone - I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2022-2023 | 48/BQA | 05/01/2023 | 90 | M/S ABU KADER KHAN | 3.57 | 2.61 | 78
1616 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Pithabad, Keshra (Maldanga Village) mouza for retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000568/2022-2023 | 369/KSD | 29/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 3.2 | 3.2 | 0
1617 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Saldiha (Katabari gram, Napit para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000570/2022-2023 | 367/KSD | 29/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.19 | 4.19 | 0
1618 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Masthol, Baliguma mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000574/2022-2023 | 363/ KSD | 29/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.82 | 4.82 | 0
1619 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Suribedia, Keshra, Khirpai mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000577/2022-2023 | 335/KSD | 16/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.58 | 4.58 | 0
1620 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Hanulia, Laxmisole, Vandarber mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000580/2022-2023 | 337/KSD | 16/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 3.99 | 3.99 | 0
1621 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Saldiha (Bouri para, Tati para, Baisnab para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2022-2023 | 365/KSD | 29/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.99 | 4.99 | 0
1622 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhana Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Keshra, No.of Mouza :- 18 nos, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol,Shaldiha, Rampur, Lakshmishol, Khirshole, Chakta magara, Joytradihi, Pithabad, Bhandarber, Keshra, Mahishadanga, Hetatora, Baliguma) Total House Hold - 2926 nos. | Assistant Engineer | Junior Engineer | ORD/000879/2021-2022 | 72/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.98 | 0.94 | 0
1623 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Approv.DPR no- 37, Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 9 nos. i.e. Nangalbhanga-18, Chwak Chuamosina-19, Bendara-38, Ramsundarpur-39, Dapanjuri-40, Dhirkona-41, Joyrampur-42, Tentulia-62 & Siharshul-63, Total House Hold - 807 | Assistant Engineer | Junior Engineer | ORD/000170/2021-2022 | 2845/BQA | 16/11/2021 | 30 | I.R.CONSTRUCTION | 58.45 | 55.43 | 0
1624 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000050/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 23.46 | 0 | 0
1625 | Bankura Mechanical | Brishnupur Sub-Division | New sevice connection for Karajbani water supply scheme (SM/16702) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01247/2024-2025 | BP-2024-25-322 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0
1626 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Karajbani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 427/BMD | 27/06/2024 | 240 | GOENKA ENTERPRISE | 51.06 | 8.49 | 21
1627 | Bankura Division | RWS Bankura Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of CWR and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-D (Lachiapur) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 1912/BQA | 13/07/2023 | 565 | EARTH MOVING (INDIA) | 133.76 | 98.43 | 25
1628 | Bankura Division | RWS Bankura Sub-Division | Laying HDPE pipeline from Nanda village to Pakuria village, in Saluipahari village in connection with Augmentation of Lachiapur (Zone- D) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 2254/BQA | 28/08/2024 | 157 | MANAS DEY | 15.23 | 0 | 80
1629 | Bankura Division | RWS Bankura Sub-Division | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 3 Nos. pump house at tubewell site and laying distribution pipeline of Zone-D (Lachiapur) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001764/2024-2025 | 495/BQA | 25/02/2025 | 561 | SUBHADIP KOLE | 45.97 | 0 | 20
1630 | Bankura Division | RWS Bankura Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000165/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.39 | 0 | 0
1631 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Lachiapur (Zone D) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000059/2025-2026 | 255/BMD | 14/05/2025 | 90 | ORIENTAL ENGINEERING CO. | 29.05 | 0 | 0
1632 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Biradihi (Zone C ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 256/BMD | 14/05/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.35 | 0 | 0
1633 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Lachiapur(Zone-D) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000196/2025-2026 | 642/BMD | 11/07/2025 | 90 | JAL PRAVAHIKA PVT LTD | 34 | 0 | 0
1634 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Lachiapur (Zone-D) under Khatra-Hirbandh-Ranibandh water supply scheme (BRGF-Ph-I) under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000608/2023-2024 | 2082/BMD | 12/09/2023 | 720 | RABINDRA NATH KHAN | 61.4 | 0 | 30
1635 | Bankura Division | Khatra Sub-Division | Raniabndh -Jhilimili Road from Ch.1.860 km to Ch. 1.890 km, from Ch. 2.264 km to Ch. 2.284 hm, from Ch. 3.309 km to Ch. 3.609 km and from Ch. 3.630¿km to Ch. 3.770 km, Restoration work damage by PHE Dept by laying pipe line under Bankura Highway Division in the district of Bankura. Augmentation of Makhnu (Zone-K) W/S Scheme (SM/17251) | Assistant Engineer | Junior Engineer | BILL/01029/2024-2025 |  | 28/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.91 | 0 | 0
1636 | Bankura Division | Khatra Sub-Division | Raniabndh -Jhilimili Road from Ch.1.860 km to Ch. 1.890 km, from Ch. 2.264 km to Ch. 2.284 hm, from Ch. 3.309 km to Ch. 3.609 km and from Ch. 3.630¿km to Ch. 3.770 km, Restoration work damage by PHE Dept by laying pipe line under Bankura Highway Division in the district of Bankura. Augmentation of Makhnu (Zone-K) W/S Scheme (SM/17251) | Assistant Engineer | Junior Engineer | BILL/01247/2024-2025 | BP-347/2024-25 | 03/10/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.91 | 0 | 0
1637 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of Air Valve of Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 126/KSD | 25/05/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.94 | 0.94 | 20
1638 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2022-2023 | 675/BQA | 28/03/2023 | 1422 | GOUTAM BHATTACHRYYA | 75.44 | 29.37 | 65
1639 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of 4 (Four) Nos. Pump Houses with ancillary works in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001154/2023-2024 | 358/BQA | 06/02/2024 | 30 | SUBHADIP KOLE | 37.55 | 1.35 | 30
1640 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000175/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1641 | Bankura Mechanical | Khatra Sub-Division | New service connection charge at T/W-III of Makhnu. | Assistant Engineer | Junior Engineer | BILL/01148/2024-2025 | BP-2024-25-284 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.98 | 0 | 0
1642 | Bankura Mechanical | Khatra Sub-Division | New service connection charge at T/W-IV of Makhnu | Assistant Engineer | Junior Engineer | BILL/01150/2024-2025 | BP-2024-25-285 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0
1643 | Bankura Mechanical | Khatra Sub-Division | New Service Connection at Makhnu T/W-I | Assistant Engineer | Junior Engineer | BILL/01482/2024-2025 | BP-2024-25-371 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.58 | 0 | 0
1644 | Bankura Mechanical | Khatra Sub-Division | New Service Connection at Makhnu T/W-II | Assistant Engineer | Junior Engineer | BILL/01483/2024-2025 | BP-2024-25-371 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.58 | 0 | 0
1645 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Makhnu (Zone k) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000418/2025-2026 | 579/BMD | 03/07/2025 | 90 | GOENKA ENTERPRISE | 28.19 | 0 | 0
1646 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Makhnu (Zone- K) ( boosting at tail end) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000150/2024-2025 | 493/BMD | 09/07/2024 | 659 | M/S BIPUL BANERJEE | 49.9 | 9.41 | 76
1647 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low Lift Pump House, Laying additional LDS and Construction of Boundary Wall at Jadab Nagar under Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000194/2024-2025 | 1866/BQA | 12/07/2024 | 628 | SOUMITRA KUMAR DAS | 34.71 | 0 | 90
1648 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Agarda and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000365/2023-2024 | 2027/BQA | 24/07/2023 | 1012 | UNIVERSAL CONSTRUCTION | 212.34 | 142.5 | 70
1649 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000107/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.96 | 0 | 0
1650 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000289/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.96 | 0 | 0
1651 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at existing Tubewell for Augmentation of Agarda and adjoining mouzas piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000167/2024-2025 | 509/BMD | 09/07/2024 | 720 | CHAKRABORTY MINING & ENGINEERING. | 24.55 | 4.08 | 100
1652 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Agarda & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000544/2023-2024 | 1980/BMD | 28/08/2023 | 120 | TAPAN KUMAR SARKAR | 56.61 | 35.89 | 64
1653 | Bankura Division | Bankura Sadar Sub-Division | Schedule for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿¿& parallel pipe line to increase pressure in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-E) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2023-2024 | 2043/BQA | 24/07/2023 | 270 | GOPAL CHANDRA CHOWDHURY | 395 | 394.38 | 100
1654 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 02 (Two) nos. Tubewell, 03 (Three) nos. rotary tubewell with low lift pump houses, construction of 250 cum. CWR with high lift Pumphouse, Repairing and Renovation of 700 Cum. OHR, construction of Boundary wall, WBSEDCEL Room, Operator's room cum Guard room and Laying HDPE pipe line from CWR site to Punisol mouza under Augmentation works for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-E) under Onda block (BRGF Ph-I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001961/2024-2025 | 696/BQA | 12/03/2025 | 203 | PRADIP PATRA | 236.76 | 0 | 7
1655 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000110/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 14.5 | 0 | 0
1656 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000293/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 14.5 | 0 | 0
1657 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-E) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000548/2023-2024 | 1984/BMD | 28/08/2023 | 120 | EASTERN INDIA SALES & SERVICE | 74.01 | 44.3 | 60
1658 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro mechanical accessories for Augmentation of Aguri bandh Punisole and its adjoining mouzas water supply scheme (Zone E) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001076/2023-2024 | 3055/BMD | 12/03/2024 | 480 | M.S. ENTERPRISE | 77.57 | 27.13 | 100
1659 | Bankura Division | Khatra Sub-Division | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 2 Nos. pump house at tubewell site, laying distribution pipeline and providing FHTC of Zone-Malian in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2025-2026 | 1120/BQA | 07/05/2025 | 60 | UNIVERSAL CONSTRUCTION | 26.03 | 0 | 0
1660 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone- Malian in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2022-2023 | 560/BQA | 17/03/2023 | 45 | PARESH CHANDRA LAYEK | 32.12 | 30.69 | 100
1661 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000172/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
1662 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Deuli (Zone Malian ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 253/BMD | 14/05/2025 | 90 | SINHA ELECTRICALS | 27.35 | 0 | 0
1663 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Zone Malian OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000197/2025-2026 | 643/BMD | 11/07/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 35.2 | 0 | 0
1664 | Bankura Division | Brishnupur Sub-Division | Restoration work of Sashpur - Dighalgram road from 3.00 kmp to 4.10 kmp(in Stretches) of Length 1.60 km due to laying of pipeline of Akui Zone-A PWSS [SM/16943] under Indas Block under JJM Project by Bankura Division. PHE Dte. over the road under Bishnupur Division P.W.Dte. in the District of Bankura. | Assistant Engineer | Junior Engineer | BILL/01418/2025-2026 |  | 09/09/2025 | 0 | EXECUTIVE ENGINEER, BANKURA DIVISION, PWD | 4.69 | 0 | 0
1665 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AKUI ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000344/2023-2024 | 1968/BQA | 18/07/2023 | 623 | S.N POLYMERS PVT LTD | 129.09 | 38.79 | 40
1666 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Augmentation of Akui Zone-A Water Supply Scheme (SM/16943 ) & 3 nos. sites of Augmentation of Akui Zone-B Water Supply Scheme (SM/17228) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001812/2024-2025 | 538/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 100
1667 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Akui (Zone-B) Piped Water Supply Scheme & Augmentation of Akui Zone-A Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001937/2024-2025 | 654/BQA | 11/03/2025 | 90 | COSMIC CONSTRUCTION | 12.97 | 0 | 0
1668 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00184/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
1669 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AKUI ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00438/2024-2025 | BP-2024-25-114 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
1670 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01626/2023-2024 | BP-2023-24-161 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.41 | 0 | 0
1671 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000358/2023-2024 | 1694/BMD | 28/07/2023 | 967 | KINGKINI TRADERS | 41.83 | 23.77 | 40
1672 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PRAKASH ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000334/2023-2024 | 2004/BQA | 19/07/2023 | 622 | S.N POLYMERS PVT LTD | 125.9 | 13.63 | 70
1673 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Prakash Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00168/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1674 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Prakash (Zone-B) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1710/BMD | 28/07/2023 | 60 | KASHINATH DEY | 20.9 | 0 | 0
1675 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Prakash Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 3074/BMD | 12/03/2024 | 120 | S. G. TECHNICAL SERVICE | 15.72 | 0 | 0
1676 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House at CWR site for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000694/2023-2024 | 2640/BQA | 21/09/2023 | 833 | SRIKANTA MONDAL | 18.91 | 0 | 0
1677 | Bankura Division | Bankura Sadar Sub-Division | Construction of 200 Cum. Clear Water Reservoir with allied works for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000695/2023-2024 | 2641/BQA | 21/09/2023 | 211 | RUFIKUL MONDAL | 43.9 | 25.99 | 65
1678 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2023-2024 | 2642/BQA | 21/09/2023 | 60 | M/S SUPRIYA CHATTERJEE | 18.14 | 11.85 | 2
1679 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Dhaban (Zone-A) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000845/2023-2024 | 2971/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.98 | 2.54 | 100
1680 | Bankura Division | Bankura Sadar Sub-Division | Distribution of Pipeline and Creation of Balance FHTC (Functional House Hold Tap Connection) for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 3020/BQA | 03/11/2023 | 60 | M/S BIPUL BANERJEE | 78.59 | 47.95 | 6
1681 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 12.64 | 0 | 0
1682 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000136/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4.39 | 0 | 0
1683 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000148/2023-2024 | 3467/BQA | 20/12/2023 | 0 | Resource Division | 11.89 | 0 | 0
1684 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000250/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 4.39 | 0 | 0
1685 | Bankura Mechanical | Bankura Sadar Sub-Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | Assistant Engineer | Junior Engineer | BILL/00128/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1686 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for DHABAN water supply scheme under BMD PHE Dte. (SM code : SM/17702) | Assistant Engineer | Junior Engineer | BILL/00429/2024-2025 | BP-2024-25-105 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0
1687 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machinery and other electromagnetically accessories for Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001089/2023-2024 | 3064/BMD | 12/03/2024 | 420 | WEST BENGAL ENGINEERING CO. | 84.1 | 0 | 37
1688 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Intermediate Boosting pumping station(IBS) and sub-station equipments at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 1470/BMD | 18/07/2023 | 60 | DAS ENTERPRISE | 173.06 | 164.82 | 70
1689 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on delivery line at Intermediate Boosting pumping station(IBS) at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura for Augmentation work Dhaban( Zone-A) under Saltora-Chhatna Water supply scheme (BRGF Phase-I) | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 2086/BMD | 12/09/2023 | 611 | DAS ENTERPRISE | 17.65 | 0 | 60
1690 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of 100 Cum. Clear Water Reservoir, Construction of Pump House, Boundary Wall, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Harirampur pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000485/2023-2024 | 2337/BQA | 14/08/2023 | 270 | MANJAR ALI KHAN | 275.04 | 60.53 | 25
1691 | Bankura Division | Bankura Mechanical Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
1692 | Bankura Division | Bankura Mechanical Sub-Division | Preparation of Detailed Project Report for Proposed Ground Water Based Harirampur Pipe Water Supply Scheme under Bankura Division, Block : Hirbandh, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 3543/BQA | 29/12/2023 | 30 | LEMNISCATE | 3.03 | 3.03 | 90
1693 | Bankura Division | Bankura Mechanical Sub-Division | Work Order for Installation of scheme information board for 2 nos. site of Augmentation of Intake, WTP & Rising Main for surface Water-based piped water supply scheme for Mukutmanipur, Khatra & Ranibundh (SM/18612) within Khatra Block, 1 no. site of Sub surface water based Harirampur pipe water supply scheme (SM/18039), 1 no. site of Improvement of Hirbandh and its adjoining mouzas water supply scheme (SM/09852), 1 no. site of Augmentation of Zone-A (Bhuakana) Water Supply Scheme (SM/17730), 1 no. site of Augmentation of Zone-B (Tilabani) Water Supply Scheme (SM/17731) within Hirbandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001911/2024-2025 | 155\KSD | 07/03/2025 | 10 | BIKASH MANDAL | 0.9 | 0 | 90
1694 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 16.15 | 0 | 0
1695 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000197/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 8.62 | 0 | 0
1696 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/00202/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
1697 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00303/2024-2025 |  | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
1698 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00304/2024-2025 |  | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
1699 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00305/2024-2025 | BP-2024-25-52 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
1700 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Harirampur piped water supply scheme Block Hirbandh under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000565/2023-2024 | 2032/BMD | 01/09/2023 | 600 | M/S SWAPAN BANERJEE | 35.43 | 0 | 30
1701 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR MAHALDANGA PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000472/2023-2024 | 2327/BQA | 14/08/2023 | 961 | M/S TARUN KUMAR PATRA | 904.78 | 271.06 | 65
1702 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Jadabnagar Piped Water Supply Scheme (SM/14527) & 3 nos. sites of Mahaldanga Piped Water Supply Scheme (SM/18318) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001827/2024-2025 | 545/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.9 | 0 | 0
1703 | Bankura Division | Brishnupur Sub-Division | Additional works for Road Crossing by Jack Pushing methodof Mahaldanga Water Supply Scheme under Joypur Block under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001942/2024-2025 | 690/BQA | 12/03/2025 | 90 | M/S TARUN KUMAR PATRA | 165.68 | 0 | 100
1704 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 17.54 | 0 | 0
1705 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 240.6 | 0 | 0
1706 | Bankura Mechanical | Brishnupur Sub-Division | Mahaldanga T/W-III | Assistant Engineer | Junior Engineer | BILL/00853/2023-2024 | BP-2023-24-39 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
1707 | Bankura Mechanical | Brishnupur Sub-Division | Mahaldanga T/W-II | Assistant Engineer | Junior Engineer | BILL/00854/2023-2024 | BP-2023-24-40 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
1708 | Bankura Mechanical | Brishnupur Sub-Division | New service connection charge at P/H-I of Mahaldanga W/S Scheme | Assistant Engineer | Junior Engineer | BILL/01240/2024-2025 | BP-2024-25-308 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.97 | 0 | 0
1709 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & T/W No-III of Mahaldanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 878/BMD | 04/05/2023 | 180 | UNIVERSAL ENTERPRISE | 53.32 | 22.94 | 32
1710 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHUAMASINA ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000393/2023-2024 | 2053/BQA | 24/07/2023 | 618 | SIB SANKAR CHOWDHURY | 230.45 | 60.77 | 60
1711 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Chuamosina (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001354/2024-2025 | 3171/BQA | 24/12/2024 | 90 | MUKHERJEE CONSTRUCTION | 12.97 | 0 | 5
1712 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 5 nos. sites of Augmentation of Chuamasina Zone-A Water Supply Scheme (SM/17696) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001804/2024-2025 | 533/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.75 | 0 | 0
1713 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chuamasina Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00166/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1714 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chuamosina Zone-A Mouza Arjunpur. SM/17696. | Assistant Engineer | Junior Engineer | BILL/00724/2024-2025 | BP-2024-25-196 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.35 | 0 | 0
1715 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chuamosina Zone -A Mouza Chuamosina JL no 17. SM /17696. | Assistant Engineer | Junior Engineer | BILL/00725/2024-2025 | BP-2024-25-197 | 28/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.6 | 0 | 0
1716 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL Procedure -A (2010) on turn key /full deposit basis for new service connection at Mouza Jhatabon under Bankura Mechanica Division ,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00730/2024-2025 | BP-2024-25-207 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.74 | 0 | 0
1717 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Exsistingt TW I,III,IV and V for Augmentation of Chuamosina and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 486/BMD | 09/07/2024 | 120 | INDRAJIT MITRA | 31.42 | 20.67 | 40
1718 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000523/2023-2024 | 1887/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 75.13 | 0 | 75
1719 | Bankura Division | Bankura Division | Deposition of fund for permission of rail crossing between Sirjam and Jhantipahari at KM 259/7-9 under South Eastern Railway under Adra Division. | Assistant Engineer | Junior Engineer | BILL/00027/2024-2025 | FHTC/04 | 18/04/2024 | 0 | SOUTH EASTERN RAILWAY | 6.78 | 0 | 0
1720 | Bankura Division | Bankura Division | Sinking of 4 (Four) Nos. 200 mm dia. X 3.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works, Construction of 150 Cum. OHR, 100 Cum. Clear Water Reservoir, Pump House, Boundary Wall with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Parashibana pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000505/2023-2024 | 2358/BQA | 14/08/2023 | 955 | RAISINHA INFRASTRUCTURE PVT. LTD. | 289.5 | 21.05 | 30
1721 | Bankura Division | Bankura Division | Route Survey Preparation of DPR for piped water supply scheme for uncover mouzas of Malpara (JL No- 151), Amdiha (161), Narasinhapur (JL No- 163), Harakbedya (JL No- 166), Kelai (JL No- 167), Parashibana (JL No- 168), Jamdoba (JL No- 169), Barshi (JL No- 171), Goyal Danga (JL No- 160) Block- Chhatna under Jal Jeevan Misson (JJM) of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2023-2024 | 2980/BQA | 31/10/2023 | 30 | LEMNISCATE | 2.76 | 0 | 100
1722 | Bankura Division | Bankura Division | Soil Investigation work for construction of OHR (150 CUM CAPACITY) under Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000894/2023-2024 | 3045/BQA | 06/11/2023 | 30 | K S GROUP | 0.56 | 0 | 0
1723 | Bankura Division | Bankura Division | Construction of Pump House cum chlorine room (5.40 M X 3.6M) & Toilet with sanitary water supply arrangement, Construction of Guard Room & Toilet with sanitary & water supply arrangement, Construction of WBSEDCL Room and Crossing Rail Track with 300 mm (OD) welded MS Casing Pipe with 100 mm dia. MS carrier pipe for Proposed sub surface water based Parashibana pipe water supply scheme under Chhatna Block under Bankura Sadar Sub-Division of Bankura Division. | Assistant Engineer | Junior Engineer | ORD/001342/2024-2025 | 3181/BQA | 24/12/2024 | 548 | RAISINHA INFRASTRUCTURE PVT. LTD. | 53.17 | 0 | 0
1724 | Bankura Division | Bankura Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 65.32 | 0 | 0
1725 | Bankura Division | Bankura Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000132/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 5.39 | 0 | 0
1726 | Bankura Division | Bankura Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000150/2023-2024 | 3467/BQA | 20/12/2023 | 0 | Resource Division | 8.67 | 0 | 0
1727 | Bankura Division | Bankura Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000232/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 5.39 | 0 | 0
1728 | Bankura Mechanical | Bankura Division | Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00197/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
1729 | Bankura Mechanical | Bankura Division | New service connection for PARASHIBANA water supply scheme under BMD PHE Dte. (SM CODE : SM/18043) | Assistant Engineer | Junior Engineer | BILL/00430/2024-2025 | BP-2024-25-104 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.47 | 0 | 0
1730 | Bankura Mechanical | Bankura Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Proposed surface water based Parashibana under Water Supply Scheme Block- Chatna under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000449/2023-2024 | 1776/BMD | 01/08/2023 | 60 | RAJIB COMPANY | 45.33 | 32.16 | 11
1731 | Bankura Mechanical | Bankura Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machinery and other electromagnetically accessories for Augmentation of sub Surface water base water supply Scheme for Parashibana to accommodate FHTC in Chhatna Block under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001071/2023-2024 | 3054/BMD | 12/03/2024 | 180 | RAJIB COMPANY | 25.63 | 0 | 40
1732 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 253/2 -3) in between Chandar Rly. Station Brindabanpur Rly. station in , P.S. Beliatore,by Jack Pushing method with 300 mm (OD) Spirally welded MS Casing Pipe with 100 mm dia. MS carrier pipe under Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2025-2026 | 1659/BQA | 24/07/2025 | 45 | SIBSANKAR CHOWDHURY | 85.35 | 0 | 5
1733 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001189/2023-2024 | 441/BQA | 08/02/2024 | 30 | LEMNISCATE | 2 | 0 | 100
1734 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000119/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.11 | 0 | 0
1735 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000275/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.11 | 0 | 0
1736 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | Assistant Engineer | Junior Engineer | BILL/00193/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1737 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation of Beliatore and adjoining mouzas (Phase-I) under Bankura Mechanical Division PHE Dte Block- Barjora Dist -Bankura | Assistant Engineer | Junior Engineer | ORD/000574/2023-2024 | 2036/BMD | 01/09/2023 | 580 | M/S BIPUL BANERJEE | 45.43 | 20.43 | 45
1738 | Bankura Division | Bankura Sadar Sub-Division | Creation of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura -II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :- 03 nos.Name of mouza:- Bikna (235), Kuraria (254), Katnar (255), No. of Household- 1363 nos. | Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 872/BQA | 18/04/2023 | 909 | GON ASSOCIATES | 25.37 | 19.06 | 76
1739 | Bankura Division | Bankura Sadar Sub-Division | Construction of High Lift Pump House, Office cum Operators' Room with Toilet, Boundary Wall at Bikna OHR Site under Augmentation Water Supply Scheme | Assistant Engineer | Junior Engineer | ORD/000069/2024-2025 | 1504/BQA | 18/06/2024 | 500 | SHYAMAL KUMAR DAS | 52.47 | 11.35 | 25
1740 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of Balance 'FHTC (Functional House Hold Tap Connection') & paralal pipe line of existing 'FHTC in connection with Jal Jeevan Mission (JJM) for Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura -II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :-03 nos. Name of mouza:- Bikna (235), Kuraria (254), Katnar (255), No. of Household- 340 nos. | Assistant Engineer | Junior Engineer | ORD/000816/2022-2023 | 718/BQA | 30/03/2023 | 1098 | JAGADISH BANERJEE | 40.96 | 19.04 | 100
1741 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2023-2024 | 454/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 0.77 | 0 | 100
1742 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 11.54 | 0 | 0
1743 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | Assistant Engineer | Junior Engineer | BILL/00192/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1744 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection at Domanbandi for augmenrtation of Bikna water supply scheme (SM/17291) under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00952/2024-2025 | BP-2024-25-233 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.07 | 0 | 0
1745 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Bikna and its adjoining mouzas piped water supply scheme (JJM Revision) Block-Bankura-II Dist -Bankura under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000559/2023-2024 | 1995/BMD | 28/08/2023 | 120 | M/S NABIN GOPAL SENGUPTA | 63.49 | 47.01 | 67
1746 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Chiltor to T01 under Sarenga Block in the District of Bankura ,Vide Package No- WB-03-30, Road Length-8.08 Km. (Augmentation works for Belaitiki (Zone-B) Water Supply Soheme under Sarenga Water Supply Scheme (BRGF Ph-I).) | Assistant Engineer | Junior Engineer | BILL/01430/2024-2025 | BP/569/2024-25 | 28/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.57 | 0 | 0
1747 | Bankura Division | Khatra Sub-Division | Repair airt iillaintenance work of the Road from L049 - Parashia to SH under Sarenga Block in the District of Bankura ,Vide Package No- WB-03-305, Road Length-l.5 Km. (Augmentation works for Belaitiki (Zone-B) Waler Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01434/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.57 | 0 | 0
1748 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2024-2025 | 1493/BQA | 18/06/2024 | 30 | MESAURE LAND | 1.89 | 1.84 | 90
1749 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2025-2026 | 1293/BQA | 17/06/2025 | 184 | TAPAS KUMAR HAZRA | 14.1 | 0 | 0
1750 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 1827/BQA | 12/07/2024 | 90 | M/S TARUN KUMAR PATRA | 28.3 | 0 | 0
1751 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2023-2024 | 1965/BQA | 18/07/2023 | 270 | I.R.CONSTRUCTION | 141.73 | 38.73 | 30
1752 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000181/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.77 | 0 | 0
1753 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System & construction of one no RBTW with other allied work at Belatikari water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000194/2025-2026 | 639/BMD | 11/07/2025 | 90 | DEBJYOTI BASU | 19.49 | 0 | 0
1754 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Additional Work for Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 857/BMD | 29/08/2024 | 60 | M.S. ENTERPRISE | 1.18 | 1.18 | 100
1755 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000138/2024-2025 | 444/BMD | 27/06/2024 | 1254 | M.S. ENTERPRISE | 16.65 | 0 | 89
1756 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement , installation of new charger panel , construction of neutralization pit , supply of XLPE cables , chlorinator items for Augmentation of Belatikari Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2024-2025 | 506/BMD | 09/07/2024 | 120 | M/S SAJAHAN CHOWDHURY | 22.11 | 0 | 0
1757 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000570/2023-2024 | 2027/BMD | 01/09/2023 | 914 | M.S. ENTERPRISE | 83.1 | 73.16 | 77
1758 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline, supply of sluice valve and construction of valve chamber with all allied works under Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2025-2026 | 1308/BQA | 17/06/2025 | 183 | SUBHAJIT BANERJEE | 20.49 | 0 | 0
1759 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works for Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 1328/BQA | 17/06/2025 | 137 | UTTAM KUMAR SINHAMAHAPATRA | 21.78 | 0 | 90
1760 | Bankura Division | Khatra Sub-Division | Construction & commissioning of FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Chiltore and its adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1924/BQA | 13/07/2023 | 270 | SUBHADIP KOLEY | 104.26 | 91.65 | 100
1761 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 200 Cum., staging height 20 Mtr.), CWR, Pump House cum Chlorine Room and Construction of Boundary Wall and Guard Room with all allied works of Augmentation of Chiltore water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001979/2024-2025 | 672/BQA | 12/03/2025 | 275 | SUBHADIP KOLE | 49.61 | 0 | 0
1762 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000179/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
1763 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00207/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
1764 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries and allied works for Augmentation of Chiltore water supply scheme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 154/BMD | 30/04/2025 | 90 | DEBJYOTI BASU | 10.26 | 0 | 0
1765 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply and installation of submersible pumping machinery and Voltage Stabilizer with allied items for Augmentation for Chiltore water supply scheme under Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 515/BMD | 09/07/2024 | 530 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 15.77 | 0 | 60
1766 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Construction of one no RBTW with providing and installation of Neutralization System , installation of 1 no Submersible Pump Motor set other work at Chiltore water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 638/BMD | 11/07/2025 | 90 | GOENKA ENTERPRISE | 33.03 | 0 | 0
1767 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Augmentation works for Chiltore and its Adjoining mouzas water supply scheme under Jal Jeevan Mission programe under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000717/2023-2024 | 2174/BMD | 30/10/2023 | 850 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 62.99 | 54.24 | 80
1768 | Bankura Division | Brishnupur Sub-Division | Laying distribution system for Kushmuri Zone- B W/S Scheme (BRGF Phase-I) within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2023-2024 | 2631/BQA | 21/09/2023 | 680 | GON ASSOCIATES | 15.03 | 0 | 97
1769 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- B W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Jinkara (19), Paharpur (55), Bara Gobindapur (59), Kapcit (23), Fatepur (56) Total No. House Hold:- 190 | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 2632/BQA | 21/09/2023 | 833 | TAPAS KUMAR HAZRA | 56.51 | 33.35 | 75
1770 | Bankura Division | Brishnupur Sub-Division | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- B Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 2633/BQA | 21/09/2023 | 742 | SK FAZLUL ALAM | 13.22 | 5.06 | 95
1771 | Bankura Division | Brishnupur Sub-Division | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- B water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2023-2024 | 3017/BQA | 03/11/2023 | 606 | FARUK ALI KHAN | 8.43 | 2.72 | 15
1772 | Bankura Division | Brishnupur Sub-Division | Sinking of 3 nos. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Kushmuri Zone- B piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2023-2024 | 360/BQA | 06/02/2024 | 45 | SUBHADIP KOLE | 51.08 | 20.78 | 5
1773 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Kushmuri (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001360/2024-2025 | 3179/BQA | 24/12/2024 | 312 | DAUD ALI KHAN | 12.97 | 0 | 55
1774 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00177/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
1775 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Paharpur boosting Tw site of Karisunda water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00986/2024-2025 |  | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.08 | 0 | 0
1776 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Pratapmath ( Khusmuri Zone-B) | Assistant Engineer | Junior Engineer | BILL/01333/2024-2025 | BP-2024-25-333 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.34 | 0 | 0
1777 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000610/2023-2024 | 2084/BMD | 12/09/2023 | 1140 | GOENKA ENTERPRISE | 70.65 | 33.7 | 60
1778 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 0 1 , Sangrampur (Part-A),Total House Hold - 124 (Sl .No.-8) | Assistant Engineer | Junior Engineer | ORD/000161/2020-2021 | 707/BQA | 19/02/2021 | 30 | JAGADISH BANERJEE | 12.73 | 0 | 0
1779 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 0 1 , Sangrampur (Part-B), Total House Hold 124 (Sl .No.- 9) | Assistant Engineer | Junior Engineer | ORD/000162/2020-2021 | 708/BQA | 19/02/2021 | 30 | BEAUTY CHATTERJEE | 12.72 | 0 | 0
1780 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-0 2 , Sangrampur (Part-C),Baharkhulia(part-A), Total House Hold - 124 ( Sl .No.- 10) | Assistant Engineer | Junior Engineer | ORD/000163/2020-2021 | 709/BQA | 19/02/2021 | 30 | SUBHANKAR BANERJEE | 12.72 | 0 | 0
1781 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 ,Baharkhulia(part-B), Total House Hold - 124 ( Sl .No.- 11 ) | Assistant Engineer | Junior Engineer | ORD/000164/2020-2021 | 710/BQA | 19/02/2021 | 30 | SAIKAT CHOWDHURY | 12.72 | 0 | 0
1782 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01(Purunia ), Total House Hold - 105 ( Sl .No.- 12 ) | Assistant Engineer | Junior Engineer | ORD/000165/2020-2021 | 711/BQA | 19/02/2021 | 30 | JAGADISH BANERJEE | 10.78 | 0 | 0
1783 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 02 Laxminarayanpur & Gangadar pur ), Total House Hold - 99 ( Sl .No.- 13) | Assistant Engineer | Junior Engineer | ORD/000166/2020-2021 | 712/BQA | 19/02/2021 | 30 | SUBHANKAR BANERJEE | 10.12 | 0 | 0
1784 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) | Assistant Engineer | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 24.11 | 0
1785 | Bankura Division | Bankura Sadar Sub-Division | Laying distribution system of UPVC pipe line with allied works from Near Bharakhullya air valve to BharakhullyaVillage (Purba Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000330/2021-2022 | 760/ BSD | 26/07/2021 | 15 | ZAKIR HOSSAIN MONDAL | 3.6 | 0 | 0
1786 | Bankura Division | Bankura Sadar Sub-Division | Laying distribution system of UPVC pipe line with allied works at BharakhullyaVillage (Paschim Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000331/2021-2022 | 761/ BSD | 26/07/2021 | 15 | ZAKIR HOSSAIN MONDAL | 3 | 0 | 0
1787 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at talanjuri petrol pump to Talanjuri Pry School of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14) | Assistant Engineer | Junior Engineer | VCH/000884/2021-2022 |  | 08/09/2021 | 0 | SUBHANKAR BANERJEE | 4.53 | 0 | 0
1788 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at talanjuri petrol pump to Talanjuri Pry School to Kendrobedia of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14) | Assistant Engineer | Junior Engineer | VCH/000895/2021-2022 |  | 08/09/2021 | 0 | SUBHANKAR BANERJEE | 2.77 | 0 | 0
1789 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at Sangrampur to purnia village of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14) | Assistant Engineer | Junior Engineer | VCH/000899/2021-2022 |  | 08/09/2021 | 0 | SUBHANKAR BANERJEE | 4.76 | 0 | 0
1790 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Maliara (Zone - A). No.of Mouza :- 01, Kuldiha, Total House Hold -233 | Assistant Engineer | Junior Engineer | VCH/001150/2021-2022 | FHTC/23 | 23/07/2021 | 0 | TAPAS PAL | 16.99 | 0 | 0
1791 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. | Assistant Engineer | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
1792 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0
1793 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) | Assistant Engineer | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
1794 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
1795 | Bankura Division | Bankura Mechanical Sub-Division | Repair and Maintenance work of the Road from L032-Dhuliapur to Kusmi under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-760, Road Length-2.5 Km.(Augmentation of water supply scheme for Baricha (Zone - A) Under Simlapal W/S Scheme.( BRGF Ph-I) | Assistant Engineer |  | BILL/01431/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.15 | 0 | 0
1796 | Bankura Division | Bankura Mechanical Sub-Division | Repair and Maintenance work of the Road from L033 - Hariharpur to Lakshmanpur under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-401, Road Length-2.581 Km. (Augmentation of water supply scheme for Baricha (Zone-A) under Simlapal water supply scheme (BRGF Ph-I). | Assistant Engineer |  | BILL/01435/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0
1797 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000406/2023-2024 | 2091/BQA | 27/07/2023 | 615 | PARAMESWAR CHOWDHURY | 197.38 | 45.89 | 27
1798 | Bankura Division | Bankura Mechanical Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000830/2023-2024 | 2956/BQA | 31/10/2023 | 30 | GEO SOLUTION | 3.28 | 3.21 | 97
1799 | Bankura Division | Bankura Mechanical Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Baricha, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001968/2024-2025 | 664/BQA | 12/03/2025 | 234 | UTTAM KUMAR SINHAMAHAPATRA | 18.76 | 0 | 90
1800 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000185/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.45 | 0 | 0
1801 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement for Augmentation for Baricha Zone -A water supply scheme under Baricha water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer |  | ORD/000331/2024-2025 | 868/BMD | 29/08/2024 | 120 | M/S TARUN KUMAR PATRA | 4.84 | 0 | 0
1802 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Boricha Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer |  | ORD/000572/2023-2024 | 2028/BMD | 01/09/2023 | 1080 | S.P. CONSTRUCTION | 96.37 | 78.56 | 80
1803 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room, Boundary Wall and Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Dhemusunya Zone-IV Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2025-2026 | 1290/BQA | 17/06/2025 | 184 | UTTAM KUMAR SINHAMAHAPATRA | 37.99 | 0 | 0
1804 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Dhemusunya under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2024-2025 | 2097/BQA | 05/08/2024 | 239 | M/S SUPRIYA CHATTERJEE | 48.19 | 0.57 | 70
1805 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Dhemusunya under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2024-2025 | 2096/BQA | 05/08/2024 | 421 | ASHOK KUMAR DEY | 48.19 | 0 | 20
1806 | Bankura Division | Khatra Sub-Division | Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Dhemushunya (Zone-IV) and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 2783/BQA | 09/10/2023 | 815 | EARTH MOVING (INDIA) | 155.4 | 43.18 | 41
1807 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000837/2023-2024 | 2963/BQA | 31/10/2023 | 30 | MEASURE LAND | 1.49 | 1.48 | 99
1808 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000192/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.77 | 0 | 0
1809 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00208/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
1810 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Dhemusunia (Zone IV) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000879/2024-2025 | 2039/BMD | 07/03/2025 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 95.37 | 0 | 10
1811 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Miscellaneous work for Gaseous Chlorination System at Head work site for Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division PHE Dte, | Assistant Engineer | Junior Engineer | ORD/001096/2023-2024 | 3071/BMD | 12/03/2024 | 600 | EASTERN INDIA SALES & SERVICE | 14.32 | 13.41 | 80
1812 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 226.27 | 6
1813 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000088/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 114.03 | 0 | 0
1814 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Khiri W/ S schme | Assistant Engineer | Junior Engineer | BILL/00418/2024-2025 | BP-2024-25-94 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
1815 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Khiri W/S scheme | Assistant Engineer | Junior Engineer | BILL/00419/2024-2025 | BP-2024-25-95 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.88 | 0 | 0
1816 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Khiri Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000147/2025-2026 | 442/BMD | 10/06/2025 | 90 | RAJIB COMPANY | 11.88 | 0 | 0
1817 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 115.31 | 6
1818 | Bankura Division | Brishnupur Sub-Division | Supply, delivery, installation of PVC flex containing information of schemes of JJM within Bishnupur & Kotulpur Blocks under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001774/2024-2025 | 463/VSD | 16/08/2024 | 10 | PARTHA ROY | 1.96 | 0 | 0
1819 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Laugram Piped Water Supply Scheme (SM/18438), 2 nos. sites of Karak Berya Piped Water Supply Scheme (SM/14247) & 2 nos. sites of Patrabandh Piped Water Supply Scheme (SM/14012) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001880/2024-2025 | 558/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 100
1820 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000062/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 174.1 | 0 | 0
1821 | Bankura Mechanical | Brishnupur Sub-Division | New service connection of P/H-II of Lowgram W/S scheme | Assistant Engineer | Junior Engineer | BILL/00523/2024-2025 | BP-2024-25-140 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.52 | 0 | 0
1822 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Laugram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000145/2025-2026 | 440/BMD | 10/06/2025 | 90 | INDRAJIT MITRA | 12.37 | 0 | 0
1823 | Bankura Division | RWS Bankura Sub-Division | single phase connection of Banpakuria village under Manbazar CCC |  | Junior Engineer | BILL/00031/2024-2025 | FHTC/04 | 23/04/2024 | 0 | MANBAZAR CCC | 0.12 | 0 | 0
1824 | Bankura Division | RWS Bankura Sub-Division | New service connection for "Banpukhuria" Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00077/2024-2025 |  | 29/04/2024 | 0 | MANBAZAR CCC | 0.12 | 0 | 0
1825 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1826 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1827 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
1828 | Bankura Division | Bankura Sadar Sub-Division | Bmsd Phe Vill- Banagram, P.O-Chhatna | Assistant Engineer | Junior Engineer | BILL/00023/2023-2024 | FHTC/06 | 05/06/2023 | 0 | CHHATNA CCC | 0.12 | 0 | 0
1829 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1830 | Bankura Division | Bankura Sadar Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10915. | Assistant Engineer | Junior Engineer | BILL/00774/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1831 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1832 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
1833 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line from Banpusra to Kalaibad to increase pressure in Kalaibad mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2022-2023 | 1322/BQA | 15/06/2022 | 15 | ASHOKE KUMAR DEY | 4.66 | 4.66 | 0
1834 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Panjanpahari mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000230/2022-2023 | 1327/BQA | 15/06/2022 | 15 | SUMITA UPADHYAY | 2.98 | 2.98 | 0
1835 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Danmari mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000231/2022-2023 | 1307/BQA | 15/06/2022 | 15 | SUMITA UPADHYAY | 4.23 | 4.23 | 0
1836 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Saparda, Tisra, Nuniadihi, Lorri mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000232/2022-2023 | 1312/BQA | 15/06/2022 | 15 | SUMITA UPADHYAY | 4.56 | 4.56 | 0
1837 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Lorri mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000233/2022-2023 | 1311/BQA | 15/06/2022 | 15 | SUMITA UPADHYAY | 4.88 | 4.87 | 0
1838 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No. of Mouza :- 17 nos, (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathanbera, Danmari, Kadra, Nisehintapur, Laxmanpur, Shunri Chitra, Lari, Nuniadihi, Panjanpahari, Sarenga Phulberia, Jagannathpur Total House Hold - 1984 nos. | Assistant Engineer | Junior Engineer | ORD/000307/2021-2022 | 3372/BQA | 31/12/2021 | 60 | SWAPAN KUMAR UPADHYAY | 100.48 | 100.48 | 0
1839 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line from Kalaibad to Tisra to increase pressure in Tisra mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2022-2023 | 1323/BQA | 15/06/2022 | 15 | GOURANGA CHATTERJEE | 4.46 | 4.3 | 0
1840 | Bankura Division | Bankura Sadar Sub-Division | Laying of UPVC pipe line from Surichitra to Nuniadihi & Panjongora due to damage by PMGSY Road of LAKSHMANPUR (ZONE- L) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project)under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. Saltora Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. (Under JJM / Jal Swapna Fund) | Assistant Engineer | Junior Engineer | ORD/000608/2021-2022 | 887/BSD | 08/09/2021 | 15 | MAA USHA CONSTRUCTION | 3.77 | 3.77 | 0
1841 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No.of Mouza :- 17 nos, (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathanbera, Danmari, Kadra, (Nisehintapur, Laxmanpur, Shunri Chitra, Lari, Nuniadihi, Panjanpahari, Sarenga Phulberia, Jagannathpur) Total House Hold - 1984 nos. | Assistant Engineer | Junior Engineer | ORD/000877/2021-2022 | 73/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.66 | 0.66 | 0
1842 | Bankura Division | Bankura Sadar Sub-Division | Saltora-Murulia Road from Ch. 7.700 km to 9.500 km, Permanent Restoration of road for the purpose of "Laying of pipeline from Udaypur village to Ituri village on main road of Saltora-Madhukunda Road under Udaypur (Zone-B) water supply scheme." under Bankura Highway Division in the district of Bankura. | Assistant Engineer | Junior Engineer | BILL/00086/2025-2026 |  | 09/04/2025 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 12.56 | 0 | 0
1843 | Bankura Division | Bankura Sadar Sub-Division | Saltora-Mejia Road from Ch 2.50 km to Ch. 7.00 km (In stretches)- Permanent restoration of road for the purpose of repairing the existing water supply pipeline by PHE Department under Bankura Highway Division in the district Bankura. | Assistant Engineer | Junior Engineer | BILL/01925/2024-2025 | BP/567/2024-25 | 29/03/2025 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 2.84 | 0 | 0
1844 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Udaypur (Zone- B) of Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 1496/BQA | 18/06/2024 | 30 | MESAURE LAND | 2.52 | 0 | 80
1845 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection) & Laying of balance distribution system of pipeline with allied works for Augmentation of Ranjitpur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, P.H.E. Dte. Block - Saltora, Name of OHR - Ranjitpur, Total House Hold - 150 nos | Assistant Engineer | Junior Engineer | ORD/000160/2025-2026 | 1301/BQA | 17/06/2025 | 45 | GOURANGA NANDI | 28.74 | 0 | 0
1846 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Ranjitpur (Zone- C) of Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2024-2025 | 2437/BQA | 25/09/2024 | 30 | CARTO | 2.21 | 0 | 80
1847 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Tilabaid (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 2339/BQA | 14/08/2023 | 270 | PARTHA PRATIM CHHATAIT | 213.98 | 0 | 0
1848 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Monipur (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000488/2023-2024 | 2340/BQA | 14/08/2023 | 270 | PARTHA PRATIM CHHATAIT | 142.05 | 0 | 0
1849 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Pabra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 153/BMD | 30/04/2025 | 90 | M/S DAS AND SARKAR ENTERPRISE | 9.72 | 0 | 0
1850 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Udaypur (Zone - B) & Routora (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000489/2023-2024 | 2341/BQA | 14/08/2023 | 270 | PARTHA PRATIM CHHATAIT | 164.04 | 35.08 | 22
1851 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte.Block - Saltora, Name of OHR - Shyampur, Total House Hold -400 nos. | Assistant Engineer | Junior Engineer | ORD/000686/2022-2023 | 587/BQA | 20/03/2023 | 1013 | PRADYUMNA KOLEY | 90.36 | 0 | 68
1852 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Manipur (Zone-D) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 2976/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.09 | 1.84 | 100
1853 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Chinabari (Zone-H) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000851/2023-2024 | 2977/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.09 | 0 | 0
1854 | Bankura Division | Bankura Sadar Sub-Division | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at different work sites at Ranagora (147), Kanki (150), Bandayagal (156), Bindajam (157) & Khudrabanagram (159) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001057/2023-2024 | 1173/BSD | 22/11/2023 | 15 | TAPAS DEY | 0.69 | 0.68 | 100
1855 | Bankura Division | Bankura Sadar Sub-Division | Crossing PWD Road by different dia MS pipe by trench less Technologies i.e Jack Pushing method with MS Carrier pipe and all alled works at Chandra More of HORAKA (Zone - G) under Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001395/2024-2025 | 42/BQA | 02/01/2025 | 45 | PARAMESWAR CHOWDHURY | 4.65 | 0 | 0
1856 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at clear water pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1408/BMD | 18/07/2023 | 420 | ORIENTAL ENGINEERING CO. | 216.67 | 206.36 | 95
1857 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of VT pumps at Intake pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1409/BMD | 18/07/2023 | 60 | ORIENTAL ENGINEERING CO. | 110.62 | 105.21 | 95
1858 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on delivery line at Intake and clear water pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000611/2023-2024 | 2085/BMD | 12/09/2023 | 300 | M/S NABIN GOPAL SENGUPTA | 48.09 | 45.89 | 97
1859 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Dashere, lowgram, , Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00267/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
1860 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1861 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1862 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at DASHERE | Assistant Engineer | Junior Engineer | BILL/01268/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
1863 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
1864 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Chanpatala site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00182/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
1865 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1866 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1867 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
1868 | Bankura Division | RWS Bankura Sub-Division | single phase connection of Sabubaid village under Khatra CCC |  | Junior Engineer | BILL/00032/2024-2025 | FHTC/04 | 29/04/2024 | 0 | KHATRA CCC | 0.12 | 0 | 0
1869 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1870 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1871 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32.5 | 48
1872 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1873 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Dakshin Kendbona,Hatgram | Assistant Engineer | Junior Engineer | BILL/00514/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
1874 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1875 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
1876 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1877 | Bankura Division | Brishnupur Sub-Division | New connection of Mahamaya (colony) J1-III Plot no-4006, Indus Block PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00839/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDUS CCC | 0.12 | 0 | 0
1878 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1879 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 37 | 48
1880 | Bankura Division | Bankura Sadar Sub-Division | Extra house hold connection of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte.)Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 01 no., (Pakhanna Pratap pur), Total House Hold - 45 nos | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 529/BSD | 28/07/2022 | 21 | UTTAM KUMAR SINHAMAHAPATRA | 4.97 | 4.97 | 0
1881 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 02 nos, (Tajpur, Shitalpur), Total House Hold - 541 nos. | Assistant Engineer | Junior Engineer | ORD/000161/2021-2022 | 2839/BQA | 16/11/2021 | 30 | ZAKIR HOSSAIN MONDAL | 30.54 | 21 | 30
1882 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 02 no., (Pakhanna Bharabpur, Palasbani), Total House Hold - 472 nos | Assistant Engineer | Junior Engineer | ORD/000162/2021-2022 | 2840/BQA | 16/11/2021 | 30 | NAYAN BARDHAN | 26.92 | 8.61 | 0
1883 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 01 no., (Radhakantapur), Total House Hold - 463 nos | Assistant Engineer | Junior Engineer | ORD/000166/2021-2022 | 2841/BQA | 16/11/2021 | 30 | GANESH ROY | 26.61 | 0 | 0
1884 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 09 nos, (Kamalpur, Gopalpur), Total House Hold - 381 nos | Assistant Engineer | Junior Engineer | ORD/000167/2021-2022 | 2842/BQA | 16/11/2021 | 30 | BIJOY KOLEY | 22.62 | 0 | 0
1885 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 01 no., (Pakhanna Pratap pur), Total House Hold - 402 nos | Assistant Engineer | Junior Engineer | ORD/000168/2021-2022 | 2843/BQA | 16/11/2021 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 24.1 | 0 | 0
1886 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 01 no., (Pakhnna), Total House Hold - 847 nos | Assistant Engineer | Junior Engineer | ORD/000169/2021-2022 | 2844/BQA | 16/11/2021 | 30 | SOUMITRA BHATTACHARYA | 48.49 | 39.79 | 0
1887 | Bankura Division | Bankura Sadar Sub-Division | Extra house hold connection of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 01 no., (Pakhanna Pratap pur), Total House Hold - 45 nos | Assistant Engineer | Junior Engineer | ORD/000210/2022-2023 | 529/BSD | 28/07/2022 | 21 | UTTAM KUMAR SINHAMAHAPATRA | 4.97 | 0 | 25
1888 | Bankura Division | Bankura Sadar Sub-Division | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 45 | NAYAN BARDHAN | 49.26 | 24.83 | 0
1889 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000284/2021-2022 | 880/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.75 | 0 | 0
1890 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000285/2021-2022 | 881/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.78 | 0 | 0
1891 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000286/2021-2022 | 882/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.82 | 0 | 0
1892 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000287/2021-2022 | 883/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 3.63 | 0 | 0
1893 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line near Tajpur, Rampur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000288/2021-2022 | 888/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
1894 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Tajpur, Rampur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000289/2021-2022 | 889/ BSD | 08/09/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.84 | 0 | 0
1895 | Bankura Division | Bankura Sadar Sub-Division | Bypass pipe line arrangement at Pakhanna Head Work site from OHR rising main to Main distribution pipe line and relaying of pipe line form Tajpur more to Tajpur village by HDPE pipe of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) | Assistant Engineer | Junior Engineer | ORD/000361/2022-2023 | 534/BSD | 28/07/2022 | 21 | ZAKIR HOSSAIN MONDAL | 4.04 | 4.01 | 0
1896 | Bankura Division | Bankura Sadar Sub-Division | Repering of Concrete drain ,Slab & concrete road due to damage of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, Mouza :- Pakhnna | Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 579/BQA | 17/03/2023 | 30 | MANAS DEY | 14.97 | 0 | 0
1897 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Radhakantapur mouza of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 539/BSD | 28/07/2022 | 21 | GANESH ROY | 4.95 | 0 | 0
1898 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 02 no., (Pakhanna Bharabpur, Palasbani), Total House Hold - 472 nos | Assistant Engineer | Junior Engineer | VCH/000229/2022-2023 | FHTC/11 | 11/04/2022 | 0 | NAYAN BARDHAN | 18.3 | 0 | 0
1899 | Bankura Division | Bankura Sadar Sub-Division | Survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme . No.of Mouza :-09 nos, (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, Palasbani, Shitalpur), Total House Hold - 3106 nos. | Assistant Engineer | Junior Engineer | VCH/000250/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.88 | 0 | 0
1900 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
1901 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
1902 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002647/2021-2022 | FHTC/10 | 10/02/2022 | 0 | GOUTAM BHATTACHRYYA | 13.52 | 0 | 0
1903 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover kherosol, Bhedua Purusatampur, narrah, gopinathpur, emukundi mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002648/2021-2022 | FHTC/10 | 10/02/2022 | 0 | BHATTACHARYYA ENTERPRISE | 2.56 | 0 | 0
1904 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-B), Total House Hold -264 | Assistant Engineer | Junior Engineer | VCH/002649/2021-2022 | FHTC/10 | 10/02/2022 | 0 | ASOKE BHATTACHARYYA | 20.38 | 0 | 0
1905 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Pakhuria (18) & Khayer Kundi (19) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | VCH/002650/2021-2022 | FHTC/10 | 10/02/2022 | 0 | DEBAKI RANJAN SARKAR | 4.07 | 0 | 0
1906 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Pakhuria (18) & Khayer Kundi (19) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | VCH/002651/2021-2022 | FHTC/10 | 10/02/2022 | 0 | DEBAKI RANJAN SARKAR | 3.05 | 0 | 0
1907 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-4) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Harinagar-23 (116 out of 336),Dharampur-22 (84 out of 299),Shaluka - 21(13 out of 125), Khazra -37(1 out of 1)House Hold - 214 | Assistant Engineer | Junior Engineer | VCH/002652/2021-2022 | FHTC/10 | 10/02/2022 | 0 | M/S SACHHIDANANDA MAZUMDAR | 16.57 | 0 | 0
1908 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | VCH/002653/2021-2022 | FHTC/10 | 10/02/2022 | 0 | GANESH ROY | 2.9 | 0 | 0
1909 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-C) , Total House Hold -175 | Assistant Engineer | Junior Engineer | VCH/002654/2021-2022 | FHTC/10 | 10/02/2022 | 0 | DAUD ALI KHAN | 1.3 | 0 | 0
1910 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gobarda (152) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002655/2021-2022 | FHTC/10 | 10/02/2022 | 0 | SUBHENDU SEKHAR GORAI | 1.21 | 0 | 0
1911 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Palsona more to Ramchandrapur High School under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Palsona & Ramchandrapur | Assistant Engineer | Junior Engineer | VCH/002656/2021-2022 | FHTC/10 | 10/02/2022 | 0 | RUFIKUL MONDAL | 4.8 | 0 | 0
1912 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No.of Mouza :- 02 no., (Pakhanna Bharabpur, Palasbani), Total House Hold - 472 nos | Assistant Engineer | Junior Engineer | VCH/002881/2021-2022 |  | 16/03/2022 | 0 | NAYAN BARDHAN | 18.3 | 0 | 0
1913 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
1914 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
1915 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Indara. | Assistant Engineer | Junior Engineer | BILL/01574/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.9 | 0 | 0
1916 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
1917 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Namonahar), Total House Hold -413 |  | Junior Engineer | ORD/000216/2020-2021 | 2033/BQA | 29/12/2020 | 30 | ASHISH KUMAR SAMANTA | 41.33 | 0 | 0
1918 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 06(Narricha, Bhabanipur, Baliguma, Sapkrrara, Unara & Dharampu) Total House Hold -404 |  | Junior Engineer | ORD/000219/2020-2021 | 2034/BQA | 29/12/2020 | 30 | ASHOKE BHATTACHARYYA | 40.43 | 0 | 0
1919 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 |  | Junior Engineer | ORD/000221/2020-2021 | 2035/BQA | 29/12/2020 | 30 | TAPAN KUMAR SARKAR | 11.41 | 0 | 0
1920 | Bankura Division | Bankura Sadar Sub-Division | Extra retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) & Special repering of existing UPVC pipe line damaged due to higher dia pipe line laying at Enayatpur Singh para of KANCHANPUR (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000284/2023-2024 | 530/BSD | 12/06/2023 | 7 | SUBHADIP KOLEY | 0.95 | 0 | 100
1921 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.56 | 0
1922 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Indas W/S Scheme under Bishnupur Sub-Division, PHE Dte. |  | Junior Engineer | VCH/001559/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SWAPAN KUMAR DE | 6.15 | 0 | 0
1923 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying by UPVC pipe for distribution network along with ancillary works at village karbhanga due to strengthening widening of Sarenga Chowrasta more to Goaltore Road under Gargaria Zone -B water supply scheme (BRGF phase -I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. sl no - 13 |  | Junior Engineer | VCH/001502/2021-2022 | FHTC/23 | 23/11/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.95 | 0 | 0
1924 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jamda (98) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15), |  | Junior Engineer | VCH/001552/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ASOKE KUMAR SAHU | 1.61 | 0 | 0
1925 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Tentulia (27) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001553/2021-2022 | FHTC/11 | 11/10/2021 | 0 | GOURANGA CHATTERJEE | 2.17 | 0 | 0
1926 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhadkidihi (92) and Puada (94) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 222 Nos. , |  | Junior Engineer | VCH/001554/2021-2022 | FHTC/11 | 11/10/2021 | 0 | BEAUTY CHATTERJEE | 12.84 | 0 | 0
1927 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KOTALPUKUR (Zone - B)) . Name.of Mouza :- 01 no., Rajprasadpur (Part), |  | Junior Engineer | VCH/001555/2021-2022 | FHTC/11 | 11/10/2021 | 0 | RANABIR CHATTERJEE | 4.78 | 0 | 0
1928 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover malindasi mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI(P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  | Junior Engineer | VCH/001556/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SOUMITRA BHATTACHARYA | 4.81 | 0 | 0
1929 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Sonareka (Part), Total House Hold- 70 (Sl No of Work- 09) |  | Junior Engineer | VCH/001557/2021-2022 | FHTC/11 | 11/10/2021 | 0 | MD. AFSAR ALI | 0.59 | 0 | 0
1930 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover malindasi mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joukrishnapur zone - l under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  | Junior Engineer | VCH/001558/2021-2022 | FHTC/11 | 11/10/2021 | 0 | RUFIKUL MONDAL | 4.65 | 0 | 0
1931 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
1932 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 |  | Junior Engineer | VCH/001620/2020-2021 |  | 15/03/2021 | 0 | TAPAN KUMAR SARKAR | 10.23 | 0 | 0
1933 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  | Junior Engineer | VCH/002288/2021-2022 | FHTC/31 | 31/01/2022 | 0 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0
1934 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506' |  | Junior Engineer | VCH/002749/2021-2022 | FHTC/3 | 03/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 3.89 | 0 | 0
1935 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | VCH/002812/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 0.27 | 0 | 0
1936 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002813/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 0.25 | 0 | 0
1937 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) |  | Junior Engineer | VCH/002814/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 0.28 | 0 | 0
1938 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) |  | Junior Engineer | ORD/000175/2020-2021 | 718/BQA | 19/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.42 | 44.09 | 0
1939 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | ORD/000292/2021-2022 | 954/ BSD | 05/10/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.72 | 0 | 0
1940 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | ORD/000293/2021-2022 | 955/ BSD | 05/10/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.1 | 0 | 0
1941 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART-A) |  | Junior Engineer | ORD/000295/2021-2022 | 843/ BSD | 18/08/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.84 | 0 | 0
1942 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART- B) |  | Junior Engineer | ORD/000296/2021-2022 | 844/ BSD | 18/08/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.79 | 0 | 0
1943 | Bankura Division | Bankura Sadar Sub-Division | Laying extra upvc pipe line to cover Dhapal & laxman pur for retrofittimg works for creation of FHTC OF Tilabad (Zone -F) OF Saltora Block under Saltora -Chhatna w/s scheme |  | Junior Engineer | VCH/002681/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SANDHYA DEY | 4.97 | 0 | 0
1944 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos |  | Junior Engineer | VCH/000268/2022-2023 | FHTC/18 | 18/04/2022 | 0 | RANABIR CHATTERJEE | 25.21 | 0 | 0
1945 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), Total House Hold -972 |  | Junior Engineer | VCH/002305/2021-2022 | FHTC/04 | 04/01/2022 | 0 | M/S TARUN KUMAR PATRA | 73.08 | 0 | 0
1946 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
1947 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jaynagar (47) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - B |  | Junior Engineer | VCH/002682/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S TARUN KUMAR PATRA | 2.74 | 0 | 0
1948 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) |  | Junior Engineer | VCH/002815/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 3.53 | 0 | 0
1949 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Guniada (1) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2020-2021 | 188/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 27.87 | 3.5 | 90
1950 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chalka (2), Chatanibaid (3) & Bangopalpur (4) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2020-2021 | 189/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 28.14 | 1.21 | 100
1951 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Guniada (1), Chalka (2), Chatanibaid (3), Bangopalpur (4) & Harirampur (6) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000517/2020-2021 | 315/KSD | 29/12/2020 | 61 | ASOKE KUMAR SAHU | 0.27 | 0 | 0
1952 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 125 |  | Junior Engineer | ORD/000008/2020-2021 | 609/BQA | 10/02/2021 | 30 | OSMAN SEKH | 8.39 | 10.06 | 0
1953 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000352/2020-2021 | 1777/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 36.98 | 1.64 | 0
1954 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 31) |  | Junior Engineer | ORD/000534/2020-2021 | 273/KSD | 10/12/2020 | 62 | GOPAL CHANDRA CHOWDHURY | 0.18 | 0 | 0
1955 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001415/2020-2021 |  | 01/03/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 35.29 | 0 | 0
1956 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 135 |  | Junior Engineer | ORD/000015/2020-2021 | 616/BQA | 10/02/2021 | 30 | MRITYUNJOY HAZRA | 9.84 | 12.07 | 0
1957 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Jamdoba, Ramgora, Harokabedya (Part), Palsora (Part) Total House Hold - 210. |  | Junior Engineer | ORD/000069/2020-2021 | 472/BQA | 05/02/2021 | 30 | NAYAN BARDHAN | 15.27 | 26.01 | 10
1958 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Magra mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000215/2021-2022 | 851/BSD | 18/08/2021 | 15 | SK. SAHAJAHAN | 4.15 | 0 | 0
1959 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03, Bhangaria, Magra , Sonadaha(part), Total House Hold -138" |  | Junior Engineer | ORD/000334/2020-2021 | 1703/BQA | 08/12/2020 | 30 | TAPAN KUMAR UPADHYAY | 9.75 | 0 | 100
1960 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Sonadaha(part), Total House Hold -137" |  | Junior Engineer | ORD/000335/2020-2021 | 1704/BQA | 08/12/2020 | 30 | TARINI CHARAN UPADHYAY | 9.72 | 0 | 0
1961 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Bankati Zone - R of Bankura - I, II & Barjora Water Supply Scheme (BRGF Ph-I) Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001986/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
1962 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-IV )Total House Hold - 139." |  | Junior Engineer | ORD/000336/2020-2021 | 1705/BQA | 08/12/2020 | 30 | SUDAM KUMAR DAS | 9.89 | 0 | 0
1963 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-III )Total House Hold - 139." |  | Junior Engineer | ORD/000337/2020-2021 | 1706/BQA | 08/12/2020 | 30 | SK. SAHAJAHAN | 9.91 | 0 | 100
1964 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-II )Total House Hold - 139." |  | Junior Engineer | ORD/000338/2020-2021 | 1707/BQA | 08/12/2020 | 30 | TAPAN KUMAR UPADHYAY | 9.91 | 0 | 100
1965 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-I )Total House Hold - 139." |  | Junior Engineer | ORD/000339/2020-2021 | 1708/BQA | 08/12/2020 | 30 | SK. SAHAJAHAN | 9.9 | 0 | 100
1966 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe Line to Cover Vangahira Napit Para mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000340/2021-2022 | 878/ BSD | 08/09/2021 | 15 | TARINI CHARAN UPADHYAY | 4.21 | 0 | 0
1967 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe Line to Cover Vangahira mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000341/2021-2022 | 879/ BSD | 08/09/2021 | 15 | TAPAN KUMAR UPADHYAY | 4.88 | 0 | 0
1968 | Bankura Division | Bankura Sadar Sub-Division | Survey work of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03 nos, (Bhangaria, Magra & Sonadaha), Total House Hold - 831. |  | Junior Engineer | VCH/001340/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.26 | 0 | 0
1969 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Sonadaha, Magra, Vangahira mouzs for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001348/2021-2022 |  | 28/09/2021 | 0 | ASHIS PAL | 4.65 | 0 | 0
1970 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , Total House Hold - 829." |  | Junior Engineer | VCH/001409/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.26 | 0 | 0
1971 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-III )Total House Hold - 139. |  | Junior Engineer | VCH/001416/2020-2021 |  | 01/03/2021 | 0 | TAPAN KUMAR UPADHYAY | 7.51 | 0 | 0
1972 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Sonadaha(part), Total House Hold -137 |  | Junior Engineer | VCH/001417/2020-2021 |  | 01/03/2021 | 0 | TARINI CHARAN UPADHYAY | 7.4 | 0 | 0
1973 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03, Bhangaria, Magra , Sonadaha(part), Total House Hold -138 ( MB No - 4041)" |  | Junior Engineer | VCH/001426/2020-2021 |  | 01/03/2021 | 0 | TAPAN KUMAR UPADHYAY | 7.6 | 0 | 0
1974 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
1975 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001988/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
1976 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001991/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
1977 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
1978 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000292/2020-2021 | 1415/BQA | 09/10/2020 | 30 | EARTHMOVING (INDIA) | 34.31 | 0 | 80
1979 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000293/2020-2021 | 1416/BQA | 09/10/2020 | 30 | EARTHMOVING (INDIA) | 37.66 | 0 | 20
1980 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273), Benasuli (275), Phulberia (278) & Dhanara (279) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 32) | Assistant Engineer | Junior Engineer | ORD/000535/2020-2021 | 274/KSD | 10/12/2020 | 62 | EARTH MOVING (INDIA) | 0.31 | 0 | 0
1981 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 65 | Assistant Engineer | Junior Engineer | VCH/000232/2021-2022 | FHTC/06 | 23/04/2021 | 0 | MOHAN KUMAR ROY | 4.73 | 0 | 0
1982 | Bankura Division | Khatra Sub-Division | Laying extra upvc pipe line to cover Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273), Benasuli (275), Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura Under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001097/2021-2022 |  | 21/09/2021 | 0 | UNITED TRADERS | 4.95 | 0 | 0
1983 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001431/2020-2021 |  | 01/03/2021 | 0 | EARTHMOVING (INDIA) | 31.31 | 0 | 0
1984 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10), | Assistant Engineer | Junior Engineer | VCH/001546/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRADYUMNA KOLEY | 3.1 | 0 | 0
1985 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Khandarani (155) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No. 03), | Assistant Engineer | Junior Engineer | VCH/001547/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SUBHADIP KOLEY | 4.85 | 0 | 0
1986 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabast ( MB No - 3998)" | Assistant Engineer | Junior Engineer | VCH/001560/2020-2021 | FHTC/283 | 22/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 33.92 | 0 | 0
1987 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2020-2021 | 1772/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 23.94 | 1.8 | 20
1988 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2020-2021 | 1773/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 17.57 | 0.56 | 20
1989 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sinyajora (32), Bhelaidiha (36) & Korkhi (37) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2020-2021 | 1771/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 13.16 | 0.2 | 20
1990 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.06 | 0
1991 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000451/2020-2021 | 115/KSD | 11/02/2021 | 10 | M/S TARUN KUMAR PATRA | 3.87 | 0 | 0
1992 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Sinyajora (32), Bhelaidiha (36), Korkhi (37), Shyampur (44), Jugidangra (47), Rasikpur (48) & Sarenga (50) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 37) | Assistant Engineer | Junior Engineer | ORD/000540/2020-2021 | 280/KSD | 10/12/2020 | 62 | M/S TARUN KUMAR PATRA | 0.26 | 0 | 0
1993 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover in Sinyajora (32) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -A) (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000676/2021-2022 | 672/KSD | 29/09/2021 | 15 | M/S TARUN KUMAR PATRA | 4.27 | 0 | 0
1994 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover in Sinyajora (32) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000677/2021-2022 | 673/KSD | 29/09/2021 | 15 | M/S TARUN KUMAR PATRA | 2.13 | 0 | 0
1995 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Beliatore W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR:- Murakata Ghosh Para , Total H.Hold-75 ( Sl.No-07) | Assistant Engineer | Junior Engineer | VCH/000254/2021-2022 | FHTC/12 | 23/04/2021 | 0 | SOMA BANERJEE | 4.5 | 0 | 0
1996 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Beliatore W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of Village-Lobason Bauri Para Total House Hold - 76. | Assistant Engineer | Junior Engineer | VCH/000255/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS PAL | 4.49 | 0 | 0
1997 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Beliatore Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of Village :- Chandar Bardgan para Part -A Total House Hold - 50. ( Sl.No-09) | Assistant Engineer | Junior Engineer | VCH/000256/2021-2022 | FHTC/12 | 23/04/2021 | 0 | MAYA CONSTRUCTION | 4.11 | 0 | 0
1998 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Beliatore W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of Village- Labason Roypara Total House Hold - 73. | Assistant Engineer | Junior Engineer | VCH/000258/2021-2022 | FHTC/12 | 23/04/2021 | 0 | M/S BANERJEE & BANERJEE | 4.27 | 0 | 0
1999 | Bankura Division | Khatra Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Harialgora , No Of Mouzas-01 Nos ( Junbedia) Total House Hold -881, | Assistant Engineer | Junior Engineer | VCH/000275/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
2000 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sinyajora (32), Bhelaidiha (36) & Korkhi (37) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001383/2020-2021 |  | 01/03/2021 | 0 | M/S TARUN KUMAR PATRA | 12.57 | 0 | 0
2001 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001384/2020-2021 |  | 01/03/2021 | 0 | M/S TARUN KUMAR PATRA | 8.76 | 0 | 0
2002 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001385/2020-2021 |  | 01/03/2021 | 0 | M/S TARUN KUMAR PATRA | 21.59 | 0 | 0
2003 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jarisa (89) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2020-2021 | 1424/BQA | 09/10/2020 | 30 | GOUTAM BHATTACHRYYA | 43.67 | 0 | 0
2004 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gotkanali (45), Bankhola (54) & Harinyaguri (90) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2020-2021 | 1425/BQA | 09/10/2020 | 30 | APEX ENTERPRISE | 28.04 | 3.81 | 0
2005 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Jarisa (89) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000452/2020-2021 | 116/KSD | 11/02/2021 | 10 | BHATTACHARIYA CONSTRUCTION | 2.24 | 0 | 0
2006 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Household survey in Gotkanali (45), Bankhola (54), Jarisa (89) & Harinyaguri (90) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 38) | Assistant Engineer | Junior Engineer | ORD/001039/2020-2021 | 280 /KSD | 10/12/2020 | 62 | APEX ENTERPRISE | 0.35 | 0.35 | 0
2007 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Jarisa (89) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000668/2021-2022 |  | 16/07/2021 | 0 | GOUTAM BHATTACHRYYA | 2.19 | 0 | 0
2008 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. | Assistant Engineer | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
2009 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Gaira, Arjunpur, Pairasol, & Bahadurpur.) Total House Hold - 506" | Assistant Engineer | Junior Engineer | ORD/000322/2020-2021 | 1371/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 100
2010 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502" | Assistant Engineer | Junior Engineer | ORD/000323/2020-2021 | 1372/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0
2011 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 30 | SOUMITRA BOSE | 23.15 | 0 | 0
2012 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 01 (One) no. 200 mm X 165 mm dia.X 258 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000646/2022-2023 | 578/BQA | 17/03/2023 | 30 | SINGHA ENTERPRISE | 3.93 | 0 | 0
2013 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000846/2021-2022 |  | 01/09/2021 | 0 | SUBHADIP KOLEY | 3.8 | 0 | 0
2014 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of FHTC in connection with JAL JEVAN MISSION & Jal Swapna of Joyrambati w/s scheme | Assistant Engineer | Junior Engineer | VCH/001914/2020-2021 | FHTC/294 | 01/03/2021 | 0 | M/S SACHHIDANANDA MAZUMDAR | 4.67 | 0 | 0
2015 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joyrambati W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001915/2020-2021 | FHTC/294 | 01/03/2021 | 0 | TAPAS KUMAR HAZRA | 4.51 | 0 | 0
2016 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Hetiasole mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001917/2020-2021 | FHTC/294 | 01/03/2021 | 0 | D. S. ENTERPRISE | 4.8 | 0 | 0
2017 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Junbakra (35) , mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3948) | Assistant Engineer | Junior Engineer | VCH/001539/2020-2021 | FHTC/268 | 05/02/2021 | 0 | APEX ENTERPRISE | 26.09 | 0 | 0
2018 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502 . ( MB No - 3997)" | Assistant Engineer | Junior Engineer | VCH/001562/2020-2021 | FHTC/283 | 22/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 36.52 | 0 | 0
2019 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
2020 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. | Assistant Engineer | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 40.2 | 5.6 | 0
2021 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2020-2021 | 199/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 38.78 | 0 | 0
2022 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 0 | 0
2023 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 22) | Assistant Engineer | Junior Engineer | ORD/000526/2020-2021 | 324/KSD | 29/12/2020 | 61 | EARTH MOVING (INDIA) | 0.38 | 0 | 0
2024 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Naria (29), Benagaria (30), Hirakhon (31), mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001232/2021-2022 | FHTC/13 | 13/08/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.24 | 0 | 0
2025 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - barjora G.P chandar, Name of OHR - Lobason bauri para, chandar shib Total House Hold - 50 no - 03. | Assistant Engineer | Junior Engineer | VCH/001256/2021-2022 | FHTC/02 | 02/08/2021 | 0 | M/S PAUL BROTHERS | 4.27 | 0 | 0
2026 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Arkama (124) & Hazamdihi (233) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001317/2021-2022 |  | 28/09/2021 | 0 | UNITED TRADERS | 4.76 | 0 | 0
2027 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21) | Assistant Engineer | Junior Engineer | VCH/001328/2021-2022 |  | 28/09/2021 | 0 | UNITED TRADERS | 4.87 | 0 | 0
2028 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Arkama (124) & Hazamdihi (233) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) | Assistant Engineer | Junior Engineer | VCH/001329/2021-2022 |  | 28/09/2021 | 0 | UNITED TRADERS | 4.12 | 0 | 0
2029 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001409/2021-2022 | FHTC/15 | 15/09/2021 | 0 | SUBHADIP KOLEY | 3.8 | 0 | 0
2030 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Gadapathar College More to Nanda Primary School to increase pressure in Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001418/2022-2023 | FHTC/16 | 16/12/2022 | 0 | DEBAKI RANJAN SARKAR | 19.69 | 0 | 0
2031 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001482/2022-2023 | FHTC/20 | 20/12/2022 | 0 | MUNMUN UPADHYAY | 13.3 | 0 | 0
2032 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), | Assistant Engineer | Junior Engineer | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0
2033 | Bankura Division | Khatra Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ), | Assistant Engineer | Junior Engineer | VCH/001587/2021-2022 | FHTC/08 | 08/10/2021 | 0 | M/S SUPRIYA CHATTERJEE | 2.76 | 0 | 0
2034 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
2035 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of Mouza- Paschim Brindabanpur | Assistant Engineer | Junior Engineer | ORD/000179/2021-2022 | 705/BSD | 17/06/2021 | 10 | M/S SUPRIYA CHATTERJEE | 4.91 | 0 | 0
2036 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Palsona more to Ramchandrapur High School under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Palsona & Ramchandrapur | Assistant Engineer | Junior Engineer | ORD/000183/2021-2022 | 709/BSD | 17/06/2021 | 10 | RUFIKUL MONDAL | 4.92 | 0 | 0
2037 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Palsana ) , Total House Hold - 140 | Assistant Engineer | Junior Engineer | ORD/000277/2020-2021 | 2076/BQA | 29/12/2020 | 30 | GANGADHAR MONDAL | 9.84 | 0 | 0
2038 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 (Ramchandra pur (Part - A ), Total House Hold - 145 | Assistant Engineer | Junior Engineer | ORD/000278/2020-2021 | 2078/BQA | 29/12/2020 | 30 | RAFIKUL MONDAL | 10.21 | 0 | 0
2039 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - C ), Total House Hold - 161 | Assistant Engineer | Junior Engineer | ORD/000279/2020-2021 | 2080/BQA | 29/12/2020 | 30 | M/S T.P. HAZRA & SONS | 11.32 | 0 | 0
2040 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - D ) & Saluka ), Total House Hold - 158 | Assistant Engineer | Junior Engineer | ORD/000280/2020-2021 | 2081/BQA | 29/12/2020 | 30 | M/S T.P. HAZRA & SONS | 11.08 | 0 | 0
2041 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Paschim Brindabanpur ), Total House Hold - 168 | Assistant Engineer | Junior Engineer | ORD/000287/2020-2021 | 2077/BQA | 29/12/2020 | 30 | M/S SUPRIYA CHATTERJEE | 11.76 | 0 | 0
2042 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - B ), Total House Hold - 151 | Assistant Engineer | Junior Engineer | ORD/000288/2020-2021 | 2079/BQA | 29/12/2020 | 30 | M/S SUPRIYA CHATTERJEE | 10.59 | 0 | 0
2043 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.28 | 0
2044 | Bankura Division | Bankura Sadar Sub-Division | supplying laying fitting fixing of HDPE pipe line from near Banogram village Dhok para to Banogram village Ray para & bauri para towards Durgapur to Bankura road (Left side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 510/BSD | 12/07/2022 | 20 | AJIT KUMAR PAUL | 4.95 | 0 | 0
2045 | Bankura Division | Bankura Sadar Sub-Division | supplying laying fitting fixing of HDPE pipe line from near Soni Mondir (Beliatore Police Station) to Banogram village Burn Para towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 503/BSD | 12/07/2022 | 20 | AJIT KUMAR PAUL | 4.98 | 0 | 0
2046 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line from Daboni village More to Markha Village more & supply of MS pipe for use of cassing along with all allied works under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [Under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000741/2022-2023 | 538/BSD | 28/07/2022 | 21 | GANESH ROY | 4.45 | 0 | 0
2047 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza Palsana | Assistant Engineer | Junior Engineer | VCH/000732/2021-2022 |  | 27/07/2021 | 0 | GANGADHAR MONDAL | 4.1 | 0 | 0
2048 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza Palsana | Assistant Engineer | Junior Engineer | VCH/001291/2021-2022 | FHTC/02 | 02/08/2021 | 0 | GANGADHAR MONDAL | 4.1 | 0 | 0
2049 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - A ) | Assistant Engineer | Junior Engineer | VCH/001338/2021-2022 |  | 28/09/2021 | 0 | RAFIKUL MONDAL | 4.65 | 0 | 0
2050 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ) | Assistant Engineer | Junior Engineer | VCH/001339/2021-2022 |  | 28/09/2021 | 0 | M/S SUPRIYA CHATTERJEE | 2.76 | 0 | 0
2051 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - C) | Assistant Engineer | Junior Engineer | VCH/001354/2021-2022 |  | 28/09/2021 | 0 | M/S T.P. HAZRA & SONS | 3.3 | 0 | 0
2052 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (FunctionalHouse Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - D ) & Saluka | Assistant Engineer | Junior Engineer | VCH/001355/2021-2022 |  | 28/09/2021 | 0 | M/S T.P. HAZRA & SONS | 2.71 | 0 | 0
2053 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 04 no [Narasole, Taljhoria, Khabanigoparpur (Part), Jhikuria] Total House Hold- 359 | Assistant Engineer | Junior Engineer | VCH/001550/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAS KUMAR HAZRA | 20.59 | 0 | 0
2054 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - D ) & Saluka ), Total House Hold - 158 | Assistant Engineer | Junior Engineer | VCH/001585/2020-2021 |  | 15/03/2021 | 0 | M/S T.P. HAZRA & SONS | 10.54 | 0 | 0
2055 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Paschim Brindabanpur ), Total House Hold - 168 | Assistant Engineer | Junior Engineer | VCH/001586/2020-2021 |  | 15/03/2021 | 0 | M/S SUPRIYA CHATTERJEE | 11.05 | 0 | 0
2056 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - B ), Total House Hold - 151 | Assistant Engineer | Junior Engineer | VCH/001587/2020-2021 |  | 15/03/2021 | 0 | M/S SUPRIYA CHATTERJEE | 8.15 | 0 | 0
2057 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - C ), Total House Hold - 161 | Assistant Engineer | Junior Engineer | VCH/001588/2020-2021 |  | 15/03/2021 | 0 | M/S T.P. HAZRA & SONS | 7.63 | 0 | 0
2058 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 (Ramchandra pur (Part - A ), Total House Hold - 145 | Assistant Engineer | Junior Engineer | VCH/001589/2020-2021 |  | 15/03/2021 | 0 | RUFIKUL MONDAL | 8.95 | 0 | 0
2059 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Palsana ) , Total House Hold - 140 | Assistant Engineer | Junior Engineer | VCH/001596/2020-2021 |  | 15/03/2021 | 0 | GANGADHAR MONDAL | 8.99 | 0 | 0
2060 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipeline of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Palsana ) , Total House Hold - 140, | Assistant Engineer | Junior Engineer | VCH/001790/2021-2022 |  | 22/11/2021 | 0 | M/S SUPRIYA CHATTERJEE | 4.84 | 0 | 0
2061 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 01 no, (Hatjore) Total House Hold - 149 | Assistant Engineer | Junior Engineer | VCH/002285/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOUTAM GHOSH | 10.74 | 0 | 0
2062 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line at Banasree pally Barjora of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002286/2021-2022 | FHTC/31 | 31/01/2022 | 0 | NAYAN BARDHAN | 4.84 | 0 | 0
2063 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 2 nos. i.e. Tentulara-20 (53 out of 106), Shaluka - 21(2 out of 125) House Hold - 55 (Sl. No. 03) | Assistant Engineer | Junior Engineer | VCH/002287/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SHYAMAPADA DEY | 4.01 | 0 | 0
2064 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) | Assistant Engineer | Junior Engineer | VCH/002288/2021-2022 | FHTC/31 | 31/01/2022 | 0 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0
2065 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Dhaban Zone A under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project)s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002439/2021-2022 | FHTC/17 | 17/02/2022 | 0 | RUFIKUL MONDAL | 1.69 | 0 | 0
2066 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 nos ( Radhaballavpur, Rampur) Total House Hold- 140 | Assistant Engineer | Junior Engineer | VCH/002440/2021-2022 | FHTC/17 | 17/02/2022 | 0 | RUFIKUL MONDAL | 8.34 | 0 | 0
2067 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57) & Chaka Doba (58) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2020-2021 | 164/BQA | 18/01/2021 | 30 | PRADIP CHAKRABORTY | 12.74 | 11.46 | 0
2068 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Paharapatpur (117), Bhaluka (120) & Kadra (121) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2020-2021 | 194/BQA | 18/01/2021 | 30 | APEX ENTERPRISE | 31.12 | 1.1 | 0
2069 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000138/2020-2021 | 195/BQA | 18/01/2021 | 30 | GOUTAM BHATTACHRYYA | 33.15 | 9.82 | 0
2070 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01 no, Shyampur (part) Total House Hold - 75 (Sl No of Work- 14) | Assistant Engineer | Junior Engineer | ORD/000197/2020-2021 | 106/ BSD | 12/02/2021 | 20 | TAPAS KUMAR HAZRA | 4.79 | 7.16 | 0
2071 | Bankura Division | Khatra Sub-Division | Construction and Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadra (121 mouza by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2022-2023 | 05/BQA | 03/01/2023 | 45 | SUNIL KUMAR MANDAL | 6.89 | 6.53 | 0
2072 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000357/2020-2021 | 43/KSD | 15/01/2021 | 59 | TAPAS DEY | 0.31 | 0 | 0
2073 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0
2074 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Heyatnagar, No. of Mouza :- 8 nos. i.e. Srikara-31, Padua-11, Adpara Kumrul-12, Sripur-26, Heyatnagar-27, Maheshpur-28, Meral-29 & Chakmeral-30, Total House Hold - 2465 | Assistant Engineer | Junior Engineer | ORD/000250/2021-2022 | 3145/BQA | 15/12/2021 | 60 | JAYANTA KUMAR MONDAL | 187.06 | 0 | 0
2075 | Bankura Division | Brishnupur Sub-Division | FHTC Maintenance of Amrul Zone-B Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2022-2023 | 318/VSD | 29/11/2022 | 15 | GOUTAM GHOSH | 0.97 | 0 | 0
2076 | Bankura Division | Brishnupur Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" | Assistant Engineer | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 2.32 | 0
2077 | Bankura Division | Brishnupur Sub-Division | 'Name of Work: Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 02, (Karanjora, Lapuria (PART)), Total House Hold - 606' | Assistant Engineer | Junior Engineer | VCH/002575/2021-2022 | FHTC/26 | 26/02/2022 | 0 | SOUMITRA BHATTACHARYA | 12.95 | 0 | 0
2078 | Bankura Division | Brishnupur Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 01, (Sonamui (PART), Total House Hold - 606 ' | Assistant Engineer | Junior Engineer | VCH/002576/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S BIPUL BANERJEE | 4.1 | 0 | 0
2079 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002577/2021-2022 | FHTC/26 | 26/02/2022 | 0 | SUBHANKAR BANERJEE | 13.07 | 0 | 0
2080 | Bankura Division | Brishnupur Sub-Division | HDPE pipe line from Barabendya Kodolia Chomatha to Khemua to increase pressure for mouza- Khemua of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002579/2021-2022 | FHTC/26 | 26/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 48.28 | 0 | 0
2081 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 07 (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyaldanga, Bagdiha) Total House Hold - 1131 | Assistant Engineer | Junior Engineer | VCH/002726/2021-2022 | FHTC/3 | 03/03/2022 | 0 | SIB SANKAR CHOWDHURY | 47.08 | 0 | 0
2082 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 | Assistant Engineer | Junior Engineer | VCH/002745/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UNICON INDIA | 116.51 | 0 | 0
2083 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC pipe line to cover sanpura & Kalipahari mouza & Dismantling & reconstruction of concrete of Saburbandh mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jorehira ( zone - B) under Chhatna block of Saltora -chhatna water supply scheme (BRGF ph - l project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002825/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.27 | 0 | 0
2084 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
2085 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhengasole W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Dhengasole, No. of Mouza :- 06 nos. i.e. Khuliamuri-126, Harabati-127, Dhengasole-128, Lohari-129, Chorkundu-130 & Karra- 131, Total House Hold - 495 | Assistant Engineer | Junior Engineer | ORD/000209/2021-2022 | 3045/BQA | 01/12/2021 | 30 | PARTHA PRATIM CHHATAIT | 75.62 | 44.76 | 0
2086 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Dhengasole W/S Scheme (BRGF Ph-I) Block- Bishnupur under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000545/2022-2023 | 487/BQA | 13/03/2023 | 45 | MRITYUNJOY HAZRA | 28.13 | 21.29 | 95
2087 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (24 out of 714), Bhagarara-25 (8 out of 71), Sanatanpur-26, Tala-27, Moula-29, House Hold - 110 | Assistant Engineer | Junior Engineer | ORD/000080/2021-2022 | 2520/BQA | 23/09/2021 | 30 | SWAPAN KUMAR DE | 9.21 | 0 | 0
2088 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (115 out of 714), House Hold - 115 | Assistant Engineer | Junior Engineer | ORD/000081/2021-2022 | 2521/BQA | 23/09/2021 | 30 | PRASANTA BHUIN | 9.64 | 0 | 0
2089 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-4) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (120 out of 714), House Hold - 120 | Assistant Engineer | Junior Engineer | ORD/000082/2021-2022 | 2522/BQA | 23/09/2021 | 30 | MAYA CONSTRUCTION | 10.03 | 0 | 0
2090 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 | Assistant Engineer | Junior Engineer | ORD/000083/2021-2022 | 2523/BQA | 23/09/2021 | 30 | AMIYA KUMAR BIT | 37.98 | 2.53 | 0
2091 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 36. Block - Bishnupur,Name of OHR - Bhara,No. of Mouza :- 1 no. i.e.Shaluka - 21(110 out of 125) House Hold - 110 | Assistant Engineer | Junior Engineer | ORD/000085/2021-2022 | 2524/BQA | 23/09/2021 | 30 | MRITYUNJOY HAZRA | 9.05 | 0 | 0
2092 | Bankura Division | Brishnupur Sub-Division | Repairing and renovation of pipe line work in connection with Jal Jeevan Mission(JJM) of Chuamasina Zone-B and Prakash Zone-B Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000644/2022-2023 | 44/VSD | 10/03/2023 | 15 | SONU SINGH | 0.96 | 0.34 | 0
2093 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with JalJeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhagarara-25 (63 out of 71), House Hold ¿ 63 (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000124/2021-2022 | 418/VSD | 22/09/2021 | 21 | SANU KARMAKAR | 4.61 | 0 | 0
2094 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Functional House Hold Tap Connection)' extra house hold in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamasina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Bhora, No. of Mouza :- 4 nos. i.e. Bhora- 44 ,Maula - 48,Sanatanpur - 49,Tala - 46 Total House Hold - 11 | Assistant Engineer | Junior Engineer | ORD/000273/2023-2024 | 156/VSD | 02/06/2023 | 15 | SHYAMAPADA DEY | 0.96 | 0 | 100
2095 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) | Assistant Engineer | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
2096 | Bankura Division | Brishnupur Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527.' | Assistant Engineer | Junior Engineer | VCH/002326/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GOUTAM BHATTACHRYYA | 5.69 | 0 | 0
2097 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone- B), No. of Mouza:- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur), (Part- B) | Assistant Engineer | Junior Engineer | VCH/002327/2021-2022 | FHTC/25 | 25/01/2022 | 0 | M/S TARUN KUMAR PATRA | 4.81 | 0 | 0
2098 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B), No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), (Part-A) | Assistant Engineer | Junior Engineer | VCH/002328/2021-2022 | FHTC/25 | 25/01/2022 | 0 | M/S TARUN KUMAR PATRA | 3.83 | 0 | 0
2099 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (24 out of 714), Bhagarara-25 (8 out of 71), Sanatanpur-26, Tala-27, Moula-29, House Hold - 110 | Assistant Engineer | Junior Engineer | VCH/002329/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SWAPAN KUMAR DE | 8.63 | 0 | 0
2100 | Bankura Division | Brishnupur Sub-Division | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002330/2021-2022 | FHTC/25 | 25/01/2022 | 0 | BISWARUP BOSE | 3.02 | 0 | 0
2101 | Bankura Division | Brishnupur Sub-Division | laying extra UPVC pipe line to cover Magra mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002331/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SK. SAHAJAHAN | 4.13 | 0 | 0
2102 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12), | Assistant Engineer | Junior Engineer | VCH/002332/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GANESH ROY | 4.99 | 0 | 0
2103 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13), | Assistant Engineer | Junior Engineer | VCH/002333/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GANESH ROY | 4.98 | 0 | 0
2104 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-4) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Harinagar-23 (116 out of 336),Dharampur-22 (84 out of 299),Shaluka - 21(13 out of 125), Khazra -37(1 out of 1)House Hold - 214 | Assistant Engineer | Junior Engineer | ORD/000086/2021-2022 | 2525/BQA | 23/09/2021 | 30 | M/S SACHHIDANANDA MAZUMDAR | 17.57 | 0 | 0
2105 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-6) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara,No. of Mouza :- 1 no. i.e. Harinagar-23 (220 out of 336), House Hold - 220 | Assistant Engineer | Junior Engineer | ORD/000088/2021-2022 | 2526/BQA | 23/09/2021 | 30 | MOHAN KUMAR ROY | 18.13 | 0 | 0
2106 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara,No. of Mouza :- 1 no. i.e. Dharampur-22 (215 out of 299), House Hold - 215 | Assistant Engineer | Junior Engineer | ORD/000112/2021-2022 | 2690/BQA | 26/10/2021 | 30 | M/S T.P. HAZRA & SONS | 17.69 | 0 | 0
2107 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 2 nos. i.e. Tentulara-20 (53 out of 106), Shaluka - 21(2 out of 125) House Hold - 55 (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000125/2021-2022 | 420/VSD | 22/09/2021 | 21 | SHYAMAPADA DEY | 4.54 | 0 | 0
2108 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Approv.DPR no- 37, Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 9 nos. i.e. Nangalbhanga-18, Chwak Chuamosina-19, Bendara-38, Ramsundarpur-39, Dapanjuri-40, Dhirkona-41, Joyrampur-42, Tentulia-62 & Siharshul-63, Total House Hold - 807 | Assistant Engineer | Junior Engineer | ORD/000170/2021-2022 | 2845/BQA | 16/11/2021 | 30 | I.R.CONSTRUCTION | 58.45 | 0 | 0
2109 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Tentulara-20 (53 out of 106), House Hold - 53 (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000174/2021-2022 | 419/VSD | 22/09/2021 | 21 | MANORANJAN GHOSH | 4.37 | 0 | 0
2110 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, Khyerkanali (PART-1) Total House Hold - 145 | Assistant Engineer | Junior Engineer | VCH/001514/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PRADIP CHAKRABORTY | 11.26 | 0 | 0
2111 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001732/2021-2022 | FHTC/23 | 23/11/2021 | 0 | M/S BIPUL BANERJEE | 24.12 | 0 | 0
2112 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
2113 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Indas, Name of OHR - Rol, No. of Mouza :- 2 nos. i.e. Rol-07 & Chichinga-08, Total House Hold - 1421 | Assistant Engineer | Junior Engineer | VCH/002337/2021-2022 | FHTC/25 | 25/01/2022 | 0 | CREATION CONSTRUCTION | 64.49 | 0 | 0
2114 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 06 nos. i.e. Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54, Haripur-55 & Banamalipur- 56 , Total House Hold - 735 | Assistant Engineer | Junior Engineer | ORD/000186/2021-2022 | 2689/BQA | 26/10/2021 | 30 | SAMRAT REALPROJECTS PRIVATE LIMITED | 65.74 | 26.19 | 0
2115 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2021-2022 | 473/BQA | 04/03/2022 | 0 | Resource Division | 4.53 | 0 | 0
2116 | Bankura Division | Khatra Sub-Division | Laying extra UPVC Pipe Line to Dahuka village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE- II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000118/2022-2023 | 458/BSD | 06/06/2022 | 15 | GOURANGA CHATTERJEE | 3.75 | 3.71 | 0
2117 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Majura (372) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 547 Nos." | Assistant Engineer | Junior Engineer | ORD/000121/2021-2022 | 2776/BQA | 08/11/2021 | 1485 | TAPAN KUMAR MANDAL | 23.48 | 0 | 0
2118 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 310 Nos." | Assistant Engineer | Junior Engineer | ORD/000122/2021-2022 | 2774/BQA | 08/11/2021 | 30 | MESSRS FREEDOM CONSTRUCTION | 11.76 | 2.01 | 0
2119 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Deuli (369) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 322 Nos." | Assistant Engineer | Junior Engineer | ORD/000123/2021-2022 | 2775/BQA | 08/11/2021 | 30 | MESSRS FREEDOM CONSTRUCTION | 12.67 | 1.79 | 0
2120 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipeline to increase water pressure at Horakabaid mouza for rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2022-2023 | 471/BSD | 06/06/2022 | 15 | TAPAN KUMAR MANDAL | 4.94 | 4.71 | 0
2121 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works from Debagram village more to Jamirapara village more [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2023-2024 | 84/KSD | 24/04/2023 | 5 | TAPAS DEY | 0.96 | 0.96 | 0
2122 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Belapal (368), Deuli (369) & Majura (372) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000590/2021-2022 | 794/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.39 | 0 | 0
2123 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368), Deuli (369) & Majura (372) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000458/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.35 | 0 | 0
2124 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 06 ( Kustora, Nekragori , Gangtara, Bhalukbasa, Hrtyasol & Patharkata ). Total House Hold - 819 | Assistant Engineer | Junior Engineer | VCH/002755/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SABIR ALI KHAN | 18.43 | 0 | 0
2125 | Bankura Division | Khatra Sub-Division | Supplying Laying by UPVC pipe (6 kg/sq cm. water presure, class lll) for distribution network along with ancillary works at village Gopaldanga and Hatibari (damaged due to strengthening - Widening of Sarenga Chowrasta more to Goaltore road by PWD (road) dte. under water supply scheme for Gargarya Zone-B of Sarenga water supply scheme (BRGF Ph-I) at Block- Sarenga , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002756/2021-2022 | FHTC/4 | 04/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.88 | 0 | 0
2126 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Dubrajpur Zone-A & B of Simlapal Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) [Part-A] (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/002758/2021-2022 | FHTC/4 | 04/03/2022 | 0 | BISWAJIT SINHA MAHAPATRA | 3.37 | 0 | 0
2127 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Dubrajpur Zone-A & B of Simlapal Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) [Part-B] (Sl. No. 12) | Assistant Engineer | Junior Engineer | VCH/002760/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SOURAV SINHA MAHAPATRA | 3.36 | 0 | 0
2128 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 5 nos. i.e. Mathurabihari-28, Ramchandrapur-30, Matukpur-31, Purba Nischintapur-32 & Kuldangar-36, Total House Hold - 828 | Assistant Engineer | Junior Engineer | VCH/002764/2021-2022 | FHTC/5 | 05/03/2022 | 0 | ASHISH KUMAR SAMANTA | 59.29 | 0 | 0
2129 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
2130 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Deuli (369) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Gargarya zone - A under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002976/2021-2022 | FHTC/26 | 26/03/2022 | 0 | MESSRS FREEDOM CONSTRUCTION | 3.02 | 0 | 0
2131 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Belapal (368) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Gargarya zone - A under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002979/2021-2022 | FHTC/26 | 26/03/2022 | 0 | MESSRS FREEDOM CONSTRUCTION | 4.76 | 0 | 0
2132 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Karisunda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Simulia, No. of Mouza :- 16 nos. i.e. Simulia-46, Bagmari-47, Santara-48, Rasulpur-49, Kapshit-23, Belbadbi-22, Bishnubati-25, Paschim Srirampur-38, Patraganti-39, Kalagram-40, Sahisnara-41, Pantrai-42, Tentulmuri-43, Chandpur-44, Singerbandh-45 & Karisunda-54, Total House Hold - 3761 | Assistant Engineer | Junior Engineer | ORD/000076/2022-2023 | 1808/BQA | 22/08/2022 | 60 | SIB SANKAR CHOWDHURY | 250.69 | 101.58 | 85
2133 | Bankura Division | Brishnupur Sub-Division | Continuation work order for Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.02.2022 to 31.07.2022 | Assistant Engineer | Junior Engineer | ORD/000720/2021-2022 | 12/VSD | 27/01/2022 | 181 | SWAPAN KUMAR BIT | 0.86 | 1.54 | 0
2134 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000881/2022-2023 | 37/A/VSD | 27/02/2023 | 28 | TAPAN KUMAR UPADHYAY | 0.29 | 0.2 | 0
2135 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 28/02/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001030/2021-2022 | 11/A/VSD | 30/01/2022 | 29 | TAPAN KUMAR UPADHYAY | 0.23 | 0.23 | 0
2136 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 14.29 | 0 | 0
2137 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 12 Nos. Total Household:- 2906 Nos. | Assistant Engineer | Junior Engineer | ORD/000260/2021-2022 | 3169/BQA | 17/12/2021 | 60 | GOPAL CHANDRA CHOUDHURY | 152.35 | 0 | 0
2138 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 12 Nos. Total Household:- 2906 Nos. | Assistant Engineer | Junior Engineer | ORD/000314/2021-2022 | 07/BQA | 03/01/2022 | 60 | GOPAL CHANDRA CHOUDHURY | 152.35 | 152.74 | 0
2139 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Lakat (161), Sarigari (163), Makli (164) & Mandankuli (241) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) | Assistant Engineer | Junior Engineer | ORD/000645/2021-2022 | 747/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.97 | 4.85 | 0
2140 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Satpatta (240), Madanpur (242) & Asurgerya (243) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 29) | Assistant Engineer | Junior Engineer | ORD/000646/2021-2022 | 759/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.96 | 4.86 | 0
2141 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 31) | Assistant Engineer | Junior Engineer | ORD/000647/2021-2022 | 761/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.95 | 4.47 | 0
2142 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) | Assistant Engineer | Junior Engineer | ORD/000681/2021-2022 | 856/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.97 | 0.23 | 0
2143 | Bankura Division | Khatra Sub-Division | Household survey in Lakat ( 161) Sarigari (163) Makli (164) Satpatta (240) Mandankuli (241) Madanpur (242) dhekikata (260) & Dhekikata ( 262) mouza Mandalkuli zone IIIA to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/000453/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.73 | 0 | 0
2144 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.DPR no - 15. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 2 nos. i.e. Beliara-65 & Dejhat-66, Total House Hold - 977 | Assistant Engineer | Junior Engineer | ORD/000210/2021-2022 | 3046/BQA | 01/12/2021 | 30 | PARAMESWAR CHOWDHURY | 72.35 | 10.6 | 0
2145 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) | Assistant Engineer | Junior Engineer | VCH/001523/2022-2023 | FHTC/18 | 18/01/2023 | 0 | PARAMESWAR CHOWDHURY | 2.78 | 0 | 0
2146 | Bankura Division | Brishnupur Sub-Division | Parallel pipe laying of HDPE pipe from Pinguri village football ground to Pinguri Village Hunuman mondir for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001524/2022-2023 | FHTC/18 | 18/01/2023 | 0 | SUBHADIP KOLEY | 4.93 | 0 | 0
2147 | Bankura Division | Brishnupur Sub-Division | Laying of HDPE pipe from Maliara OHR site to Pinguri village football ground for increase pressure of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001525/2022-2023 | FHTC/18 | 18/01/2023 | 0 | SUBHADIP KOLEY | 4.8 | 0 | 0
2148 | Bankura Division | Brishnupur Sub-Division | Parallel pipe laying of HDPE pipe from Pinguri Village Hunuman mondir to Khatal Bagan Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001526/2022-2023 | FHTC/18 | 18/01/2023 | 0 | SUBHADIP KOLEY | 4.93 | 0 | 0
2149 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 | Assistant Engineer | Junior Engineer | VCH/001546/2022-2023 | FHTC/06 | 06/01/2023 | 0 | M/S TARUN KUMAR PATRA | 93.05 | 0 | 0
2150 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001547/2022-2023 | FHTC/06 | 06/01/2023 | 0 | GANESH ROY | 6.02 | 0 | 0
2151 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
2152 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 694 nos. out of 2080 nos ( PART - C) | Assistant Engineer | Junior Engineer | ORD/000018/2022-2023 | 926/BQA | 21/04/2022 | 60 | PRINCE INDUTRIES (INDIA) | 33.43 | 33.3 | 0
2153 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2080 nos. ( PART-B) | Assistant Engineer | Junior Engineer | ORD/000034/2022-2023 | 1212/BQA | 01/06/2022 | 60 | GOUTAM BHATTACHRYYA | 33.41 | 33.08 | 0
2154 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2080 nos. ( 693 out of 2080)( PART- A ) | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 1225/BQA | 07/06/2022 | 60 | PARAMESWAR CHOWDHURY | 33.41 | 31.72 | 0
2155 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2021-2022 | 106/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.69 | 0.69 | 0
2156 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000037/2021-2022 | 577/BQA | 17/03/2022 | 0 | Resource Division | 12.81 | 0 | 0
2157 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | ORD/000253/2021-2022 | 3147/BQA | 15/12/2021 | 60 | M/S TARUN KUMAR PATRA | 177.51 | 45.65 | 0
2158 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | ORD/000393/2021-2022 | 204/BQA | 01/02/2022 | 60 | M/S TARUN KUMAR PATRA | 177.51 | 0 | 0
2159 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2021-2022 | 479/BQA | 04/03/2022 | 0 | Resource Division | 17.36 | 0 | 0
2160 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001172/2022-2023 | FHTC/27 | 27/09/2022 | 0 | M/S TARUN KUMAR PATRA | 58.15 | 0 | 0
2161 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Bamunpara, Panjapara, total house hold - 68 | Assistant Engineer | Junior Engineer | VCH/002400/2021-2022 | FHTC/21 | 21/02/2022 | 0 | AJIT KUMAR DUTTA | 3.91 | 0 | 0
2162 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Panjapara, Total house hold - 62 | Assistant Engineer | Junior Engineer | VCH/002401/2021-2022 | FHTC/21 | 21/02/2022 | 0 | NAYAN BARDHAN | 3.57 | 0 | 0
2163 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kushmuri, No. of Mouza :- 09 nos. i.e. Sanpura-57, Jagaldwip-58, Dasarathbati-61, Bhabapur-100, Shyampur-97, Kushmuri - 98, Khayerbani- 99, Khatnagar 101 & Jotbehar - 102, Total House Hold - 2653 | Assistant Engineer | Junior Engineer | VCH/002402/2021-2022 | FHTC/21 | 21/02/2022 | 0 | BANDHAB ENGINEERS CO-OP SOCIETY LTD. | 126.5 | 0 | 0
2164 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
2165 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kharshi, No. of Mouza :- 05 nos. i.e. Jhiknara-119 & Kharsi-121, Narra-120, Ratra-122 & Salikona-123, Total House Hold - 2522 | Assistant Engineer | Junior Engineer | ORD/000254/2021-2022 | 3148/BQA | 15/12/2021 | 60 | TAPAS SANTRA | 175.44 | 152.22 | 0
2166 | Bankura Division | Bankura Sadar Sub-Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II). No. of Mouza :-03 nos (Kadasole, Kamarsol, Ghutgaria), Total House Hold -1874 nos. | Assistant Engineer | Junior Engineer | ORD/000039/2022-2023 | 1380/BQA | 27/06/2022 | 60 | SIB SANKAR CHOWDHURY | 212.38 | 123.96 | 15
2167 | Bankura Division | Bankura Sadar Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) | Assistant Engineer | Junior Engineer | ORD/000188/2022-2023 | 348/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.96 | 4.96 | 0
2168 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line near Ramkrishna Mission Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000205/2021-2022 | 756/BSD | 26/07/2021 | 15 | ZAKIR HOSSAIN MONDAL | 4.79 | 0 | 0
2169 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Barjora Headwork site near Kadasole to Barjora Forest Office of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000481/2020-2021 | 93/BSD | 12/02/2021 | 20 | ZAKIR HOSSAIN MONDAL | 4.8 | 0 | 0
2170 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Barjora Forest Office to End of Forest colony of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000482/2020-2021 | 94/BSD | 12/02/2021 | 20 | ZAKIR HOSSAIN MONDAL | 4.79 | 0 | 0
2171 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2021-2022 | 272/BQA | 11/02/2022 | 0 | Resource Division | 87.92 | 0 | 0
2172 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from End of Forest colony to Ramkrishna Mission Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000483/2020-2021 | 95/BSd | 12/02/2021 | 20 | ZAKIR HOSSAIN MONDAL | 4.78 | 0 | 0
2173 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line at Schooldanga Barjora of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission (JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000484/2020-2021 | 221/BSD | 25/02/2021 | 15 | ZAKIR HOSSAIN MONDAL | 4.76 | 0 | 0
2174 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line at Banasree pally Barjora of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000485/2020-2021 | 222/BSD | 25/02/2021 | 15 | NAYAN BARDHAN | 4.84 | 0 | 0
2175 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Ramkrishna Mission Ashram to Barjora Pry. School of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000486/2020-2021 | 96/BSD | 12/02/2021 | 20 | NAYAN BARDHAN | 4.82 | 0 | 0
2176 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Barjora Pry. School to near Barjora BDO Office of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000487/2020-2021 | 97/BSD | 12/02/2021 | 20 | NAYAN BARDHAN | 4.81 | 0 | 0
2177 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-03 nos, (Kadasole, Kamarsol, Ghutgaria), Total House Hold -1874 nos. | Assistant Engineer | Junior Engineer | ORD/000881/2021-2022 | 81/BSD | 14/01/2022 | 3 | TAPAS DEY | 0.62 | 0 | 80
2178 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 560 | Assistant Engineer | Junior Engineer | VCH/002323/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SIB SANKAR CHOWDHURY | 26.82 | 0 | 0
2179 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra HDPE pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | VCH/002325/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SUBHADIP KOLEY | 1.79 | 0 | 0
2180 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527.' | Assistant Engineer | Junior Engineer | VCH/002326/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GOUTAM BHATTACHRYYA | 5.69 | 0 | 0
2181 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas, (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III). No.of Mouza :- 13 nos (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold - 2821 nos. | Assistant Engineer | Junior Engineer | VCH/003101/2021-2022 | FHTC/28 | 28/03/2022 | 0 | M/S TARUN KUMAR PATRA | 151.09 | 0 | 0
2182 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 5 Nos. Total Household:- 640 Nos. | Assistant Engineer | Junior Engineer | ORD/000413/2021-2022 | 410/BQA | 28/02/2022 | 30 | SARKAR CONSTRUCTION | 37.44 | 37.43 | 0
2183 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) | Assistant Engineer | Junior Engineer | ORD/000606/2021-2022 | 804/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.21 | 0.21 | 0
2184 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of UPVC pipeline in Kharika (27), Khapmayna (29) & Bankata (31) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000661/2022-2023 | 506/BQA | 13/03/2023 | 45 | MANAS DEY | 3.56 | 3.19 | 0
2185 | Bankura Division | Khatra Sub-Division | Installation of stret stand post under Simlapal water supply scheme BRGF PH - I under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000284/2022-2023 | FHTC/26 | 26/04/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 2.15 | 0 | 0
2186 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Pathardoba, Zone-A & B and Baricha, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 58 Nos. Total Household:- 7982 Nos. Name of Mouzas:- Under Pathardoba, Zone-A :- Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) Under Pathardoba, Zone-B:- Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) Under Baricha, Zone-B:- Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) | Assistant Engineer | Junior Engineer | ORD/000025/2022-2023 | 1085/BQA | 12/05/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 482.88 | 160.87 | 0
2187 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) mouzas under Baricha, Zone-B to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) | Assistant Engineer | Junior Engineer | ORD/000609/2021-2022 | 800/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.77 | 0.62 | 0
2188 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2022-2023 | 1836/BQA | 29/08/2022 | 0 | Resource Division | 33.83 | 0 | 0
2189 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 5.09 | 0 | 0
2190 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debagram (79), Baidyanathpur (80), Mankhamar (81), Lodna (89) & Madanpur (90) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household-88 nos.. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 802/BQA | 11/04/2023 | 90 | TARINI CHARAN UPADHYAY | 20.32 | 19.91 | 95
2191 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jaba Balarampur (68), Bagjata (78), Debagram (79), Baidyanathpur (80), Mankhamar (81), Bhatgram (82), Banamalipur (83), Mukundabati (84), Lodna (89) & Madanpur (90) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2000 nos. | Assistant Engineer | Junior Engineer | ORD/000420/2021-2022 | 470/BQA | 04/03/2022 | 60 | MUNMUN UPADHYAY | 99.98 | 99.97 | 0
2192 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Jaba Balarampur (68), Bagjata (78), Debagram (79), Baidyanathpur (80), Mankhamar (81), Bhatgram (82), Banamalipur (83), Mukundabati (84), Lodna (89) & Madanpur (90) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2021-2022 | 91/BSD | 28/01/2022 | 60 | TAPAS DEY | 0.67 | 0.67 | 0
2193 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2021-2022 | 454/BQA | 03/03/2022 | 0 | Resource Division | 11 | 0 | 0
2194 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying Extra UPVC Pipe Line to Cover Jamthol mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone- A) under Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 107/KSD | 28/04/2023 | 30 | TAPAS KUMAR HAZRA | 0.84 | 0 | 100
2195 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, No. of Mouza :- Jamthol, Total House Hold :-7 nos. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 109/KSD | 28/04/2023 | 30 | TAPAS KUMAR HAZRA | 0.45 | 0.42 | 100
2196 | Bankura Division | Bankura Sadar Sub-Division | Crossing of Road by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Laying of MS Distribution Main for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte (Part -A) Location of site: Bhilani Bridge (Right side) | Assistant Engineer | Junior Engineer | ORD/000197/2022-2023 | 261/KSD | 12/07/2022 | 15 | SIB SANKAR CHOWDHURY | 4.11 | 4.11 | 0
2197 | Bankura Division | Bankura Sadar Sub-Division | Bridge crossing at Bhilani by 250mm dia MS Pipe & other allied works at Dhaban under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000198/2022-2023 | 262/KSD | 12/07/2022 | 15 | SIB SANKAR CHOWDHURY | 3.86 | 3.85 | 0
2198 | Bankura Division | Bankura Sadar Sub-Division | Crossing of Road by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Laying of MS Distribution Main for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte (Part -B) Location of site: Bhilani Bridge (Left side) . | Assistant Engineer | Junior Engineer | ORD/000199/2022-2023 | 258/KSD | 12/07/2022 | 15 | SIB SANKAR CHOWDHURY | 4.11 | 4.11 | 0
2199 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jamthol (PART) Total House Hold- 140 | Assistant Engineer | Junior Engineer | ORD/000204/2020-2021 | 989/BQA | 26/02/2021 | 30 | MRITYUNJOY HAZRA | 9.83 | 0.68 | 0
2200 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No. of Mouza :- 01 no., Jorthol (Part), Total House Hold- 75 nos. | Assistant Engineer | Junior Engineer | ORD/000478/2021-2022 | 54/BSD | 07/01/2022 | 15 | M/S T.P. HAZRA & SONS | 4.91 | 0 | 0
2201 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of extra 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 01 no., Taljoria (Part), Total House Hold- 35 nos. | Assistant Engineer | Junior Engineer | ORD/000487/2021-2022 | 55/BSD | 07/01/2022 | 15 | TAPAS KUMAR HAZRA | 4.29 | 0 | 40
2202 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No. of Mouza :- 01 no., Jorthol (Part), Total House Hold- 75 nos. | Assistant Engineer | Junior Engineer | ORD/000548/2021-2022 | 54/BSD | 07/01/2022 | 15 | M/S T.P. HAZRA & SONS | 4.91 | 4.91 | 0
2203 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Household survey of retrofitting works of creation of ¿FHTC (Functional House Hold Tap Connection)¿ in connection with Jal Jeevan Mission (JJM) and Jal Swapna under Saltora-Chhatna W/S Scheme (BRGF Ph-I Project) under Bankura Division of Bankura Division, P.H.E. Dte. Block- Chhatna, Name of OHR- Dhaban, Hapania, Jorehira, Kalipur, Tilna, Chinabari, Bandagal & Nabagram, No. of Mouza- 97 Nos., Total Household- 1868 Nos. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 38/KSD | 13/03/2023 | 30 | TAPAS DEY | 0.62 | 0.62 | 100
2204 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- 01 no., Jorethol (Part), Total House Hold- 38 nos. | Assistant Engineer | Junior Engineer | ORD/000990/2022-2023 | 345/KSD | 16/08/2022 | 20 | TAPAS KUMAR HAZRA | 1.61 | 0.82 | 100
2205 | Bankura Division | Bankura Sadar Sub-Division | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at different work sites Kendbede (05), Bhelani (14), Dhaban (22), Sidhaberia (25) & Kuladabar (09) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001058/2023-2024 | 1174/BSD | 22/11/2023 | 15 | TAPAS DEY | 0.69 | 0.67 | 100
2206 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthol (PART) ,Bhelani (PART) Total House Hold- 140 | Assistant Engineer | Junior Engineer | VCH/000652/2022-2023 | FHTC/21 | 21/07/2022 | 0 | TAPAS KUMAR HAZRA | 1.68 | 0 | 0
2207 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthal (PART) Total House Hold- 140 | Assistant Engineer | Junior Engineer | VCH/000656/2022-2023 | FHTC/21 | 21/07/2022 | 0 | SAIKAT CHOWDHURY | 1.68 | 0 | 0
2208 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zone - A) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | VCH/002385/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 40 | 0 | 0
2209 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover from Dhabani village Starting point to Dhabani village (Koborsthan) , from Jamjuri to Kiaboti (Shib Mondir), from Lagalberia to Kawabasa & Metyala mouza by retrofitting of Bhulanpur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000268/2022-2023 | 2236/BQA | 09/12/2022 | 45 | SUBHADIP KOLEY | 56.09 | 56.09 | 0
2210 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rautara (41), Kawabasa (42), Panbaraj (43), Kiabati (44), Bhulanpur (45), Palash Bani (46), Gengari (47), Pratappur (48), Gopalpur (49), Dhabani (50), Metyala (51), Jamjuri (52), Churamanipur (53) & Shyam Nagar (156) mouzas by retrofitting Bhulanpur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 3005 nos. | Assistant Engineer | Junior Engineer | ORD/000421/2021-2022 | 471/BQA | 04/03/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 154.98 | 122.14 | 0
2211 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Rautara (41), Kawabasa (42), Panbaraj (43), Kiabati (44), Bhulanpur (45), Palash Bani (46), Gengari (47), Pratappur (48), Gopalpur (49), Dhabani (50), Metyala (51), Jamjuri (52), Churamanipur (53) & Shyam Nagar (156) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Bhulanpur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2021-2022 | 92/BSD | 28/01/2022 | 59 | TAPAS DEY | 1 | 0.8 | 80
2212 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2021-2022 | 568/BQA | 17/03/2022 | 0 | Resource Division | 18.51 | 0 | 0
2213 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
2214 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara,Ichharia,Dhallapara,Amchura, Kalaberia, Kalyanpur,Bhramanpara,Bhabanipur & Murhura. Total House Hold - 162 | Assistant Engineer | Junior Engineer | ORD/000004/2021-2022 | 1506/BQA | 25/06/2021 | 30 | MOHAN KUMAR ROY | 10.82 | 4.37 | 100
2215 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 135 | Assistant Engineer | Junior Engineer | ORD/000013/2020-2021 | 614/BQA | 10/02/2021 | 30 | MOHAN KUMAR ROY | 9.86 | 0 | 0
2216 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 140 | Assistant Engineer | Junior Engineer | ORD/000014/2020-2021 | 615/BQA | 10/02/2021 | 30 | MOHAN KUMAR ROY | 9.87 | 0 | 0
2217 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (PART-A) Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 1 no. i.e. Jamdoba-154, Habitation's Name:- Roypara, Kundupara, Palpara, Tantipara & Layekpara, Total House Hold - 72 | Assistant Engineer | Junior Engineer | ORD/000101/2020-2021 | 161/VSD | 18/09/2020 | 21 | MOHAN KUMAR ROY | 4.84 | 0 | 0
2218 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 65 | Assistant Engineer | Junior Engineer | ORD/000141/2020-2021 | 22/VSD | 20/01/2021 | 30 | MOHAN KUMAR ROY | 4.85 | 0 | 0
2219 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no 300mm X 200mm X 240m deep Tubewell (Replacement Tubewell) at Ichharia (P.H No-2) by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe of Panchal Zone-I water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 1329/BQA | 01/06/2023 | 670 | M/S PARAMESWAR CHOWDHURY | 18.4 | 0 | 0
2220 | Bankura Division | Brishnupur Sub-Division | FHTC Maintenance of Panchal Zone-I Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000299/2022-2023 | 317/VSD | 29/11/2022 | 15 | SUBHENDU SEKHAR GORAI | 0.97 | 0.97 | 0
2221 | Bankura Division | Brishnupur Sub-Division | Additional Laying distribution system of Augmentation of Panchal Zone -I piped Water Supply Scheme within Sonamukhi Block under Bishnupur Sub - Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001365/2024-2025 | 3127/BQA | 19/12/2024 | 378 | MUNSHI JAVEDUR JAMAN | 9.48 | 0 | 0
2222 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara, Ichharia, Dhallapara, Amchura, Kalaberia, Kalyanpur, Bhramanpara, Bhabanipur & Murhura. Total House Hold - 74. | Assistant Engineer | Junior Engineer | ORD/000147/2020-2021 | 56/VSD | 10/02/2021 | 21 | BIJOY KOLEY | 4.79 | 0 | 0
2223 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, | Assistant Engineer | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
2224 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 65 | Assistant Engineer | Junior Engineer | VCH/001584/2020-2021 |  | 15/03/2021 | 0 | MOHAN KUMAR ROY | 4.73 | 0 | 0
2225 | Bankura Division | Bankura Sadar Sub-Division | Bill for Road restoration Jhantipahari Kashipur Road from CH:0.060 KM to 0.76 KM permanent Restoration of road for the purpose of laying UPVC pipe line along and across of Jhantipahari High school- Chhatna Saltora Road | Assistant Engineer | Junior Engineer | BILL/00108/2026-2027 |  | 09/04/2026 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 59.37 | 0 | 0
2226 | Bankura Division | Bankura Sadar Sub-Division | rail bhoomi crossing seva | Assistant Engineer | Junior Engineer | BILL/00914/2023-2024 | FHTC/09 | 01/09/2023 | 0 | SOUTH EASTERN RAILWAY | 1.06 | 0 | 0
2227 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 01 no. 200 mm dia. Horizontal River Bed Tube Well with fitting of 200 mm dia. strainer with of collecting line in river DARAKESHWAR under Augmentation of Jhantipahari water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Zone- II) | Assistant Engineer | Junior Engineer | ORD/000151/2025-2026 | 1304/BQA | 17/06/2025 | 45 | COSMIC CONSTRUCTION | 8.96 | 0 | 0
2228 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of Augmentation of Sub-Surface Based Water Supply Scheme for Jhantipahari (Zone-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2024-2025 | 1809/BQA | 11/07/2024 | 120 | M/S TARUN KUMAR PATRA | 191.18 | 133.47 | 60
2229 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of Augmentation of Sub-Surface Based Water Supply Scheme for Jhantipahari (Zone-II) under Bankura Sub-Division of BANKURA Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000175/2024-2025 | 1812/BQA | 11/07/2024 | 539 | GOPAL CHANDRA CHOWDHURY | 129.15 | 0 | 6
2230 | Bankura Division | Bankura Sadar Sub-Division | Construction of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- I/O.H.R./7/2012 (Sheet 1 &2)with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. and allied works for Augmentation of JHANTIPAHARI W/S Scheme (Zone - I) under Bankura Divn, PHE Dte. (Part - A), and HDPE pipe line for distribution system with FHTC for the proposed Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000205/2022-2023 | 1970/BQA | 22/09/2022 | 1286 | M/S TARUN KUMAR PATRA | 328.26 | 286.87 | 73
2231 | Bankura Division | Bankura Sadar Sub-Division | Construction of 250 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- I/O.H.R./7/2012 (Sheet 1 &2)with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. and allied works for Augmentation of JHANTIPAHARI W/S Scheme (Zone - II) under Bankura Divn, PHE Dte. (Part - A), and HDPE pipe line for distribution system with FHTC for the proposed Augmentation of Jhantipahari piped W/S Scheme (Zone - II) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000209/2022-2023 | 1971/BQA | 22/09/2022 | 1287 | GOPAL CHANDRA CHOWDHURY | 393.86 | 316.91 | 80
2232 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 2269/BQA | 01/08/2023 | 974 | M/S TARUN KUMAR PATRA | 153.91 | 0 | 82
2233 | Bankura Division | Bankura Sadar Sub-Division | Construction of Guard Room & Toilet & Boundary Wall of Augmentation of Jhantipahari piped W/S Scheme and adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001410/2024-2025 | 27/BQA | 02/01/2025 | 90 | BROTIN UPADHYAY | 25.89 | 0 | 0
2234 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
2235 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 300 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Jhantipahari and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Zone- I) | Assistant Engineer | Junior Engineer | ORD/000236/2022-2023 | 362/BSD | 13/04/2022 | 15 | MABCO CONSULTANT | 1.85 | 1.85 | 0
2236 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Jhantipahari and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Zone- II) | Assistant Engineer | Junior Engineer | ORD/001102/2022-2023 | 361\BSD | 13/04/2022 | 15 | MOYTEC | 1.85 | 1.85 | 100
2237 | Bankura Division | Bankura Sadar Sub-Division | Construction of high lift pump house, construction of guard room and toilet and construction of WBSEDCL room at Jhantipahari water supply scheme (Zone - I) under Augmentation of Sub-Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District:- Bankura. | Assistant Engineer | Junior Engineer | ORD/001382/2024-2025 | 20/BQA | 02/01/2025 | 545 | SHYAMAL KUMAR DAS | 45.94 | 0 | 1
2238 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 252/1 -3) in between Jhantipahari Rly. Station (JPH) & Chhatna Rly. station (CJN) , P.S.Chhatna ,by Jack Pushing method with 300 mm (OD) Spirally welded MS Casing Pipe with 100 mm dia. MS carrier pipe under Augmentation of Jhantipahari piped Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001951/2024-2025 | 681/BQA | 12/03/2025 | 60 | GOPAL CHANDRA CHOWDHURY | 33.25 | 0 | 100
2239 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 305.79 | 0 | 0
2240 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 100KVA to 138 KVA at 11KV having Consumer ID : 942304300 at the premises at Jhantipahari water supply scheme(Intake), Jhantipahari, Bankura. | Assistant Engineer | Junior Engineer | BILL/00958/2024-2025 | BP-2024-25-236 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0
2241 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of sub Surface water base water supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Mechanical Division PHE Dte, Dist :Bankura under JJM. | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 1818/BMD | 09/08/2023 | 180 | EASTERN INDIA SALES & SERVICE | 176.93 | 116.89 | 45
2242 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2243 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Damodarpur Nabadeulvira | Assistant Engineer | Junior Engineer | BILL/00515/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
2244 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10985. | Assistant Engineer | Junior Engineer | BILL/00764/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
2245 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2246 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 35 | 48
2247 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2248 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Paharpur, Bheduasole | Assistant Engineer | Junior Engineer | BILL/00512/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
2249 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2250 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
2251 | Bankura Division | Bankura Sadar Sub-Division | New service connection for GHUGUJAN Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00055/2024-2025 |  | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
2252 | Bankura Division | Bankura Sadar Sub-Division | New service connection for KALIPAHARI HATGRAM Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00064/2024-2025 |  | 24/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2253 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Ghugujan" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00072/2024-2025 | BP-38/2024-25 | 06/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
2254 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2255 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10903 | Assistant Engineer | Junior Engineer | BILL/00905/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2256 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2257 | Bankura Division | Bankura Sadar Sub-Division | New service connection forGhugujan water supply scheme(SVS) under BMD PHE Dte.(SM/10903) | Assistant Engineer | Junior Engineer | BILL/01456/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
2258 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Jirabaid,Gp-anchuri under Ghugujun,Bankura-I block under PHE Dte.(SM/10903) | Assistant Engineer | Junior Engineer | BILL/01653/2025-2026 |  | 24/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2259 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 48
2260 | Bankura Division | Brishnupur Sub-Division | New service connection for Kishorkona (Dighalgram) Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00130/2024-2025 |  | 16/05/2024 | 0 | INDUS CCC | 0.11 | 0 | 0
2261 | Bankura Division | Brishnupur Sub-Division | New service connection for Kishorkona (Dighalgram) Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00159/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDUS CCC | 0.11 | 0 | 0
2262 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2263 | Bankura Division | Brishnupur Sub-Division | New connection of Mahamaya (colony) 51-III, Indus Block PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00840/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDUS CCC | 0.12 | 0 | 0
2264 | Bankura Division | Brishnupur Sub-Division | New connection of Kishorkona Jl No-115, Indus Block PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00841/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDUS CCC | 0.12 | 0 | 0
2265 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2266 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 63 | 48
2267 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2268 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2269 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
2270 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
2271 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Jovi C/o Sudip saha, Jovi, Ranibandh |  | Junior Engineer | BILL/00049/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
2272 | Bankura Division | RWS Bankura Sub-Division | Phe complex Ailakandi,Raghunathpur Nyada |  | Junior Engineer | BILL/00190/2023-2024 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
2273 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2274 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Uttarkamalpur Sonardanga |  | Junior Engineer | BILL/01223/2022-2023 | indpur/15 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
2275 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2276 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 24.76 | 48
2277 | Bankura Division | RWS Bankura Sub-Division | New Connection at Banktore, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00442/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
2278 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
2279 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2280 | Bankura Division | Khatra Sub-Division | P.H.E Dte. Damodarpur, Ps- Khatra Dist-Bankura | Assistant Engineer | Junior Engineer | BILL/00777/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
2281 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2282 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
2283 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Dhandora | Assistant Engineer | Junior Engineer | BILL/00175/2025-2026 |  | 25/04/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0
2284 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2285 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2286 | Bankura Division | Bankura Sadar Sub-Division | New service connection at kustore | Assistant Engineer | Junior Engineer | BILL/01409/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2287 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.6 | 48
2288 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2289 | Bankura Division | RWS Bankura Sub-Division | New Connection at Bheduya, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00426/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
2290 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2291 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
2292 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2293 | Bankura Division | RWS Bankura Sub-Division | New Connection at Bhandia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00435/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
2294 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2295 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
2296 | Bankura Division | RWS Bankura Sub-Division | New service connection for Bhalukbasa Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00122/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
2297 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2298 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2299 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
2300 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2301 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2302 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.6 | 48
2303 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2304 | Bankura Division | RWS Bankura Sub-Division | Paharia, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00760/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
2305 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2306 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 29.5 | 48
2307 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2308 | Bankura Division | Khatra Sub-Division | Quotation of WBSEDCL for the scheme of TSM/012322 |  | Junior Engineer | BILL/00847/2024-2025 | BP/459/2024-25 | 21/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0
2309 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2310 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
2311 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2312 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10975. |  | Junior Engineer | BILL/00769/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
2313 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakundi,Gangpur Keliapathar |  | Junior Engineer | BILL/01121/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
2314 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2315 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
2316 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site Pratappur, Gopinathpur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00283/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
2317 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2318 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2319 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
2320 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Tungi | Assistant Engineer | Junior Engineer | BILL/01575/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2321 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
2322 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Asude, (G.M Cold store), Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00286/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
2323 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2324 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2325 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW CONNECTION AT ASUDE | Assistant Engineer | Junior Engineer | BILL/01277/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
2326 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36 | 48
2327 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2328 | Bankura Division | RWS Bankura Sub-Division | New Service connection at Mini Piped w/s scheme at Village Chaitandihi, Po-Puara, under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00818/2023-2024 | FHTC/04 | 29/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
2329 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2330 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
2331 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Nutangram Radhamohanpur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00179/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
2332 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2333 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2334 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 35 | 48
2335 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BHAT PUSHKARANI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000373/2023-2024 | 2035/BQA | 24/07/2023 | 982 | DEBAKI RANJAN SARKAR | 573.53 | 248.99 | 70
2336 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2024-2025 | 2942/BQA | 21/11/2024 | 0 | Resource Division | 10.96 | 0 | 0
2337 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 162.57 | 0 | 0
2338 | Bankura Mechanical | Brishnupur Sub-Division | Bhat Pushkarini Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01514/2023-2024 | BP-2023-24-118 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.76 | 0 | 0
2339 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Bhat Pushkarini piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 772/BMD | 24/04/2023 | 180 | PRADIP KUMAR DHABAL | 39.43 | 20.99 | 54
2340 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KARACHMANI KHAYARSOL PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2023-2024 | 1053/BQA | 02/05/2023 | 1000 | PARAMESWAR CHOWDHURY | 239.64 | 79.47 | 3
2341 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Karachmani Khayarsol Piped Water Supply Scheme (SM/12420), 2 nos. sites of Bhat Pushkarini Piped Water Supply Scheme (SM/12416) & 2 nos. sites of Rani Bandh Piped Water Supply Scheme (SM/12415) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001891/2024-2025 | 569/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
2342 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000056/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 23.46 | 0 | 0
2343 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Karachmoni Khayrasol TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/12420) | Assistant Engineer | Junior Engineer | BILL/01255/2024-2025 | BP-2024-25-326 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
2344 | Bankura Mechanical | Brishnupur Sub-Division | Karachmani Khayarsol Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01515/2023-2024 | BP-2023-24-116 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
2345 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Karachmani Khayarsol piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 654/BMD | 17/04/2023 | 715 | UNITED TRADERS | 31.37 | 13.99 | 50
2346 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for proposed CWR water based Karachmani Khayarsol PWSS piped water supply scheme Block Sonamukhi under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000147/2024-2025 | 490/BMD | 09/07/2024 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 24.25 | 0 | 0
2347 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2348 | Bankura Division | Brishnupur Sub-Division | New Connection at Kamardihi,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00486/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
2349 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2350 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
2351 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2352 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2353 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18.6 | 48
2354 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 13 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002204/2024-2025 | 581\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 1.96 | 0 | 0
2355 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2356 | Bankura Division | Brishnupur Sub-Division | New Connection at Dumni,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00496/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
2357 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2358 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 33 | 48
2359 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - KHYERKANALI. No. of Mouza :- 04 nos, (Kharigara, Dhonara, Chingragoalasol & Madlakamdebpu), Total House Hold - 727 nos. | Assistant Engineer | Junior Engineer | ORD/000770/2022-2023 | 669/BQA | 28/03/2023 | 60 | I.R.CONSTRUCTION | 97.78 | 97.72 | 90
2360 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for jorabandh adibasi para | Assistant Engineer | Junior Engineer | BILL/00051/2024-2025 | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0
2361 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
2362 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 16 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002205/2024-2025 | 582\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.4 | 0 | 0
2363 | Bankura Division | Brishnupur Sub-Division | New Connection at Dakshinsol, PHE Dte | Assistant Engineer | Junior Engineer | BILL/00305/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
2364 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2365 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2366 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
2367 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Madhurpur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00173/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
2368 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2369 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2370 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 48
2371 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Bhabanipur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00190/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
2372 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2373 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2374 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
2375 | Bankura Division | Brishnupur Sub-Division | New Connection at Samanta Bandi, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00300/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
2376 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2377 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2378 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
2379 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2380 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2381 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 48
2382 | Bankura Division | Brishnupur Sub-Division | New Connection at Shibdanga, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00312/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
2383 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2384 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2385 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
2386 | Bankura Division | Brishnupur Sub-Division | New Connection at Tiura, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00298/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
2387 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2388 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2389 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
2390 | Bankura Division | Brishnupur Sub-Division | New Connection at Nachanhati, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00297/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
2391 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2392 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2393 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
2394 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2395 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2396 | Bankura Division | Bankura Sadar Sub-Division | Service connection charge | Assistant Engineer | Junior Engineer | BILL/01408/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
2397 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.6 | 48
2398 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-45, Mouza-Bera, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00274/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
2399 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2400 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2401 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38.6 | 48
2402 | Bankura Division | Khatra Sub-Division | Khatra - Ambikanagar Road from Ch. 6.328 km to Ch. 6.443 km ,from Ch. 6.593 km to Ch. 6.828 km and from Ch. 8.725 km to Ch. 9.325 km, Restoration work damage by PHE Department for laying pipe line under Bankura High way Division in the district of Bankura. Augmentation of MKR(Zone-I/B)W/S Scheme (SM/15001) | Assistant Engineer | Junior Engineer | BILL/01030/2024-2025 |  | 28/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 21.13 | 0 | 0
2403 | Bankura Division | Khatra Sub-Division | Khatra - Ambikanagar Road from Ch. 6.328 km to Ch. 6.443 km ,from Ch. 6.593 km to Ch. 6.828 km and from Ch. 8.725 km to Ch. 9.325 km, Restoration work damage by PHE Department for laying pipe line under Bankura High way Division in the district of Bankura. Augmentation of MKR(Zone-I/B)W/S Scheme (SM/15001) | Assistant Engineer | Junior Engineer | BILL/01245/2024-2025 | BP-347/2024-25 | 03/10/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 21.13 | 0 | 0
2404 | Bankura Division | Khatra Sub-Division | supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design ) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 1062/BQA | 03/05/2023 | 783 | GOUTAM BHATTACHRYYA | 200.64 | 40.92 | 30
2405 | Bankura Division | Khatra Sub-Division | Work order for Crossing of Road near Gorabari High School by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2024-2025 | 1835/BQA | 12/07/2024 | 352 | SWAPAN KUMAR CHANDRA | 7.3 | 0 | 80
2406 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
2407 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000537/2022-2023 | 435/BQA | 06/03/2023 | 1122 | NAYAN BARDHAN | 8.66 | 0 | 0
2408 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000538/2022-2023 | 436/BQA | 06/03/2023 | 849 | SOURAV SINHAMAHAPATRA | 4.63 | 0 | 0
2409 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000539/2022-2023 | 437/BQA | 06/03/2023 | 758 | ASOKE KUMAR SAHU | 19.49 | 0 | 0
2410 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-1B) (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 180/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.06 | 2.87 | 0
2411 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Phulhari village to Damdi Village (Existing pipeline damaged due to widening of Dam inspection road at country side of Dam) with all allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001608/2023-2024 | 677/BQA | 27/02/2024 | 25 | PRADYUMNA KOLEY | 5.95 | 5.93 | 90
2412 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline near Mukutmanipur Bus Stand to Phulhari Village (Existing pipeline damaged due to widening of Dam inspection road at country side of Dam) with all allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001609/2023-2024 | 678/BQA | 27/02/2024 | 25 | S. B. CONSTRUCTION | 7.05 | 7.04 | 90
2413 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 5.91 | 0 | 0
2414 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000200/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.31 | 0 | 0
2415 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 1B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 1121/BMD | 24/05/2023 | 30 | M/S DE ENGINEERING CONCERN | 2.28 | 0 | 0
2416 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 171.11 | 55
2417 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 11.73 | 0 | 0
2418 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000096/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 57.2 | 0 | 0
2419 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Jamkuri w/s (T/W-II) at Patrasayer block under BMD PHE Dte.(SM/14007) | Assistant Engineer | Junior Engineer | BILL/00366/2025-2026 |  | 12/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6 | 0 | 0
2420 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Jamkuri (T/W-II) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/14007) | Assistant Engineer | Junior Engineer | BILL/01466/2024-2025 | BP-2024-25-365 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0
2421 | Bankura Mechanical | Brishnupur Sub-Division | Jamkuri Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01667/2023-2024 | BP-2023-24-184 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.94 | 0 | 0
2422 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Jamkuri Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 236/BMD | 14/05/2025 | 90 | KINGKINI TRADERS | 11.67 | 0 | 0
2423 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 298.09 | 6
2424 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
2425 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Makarandapur Piped Water Supply Scheme (SM/14520) , 2 nos. sites of Hirapur Piped Water Supply Scheme (SM/12418) & 2 nos. sites of Nabasan Piped Water Supply Scheme (SM/13874) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001834/2024-2025 | 548/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.9 | 0 | 0
2426 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 188.77 | 0 | 0
2427 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Makarandapur Piped Water Supply Scheme t/w-II ,Makarandapur(Adhakata) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00131/2024-2025 | BP-2024-25-23 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0
2428 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Makarandapur Piped Water Supply Scheme t/w-I ,Makarandapur(Magura) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00132/2024-2025 | BP-2024-25-24 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0
2429 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Markandapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 458/BMD | 10/06/2025 | 90 | M/S SOMA ENTERPRISES | 11.86 | 0 | 0
2430 | Bankura Division | Brishnupur Sub-Division | JOYPUR TO GELIA ( WB-03-ADB-37 ) | Assistant Engineer | Junior Engineer | BILL/01441/2024-2025 | C032565786496 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 6.3 | 0 | 0
2431 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 244.21 | 6
2432 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
2433 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Kataban Piped Water Supply Scheme (SM/14526) & 3 nos. sites of Banna Piped Water Supply Scheme (SM/14525) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001837/2024-2025 | 550/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.75 | 0 | 0
2434 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000004/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 20.97 | 0 | 0
2435 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 174.48 | 0 | 0
2436 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Banna Piped Water Supply Scheme t/w-II ,Banna (Lokepur) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00137/2024-2025 | BP-2024-25-19 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0
2437 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Banna Piped Water Supply Scheme t/w-III ,Banna (Gelia Ruidas Para) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00139/2024-2025 | BP-2024-25-20 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.57 | 0 | 0
2438 | Bankura Mechanical | Brishnupur Sub-Division | Banna Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01496/2023-2024 | BP-2023-24-97 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
2439 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Banna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 453/BMD | 10/06/2025 | 90 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 12.93 | 0 | 0
2440 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 194.47 | 55
2441 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Deshra Piped Water Supply Scheme (SM/14246) & 3 nos. sites of Baragaria Piped Water Supply Scheme (SM/18789) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001878/2024-2025 | 556/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 100
2442 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000032/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 95.48 | 0 | 0
2443 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Deshra W/S Scheme. | Assistant Engineer | Junior Engineer | BILL/01349/2024-2025 | BP-2024-25-348 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.86 | 0 | 0
2444 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Deshra W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01352/2024-2025 | BP-2024-25-349 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 25.15 | 0 | 0
2445 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Deshra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000143/2025-2026 | 438/BMD | 10/06/2025 | 90 | KINGKINI TRADERS | 12.94 | 0 | 0
2446 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 01 (one) no. DTH Tube Well and Construction of High lift Pump House under Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000369/2024-2025 | 2348/BQA | 09/09/2024 | 30 | PARAMESWAR CHOWDHURY | 21.08 | 0 | 0
2447 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000439/2023-2024 | 2273/BQA | 01/08/2023 | 581 | PARAMESWAR CHOWDHURY | 228.56 | 60.36 | 24
2448 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection)¿ in connection with Jal Jeevan Mission (JJM) for ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Arjunpur No.of Mouza :- 02 nos. Arjunpur & Bahadurpur. Total House Hold -16 nos. | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 62/BSD | 24/01/2023 | 7 | COSMIC CONSTRUCTION | 0.96 | 0.96 | 100
2449 | Bankura Division | Bankura Sadar Sub-Division | Laying MS pipe line across culvert at near Khejurbedia village and construction of column & footing of ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001040/2023-2024 | 1143/BSD | 22/11/2023 | 15 | SONIA ENTERPRISE | 0.97 | 0.96 | 100
2450 | Bankura Division | Bankura Sadar Sub-Division | Crossing of Road by Jack pushing method with( 300 mm dia MS casing pipe ( 8mm thick for casing) & 150 mm dia MS carrier pipe for Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Location of Site:- Kadmaghati More & Near Arjunpur OHR site (NH-60 Road) | Assistant Engineer | Junior Engineer | ORD/001104/2024-2025 | 2973/BQA | 26/11/2024 | 90 | PARAMESWAR CHOWDHURY | 14.96 | 0 | 50
2451 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Arjunpur (Zone- N) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001196/2023-2024 | 449/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.46 | 0 | 100
2452 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000081/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.65 | 0 | 0
2453 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000239/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.65 | 0 | 0
2454 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00145/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2455 | Bankura Mechanical | Bankura Sadar Sub-Division | Load extension for Arjunpur augmentation OHR site (SM/16966) of Bankura I,II & Barjora water supply scheme under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01236/2024-2025 | BP-2024-25-311 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
2456 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Arjunpur ( Zone-N) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 505/BMD | 09/07/2024 | 120 | RAJIB COMPANY | 8.79 | 0 | 0
2457 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Arjunpur (Zone-N) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 1465/BMD | 18/07/2023 | 60 | DAS ENTERPRISE | 81.56 | 48.97 | 71
2458 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chaka (327), Poshda (328), Murachhara (329), Dheko (330), Chorkul (331) & Golor (332) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 6 Nos. Total Household- 1628 Nos. | Assistant Engineer | Junior Engineer | ORD/000081/2023-2024 | 1052/BQA | 02/05/2023 | 701 | AMIYA KUMAR BIT | 116.73 | 80.39 | 55
2459 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patmauli (305), Junbani (306), Katapal (339), Pechhela (340), Tikarpara (359), Mohanpur (361), Nischintapur (362), Dumuror (363) & Gobarda (364) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 9 Nos. Total Household- 1411 Nos. | Assistant Engineer | Junior Engineer | ORD/000083/2023-2024 | 1054/BQA | 02/05/2023 | 150 | SUBHADIP KOLEY | 104.71 | 85.76 | 50
2460 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baksi (333), Khayerbani (334), Jaynagar (335), Gopalpur (336), Phutiberya (337) & Bandarbani (338) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 6 Nos. Total Household- 1439 Nos. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1098/BQA | 10/05/2023 | 601 | SUBHENDU SEKHAR GORAI | 114.46 | 95.78 | 40
2461 | Bankura Division | Khatra Sub-Division | Work order for Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2024-2025 | 1831/BQA | 12/07/2024 | 262 | PRADIP CHAKRABORTY | 89.29 | 0 | 90
2462 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber with all other allied works of Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2025-2026 | 1311/BQA | 17/06/2025 | 199 | M/S BANERJEE & BANERJEE | 20.83 | 0 | 0
2463 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000053/2023-2024 | 2412/BQA | 18/08/2023 | 0 | Resource Division | 27.58 | 0 | 0
2464 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-IV/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2025-2026 | 1314/BQA | 17/06/2025 | 60 | GOUTAM BHATTACHARYYA | 30.64 | 0 | 0
2465 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting & fixing of HDPE pipeline of Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000882/2023-2024 | 3010/BQA | 03/11/2023 | 90 | ASHOK KUMAR DEY | 69.32 | 67.94 | 100
2466 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post under Lurka Zone-A of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/001014/2021-2022 | 21/KSD | 10/02/2022 | 30 | JAGABANDHU MONDAL | 4.66 | 0 | 0
2467 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber with all other allied works under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-V/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2025-2026 | 1313/BQA | 17/06/2025 | 122 | M/S TARUN KUMAR PATRA | 51.93 | 0 | 0
2468 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
2469 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2023-2024 | 2393/BQA | 16/08/2023 | 467 | MOHAMMAD HASAN KHAN | 8.64 | 6.43 | 90
2470 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000508/2023-2024 | 2356/BQA | 14/08/2023 | 596 | M/S TARUN KUMAR PATRA | 564.3 | 0 | 85
2471 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-5B) (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000971/2022-2023 | 188/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.87 | 3.82 | 0
2472 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001033/2023-2024 | 3439/BQA | 15/12/2023 | 45 | SOUMITRA KUMAR DAS | 19.54 | 15.12 | 90
2473 | Bankura Division | Khatra Sub-Division | "Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) Near Kharban More & (2) Near Khatra Adibasi Mahavidyalaya" | Assistant Engineer | Junior Engineer | ORD/001965/2024-2025 | 685/BQA | 12/03/2025 | 60 | M/S TARUN KUMAR PATRA | 15.12 | 0 | 0
2474 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 134.7 | 0 | 0
2475 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000208/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 23.5 | 0 | 0
2476 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1126/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
2477 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of KALYANI and adjoining mouzas W/S Scheme (Zone - B) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (FHTC-416 Nos.) | Assistant Engineer | Junior Engineer | ORD/000431/2023-2024 | 2010/BQA | 19/07/2023 | 986 | M/S TARUN KUMAR PATRA | 164.5 | 68.3 | 54
2478 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.48 | 0 | 0
2479 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000226/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.48 | 0 | 0
2480 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-B) & Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000552/2023-2024 | 1988/BMD | 28/08/2023 | 120 | R.N.S. TRADING | 48.56 | 0 | 0
2481 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Kalyani Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001097/2023-2024 | 3072/BMD | 12/03/2024 | 720 | P.K. ENGINEERING | 47.94 | 0 | 65
2482 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 1923/BQA | 13/07/2023 | 689 | SABIR ALI KHAN | 126 | 61.82 | 86
2483 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000383/2024-2025 | 2435/BQA | 25/09/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 2.53 | 0 | 100
2484 | Bankura Division | Bankura Sadar Sub-Division | Repairing and painting of Pump House , Chlorine room , Boundary wall & cleaning compound premises with other allied works under Chingani Water Supply Scheme of Block-Onda under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000410/2025-2026 | 1942/BQA | 09/09/2025 | 90 | TAPAS KUMAR HAZRA | 5.91 | 0 | 0
2485 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary Wall at Chingani CWR Site in connection with Jal Jeevan Mission (JJM) for for Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001376/2024-2025 | 55/BQA | 02/01/2025 | 454 | PRABIR BARDHAN | 8.31 | 0 | 1
2486 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000096/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.82 | 0 | 0
2487 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000271/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.82 | 0 | 0
2488 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01629/2023-2024 | BP-2023-24-157 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.2 | 0 | 0
2489 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of H/L and L/L Pumping machinery with other elector mechanical accessories for Augmentation of Chingani and Adjoining mouza water supply scheme at mouza Dhengasole under Bankura Mechanical Division, PHE Dte. Block Onda, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000122/2024-2025 | 432/BMD | 27/06/2024 | 360 | UNITED TRADERS | 40.96 | 0 | 70
2490 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chingani & Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 1987/BMD | 28/08/2023 | 120 | MITRA ENTERPRISE | 35.6 | 24.58 | 60
2491 | Bankura Division | Brishnupur Sub-Division | Nabanda- Joykrishnapur road from 25.800 km to 26.800 km restoration work of road due to laying of pipe lines for Ayodhya piped water supply scheme under JJM project by bankura division PHE Dte. under Bankura Highway Division .P.W.D in the district of Bankura | Assistant Engineer | Junior Engineer | BILL/02662/2023-2024 | FHTC/03 | 22/03/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 2.2 | 0 | 0
2492 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AJODHYA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000389/2023-2024 | 2049/BQA | 24/07/2023 | 979 | PRINCE INDUTRIES (INDIA) | 190.71 | 78.08 | 90
2493 | Bankura Division | Brishnupur Sub-Division | Additional sinking of 1 no 300mm X 200mm X 165m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Morar Zone-A of Bishnupur Block (JJM) under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000526/2025-2026 | 2134/BQA | 16/10/2025 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.04 | 0 | 0
2494 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Benda Water Supply Scheme (SM/17244), 2 nos. sites of Augmentation of Ajodhya Water Supply Scheme (SM/17246) & 2 no. sites of Augmentation of Dhengasole Water Supply Scheme (SM/17699) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001807/2024-2025 | 535/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.9 | 0 | 0
2495 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL procedure -A(2010) on turn key/full deposit basis for new service connection at Mouza Amrel of Ajodhya w/s scheme .SM/17246 | Assistant Engineer | Junior Engineer | BILL/00031/2024-2025 | BP-2024-25-14 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0
2496 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL Procedure -A(2010) on turn key /full deposit basis for new service connection at Mouza Paikpara of Ajodhya W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00112/2024-2025 | BP-2024-25-15 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.52 | 0 | 0
2497 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Ajodhya Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00172/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2498 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ajodhya piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 1782/BMD | 01/08/2023 | 720 | ABHIJIT MUKHERJEE | 52.17 | 32.83 | 63
2499 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High Lift pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ajodhya and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001098/2023-2024 | 3073/BMD | 12/03/2024 | 600 | TAPAN KUMAR SARKAR | 39.24 | 0 | 65
2500 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Tilna (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 1958/BQA | 18/07/2023 | 624 | NAYAN BARDHAN | 119.59 | 101.6 | 85
2501 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Tilna (Zone-E) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 2970/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.68 | 2.02 | 100
2502 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000105/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.25 | 0 | 0
2503 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000286/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.25 | 0 | 0
2504 | Bankura Division | Bankura Sadar Sub-Division | Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B). SM Code-SM/17257. (Bheduasole to Kalisen 222/17-19 to 222/18-20). Payment of Wayleave Plan &survey charges. | Assistant Engineer | Junior Engineer | BILL/00690/2024-2025 | BP-228/2024-25 | 21/08/2024 | 0 | SOUTH EASTERN RAILWAY | 0.11 | 0 | 0
2505 | Bankura Division | Bankura Sadar Sub-Division | Rail crossing Wayleave Facility charges of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B). SM/17257.Railway track at 222/17-19 in between Bheduaasol to Kalisen. | Assistant Engineer | Junior Engineer | BILL/00990/2024-2025 | BP-335/2024-25 | 27/09/2024 | 0 | SOUTH EASTERN RAILWAY | 6.21 | 0 | 0
2506 | Bankura Division | Bankura Sadar Sub-Division | Augmentation works for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2023-2024 | 1970/BQA | 18/07/2023 | 985 | PRINCE INDUTRIES (INDIA) | 196 | 100.94 | 90
2507 | Bankura Division | Bankura Sadar Sub-Division | Supplying of different dia. CIDF sluice valve PN- 1.0 in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A,B,C & D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000713/2022-2023 | 621/BQA | 23/03/2023 | 30 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.52 | 3.76 | 20
2508 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001143/2024-2025 | 2977/BQA | 26/11/2024 | 90 | LABIR MIRSHAD KHAN | 5.35 | 0 | 100
2509 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 2 (two) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) & 150 mm dia MS delivery main connecting line from 2 (two) nos Vertical Tube Well to OHR Inlet pipe in connection with Jal Jeevan Mission (JJM) for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001381/2024-2025 | 60/BQA | 03/01/2025 | 514 | JAI BHARAT COMMERCIAL CORPORATION | 30.08 | 0 | 0
2510 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 222/17 -19) in between Bheduasole(BXL) Rly. Station and Kalisen Rly. station in Kamalpur mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001954/2024-2025 | 682/BQA | 12/03/2025 | 60 | GOPAL CHANDRA CHOWDHURY | 51.58 | 0 | 0
2511 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000108/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.5 | 0 | 0
2512 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000291/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.5 | 0 | 0
2513 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at mouza Kotalpur of Aguriband Punisole Z-B ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00290/2024-2025 | BP-2024-25-62 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.08 | 0 | 0
2514 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-B) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000546/2023-2024 | 1982/BMD | 28/08/2023 | 120 | S.DUTTA | 45.88 | 29.29 | 64
2515 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineryes and H.T Switch Gear with allied works for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 1002/BMD | 24/09/2024 | 360 | PRADIP KUMAR DHABAL | 50.06 | 0 | 45
2516 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Additional Tubewell for Augmentation works for Aguribandh Punisole (Zone C) Water Supply Scheme in the Block Onda under Bankura Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000874/2024-2025 | 2036/BMD | 07/03/2025 | 120 | SWAPAN ENTERPRISE | 17.36 | 0 | 0
2517 | Bankura Division | Bankura Sadar Sub-Division | Laying of balance distribution system of Pipeline in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinabari (Zone - H) (Part) and Augmentation of Jamtora (Zone - G) (Part) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 1231/BQA | 02/06/2025 | 90 | ZAKIR HOSSIN MONDAL | 116.21 | 0 | 0
2518 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works, Construction of Pump House and 100 Cum. CWR for Augmentation of Chinabari (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000405/2023-2024 | 2092/BQA | 27/07/2023 | 270 | MADHU SUDAN RAKSHIT | 177.01 | 112.67 | 62
2519 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Chinabari (Zone-H) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000847/2023-2024 | 2973/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.09 | 1.86 | 100
2520 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Chinabari (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001667/2024-2025 | 358/BQA | 07/02/2025 | 509 | SAYED PAHALOWAN | 22.42 | 0 | 5
2521 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000140/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.81 | 0 | 0
2522 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000245/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.81 | 0 | 0
2523 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection charge for CHINABARI water supply scheme under BMD PHE Dte. (SM CODE : SM/17705) | Assistant Engineer | Junior Engineer | BILL/00630/2026-2027 |  | 10/06/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.46 | 0 | 0
2524 | Bankura Division | Brishnupur Sub-Division | Repair and Maintenance work of the Road from Palashdanga to T12 under Sonamukhi Block in the District to Bankura ,Vide Package No-WB-03-50, Road Length- 16.80 Km. Scheme code for i) chakai PWSS (ch-3000m to ch- 7100m)- SM/14245 ii) Birsinghapur pwss (ch- 9400m to 12100m)- SM/17223 iii) Dhulai PWSS (Ch-13100m to 16800m)- SM/18753 | Assistant Engineer | Junior Engineer | BILL/01251/2024-2025 | BP-439/2024-25 | 28/11/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 30.91 | 0 | 0
2525 | Bankura Division | Brishnupur Sub-Division | Requisition for shifting of 11kv HTOH for construction of PHE building at bishnupur mouza under Birsingpur PWSS p.s sonamukhi | Assistant Engineer | Junior Engineer | BILL/02155/2023-2024 | FHTC/11 | 27/11/2023 | 0 | PATRASAYER CCC | 6.09 | 0 | 0
2526 | Bankura Division | Brishnupur Sub-Division | Construction of Approach Road for (Head Work Site & 2nd Tubewell site), Guard wall at OHR side, HDD Boring, Additional pipeline for Laying Distribution Syatem in connection with Jal Jeevan Mission (JJM) Birsingpur Piped water Supply Scheme within Sonamukhi Block under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000254/2025-2026 | 1495/BQA | 07/07/2025 | 90 | PRINCE INDUSTRIES (INDIA) | 60.65 | 0 | 60
2527 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BRISINGHPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000340/2023-2024 | 1964/BQA | 18/07/2023 | 985 | PRINCE INDUTRIES (INDIA) | 559.16 | 355.23 | 85
2528 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Birsingpur Piped Water Supply Scheme (SM/17223), 2 nos. sites of Patsol Piped Water Supply Scheme (SM/14011) & 2 nos. sites of Telrui Piped Water Supply Scheme (SM/13711) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001896/2024-2025 | 574/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
2529 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2024-2025 | 712/BQA | 13/03/2025 | 0 | Resource Division | 15.71 | 0 | 0
2530 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000049/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 45.67 | 0 | 0
2531 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for BIRSINGPUR TW-2 (JL NO-48, PLOT-147)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00014/2024-2025 | BP-2024-25-16 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
2532 | Bankura Mechanical | Brishnupur Sub-Division | Birsingpur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01517/2023-2024 | BP-2023-24-112 | 22/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.1 | 0 | 0
2533 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Birsingpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000031/2023-2024 | 658/BMD | 17/04/2023 | 1080 | M/S S G ENTERPRISE | 40.22 | 13.3 | 33
2534 | Bankura Division | Khatra Sub-Division | Crossing of distribution pipeline accross Khatra-Simlapal road by adopting trench less technologies (e.g. Jack Pushing method etc.) for Proposed sub surface water based Tilaboni pipe water supply scheme under Jal Jeevan Mission programme of Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) Near Jarisa Primary School | Assistant Engineer | Junior Engineer | ORD/000187/2025-2026 | 1325/BQA | 17/06/2025 | 45 | PRADYUMNA KOLEY | 5.07 | 0 | 95
2535 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works, Construction of Clear Water Reservoir (100 Cum.), Pump House, Boundary Wall, Construction of Over Head Reservoir (250 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Tilaboni pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000826/2023-2024 | 2952/BQA | 31/10/2023 | 883 | RAISINHA INFRASTRUCTURE PVT. LTD. | 376.25 | 159.07 | 65
2536 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
2537 | Bankura Division | Khatra Sub-Division | Preparation of Detailed Project Report for Proposed sub surface water based Tilaboni pipe water supply scheme, under Bankura Division, Block : Simlapal, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001077/2023-2024 | 3539/BQA | 29/12/2023 | 30 | LEMNISCATE | 3.03 | 3.03 | 90
2538 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 2 nos. site of Proposed sub surface water based Tilaboni pipe water supply scheme [SM/17227], 2 nos. site of Augmentation of Piped Water Supply Scheme for Lakshmisagar [SM/18424] and 2 nos. site of Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) [SM/17295] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001923/2024-2025 | 167\KSD | 07/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 90
2539 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 15.5 | 0 | 0
2540 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000193/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 15.5 | 0 | 0
2541 | Bankura Mechanical | Khatra Sub-Division | New service connection at CWR site of Tilaboni Piped Water Supply Scheme Mouza-Jamda,Vill-Tilaboni GP- Lakshmisagar JL No-38, Plot no.-67 of Simlapal block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00985/2024-2025 | BP-2024-25-244 | 21/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.04 | 0 | 0
2542 | Bankura Mechanical | Khatra Sub-Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/01658/2023-2024 | BP-2023-24-180 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0
2543 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for proposed Sub surface water based Tilabani piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000617/2023-2024 | 2089/BMD | 12/09/2023 | 720 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 38.3 | 0 | 60
2544 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR JAMUNABANDH PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000374/2023-2024 | 2036/BQA | 24/07/2023 | 831 | DEBAKI RANJAN SARKAR | 457.16 | 205.77 | 90
2545 | Bankura Division | Brishnupur Sub-Division | Preparation of Detailed Project Report for Proposed ground water based JAMUNA BAND pipe water supply scheme, under Bankura Division Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001210/2023-2024 | 484/BQA | 09/02/2024 | 150 | ROY CHOWDHURY ASSOCIATES | 3.56 | 3.56 | 91
2546 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 15.8 | 0 | 0
2547 | Bankura Mechanical | Brishnupur Sub-Division | Jamuna Band Pipe Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00173/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
2548 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Jamunabundh TW-I W/S scheme under BMD.PHE Dte. SM/18037 | Assistant Engineer | Junior Engineer | BILL/00497/2024-2025 | BP-2023-24- | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
2549 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Jamunabundh T/W-II.SM/18037 | Assistant Engineer | Junior Engineer | BILL/01354/2024-2025 | BP-2024-25-330 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.18 | 0 | 0
2550 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jamuna Bandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 1771/BMD | 01/08/2023 | 692 | M/S BIPUL BANERJEE | 36.9 | 20.14 | 65
2551 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF SASHPUR ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000305/2023-2024 | 1919/BQA | 13/07/2023 | 990 | PRINCE INDUTRIES (INDIA) | 184.65 | 92.25 | 80
2552 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Sashpur (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001379/2024-2025 | 24/BQA | 02/01/2025 | 90 | SK FAZLUL ALAM | 12.94 | 0 | 70
2553 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00175/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2554 | Bankura Mechanical | Brishnupur Sub-Division | Load Enhancement charges for SASPUR ZONE-B Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00721/2024-2025 | BP-2024-25-198 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
2555 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Ashwinpur Boosting Tw Site of Sashpur Zone B water supply scheme under B.M.D PHE Dte.(SM/17421) | Assistant Engineer | Junior Engineer | BILL/01136/2024-2025 | BP-2024-25-283 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.07 | 0 | 0
2556 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01618/2023-2024 | BP-2023-24-152 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0
2557 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000530/2023-2024 | 1894/BMD | 17/08/2023 | 655 | M/S SAJAHAN CHOWDHURY | 75.78 | 42.72 | 60
2558 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A)under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000466/2023-2024 | 2321/BQA | 14/08/2023 | 270 | APURBA PATRA | 135.51 | 98.47 | 70
2559 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low Lift Pump House and Boundary Wall under Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001406/2024-2025 | 25/BQA | 02/01/2025 | 274 | ARIJIT GUHA | 14.44 | 0 | 0
2560 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000117/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.8 | 0 | 0
2561 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000280/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.8 | 0 | 0
2562 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur( Zone-A) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000557/2023-2024 | 1993/BMD | 28/08/2023 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 33.54 | 25.39 | 76
2563 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ratanpur Zone -A and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001100/2023-2024 | 3075/BMD | 12/03/2024 | 120 | INDRAJIT MITRA | 15.85 | 4.2 | 100
2564 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Bhutsahar Nadighat to Parasole village under Simlapal Block in the District of Bankura ,Vide Package No- Road Length-4.5 Km. ( Augmentation of water supply scheme for Baricha (Zone-B) under Simlapal water supply scheme (BRGF Ph-I). | Assistant Engineer | Junior Engineer | BILL/01439/2024-2025 | BP/569/2024-25 | 28/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.53 | 0 | 0
2565 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Bhutsahar Nadighat to Parasole village under Simlapal Block in the District of Bankura ,Vide Package No- Road Length-4.5 Km. ( Augmentation of water supply scheme for Baricha (Zone-B) under Simlapal water supply scheme (BRGF Ph-I). | Assistant Engineer | Junior Engineer | BILL/02120/2024-2025 | BP-536/2024-25 | 23/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.04 | 0 | 0
2566 | Bankura Division | Khatra Sub-Division | Work Order for Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 1826/BQA | 12/07/2024 | 478 | SUBHADIP KOLE | 69.99 | 0 | 70
2567 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Baricha Zone - B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2024-2025 | 2433/BQA | 25/09/2024 | 30 | CARTO | 1.89 | 1.84 | 90
2568 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2023-2024 | 2082/BQA | 27/07/2023 | 270 | UNIVERSAL CONSTRUCTION | 160.24 | 37.9 | 35
2569 | Bankura Division | Khatra Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/01/2024 to 30/06/2024. | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 370/KSD | 29/12/2023 | 182 | BISWAJIT LAI | 0.86 | 2.02 | 90
2570 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000186/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.34 | 0 | 0
2571 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | BILL/00217/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2572 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Baricha, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001969/2024-2025 | 665/BQA | 12/03/2025 | 142 | DAUD ALI KHAN | 13.59 | 0 | 90
2573 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 900 | A.K.INDUSTRIES | 127.79 | 0 | 85
2574 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Baricha Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000576/2023-2024 | 2037/BMD | 01/09/2023 | 1140 | S.P. CONSTRUCTION | 83.04 | 43.68 | 39
2575 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve Chamber, Construction Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000248/2025-2026 | 1456/BQA | 02/07/2025 | 90 | PRINCE INDUSTRIES (INDIA) | 147.3 | 0 | 0
2576 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of FHTC (Functional House Hold Tap Connection) and Construction of 3 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000308/2023-2024 | 1921/BQA | 13/07/2023 | 720 | PRINCE INDUTRIES (INDIA) | 279.75 | 83.43 | 82
2577 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/07/2025 to 30/09/2025. | Assistant Engineer | Junior Engineer | ORD/000339/2025-2026 | 328\KSD | 24/06/2025 | 78 | SEKH MUJTABA ALI | 0.37 | 0 | 0
2578 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000613/2022-2023 | 569/BQA | 17/03/2023 | 30 | M/S D.PALIT & CO. | 66.3 | 41.31 | 100
2579 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000828/2023-2024 | 2954/BQA | 31/10/2023 | 30 | MEASURE LAND | 3.9 | 3.86 | 95
2580 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 6 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17440] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001924/2024-2025 | 168\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
2581 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000187/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 5.24 | 0 | 0
2582 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00212/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2583 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01659/2023-2024 | BP-2023-24-178 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.83 | 0 | 0
2584 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set other allied work at Dubrajpur Zone-A & Dubrajpur Zone-B water supply scheme under Simlapal Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000199/2025-2026 | 645/BMD | 11/07/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 27.64 | 0 | 0
2585 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 800 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Dubrajpur, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001972/2024-2025 | 668/BQA | 12/03/2025 | 275 | TAPAN KUMAR MANDAL | 24.01 | 0 | 0
2586 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2024/BMD | 01/09/2023 | 120 | ABHIJIT MUKHERJEE | 70.19 | 48.69 | 65
2587 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro allied electro-mechanical accessories for Augmentation for Dubrajpur Zone-A piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Simlapal , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001091/2023-2024 | 3066/BMD | 12/03/2024 | 120 | ABHIJIT MUKHERJEE | 26.71 | 22.72 | 35
2588 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Dubrajpur Zone-A water supply scheme under Dubrajpur water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001093/2023-2024 | 3068/BMD | 12/03/2024 | 480 | JAL PRAVAHIKA PVT LTD | 40.01 | 34.66 | 70
2589 | Bankura Division | Brishnupur Sub-Division | Sinking of1 no. 300mm X 200mm X 250m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for INDAS piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2023-2024 | 2624/BQA | 21/09/2023 | 330 | D. S. ENTERPRISE | 18.93 | 11.26 | 70
2590 | Bankura Division | Brishnupur Sub-Division | Laying distribution system for INDAS W/S Scheme within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000672/2023-2024 | 2625/BQA | 21/09/2023 | 543 | SAIKAT CHOWDHURY | 8.89 | 0 | 70
2591 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for INDAS Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000675/2023-2024 | 2626/BQA | 21/09/2023 | 514 | ARIJIT GUHA | 6.6 | 6.54 | 92
2592 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 60 mtr long for INDAS water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000867/2023-2024 | 3016/BQA | 03/11/2023 | 60 | GOLAM KHAJA KHAN | 4.44 | 4.43 | 90
2593 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of INDAS W/S Scheme within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001239/2023-2024 | 629/BQA | 21/02/2024 | 405 | AMIYA KUMAR BIT | 67.79 | 50.98 | 15
2594 | Bankura Division | Brishnupur Sub-Division | Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Indas Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001355/2024-2025 | 3172/BQA | 24/12/2024 | 90 | BEAUTY CHATTERJEE | 26.99 | 0 | 0
2595 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00012/2024-2025 | BP-2024-25-8 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
2596 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00013/2024-2025 |  | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
2597 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Indas Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00188/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
2598 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for Augmentation of Indas water supply scheme under indus Block under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 428/BMD | 27/06/2024 | 300 | M/S BIPUL BANERJEE | 35.24 | 25.77 | 40
2599 | Bankura Division | Brishnupur Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Sonamukhi Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000215/2022-2023 | 1115/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 135.05 | 8.84 | 100
2600 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 220.98 | 55
2601 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000061/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 217.39 | 0 | 0
2602 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Birdabanpur Tw-1 Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00953/2024-2025 | BP-2024-25-225 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5 | 0 | 0
2603 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Brindabanpur Tw-2 water supply scheme under Bankura Mechanical Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00954/2024-2025 | BP-2024-25-226 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.45 | 0 | 0
2604 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Birdabanpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/ | Assistant Engineer | Junior Engineer | BILL/01246/2024-2025 | BP-2024-25-320 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0
2605 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Brindabanpur Piped Water Supply Scheme under BMD PHE Dte Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000061/2025-2026 | 257/BMD | 14/05/2025 | 90 | INDRAJIT MITRA | 12.68 | 0 | 0
2606 | Bankura Division | Brishnupur Sub-Division | Restoration work of MRL09- Ranpur to Belut under Patrasayer Block, PACKAGE NO.-WB-03-844 under PMGSY-III of Length 1,685.00 Mtr. due to laying of pipeline of Ghoradanga PWSS [SM/18611] by Bankura Division. PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01417/2025-2026 |  | 09/09/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 9.64 | 0 | 0
2607 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHORA DANGA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000479/2023-2024 | 2334/BQA | 14/08/2023 | 779 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 648.29 | 120.46 | 60
2608 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Ghora Danga Piped Water Supply Scheme (SM/18611), 2 nos. of Mukundapur Piped Water Supply Scheme (SM/14006) & 2 nos. of Jamkuri Piped Water Supply Scheme (SM/14007) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001888/2024-2025 | 566/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
2609 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 155.44 | 0 | 0
2610 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for ghoradanga(T/W-I) water supply scheme under BMD PHE Dte.(SM/18611) | Assistant Engineer | Junior Engineer | BILL/01356/2024-2025 | BP-2024-25-327 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
2611 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Ghoradanga (T/W-II) water supply scheme under BMD PHE Dte.(SM/18611) | Assistant Engineer | Junior Engineer | BILL/01464/2024-2025 | BP-2024-25-360 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.96 | 0 | 0
2612 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for newly sunk TW No I, TW No II of Ghora danga Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000114/2024-2025 | 425/BMD | 27/06/2024 | 600 | RAJIB COMPANY | 50.06 | 0 | 30
2613 | Bankura Division | Brishnupur Sub-Division | Construction of Approach Road for (Head Work Site & 2nd Tubewell site), Guard wall at OHR side, HDD Boring in connection with Jal Jeevan Mission (JJM) Rampur Piped water Supply Scheme within Patrasayer Block under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2025-2026 | 1496/BQA | 07/07/2025 | 90 | M/S TARUN KUMAR PATRA | 36.2 | 0 | 30
2614 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RAMPUR PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2023-2024 | 2328/BQA | 14/08/2023 | 961 | M/S TARUN KUMAR PATRA | 835.53 | 134.53 | 80
2615 | Bankura Division | Brishnupur Sub-Division | Jack Pushing under different place over Irrigation Canal & Bodai Nadi for Rampur Piped Water Supply Scheme under Patrasyer Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18349). | Assistant Engineer | Junior Engineer | ORD/001959/2024-2025 | 694/BQA | 12/03/2025 | 90 | M/S TARUN KUMAR PATRA | 123.94 | 0 | 80
2616 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for T/W III of Rampur water supply scheme at Patrasayer Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01137/2024-2025 | BP-2024-25-275 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.91 | 0 | 0
2617 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for P/H II of Rampur water supply scheme at Patrasayer Block (SM/18349) | Assistant Engineer | Junior Engineer | BILL/01138/2024-2025 | BP-2024-25-276 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0
2618 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for P/H no I of Rampur Water supply scheme at Patrasayer Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01139/2024-2025 | BP-2024-25-277 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.11 | 0 | 0
2619 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Rampur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 243/BMD | 14/05/2025 | 90 | CHAKRABORTY MINING & ENGINEERING. | 12.22 | 0 | 0
2620 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Rampur Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 1169/BMD | 01/06/2023 | 1080 | ORIENTAL ENGINEERING CO. | 68.63 | 23.1 | 33
2621 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR DALI MAHARA VILLAGE (Khayerkundi Schoolpara Mollan)) HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME.(SM/13257) | Assistant Engineer | Junior Engineer | BILL/00196/2024-2025 | BP-90/2024-25 | 05/06/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
2622 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
2623 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Bhagabundh to PatalKhuri (Bridge) to Cover Patal Khuri mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000290/2022-2023 | 506/BSD | 12/07/2022 | 15 | GOPAL CHANDRA CHOWDHURY | 4.63 | 4.63 | 0
2624 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from PatalKhuri (Bridge) to Patalkhuri village to cover Patal Khuri mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000292/2022-2023 | 508/BSD | 12/07/2022 | 15 | GOPAL CHANDRA CHOWDHURY | 4.16 | 4.15 | 0
2625 | Bankura Division | Bankura Sadar Sub-Division | Laying of 150 mm dia. DI pipe line for Ekteswar W/S Scheme & Restoration & laying of M.S. pipeline near Rajagram Bridge to Cover up Nandigram Village under Bankura Sadar Sub - Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000305/2022-2023 | 465/BSD | 06/06/2022 | 15 | SAMIRUDDIN KHAN | 4.36 | 0 | 100
2626 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 05 Nos. ( Patalkuri, Nandigram, Damadarpur, Agaya & Manusmara. ) Total House Hold - 1086, 1086/2=543 (PART-A) | Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 689/BQA | 30/03/2023 | 1098 | ASHOKE KUMAR DEY | 27.33 | 0 | 0
2627 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 05 Nos. ( Patalkuri, Nandigram, Damadarpur, Agaya & Manusmara. ) Total House Hold - 1086 , 1086/2=543 (PART-B) | Assistant Engineer | Junior Engineer | ORD/000832/2022-2023 | 690/BQA | 30/03/2023 | 45 | M/S KHAN ENTERPRISE | 27.33 | 0 | 0
2628 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from T05-Bhalukamari to Mamra under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-674, Road Length-10.21 Km. ( Augmentation of water supply scheme for Parsola (Zone-A) under Simlapal water supply scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01462/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 5.2 | 0 | 0
2629 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from L052 - Rasikpur to MDR under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-276, Road Length-3.24 Km. ( Augmentation of water supply scheme for Parsola (Zone-A) under Simlapal water supply scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | BILL/01465/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.47 | 0 | 0
2630 | Bankura Division | Khatra Sub-Division | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR and road crossing of distribution pipeline at different location by trenchless technologies with other allied works of Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2025-2026 | 1310/BQA | 17/06/2025 | 163 | PRADIP PATRA | 46.21 | 0 | 0
2631 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2023-2024 | 2957/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.98 | 2.92 | 98
2632 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works, Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas, Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of Pump House for Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001621/2024-2025 | 213/BQA | 17/01/2025 | 319 | PARTHA SARATHI PATRA | 197.98 | 0 | 81
2633 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Parsola, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001970/2024-2025 | 666/BQA | 12/03/2025 | 273 | ASHIS PAL | 18.77 | 0 | 0
2634 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01663/2023-2024 | BP-2023-24-173 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.43 | 0 | 0
2635 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation Submersible Pump Motor set, Neutralization System with other work at Parsola Zone -A water supply scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000200/2025-2026 | 646/BMD | 11/07/2025 | 90 | WEST BENGAL ENGINEERING CO. | 19.42 | 0 | 0
2636 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement for Augmentation for Parsola Zone -A water supply scheme under Parsala water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000324/2024-2025 | 865/BMD | 29/08/2024 | 120 | M/S DE ENGINEERING CONCERN | 5.93 | 0 | 0
2637 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of water supply scheme for Parsola Zone-A and its adjoining mouzas under simlapal water (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000992/2023-2024 | 2852/BMD | 09/02/2024 | 360 | R.N.S. TRADING | 122.02 | 0 | 35
2638 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - siringa, lowgram, , Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00264/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
2639 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2640 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2641 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW CONNECTION CHARGE AT SIRINGA | Assistant Engineer | Junior Engineer | BILL/01261/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
2642 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
2643 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Kawatanaga C/o Sudip Saha, Kawatanaga, Ranibandh |  | Junior Engineer | BILL/00041/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
2644 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2645 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2646 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
2647 | Bankura Division | Brishnupur Sub-Division | Restoration of work (for temporary & final closer) of a ghogh over the left Bank of the Kotulpur Branch Canal Below the PHE pipe line in between ch. 600.00 to 615.00 in Mouza-Hariharchak, G.P- Mirjapur, P.S & Block;- Kotulpur, dist:- Bankura under the Executive Engineer of Bankura Division, Public Health Engineering Directorate and of Kangsabati Canals Division No.-III, Bishnupur in connection with the Work ¿Supply, Delivery, Construction,Commissioning and Completion of all civil works including all allied, related and enabling works for Baragaria piped water supply scheme, Block- Kotulpur, Dist Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte.'' | Assistant Engineer | Junior Engineer | ORD/000131/2025-2026 | 1292/BQA | 17/06/2025 | 25 | SOUMEN KHAN | 11.77 | 0 | 90
2648 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BARAGARIA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 2743/BQA | 04/10/2023 | 540 | GOPAL CHANDRA CHOWDHURY | 962.3 | 301.37 | 65
2649 | Bankura Division | Brishnupur Sub-Division | Balanced ancillary works for Barageria Water Supply Scheme under Joypur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18789) | Assistant Engineer | Junior Engineer | ORD/001960/2024-2025 | 695/BQA | 12/03/2025 | 385 | GOPAL CHANDRA CHOWDHURY | 231.66 | 0 | 80
2650 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 139.21 | 0 | 0
2651 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Barageria W/S scheme | Assistant Engineer | Junior Engineer | BILL/00422/2024-2025 | BP-2024-25-99 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0
2652 | Bankura Mechanical | Brishnupur Sub-Division | New service connection charge at P/H-II of Bargeria W/S scheme | Assistant Engineer | Junior Engineer | BILL/00530/2024-2025 | BP-2024-25-139 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.79 | 0 | 0
2653 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Baragaria Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2066/BMD | 11/09/2023 | 1080 | M/S SOMA ENTERPRISES | 68.06 | 34.69 | 37
2654 | Bankura Division | Brishnupur Sub-Division | (site - Gopalganj, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00301/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
2655 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2656 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2657 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 54 | 48
2658 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 48 | 48
2659 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2660 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Banshketya Jiorda | Assistant Engineer | Junior Engineer | BILL/01029/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
2661 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2662 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
2663 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
2664 | Bankura Division | Brishnupur Sub-Division | New Connection at Parashia,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00487/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
2665 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
2666 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
2667 | Bankura Division | Brishnupur Sub-Division | Supply, delivery, construction, commissioning and completion of all civil works including all allied, related and enabling works for Biur piped water supply scheme, Block- Patrasayer, Dist- Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 2928/BQA | 26/10/2023 | 579 | DEBAKI RANJAN SARKAR | 793.67 | 0 | 60
2668 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Biur Piped Water Supply Scheme (SM/18754) & 3 nos. of Nandur Piped Water Supply Scheme (SM/18252) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001887/2024-2025 | 565/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
2669 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 101.52 | 0 | 0
2670 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Biur-Betur (T/W-I) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/18754) | Assistant Engineer | Junior Engineer | BILL/01485/2024-2025 | BP-2024-25-368 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.15 | 0 | 0
2671 | Bankura Mechanical | Brishnupur Sub-Division | Biur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01672/2023-2024 | BP-2023-24-174 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
2672 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk at TW No I and T.W No II of Biur piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | 424/BMD | 27/06/2024 | 360 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.86 | 0 | 33
2673 | Bankura Division | Brishnupur Sub-Division | The maintenance and repair estimate prepared in respect of the road namely NAFARDANGA TO RANPUR having Package No -WB-03-'14 under Sonamukhi block, in the District of Bankura under PMGSY ,WBSRDA , Bishnupur Division. Road Name : NAFARDANGA TO RANPUR From Nanda Mohanpur Piped Water Supply Scheme (SM/19178 ). | Assistant Engineer | Junior Engineer | BILL/00473/2025-2026 |  | 20/06/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 13.39 | 0 | 0
2674 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 0 | 55
2675 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Nanda Mohanpur Piped Water Supply Scheme (SM/19178) & 3 nos. sites of Ranpur Piped Water Supply Scheme (SM/14519) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001898/2024-2025 | 576/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
2676 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 250.24 | 0 | 0
2677 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW1 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-2024-25-317 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.49 | 0 | 0
2678 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01251/2024-2025 | BP-2024-25-318 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.67 | 0 | 0
2679 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01252/2024-2025 | BP-2024-25-319 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.95 | 0 | 0
2680 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandamohonpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000179/2025-2026 | 452/BMD | 10/06/2025 | 90 | M/S BIPUL BANERJEE | 12.36 | 0 | 0
2681 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline, providing FHTC (Functional House Hold Tap Connection), Construction of platform, valve chamber with all allied works of Zone-O (Madandihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000067/2025-2026 | 1007/BQA | 25/04/2025 | 304 | MANI SANKAR MUKHERJEE | 7.83 | 0 | 100
2682 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline with all allied works of Zone-M (Purnapani ) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000078/2024-2025 | 1498/BQA | 18/06/2024 | 440 | SUBHENDU BANERJEE | 8.12 | 0 | 0
2683 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Bhurkura more to Budhkhila village to increase pressure in Budhkhila (61), Atasole (61) & Susunigeria (77) Mouza and from Rudra more to Ladda Primary School to increse pressure in Ladda(33) Mouza under Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000088/2023-2024 | 1070/BQA | 04/05/2023 | 45 | MAYA CONSTRUCTION | 30.07 | 30.03 | 80
2684 | Bankura Division | Khatra Sub-Division | Laying of pipeline and Construction & Commissioning of FHTC (Functional House Hold Tap Connection) in different mouzas of Augmentation works for Zone-P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000192/2024-2025 | 2135/BQA | 07/08/2024 | 450 | TAPAN KUMAR MANDAL | 14.48 | 2.09 | 90
2685 | Bankura Division | Khatra Sub-Division | Laying pipeline and providing FHTC (Functional House Hold Tap Connection) of Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000253/2025-2026 | 1494/BQA | 07/07/2025 | 45 | SUBHENDU BANERJEE | 13.61 | 0 | 0
2686 | Bankura Division | Khatra Sub-Division | Construction of 200 Cum. Clear Water Reservoir, Pump House, Boundary Wall, Construction of 200 Cum. Over Head Reservoir with ancillary works, Laying Rising Main, Distribution pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-L (Dhankura) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000337/2024-2025 | 2298/BQA | 03/09/2024 | 270 | S. S. S. ENTERPRISES | 536.72 | 0 | 0
2687 | Bankura Division | Khatra Sub-Division | Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2024 to 28/02/2025. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000438/2024-2025 | 394/KSD | 25/06/2024 | 204 | BISWAJIT LAI | 0.97 | 0 | 0
2688 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
2689 | Bankura Division | Khatra Sub-Division | Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 02/01/2024 to 31/03/2024. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001134/2023-2024 | 369/KSD | 29/12/2023 | 78 | SEKH MUJTABA ALI | 0.37 | 1.16 | 0
2690 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/07/2024 to 30/09/2024. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000376/2024-2025 | 385\KSD | 24/06/2024 | 78 | SEKH MUJTABA ALI | 0.37 | 1.19 | 90
2691 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-M (Purnapani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000377/2023-2024 | 2070/BQA | 25/07/2023 | 861 | AJIT KUMAR PAUL | 96.97 | 80.37 | 83
2692 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/10/2024 to 31/12/2024. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000377/2024-2025 | 525/KSD | 17/09/2024 | 78 | SEKH MUJTABA ALI | 0.37 | 0 | 90
2693 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline in Thutasole (42) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ under Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000443/2023-2024 | 201/KSD | 18/07/2023 | 3 | SUBHENDU BANERJEE | 0.6 | 0.58 | 97
2694 | Bankura Division | Khatra Sub-Division | Work Order for Laying of UPVC pipeline at Baraban village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000445/2023-2024 | 253/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.94 | 0.94 | 20
2695 | Bankura Division | Khatra Sub-Division | Work Order for Laying of UPVC pipeline at Baraban village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000447/2023-2024 | 255/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.97 | 0.97 | 20
2696 | Bankura Division | Khatra Sub-Division | Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/04/2024 to 30/06/2024. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001505/2023-2024 | 136/KSD | 27/03/2024 | 78 | SEKH MUJTABA ALI | 0.37 | 1.15 | 0
2697 | Bankura Division | Khatra Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/03/2025 to 31/10/2025. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/002131/2024-2025 | 110\KSD | 25/02/2025 | 204 | BISWAJIT LAI | 0.97 | 0 | 0
2698 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000001/2024-2025 | 1528/BQA | 20/06/2024 | 0 | Resource Division | 55.44 | 0 | 0
2699 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000033/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 107.66 | 0 | 0
2700 | Bankura Division | Khatra Sub-Division | Work Order for Laying of UPVC pipeline at Indkuri village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000449/2023-2024 | 257/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.92 | 0.92 | 25
2701 | Bankura Division | Khatra Sub-Division | Work Order for Laying of UPVC pipeline at Indkuri village for increasing pressure in pipeline under Augmentation works for Zone-I (Hatikheda), under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 259/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.87 | 0.85 | 25
2702 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamarkuli (17) & Barda (18) mouzas of Augmentation of Zone-I (Hatikheda) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza - 2 Nos. Total Household- 315 Nos. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000473/2022-2023 | 288/BQA | 13/02/2023 | 701 | BEAUTY CHATTERJEE | 39.8 | 39.12 | 90
2703 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000476/2023-2024 | 2331/BQA | 14/08/2023 | 270 | SUBHENDU SEKHAR GORAI | 112.19 | 112.05 | 30
2704 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000610/2022-2023 | 567/BQA | 17/03/2023 | 866 | M/S TARUN KUMAR PATRA | 80.09 | 49.92 | 81
2705 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-O (Madandihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000709/2023-2024 | 2679/BQA | 26/09/2023 | 45 | SRIKANTA MONDAL | 51.87 | 49.98 | 49
2706 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000052/2023-2024 | 2412/BQA | 18/08/2023 | 0 | Resource Division | 18.48 | 0 | 0
2707 | Bankura Mechanical | Khatra Sub-Division | New service connection at JOVI village, Extension of Ghagra IBS Piped Water Supply Scheme's on-line boosting pump, Rudra gp of Ranibandh block under BMD PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00335/2025-2026 | 281/W-1714 | 19/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.32 | 0 | 0
2708 | Bankura Mechanical | Khatra Sub-Division | New service connection at Dhankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01477/2024-2025 | BP-2024-25-369 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.42 | 0 | 0
2709 | Bankura Mechanical | Khatra Sub-Division | New Service connection at Dhankura IBS OHR | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01479/2024-2025 |  | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.95 | 0 | 0
2710 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000743/2023-2024 | 2740/BQA | 04/10/2023 | 483 | AMIYA KUMAR BIT | 141.71 | 125.71 | 35
2711 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000838/2023-2024 | 2964/BQA | 31/10/2023 | 30 | MEASURE LAND | 4.45 | 3.69 | 80
2712 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - L (Dhankura) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000839/2023-2024 | 2965/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.09 | 2.09 | 90
2713 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - M (Purnapani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000840/2023-2024 | 2966/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.97 | 2.34 | 94
2714 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Zone - P (Nachna) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000841/2023-2024 | 2967/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.95 | 2.49 | 95
2715 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Rudra (Zone-J) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000198/2025-2026 | 644/BMD | 11/07/2025 | 90 | TAPAN KUMAR SARKAR | 11.33 | 0 | 0
2716 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Bansol More to Dhagara Post Office and interconnection with existing rising main to increase pressure in Bansol, Chaitandihi and Dhagara Mouza under Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001083/2023-2024 | 101/BQA | 08/01/2024 | 30 | SUBHENDU BANERJEE | 16.63 | 0 | 0
2717 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Dulalpur (32) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001125/2023-2024 | 246/BQA | 25/01/2024 | 30 | BIKASH MANDAL | 6.46 | 6.4 | 80
2718 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Nischintapur and Mahespur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001127/2023-2024 | 205/BQA | 24/01/2024 | 60 | GANGADHAR MONDAL | 20.23 | 19.62 | 90
2719 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Bansol More to Dhagara Post Office and interconnection with existing rising main to increase pressure in Bansol, Chaitandihi and Dhagara Mouza under Zone-I (Hatikheda) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001158/2023-2024 | 377/BQA | 07/02/2024 | 53 | SUBHENDU BANERJEE | 16.63 | 16.58 | 90
2720 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 1 No. CWR at OHR site, Construction of 2 Nos. Pump House at Tubewell site, Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-M (Purnapani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001409/2024-2025 | 50/BQA | 02/01/2025 | 90 | PRINCE INDUSTRIES (INDIA) | 60.85 | 0 | 0
2721 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Zone-I (Hatikheda), 1 no. site of Zone-J (Rudra), 3 nos. site of Zone-L (Dhankura), 1 no. site of Zone-M (Purnapani) under Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18403) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001914/2024-2025 | 158\KSD | 07/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 90
2722 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Zone-O (Madandihi), 1 no. site of Zone-P (Nachna) under Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18403), 3 nos. site of Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17251), 1 no. site of Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17429) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001915/2024-2025 | 159\KSD | 07/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 90
2723 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Budhkhila village to Tamakhun and Moukanali village for increasing pressure and construction of platform of Zone-J (Rudra) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001974/2024-2025 | 703/BQA | 12/03/2025 | 60 | SK. SAHAJAHAN | 28.68 | 0 | 80
2724 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/01/2025 to 31/03/2025. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001978/2024-2025 | 677\KSD | 30/12/2024 | 78 | SEKH MUJTABA ALI | 0.37 | 0 | 80
2725 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoirs (Back Wash Reservoir capacity 400 Cum. at WTP site and Over Head reservoir capacity 100 Cum. at Ambikanagar), chemical cum chlorination room, annex building, CFL 1 & 2, pump house, CWR, staff quarter, sub-station, WBSEDCL room and boundary wall within WTP site, intake pump house & intake access bridge including MS carrier pipe, pipe carrying bridge including MS pipe at different location, construction of guard room at Ambikanagar OHR site and construction of godown at WTP site with other allied works for Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001983/2024-2025 | 678/BQA | 12/03/2025 | 90 | PRINCE INDUSTRIES (INDIA) | 77.58 | 0 | 0
2726 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/04/2025 to 30/06/2025. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/002076/2024-2025 | 235\KSD | 28/03/2025 | 78 | SEKH MUJTABA ALI | 0.37 | 0 | 0
2727 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation works of gaseous chlorination system and neutralisation system at Mukutmanipur WTP(old) site under Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000006/2025-2026 | 141/BMD | 30/04/2025 | 360 | GOPAL CHANDRA CHOWDHURY | 41.17 | 0 | 90
2728 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply delivery & Installation of submersible Pump motor set & HSC Pump at CWR for Augmentation of WTP under Khatra-Hirbandh-Ranibandh Surface Water based piped water supply scheme under Bankura Mechanical Division, PHE Dte.Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000007/2025-2026 | 142/BMD | 30/04/2025 | 90 | MAHADEV ENTERPRISE | 94.53 | 0 | 0
2729 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation works of gaseous chlorination system and nutralisation system with related allied works at WTP of Hatikheda (Zone I), Rudra(Zone J), Dhankura(Zone L), Purnapani (Zone M), Madandihi (Zone O), Nachna(Zone P), under Khatra Hirbandh Ranibandh water supply scheme under BMD PHE DTE. Dist- Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000037/2025-2026 | 242/BMD | 14/05/2025 | 90 | DEY ENTERPRISE | 58.21 | 0 | 0
2730 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Proposed surface water based IBS of Dhankura for Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000149/2024-2025 | 492/BMD | 09/07/2024 | 480 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 96.64 | 0 | 41
2731 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of high lift and low lift Pumping machineries with other electro-mechanical accessories at tail end & CWR site for Augmentation works for Purnapani Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000171/2024-2025 | 513/BMD | 09/07/2024 | 120 | EASTERN INDIA SALES & SERVICE | 56.1 | 0 | 0
2732 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter with related allied works at Hatikheda (Zone-I), Rudra(Zone-J),Dhankura (Zone-L),Purnapani (Zone-M), Madandihi (Zone-O),Nachna (Zone-P), under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000415/2025-2026 | 2060/BMD | 18/09/2025 | 90 | ORIENTAL ENGINEERING CO. | 200.39 | 0 | 0
2733 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 30 | AMITAVA CHAKRABORTY | 29.71 | 0 | 0
2734 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 03 (Kantabandh ,Radharamanpur , Birsing pur ), Total House Hold -166 |  | Junior Engineer | ORD/000019/2020-2021 | 622/BQA | 10/02/2021 | 30 | DAUD ALI KHAN | 11.91 | 0 | 0
2735 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Elia Narayan pur , Rautora), Total House Hold -158 |  | Junior Engineer | ORD/000020/2020-2021 | 623/BQA | 10/02/2021 | 30 | DAUD ALI KHAN | 11.38 | 0 | 0
2736 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Asansola (Part- B), Total House Hold -169 |  | Junior Engineer | ORD/000022/2020-2021 | 624/BQA | 10/02/2021 | 30 | DAUD ALI KHAN | 12.18 | 0 | 0
2737 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- A), Total House Hold -175 |  | Junior Engineer | ORD/000023/2020-2021 | 625/BQA | 10/02/2021 | 30 | GOUTAM GHOSH | 12.66 | 0 | 0
2738 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- C), Total House Hold -106 |  | Junior Engineer | ORD/000026/2020-2021 | 628/BQA | 10/02/2021 | 30 | GOURANGA NANDI | 7.64 | 0 | 0
2739 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 |  | Junior Engineer | ORD/000027/2020-2021 | 629/BQA | 10/02/2021 | 30 | SUBHENDU SEKHAR GORAI | 18.25 | 0 | 0
2740 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ,Jagannath pur (Part- B), Total House Hold -107 |  | Junior Engineer | ORD/000096/2020-2021 | 627/BQA | 10/02/2021 | 30 | GOURANGA NANDI | 7.82 | 0 | 0
2741 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jamthol (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000204/2020-2021 | 989/BQA | 26/02/2021 | 30 | MRITYUNJOY HAZRA | 9.83 | 17.13 | 0
2742 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , Jagannath pur (Part- D), Asansola (Part- A), Total House Hold -170 |  | Junior Engineer | ORD/000209/2020-2021 | 626/BQA | 10/02/2021 | 30 | GOUTAM GHOSH | 12.29 | 0 | 0
2743 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | ORD/000399/2020-2021 | 857/BQA | 25/02/2021 | 30 | SUBHANKAR BANERJEE | 35.1 | 10.64 | 0
2744 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. |  | Junior Engineer | ORD/000407/2021-2022 | 15/ BSD | 07/01/2022 | 15 | DAUD ALI KHAN | 4.42 | 0 | 0
2745 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- (Dadimukha, Saldanga), Total House Hold - 55 nos. |  | Junior Engineer | ORD/000409/2021-2022 | 09/ BSD | 07/01/2022 | 12 | SUBHENDU SEKHAR GORAI | 3.96 | 0 | 0
2746 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line for increase pressure at Jaganathpur Somondal para of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Name of Mouza Jaganathpur) |  | Junior Engineer | ORD/000495/2022-2023 | 373/BQA | 23/02/2023 | 45 | GOURANGA NANDI | 2.08 | 0 | 0
2747 | Bankura Division | Bankura Sadar Sub-Division | Supply laying & fitting fixing of GI pipeline crossing at Sali river of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-17) |  | Junior Engineer | VCH/000876/2021-2022 |  | 07/09/2021 | 0 | DAUD ALI KHAN | 1.75 | 0 | 0
2748 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC line of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-18) |  | Junior Engineer | VCH/000877/2021-2022 |  | 07/09/2021 | 0 | DAUD ALI KHAN | 3.98 | 0 | 0
2749 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), |  | Junior Engineer | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0
2750 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 07 ( Kapista, Domnageria, Muradihi, Pachirdanga, Bhola, Kantakuli & Jagatraydihi), Total House Hold - 454 |  | Junior Engineer | VCH/002675/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PRINCE INDUTRIES (INDIA) | 1.26 | 0 | 0
2751 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Gaira, Arjunpur, Pairasol, & Bahadurpur.) Total House Hold - 50 |  | Junior Engineer | VCH/002676/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 1.39 | 0 | 0
2752 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Masanjhar OHR to Itamara Primary School to increase pressure in Talgaria (93) & Itamara (94) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2022-2023 | 1689/BQA | 27/07/2022 | 30 | M/S TARUN KUMAR PATRA | 11.48 | 10.85 | 0
2753 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangamati (141) & Masanjhar (142) mouzas by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2020-2021 | 190/BQA | 18/01/2021 | 30 | M/S TARUN KUMAR PATRA | 35.41 | 0 | 30
2754 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagaria (96), Pathardihi (97), Jambedya (98), Talgaria (93), Itamara (94) & Uganpathar (95) mouzas by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2020-2021 | 191/BQA | 18/01/2021 | 30 | M/S TARUN KUMAR PATRA | 33.54 | 0.82 | 30
2755 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 73. | Assistant Engineer | Junior Engineer | ORD/000149/2020-2021 | 57/VSD | 10/02/2021 | 21 | M/S BANERJEE & BANERJEE | 4.8 | 9.37 | 0
2756 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Talgaria (93), Itamara (94), Uganpathar (95), Benagaria (96), Pathardihi (97), Jambedya (98), Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangamati (141) & Masanjhar (142) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000522/2020-2021 | 320/KSD | 29/12/2020 | 61 | D. S. ENTERPRISE | 0.33 | 0 | 0
2757 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora-Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chatna, Name of OHR - Dhaban No.of Mouza :- 01, Dhaban (PART- )Total House Hold - 66 , Tender No - 79/20-21/EE/BQA W/O - 165/BSD dt 18.02.2021 | Assistant Engineer | Junior Engineer | VCH/000623/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SK SAMSA ALAM | 2.18 | 0 | 0
2758 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Masanjhar (142) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) | Assistant Engineer | Junior Engineer | VCH/001324/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 2.8 | 0 | 0
2759 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Namonahar), Total House Hold -413 | Assistant Engineer | Junior Engineer | VCH/001499/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ASHISH KUMAR SAMANTA | 3.86 | 0 | 0
2760 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 03 nos, (Brindajam, Simulbedia, Dhatala) Total House Hold -384, | Assistant Engineer | Junior Engineer | VCH/001855/2021-2022 | FHTC/03 | 03/11/2021 | 0 | GOUTAM BHOWMIK | 7.92 | 0 | 0
2761 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
2762 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-6) DPR no - 36.Block - Bishnupur, Name of OHR - Bhara,No. of Mouza :- 1 no. i.e. Harinagar-23 (220 out of 336), House Hold - 220 | Assistant Engineer | Junior Engineer | VCH/002493/2021-2022 | FHTC/3 | 03/02/2022 | 0 | MOHAN KUMAR ROY | 16.99 | 0 | 0
2763 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 4, Belebad,Moulahir, Mujrakundi Raj band Total House Hold -576 . | Assistant Engineer | Junior Engineer | VCH/002494/2021-2022 | FHTC/3 | 03/02/2022 | 0 | M/S BIPUL BANERJEE | 20.03 | 0 | 0
2764 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC Pipe Line to Cover Gourangadihi, Ladadihi, kesia, Bhedua, Kulpat bankati , gouripur mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002496/2021-2022 | FHTC/3 | 03/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.83 | 0 | 0
2765 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 05 Nos. Total Household - 853 Nos. ' | Assistant Engineer | Junior Engineer | VCH/002506/2021-2022 | FHTC/3 | 03/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 43 | 0 | 0
2766 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 |  | Junior Engineer | ORD/000252/2020-2021 | 2058/BQA | 29/12/2020 | 30 | JAGADISH BANERJEE | 11.87 | 0 | 0
2767 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-B) Total House Hold -115 |  | Junior Engineer | ORD/000253/2020-2021 | 2059/BQA | 29/12/2020 | 30 | SUBHANKAR BANERJEE | 11.8 | 0 | 0
2768 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-C) Total House Hold -116 |  | Junior Engineer | ORD/000254/2020-2021 | 2060/BQA | 29/12/2020 | 30 | SUBHANKAR BANERJEE | 11.93 | 0 | 0
2769 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 |  | Junior Engineer | ORD/000262/2020-2021 | 2061/BQA | 29/12/2020 | 30 | JAGADISH BANERJEE | 12.1 | 0 | 0
2770 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-E) Total House Hold -102 |  | Junior Engineer | ORD/000263/2020-2021 | 2062/BQA | 29/12/2020 | 30 | GOUTAM GHOSH | 10.52 | 0 | 0
2771 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Total House Hold -75 ( MB No - 4020) |  | Junior Engineer | VCH/001427/2020-2021 |  | 01/03/2021 | 0 | ASHISH PAUL | 4.56 | 0 | 0
2772 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-F) Total House Hold -101 |  | Junior Engineer | ORD/000264/2020-2021 | 2063/BQA | 29/12/2020 | 30 | GOUTAM GHOSH | 10.44 | 0 | 0
2773 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 5.09 | 0
2774 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban, No.of Mouza :- 1, Kumirdoha (PART) Total House Hold - 65. , |  | Junior Engineer | VCH/000266/2021-2022 | FHTC/12 | 23/04/2021 | 0 | KABISH KUMAR GHOSH | 4.34 | 0 | 0
2775 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban, No.of Mouza :- 1, Kumirdoha (PART) Total House Hold - 65. , |  | Junior Engineer | VCH/000268/2021-2022 | FHTC/12 | 23/04/2021 | 0 | SIMA KUMBHAKAR | 3.6 | 0 | 0
2776 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Jagadalla , Anchuri , Chaturdihi , Adharthol , & Kustora, |  | Junior Engineer | VCH/000274/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS DEY | 1.77 | 0 | 0
2777 | Bankura Division | Bankura Sadar Sub-Division | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-F) Total House Hold -101 ( MB No - 4023)" |  | Junior Engineer | VCH/001424/2020-2021 |  | 01/03/2021 | 0 | GOUTAM GHOSH | 7.64 | 0 | 0
2778 | Bankura Division | Bankura Sadar Sub-Division | "Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-E) Total House Hold -102 ( MB No - 4023)" |  | Junior Engineer | VCH/001425/2020-2021 |  | 01/03/2021 | 0 | GOUTAM GHOSH | 7.91 | 0 | 0
2779 | Bankura Division | Bankura Sadar Sub-Division | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 ( MB No - 4022)" |  | Junior Engineer | VCH/001434/2020-2021 |  | 01/03/2021 | 0 | JAGADISH BANERJEE | 8.2 | 0 | 0
2780 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 ( MB No - 4022)" |  | Junior Engineer | VCH/001435/2020-2021 |  | 01/03/2021 | 0 | JAGADISH BANERJEE | 9.26 | 0 | 0
2781 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-B) Total House Hold -115 . ( MB No - 3722)" |  | Junior Engineer | VCH/001437/2020-2021 |  | 01/03/2021 | 0 | SUBHANKAR BANERJEE | 8.38 | 0 | 0
2782 | Bankura Division | Bankura Sadar Sub-Division | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-C) Total House Hold -116 . ( MB No - 3722)" |  | Junior Engineer | VCH/001438/2020-2021 |  | 01/03/2021 | 0 | SUBHANKAR BANERJEE | 9.19 | 0 | 0
2783 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 03 nos. i.e. Abantika- 88 , Belthya- 89 & Deuli- 91, Total House Hold - 733 |  | Junior Engineer | VCH/002416/2021-2022 | FHTC/17 | 17/02/2022 | 0 | S B ASSOCIATES | 41.78 | 0 | 0
2784 | Bankura Division | Brishnupur Sub-Division | FHTC Maintenance of Indas Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000298/2022-2023 | 316/VSD | 29/11/2022 | 15 | GOUTAM GHOSH | 0.96 | 0 | 0
2785 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Indas W/S Scheme (PWSS) Block- Indas under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000671/2022-2023 | 514/BQA | 13/03/2023 | 90 | S B ASSOCIATES | 90.97 | 78.61 | 50
2786 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 8.74 | 0 | 0
2787 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2021-2022 | 477/BQA | 04/03/2022 | 0 | Resource Division | 7.94 | 0 | 0
2788 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 04 nos, (Jagannathbati Raghunathpur, Manoharpur & Mohanpur), Total House Hold - 516. |  | Junior Engineer | ORD/000061/2020-2021 | 468/BQA | 05/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.24 | 0 | 100
2789 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) |  | Junior Engineer | ORD/000175/2020-2021 | 718/BQA | 19/02/2021 | 30 | PARAMESWAR CHOWDHURY | 37.42 | 0 | 0
2790 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Chatraraj para,Garaipara,Napitpara & Mandalpara at Mouladanga mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000402/2022-2023 | 626/BSD | 16/08/2022 | 21 | GOURANGA CHATTERJEE | 2.47 | 0 | 0
2791 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- A) |  | Junior Engineer | ORD/000464/2021-2022 | 184/BSD | 18/02/2022 | 10 | GOURANGA CHATTERJEE | 3.5 | 0 | 0
2792 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- B) |  | Junior Engineer | ORD/000465/2021-2022 | 185/BSD | 18/02/2022 | 10 | M/S BANERJEE & BANERJEE | 3.48 | 0 | 0
2793 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from green Garden to Havey more to increase presure in Mithila & Monoharpur mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (ZONE-M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/001095/2021-2022 | 258/BSD | 15/03/2022 | 10 | M/S PARAMESWAR CHOWDHURY | 4.95 | 0 | 100
2794 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Mithila Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block |  | Junior Engineer | VCH/001478/2021-2022 |  | 08/10/2021 | 0 | PARAMESWAR CHOWDHURY | 4.65 | 0 | 0
2795 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 |  | Junior Engineer | VCH/001487/2021-2022 | FHTC/03 | 03/11/2021 | 0 | BEAUTY CHATTERJEE | 7.46 | 0 | 0
2796 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Haludkanali (113) mouza for construction and commissioning of FHTC ( functional house hold tap connection) by retrofitting zone - P ( Nachna) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF PH - I) at block-Ranibandh dist - Bankura under jal jeevan mission programme under Khatra sub - Division PHE Dte. part A sl no - 08 |  | Junior Engineer | VCH/001724/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PRADYUMNA KOLEY | 4.8 | 0 | 0
2797 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 03 (Balia, Barabagan & Kasibediya (PART) Total House Hold -399 | Assistant Engineer | Junior Engineer | ORD/000189/2020-2021 | 2130/BQA | 31/12/2020 | 30 | KHAN ENTERPRISE | 44.34 | 0 | 0
2798 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 02 ( Kasibediya (PART) & Chingra.) Total House Hold -398 | Assistant Engineer | Junior Engineer | ORD/000190/2020-2021 | 2131/BQA | 31/12/2020 | 30 | KHAN ENTERPRISE | 44.28 | 0 | 0
2799 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 4.54 | 0
2800 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Beladi more to Barabagan Junior High School to Cover Balia, Basulitora, Rangametya mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-I ) | Assistant Engineer | Junior Engineer | ORD/000450/2021-2022 | 572/BQA | 15/03/2022 | 45 | PARAMESWAR CHOWDHURY | 21.15 | 17.4 | 0
2801 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Beladi more to Barabagan Junior High School to Cover Balia, Basulitora, Rangametya mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-II ) | Assistant Engineer | Junior Engineer | ORD/000452/2021-2022 | 573/BQA | 15/02/2022 | 45 | AMITAVA CHAKRABORTY | 21.15 | 17.36 | 0
2802 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No. of Mouza :- 02 no, Arrah (Part), Khudrabanagram Total House Hold - 383. | Assistant Engineer | Junior Engineer | VCH/002452/2021-2022 | FHTC/1 | 01/02/2022 | 0 | NAYAN BARDHAN | 28.49 | 0 | 0
2803 | Bankura Division | Khatra Sub-Division | Supply of stationary article for office of Bankura Division, PHE Dte. for the month sep | Assistant Engineer | Junior Engineer | BILL/00044/2022-2023 |  | 05/12/2022 | 0 | BANKURA WHOLESALE COSUMERS' CO-OPERATIVE SOCITY LTD. | 0.4 | 0 | 0
2804 | Bankura Division | Khatra Sub-Division |  | Assistant Engineer | Junior Engineer | BILL/00045/2022-2023 |  | 06/12/2022 | 0 | PRADIP KR. BANERJEE | 0.07 | 0 | 0
2805 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. | Assistant Engineer | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 40.2 | 3.41 | 0
2806 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shukni Basa (181), Majgerya (182), Birbhandh (183), Dudhenala (184), Khunta Banda (185) & Kharujhor (186) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household - 527 Nos. | Assistant Engineer | Junior Engineer | ORD/000032/2021-2022 | 1779/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 36.83 | 49.26 | 0
2807 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baragram (86) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 196 Nos. " | Assistant Engineer | Junior Engineer | ORD/000033/2021-2022 | 1780/BQA | 09/07/2021 | 30 | DAUD ALI KHAN | 12.24 | 0.76 | 0
2808 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surulia (87) and Jalneja (88) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 145 Nos. " | Assistant Engineer | Junior Engineer | ORD/000034/2021-2022 | 1781/BQA | 09/07/2021 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 9.23 | 0 | 20
2809 | Bankura Division | Khatra Sub-Division | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000775/2021-2022 | 111/KSD | 15/03/2022 | 365 | RAJ KUMAR BAURI | 0.01 | 0 | 80
2810 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2021-2022 | 273/BQA | 11/02/2022 | 0 | Resource Division | 87.84 | 0 | 0
2811 | Bankura Division | Khatra Sub-Division | Route survey Preparation of detailed project report for Agumentation of Jhantipahari piped water supply scheme zone - ll under Bankura sadar sub - Division of Bankura Division, PHE Dte. under Jal Swapna project sl no - 03 W/O NO - 903/BSD dt. 24.09.2021 | Assistant Engineer | Junior Engineer | VCH/000225/2022-2023 | FHTC/08 | 08/04/2022 | 0 | LEMNISCATE | 3.04 | 0 | 0
2812 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Purnapani (89) and Pirargari (95) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 197 Nos. " | Assistant Engineer | Junior Engineer | ORD/000035/2021-2022 | 1782/BQA | 09/07/2021 | 30 | DAUD ALI KHAN | 12.28 | 0.77 | 0
2813 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhabanipathar (90) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 114 Nos. " | Assistant Engineer | Junior Engineer | ORD/000036/2021-2022 | 1783/BQA | 09/07/2021 | 30 | SUNIL KUMAR MANDAL | 7.37 | 0 | 0
2814 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhadkidihi (92) and Puada (94) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 222 Nos. | Assistant Engineer | Junior Engineer | ORD/000037/2021-2022 | 1784/BQA | 09/07/2021 | 30 | BEAUTY CHATTERJEE | 13.71 | 0.86 | 0
2815 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nutandihi (93) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. ,Total Household - 171 Nos. " | Assistant Engineer | Junior Engineer | ORD/000038/2021-2022 | 1785/BQA | 09/07/2021 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 10.68 | 0 | 0
2816 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 05 Nos. Total Household - 853 Nos. " | Assistant Engineer | Junior Engineer | ORD/000039/2021-2022 | 1786/BQA | 09/07/2021 | 30 | PARTHA PRATIM CHATAIT | 56.47 | 0 | 0
2817 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover gara mouza for const. and commissioning of FHTC with Jal Jeevan mission (JJM) JAl Swapna of Jarehira ( Zone-B) under Saltora Chhatna Block W/S scheme (BRGF Ph-I ) under bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002476/2021-2022 | FHTC/19 | 19/02/2022 | 0 | SK. ALAMAGIR ALAM | 3.14 | 0 | 0
2818 | Bankura Division | Khatra Sub-Division | laying distribution system of UPVC pipe line with allied works from Oltotr to Madhavpur Village & Bahadur pur Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002521/2021-2022 | FHTC/22 | 22/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.83 | 0 | 0
2819 | Bankura Division | Khatra Sub-Division | Laying distribution system of UPVC pipe line with allied works from Near Beliatore police Station air valve to Oltora Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002638/2021-2022 | FHTC/01 | 01/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.88 | 0 | 0
2820 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Churapathar (106) & Nachna (107) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 402 Nos. " | Assistant Engineer | Junior Engineer | ORD/000040/2021-2022 | 1787/BQA | 09/07/2021 | 30 | PRADYUMNA KOLEY | 26.36 | 50.61 | 0
2821 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Birkham (110) mouza under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 410 Nos. " | Assistant Engineer | Junior Engineer | ORD/000041/2021-2022 | 1788/BQA | 09/07/2021 | 30 | PARTHA PRATIM CHATAIT | 27.18 | 0 | 0
2822 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Buriam (112) & Haludkanali (113) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 02 Nos. Total Household - 420 Nos. | Assistant Engineer | Junior Engineer | ORD/000042/2021-2022 | 1789/BQA | 09/07/2021 | 30 | SUBHADIP KOLEY | 27.68 | 0 | 0
2823 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haludkanali (102) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000044/2020-2021 | 131/KSD | 12/02/2021 | 15 | SUBHADIP KOLEY | 4.1 | 0 | 0
2824 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haludkanali (102) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000045/2020-2021 | 132/KSD | 12/02/2021 | 15 | PRADYUMNA KOLEY | 3.92 | 0 | 0
2825 | Bankura Division | Khatra Sub-Division | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 | Assistant Engineer | Junior Engineer | VCH/002642/2021-2022 | FHTC/10 | 10/02/2022 | 0 | CLIFFORD FACILITY SERVICES PVT. LTD. | 6.16 | 0 | 0
2826 | Bankura Division | Khatra Sub-Division | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 | Assistant Engineer | Junior Engineer | VCH/002643/2021-2022 | FHTC/10 | 10/02/2022 | 0 | CLIFFORD FACILITY SERVICES PVT. LTD. | 7.37 | 0 | 0
2827 | Bankura Division | Khatra Sub-Division | Prayer for release fund for laboratory personal's for the month of Sep 2021 to Oct 2021 "MMKS/221/ Nov 2021 dt - 16.11.2021" | Assistant Engineer | Junior Engineer | VCH/002644/2021-2022 | FHTC/10 | 10/02/2022 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.66 | 0 | 0
2828 | Bankura Division | Khatra Sub-Division | Prayer for release fund for laboratory personal's for the Durga puja Festival 2021 "MMKS/219/ Sep 2021 dt - 02.09.2021" | Assistant Engineer | Junior Engineer | VCH/002645/2021-2022 | FHTC/10 | 10/02/2022 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.14 | 0 | 0
2829 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Surulia (87) & Jalneja (88) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2022-2023 | 1684/BQA | 27/07/2022 | 30 | SOURAV SINHA MAHAPATRA | 5.68 | 0 | 0
2830 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Kankri Jharna More to Barikul Primary School to increase pressure in Barikul (179) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000061/2022-2023 | 1685/BQA | 27/07/2022 | 30 | APEX ENTERPRISE | 7.7 | 0 | 0
2831 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | ORD/000067/2021-2022 | 2289/BQA | 06/09/2021 | 45 | M/S TARUN KUMAR PATRA | 191.43 | 0 | 0
2832 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82) Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | ORD/000068/2021-2022 | 2290/BQA | 06/09/2021 | 45 | GOPAL CHANDRA CHOUDHURY | 251.08 | 0 | 0
2833 | Bankura Division | Khatra Sub-Division | Prayer for release fund for laboratory personal's for the month of Sep 2021 to Oct 2021 SBUS/03/2021-22 dt - 02.07.2021 | Assistant Engineer | Junior Engineer | VCH/002646/2021-2022 | FHTC/10 | 10/02/2022 | 0 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.66 | 0 | 0
2834 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to Jantadumur mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Dhankura Zone L of Khatra Hirbandh Ranibandh w/s scheme (Part -B) | Assistant Engineer | Junior Engineer | VCH/003023/2021-2022 | FHTC/28 | 28/03/2022 | 0 | SUBHENDU BANERJEE | 4.5 | 0 | 0
2835 | Bankura Division | Khatra Sub-Division | Preparation of detailed project report for Augmentation of Saltora piped water supply scheme block - Saltora district under Bankura Division, PHE Dte. under Jal Swapna project zone - l | Assistant Engineer | Junior Engineer | VCH/003126/2021-2022 | FHTC/31 | 31/03/2022 | 0 | LEMNISCATE | 3.18 | 0 | 0
2836 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madandihi (101) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000073/2020-2021 | 133/KSD | 12/02/2021 | 15 | BISWAJIT LAI | 4.19 | 0 | 0
2837 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 45 | ALOK ENTERPRISE | 135.35 | 59.06 | 0
2838 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000085/2020-2021 | 134/KSD | 12/02/2021 | 15 | BIKASH MANDAL | 3.83 | 0 | 0
2839 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000086/2020-2021 | 135/KSD | 12/02/2021 | 15 | TAPAN KUMAR MANDAL | 3.69 | 0 | 0
2840 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000087/2020-2021 | 136/KSD | 12/02/2021 | 15 | SUNIL KUMAR MANDAL | 3.65 | 0 | 0
2841 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000091/2020-2021 | 137/KSD | 12/02/2021 | 15 | SUNIL KUMAR MANDAL | 3.65 | 0 | 0
2842 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamardanga (99) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000093/2020-2021 | 138/KSD | 12/02/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 3.44 | 0 | 0
2843 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamardanga (99) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000099/2020-2021 | 139/KSD | 12/02/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 3.4 | 0 | 0
2844 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (98) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000102/2020-2021 | 140/KSD | 12/02/2021 | 15 | ASOKE KUMAR SAHU | 3.98 | 0 | 0
2845 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (98) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000104/2020-2021 | 141/KSD | 12/02/2021 | 15 | ASOKE KUMAR SAHU | 3.84 | 0 | 58
2846 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline from Atchala to Jaynagar Primary School to increase pressure to cover Jaynagar (47) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 207/KSD | 03/06/2022 | 20 | M/S. AMAL KUMAR SARKAR | 3.78 | 0 | 0
2847 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Madankata (176) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 208/KSD | 03/06/2022 | 20 | M/S. AMAL KUMAR SARKAR | 4.62 | 0 | 0
2848 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000120/2022-2023 | 322/KSD | 01/08/2022 | 15 | D. S. ENTERPRISE | 3.93 | 0 | 0
2849 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Thutasole (42) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000123/2022-2023 | 325/KSD | 01/08/2022 | 15 | SUBHENDU BANERJEE | 2.34 | 0 | 0
2850 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2021-2022 | 2828/BQA | 16/11/2021 | 30 | TAPAS GHOSH | 12.37 | 0.09 | 0
2851 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in different mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) & Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000220/2021-2022 | 622/KSD | 09/08/2021 | 92 | TAPAS DEY | 4.56 | 0.76 | 0
2852 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Madandihi(101) & Malcharar (100) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000233/2021-2022 | 675/KSD | 29/09/2021 | 15 | SUBHADIP KOLEY | 4.36 | 0 | 0
2853 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jamda (98) & Kamardanga (99) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000240/2021-2022 | 674/KSD | 29/09/2021 | 15 | EDER ALI KHAN | 4.23 | 0 | 0
2854 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000273/2021-2022 | 679/KSD | 29/09/2021 | 15 | SUBHADIP KOLEY | 1.8 | 0 | 0
2855 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000274/2021-2022 | 646/KSD | 17/09/2021 | 15 | SAMIRUDDIN KHAN | 4.26 | 0 | 0
2856 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000275/2021-2022 | 647/KSD | 17/09/2021 | 15 | DAUD ALI KHAN | 3.52 | 0 | 0
2857 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Purnapani (89) & Pirargari (95) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000276/2021-2022 | 651/KSD | 17/09/2021 | 15 | DAUD ALI KHAN | 1.35 | 0 | 0
2858 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Bhabanipathar (90) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000280/2021-2022 | 719/KSD | 12/11/2021 | 15 | TAPAN KUMAR MANDAL | 1.57 | 0 | 0
2859 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000283/2021-2022 | .649/KSD | 17/09/2021 | 15 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0
2860 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000322/2021-2022 | 720/KSD | 12/11/2021 | 15 | UNITED TRADERS | 4.97 | 0 | 0
2861 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000323/2021-2022 | 721/KSD | 12/11/2021 | 15 | UNITED TRADERS | 3.78 | 0 | 0
2862 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Paryasa (169) & Purnapani Chhota Tung (170) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) | Assistant Engineer | Junior Engineer | ORD/000324/2021-2022 | 722/KSD | 12/11/2021 | 15 | UNITED TRADERS | 2.87 | 0 | 0
2863 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 12) | Assistant Engineer | Junior Engineer | ORD/000325/2021-2022 | 723/KSD | 12/11/2021 | 15 | UNITED TRADERS | 4.9 | 0 | 0
2864 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No. 13) | Assistant Engineer | Junior Engineer | ORD/000326/2021-2022 | 724/KSD | 12/11/2021 | 15 | UNITED TRADERS | 4.01 | 0 | 0
2865 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Birbhandh (183) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) | Assistant Engineer | Junior Engineer | ORD/000327/2021-2022 | 725/KSD | 12/11/2021 | 15 | UNITED TRADERS | 3.56 | 0 | 0
2866 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Dhadanga (97) & Haludkanali (102) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000334/2021-2022 | 658/KSD | 17/09/2021 | 15 | SUBHENDU BANERJEE | 3.36 | 0 | 0
2867 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Dhadanga (97) & Haludkanali (102) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O ( Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 16) | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 659/KSD | 17/09/2021 | 15 | SUBHENDU BANERJEE | 3.48 | 0 | 0
2868 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dhadkidihi (92) & Puada (94) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 648/KSD | 17/09/2021 | 15 | BEAUTY CHATTERJEE | 4.5 | 0 | 0
2869 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Ghagra (115) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000364/2021-2022 | 811/KSD | 15/12/2021 | 15 | SUBHADIP KOLEY | 5 | 0 | 0
2870 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000365/2021-2022 | 813/KSD | 15/12/2021 | 15 | PRADYUMNA KOLEY | 4.71 | 0 | 0
2871 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baragram (86) Mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000384/2021-2022 | 816/KSD | 15/12/2021 | 15 | SAMIRUDDIN KHAN | 2.6 | 2.59 | 0
2872 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 | Assistant Engineer | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 30 | NAYAN BARDHAN | 14.75 | 26.75 | 0
2873 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Rajabandh to Dhanara to increase pressure at Dhanara (36) & Gholkuri (27) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ of Augmentation of Zone-J (Rudra) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000472/2022-2023 | 287/BQA | 13/02/2023 | 45 | SAMIRUDDIN KHAN | 8.85 | 0 | 0
2874 | Bankura Division | Khatra Sub-Division | Work Order for Restoration of PMGSY Concrete road at village Rudra damaged during FHTC (Functional House Hold Tap Connection) work of Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 23) | Assistant Engineer | Junior Engineer | ORD/000500/2021-2022 | 46/KSD | 16/02/2022 | 15 | GOPAL CHANDRA CHOWDHURY | 3.67 | 3.67 | 0
2875 | Bankura Division | Khatra Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 0.01 | 0
2876 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Surulia (87) & Nutandihi (93) mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000527/2021-2022 | 30/KSD | 16/02/2022 | 10 | UTTAM KUMAR SINHAMAHAPATRA | 1.91 | 0 | 0
2877 | Bankura Division | Khatra Sub-Division | Work Order for Extension of distribution main by UPVC pipe (6Kg/Sq. Cm. Water Pressure, class III) along with installation of Street Stand Post etc. to cover Dudhenala & Ghatpal village under Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000569/2021-2022 | 545/KSD | 29/06/2021 | 10 | UNITED TRADERS | 3.53 | 0 | 0
2878 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) | Assistant Engineer | Junior Engineer | ORD/000615/2021-2022 | 43/KSD | 16/02/2022 | 15 | ASOKE KUMAR SAHU | 3.26 | 0 | 0
2879 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Bhabanipathar (90) & Malcharar (100) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000692/2021-2022 | 27/KSD | 16/02/2022 | 10 | SUBHENDU BANERJEE | 3.83 | 0 | 40
2880 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malbera (109) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) | Assistant Engineer | Junior Engineer | ORD/000693/2021-2022 | 37/KSD | 16/02/2022 | 15 | PARTHA PRATIM CHHATAIT | 3.82 | 0 | 0
2881 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Tungcharar (108) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 15) | Assistant Engineer | Junior Engineer | ORD/000694/2021-2022 | 39/KSD | 16/02/2022 | 15 | PARTHA PRATIM CHHATAIT | 3.73 | 0 | 0
2882 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Tungcharar (108) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000695/2021-2022 | 40/KSD | 16/02/2022 | 15 | PARTHA PRATIM CHHATAIT | 3.03 | 0 | 0
2883 | Bankura Division | Khatra Sub-Division | Work order for Supply of 01 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for official use of Deputy Superintending Engineer, PIU, Bankura, WBDWSIP, P.H.E. Dte. for the Period from 01.03.2022 to 31.08.2022. | Assistant Engineer | Junior Engineer | ORD/000723/2021-2022 | 54/KSD | 23/02/2022 | 184 | TAPAN KUMAR UPADHYAY | 0.87 | 0.74 | 0
2884 | Bankura Division | Khatra Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/01/2023 to 30/06/2023. | Assistant Engineer | Junior Engineer | ORD/000729/2022-2023 | 419/KSD | 27/12/2022 | 181 | BISWAJIT LAI | 0.86 | 2.62 | 20
2885 | Bankura Division | Khatra Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01/02/2022 to 31/07/2022. | Assistant Engineer | Junior Engineer | ORD/001046/2021-2022 | 15/KSD | 28/01/2022 | 181 | SRIKANTA MONDAL | 0.86 | 0 | 100
2886 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline with in pachirdang mouzas for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Anchuri (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000220/2022-2023 | FHTC/08 | 08/04/2022 | 0 | M/S BANERJEE & BANERJEE | 6.57 | 0 | 0
2887 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06, Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah (PART), Total House Hold - 528.' | Assistant Engineer | Junior Engineer | VCH/000226/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SWAPAN KUMAR CHANDRA | 9.23 | 0 | 0
2888 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Bhedua Purosatyampur, Narrah mouzas for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000227/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SELCO | 3.61 | 0 | 0
2889 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. | Assistant Engineer | Junior Engineer | VCH/000228/2022-2023 | FHTC/11 | 11/04/2022 | 0 | DAUD ALI KHAN | 4.42 | 0 | 0
2890 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurulpahari (238) AND Baurisol (240) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000372/2022-2023 | FHTC/02 | 02/05/2022 | 0 | EARTH MOVING (INDIA) | 11.14 | 0 | 0
2891 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Kulpat, Kesia,& Bhedua(Part), Total House Hold - 435' | Assistant Engineer | Junior Engineer | VCH/000373/2022-2023 | FHTC/02 | 02/05/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.76 | 0 | 0
2892 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Baharamuri ( 91) mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Zone - Q) (Jambedia) Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000374/2022-2023 | FHTC/02 | 02/05/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.91 | 0 | 0
2893 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jibanpur (92) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A | Assistant Engineer | Junior Engineer | VCH/000375/2022-2023 | FHTC/02 | 02/05/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.78 | 0 | 0
2894 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Kadamkanali (146) mouza and Bhangahar village under Kubasol (139) mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Zone - B) (Tilaboni) Khatra - Hirbandh - Ranibandh water supply scheme (BRGF ph - I project) at block - Hirbandh & Khatra dist - Bankura under Bankura Khatra Sub - Division of Bankura Division, PHE Dte. ( Sl .No.- 13) | Assistant Engineer | Junior Engineer | VCH/000376/2022-2023 | FHTC/02 | 02/05/2022 | 0 | SANJOY PATRA | 3.19 | 0 | 0
2895 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chakadoba (73), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000377/2022-2023 | FHTC/02 | 02/05/2022 | 0 | SANJOY PATRA | 4.24 | 0 | 0
2896 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Junbedai mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000378/2022-2023 | FHTC/02 | 02/05/2022 | 0 | M/S SUPRIYA CHATTERJEE | 3.85 | 0 | 0
2897 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000557/2022-2023 |  | 18/07/2022 | 0 | GON ASSOCIATES | 5.44 | 0 | 0
2898 | Bankura Division | Khatra Sub-Division | Restoration of PMGSY concrete road at village Rudra damaged during of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 23 | Assistant Engineer | Junior Engineer | VCH/000558/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 3.67 | 0 | 0
2899 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Tamakhun (62) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 28 | Assistant Engineer | Junior Engineer | VCH/000568/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.44 | 0 | 0
2900 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Rudra (38) Mahespur (52) chirkun Kanali (54) & Budh Khila (60) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 20 | Assistant Engineer | Junior Engineer | VCH/000569/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.51 | 0 | 0
2901 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from dhagra post office to chaitandihi more to increase pressure to cover Dhagra (82) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - I ( Hatikheda ) of Khatra - Hirbandh - Ranibandh W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission (JJM) and JAL SWAPNA under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000583/2022-2023 |  | 22/07/2022 | 0 | BEAUTY CHATTERJEE | 4.87 | 0 | 0
2902 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Tamakhun (62) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 28 | Assistant Engineer | Junior Engineer | VCH/000744/2022-2023 | FHTC/03 | 03/08/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.44 | 0 | 0
2903 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Rudra (38), Mahespur (52), Chirkun Kanali (54) & Budh Khila (60) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) | Assistant Engineer | Junior Engineer | VCH/000752/2022-2023 | FHTC/03 | 03/08/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.51 | 0 | 0
2904 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Dhagra post office to Chaitandihi more to increase pressure to Dhagra (82) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000760/2022-2023 | FHTC/01 | 01/08/2022 | 0 | BEAUTY CHATTERJEE | 4.87 | 0 | 0
2905 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) | Assistant Engineer | Junior Engineer | VCH/001029/2021-2022 |  | 16/09/2021 | 0 | PRADYUMNA KOLEY | 3.1 | 0 | 0
2906 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Buriam (112) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/001030/2021-2022 |  | 16/09/2021 | 0 | SUBHADIP KOLEY | 2.47 | 0 | 0
2907 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) | Assistant Engineer | Junior Engineer | VCH/001031/2021-2022 |  | 16/09/2021 | 0 | SUBHADIP KOLEY | 2.42 | 0 | 0
2908 | Bankura Division | Khatra Sub-Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza - PHULBERIA, | Assistant Engineer | Junior Engineer | VCH/001292/2021-2022 | FHTC/02 | 02/08/2021 | 0 | GANGADHAR MONDAL | 3.15 | 0 | 0
2909 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - barjora G.P chandar, Name of OHR - Murakata Total House Hold - 45 sl no - 08. | Assistant Engineer | Junior Engineer | VCH/001293/2021-2022 | FHTC/02 | 02/08/2021 | 0 | JAGADISH BANERJEE | 4.4 | 0 | 0
2910 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/001315/2021-2022 |  | 28/09/2021 | 0 | UNITED TRADERS | 4.94 | 0 | 0
2911 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) | Assistant Engineer | Junior Engineer | VCH/001316/2021-2022 |  | 28/09/2021 | 0 | UNITED TRADERS | 4.95 | 0 | 0
2912 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jamda (98) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) | Assistant Engineer | Junior Engineer | VCH/001325/2021-2022 |  | 28/09/2021 | 0 | ASOKE KUMAR SAHU | 1.61 | 0 | 0
2913 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to Cover Pratappur , Balarampur, Telegarah, Chapatara & Sendra Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/001404/2021-2022 | FHTC/15 | 15/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.59 | 0 | 0
2914 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to Cover Cherabasta , Aina Gobindapur, Mukundapur Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001405/2021-2022 | FHTC/15 | 15/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.78 | 0 | 0
2915 | Bankura Division | Khatra Sub-Division | Laying of M.S pipeline for crossing bridge to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura I II and Barjora Block ( BRGF ph -I) under Bankura Sadar Sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001406/2021-2022 | FHTC/15 | 15/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 1.98 | 0 | 0
2916 | Bankura Division | Khatra Sub-Division | Laying extra new UPVC pipeline to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I , II & Barjora Block W/S Scheme ( BRGF Ph-I project) under Bankura Sadar Sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001407/2021-2022 | FHTC/15 | 15/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.19 | 0 | 0
2917 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to Cover Ailtha, Bagneja, Uparbandh, Akurbad, Banki, Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001408/2021-2022 | FHTC/15 | 15/09/2021 | 0 | SUBHADIP KOLEY | 4.69 | 0 | 0
2918 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001409/2021-2022 | FHTC/15 | 15/09/2021 | 0 | SUBHADIP KOLEY | 3.8 | 0 | 0
2919 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Nutandihi Mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001500/2021-2022 |  | 08/10/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.85 | 0 | 0
2920 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), | Assistant Engineer | Junior Engineer | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0
2921 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Jarisa (89) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., | Assistant Engineer | Junior Engineer | VCH/001568/2021-2022 | FHTC/11 | 11/10/2021 | 0 | BHATTACHARIYA CONSTRUCTION | 2.19 | 0 | 0
2922 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 120, | Assistant Engineer | Junior Engineer | VCH/001569/2021-2022 | FHTC/11 | 11/10/2021 | 0 | GOUTAM GHOSH | 5.68 | 0 | 0
2923 | Bankura Division | Khatra Sub-Division | Extra UPVC line of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-18), | Assistant Engineer | Junior Engineer | VCH/001570/2021-2022 | FHTC/11 | 11/10/2021 | 0 | DAUD ALI KHAN | 3.98 | 0 | 0
2924 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Arkama (124) & Hazamdihi (233) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22), | Assistant Engineer | Junior Engineer | VCH/001571/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNITED TRADERS | 4.12 | 0 | 0
2925 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21), | Assistant Engineer | Junior Engineer | VCH/001572/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNITED TRADERS | 4.87 | 0 | 0
2926 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban zone - A W/S Scheme under Saltora - Chhatna ( BRGF PH - I j project ) Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban Total House Hold - 144 | Assistant Engineer | Junior Engineer | VCH/001573/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAS KUMBHAKAR | 9.23 | 0 | 0
2927 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover parasibad & Laxmijanardanpur mouzas for construction and commissioning of FHTC in connection with jal jeevan mission (JJM) and Jal Swapna of Sonadaha ( Zone-Q) under Bankura I, II & Barjora Block W/S scheme ( BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001574/2021-2022 | FHTC/11 | 11/10/2021 | 0 | NAYAN BARDHAN | 2.75 | 0 | 0
2928 | Bankura Division | Khatra Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Saltora Block under Salota - Chhatna block (BRGF ph - I project) under Bankura sadar sub-division of Bankura division PHE Dte. block - Saltora, no. of mouza - 03 nos total house hold - 7930 (M.b. No. 3507) | Assistant Engineer | Junior Engineer | VCH/001575/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAS DEY | 1.75 | 0 | 0
2929 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora - Chhatna water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Chhatna ,Name of OHR - Dhaban . Total House Hold -67 nos M.B. No. 5098 | Assistant Engineer | Junior Engineer | VCH/001576/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SOUMITRA KUMAR DAS | 4.21 | 0 | 0
2930 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban , Total House Hold - 67 | Assistant Engineer | Junior Engineer | VCH/001577/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SRIKANTA MONDAL | 3.06 | 0 | 0
2931 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Telebedia (Zone - M) under bankura - l & ll & barjora block water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. M.B. No. 5115 | Assistant Engineer | Junior Engineer | VCH/001580/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PARAMESWAR CHOWDHURY | 4.6 | 0 | 0
2932 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilna (Zone - E) under Saltora - Chhatna water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Chhatna ,Name of OHR - Tilna . Total House Hold - 384 nos | Assistant Engineer | Junior Engineer | VCH/001581/2021-2022 | FHTC/11 | 11/10/2021 | 0 | GOUTAM BHOWMIK | 12.64 | 0 | 0
2933 | Bankura Division | Khatra Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) & KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Bankura- II, Name of OHR- 1) Tilabedia, 2) Khyerkanali, No. of Mouza :- 25 nos (Mouladanga, Mithila, Jagannathbati, raghunathpur, Manoharpur, Mohanpur, Kesekol, Domanbandhi, Kumuria, Tilabedia, Kamladanga, Bambanpur, Nabada, Sibarampur, Churamonipur, Khyerkanali, Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalaphar, Kaljuri, Muraboni & Rasiknagarpur), Total House Hold = 3931 nos., | Assistant Engineer | Junior Engineer | VCH/001582/2021-2022 | FHTC/08 | 08/10/2021 | 0 | TAPAS DEY | 1.24 | 0 | 0
2934 | Bankura Division | Khatra Sub-Division | Household Survey of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla, Anchuri, Chaturdihi, Andharthol & Kustora. No.of Mouza :- 114 Total House Hold - 15724., | Assistant Engineer | Junior Engineer | VCH/001583/2021-2022 | FHTC/08 | 08/10/2021 | 0 | TAPAS DEY | 2.02 | 0 | 0
2935 | Bankura Division | Khatra Sub-Division | Household survey in Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (179), Dhabani (180), Jalhari (181) & Harangara (185) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) | Assistant Engineer | Junior Engineer | VCH/001584/2021-2022 | FHTC/08 | 08/10/2021 | 0 | TAPAS DEY | 0.04 | 0 | 0
2936 | Bankura Division | Khatra Sub-Division | Household survey in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (68) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) | Assistant Engineer | Junior Engineer | VCH/001585/2021-2022 | FHTC/08 | 08/10/2021 | 0 | TAPAS DEY | 0.23 | 0 | 0
2937 | Bankura Division | Khatra Sub-Division | Household survey in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 15), | Assistant Engineer | Junior Engineer | VCH/001586/2021-2022 | FHTC/08 | 08/10/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
2938 | Bankura Division | Khatra Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ), | Assistant Engineer | Junior Engineer | VCH/001587/2021-2022 | FHTC/08 | 08/10/2021 | 0 | M/S SUPRIYA CHATTERJEE | 2.76 | 0 | 0
2939 | Bankura Division | Khatra Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
2940 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
2941 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, (Patdoha) Total House Hold - 489 | Assistant Engineer | Junior Engineer | VCH/002315/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SUBHANKAR BANERJEE | 27.3 | 0 | 0
2942 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Majura (372) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 547 Nos.' | Assistant Engineer | Junior Engineer | VCH/002443/2021-2022 | FHTC/19 | 19/02/2022 | 0 | TAPAN KUMAR MANDAL | 16.66 | 0 | 0
2943 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Parkul (217), Mashara (218), Goaladanga (219), Chandanpur (261), Beniabaid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002446/2021-2022 | FHTC/19 | 19/02/2022 | 0 | EARTH MOVING (INDIA) | 38.69 | 0 | 0
2944 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002449/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ASOKE BHATTACHARYYA | 37.72 | 0 | 0
2945 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chandpara (357) and Bamandiha (358) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 369 Nos.' | Assistant Engineer | Junior Engineer | VCH/002456/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ASHOKE KUMAR DEY | 12.3 | 0 | 0
2946 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC ( Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and Jal Swapna of Kanchanpur ( Zone - C) under bankura I,II & Barjora Block W/S scheme (BRGF Ph I Project ) undre Bankura Sadar Sub Division of Bankura Division , PHE Dte. , Block- Barjora , Name of the OHR- KAnchanpur (Zone-C) No of Mouzas : Khandari. | Assistant Engineer | Junior Engineer | VCH/002457/2021-2022 | FHTC/19 | 19/02/2022 | 0 | SUBHADIP KOLEY | 4.78 | 0 | 0
2947 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Gobarda (152) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | VCH/002459/2021-2022 | FHTC/19 | 19/02/2022 | 0 | PRADYUMNA KOLEY | 2.34 | 0 | 0
2948 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpur (Part), Total House Hold- 70 (Sl No of Work- 08) | Assistant Engineer | Junior Engineer | VCH/002460/2021-2022 | FHTC/19 | 19/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 0.52 | 0 | 0
2949 | Bankura Division | Khatra Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :10 (Basuda, Rajprasadpur(Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar ), Total House Hold -473 | Assistant Engineer | Junior Engineer | VCH/002463/2021-2022 | FHTC/19 | 19/02/2022 | 0 | AMIYA KUMAR BIT | 6.65 | 0 | 0
2950 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345) and Janapara (356) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 359 Nos.' | Assistant Engineer | Junior Engineer | VCH/002465/2021-2022 | FHTC/19 | 19/02/2022 | 0 | BIJOY KOLEY | 13.71 | 0 | 0
2951 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Gara), Total House Hold -132 | Assistant Engineer | Junior Engineer | VCH/002466/2021-2022 | FHTC/19 | 19/02/2022 | 0 | SK. ALAMAGIR ALAM | 7.32 | 0 | 0
2952 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1 nos, Barkona Total House Hold - 620. | Assistant Engineer | Junior Engineer | VCH/002478/2021-2022 | FHTC/19 | 19/02/2022 | 0 | SOUMITRA BHATTACHARYA | 22.02 | 0 | 0
2953 | Bankura Division | Khatra Sub-Division | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Deuli (369) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 322 Nos.' | Assistant Engineer | Junior Engineer | VCH/002480/2021-2022 | FHTC/19 | 19/02/2022 | 0 | MESSRS FREEDOM CONSTRUCTION | 10.69 | 0 | 0
2954 | Bankura Division | Khatra Sub-Division | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 310 Nos.' | Assistant Engineer | Junior Engineer | VCH/002482/2021-2022 | FHTC/19 | 19/02/2022 | 0 | MESSRS FREEDOM CONSTRUCTION | 9.63 | 0 | 0
2955 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 02 (Ekteswar (PART ) & Sankardihi. Total House Hold - 452 nos. | Assistant Engineer | Junior Engineer | VCH/002483/2021-2022 | FHTC/19 | 19/02/2022 | 0 | GOUTAM BHOWMIK | 20.52 | 0 | 0
2956 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 1 no. i.e. Majuria-135 , Total House Hold - 943 | Assistant Engineer | Junior Engineer | VCH/002485/2021-2022 | FHTC/19 | 19/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 57.01 | 0 | 0
2957 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | VCH/002489/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.78 | 0 | 0
2958 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | VCH/002490/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.82 | 0 | 0
2959 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/002492/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.84 | 0 | 0
2960 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Kanchanpur (PART) Total House Hold - 507' | Assistant Engineer | Junior Engineer | VCH/002495/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 1.66 | 0 | 0
2961 | Bankura Division | Khatra Sub-Division | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | VCH/002497/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 3.52 | 0 | 0
2962 | Bankura Division | Khatra Sub-Division | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | VCH/002498/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.78 | 0 | 0
2963 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502' | Assistant Engineer | Junior Engineer | VCH/002499/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 6.93 | 0 | 0
2964 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata ,Main road to durga mondir (Part), Total House Hold -35. | Assistant Engineer | Junior Engineer | VCH/002500/2021-2022 | FHTC/02 | 02/02/2022 | 0 | ASHIS PAL | 4.74 | 0 | 0
2965 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata Roy Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | VCH/002501/2021-2022 | FHTC/02 | 02/02/2022 | 0 | ASHIS PAL | 0.22 | 0 | 0
2966 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 3, (Madhabpur , Netkamal, Karkata) , Total House Hold - 435 | Assistant Engineer | Junior Engineer | VCH/002502/2021-2022 | FHTC/02 | 02/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 24.92 | 0 | 0
2967 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 2, ( Adhury, Gogra (part ) , Total House Hold - 439 | Assistant Engineer | Junior Engineer | VCH/002503/2021-2022 | FHTC/02 | 02/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 22.73 | 0 | 0
2968 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 | Assistant Engineer | Junior Engineer | VCH/002504/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GANGADHAR MONDAL | 0.62 | 0 | 0
2969 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Palsana ) , Total House Hold - 140 | Assistant Engineer | Junior Engineer | VCH/002505/2021-2022 | FHTC/02 | 02/02/2022 | 0 | GANGADHAR MONDAL | 0.78 | 0 | 0
2970 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 16) | Assistant Engineer | Junior Engineer | VCH/002511/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOURANGA CHATTERJEE | 0.25 | 0 | 0
2971 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 18) | Assistant Engineer | Junior Engineer | VCH/002512/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOURANGA CHATTERJEE | 0.22 | 0 | 0
2972 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/002513/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOURANGA CHATTERJEE | 3.38 | 0 | 0
2973 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 17) | Assistant Engineer | Junior Engineer | VCH/002514/2021-2022 | FHTC/22 | 22/02/2022 | 0 | AJIT KUMAR PAUL | 0.22 | 0 | 0
2974 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 19) | Assistant Engineer | Junior Engineer | VCH/002515/2021-2022 | FHTC/22 | 22/02/2022 | 0 | AJIT KUMAR PAUL | 2.09 | 0 | 0
2975 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 | Assistant Engineer | Junior Engineer | VCH/002516/2021-2022 | FHTC/22 | 22/02/2022 | 0 | AJIT KUMAR PAUL | 1.41 | 0 | 0
2976 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01(Purunia ), Total House Hold - 105 ( Sl .No.- 12 ) | Assistant Engineer | Junior Engineer | VCH/002517/2021-2022 | FHTC/22 | 22/02/2022 | 0 | JAGADISH BANERJEE | 2.08 | 0 | 0
2977 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 | Assistant Engineer | Junior Engineer | VCH/002518/2021-2022 | FHTC/22 | 22/02/2022 | 0 | TAPAS PAL | 1.38 | 0 | 0
2978 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 04 (Gourangadihi, Ledadihi, Ramdihi & Gouripur .), Total House Hold - 434 | Assistant Engineer | Junior Engineer | VCH/002519/2021-2022 | FHTC/22 | 22/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 0.09 | 0 | 0
2979 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC Pipe Line to Cover gouripur,bonkati,ladadihi mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002520/2021-2022 | FHTC/22 | 22/02/2022 | 0 | BISWARUP BOSE | 4.61 | 0 | 0
2980 | Bankura Division | Khatra Sub-Division | Laying distribution system of UPVC pipe line with allied works from Near Bharakhullya air valve to BharakhullyaVillage (Purba Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002522/2021-2022 | FHTC/22 | 22/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 3.6 | 0 | 0
2981 | Bankura Division | Khatra Sub-Division | Laying distribution system of UPVC pipe line with allied works at BharakhullyaVillage (Paschim Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002523/2021-2022 | FHTC/22 | 22/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 2.99 | 0 | 0
2982 | Bankura Division | Khatra Sub-Division | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 182 Nos.' | Assistant Engineer | Junior Engineer | VCH/002524/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GON ASSOCIATES | 9.63 | 0 | 0
2983 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line from S.P.N school to Barjora Maliara Main Road , Barjojora School Danga Prymary School to Dena Bank , Suman Tewary house to Barjora Maliara Main Road & Baltu Babar Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002525/2021-2022 | FHTC/22 | 22/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.96 | 0 | 0
2984 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03, Bhangaria, Magra , Sonadaha(part), Total House Hold -138' | Assistant Engineer | Junior Engineer | VCH/002526/2021-2022 | FHTC/22 | 22/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 1.64 | 0 | 0
2985 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jamda (98) & Kamardanga (99) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 4) | Assistant Engineer | Junior Engineer | VCH/002527/2021-2022 | FHTC/22 | 22/02/2022 | 0 | EDER ALI KHAN | 4.23 | 0 | 0
2986 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Choto chaka, Total House Hold- 66 (Sl No of Work- 02) | Assistant Engineer | Junior Engineer | VCH/002528/2021-2022 | FHTC/22 | 22/02/2022 | 0 | KASTURI ROY | 0.19 | 0 | 0
2987 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos Beldanga (Part). Total House Hold - 130' | Assistant Engineer | Junior Engineer | VCH/002529/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SHYAMAL KUMAR DAS | 0.5 | 0 | 0
2988 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 03 (Kantabandh ,Radharamanpur , Birsing pur ), Total House Hold -166 | Assistant Engineer | Junior Engineer | VCH/002530/2021-2022 | FHTC/22 | 22/02/2022 | 0 | DAUD ALI KHAN | 0.82 | 0 | 0
2989 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos (Bonkati (Part ). Total House Hold - 132' | Assistant Engineer | Junior Engineer | VCH/002531/2021-2022 | FHTC/22 | 22/02/2022 | 0 | PRANABANANDA TEWARI | 1.25 | 0 | 0
2990 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 Radhanagar(part) & Maukara,) Total House Hold - 280' | Assistant Engineer | Junior Engineer | VCH/002532/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 3.84 | 0 | 0
2991 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 ( Upardihi & Kulmura.) Total House Hold - 441' | Assistant Engineer | Junior Engineer | VCH/002533/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 6.56 | 0 | 0
2992 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC , Jal jeevan mission and Jal Swapna of Kotalpur ( Zone-B ) under bankura I , II & Barjora Block W/S scheme ( BRGF Ph - I ) under Bankura Sadar Sub-Division , PHE Dte. Block Barjora , Name of OHR Kotulpur ( Zone-B ) . No.Of Mouzas: 05 ( Purakunda , Sitalpur, suratpur , Chandi & Balarampur ) Total H.Hold : 958 | Assistant Engineer | Junior Engineer | VCH/002534/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 1.78 | 0 | 0
2993 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Total House Hold -76 | Assistant Engineer | Junior Engineer | VCH/002544/2021-2022 | FHTC/22 | 22/02/2022 | 0 | TAPAS PAL | 0.33 | 0 | 0
2994 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata Ghosh Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | VCH/002547/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SOMA BANERJEE | 0.3 | 0 | 0
2995 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 03 nos, ( Dhatala, Binodihi ,Bashkatia) Total House Hold - 394. | Assistant Engineer | Junior Engineer | VCH/002549/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SAIKAT CHOWDHURY | 5.51 | 0 | 0
2996 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe 15 mm NB PVC to cover Dhatala, Banskkathia , Binoddihi mouza for const. and commissioning of FHTC connection with JJM and Jal Jeevan Mission of Shyampur ( Zone E ) under Saltota Chhatna W/S Scheme ( BRGF Ph -I) under Bankura Sadar Sub Division Of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002556/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SAIKAT CHOWDHURY | 4.94 | 0 | 0
2997 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-0 2 , Sangrampur (Part-C),Baharkhulia(part-A), Total House Hold - 124 ( Sl .No.- 10) | Assistant Engineer | Junior Engineer | VCH/002558/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SUBHANKAR BANERJEE | 1.4 | 0 | 0
2998 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 02 Laxminarayanpur & Gangadar pur ), Total House Hold - 99 ( Sl .No.- 13) | Assistant Engineer | Junior Engineer | VCH/002559/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SUBHANKAR BANERJEE | 1.41 | 0 | 0
2999 | Bankura Division | Khatra Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos, (Duyaranda, Kelebela), Total House Hold - 422.' | Assistant Engineer | Junior Engineer | VCH/002560/2021-2022 | FHTC/22 | 22/02/2022 | 0 | SOUMITRA BOSE | 3.76 | 0 | 0
3000 | Bankura Division | Khatra Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Garerban, Ekteswar (Part, 30%), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar, No.of Mouza :- 02 no., (Garerban, Ekteswar (Part, 30%), Total House Hold - 480 nos. | Assistant Engineer | Junior Engineer | VCH/002561/2021-2022 | FHTC/22 | 22/02/2022 | 0 | MAKALI CONSTRUCTION | 21.47 | 0 | 0
3001 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline & 15 mm pipe to cover parasia mouza for const. and commissioning of FHTC connection with JJM and Jal Swapna of Jorehere ( Zone- B ) under saltora chhatna W/S Scheme ( BRGF Ph - I ) under Bankura Sadar Sub Divisiob of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002566/2021-2022 | FHTC/22 | 22/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 4.62 | 0 | 0
3002 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtcional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Parasia), Total House Hold -155 | Assistant Engineer | Junior Engineer | VCH/002568/2021-2022 | FHTC/22 | 22/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 2.96 | 0 | 0
3003 | Bankura Division | Khatra Sub-Division | Additional UPVC Pipe Line for increasing pressure in existing distribution pipe line of Belboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002578/2021-2022 | FHTC/24 | 24/02/2022 | 0 | M/S TARUN KUMAR PATRA | 2.08 | 0 | 0
3004 | Bankura Division | Khatra Sub-Division | laying of HDPE pipe line from Ramkrishna Mission Ashram to Barjora Pry. School of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II)[ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002580/2021-2022 | FHTC/24 | 24/02/2022 | 0 | NAYAN BARDHAN | 4.81 | 0 | 0
3005 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Gadardihi (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Gadardihi (Zone - E) . No.of Mouza :- 01 Lalbazar (PART-A) Total House Hold -141 | Assistant Engineer | Junior Engineer | VCH/002581/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SUBHANKAR BANERJEE | 0.97 | 0 | 0
3006 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 | Assistant Engineer | Junior Engineer | VCH/002582/2021-2022 | FHTC/24 | 24/02/2022 | 0 | JAGADISH BANERJEE | 2.6 | 0 | 0
3007 | Bankura Division | Khatra Sub-Division | Extra UPVC pipe line from Soragara Village to Enayetpur village of retrofitting work for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GODARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Barjora, Name of OHR:- GODARDIHI (Zone - E), Name of Mouza:- Enayetpur. | Assistant Engineer | Junior Engineer | VCH/002583/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SUBHANKAR BANERJEE | 4.32 | 0 | 0
3008 | Bankura Division | Khatra Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I), Name of mouza- Joykrishna pur Sarenga (PART- B), | Assistant Engineer | Junior Engineer | VCH/002634/2021-2022 | FHTC/01 | 01/02/2022 | 0 | M/S SUPRIYA CHATTERJEE | 3.73 | 0 | 0
3009 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC Pipe Line to Cover Kulpat bankati, Gourandihi, Kesia, Ladadihi, Ramdihi, Choto kalajharia, Radharamanpur, Baro kalajuria mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002635/2021-2022 | FHTC/01 | 01/02/2022 | 0 | PRANABANANDA TEWARI | 2.91 | 0 | 0
3010 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002636/2021-2022 | FHTC/01 | 01/02/2022 | 0 | PRANABANANDA TEWARI | 2.84 | 0 | 0
3011 | Bankura Division | Khatra Sub-Division | extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza :- 10 nos, (Basuda, Rajprasadpur (Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar) | Assistant Engineer | Junior Engineer | VCH/002637/2021-2022 | FHTC/01 | 01/02/2022 | 0 | AMIYA KUMAR BIT | 4.36 | 0 | 0
3012 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17) | Assistant Engineer | Junior Engineer | VCH/002639/2021-2022 | FHTC/01 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 6.26 | 0 | 0
3013 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | VCH/002640/2021-2022 | FHTC/01 | 01/02/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.89 | 0 | 0
3014 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover Bhabanipathar (90) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08 | Assistant Engineer | Junior Engineer | VCH/002641/2021-2022 | FHTC/01 | 01/02/2022 | 0 | TAPAN KUMAR MANDAL | 1.57 | 0 | 0
3015 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002647/2021-2022 | FHTC/10 | 10/02/2022 | 0 | GOUTAM BHATTACHRYYA | 13.52 | 0 | 0
3016 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Bhedua (264) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone- IIA (Baragari) of Khatra - Hirbandh-Ranibandh water supply scheme (BRGF Ph-I) at Block- Khatra Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A Sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002967/2021-2022 |  | 25/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.36 | 0 | 0
3017 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to Dhadanga & Haludkanali mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Madandihi Zone O of Khatra Hirbandh Ranibandh w/s scheme (Part -B) | Assistant Engineer | Junior Engineer | VCH/003024/2021-2022 | FHTC/28 | 28/03/2022 | 0 | SUBHENDU BANERJEE | 0.42 | 0 | 0
3018 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Ambikanagar ( 19) & Jaynagar (47) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B | Assistant Engineer | Junior Engineer | VCH/003029/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.78 | 0 | 0
3019 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | VCH/003031/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 11.61 | 0 | 0
3020 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Dhagra (82 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003032/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 3.95 | 0 | 0
3021 | Bankura Division | Khatra Sub-Division | aying extra HDPE pipe line to cover Ambikanagar ( 19) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - A | Assistant Engineer | Junior Engineer | VCH/003033/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.88 | 0 | 0
3022 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Rajsol (41 ) & Bansol (83) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003035/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.07 | 0 | 0
3023 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Doba (40 ) & Kheria Kocha (50) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003037/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.44 | 0 | 0
3024 | Bankura Division | Khatra Sub-Division | aying extra HDPE pipe line to cover Hatikheda (20 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003038/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 2.54 | 0 | 0
3025 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Dulalpur (32 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003040/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 3.91 | 0 | 0
3026 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Ambikanagar ( 19) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B | Assistant Engineer | Junior Engineer | VCH/003042/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0
3027 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Puada (94) mouza by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003044/2021-2022 | FHTC/27 | 27/03/2022 | 0 | BEAUTY CHATTERJEE | 1.31 | 0 | 0
3028 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 | Assistant Engineer | Junior Engineer | VCH/003099/2021-2022 | FHTC/30 | 30/03/2022 | 0 | MUNMUN UPADHYAY | 35.35 | 0 | 0
3029 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas, (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III). No.of Mouza :- 13 nos (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold - 2821 nos. | Assistant Engineer | Junior Engineer | VCH/003101/2021-2022 | FHTC/28 | 28/03/2022 | 0 | M/S TARUN KUMAR PATRA | 151.09 | 0 | 0
3030 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pitadungri (275) Kuchiarmahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003102/2021-2022 | FHTC/30 | 30/03/2022 | 0 | SWAPAN KUMAR UPADHYAY | 47.33 | 0 | 0
3031 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe, line to cover sirsara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f cherabasta (Zone - K) under Bankura - I & II & Barjora - Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003112/2021-2022 | FHTC/30 | 30/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.92 | 0 | 0
3032 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe, line to cover Mobarakpur , Agra, Sirasara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Cherabasta (Zone - K) under Bankura - I & II & Barjora - Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003113/2021-2022 | FHTC/30 | 30/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.51 | 0 | 0
3033 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633' | Assistant Engineer | Junior Engineer | VCH/003114/2021-2022 |  | 30/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 8.22 | 0 | 0
3034 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605' | Assistant Engineer | Junior Engineer | VCH/003115/2021-2022 |  | 30/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 6.47 | 0 | 0
3035 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576' | Assistant Engineer | Junior Engineer | VCH/003116/2021-2022 |  | 30/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 12.5 | 0 | 0
3036 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Bara Bendya & Khemua), Total House Hold -396 (SL.No-18) | Assistant Engineer | Junior Engineer | VCH/003117/2021-2022 |  | 30/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 40.32 | 0 | 0
3037 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline with in pachirdang mouzas for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Anchuri (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003118/2021-2022 |  | 30/03/2022 | 0 | M/S BANERJEE & BANERJEE | 6.57 | 0 | 0
3038 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 02 nos, (Moyragora, Jaynagar) Total House Hold - 146 | Assistant Engineer | Junior Engineer | VCH/003119/2021-2022 |  | 30/03/2022 | 0 | M/S BANERJEE & BANERJEE | 3.99 | 0 | 0
3039 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no ,Sidhaberia (Part), Total House Hold- 145 nos. | Assistant Engineer | Junior Engineer | VCH/003120/2021-2022 |  | 30/03/2022 | 0 | TAPAS KUMBHAKAR | 9.46 | 0 | 0
3040 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Dhanara (36 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 04 | Assistant Engineer | Junior Engineer | VCH/003122/2021-2022 | FHTC/29 | 29/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.62 | 0 | 0
3041 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Narikala, No. of Mouza :- 02 nos. i.e. Layak Bandh - 13 & Chua Masina - 17, Total House Hold - 2202 | Assistant Engineer | Junior Engineer | VCH/003123/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 44.72 | 0 | 0
3042 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 no, ( Namabad , Gopinathdihi) Total House Hold-141 | Assistant Engineer | Junior Engineer | VCH/003124/2021-2022 | FHTC/17 | 17/03/2022 | 0 | ASHIS PAL | 2.88 | 0 | 0
3043 | Bankura Division | Khatra Sub-Division | Assessment of performance of the scheme including actual delivery of drinking water supply scheme qulity of water being supplied and assess peoples perception of the supply of water including the level of peoples satisfaction of the piped water supply scheme for Bankura district convering 14 blocks in 1st phase founded under backward region grant fund (BRGF) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003127/2021-2022 | FHTC/31 | 31/03/2022 | 0 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE & MONITORING ADVANCEMENT FOUNDATION | 9.9 | 0 | 0
3044 | Bankura Division | Khatra Sub-Division | Installation of 4 nos. stand alone community purification plant with provision of tube well solar power operated pumping machinery and treatment unit for removal of fluoride affected habitation of different dev. Block under Bankura district within Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003128/2021-2022 | FHTC/31 | 31/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 21.73 | 0 | 0
3045 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 45 | UNICON INDIA | 317.75 | 0 | 100
3046 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (PART-B) Block - Sonamukhi, Name of OHR - Kanaipur No. of Mouza :- 1 no. i.e. Kanaipur 159, Habitation's Name:- Kanaipur,Majirdanga,Dhakkata and Kinkoria,Total House Hold - 69 | Assistant Engineer | Junior Engineer | ORD/000090/2020-2021 | 162/vsd | 18/09/2020 | 21 | BIJOY KOLEY | 4.83 | 0 | 0
3047 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) | Assistant Engineer | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.46 | 2.57 | 0
3048 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying extra HDPE pipeline to cover Baricha (180), Dhuliapur (177) & Hariharpur (178) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000649/2021-2022 | 754/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.95 | 4.83 | 0
3049 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kumorebahal (159) & Dhabani (180) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household - 138 Nos. | Assistant Engineer | Junior Engineer | VCH/002674/2021-2022 | FHTC/2 | 02/03/2022 | 0 | D. S. ENTERPRISE | 10.01 | 0 | 0
3050 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 Khyerkanali (PART-2) Total House Hold - 123 | Assistant Engineer | Junior Engineer | VCH/002677/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PRADIP CHAKRABORTY | 0.72 | 0 | 0
3051 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, Khyerkanali (PART-1) Total House Hold - 145 | Assistant Engineer | Junior Engineer | VCH/002679/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PRADIP CHAKRABORTY | 0.29 | 0 | 0
3052 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 (Junbedia (PART), Total House Hold - 440 | Assistant Engineer | Junior Engineer | VCH/002680/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM BHOWMIK | 9.07 | 0 | 0
3053 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 | Assistant Engineer | Junior Engineer | VCH/002683/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM BHOWMIK | 59.53 | 0 | 0
3054 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002696/2021-2022 | FHTC/2 | 02/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 31.26 | 0 | 0
3055 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC pipe line & 15 mm NB PVC pipe to cover Dhatala, Banshkathia, Biniddihi, mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002697/2021-2022 | FHTC/2 | 02/03/2022 | 0 | BEAUTY CHATTERJEE | 4.98 | 0 | 0
3056 | Bankura Division | Brishnupur Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Func tional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joykrishnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Joykrishnapur (Zone - I) No.of Mouza :- Oltara , sl no - 24 | Assistant Engineer | Junior Engineer | VCH/002698/2021-2022 | FHTC/2 | 02/03/2022 | 0 | RUFIKUL MONDAL | 4.92 | 0 | 0
3057 | Bankura Division | Brishnupur Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Func tional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joykrishnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Joykrishnapur (Zone - I) No.of Mouza :- Bahadur pur sl no - 25 | Assistant Engineer | Junior Engineer | VCH/002699/2021-2022 | FHTC/2 | 02/03/2022 | 0 | TAPAS KUMAR HAZRA | 4.76 | 0 | 0
3058 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gobindapur (Part -A ), Total House Hold - 145 | Assistant Engineer | Junior Engineer | VCH/002700/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SUBHANKAR BANERJEE | 1.54 | 0 | 0
3059 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-A ), Total House Hold - 200 | Assistant Engineer | Junior Engineer | VCH/002701/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SUBHANKAR BANERJEE | 1.95 | 0 | 0
3060 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Mukundrapur village of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000238/2021-2022 | 945/BSD | 04/10/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.71 | 0 | 0
3061 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line t to cover Valai Bhagan Village of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000239/2021-2022 | 946/BSD | 04/10/2021 | 15 | UNIVERSAL CONSTRUCTION | 3.73 | 0 | 0
3062 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 ( Dhenga kend, Golhati & Bonomadhavpur ), Total House Hold -425 |  | Junior Engineer | ORD/000271/2020-2021 | 2070/BQA | 29/12/2020 | 30 | UNIVERSAL CONSTRUCTION | 40.48 | 71.68 | 0
3063 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), Total House Hold -416 |  | Junior Engineer | ORD/000272/2020-2021 | 2071/BQA | 29/12/2020 | 30 | UNIVERSAL CONSTRUCTION | 39.34 | 0 | 0
3064 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone- H), Name of Mouza :- Bonomadhavpur |  | Junior Engineer | ORD/000345/2021-2022 | 854/ BSD | 18/08/2021 | 15 | BISWESWAR CONSTRUCTION | 4.87 | 0 | 0
3065 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line from Jorjhal Roypara to Barabendya High School of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), |  | Junior Engineer | ORD/000347/2021-2022 | 853/ BSD | 18/08/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.98 | 0 | 0
3066 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line from Mukuti Village Tematha more to Jorjhal Roypara of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), |  | Junior Engineer | ORD/000348/2021-2022 | 852/ BSD | 18/08/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.97 | 0 | 0
3067 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line t to cover Valai Bhagan Village of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000357/2021-2022 | 946/ BSD | 04/10/2021 | 15 | UNIVERSAL CONSTRUCTION | 3.73 | 0 | 0
3068 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 ( Dhenga kend, Golhati & Bonomadhavpur ), Total House Hold -425 |  | Junior Engineer | VCH/001618/2020-2021 |  | 15/03/2021 | 0 | UNIVERSAL CONSTRUCTION | 35.84 | 0 | 0
3069 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | VCH/002289/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.1 | 0 | 0
3070 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | VCH/002292/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.72 | 0 | 0
3071 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
3072 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108) Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000076/2020-2021 | 482/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 16.61 | 8.5 | 0
3073 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 ( Panchbaga.), Total House Hold - 438 |  | Junior Engineer | ORD/000311/2020-2021 | 1363/BQA | 08/10/2020 | 30 | GOUTAM BHOWMIK | 37.93 | 0 | 0
3074 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 04 (Gourangadihi, Ledadihi, Ramdihi & Gouripur .), Total House Hold - 434 |  | Junior Engineer | ORD/000313/2020-2021 | 1364/BQA | 08/10/2020 | 30 | PARTHA PRATIM CHATAIT | 37.75 | 0 | 100
3075 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000347/2020-2021 | 1772/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 23.94 | 20.56 | 20
3076 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Gourangadihi, Ladadihi, kesia, Bhedua, Kulpat bankati , gouripur mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000430/2020-2021 | 137/ BSD | 18/02/2021 | 10 | PARTHA PRATIM CHHATAIT | 4.89 | 0 | 0
3077 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line to increase pressure at Bibadinagar village for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000475/2022-2023 | 624/BSD | 16/08/2022 | 21 | PRADYUMNA KOLEY | 3.56 | 0 | 0
3078 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line to increase pressure at panchbaga mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000476/2022-2023 | 623/BSD | 16/08/2022 | 21 | BIJOY KOLEY | 4.38 | 0 | 0
3079 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover PANCHBAGA 'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000488/2020-2021 | 133/BSD | 18/02/2021 | 10 | GOUTAM BHOWMIK | 4.42 | 0 | 0
3080 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Harialgora , No Of Mouzas-01 Nos ( Junbedia) Total House Hold -881 |  | Junior Engineer | VCH/001612/2020-2021 |  | 15/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
3081 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
3082 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata ,Chandar Durgamondir para (part), Total House Hold -45. |  | Junior Engineer | VCH/002585/2021-2022 | FHTC/26 | 26/02/2022 | 0 | JAGADISH BANERJEE | 0.28 | 0 | 0
3083 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
3084 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Balarampur (138), Kubasol (139) & Ban Pukhuria (140) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2020-2021 | 184/BQA | 18/01/2021 | 30 | SANJOY PATRA | 41.01 | 0 | 0
3085 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chakadoba (73), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2020-2021 | 185/BQA | 18/01/2021 | 30 | SANJOY PATRA | 39.68 | 0 | 0
3086 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 85.95 | 0
3087 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Chakadoba (73), Balarampur (138), Kubasol (139), Ban Pukhuria (140), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000513/2020-2021 | 311/KSD | 29/12/2020 | 61 | SANJOY PATRA | 0.38 | 0 | 0
3088 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 04 nos, (Kaminbedia, Sihikapahari, Dubra, Tilna) Total House Hold - 429 | Assistant Engineer | Junior Engineer | VCH/002474/2021-2022 | FHTC/1 | 01/02/2022 | 0 | PARAMESWAR CHOWDHURY | 24.86 | 0 | 0
3089 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with JalJeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhagarara-25 (63 out of 71), House Hold ¿ 63 (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/002475/2021-2022 | FHTC/1 | 01/02/2022 | 0 | SANU KARMAKAR | 3.86 | 0 | 0
3090 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover (Madhabpur, Netkamal, Karkata) mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002477/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.97 | 0 | 0
3091 | Bankura Division | Khatra Sub-Division | Laying extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Madhabpur, Netkamal, Karkata mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Block of Saltora-Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002479/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.07 | 0 | 0
3092 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), Total House Hold -416 | Assistant Engineer | Junior Engineer | VCH/002481/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 3.97 | 0 | 0
3093 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 ( Dhenga kend, Golhati & Bonomadhavpur ), Total House Hold -425 | Assistant Engineer | Junior Engineer | VCH/002484/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.68 | 0 | 0
3094 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
3095 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 03 nos. i.e. Kenjera-129, Chattrakhanda-130 & Nagatentul-131 , Total House Hold - 613 | Assistant Engineer | Junior Engineer | ORD/000172/2021-2022 | 2847/BQA | 22/11/2021 | 30 | AJIT KUMAR PAUL | 57.88 | 41.71 | 0
3096 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Pathardoba, Zone-A & B and Baricha, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 58 Nos. Total Household:- 7982 Nos. Name of Mouzas:- Under Pathardoba, Zone-A :- Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) Under Pathardoba, Zone-B:- Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) Under Baricha, Zone-B:- Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) | Assistant Engineer | Junior Engineer | ORD/000025/2022-2023 | 1085/BQA | 12/05/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 482.88 | 160.87 | 0
3097 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000282/2021-2022 | 702/KSD | 29/10/2021 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.89 | 0 | 0
3098 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) mouzas under Pathardoba, Zone-A to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21) | Assistant Engineer | Junior Engineer | ORD/000678/2021-2022 | 807/KSD | 14/12/2021 | 90 | TAPAS DEY | 1.09 | 1.09 | 0
3099 | Bankura Division | Khatra Sub-Division | Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and laying of HDPE pipeline under Pathardoba, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza- Sonakanda, Tapubaid & Jirabaid | Assistant Engineer | Junior Engineer | ORD/000698/2023-2024 | 2666/BQA | 22/09/2023 | 544 | SAIKAT CHOWDHURY | 43.96 | 31.56 | 85
3100 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 5.11 | 0 | 0
3101 | Bankura Division | Khatra Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/03/2022 to 31/05/2022. | Assistant Engineer | Junior Engineer | ORD/001079/2021-2022 | 25KSD | 16/02/2022 | 77 | PARTHA PRATIM CHHATAIT | 0.37 | 0 | 0
3102 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Surulia (87) & Nutandihi (93) mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/000781/2022-2023 | FHTC/29 | 29/11/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 1.91 | 0 | 0
3103 | Bankura Division | Khatra Sub-Division | Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/001451/2022-2023 | FHTC/06 | 06/12/2022 | 0 | EARTH MOVING (INDIA) | 4.75 | 0 | 0
3104 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) | Assistant Engineer | Junior Engineer | VCH/001453/2022-2023 | FHTC/06 | 06/12/2022 | 0 | M/S K.B.CONSTRUCTION | 15.31 | 0 | 0
3105 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0
3106 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Rol, No. of Mouza :- 2 nos. i.e. Rol-07 & Chichinga-08, Total House Hold - 1421 | Assistant Engineer | Junior Engineer | ORD/000090/2021-2022 | 2504/BQA | 23/09/2021 | 30 | CREATION CONSTRUCTION | 71.71 | 0 | 0
3107 | Bankura Division | Brishnupur Sub-Division | Laying of UPVC & GI pipe line to increase pressure at Chandar Mouza Water Supply Arrangement with allied works at Beliatore Jamini Roy College ground and water supply connection near PWD Sulabha Sauchalaya at Beliatore more under Beliatore W/S Scheme under Bankura Sadar Sub-Division of Bankura Division , PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) | Assistant Engineer | Junior Engineer | ORD/000332/2022-2023 | 532/BSD | 28/07/2022 | 21 | AJIT KUMAR PAUL | 2.58 | 2.58 | 0
3108 | Bankura Division | Brishnupur Sub-Division | Supplying laying fitting fixing of HDPE pipe line connection from Air valve of Maliara Rising main(Near Ghutgoria village ) to Hindur danga village (under Baguli Mouza ) for Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 619/BSD | 16/08/2022 | 21 | ASHIS KUMAR SAMANTA | 4.89 | 4.88 | 0
3109 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) | Assistant Engineer | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.46 | 1.06 | 0
3110 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 | Assistant Engineer | Junior Engineer | VCH/002344/2021-2022 | FHTC/25 | 25/01/2022 | 0 | AMIYA KUMAR BIT | 35.44 | 0 | 0
3111 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 | Assistant Engineer | Junior Engineer | VCH/002353/2021-2022 | FHTC/25 | 25/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0
3112 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Chandar main Bazar to Chandar gram end & Baroma kali than (Chomatha), Bramhon para (Part), Chandar maibazar, Total House Hold -25. | Assistant Engineer | Junior Engineer | VCH/002354/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SOMENATH ACHARYYA | 4.8 | 0 | 0
3113 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20 | Assistant Engineer | Junior Engineer | VCH/002355/2021-2022 | FHTC/25 | 25/01/2022 | 0 | BIDHAN BANERJEE | 4.84 | 0 | 0
3114 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC Pipe Line to Cover Duyaranda, Kelebela mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI(Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002356/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SOUMITRA BOSE | 4.61 | 0 | 0
3115 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC Pipe Line to Cover Bonkati, Beldanga, Gajabari mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002357/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SHYAMAL KUMAR DAS | 4.31 | 0 | 0
3116 | Bankura Division | Brishnupur Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140 | Assistant Engineer | Junior Engineer | VCH/002358/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GANGADHAR MONDAL | 0.81 | 0 | 0
3117 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- -01 no (Pinguri (Part-B ), Total House Hold -330 | Assistant Engineer | Junior Engineer | VCH/002359/2021-2022 | FHTC/28 | 28/01/2022 | 0 | AJIT KUMAR PAUL | 1.56 | 0 | 0
3118 | Bankura Division | Brishnupur Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Gogra, Adhury mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Horaka (Zone - G) under Saltora Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002360/2021-2022 | FHTC/28 | 28/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.86 | 0 | 0
3119 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. | Assistant Engineer | Junior Engineer | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0
3120 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 10 no, Khabanigoparpur (Part) Total House Hold-140 | Assistant Engineer | Junior Engineer | ORD/000052/2021-2022 | 1931/BQA | 28/07/2021 | 30 | SRIKANTA MONDAL | 9.31 | 12.25 | 20
3121 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 0.65 | 0
3122 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172, | Assistant Engineer | Junior Engineer | VCH/001767/2021-2022 | FHTC/29 | 29/10/2021 | 0 | ASHOKE KUMAR DEY | 13.01 | 0 | 0
3123 | Bankura Division | Brishnupur Sub-Division | Lying extra upvc pipe line to cover Jagannathpur mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001768/2021-2022 | FHTC/28 | 28/10/2021 | 0 | APEX ENTERPRISE | 4.64 | 0 | 0
3124 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipe line to cover Shyam bazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme, | Assistant Engineer | Junior Engineer | VCH/001769/2021-2022 | FHTC/28 | 28/10/2021 | 0 | BHATTACHARYYA ENTERPRISE | 4.96 | 0 | 0
3125 | Bankura Division | Brishnupur Sub-Division | Laying extra upvc pipeline to cover Shyambazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001770/2021-2022 | FHTC/28 | 28/10/2021 | 0 | BHATTACHARYYA ENTERPRISE | 4.86 | 0 | 0
3126 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipe line to cover Nutandihi Mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001771/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.85 | 0 | 0
3127 | Bankura Division | Brishnupur Sub-Division | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. under Jal Jeevan Mission and Jal Swapan Programme sl no - 15 part - A | Assistant Engineer | Junior Engineer | VCH/002922/2021-2022 | FHTC/21 | 21/03/2022 | 0 | ASHISH KUMAR SAMANTA | 4.17 | 0 | 0
3128 | Bankura Division | Brishnupur Sub-Division | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. part - C under Jal Jeevan Mission and Jal Swapan Programme sl no - 12 | Assistant Engineer | Junior Engineer | VCH/002923/2021-2022 | FHTC/21 | 21/03/2022 | 0 | ASHISH KUMAR SAMANTA | 3.06 | 0 | 0
3129 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
3130 | Bankura Division | Brishnupur Sub-Division | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. part - B under Jal Jeevan Mission and Jal Swapan Programme sl no - 16 | Assistant Engineer | Junior Engineer | VCH/002924/2021-2022 | FHTC/21 | 21/03/2022 | 0 | ASHISH KUMAR SAMANTA | 4.58 | 0 | 0
3131 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000105/2021-2022 | 2501/BQA | 23/09/2021 | 30 | GOUTAM BHATTACHRYYA | 52.99 | 0 | 0
3132 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) | Assistant Engineer | Junior Engineer | ORD/000604/2021-2022 | 803/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.3 | 0 | 0
3133 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of HDPE pipeline in Parsola Mouza under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2023-2024 | 3011/BQA | 03/11/2023 | 45 | BHATTACHARYYA CONSTRUCTION | 1.45 | 0 | 50
3134 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000209/2022-2023 | FHTC/11 | 11/04/2022 | 0 | GOUTAM BHATTACHRYYA | 32.23 | 0 | 0
3135 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
3136 | Bankura Division | Khatra Sub-Division | Supply & delivery of portable multi parameter water quality testing device of the device of rural drinking water sources of 146 Nos. GP in Bankura District of west Bengal under PHE Dte | Assistant Engineer | Junior Engineer | VCH/002839/2021-2022 | FHTC/9 | 09/03/2022 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 13.33 | 0 | 0
3137 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Rudra (38 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002838/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.49 | 0 | 0
3138 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Pukhuria (10) mouzas Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Parsola Zone - B under and its adjoining mouza under Simlapal water supply shceme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, | Assistant Engineer | Junior Engineer | VCH/003125/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TAPAN KUMAR MANDAL | 3.98 | 0 | 0
3139 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukhadali (129), Chhotajamabedya (177) & Kusumtikri (178) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 3 Nos. Total Household:- 250 Nos. | Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 886/BQA | 13/04/2022 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 16.38 | 14.58 | 80
3140 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000272/2021-2022 | 3181/BQA | 21/12/2021 | 30 | SANJOY PATRA | 87.36 | 16.94 | 100
3141 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Goalbari (128) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 420 Nos. | Assistant Engineer | Junior Engineer | ORD/000456/2021-2022 | 670/BQA | 25/03/2022 | 30 | SAIKAT CHOWDHURY | 26.23 | 25.51 | 0
3142 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chatiasol (120) & Barajamabedya (127) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 362 Nos. | Assistant Engineer | Junior Engineer | ORD/000457/2021-2022 | 671/BQA | 25/03/2022 | 30 | JAGADISH BANERJEE | 22.73 | 21.73 | 0
3143 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baraamjhor (184) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 365 Nos. | Assistant Engineer | Junior Engineer | ORD/000458/2021-2022 | 672/BQA | 25/03/2022 | 30 | BEAUTY CHATTERJEE | 23.03 | 21.58 | 0
3144 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2022-2023 | 1839/BQA | 29/08/2022 | 0 | Resource Division | 8.91 | 0 | 0
3145 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Betjhor (179), Botha (180), Bhangadali (181), Ghungia (182) & Benasuli (183) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 377 Nos. | Assistant Engineer | Junior Engineer | ORD/000459/2021-2022 | 673/BQA | 25/03/2022 | 30 | SAKTIPADA MANDAL | 23.32 | 0 | 0
3146 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175) & Sindurpur (176) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 706 Nos. ( Part -A) | Assistant Engineer | Junior Engineer | ORD/000469/2021-2022 | 778/BQA | 31/03/2022 | 30 | GANESH ROY | 25.3 | 0 | 30
3147 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000475/2021-2022 | 108/KSD | 10/03/2022 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.6 | 3.11 | 20
3148 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175) & Sindurpur (176) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 706 Nos. ( Part-B ) | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 779/BQA | 31/03/2022 | 1372 | SUBHADIP KOLEY | 25.3 | 4.65 | 30
3149 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) with laying of UPVC pipeline in Goalbari (128) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2022-2023 | 333/BQA | 20/02/2023 | 45 | SAIKAT CHOWDHURY | 11.97 | 11.92 | 0
3150 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline in Sukhadali (129) & Kusumtikri (178) mouzas for retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2023-2024 | 2581/BQA | 15/09/2023 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 3.46 | 0 | 0
3151 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177), Kusumtikri (178), Betjhor (179), Botha (180), Bhangadali (181), Ghungia (182), Benasuli (183) & Baraamjhor (184) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 25) | Assistant Engineer | Junior Engineer | ORD/000688/2021-2022 | 864/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.83 | 0.43 | 0
3152 | Bankura Division | Khatra Sub-Division | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001075/2021-2022 | 734/BQA | 28/03/2022 | 10 | SANJOY PATRA | 4.99 | 4.97 | 25
3153 | Bankura Division | Khatra Sub-Division | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001076/2021-2022 | 737/BQA | 28/03/2022 | 10 | SANJOY PATRA | 4.98 | 4.91 | 20
3154 | Bankura Division | Khatra Sub-Division | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/001077/2021-2022 | 740/BQA | 28/03/2022 | 10 | SANJOY PATRA | 4.99 | 4.92 | 20
3155 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
3156 | Bankura Division | Bankura Sadar Sub-Division | Bridge crossing at Bhilani by 250mm dia MS Pipe & other allied works at Dhaban under Chhatna Block of Saltora- Chhatn W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000196/2022-2023 | 255/KSD | 12/07/2022 | 15 | SIB SANKAR CHOWDHURY | 2.41 | 2.4 | 0
3157 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No. of Mouza :- 01 no., Sidhabari (Part), Total House Hold- 35 nos. | Assistant Engineer | Junior Engineer | ORD/000422/2021-2022 | 52/BSD | 07/01/2022 | 10 | SK SAMSA ALAM | 2.99 | 0 | 0
3158 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- Bhabanipur, Upargara ( Part ) Total House Hold- 128 | Assistant Engineer | Junior Engineer | ORD/000491/2020-2021 | 621/BQA | 10/02/2021 | 30 | TAPAN KUMAR UPADHYAY | 11.33 | 0 | 0
3159 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Kumirdoha (Part), Total House Hold- 65 | Assistant Engineer | Junior Engineer | ORD/000494/2020-2021 | 156/ BSD | 18/02/2021 | 21 | KABISH KUMAR GHOSH | 4.77 | 0.43 | 0
3160 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Kumirdoha (Part), Total House Hold- 65 | Assistant Engineer | Junior Engineer | ORD/000495/2020-2021 | 157/ BSD | 18/02/2021 | 21 | SIMA KUMBHAKAR | 4.74 | 1.14 | 0
3161 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Kumirdoha (Part), Total House Hold- 65 | Assistant Engineer | Junior Engineer | ORD/000496/2020-2021 | 158/ BSD | 18/02/2021 | 21 | PRASANTA BHUIN | 4.74 | 0.86 | 0
3162 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No. of Mouza :- 01 nos (Fulberia), Total House Hold- 35 nos. | Assistant Engineer | Junior Engineer | ORD/000496/2021-2022 | 49/BSD | 07/01/2022 | 10 | LABIR MIRSHAD KHAN | 3 | 3 | 0
3163 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Kumirdoha (Part), Gairabad (Part) Total House Hold- 65 | Assistant Engineer | Junior Engineer | ORD/000497/2020-2021 | 161/ BSD | 18/02/2021 | 21 | LABIR MIRSHAD KHAN | 4.74 | 1.78 | 0
3164 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Gairabad (Part), Fulberia Total House Hold- 66 | Assistant Engineer | Junior Engineer | ORD/000498/2020-2021 | 165/ BSD | 18/02/2021 | 21 | SK SAMSA ALAM | 4.79 | 0.98 | 0
3165 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000499/2020-2021 | 162/ BSD | 18/02/2021 | 21 | MR. DURGADAS SINGHA | 4.83 | 1.07 | 0
3166 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000500/2020-2021 | 159/ BSD | 18/02/2021 | 21 | SRIKANTA MONDAL | 4.83 | 1.77 | 0
3167 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000501/2020-2021 | 166/ BSD | 18/02/2021 | 20 | SOUMITRA KUMAR DAS | 4.83 | 0.62 | 0
3168 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000502/2020-2021 | 163/ BSD | 18/02/2021 | 21 | ACHARJEE & SON | 4.83 | 0 | 100
3169 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000503/2020-2021 | 164/ BSD | 18/02/2021 | 21 | RAHUL CHATERJEE | 4.83 | 1.04 | 0
3170 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- Dhaban (Part), Total House Hold- 67 | Assistant Engineer | Junior Engineer | ORD/000748/2020-2021 | 162/BSD | 18/02/2021 | 21 | DURGADAS SINGHA | 4.83 | 0 | 0
3171 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no ,Sidhaberia (Part), Total House Hold- 145 nos. | Assistant Engineer | Junior Engineer | VCH/000222/2022-2023 | FHTC/08 | 08/04/2022 | 0 | TAPAS KUMBHAKAR | 9.46 | 0 | 0
3172 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban zone - A under Saltora - Chhatna water supply scheme ( BRGF PH - I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -chhatna Name of OHR -No (Dhaban , No. of Mouza :- 01 nos, Total House Hold - 35 nos. | Assistant Engineer | Junior Engineer | VCH/000269/2022-2023 | FHTC/18 | 18/04/2022 | 0 | SK SAMSA ALAM | 2.99 | 0 | 0
3173 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- Upargara ( Part ) Total House Hold- 128 | Assistant Engineer | Junior Engineer | VCH/000655/2022-2023 | FHTC/21 | 21/07/2022 | 0 | SAIKAT CHOWDHURY | 1.79 | 0 | 0
3174 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Gogra, Adhury mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Horaka (Zone - G) under Saltora Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002360/2021-2022 | FHTC/28 | 28/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.86 | 0 | 0
3175 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line near Tajpur, Rampur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/002361/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0
3176 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Tajpur, Rampur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | VCH/002362/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.82 | 0 | 0
3177 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dhanarangi (8) & Bansol (16) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) | Assistant Engineer | Junior Engineer | VCH/002363/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DEBAKI RANJAN SARKAR | 2.34 | 0 | 0
3178 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Salapahari (5) & Elora (7) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 19) | Assistant Engineer | Junior Engineer | VCH/002364/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DEBAKI RANJAN SARKAR | 1.02 | 0 | 0
3179 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Lachaipur (9) & Gopalpur (11) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 20) | Assistant Engineer | Junior Engineer | VCH/002365/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DEBAKI RANJAN SARKAR | 4.17 | 0 | 0
3180 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying additional 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, PN16) pipe to cover Dakai (268) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) | Assistant Engineer | Junior Engineer | VCH/002366/2021-2022 | FHTC/28 | 28/01/2022 | 0 | ASOKE KUMAR SAHU | 2.08 | 0 | 0
3181 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Susunia mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002367/2021-2022 | FHTC/28 | 28/01/2022 | 0 | I.R.CONSTRUCTION | 3.47 | 0 | 0
3182 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Supplying, laying by UPVC pipe (6 Kg/Sq. Cm. Water Pressure, class III) for distribution network along with ancillary works at village Karbhanga due to Strengthening - Widening of Sarenga Chowrasta More to Goaltore road by PWD (Roads) Dte. under Water supply scheme for Gargaria Zone-B of Sarenga Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Under Jal Swapna & Jal Jeevan Mission Programme Fund) (Sl. No.- 14) | Assistant Engineer | Junior Engineer | VCH/002368/2021-2022 | FHTC/28 | 28/01/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.87 | 0 | 0
3183 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-4) DPR no - 35.Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (120 out of 714), House Hold - 120 | Assistant Engineer | Junior Engineer | VCH/002369/2021-2022 | FHTC/28 | 28/01/2022 | 0 | MAYA CONSTRUCTION | 8.32 | 0 | 0
3184 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra HDPE pipeline to cover Mahaldanga (34) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) | Assistant Engineer | Junior Engineer | VCH/002370/2021-2022 | FHTC/28 | 28/01/2022 | 0 | ASOKE KUMAR SAHU | 4.97 | 0 | 0
3185 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART- B) | Assistant Engineer | Junior Engineer | VCH/002371/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.77 | 0 | 0
3186 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtcional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Parasia), Total House Hold -155 |  | Junior Engineer | ORD/000024/2021-2022 | 1799/BQA | 09/07/2021 | 30 | TAPAN KUMAR UPADHYAY | 9.05 | 0 | 0
3187 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Gara), Total House Hold -132 |  | Junior Engineer | ORD/000029/2021-2022 | 1798/BQA | 09/07/2021 | 30 | SK. ALAMAGIR ALAM | 7.34 | 0 | 0
3188 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Jorhira, Arajuri), Total House Hold -447 |  | Junior Engineer | ORD/000053/2021-2022 | 1931 A /BQA | 28/07/2021 | 30 | TAPAS PAL | 26.93 | 5.35 | 0
3189 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Sanpura, Kalipahari), Total House Hold - 451 |  | Junior Engineer | ORD/000054/2021-2022 | 1931 B / BQA | 28/07/2021 | 30 | TARINI CHARAN UPADHYAY | 27.98 | 0 | 0
3190 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- Sanpura (Part) Total House Hold - 59 nos. |  | Junior Engineer | ORD/000069/2022-2023 | 254/KSD | 12/07/2022 | 15 | TARINI CHARAN UPADHYAY | 4.36 | 0 | 0
3191 | Bankura Division | Bankura Sadar Sub-Division | Laying UPVC pipes for jorehera mouza of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) |  | Junior Engineer | VCH/001207/2022-2023 | FHTC/15 | 15/09/2022 | 0 | TAPAS PAL | 1.52 | 0 | 0
3192 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- Jorehira (Part), Total House Hold - 50 nos. (Sl. No. 12) |  | Junior Engineer | ORD/000084/2022-2023 | 259/KSD | 12/07/2022 | 15 | DURGADAS SINGHA | 2.5 | 2.49 | 0
3193 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying Extra UPVC Pipe Line to Cover Jorehira mouza & Dismantaling & reconstruction of concrete for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000086/2022-2023 | 352/KSD | 16/08/2022 | 20 | DURGADAS SINGHA | 3.81 | 3.79 | 0
3194 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHIRA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - JOREHIRA, No. of Mouza :- 01 no., JORHIRA (PART), Total House Hold :- 10 Nos. |  | Junior Engineer | ORD/000127/2023-2024 | 98/KSD | 28/04/2023 | 30 | TAPAS KUMBHAKAR | 0.59 | 0 | 100
3195 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No. of Mouza:- 1 no., ( Parasia), Total House Hold -18 nos. (Sl. No. 04) |  | Junior Engineer | ORD/000137/2022-2023 | 251/KSD | 12/07/2022 | 15 | TAPAN KUMAR UPADHYAY | 1.4 | 0 | 0
3196 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHIRA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - JOREHIRA, No. of Mouza :- 03 no, PARASIA (PART), Jhikuria (PART), kuladabar(PART), Total House Hold :- 12 Nos. |  | Junior Engineer | ORD/000157/2023-2024 | 102/KSD | 28/04/2023 | 30 | TAPAS KUMAR HAZRA | 0.68 | 0 | 100
3197 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 |  | Junior Engineer | ORD/000210/2020-2021 | 2031/BQA | 29/12/2020 | 30 | RANABIR CHATTERJEE | 41.02 | 2.46 | 0
3198 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Parasia air valve to Jirrah village for water supply arrangement at Jirrah village for retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000277/2022-2023 | 07/BQA | 03/01/2023 | 45 | BISWARUP BOSE | 26.51 | 14.92 | 0
3199 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Chhatna, Name of OHR - Jorehira, No.of Mouza :- 01 no., Jorehira (Part), Total House Hold- 75 nos. |  | Junior Engineer | ORD/000312/2021-2022 | 3367/BQA | 31/12/2021 | 30 | DURGADAS SINGHA | 5.59 | 5.59 | 0
3200 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Jorehira, No. of Mouza:- 1 no., ( Parasia), Total House Hold -18 nos. (Sl. No. 04) |  | Junior Engineer | VCH/001203/2022-2023 | FHTC/28 | 28/09/2022 | 0 | TAPAN KUMAR UPADHYAY | 1.39 | 0 | 0
3201 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
3202 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Mithila Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block, |  | Junior Engineer | VCH/001783/2021-2022 | FHTC/28 | 28/10/2021 | 0 | PARAMESWAR CHOWDHURY | 4.65 | 0 | 0
3203 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kesiakole Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block, |  | Junior Engineer | VCH/001784/2021-2022 | FHTC/28 | 28/10/2021 | 0 | PARAMESWAR CHOWDHURY | 3.95 | 0 | 0
3204 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 12) |  | Junior Engineer | VCH/001785/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0
3205 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2), |  | Junior Engineer | VCH/001786/2021-2022 | FHTC/07 | 07/10/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
3206 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover dadhimukha & Jagdalla mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002588/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 4.48 | 0 | 0
3207 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002589/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 4.22 | 0 | 0
3208 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002598/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 29.87 | 0 | 0
3209 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Simia , bank simul mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Chinabari Zone - H under Saltora block Saltora - Chhatna Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte part - A |  | Junior Engineer | VCH/003104/2021-2022 | FHTC/30 | 30/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.73 | 0 | 0
3210 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Simia , bank simul mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Chinabari Zone - H under Saltora block Saltora - Chhatna Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte part - B |  | Junior Engineer | VCH/003105/2021-2022 | FHTC/30 | 30/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.11 | 0 | 0
3211 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2020-2021 | 474/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 23.18 | 1.88 | 0
3212 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5) & Elora (7) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2020-2021 | 476/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 37.99 | 0 | 0
3213 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dhanarangi (8) & Bansol (16) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) | Assistant Engineer | Junior Engineer | ORD/000262/2021-2022 | 554/KSD | 29/06/2021 | 10 | DEBAKI RANJAN SARKAR | 2.34 | 0 | 0
3214 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Salapahari (5) & Elora (7) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 19) | Assistant Engineer | Junior Engineer | ORD/000263/2021-2022 | 555/KSD | 29/06/2021 | 10 | DEBAKI RANJAN SARKAR | 1.03 | 0 | 0
3215 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Salapahari (5), Elora (7), Dhanarangi (8) & Bansol (16) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000518/2020-2021 | 316/KSD | 29/12/2020 | 61 | ASOKE KUMAR SAHU | 0.29 | 0 | 0
3216 | Bankura Division | Khatra Sub-Division | E - Payment / Online payment -RTGS/NEFT/IMPS office of the RWS bankura Sub Division under Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002308/2021-2022 | FHTC/04 | 04/01/2022 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0
3217 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
3218 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/002292/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.72 | 0 | 0
3219 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Total House Hold -73 | Assistant Engineer | Junior Engineer | VCH/002293/2021-2022 | FHTC/31 | 31/01/2022 | 0 | M/S BANERJEE & BANERJEE | 0.39 | 0 | 0
3220 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar , Name of Village Kadakuli Man Para, Total House Hold -70 | Assistant Engineer | Junior Engineer | VCH/002295/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GON ASSOCIATES | 0.33 | 0 | 0
3221 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/002296/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.75 | 0 | 0
3222 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002297/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SUBHANKAR BANERJEE | 7.61 | 0 | 0
3223 | Bankura Division | Khatra Sub-Division | Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/002299/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0
3224 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SOMSAR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Somsar, No. of Mouza :- 01 no. i.e. (Somsar-02), Total House Hold - 1058 | Assistant Engineer | Junior Engineer | VCH/002454/2021-2022 | FHTC/1 | 01/02/2022 | 0 | M/S K.B.CONSTRUCTION | 13.26 | 0 | 0
3225 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5) & Elora (7) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003016/2021-2022 | FHTC/28 | 28/03/2022 | 0 | DEBAKI RANJAN SARKAR | 8.12 | 0 | 0
3226 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3227 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Deulvira Nabadeulvira |  | Junior Engineer | BILL/00516/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3228 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3229 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
3230 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3231 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Chandra Sonardanga |  | Junior Engineer | BILL/00520/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3232 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10993. |  | Junior Engineer | BILL/00766/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3233 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3234 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
3235 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3236 | Bankura Division | Bankura Sadar Sub-Division | Sibarampur,9330862734,Bankura-I | Assistant Engineer | Junior Engineer | BILL/00761/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
3237 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3238 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32.5 | 48
3239 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3240 | Bankura Division | Bankura Sadar Sub-Division | Kaludihi,Bankura-I | Assistant Engineer | Junior Engineer | BILL/00762/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
3241 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3242 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30.5 | 48
3243 | Bankura Division | Bankura Sadar Sub-Division | Bmsd Phe Dte Vill-Panchpukuria, Po-Jhagrapur, Ps-Bankura | Assistant Engineer | Junior Engineer | BILL/00024/2023-2024 | FHTC/06 | 05/06/2023 | 0 | CHHATNA CCC | 0.12 | 0 | 0
3244 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3245 | Bankura Division | Bankura Sadar Sub-Division | New Connection at Shyamsundarpur,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00493/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
3246 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3247 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Panchpukuria. | Assistant Engineer | Junior Engineer | BILL/01399/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3248 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31.05 | 48
3249 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45 | 48
3250 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Burisal C/o Sudip saha, Burisal, Ranibandh |  | Junior Engineer | BILL/00039/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
3251 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3252 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3253 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
3254 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-50, Mouza-Jagannathpur, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00286/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3255 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3256 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3257 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38.6 | 48
3258 | Bankura Division | RWS Bankura Sub-Division | New Service Connection at Shyamsundarpur, Block-Taldangra , PHE Dte. |  | Junior Engineer | BILL/00317/2023-2024 | FHTC/08 | 04/08/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
3259 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3260 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3261 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
3262 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3263 | Bankura Division | RWS Bankura Sub-Division | New Connection at Golokpur,Taldangra,Pin-722102,PHE Dte. |  | Junior Engineer | BILL/00710/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
3264 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3265 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36 | 48
3266 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Goalkpur Village (SM/11040), (2) Mini Piped Water Supply Scheme for Bhedua Village (SM/11041), (3) Mini Piped Water Supply Scheme for Nachna Village (SM/11043), (4) Mini Piped Water Supply Scheme for Taltala Village (SM/11044), (5) Mini Piped Water Supply Scheme for Baharagarya Village (SM/11075) and (6) Mini Piped Water Supply Scheme for Jiakanali Village (SM/11078) |  | Junior Engineer | ORD/001998/2024-2025 | 198\KSD | 10/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 95
3267 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3268 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3269 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 55 | 48
3270 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3271 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3272 | Bankura Division | Bankura Sadar Sub-Division | Service connection at Kustore | Assistant Engineer | Junior Engineer | BILL/01458/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
3273 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
3274 | Bankura Division | Bankura Sadar Sub-Division | Manjura, Bankura-I,9330862734 | Assistant Engineer | Junior Engineer | BILL/00765/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
3275 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 33.5 | 48
3276 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3277 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for mini water supply scheme at Thanadumur,Pabra, village under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00835/2023-2024 | FHTC/09 | 19/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
3278 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3279 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
3280 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Jaljala, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00271/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3281 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3282 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3283 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
3284 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - dehuaboni, Mirjapur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00263/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3285 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3286 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3287 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
3288 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3289 | Bankura Division | Brishnupur Sub-Division | Quatation bill napukur, M.M.P Kotulpur | Assistant Engineer | Junior Engineer | BILL/00676/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3290 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3291 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Napukur | Assistant Engineer | Junior Engineer | BILL/01253/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3292 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
3293 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3294 | Bankura Division | RWS Bankura Sub-Division | New Service Connection at Mini Piped w/s scheme at village Jagatdeuli,P.O-Shilpajambedia under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00813/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3295 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3296 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
3297 | Bankura Division | Brishnupur Sub-Division | (site - Bamunairy, M.M.P, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00302/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3298 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3299 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3300 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW CONNECTION CHARGES AT BAMUNAIRY | Assistant Engineer | Junior Engineer | BILL/01272/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3301 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38 | 48
3302 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3303 | Bankura Division | RWS Bankura Sub-Division | New Service connection at Mini Piped w/s scheme at village-Kurushthalia Po-Araldihi under Bankura Mechanical Division PHE Dte. |  | Junior Engineer | BILL/00815/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3304 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3305 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
3306 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3307 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3308 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Duburia. | Assistant Engineer | Junior Engineer | BILL/01571/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3309 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
3310 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3311 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Kelara Brahmandiha | Assistant Engineer | Junior Engineer | BILL/00518/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3312 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3313 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
3314 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3315 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Botkula Brajarajpur | Assistant Engineer | Junior Engineer | BILL/01124/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3316 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3317 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
3318 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3319 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10976. |  | Junior Engineer | BILL/00768/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3320 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Kaliapathar Keliapathar |  | Junior Engineer | BILL/01126/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3321 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3322 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
3323 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
3324 | Bankura Division | Bankura Sadar Sub-Division | New connecion at vill-Rangadihi p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02602/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
3325 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45 | 48
3326 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3327 | Bankura Division | Brishnupur Sub-Division | New Connection at Jamsala,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00485/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
3328 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3329 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
3330 | Bankura Division | Brishnupur Sub-Division | (site - Malikota, gopinathpur, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00300/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3331 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3332 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3333 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
3334 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3335 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Kuchibedia, Jorda | Assistant Engineer | Junior Engineer | BILL/00521/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3336 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10884. | Assistant Engineer | Junior Engineer | BILL/00772/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
3337 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3338 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 34.5 | 48
3339 | Bankura Division | Brishnupur Sub-Division | (site - pritchak, mirzapur, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00303/2022-2023 |  | 18/01/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3340 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3341 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, Mirzapur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00717/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3342 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3343 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
3344 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, Mirzapur, Kotulpur) | Assistant Engineer | Junior Engineer | VCH/000638/2023-2024 |  | 12/09/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3345 | Bankura Division | Bankura Sadar Sub-Division | Extra FHTC survey work of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for KHYERKANALI, CHERABASTA, CHATARKANALI, TELEBEDIA, ARJUNPUR, HORIALGORA, KENDBONI, SONAHAHA & BANKATI under Bankura- I, II & Barjora Block W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 326/BSD | 06/04/2023 | 60 | TAPAS DEY | 0.87 | 0.87 | 100
3346 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line, valve chamber & Household tap connection (FHTC) at Mobarakpur village & Kadmaghati School & ICDS of CHERABASTA (Zone - K) & ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 323/BSD | 06/04/2023 | 7 | BAYEN CONSTRUCTION | 0.96 | 0.95 | 100
3347 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (SM/11822) | Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 378/BQA | 23/02/2023 | 45 | SANJOY MONDAL | 25.4 | 25.37 | 100
3348 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder due to damage caused for the laying of pipe line by PHE Department in the different stretches in Joypur baital road UNDER Bishnupur division PWDte. during the year 23-24 | Assistant Engineer | Junior Engineer | BILL/02195/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 2.71 | 0 | 0
3349 | Bankura Division | Brishnupur Sub-Division | Laying distribution system for Augmentation of Joypur ( JJM Revision ) Piped W/S. Scheme of Joypur Block under Bankura Division, PHE. Dte. ( PART-A) | Assistant Engineer | Junior Engineer | ORD/000040/2022-2023 | 1381/BQA | 27/06/2022 | 1223 | DEBAKI RANJAN SARKAR | 100 | 43.65 | 80
3350 | Bankura Division | Brishnupur Sub-Division | Laying distribution system for Augmentation of Joypur ( JJM Revision ) Piped W/S. Scheme of Joypur Block under Bankura Division, PHE. Dte. ( PART-B) | Assistant Engineer | Junior Engineer | ORD/000041/2022-2023 | 1394/BQA | 27/06/2022 | 1010 | SIB SANKAR CHOWDHURY | 100.05 | 46.01 | 90
3351 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no 300mm X 200mm X 250m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe at New Head Work Site for Augmetation of Joypur( JJM Revision ) Piped water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2023-2024 | 1067/BQA | 04/05/2023 | 698 | I.R.CONSTRUCTION | 19.03 | 0 | 95
3352 | Bankura Division | Brishnupur Sub-Division | Renovation of RCC Elevated Over Head Reservoir of 273 cum capacity with staging height 20 m and other allied works Augmentation of Joypur water supply scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2025-2026 | 1805/BQA | 19/08/2025 | 90 | SWAPAN KUMAR BIT | 11.69 | 0 | 90
3353 | Bankura Division | Brishnupur Sub-Division | Construction of Office cum Godown with sanitary and water supply arrangement at Head Work Site (New) of 60 sqmtr. (approx) area at water supply scheme for surface water based for Augmentation of Joypur water supply scheme under Bishnupur Sub-Division, Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 53BQA | 05/01/2023 | 908 | UTTAM KUMAR SINHAMAHAPATRA | 12.53 | 7.78 | 35
3354 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 90 mtr long for Augmentation of Joypur water supply scheme (Head Work Site, New) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 54/BQA | 05/01/2023 | 45 | BIJOY KOLEY | 5.28 | 4.78 | 50
3355 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.40 m x 3.6 m) for Augmentation of Joypur Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 55/BQA | 05/01/2023 | 90 | SAYED PAHALOWAN | 6.54 | 6.3 | 65
3356 | Bankura Division | Brishnupur Sub-Division | Rising main with new D.I pipe under Joypur water supply scheme (Augmentation) under Joypur Block within Bishnupur Sub-Division under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 56/BQA | 05/01/2023 | 45 | RAFIKUL MONDAL | 23.74 | 13.8 | 20
3357 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 7 nos. i.e.Kalabani-12,Padumpur-14,Rajsol-15,Salda-35,Joypur-36,Bamangram-40,Gokulnagar-43, Total House Hold - 3380 | Assistant Engineer | Junior Engineer | ORD/000389/2021-2022 | 200/BQA | 01/02/2022 | 827 | M/S CARE | 179.91 | 63.17 | 5
3358 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of RCC Over Head Reservoir of capacity 250 cum and staging height 20 mtr.with allied works for Augmentation of Joypur ( JJM Revision ) Piped W/S under Joypur Block of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2022-2023 | 181/BQA | 30/01/2023 | 270 | SRIKANTA MONDAL | 70.43 | 70.34 | 60
3359 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Kotalpara, Total House Hold - 30 | Assistant Engineer | Junior Engineer | ORD/000505/2020-2021 | 214/VSD | 07/12/2020 | 21 | NAYAN BARDHAN | 3.44 | 3.26 | 0
3360 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. (Part-A) Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Dulepara & Telipara, Total House Hold -66. | Assistant Engineer | Junior Engineer | ORD/000506/2020-2021 | 157/VSD | 18/09/2020 | 21 | BIT ENTERPRISE | 4.71 | 4.29 | 0
3361 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. (Part-A) Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Napitpara, Total House Hold -65 | Assistant Engineer | Junior Engineer | ORD/000507/2020-2021 | 158/VSD | 18/09/2020 | 21 | SWAPAN KUMAR BIT | 4.62 | 4.06 | 0
3362 | Bankura Division | Brishnupur Sub-Division | Additional work of Road Crossing for Jack Pussing of Augumentation of Joypur Water Supply Scheme under Joypur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000871/2023-2024 | 3003/BQA | 06/11/2023 | 513 | SIBSANKAR CHOWDHURY | 34.14 | 0 | 85
3363 | Bankura Division | Brishnupur Sub-Division | Supply of Various Type of Materials for construction and commissioning of RCC Over Head Reservoir of capacity 250 cum and staging height 20 mtr.with allied works for Augmentation of Joypur ( JJM Revision ) Piped W/S Scheme Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 3008/BQA | 03/11/2023 | 45 | SRIKANTA MONDAL | 5.95 | 5.95 | 90
3364 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Augmentation of Joypur Water Supply Scheme (SM/09878 ) & 2 nos. sites of Augmentationn Moynapur Water Supply Scheme (SM/09927) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001826/2024-2025 | 544/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.75 | 0 | 0
3365 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000062/2023-2024 | 2665/BQA | 22/09/2023 | 0 | Resource Division | 42.53 | 0 | 0
3366 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2023-2024 | 111/BQA | 10/01/2024 | 0 | Resource Division | 20.82 | 0 | 0
3367 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Joypur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00124/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
3368 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Katul of Joypur Piped Water Supply Scheme t/w-III ,Katul of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 | BP-2024-25-89 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0
3369 | Bankura Mechanical | Brishnupur Sub-Division | Joypur Pump house-II | Assistant Engineer | Junior Engineer | BILL/01508/2023-2024 | BP-2023-24-108 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.59 | 0 | 0
3370 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Joypur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000425/2023-2024 | 1686/BMD | 27/07/2023 | 859 | PRADIP KUMAR DHABAL | 39.53 | 30.88 | 30
3371 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43.5 | 48
3372 | Bankura Division | RWS Bankura Sub-Division | New service connection for Harishchndrapur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00119/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
3373 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3374 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3375 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
3376 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3377 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Salgolia Keliapathar | Assistant Engineer | Junior Engineer | BILL/01122/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3378 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3379 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 23 | 48
3380 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Amlasol site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00181/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
3381 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3382 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3383 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
3384 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 177.28 | 6
3385 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
3386 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 19.3 | 0 | 0
3387 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000298/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 4.05 | 0 | 0
3388 | Bankura Mechanical | Brishnupur Sub-Division | Ghagara Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01497/2023-2024 | BP-23-24 -110 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.38 | 0 | 0
3389 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Shibardanga site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00196/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
3390 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3391 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3392 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27 | 48
3393 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Jhero, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00272/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
3394 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3395 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3396 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
3397 | Bankura Division | RWS Bankura Sub-Division | New Connection at Domakonda, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00443/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
3398 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
3399 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Painada Modarpur Village (SM/11036), (2) Mini Piped Water Supply Scheme for Resiagara Village (SM/11037), (3) Mini Piped Water Supply Scheme for Shyamsundarpur Village (SM/11038), (4) Mini Piped Water Supply Scheme for Dunduria Village (SM/11199), (5) Mini Piped Water Supply Scheme for Domakonda Village (SM/11203) and (6) Mini Piped Water Supply Scheme for Chenchurya Village (SM/11046). |  | Junior Engineer | ORD/002000/2024-2025 | 200\KSD | 10/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 95
3400 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Mayapur Harinagar | Assistant Engineer | Junior Engineer | BILL/00050/2024-2025 | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0
3401 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3402 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3403 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
3404 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 13 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002199/2024-2025 | 579\VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 1.96 | 0 | 0
3405 | Bankura Division | Brishnupur Sub-Division | New Connection at Paschim Nabason | Assistant Engineer | Junior Engineer | BILL/00302/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
3406 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3407 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3408 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
3409 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3410 | Bankura Division | Brishnupur Sub-Division | New Connection at Kamar Bera,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00488/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
3411 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3412 | Bankura Division | Brishnupur Sub-Division | New Service Connection for Mini Piped water supply Scheme at Khosalpur, Hamirpur block-Patrasayer under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02574/2023-2024 | FHTC/03 | 12/03/2024 | 0 | PATRASAYER CCC | 0.72 | 0 | 0
3413 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
3414 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3415 | Bankura Division | Brishnupur Sub-Division | New Connection at Dihilapur,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00489/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
3416 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3417 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32.6 | 48
3418 | Bankura Division | Bankura Sadar Sub-Division | Construction of boundary wall at proposed and existing OHR site, construction of guard room at zone- I, construction of high lift pump house at zone- II and road crossing works by Jackpushing method by hume pipe under Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2025-2026 | 1296/BQA | 17/06/2025 | 288 | PRINCE INDUSTRIES (INDIA) | 57 | 0 | 2
3419 | Bankura Division | Bankura Sadar Sub-Division | . Preparation of DPR for Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Jal Jeevan Mission (JJM) Project of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2023-2024 | 1334/BQA | 01/06/2023 | 30 | ENVIROTECH SOLUTIONS | 3.87 | 3.87 | 100
3420 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura Sadar Sub - Division within Bankura Division, PHE Dte.(ZONE I) | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 1962/BQA | 18/07/2023 | 985 | PRINCE INDUTRIES (INDIA) | 391.39 | 77.38 | 54
3421 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura Sadar Sub - Division within Bankura Division, PHE Dte.(Zone- II) | Assistant Engineer | Junior Engineer | ORD/000398/2023-2024 | 2083/BQA | 27/07/2023 | 889 | SANJOY PATRA | 298.83 | 26.4 | 12
3422 | Bankura Division | Bankura Sadar Sub-Division | Extention of HDPE Pipe line and installation of street stand post (SSP) at Samijinagar(Ghoshpara) and Madananaolly under Ashna (Katjuridanga) W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 375/BQA | 23/02/2023 | 45 | SUBHADIP DAS | 2.01 | 1.99 | 0
3423 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (150 CUM CAPACITY) staging hight 20 mtr. under Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura (Sadar) Sub - Division within Bankura Division, PHE Dte. (Zone- II) | Assistant Engineer | Junior Engineer | ORD/000637/2022-2023 | 576/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
3424 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 70.44 | 0 | 0
3425 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000126/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 6.22 | 0 | 0
3426 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000229/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 6.22 | 0 | 0
3427 | Bankura Mechanical | Bankura Sadar Sub-Division | Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of water supply scheme for Ashna (Karjuridanga) and adjoiningmouza under Bankura Mechanical Division, PHE Dte., Block: Bankura-I Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000535/2024-2025 | 449/BMD | 28/06/2024 | 180 | MAHADEV ENTERPRISE | 127.99 | 0 | 30
3428 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3429 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3430 | Bankura Division | Bankura Sadar Sub-Division | service connection at kustore | Assistant Engineer | Junior Engineer | BILL/01407/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
3431 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
3432 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3433 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3434 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
3435 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Chhatina site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00176/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
3436 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3437 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3438 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 48
3439 | Bankura Division | Brishnupur Sub-Division | New Connection at Chhota Narayanpur, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00299/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
3440 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3441 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3442 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
3443 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3444 | Bankura Division | Brishnupur Sub-Division | New Connection at Bara Narayanpur, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00719/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
3445 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3446 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
3447 | Bankura Division | Brishnupur Sub-Division | New Connection at Maitya, Sonamukhi, PHE Dte | Assistant Engineer | Junior Engineer | BILL/00301/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
3448 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3449 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3450 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
3451 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3452 | Bankura Division | RWS Bankura Sub-Division | New Connection at JL No-91, Mouza-Banakharanga, Bliock-Raipur PHE Dte. |  | Junior Engineer | BILL/00626/2023-2024 | FHTC/04 | 29/04/2024 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3453 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3454 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
3455 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 13.1 | 0 | 0
3456 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000073/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 53.82 | 0 | 0
3457 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Atra(T/W-I) water supply scheme at patrasayer block under BMD PHE Dte.(SM/14000) | Assistant Engineer | Junior Engineer | BILL/01469/2024-2025 | BP-2024-25-366 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0
3458 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at Atra (T/W-II) water supply scheme at patrasayer block under BMD PHE Dte.(SM/14000) | Assistant Engineer | Junior Engineer | BILL/01470/2024-2025 | BP-2024-25-367 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
3459 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Atra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2025-2026 | 237/BMD | 14/05/2025 | 90 | M/S D. PALIT AND CO. | 11.66 | 0 | 0
3460 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Atra Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 880/BMD | 04/05/2023 | 1080 | RAJIB COMPANY | 47 | 18.97 | 40
3461 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
3462 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
3463 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
3464 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 1488/BQA | 18/06/2024 | 45 | SUBHADIP KOLE | 20.47 | 20.37 | 90
3465 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design ) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 1198/BQA | 22/05/2023 | 270 | PRAVAT SARKAR | 367.98 | 139.72 | 40
3466 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
3467 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 2425/BQA | 22/08/2023 | 45 | JALALUDDIN MOLLA | 19.49 | 0 | 0
3468 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000578/2022-2023 | 448/BQA | 06/03/2023 | 90 | DURGADAS SINGHA | 8.65 | 0 | 0
3469 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2022-2023 | 451/BQA | 06/03/2023 | 90 | ASHIS PAL | 8.65 | 0 | 0
3470 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2022-2023 | 452/BQA | 06/03/2023 | 416 | ROY CHOWDHURY ENTERPRISE | 4.63 | 0 | 0
3471 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-8B) (Sl. No. 15) | Assistant Engineer | Junior Engineer | ORD/000635/2022-2023 | 193/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.43 | 3.4 | 0
3472 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2023-2024 | 886/BQA | 12/03/2024 | 643 | SWAPAN KUMAR UPADHYAY | 19.54 | 5.12 | 80
3473 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000047/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 0.55 | 0 | 0
3474 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000213/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 11.09 | 0 | 0
3475 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-8B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000245/2023-2024 | 1130/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
3476 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KALYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 1136/BQA | 15/05/2023 | 276 | MD. AAMIR KHAN | 351.57 | 79.63 | 5
3477 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Kalyanpur Piped Water Supply Scheme (SM/14010) & 2 nos. sites of Dhan Simla Piped Water Supply Scheme (SM/16706) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001894/2024-2025 | 572/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.6 | 0 | 0
3478 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000055/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 61.34 | 0 | 0
3479 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Kalyanpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14010) | Assistant Engineer | Junior Engineer | BILL/01253/2024-2025 | BP-2024-25-325 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.71 | 0 | 0
3480 | Bankura Mechanical | Brishnupur Sub-Division | Kalyanpur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01513/2023-2024 | BP-2023-24-115 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
3481 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kalyanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 870/BMD | 04/05/2023 | 180 | INDRAJIT MITRA | 31.37 | 14.56 | 46
3482 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR HARINASHULI & JADABNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1918/BQA | 13/07/2023 | 810 | GOPAL CHANDRA CHOWDHURY | 1591.82 | 591.28 | 85
3483 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
3484 | Bankura Division | Brishnupur Sub-Division | Jack Pussing, Land development & Rock cutting for foundation of 500 M3 capacity RCC OHR with 20 Mtr. staging height of Jadabnagar Water Supply Scheme & 450 M3 capacity RCC OHR with 20 Mtr. staging height of Harinasuli Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 3001/BQA | 03/11/2023 | 45 | GOPAL CHANDRA CHOWDHURY | 74.67 | 36.64 | 95
3485 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 74.23 | 0 | 0
3486 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 2524/BQA | 08/09/2023 | 0 | Resource Division | 18.03 | 0 | 0
3487 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000154/2023-2024 | 111/BQA | 10/01/2024 | 0 | Resource Division | 18.03 | 0 | 0
3488 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-I | Assistant Engineer | Junior Engineer | BILL/00848/2023-2024 | BP-2023-24-41 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.08 | 0 | 0
3489 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-II | Assistant Engineer | Junior Engineer | BILL/00849/2023-2024 | BP-2023-24-42 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.87 | 0 | 0
3490 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-III | Assistant Engineer | Junior Engineer | BILL/00850/2023-2024 | BP-2023-24-43 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.56 | 0 | 0
3491 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Jadabnagar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000165/2023-2024 | 877/BMD | 04/05/2023 | 1035 | EASTERN INDIA SALES & SERVICE | 59.05 | 30.27 | 55
3492 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHAGARIA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2023-2024 | 1971/BQA | 18/07/2023 | 1048 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 534.2 | 194.99 | 70
3493 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Dhagaria Piped Water Supply Scheme (SM/15023), 2 nos. sites of Atra Piped Water Supply Scheme (SM/14000) & 2 nos. sites of Salkhara Piped Water Supply Scheme (SM/14003) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001883/2024-2025 | 561/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
3494 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 11.4 | 0 | 0
3495 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000034/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 26.98 | 0 | 0
3496 | Bankura Mechanical | Brishnupur Sub-Division | New sevice connection at Hamirpur-II for Dhagoria water supply scheme at Patrasater block under BMD PHE Dte.(SM/15023) | Assistant Engineer | Junior Engineer | BILL/01467/2024-2025 | BP-2024-25-364 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.31 | 0 | 0
3497 | Bankura Mechanical | Brishnupur Sub-Division | Dhagaria Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01670/2023-2024 | BP-2023-24-182 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.51 | 0 | 0
3498 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhagaria Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000035/2025-2026 | 240/BMD | 14/05/2025 | 90 | M/S SOMA ENTERPRISES | 11.67 | 0 | 0
3499 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Dhagaria Piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrashayar , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 769/BMD | 24/04/2023 | 1080 | M/S SWAPAN BANERJEE | 47.1 | 27.72 | 58
3500 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder due to damage caused for the laying of pipe line by PHE department in the different stretches in kotulpur kamarpukur road under Bishnupur division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02190/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 13.06 | 0 | 0
3501 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE Department from 0.800 km to 3.165 km in Kotulpur Indas road (MDR) under Bishnupur Division P.W.Dte. during the year 23-24 | Assistant Engineer | Junior Engineer | BILL/02191/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 8.64 | 0 | 0
3502 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder & Bituminious portion due to damage caused for the laying of pipe line by PHE Department from 29.09 km to 30.00 km in Bishnupur - Kotulpur road SH 2 UNDER Bishnupur division PWDte. during the year 23-24 | Assistant Engineer | Junior Engineer | BILL/02194/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 15.7 | 0 | 0
3503 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder due to probable caused for the laying of pipe line by PHE Department in the different stretches in Bishnupur - Kotulpur road sh 2 UNDER Bishnupur division PWDte. during the year 23-24 | Assistant Engineer | Junior Engineer | BILL/02196/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 16.09 | 0 | 0
3504 | Bankura Division | Brishnupur Sub-Division | Laying distribution system Augmentation of Kotulpur Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 1061/BQA | 10/05/2022 | 1057 | M/S TARUN KUMAR PATRA | 191.68 | 177.15 | 100
3505 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 170 mtr long for augmentation of Kotulpur water supply scheme (Head Work Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 57/BQA | 05/01/2023 | 30 | ANNDAMAYEE CONSTRUCTION | 8.99 | 5.84 | 0
3506 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 70 mtr long for augmentation of Kotulpur water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 58/BQA | 05/01/2023 | 30 | SK. ALAMGIR ALAM | 7.28 | 3.01 | 10
3507 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 70 mtr long for augmentation of Kotulpur water supply scheme (pump house no 3) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 59/BQA | 05/01/2023 | 226 | LABIR MIRSHAD KHAN | 7.28 | 6.79 | 20
3508 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 No.Tube well 300 X 200 mm dia. X 165 Mtr. Depth Deep Tube well at Chadnighat by Rig boring for Kotulpur W/S Scheme Under Bishnupur Sub-Division of Bankura Division, PHE Dte. within Kotulpur Block, Dist :- BANKURA | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 60/BQA | 05/01/2023 | 30 | OSMAN SEKH | 14.89 | 14.53 | 90
3509 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 18 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KOTULPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 354/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 12.83 | 12.83 | 20
3510 | Bankura Division | Brishnupur Sub-Division | "Sinking of 1 No. Tube well 300 X 200 mm dia. X 165 Mtr. Depth Deep Tube well (at Opposite of Office cum Godown) by Rig boring for Kotulpur W/S Scheme Under Bishnupur Sub-Division of Bankura Division, PHE Dte. within Kotulpur Block, Dist :- BANKURA TSM No.- TSM/005085, SM/09981 , AAFS Project Id :- PH212246187S000" | Assistant Engineer | Junior Engineer | ORD/000556/2022-2023 | 520/BQA | 14/03/2023 | 932 | TAPAS KUMAR HAZRA | 14.88 | 13.98 | 60
3511 | Bankura Division | Brishnupur Sub-Division | Aditional work of Road Crossing for Jack Pussing of Augumention of Kotulpur Water Supply Scheme under Bishnupur Sub vision of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000870/2023-2024 | 3002/BQA | 03/11/2023 | 45 | M/S TARUN KUMAR PATRA | 47.66 | 45.52 | 90
3512 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.40 m x 3.6 m) for augmentation of Kotulpur Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. TSM No.- TSM/005085, SM/09981 , AAFS Project Id :- PH212246187S000 | Assistant Engineer | Junior Engineer | ORD/000922/2023-2024 | 3112/BQA | 09/11/2023 | 509 | PRASANTA BHUIN | 6.54 | 0 | 30
3513 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) of Kotulpur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block -Kotulpur, Name of OHR - Kotulpur, No. of Mouza :- 4 nos. i.e.Gogra-48,Ganti-49,Kotulpur (CT)-51,Shiromonipur-102. Total House Hold - 4060 | Assistant Engineer | Junior Engineer | ORD/001085/2021-2022 | 201/BQA | 01/02/2022 | 828 | M/S CARE | 175.9 | 95.04 | 15
3514 | Bankura Division | Brishnupur Sub-Division | Construction of FHTC Platform, Construction of Boundary Wall & Pump House for Augmentation of Kotulpur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001356/2024-2025 | 3177/BQA | 24/12/2024 | 90 | TAPAS KUMAR HAZRA | 88.51 | 0 | 15
3515 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentationn Jayrambati Water Supply Scheme (SM/09880 ) & 3 nos. sites of Augmentationn Kotulpur Water Supply Scheme (SM/09981) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001874/2024-2025 | 552/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 100
3516 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000151/2023-2024 | 111/BQA | 10/01/2024 | 0 | Resource Division | 25.01 | 0 | 0
3517 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kotulpur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00125/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
3518 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-IV of Kotulpur W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01350/2024-2025 | BP-2024-25-353 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.84 | 0 | 0
3519 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kotulpur H/W site under Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1070/BMSD | 05/07/2024 | 119 | PRADIP KUMAR DHABAL | 4.38 | 0 | 100
3520 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000176/2023-2024 | 936/BMD | 12/05/2023 | 1080 | M/S SOMA ENTERPRISES | 45.85 | 34.16 | 75
3521 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House,Switch Room & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) | Assistant Engineer | Junior Engineer | ORD/000076/2025-2026 | 1015/BQA | 25/04/2025 | 341 | SOUMITRA KUMAR DAS | 32.17 | 0 | 0
3522 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block - Barjora, | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 1960/BQA | 18/07/2023 | 985 | PRINCE INDUTRIES (INDIA) | 352.95 | 199.55 | 80
3523 | Bankura Division | Bankura Sadar Sub-Division | FHTC (Functional House Hold Tap Connection') in SCHOOL, ICDS & House hold in connection with Jal Jeevan Mission (JJM) for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjor under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. (Zone- IA). No. of Mouza :- 01 nos., (Tikargram), No. of Household- 08 nos. | Assistant Engineer | Junior Engineer | ORD/001043/2023-2024 | 1165/BSD | 22/11/2023 | 15 | SAMIRUDDIN KHAN | 0.92 | 0.91 | 100
3524 | Bankura Division | Bankura Sadar Sub-Division | UPVC Pipe line inter connection From Lagardanga to Tikargram village of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IA) | Assistant Engineer | Junior Engineer | ORD/001075/2023-2024 | 1163\BSD | 22/11/2023 | 195 | AMIR UDDIN KHAN | 0.92 | 0.92 | 100
3525 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001184/2023-2024 | 436/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.77 | 0 | 100
3526 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000089/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4 | 0 | 0
3527 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | Assistant Engineer | Junior Engineer | BILL/00154/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
3528 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Sahebdanga Pump House augmentation work under Barjora (Left out Mouza) (zone-IA ) water supply scheme (SM/16974) | Assistant Engineer | Junior Engineer | BILL/00723/2024-2025 | BP-2024-25-200 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.63 | 0 | 0
3529 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 120 | SINHA ELECTRICALS | 11.28 | 0 | 0
3530 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC cum PDB and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) (Zone IA) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001034/2023-2024 | 2966/BMD | 29/02/2024 | 180 | TAPAN KUMAR SARKAR | 28.66 | 20.01 | 68
3531 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IA) under Bankura Mechanical Division, PHED. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 1780/BMD | 01/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 30
3532 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 300 mm X 200 mm X 200 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe,Construction of Pump House & Boundary wall at Tubewell site for Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 1323/BQA | 17/06/2025 | 138 | ASHOK KUMAR DEY | 31.13 | 0 | 0
3533 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-C (Biradihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 720/BQA | 30/03/2023 | 90 | MA KANKALI ENTERPRISE | 37.13 | 36.29 | 30
3534 | Bankura Division | Bankura Mechanical Sub-Division | Construction of Pump House at Tubewell site of Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001372/2024-2025 | 30/BQA | 02/01/2025 | 365 | KABISH KUMAR GHOSH | 7.12 | 0 | 80
3535 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 2 Nos. pump house at tubewell site, laying distribution pipeline and providing FHTC and platform of Zone-C (Biradihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001373/2024-2025 | 32/BQA | 02/01/2025 | 333 | UTTAM KUMAR SINHAMAHAPATRA | 31.31 | 0 | 20
3536 | Bankura Division | Bankura Mechanical Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Augmentation of Zone-C (Biradihi) Water Supply Scheme (SM/16980), 1 no. site of Augmentation of Zone-D (Lachiapur) Water Supply Scheme (SM/16984), 1 no. site of Augmentation of Zone-E (Naria) Water Supply Scheme (SM/17304), 1 no. site of Augmentation of Zone-F (Masanjhar) Water Supply Scheme (SM/17729), 1 no. site of Augmentation of Malian Water Supply Scheme (SM/17260) and 1 no. site of Augmentation of Zone-Q (Jambedia) Water Supply Scheme (SM/17432) within Hirbandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001912/2024-2025 | 156\KSD | 07/03/2025 | 10 | TAPAN KUMAR MANDAL | 0.9 | 0 | 90
3537 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000164/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
3538 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection of Biradihi OHR zone-C Piped Water Supply Scheme at t/w-I ,Moshiara of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00537/2024-2025 | BP-2024-25-145 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.49 | 0 | 0
3539 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Biradihi (Zone-C) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000195/2025-2026 | 641/BMD | 11/07/2025 | 90 | ABHIJIT MUKHERJEE | 22.82 | 0 | 0
3540 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories and providing spares of existing gaseous chlorination system for Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000140/2024-2025 | 483/BMD | 09/07/2024 | 600 | TAPAN KUMAR SARKAR | 27.35 | 0 | 20
3541 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BENDA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000332/2023-2024 | 2002/BQA | 19/07/2023 | 622 | S.N POLYMERS PVT LTD | 143.48 | 30.85 | 70
3542 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Benda Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001349/2024-2025 | 3166/BQA | 24/12/2024 | 90 | GOURANGA NANDI | 12.97 | 0 | 0
3543 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Benda water supply scheme | Assistant Engineer | Junior Engineer | BILL/00186/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
3544 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Mouza Ranikhamar of Benda w/s scheme.SM/17244 | Assistant Engineer | Junior Engineer | BILL/00538/2024-2025 | BP-2024-25-144 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.15 | 0 | 0
3545 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Additional quotation for full deposit work at mouza Ranikhamar ,JL no 53, Pl no 514 ,Dwarika, Bishnupur.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01238/2024-2025 | BP-2024-25-310 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.68 | 0 | 0
3546 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Zone-II CWR site of Kathjuridanga w/s scheme at Bidisha Nagar Mouza-Ailakandi.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01471/2024-2025 | BP-2024-25-362 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.02 | 0 | 0
3547 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Deuli ,Benda W/S scheme.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01602/2024-2025 |  | 17/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.69 | 0 | 0
3548 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Benda and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000137/2024-2025 | 443/BMD | 27/06/2024 | 360 | UNITED TRADERS | 21.56 | 0 | 100
3549 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Benda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000515/2023-2024 | 1880/BMD | 17/08/2023 | 840 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 65.93 | 39.69 | 48
3550 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BASUDEBPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2023-2024 | 2335/BQA | 14/08/2023 | 480 | KHAN ENTERPRISE | 529.02 | 72.88 | 2
3551 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Basudebpur Piped Water Supply Scheme (SM/16944) & 3 nos. sites of Dhulai Piped Water Supply Scheme. (SM/18753) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001895/2024-2025 | 573/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
3552 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 125.93 | 0 | 0
3553 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service connection for Basudebpur TW-I water supply scheme of sonamukhi block under Bankura Mechanical Division P.H.E Dte.(SM/16944) | Assistant Engineer | Junior Engineer | BILL/01180/2024-2025 | BP-2024-25-300 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0
3554 | Bankura Mechanical | Brishnupur Sub-Division | New three phase Service Connection for Basudebpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/16944) | Assistant Engineer | Junior Engineer | BILL/01181/2024-2025 | BP-2024-25-301 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.86 | 0 | 0
3555 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Basudebpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 657/BMD | 17/04/2023 | 180 | RAJIB COMPANY | 40.25 | 19.17 | 48
3556 | Bankura Division | Bankura Sadar Sub-Division | Laying of balance distribution system of Pipeline in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinabari (Zone - H) (Part) and Augmentation of Jamtora (Zone - G) (Part) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 1231/BQA | 02/06/2025 | 90 | ZAKIR HOSSIN MONDAL | 116.21 | 0 | 0
3557 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Alijhara, Bijpur Mouza of under Jamtora (Zone- G) Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, Total House Hold - 10 nos (Part-A) | Assistant Engineer | Junior Engineer | ORD/000292/2024-2025 | 649/BSD | 10/06/2024 | 7 | DURGADAS SINGHA | 0.96 | 0 | 100
3558 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Alijhara, Bijpur Mouza of under Jamtora (Zone- G) Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR -Jamtora, Total House Hold - 9 nos (Part-B) | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 650/BSD | 10/06/2024 | 7 | DURGADAS SINGHA | 0.65 | 0 | 100
3559 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Alijhara, Bijpur Mouza of under Jamtora (Zone- G) Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR -Jamtora, Total House Hold - 9 nos (Part-C) | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 651/BSD | 10/06/2024 | 7 | DURGADAS SINGHA | 0.65 | 0 | 100
3560 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Jamtora (Zone - I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000739/2023-2024 | 2353/BQA | 14/08/2023 | 270 | M/S BIPUL BANERJEE | 109.07 | 72.58 | 45
3561 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Jamtora (Zone-G) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 2972/BQA | 31/10/2023 | 30 | GEO SOLUTION | 2.37 | 1.93 | 100
3562 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000139/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.46 | 0 | 0
3563 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000248/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.46 | 0 | 0
3564 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Bantila More to Pithabaid village to increase pressure in Pithabaid (222) Mouza under Zone-IIA (Baragari) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1108/BQA | 11/05/2023 | 45 | SOUPTIK CHANDRA | 8.29 | 8.12 | 100
3565 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-IIA (Baragari) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 558/BQA | 17/03/2023 | 120 | BIJOY KOLEY | 52.59 | 52.58 | 90
3566 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Baragari OHR to Mashra Village, Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) and Construction of Platform with all allied works in connection with Augmentation of Baragari Zone-IIA Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001575/2024-2025 | 335/BQA | 29/01/2025 | 45 | D. S. ENTERPRISE | 13.27 | 0 | 0
3567 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Gopalpur more to Pithadungri Village and Sinking of 3 (Three) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with all allied works in connection with Augmentation of Baragari (Zone-IIA) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001763/2024-2025 | 529/BQA | 25/02/2025 | 303 | UTTAM KUMAR SINHAMAHAPATRA | 30.66 | 0 | 90
3568 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000170/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.91 | 0 | 0
3569 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00210/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
3570 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter Motorized Sulice valve with related allied works at Baragari (Zone-G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000023/2025-2026 | 234/BMD | 14/05/2025 | 90 | JAL PRAVAHIKA PVT LTD | 28.18 | 0 | 0
3571 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000688/2023-2024 | 2634/BQA | 21/09/2023 | 469 | SUBHENDU SEKHAR GORAI | 21.16 | 16.11 | 70
3572 | Bankura Division | Bankura Mechanical Sub-Division | Laying Rising Main of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000689/2023-2024 | 2635/BQA | 21/09/2023 | 915 | M/S. AMAL KUMAR SARKAR | 12.56 | 0 | 50
3573 | Bankura Division | Bankura Mechanical Sub-Division | SConstruction of 2 Nos. 100 Cum Clear Water Reservoir for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000690/2023-2024 | 2636/BQA | 21/09/2023 | 90 | SUBHADIP KOLE | 47.49 | 16.71 | 30
3574 | Bankura Division | Bankura Mechanical Sub-Division | Construction of 2 Nos. Pump House with ancillary works for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000756/2023-2024 | 2863/BQA | 11/10/2023 | 480 | SUBHAJIT BANERJEE | 15.32 | 12.7 | 40
3575 | Bankura Division | Bankura Mechanical Sub-Division | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000762/2023-2024 | 2866/BQA | 11/10/2023 | 753 | TAPAS PAL | 38.91 | 0 | 0
3576 | Bankura Division | Bankura Mechanical Sub-Division | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000764/2023-2024 | 2867/BQA | 11/10/2023 | 903 | M/S SUPRIYA CHATTERJEE | 38.91 | 0 | 38
3577 | Bankura Division | Bankura Mechanical Sub-Division | Construction Boundary wall at CWR site of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000865/2023-2024 | 3018/BQA | 03/11/2023 | 695 | SWAPAN KUMAR PATRA | 12.42 | 8.66 | 90
3578 | Bankura Division | Bankura Mechanical Sub-Division | Construction Boundary wall at CWR site of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000866/2023-2024 | 3019/BQA | 03/11/2023 | 876 | SWAPAN KUMAR PATRA | 12.15 | 0 | 0
3579 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000011/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 91.73 | 0 | 0
3580 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000196/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 4.95 | 0 | 0
3581 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/00201/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
3582 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/01662/2023-2024 | BP-2023-24-177 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
3583 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Khayerbani piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000566/2023-2024 | 2033/BMD | 01/09/2023 | 597 | RAJIB COMPANY | 45.28 | 21.8 | 48
3584 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BETANAL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000501/2023-2024 | 2351/BQA | 14/08/2023 | 270 | SUBHANKAR BANERJEE | 168.53 | 72.58 | 18
3585 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House for Augmentation of Betanal (Zone - A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001350/2024-2025 | 3167/BQA | 24/12/2024 | 90 | M/S ASHA ENGINEERING | 6.52 | 0 | 0
3586 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00178/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
3587 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01624/2023-2024 | BP-2023-24-151 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.77 | 0 | 0
3588 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical accessories at boosting P.H for augmentation of Betanal Zone A water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2025-2026 | 151/BMD | 30/04/2025 | 90 | ABHIJIT MUKHERJEE | 18.95 | 0 | 0
3589 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and Installation of Valves with other electro-mechanical accessories at Betanal CWR pipe line based water supply schemes of Indus under B.M.D, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2024-2025 | 777/BMD | 20/08/2024 | 347 | M/S SWAPAN BANERJEE | 12.56 | 0 | 95
3590 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000516/2023-2024 | 1881/BMD | 17/08/2023 | 684 | EASTERN INDIA SALES & SERVICE | 48.95 | 14.71 | 45
3591 | Bankura Division | Khatra Sub-Division | Balance work of Rising Main for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme and Proposed Sub-Surface Water Based Pirra Bakra Pipe Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000196/2025-2026 | 1410/BQA | 26/06/2025 | 158 | PRADIP PATRA | 10.35 | 0 | 0
3592 | Bankura Division | Khatra Sub-Division | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of Clear Water Reservoir, Construction of Pump House, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pirrabakra pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000502/2023-2024 | 2352/BQA | 14/08/2023 | 944 | S B ASSOCIATES | 223.33 | 48.08 | 80
3593 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
3594 | Bankura Division | Khatra Sub-Division | Preparation of Detailed Project Report for Proposed Sub Surface Water Based Pirra Bakra Pipe Water Supply Scheme under Bankura Division, Block : Khatra, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001079/2023-2024 | 3542/BQA | 29/12/2023 | 30 | LEMNISCATE | 2.76 | 2.76 | 90
3595 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 51.54 | 0 | 0
3596 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000195/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.07 | 0 | 0
3597 | Bankura Mechanical | Khatra Sub-Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/00200/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
3598 | Bankura Mechanical | Khatra Sub-Division | New service connection at PH-II of Pirra bankra W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00357/2025-2026 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.99 | 0 | 0
3599 | Bankura Mechanical | Khatra Sub-Division | New service connection at Pirrabakra. | Assistant Engineer | Junior Engineer | BILL/01475/2024-2025 | BP-2024-25-359 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0
3600 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Pirra Bakra piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000571/2023-2024 | 2035/BMD | 01/09/2023 | 960 | M/S BIPUL BANERJEE | 35.44 | 22.61 | 65
3601 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Low lift Pumping machineries with other electro mechanical accessories for 2nd no tubewell for proposed ground water based Pirra Bankra piped water supply scheme Block Khatra under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000881/2024-2025 | 2041/BMD | 07/03/2025 | 240 | M/S BIPUL BANERJEE | 9.91 | 0 | 60
3602 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with HDPE pipeline including fabrication of MS pipe & allied works for Kantabari Water Supply Scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site: Kantabari - Bhedua More at Kantabari) | Assistant Engineer | Junior Engineer | ORD/000185/2024-2025 | 1856/BQA | 12/07/2024 | 60 | SWAPAN KUMAR CHANDRA | 8.52 | 0 | 95
3603 | Bankura Division | Bankura Sadar Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KANTABARI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- ONDA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 2345/BQA | 14/08/2023 | 1235 | GOUTAM BHATTACHRYYA | 260.01 | 83.69 | 49
3604 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
3605 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 3048/BQA | 06/11/2023 | 30 | K S GROUP | 0.58 | 0.58 | 100
3606 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Kantabari (JL No- 265) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001089/2021-2022 | 283\BSD | 21/03/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.63 | 3.63 | 95
3607 | Bankura Division | Bankura Sadar Sub-Division | Construction of Guard Room and Boundary Wall at Kantabari OHR Site under Proposed Ground Water based Kantabari Pipe Water Supply Scheme under Bankura Division, Block:- Onda. | Assistant Engineer | Junior Engineer | ORD/001403/2024-2025 | 46/BQA | 02/01/2025 | 482 | RAHIBUDDIN MANDAL | 22.09 | 0 | 5
3608 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 1.42 | 0 | 0
3609 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000125/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.09 | 0 | 0
3610 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000260/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.09 | 0 | 0
3611 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | Assistant Engineer | Junior Engineer | BILL/00134/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0
3612 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories at CWR site at mouza Punisole for Augmentation of Aguriband Punisole (Zone E) and Adj. mouzas piped water supply scheme in the Block Onda under Bankura Mechanical Division PHE Dte Block Bankura-I Dist Bankura | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 2042/BMD | 07/03/2025 | 120 | M.S. ENTERPRISE | 67.43 | 0 | 0
3613 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from T05- Lakshmipur to SH under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-826, Road Length-8.68 Km. ( Augmentation ofwater supply scheme for Dubr4jpur (Zone-B) under Simlapal water supply Scheme (BRGF-Ph-I) | Assistant Engineer | Junior Engineer | BILL/01463/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.94 | 0 | 0
3614 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Sinking of 1 No. 300 mm X 200 mm X 250 Metre deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Valve Chamber, Construction of Boundary wall at Tubewell site, Construction of Pump House for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 1486/BQA | 18/06/2024 | 714 | SUBHENDU SEKHAR GORAI | 96.46 | 0 | 85
3615 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 3 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 2034/BQA | 24/07/2023 | 618 | PARAMESWAR CHOWDHURY | 237.05 | 37.92 | 30
3616 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2022-2023 | 570/BQA | 17/03/2023 | 30 | SUBHADIP KOLEY | 66.27 | 60.47 | 65
3617 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000855/2023-2024 | 2955/BQA | 31/10/2023 | 30 | MEASURE LAND | 4.5 | 4.44 | 95
3618 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 6 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17288] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001926/2024-2025 | 170\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
3619 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000188/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 4.8 | 0 | 0
3620 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01657/2023-2024 | BP-2023-24-179 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.16 | 0 | 0
3621 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 4 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17288] and 2 nos. site of Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/18894] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001927/2024-2025 | 171\KSD | 07/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 90
3622 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 240 m deep Tubewell (Replacement Tubewell) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Repairing and painting of Over Head Reservoir (Capacity 700 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Dubrajpur, Zone-B water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001975/2024-2025 | 669/BQA | 12/03/2025 | 60 | S B ASSOCIATES | 78.15 | 0 | 0
3623 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories in boosting site and existing pump house for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000146/2024-2025 | 489/BMD | 09/07/2024 | 360 | PRADIP KUMAR DHABAL | 25.33 | 0 | 20
3624 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Dubrajpur Zone-B water supply scheme under Dubrajpur water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000266/2024-2025 | 774/BMD | 20/08/2024 | 651 | GOENKA ENTERPRISE | 40.86 | 0 | 90
3625 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 900 | A.K.INDUSTRIES | 127.79 | 19.91 | 85
3626 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000567/2023-2024 | 2025/BMD | 01/09/2023 | 723 | SINHA ELECTRICALS | 71.68 | 47.77 | 66
3627 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 500 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room, Boundary Wall, laying distribution pipeline to provide FHTC, Sinking of 1 (One) No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), construction of Pump House and boundary wall at tubewell site with all allied works of Augmentation works for Mandalkuli, Zone-IIIB Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2025-2026 | 1289/BQA | 17/06/2025 | 183 | SUBHADIP KOLE | 67.34 | 0 | 0
3628 | Bankura Division | Khatra Sub-Division | Sinking of 1 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) including interconnection with 100 mm dia. G.I. Pipe,Construction of Pump House & Boundary wall at Tubewell site for Augmentation works for Mandalkuli, Zone-IIIB Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000282/2025-2026 | 1544/BQA | 14/07/2025 | 172 | MOUSUMI PODDARSINGHA | 19.55 | 0 | 0
3629 | Bankura Division | Khatra Sub-Division | Construction & commissioning of FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Mandalkuli, Zone-IIIB and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2023-2024 | 1957/BQA | 18/07/2023 | 270 | GOPAL CHANDRA CHOWDHURY | 147.48 | 142.61 | 100
3630 | Bankura Division | Khatra Sub-Division | Route survey, preparation of DPR for Augmentation of Intake ,WTP & Rising main for Surface water based Piped water Supply Scheme for Mukutmanipur , Khatra & Ranibandh Under Jal Jeevan Mission of Khatra Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001212/2023-2024 | 486/BQA | 09/02/2024 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.42 | 0 | 0
3631 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000190/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 4 | 0 | 0
3632 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00216/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
3633 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Mandalkuli (IIIB) under Raipur Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000014/2025-2026 | 149/BMD | 30/04/2025 | 90 | M/S SWAPAN BANERJEE | 13.38 | 0 | 0
3634 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000238/2023-2024 | 1123/BMD | 24/05/2023 | 30 | UNICON | 2.38 | 0 | 0
3635 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Mandalkuli (Zone IIIB) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000876/2024-2025 | 2037/BMD | 07/03/2025 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 84.8 | 0 | 0
3636 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BETANAL ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 1930/BQA | 13/07/2023 | 909 | SINGHA ENTERPRISE | 197.87 | 0 | 50
3637 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Betanal (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001351/2024-2025 | 3168/BQA | 24/12/2024 | 269 | ASEK ALI KHAN | 12.96 | 0 | 80
3638 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Betanal Zone-A Water Supply Scheme (SM/17692) & Augmentation of Betanal Zone-B Water Supply Scheme (SM/17418), 1 no. site of Augmentation of Karisunda Water Supply Scheme (SM/17419), 2 nos. sites of Augmentation of Kushmuri Zone-A Water Supply Scheme (SM/17420 ) & Augmentation of Kushmuri Zone-B Water Supply Scheme within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001814/2024-2025 | 540/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
3639 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement work for Betanal Zone-B water supply scheme at Indus Block Under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00006/2024-2025 | BP-2024-25-92 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0
3640 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00179/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
3641 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01617/2023-2024 | BP-2023-24-154 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.74 | 0 | 0
3642 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01627/2023-2024 | BP-2023-24-155 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
3643 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories at boosting P.H for Augmentation of Betanal Zone-B Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 858/BMD | 29/08/2024 | 300 | M/S SAJAHAN CHOWDHURY | 18.51 | 0 | 0
3644 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Betanal Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 859/BMD | 29/08/2024 | 120 | M.S. ENTERPRISE | 15.51 | 0 | 100
3645 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-B piped water supply scheme(BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 1698/BMD | 28/07/2023 | 777 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 67.31 | 34.66 | 40
3646 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHUAMASINA ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000392/2023-2024 | 2052/BQA | 24/07/2023 | 617 | SIB SANKAR CHOWDHURY | 155.9 | 41.21 | 65
3647 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House for Augmentation of Chuamosina (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001378/2024-2025 | 19/BQA | 02/01/2025 | 90 | SANTI RANJAN MANDAL | 6.56 | 0 | 0
3648 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chuamasina Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00167/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
3649 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 1886/BMD | 17/08/2023 | 1020 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 75.75 | 47.23 | 55
3650 | Bankura Division | Bankura Sadar Sub-Division | Wayleave/Track crossing proposal with application ID:SER-ADRA-WL-14 For Puncha (zone-c) SM Code-SM/SM/17285 | Assistant Engineer | Junior Engineer | BILL/00059/2024-2025 | FHTC/04 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY | 0.1 | 0 | 0
3651 | Bankura Division | Bankura Sadar Sub-Division | Payment of Wayleave fecility charges of PUNCHA (ZONE-C) W/S Scheme. Scheme Code-SM/17285. Application ID-SER-ADRA-2024-WL-14 | Assistant Engineer | Junior Engineer | BILL/00274/2024-2025 | BP-114/2024-25 | 19/06/2024 | 0 | SOUTH EASTERN RAILWAY | 5.64 | 0 | 0
3652 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of Augmentation of Puncha and its adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000184/2024-2025 | 1814/BQA | 11/07/2024 | 570 | M/S TARUN KUMAR PATRA | 125.34 | 0 | 85
3653 | Bankura Division | Bankura Sadar Sub-Division | Creation of FHTC (Functional House Hold Tap Connection)¿& parallel pipe line in connection with Jal Jeevan Mission (JJM) for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2023-2024 | 1925/BQA | 13/07/2023 | 962 | M/S TARUN KUMAR PATRA | 353.11 | 200.3 | 82
3654 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 2 (two) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method and Repairing and Renovation of RCC Elevated Over Head Reservoir of 500 Cum capacity under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I). | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 2347/BQA | 09/09/2024 | 30 | SUBHANKAR BANERJEE | 43.54 | 0 | 0
3655 | Bankura Division | Bankura Sadar Sub-Division | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 | Assistant Engineer | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 45 | SAMIRUDDIN KHAN | 5.4 | 1.5 | 100
3656 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000116/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 12.66 | 0 | 0
3657 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000283/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 12.66 | 0 | 0
3658 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at mouza Shingahati of Puncha zone C ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00288/2024-2025 | BP-2024-25-59 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0
3659 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-C) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000556/2023-2024 | 1992/BMD | 28/08/2023 | 120 | MENAKA ENTERPRISE | 41.73 | 28.3 | 60
3660 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3661 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for mini water supply scheme at Siakuldoba, Goswamidihi village under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00831/2023-2024 | FHTC/09 | 07/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
3662 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3663 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
3664 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3665 | Bankura Division | Brishnupur Sub-Division | New Connection at Goala Danga,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00490/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
3666 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3667 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18.6 | 48
3668 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Dharisayer site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00187/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
3669 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3670 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3671 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38 | 48
3672 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3673 | Bankura Division | RWS Bankura Sub-Division | Siarbada, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00769/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
3674 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3675 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36.6 | 48
3676 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "kesiadoba" Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00070/2024-2025 |  | 26/04/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
3677 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE (Kesiadoba) HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00124/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
3678 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3679 | Bankura Division | Bankura Sadar Sub-Division | New Service connection at Mini Piped w/s scheme at Kantakuli Po-Nabadeuluira under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00817/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
3680 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10902 | Assistant Engineer | Junior Engineer | BILL/00914/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
3681 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3682 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Kesiadoba water supply scheme(SVS) under PHE Dte.(SM/10902) | Assistant Engineer | Junior Engineer | BILL/01404/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
3683 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 48
3684 | Bankura Division | Bankura Sadar Sub-Division | Quotation for new service connection at Malindasi, Bankura-II at B.M.S.D under BMD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00330/2023-2024 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
3685 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3686 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3687 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 35 | 48
3688 | Bankura Division | RWS Bankura Sub-Division | New service connection for Raghunathpur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00185/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
3689 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3690 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3691 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
3692 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3693 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3694 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
3695 | Bankura Division | RWS Bankura Sub-Division | New service connection for Banakharanga Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00145/2024-2025 |  | 16/05/2024 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3696 | Bankura Division | RWS Bankura Sub-Division | New service connection for Banakharanga Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00167/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3697 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3698 | Bankura Division | RWS Bankura Sub-Division | New Connection at JL No-86, Mouza-Bankanli, Bliock-Raipur PHE Dte. |  | Junior Engineer | BILL/00627/2023-2024 | FHTC/11 | 10/11/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3699 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3700 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
3701 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Barakharanga Village (SM/11009), (2) Mini Piped Water Supply Scheme for Khejurbedia Village (SM/11016), (3) Mini Piped Water Supply Scheme for Khalpara Village (SM/11015), (4) Mini Piped Water Supply Scheme for Lachhipur Village (SM/11017) and (5) Mini Piped Water Supply Scheme for Bera Village (SM/13266) |  | Junior Engineer | ORD/001993/2024-2025 | 193\KSD | 10/03/2025 | 10 | SANDHYA DEY | 0.75 | 0 | 90
3702 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3703 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Jiorda | Assistant Engineer | Junior Engineer | BILL/01027/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
3704 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3705 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
3706 | Bankura Division | Khatra Sub-Division | New service connection for Memouli Mini water supply scheme under Bankura Division PHE DTE |  | Junior Engineer | BILL/00132/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
3707 | Bankura Division | Khatra Sub-Division | New Service Connection at Memouli, Machatora,Block-Simlapal, PHE Dte. |  | Junior Engineer | BILL/00319/2023-2024 | FHTC/04 | 29/04/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
3708 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3709 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3710 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
3711 | Bankura Division | Brishnupur Sub-Division | New Connection at Gopdanga, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00313/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
3712 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3713 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3714 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
3715 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 14 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002203/2024-2025 | 581\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.11 | 0 | 0
3716 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
3717 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 10 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Bishnupur Block & 07 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002197/2024-2025 | 578\VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 2.56 | 0 | 0
3718 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-20, Mouza-Rautkhana, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00279/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
3719 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
3720 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
3721 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
3722 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 158.88 | 55
3723 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Binod Nagar Piped Water Supply Scheme (SM/18340), 2 nos. of Goala Danga Piped Water Supply Scheme (SM/14001) & 2 nos. of Kushadwip Piped Water Supply Scheme (SM/15266) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001889/2024-2025 | 567/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
3724 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000095/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 34.99 | 0 | 0
3725 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Binod Nagar water supply scheme(T/W-II) at Patrasayer block under BMD PHE Dte.(SM/18340) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01235/2024-2025 | BP-2024-25-379 | 13/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
3726 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Binod Nagar (T/W-I) water supplyb scheme at Patrasayer Block under BMD PHE Dte.(SM/18340) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01340/2024-2025 | BP-2024-25-392 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.27 | 0 | 0
3727 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Binod Nagar Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000024/2025-2026 | 235/BMD | 14/05/2025 | 90 | AMITAVA CHAKRABORTY | 11.65 | 0 | 0
3728 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Hare Krishnapur (Part--A ), Total House Hold -160 |  | Junior Engineer | ORD/000233/2020-2021 | 2044/BQA | 29/12/2020 | 30 | GOUTAM GHOSH | 11.77 | 0 | 0
3729 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :01 , Hare Krishnapur (Part-- B), Total House Hold -101 |  | Junior Engineer | ORD/000235/2020-2021 | 2045/BQA | 29/12/2020 | 30 | GOURANGA NANDI | 7.3 | 0 | 0
3730 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Dadimukha , Total House Hold -383 |  | Junior Engineer | ORD/000236/2020-2021 | 2046/BQA | 29/12/2020 | 30 | SUBHENDU SEKHAR GORAI | 27.67 | 0 | 0
3731 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 (Gopbandh ), Total House Hold -155 |  | Junior Engineer | ORD/000238/2020-2021 | 2047/BQA | 29/12/2020 | 30 | DAUD ALI KHAN | 11.05 | 0 | 0
3732 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Bankuradanga , Purusattam pur(PART-A) ,), Total House Hold -170 |  | Junior Engineer | ORD/000239/2020-2021 | 2048/BQA | 29/12/2020 | 30 | GOUTAM GHOSH | 12.28 | 0 | 0
3733 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Purusattam pur(PART-B) , Bhairb pur ), Total House Hold -108 |  | Junior Engineer | ORD/000240/2020-2021 | 2049/BQA | 29/12/2020 | 30 | GOURANGA NANDI | 7.77 | 0 | 0
3734 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ( Belut ), Total House Hold -226 |  | Junior Engineer | ORD/000242/2020-2021 | 2050/BQA | 29/12/2020 | 30 | SUBHENDU SEKHAR GORAI | 16.3 | 0 | 0
3735 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simul Kundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) |  | Junior Engineer | ORD/000377/2020-2021 | 28/KSD | 14/01/2021 | 15 | SRIKANTA MONDAL | 4.99 | 9.73 | 0
3736 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Belut, Total House Hold - 65 nos. |  | Junior Engineer | ORD/000408/2021-2022 | 08/ BSD | 07/01/2022 | 10 | SUBHENDU SEKHAR GORAI | 3.65 | 0 | 0
3737 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 1.82 | 0
3738 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Buriam (112) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  | Junior Engineer | VCH/001387/2021-2022 | FHTC/24 | 24/09/2021 | 0 | SUBHADIP KOLEY | 2.47 | 0 | 0
3739 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA ( |  | Junior Engineer | VCH/001419/2020-2021 |  | 01/03/2021 | 0 | DAUD ALI KHAN | 10.16 | 0 | 0
3740 | Bankura Division | Bankura Sadar Sub-Division | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Dadimukha , Total House Hold -383 ( MB No - 3815)" |  | Junior Engineer | VCH/001432/2020-2021 |  | 01/03/2021 | 0 | SUBHENDU SEKHAR GORAI | 24.53 | 0 | 0
3741 | Bankura Division | Bankura Sadar Sub-Division | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ( Belut ), Total House Hold -226 ( MB No - 3815)" |  | Junior Engineer | VCH/001433/2020-2021 |  | 01/03/2021 | 0 | SUBHENDU SEKHAR GORAI | 14.34 | 0 | 0
3742 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Purusattam pur(PART-B) , Bhairb pur ), Total House Hold -108 |  | Junior Engineer | VCH/001574/2020-2021 |  | 15/03/2021 | 0 | GOURANGA NANDI | 6.77 | 0 | 0
3743 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Hare Krishnapur (Part--A ), Total House Hold -160 |  | Junior Engineer | VCH/001575/2020-2021 |  | 15/03/2021 | 0 | GOUTAM GHOSH | 10.56 | 0 | 0
3744 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 03 nos. i.e. Abantika- 88 , Belthya- 89 & Deuli- 91, Total House Hold - 733 |  | Junior Engineer | VCH/002416/2021-2022 | FHTC/17 | 17/02/2022 | 0 | S B ASSOCIATES | 41.78 | 0 | 0
3745 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No. 13) |  | Junior Engineer | VCH/002432/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 4 | 0 | 0
3746 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Birbhandh (183) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) |  | Junior Engineer | VCH/002436/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 3.56 | 0 | 0
3747 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 nos ( Radhaballavpur, Rampur) Total House Hold- 140 |  | Junior Engineer | VCH/002440/2021-2022 | FHTC/17 | 17/02/2022 | 0 | RUFIKUL MONDAL | 8.34 | 0 | 0
3748 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- Bhabanipur, Upargara ( Part ) Total House Hold- 128 |  | Junior Engineer | VCH/002487/2021-2022 | FHTC/1 | 01/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 3.33 | 0 | 0
3749 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
3750 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 03 (Darpanagar, Urama & Pathrabid,, Total House Hold - 464 |  | Junior Engineer | ORD/000039/2020-2021 | 641/BQA | 10/02/2021 | 30 | PRINCE INDUTRIES (INDIA) | 43.55 | 79.28 | 0
3751 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 07 ( Kapista, Domnageria, Muradihi, Pachirdanga, Bhola, Kantakuli & Jagatraydihi), Total House Hold - 454 |  | Junior Engineer | ORD/000040/2020-2021 | 642/BQA | 10/02/2021 | 30 | PRINCE INDUTRIES (INDIA) | 43.08 | 0 | 0
3752 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 30 | NAYAN BARDHAN | 14.75 | 23.37 | 0
3753 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line with in Pachirdang Village to increse pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  | Junior Engineer | ORD/000441/2021-2022 | 509/BQA | 10/03/2022 | 30 | M/S BANERJEE & BANERJEE | 14.41 | 0 | 0
3754 | Bankura Division | Bankura Sadar Sub-Division | Laying balance HDPE Pipe Line with in Pachirdang Village to increase pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000512/2022-2023 | 59/BSD | 24/01/2023 | 21 | M/S BANERJEE & BANERJEE | 0.96 | 0 | 0
3755 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 0.11 | 0
3756 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Kanchanpur(PART) ,Kalapani & Nirshce), Total House Hold -476 |  | Junior Engineer | VCH/002801/2021-2022 | FHTC/5 | 05/03/2022 | 0 | ASOKE BHATTACHARYYA | 2.57 | 0 | 0
3757 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Damodarpur), Total House Hold -226 ( Sl .No.- 7) |  | Junior Engineer | VCH/002802/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SARKAR CONSTRUCTION | 1.49 | 0 | 0
3758 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rajadali (156), Sibarampur (157), Loadihi (158), Satsol (160), Sarga (161), Jhanti Pahari (162) & Sunrigara (163) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 07 Nos. Total Household - 149 Nos." | Assistant Engineer | Junior Engineer | ORD/000043/2021-2022 | 1790/BQA | 09/07/2021 | 30 | ROY CHOWDHURY ENTERPRISE | 9.53 | 0 | 0
3759 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kumorebahal (159) & Dhabani (180) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household - 138 Nos. | Assistant Engineer | Junior Engineer | ORD/000044/2021-2022 | 1791/BQA | 09/07/2021 | 30 | D. S. ENTERPRISE | 10.08 | 0 | 0
3760 | Bankura Division | Khatra Sub-Division | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Susne (178) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household - 154 Nos." | Assistant Engineer | Junior Engineer | ORD/000045/2021-2022 | 1792/BQA | 09/07/2021 | 30 | TAPAN KUMAR MANDAL | 11.84 | 0 | 0
3761 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Rajadali (156) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 205/KSD | 03/06/2022 | 20 | SUBHENDU BANERJEE | 4.64 | 0 | 0
3762 | Bankura Division | Khatra Sub-Division | Laying HDPE Pipe Line from Kendboni to Lapuria Village & Garakusum village to increase presure in Lapuria & Garakusum mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (ZONE-P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2022-2023 | 472/BSD | 06/06/2022 | 15 | ASHIS KUMAR SAMANTA | 4.95 | 4.93 | 0
3763 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamberia (179) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household - 160 Nos. | Assistant Engineer | Junior Engineer | ORD/000159/2021-2022 | 2829/BQA | 16/11/2021 | 30 | TAPAS GHOSH | 10.96 | 0.04 | 0
3764 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 140 out of 921 | Assistant Engineer | Junior Engineer | ORD/000414/2020-2021 | 869/BQA | 25/02/2021 | 30 | TAPAN KUMAR MANDAL | 10.76 | 11.46 | 0
3765 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhabani (180) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 27) | Assistant Engineer | Junior Engineer | ORD/000494/2021-2022 | 88/KSD | 09/03/2022 | 7 | ASOKE KUMAR SAHU | 1.01 | 0.93 | 0
3766 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (179), Dhabani (180), Jalhari (181) & Harangara (185) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000511/2020-2021 | 309/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.3 | 0 | 0
3767 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline from Nadupara Primary School to Nadupara ICDS Centre to increase pressure in Nadupara (177) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000616/2021-2022 | 94/KSD | 10/03/2022 | 10 | ASOKE KUMAR SAHU | 1.65 | 1.62 | 0
3768 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Manora (52) & Chakadoba (58) mouza under Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000690/2021-2022 | 26/KSD | 16/02/2022 | 7 | PRADIP CHAKRABORTY | 1.76 | 0 | 0
3769 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Itamara (60), Jambeda (64) & Domohani (154) mouza under Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block-Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000691/2021-2022 | 28/KSD | 16/02/2022 | 10 | PRADIP CHAKRABORTY | 3.43 | 0 | 45
3770 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- A (Bhuakana), Zone- E (Naria), Zone-Q (Jambedia), Zone-CE (Ashatara), Zone- Malian & Zone- G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 37/KSD | 13/03/2023 | 706 | TAPAS DEY | 0.71 | 0.71 | 90
3771 | Bankura Division | Khatra Sub-Division | Household survey in Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (179), Dhabani (180), Jalhari (181) & Harangara (185) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) | Assistant Engineer | Junior Engineer | VCH/001034/2021-2022 |  | 16/09/2021 | 0 | TAPAS DEY | 0.04 | 0 | 0
3772 | Bankura Division | Khatra Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
3773 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
3774 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0
3775 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) | Assistant Engineer | Junior Engineer | ORD/000213/2021-2022 | 3049/BQA | 01/12/2021 | 30 | M/S K.B.CONSTRUCTION | 69.82 | 54.19 | 0
3776 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2021-2022 | 478/BQA | 04/03/2022 | 0 | Resource Division | 6.73 | 0 | 0
3777 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) | Assistant Engineer | Junior Engineer | VCH/001453/2022-2023 | FHTC/06 | 06/12/2022 | 0 | M/S K.B.CONSTRUCTION | 15.31 | 0 | 0
3778 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 07 (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyaldanga, Bagdiha) Total House Hold - 1131 |  | Junior Engineer | ORD/000028/2021-2022 | 1797/BQA | 09/07/2021 | 30 | SIB SANKAR CHOWDHURY | 62.14 | 15.06 | 10
3779 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 |  | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 28.91 | 0 | 95
3780 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Phaspa mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000170/2022-2023 | 339/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 3.71 | 0 | 80
3781 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Namo Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000171/2022-2023 | 342/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 4.79 | 0 | 85
3782 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction extra concrete at Pahar Ghata mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte |  | Junior Engineer | ORD/000571/2021-2022 | 169/BSD | 16/02/2022 | 15 | SIB SANKAR CHOWDHURY | 1.83 | 1.79 | 10
3783 | Bankura Division | Bankura Sadar Sub-Division | Dismantaling & Recnstruction Concrete at Bagdiha & Paharghata 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna - Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000572/2021-2022 | 1044/BSD | 14/12/2021 | 15 | SIB SANKAR CHOWDHURY | 4.82 | 4.79 | 5
3784 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Paharghata, Bagdiha, Hapania mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000573/2021-2022 | 1045/BSD | 14/12/2021 | 15 | SIB SANKAR CHOWDHURY | 4.96 | 4.96 | 10
3785 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Paharghata, Hapania mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000574/2021-2022 | 1046/BSD | 14/12/2021 | 15 | SIB SANKAR CHOWDHURY | 5 | 4.99 | 40
3786 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Metyla mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone-D) under Chhatna- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000575/2021-2022 | 168/BSD | 16/02/2022 | 15 | SIB SANKAR CHOWDHURY | 5 | 4.78 | 10
3787 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Goyal Danga mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone-D) under Chhatna- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000576/2021-2022 | 181/BSD | 18/02/2022 | 15 | SIB SANKAR CHOWDHURY | 4.91 | 0 | 0
3788 | Bankura Division | Bankura Sadar Sub-Division | Recnstruction Concrete at Pahar Ghata mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000578/2021-2022 | 1043/BSD | 14/12/2021 | 15 | SIB SANKAR CHOWDHURY | 4.95 | 4.94 | 10
3789 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyaldanga, Bagdiha) of HAPANIA (Zone - D) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) |  | Junior Engineer | VCH/002386/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 40 | 0 | 0
3790 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | ORD/000236/2021-2022 | 943/BSD | 04/10/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.84 | 0 | 0
3791 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | ORD/000237/2021-2022 | 944/BSD | 04/10/2021 | 15 | GOPAL CHANDRA CHOUDHURY | 4.82 | 0 | 0
3792 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 |  | Junior Engineer | ORD/000457/2020-2021 | 136/SE/PIU-BANKURA | 24/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 74.74 | 0 | 0
3793 | Bankura Division | Bankura Sadar Sub-Division | Connection of bhagabunh village from existing pipe line under Bankura - I - II & Barjora block water supply (BRGF ph - I project) Chaturdihi ( OHR) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. M.B. No.3770 |  | Junior Engineer | VCH/000469/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ZAKIR HOSSAIN MONDAL | 3.17 | 0 | 0
3794 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jagannathpur (110), Nimdiha (112) & Pirrabakra (113) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001449/2021-2022 | FHTC/23 | 23/11/2021 | 0 | GOUTAM BHATTACHRYYA | 16.14 | 0 | 0
3795 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Junbedia (part) mouzs for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horialgora (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , |  | Junior Engineer | VCH/001578/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PARTHA PRATIM CHATAIT | 4.61 | 0 | 0
3796 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipeline at school danga Barjora of Barjora water supply scheme left out mouzas of Barjora block under BRGF PH - I within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Sl no - 11 |  | Junior Engineer | VCH/001861/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ZAKIR HOSSAIN MONDAL | 4.76 | 0 | 0
3797 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horialgora (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , Junbedia part |  | Junior Engineer | VCH/001579/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PARTHA PRATIM CHATAIT | 12.26 | 0 | 0
3798 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 |  | Junior Engineer | VCH/001750/2021-2022 | FHTC/23 | 23/11/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 74.71 | 0 | 0
3799 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban No. of Mouza :- 01 nos Asurabad (Part), Total House Hold- 140 |  | Junior Engineer | VCH/001862/2021-2022 | FHTC/23 | 23/11/2021 | 0 | PARESH CHANDRA LAYEK | 9.4 | 0 | 0
3800 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 3,( Kalipur, Parulia(Part), Biskodar,) Total House Hold - 437 |  | Junior Engineer | ORD/000055/2020-2021 | 462/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 36.36 | 25.13 | 20
3801 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108) Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000076/2020-2021 | 482/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 16.61 | 6.17 | 0
3802 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyambazar (109) Banbedia (111) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000077/2020-2021 | 483/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 20.37 | 35.91 | 0
3803 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAGDALLA (Zone - S) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla. No.of Mouza :- 04 (Jagdalla, Dadhimukha, Jamboni, & Rasunkur) Total House Hold - 1185 |  | Junior Engineer | ORD/000192/2020-2021 | 208/BQA | 19/01/2021 | 1898 | M/S TARUN KUMAR PATRA | 80.17 | 0 | 0
3804 | Bankura Division | Bankura Sadar Sub-Division | Laying Auxilary HDPE Pipe Line from Node 125 to Node 146 to increse pressure in Tentladanga & Rasunkur mouzas & Node 40 to Node 51 to increse pressure Jagdalla Gorabari Village for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone- S) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  | Junior Engineer | ORD/000275/2022-2023 | 09/BQA | 03/01/2023 | 45 | M/S TARUN KUMAR PATRA | 15.9 | 0 | 100
3805 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
3806 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 3,( Kalipur, Parulia(Part), Biskodar,) Total House Hold - 437 |  | Junior Engineer | ORD/000055/2020-2021 | 462/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 36.36 | 20.7 | 20
3807 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part), Total House Hold - 75 (Sl No of Work- 08) |  | Junior Engineer | ORD/000139/2020-2021 | 100/ BSD | 12/02/2021 | 20 | SANDHYA DEY | 4.75 | 3.99 | 0
3808 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 3 ( Nidya, Papurdihi & Beharadihi), Total House Hold - 467 |  | Junior Engineer | ORD/000187/2020-2021 | 2128/BQA | 31/12/2020 | 1917 | M/S TARUN KUMAR PATRA | 42.43 | 0 | 0
3809 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 5 (Dhaboagram, Tantkanali, Nawdi, Katgoria & Dupsora), Total House Hold - 453 |  | Junior Engineer | ORD/000188/2020-2021 | 2129/BQA | 31/12/2020 | 1917 | M/S TARUN KUMAR PATRA | 41.78 | 19.16 | 0
3810 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-C) , Total House Hold -175 |  | Junior Engineer | ORD/000404/2020-2021 | 862/BQA | 25/02/2021 | 30 | DAUD ALI KHAN | 15.18 | 27.18 | 0
3811 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Kendsayer to Harekrishnapur to Cover Harekrishnapur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000442/2021-2022 | 510/BQA | 10/03/2022 | 30 | TAPAS KUMAR HAZRA | 14.14 | 0 | 0
3812 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
3813 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangamati (141) & Masanjhar (142) mouzas by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000133/2020-2021 | 190/BQA | 18/01/2021 | 30 | M/S TARUN KUMAR PATRA | 35.41 | 34.55 | 30
3814 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 02 ,( Bhairabdanga, Radhakantapur), Total House Hold -463 |  | Junior Engineer | ORD/000268/2020-2021 | 2067/BQA | 29/12/2020 | 30 | SIB SANKAR CHOWDHURY | 42.9 | 0 | 0
3815 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Bandarkoda, Barkura , Kantabesa), Total House Hold -433 |  | Junior Engineer | ORD/000269/2020-2021 | 2068/BQA | 29/12/2020 | 30 | SIB SANKAR CHOWDHURY | 40.25 | 0 | 0
3816 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 01 ( Nityanandapur), Total House Hold -156 |  | Junior Engineer | ORD/000270/2020-2021 | 2069/BQA | 29/12/2020 | 30 | I.R.CONSTRUCTION | 14.44 | 0 | 0
3817 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . Name of mouza -Bandarkoda |  | Junior Engineer | ORD/000350/2021-2022 | 677/ BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 4.37 | 0 | 0
3818 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 30 | SOUMITRA BOSE | 23.15 | 11.13 | 0
3819 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Barkura mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000518/2021-2022 | 236/BSD | 15/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.58 | 4.58 | 0
3820 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Bandarkonda mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000519/2021-2022 | 238/BSD | 15/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.99 | 4.99 | 0
3821 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Sagrakata mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000524/2021-2022 | 225/BSD | 11/03/2022 | 10 | SIB SANKAR CHOWDHURY | 4.63 | 0 | 0
3822 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Maliara (Zone - A). No.of Mouza :- 01, Kuldiha, Total House Hold -233 |  | Junior Engineer | VCH/001150/2021-2022 | FHTC/23 | 23/07/2021 | 0 | TAPAS PAL | 16.99 | 0 | 0
3823 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Roybandh, Bankati mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002300/2021-2022 | FHTC/04 | 04/01/2022 | 0 | PRANABANANDA TEWARI | 4.32 | 0 | 0
3824 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
3825 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Joytunga to Chandan pur village to increase pressure at Chandrapur village and installation of valve chambers at different location of retrofitting works for crease 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saulia zone - G under Bankura - l & ll & Barjora block Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. sl no - 11 |  | Junior Engineer | VCH/003103/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.61 | 0 | 0
3826 | Bankura Division | Bankura Sadar Sub-Division | HDPE , GI & MS pipe line to increase pressure at Chandar , Jorshal , Babhor khola , Ladna ,Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joytunga (Zone - H) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora ,Total House Hold -360nos. ( Part-B ) 180 nos. |  | Junior Engineer | ORD/000003/2023-2024 | 774/BQA | 04/04/2023 | 60 | GOUTAM MUKHERJEE | 38.44 | 0 | 100
3827 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipeline to cover Kastora & Singhir mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000149/2022-2023 | 559/BSD | 29/07/2022 | 21 | TAPAN KUMAR MANDAL | 3.37 | 3.37 | 0
3828 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17) |  | Junior Engineer | ORD/000172/2020-2021 | 716/BQA | 19/02/2021 | 30 | UNIVERSAL CONSTRUCTION | 44.07 | 0 | 0
3829 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Bara Bendya & Khemua), Total House Hold -396 (SL.No-18) |  | Junior Engineer | ORD/000174/2020-2021 | 717/BQA | 19/02/2021 | 30 | UNIVERSAL CONSTRUCTION | 44.06 | 40.32 | 0
3830 | Bankura Division | Bankura Sadar Sub-Division | HDPE pipe line from Barabendya Kodolia Chomatha to Khemua to increase pressure for mouza- Khemua of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000244/2021-2022 | 3091/BQA | 13/12/2021 | 30 | UNIVERSAL CONSTRUCTION | 48.55 | 0 | 0
3831 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/001626/2021-2022 | FHTC/29 | 29/10/2021 | 0 | ASOKE KUMAR SAHU | 3.64 | 0 | 0
3832 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/001627/2021-2022 | FHTC/29 | 29/10/2021 | 0 | ASOKE KUMAR SAHU | 3.35 | 0 | 0
3833 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/001628/2021-2022 | FHTC/29 | 29/10/2021 | 0 | ASOKE KUMAR SAHU | 2.98 | 0 | 0
3834 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Kostia mouza of Retrofitting works for creation of 'FHTC (Func tional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000358/2021-2022 | 956/ BSD | 05/10/2021 | 15 | BISWESWAR CONSTRUCTION | 3.26 | 0 | 0
3835 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Bearabendya mouza of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000359/2021-2022 | 957/ BSD | 05/10/2021 | 15 | BISWESWAR CONSTRUCTION | 3.92 | 0 | 0
3836 | Bankura Division | Bankura Sadar Sub-Division | Replacing of damaged MS carrier pipe line of rising main of Joytunga (Zone- H) OHR at Rail way track crossing Chandar village (Bankura to sonamukhi Rail way line) along with allied works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000360/2022-2023 | 533/BSD | 28/07/2022 | 21 | ZAKIR HOSSAIN MONDAL | 3.08 | 0 | 0
3837 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at talanjuri petrol pump to Talanjuri Pry School to Kendrobedia of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14), |  | Junior Engineer | VCH/001615/2021-2022 | FHTC/07 | 07/10/2021 | 0 | SUBHANKAR BANERJEE | 2.77 | 0 | 0
3838 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at talanjuri petrol pump to Talanjuri Pry School of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14), |  | Junior Engineer | VCH/001616/2021-2022 | FHTC/07 | 07/10/2021 | 0 | SUBHANKAR BANERJEE | 4.53 | 0 | 0
3839 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 06 nos, (Akurbad, Banki, Matranga, Pratappur, Balarampur & Teleghra.) Total House Hold - 1209 |  | Junior Engineer | VCH/001617/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
3840 | Bankura Division | Bankura Sadar Sub-Division | Laying distribution system including all type of specials valves street stand post with UPVC pipes for Mejia (ph - ll) Water supply scheme under Bankura sadar Sub - Division of Bankura Disivion PHE Dte. |  | Junior Engineer | VCH/001853/2021-2022 | FHTC/24 | 24/11/2021 | 0 | GOUTAM MUKHERJEE | 0.41 | 0 | 0
3841 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 07 nos, (Talandanga, Upar Narrah, Kherosol, Chhatarkanali, Rampur, Emokundi & Gopinathpur), Total House Hold - 1057. |  | Junior Engineer | VCH/001618/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.3 | 0 | 0
3842 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06 nos, (Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah), Total House Hold - 1056., |  | Junior Engineer | VCH/001619/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
3843 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No. of Mouza :- 09 nos, (Nabagram, Vidyadharpur, Ailtha, Munipur, Bagneja, Upar bandh, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 1209. |  | Junior Engineer | VCH/001620/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
3844 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 06 nos, (Mobarakpur, Chaptara, Sendra, Agra, Adra & Sirsraa.) Total House Hold - 1209 |  | Junior Engineer | VCH/001621/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
3845 | Bankura Division | Bankura Sadar Sub-Division | Survey work Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 06 nos, (Khejurbedia, Upardihi, Radhanagar, Bagrakonda, Moukura & Kulmura.) Total House Hold - 1008. |  | Junior Engineer | VCH/001622/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
3846 | Bankura Division | Bankura Sadar Sub-Division | Survey work of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 07 nos, (Kendboni, Kantaboni, Mamurjuri, Dhansimul, Jarka, Sonamui & Malindasi), Total House Hold - 1213 |  | Junior Engineer | VCH/001623/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
3847 | Bankura Division | Bankura Sadar Sub-Division | Survey work of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03 nos, (Bhangaria, Magra & Sonadaha), Total House Hold - 831. |  | Junior Engineer | VCH/001624/2021-2022 | FHTC/29 | 29/10/2021 | 0 | TAPAS DEY | 0.26 | 0 | 0
3848 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Masanjhar (142) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) |  | Junior Engineer | VCH/001625/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 2.8 | 0 | 0
3849 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No.- 8) |  | Junior Engineer | VCH/001630/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.92 | 0 | 0
3850 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 9) |  | Junior Engineer | VCH/001632/2021-2022 | FHTC/29 | 29/10/2021 | 0 | M/S TARUN KUMAR PATRA | 4.92 | 0 | 0
3851 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
3852 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
3853 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. |  | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
3854 | Bankura Division | Bankura Sadar Sub-Division | works for creation FHTC (Functional House Hold Tap Connection) Jal Swapna & Jal Jeevan Mission Programme of Joytunga zone - H under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- l I, Name of OHR - Joytunga zone - H No.of Mouza :- 02 ( Joytunga, Kostia). Total House Hold -23 sl no - 09 |  | Junior Engineer | VCH/002946/2021-2022 | FHTC/23 | 23/03/2022 | 0 | BISWESWAR CONSTRUCTION | 4.88 | 0 | 0
3855 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Bara Bendya & Khemua), Total House Hold -396 (SL.No-18) |  | Junior Engineer | VCH/003117/2021-2022 |  | 30/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 40.32 | 0 | 0
3856 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mukundapur (114), Khakrakanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000142/2020-2021 | 197/BQA | 18/01/2021 | 30 | APEX ENTERPRISE | 37.4 | 61.36 | 0
3857 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kolaberia (PART- A), Total House Hold -427 |  | Junior Engineer | ORD/000275/2020-2021 | 2074/BQA | 29/12/2020 | 30 | UNIVERSAL CONSTRUCTION | 44.3 | 0 | 0
3858 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 05 , Kolaberia (PART- A ) ,Bandarkhola, Ramharipur, Katapesia, Maitha Gopinathpur ), Total House Hold -426 |  | Junior Engineer | ORD/000276/2020-2021 | 2075/BQA | 29/12/2020 | 30 | UNIVERSAL CONSTRUCTION | 44.26 | 74.02 | 0
3859 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . Name.of Mouza :- Maitha Gopinathpur |  | Junior Engineer | ORD/000349/2021-2022 | 855/ BSD | 18/08/2021 | 15 | BISWESWAR CONSTRUCTION | 4.93 | 0 | 0
3860 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Maitha Gopinathpur mouza mouza of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000375/2021-2022 | 1052/ BSD | 15/12/2021 | 15 | BISWESWAR CONSTRUCTION | 2.33 | 0 | 0
3861 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line from Ayna jore to Mukundra pur Tematha more of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000381/2021-2022 | 1051/ BSD | 15/12/2021 | 15 | BISWESWAR CONSTRUCTION | 4.7 | 0 | 0
3862 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kolaberia (PART- A), Total House Hold -427 |  | Junior Engineer | VCH/001619/2020-2021 |  | 15/03/2021 | 0 | UNIVERSAL CONSTRUCTION | 35.41 | 0 | 0
3863 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 03 nos, (Brindajam, Simulbedia, Dhatala) Total House Hold -384, |  | Junior Engineer | VCH/001855/2021-2022 | FHTC/03 | 03/11/2021 | 0 | GOUTAM BHOWMIK | 7.92 | 0 | 0
3864 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | VCH/002289/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.1 | 0 | 0
3865 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
3866 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SOMSAR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Somsar, No. of Mouza :- 01 no. i.e. (Somsar-02), Total House Hold - 1058 |  | Junior Engineer | VCH/002454/2021-2022 | FHTC/1 | 01/02/2022 | 0 | M/S K.B.CONSTRUCTION | 13.26 | 0 | 0
3867 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 30 | SUMITA UPADHYAY | 13.03 | 0.38 | 0
3868 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 323/KSD | 01/08/2022 | 15 | PRADYUMNA KOLEY | 3.81 | 3.77 | 0
3869 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lachaipur (9), Fetapur (10), Gopalpur (11) & Tilabad (13) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2020-2021 | 173/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 31.06 | 0 | 0
3870 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2020-2021 | 174/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 30.83 | 0 | 0
3871 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Lachaipur (9) & Gopalpur (11) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 20) | Assistant Engineer | Junior Engineer | ORD/000265/2021-2022 | 556/KSD | 29/06/2021 | 10 | DEBAKI RANJAN SARKAR | 4.26 | 0 | 0
3872 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 100 | 0
3873 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000516/2020-2021 | 314/KSD | 29/12/2020 | 61 | D. S. ENTERPRISE | 0.3 | 0 | 100
3874 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 | Assistant Engineer | Junior Engineer | VCH/000204/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SIB SANKAR CHOWDHURY | 85.33 | 0 | 0
3875 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | VCH/002296/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.75 | 0 | 0
3876 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06, Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah (PART), Total House Hold - 528.' | Assistant Engineer | Junior Engineer | VCH/002878/2021-2022 |  | 16/03/2022 | 0 | SWAPAN KUMAR CHANDRA | 9.23 | 0 | 0
3877 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003050/2021-2022 | FHTC/28 | 28/03/2022 | 0 | DEBAKI RANJAN SARKAR | 0.84 | 0 | 0
3878 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Parkul (217), Mashara (218), Goaladanga (219), Chandanpur (261), Beniabaid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2021-2022 | 2503/BQA | 23/09/2021 | 30 | EARTH MOVING (INDIA) | 44.75 | 6.05 | 0
3879 | Bankura Division | Khatra Sub-Division | Laying fitting fixing of HDPE pipe from Ghutgoria to Kulbona Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) | Assistant Engineer | Junior Engineer | ORD/000143/2022-2023 | 563/BSD | 29/07/2022 | 30 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0
3880 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 26) | Assistant Engineer | Junior Engineer | ORD/000529/2020-2021 | 327/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.26 | 0.21 | 0
3881 | Bankura Division | Khatra Sub-Division | Work Order for Laying UPVC pipeline at Chandanpur village to increase pressure in Chandanpur (261) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-IIA (Baragari) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) | Assistant Engineer | Junior Engineer | ORD/000658/2021-2022 | 87/KSD | 09/03/2022 | 10 | BIKASH MANDAL | 3.04 | 3.03 | 0
3882 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure to cover Mashara (218) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - IIA ( Baragari ) of Khatra - Hirbandh - Ranibandh W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission (JJM) and JAL SWAPNA under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000759/2022-2023 | FHTC/01 | 01/08/2022 | 0 | SUBHADIP KOLEY | 4.98 | 0 | 0
3883 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
3884 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
3885 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Parkul (217) & Goaladanga (219) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 14 | Assistant Engineer | Junior Engineer | VCH/002951/2021-2022 | FHTC/23 | 23/03/2022 | 0 | UNITED TRADERS | 2.49 | 0 | 0
3886 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Beniabaid (262) & Kandrahara (263) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 10 part - A sl no -- 10 | Assistant Engineer | Junior Engineer | VCH/002952/2021-2022 | FHTC/23 | 23/03/2022 | 0 | UNITED TRADERS | 4.44 | 0 | 0
3887 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Beniabaid (262) & Kandrahara (263) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 10 part - B sl no - 11 | Assistant Engineer | Junior Engineer | VCH/002953/2021-2022 | FHTC/23 | 23/03/2022 | 0 | UNITED TRADERS | 4.52 | 0 | 0
3888 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 (Junbedia (PART), Total House Hold - 440 | Assistant Engineer | Junior Engineer | ORD/000308/2020-2021 | 1361/BQA | 08/10/2020 | 30 | GOUTAM BHOWMIK | 38.05 | 0 | 100
3889 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 (Junbedia(PART), Total House Hold - 441 | Assistant Engineer | Junior Engineer | ORD/000310/2020-2021 | 1362/BQA | 08/10/2020 | 30 | PARTHA PRATIM CHATAIT | 38.05 | 0 | 100
3890 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Horialgora, No. of Mouza :- 01 nos , Junbedia (Part), Total House Hold - 200 nos. | Assistant Engineer | Junior Engineer | ORD/000321/2021-2022 | 3368/BQA | 31/12/2021 | 30 | M/S SUPRIYA CHATTERJEE | 21.35 | 0 | 100
3891 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Junbedia (Part- B) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000429/2020-2021 | 136/ BSD | 18/02/2021 | 10 | PARTHA PRATIM CHHATAIT | 4.91 | 0 | 100
3892 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Kulpat, Kesia,& Bhedua(Part), Total House Hold - 435 | Assistant Engineer | Junior Engineer | VCH/001382/2020-2021 |  | 01/03/2021 | 0 | PARTHA PRATIM CHATAIT | 30.09 | 0 | 0
3893 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgorai (Zone - o) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , Total House Hold - 870." | Assistant Engineer | Junior Engineer | VCH/001407/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
3894 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Jarisa (89) , mouza by retrofitting zone - ll piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3950) | Assistant Engineer | Junior Engineer | VCH/001541/2020-2021 | FHTC/268 | 05/02/2021 | 0 | GOUTAM BHATTACHRYYA | 35.71 | 0 | 0
3895 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
3896 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 145 |  | Junior Engineer | ORD/000010/2020-2021 | 611/BQA | 10/02/2021 | 30 | SWAPAN KUMAR DE | 9.83 | 4.92 | 0
3897 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 135 |  | Junior Engineer | ORD/000015/2020-2021 | 616/BQA | 10/02/2021 | 30 | MRITYUNJOY HAZRA | 9.84 | 7.08 | 0
3898 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Guniada (1) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000131/2020-2021 | 188/BQA | 18/01/2021 | 30 | DEBAKI RANJAN SARKAR | 27.87 | 7.12 | 90
3899 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 60 out of 921. |  | Junior Engineer | ORD/000150/2020-2021 | 58/VSD | 10/02/2021 | 21 | AJIT KUMAR DUTTA | 4.82 | 7.27 | 0
3900 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506" |  | Junior Engineer | ORD/000324/2020-2021 | 1373/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 42.54 | 0 | 100
3901 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Kanchanpur (PART) Total House Hold - 507" |  | Junior Engineer | ORD/000326/2020-2021 | 1374/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 42.58 | 0 | 0
3902 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.97 | 0
3903 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Purandarpur & Kanchanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/000129/2021-2022 |  | 21/04/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.35 | 0 | 0
3904 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/000135/2021-2022 |  | 21/04/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0
3905 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 1, Shyampur (PART) Total House Hold - 75. , (1) Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1)under Saltora- Chhatna W/S Scheme (BRGF ph - I project) |  | Junior Engineer | VCH/000245/2021-2022 | FHTC/06 | 23/04/2021 | 0 | RUFIKUL MONDAL | 3.92 | 0 | 0
3906 | Bankura Division | Bankura Sadar Sub-Division | Laying extra new UPVC pipeline to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I , II & Barjora Block W/S Scheme ( BRGF Ph-I project) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000844/2021-2022 |  | 01/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.19 | 0 | 0
3907 | Bankura Division | Bankura Sadar Sub-Division | Laying of M.S pipeline for crossing bridge to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura I II and Barjora Block ( BRGF ph -I) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000845/2021-2022 |  | 01/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 1.98 | 0 | 0
3908 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR - Arjunpur no .of Mouza :- 05 etc , Total House Hold -1008" |  | Junior Engineer | VCH/001413/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
3909 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR - Arjunpur no .of Mouza :- 05 etc , Total House Hold -1013" |  | Junior Engineer | VCH/001414/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
3910 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506 ( MB No - 3993)" |  | Junior Engineer | VCH/001422/2020-2021 |  | 01/03/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 37.09 | 0 | 0
3911 | Bankura Division | Bankura Sadar Sub-Division | Household survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA, IB, III & IV). Block - Barjora, Name of OHR:- BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) Zone-IA, IB, III & IV, No. of Mouza:- 31 nos. (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara), (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur), (Basudevpur uttar, Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birshinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) & (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), Total House Hold- 902 nos. | Assistant Engineer | Junior Engineer | ORD/000102/2023-2024 | 325/BSD | 06/04/2023 | 60 | TAPAS DEY | 0.3 | 0 | 100
3912 | Bankura Division | Bankura Sadar Sub-Division | Laying fitting fixing of HDPE pipe from Kulbona Village to Tikhargram village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA | Assistant Engineer | Junior Engineer | ORD/000141/2022-2023 | 564/BSD | 29/07/2022 | 30 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0
3913 | Bankura Division | Bankura Sadar Sub-Division | Laying fitting fixing of HDPE pipe from Ghutgoria to Kulbona Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) | Assistant Engineer | Junior Engineer | ORD/000143/2022-2023 | 563/BSD | 29/07/2022 | 30 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0
3914 | Bankura Division | Bankura Sadar Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) | Assistant Engineer | Junior Engineer | ORD/000187/2022-2023 | 347/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.95 | 0 | 0
3915 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection¿ in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 6 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratapur, Sitarampur, Salgara) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase ¿ I) within Barjora Block under Bankura Sadar Sub ¿ Division, PHE Dte. (Zone ¿ IA). Block ¿ Barjora, Name of OHR ¿ BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase ¿ I) (Zone ¿ IA) No. of Mouza :- 06 (Chak Kulbana, Methyali, Nutangram, Pratapur, Sitarampur, Salgara) Total House Hold ¿ 2226 nos. | Assistant Engineer | Junior Engineer | ORD/000258/2021-2022 | 3167/BQA | 17/12/2021 | 60 | GOPAL CHANDRA CHOUDHURY | 134.03 | 133.89 | 0
3916 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) . No.of Mouza :-06 nos, (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara), Total House Hold - 2226 nos. | Assistant Engineer | Junior Engineer | VCH/000248/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.74 | 0 | 0
3917 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) | Assistant Engineer | Junior Engineer | VCH/002389/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 70 | 0 | 0
3918 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 5 nos. i.e. Mathurabihari-28, Ramchandrapur-30, Matukpur-31, Purba Nischintapur-32 & Kuldangar-36, Total House Hold - 828 | Assistant Engineer | Junior Engineer | ORD/000097/2021-2022 | 2505/BQA | 23/09/2021 | 30 | ASHISH KUMAR SAMANTA | 64.21 | 4.77 | 0
3919 | Bankura Division | Brishnupur Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) | Assistant Engineer | Junior Engineer | VCH/000918/2022-2023 | FHTC/21 | 21/11/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.95 | 0 | 0
3920 | Bankura Division | Brishnupur Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-III )Total House Hold - 139.' | Assistant Engineer | Junior Engineer | VCH/000948/2022-2023 | FHTC/16 | 16/11/2022 | 0 | SK. SAHAJAHAN | 1.05 | 0 | 0
3921 | Bankura Division | Brishnupur Sub-Division | Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) | Assistant Engineer | Junior Engineer | VCH/001015/2022-2023 | FHTC/16 | 16/11/2022 | 0 | ASOKE KUMAR SAHU | 3.19 | 0 | 0
3922 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 2, ( (Subarda, Shalchura ) Total House Hold - 496 | Assistant Engineer | Junior Engineer | VCH/001122/2022-2023 | FHTC/16 | 16/11/2022 | 0 | UNIVERSAL CONSTRUCTION | 8.99 | 0 | 0
3923 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | VCH/001275/2022-2023 | FHTC/16 | 16/11/2022 | 0 | PRADYUMNA KOLEY | 0.21 | 0 | 0
3924 | Bankura Division | Brishnupur Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 6) | Assistant Engineer | Junior Engineer | VCH/001278/2022-2023 | FHTC/16 | 16/11/2022 | 0 | GOURANGA CHATTERJEE | 0.08 | 0 | 0
3925 | Bankura Division | Brishnupur Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | VCH/001279/2022-2023 | FHTC/16 | 16/11/2022 | 0 | GOURANGA CHATTERJEE | 0.08 | 0 | 0
3926 | Bankura Division | Brishnupur Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | VCH/001280/2022-2023 | FHTC/16 | 16/11/2022 | 0 | BEAUTY CHATTERJEE | 0.33 | 0 | 0
3927 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC Pipe Line to Cover Jhunka mouza for retrofitting works for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001337/2022-2023 | FHTC/16 | 16/11/2022 | 0 | SUMIT GHOSH | 3.71 | 0 | 0
3928 | Bankura Division | Brishnupur Sub-Division | Supplying Fiting Fixing & Laying 160 mm dia. HDPE Pipe from Parasibona air valve point to firm Gate to cover Bharatpur, Gidhuria & Jaljalibansal for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part- A) (under JJM Programme Fund) | Assistant Engineer | Junior Engineer | VCH/001371/2022-2023 | FHTC/21 | 21/11/2022 | 0 | RAHUL CHATERJEE | 4.76 | 0 | 0
3929 | Bankura Division | Brishnupur Sub-Division | Supplying Fitting Fixing & Laying 160 mm dia. HDPE Pipe from Parasibona air valve point to firm Gate to cover Bharatpur, Gidhuria & Jaljalibansal for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part- B) (under JJM Programme Fund) | Assistant Engineer | Junior Engineer | VCH/001372/2022-2023 | FHTC/21 | 21/11/2022 | 0 | RAHUL CHATERJEE | 3.38 | 0 | 0
3930 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 02 nos, ( Jhunka, Bharatpur (Part) Total House Hold - 437 nos. | Assistant Engineer | Junior Engineer | VCH/001383/2022-2023 | FHTC/16 | 16/11/2022 | 0 | SUMIT GHOSH | 10.71 | 0 | 0
3931 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001384/2022-2023 | FHTC/16 | 16/11/2022 | 0 | APEX ENTERPRISE | 19.67 | 0 | 0
3932 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline to increase pressure in Surulia (87) & Jalneja (88) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001432/2022-2023 | FHTC/15 | 15/12/2022 | 0 | SOURAV SINHA MAHAPATRA | 5.66 | 0 | 0
3933 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Kherkanali No.of Mouza :- 01 nos. ( Kaljuri)Total House Hold -120 nos. | Assistant Engineer | Junior Engineer | VCH/001433/2022-2023 | FHTC/15 | 15/12/2022 | 0 | MOHAN KUMAR ROY | 14.32 | 0 | 0
3934 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Rol, No. of Mouza :- 4 nos. i.e. Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Durgajal-10, Total House Hold - 1240 | Assistant Engineer | Junior Engineer | ORD/000111/2021-2022 | 2688/BQA | 26/10/2021 | 30 | SAMRAT REALPROJECTS PRIVATE LIMITED | 62.97 | 52.4 | 0
3935 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 1.08 | 0 | 0
3936 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000101/2021-2022 | 2498/BQA | 23/09/2021 | 30 | M/S BIPUL BANERJEE | 64.52 | 12.44 | 90
3937 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works at culvert portion from Taldiha village more to Brahamandiha village more [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000134/2022-2023 | 302/KSD | 26/07/2022 | 10 | UTTAM KUMAR SINHAMAHAPATRA | 4.35 | 4.35 | 0
3938 | Bankura Division | Khatra Sub-Division | Work Order for Supplying, laying by UPVC pipe (6 Kg/Sq. Cm. Water Pressure, class III) for distribution network along with ancillary works at village Karbhanga due to Strengthening - Widening of Sarenga Chowrasta More to Goaltore road by PWD (Roads) Dte. under Water supply scheme for Gargaria Zone-B of Sarenga Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Under Jal Swapna & Jal Jeevan Mission Programme Fund) (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000362/2021-2022 | 657/KSD | 17/09/2021 | 15 | UTTAM KUMAR SINHAMAHAPATRA | 4.88 | 0 | 0
3939 | Bankura Division | Khatra Sub-Division | : Work Order for Household survey in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000593/2021-2022 | 796/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.33 | 0 | 0
3940 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna | Assistant Engineer | Junior Engineer | VCH/000455/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.26 | 0 | 0
3941 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 5 nos. i.e. Mathurabihari-28, Ramchandrapur-30, Matukpur-31, Purba Nischintapur-32 & Kuldangar-36, Total House Hold - 828 | Assistant Engineer | Junior Engineer | VCH/002764/2021-2022 | FHTC/5 | 05/03/2022 | 0 | ASHISH KUMAR SAMANTA | 59.29 | 0 | 0
3942 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC pipe line to cover Jiakanali ( 274) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - IIA (Baragari) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. part - B | Assistant Engineer | Junior Engineer | VCH/002766/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU BANERJEE | 3.83 | 0 | 0
3943 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
3944 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mitha-Am (122) & Laladi (155) mouzas by retrofitting Zone- K (Makhnu) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 14 Nos. Total Household:- 2933 Nos. | Assistant Engineer | Junior Engineer | ORD/000391/2021-2022 | 202/BQA | 01/02/2022 | 1157 | M/S TARUN KUMAR PATRA | 158.46 | 89.69 | 90
3945 | Bankura Division | Khatra Sub-Division | Laying 100mm and 150 mm dia DI pipeline at Routara (129) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000471/2022-2023 | 286/BQA | 13/02/2023 | 45 | ASOKE KUMAR SAHU | 2.03 | 1.93 | 20
3946 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mitha-Am (122) & Laladi (155) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone- K (Makhnu) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 19) | Assistant Engineer | Junior Engineer | ORD/000683/2021-2022 | 858/KSD | 31/12/2021 | 1143 | TAPAS DEY | 0.98 | 0 | 70
3947 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2021-2022 | 453/BQA | 03/03/2022 | 0 | Resource Division | 16.1 | 0 | 0
3948 | Bankura Division | Khatra Sub-Division | Household survey in Kama (65), Benkakocha (66) Kulam (67), chalthat (71) Jamperya (117) Maula (118) Mitha -Am (122) & Laladi (155) mouzas retrofitting Zone- K (Makhnu), of improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003067/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TAPAS DEY | 0.54 | 0 | 0
3949 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gargarya (349) and Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 653 Nos. | Assistant Engineer | Junior Engineer | ORD/000203/2021-2022 | 3021/BQA | 29/11/2021 | 30 | TAPAN KUMAR MANDAL | 28.09 | 28.04 | 0
3950 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) | Assistant Engineer | Junior Engineer | ORD/000206/2022-2023 | 1301/BQA | 15/06/2022 | 10 | UTTAM KUMAR SINHAMAHAPATRA | 1.68 | 1.6 | 0
3951 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Nibra (353) & Indabinda (354) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000208/2022-2023 | 1289/BQA | 15/06/2022 | 10 | UTTAM KUMAR SINHAMAHAPATRA | 4.83 | 4.46 | 0
3952 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Gargarya (349) & Parulia (355) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 14) | Assistant Engineer | Junior Engineer | ORD/000216/2022-2023 | 1293/BQA | 15/06/2022 | 10 | TAPAN KUMAR MANDAL | 4.91 | 4.85 | 0
3953 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Gargarya (349) & Parulia (355) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000217/2022-2023 | 1295/BQA | 15/06/2022 | 10 | TAPAN KUMAR MANDAL | 4.97 | 4.89 | 0
3954 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbani (346), Rasunia (347), Jakpur (348), Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 362 Nos. | Assistant Engineer | Junior Engineer | ORD/000387/2021-2022 | 441/BQA | 03/03/2022 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 14.48 | 3.42 | 0
3955 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000588/2021-2022 | 792/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.34 | 0.34 | 0
3956 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbani (346), Rasunia (347), Jakpur (348), Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 362 Nos. | Assistant Engineer | Junior Engineer | VCH/000258/2022-2023 | FHTC/12 | 12/04/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 11.04 | 0 | 0
3957 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 1 no. i.e. Majuria-135 , Total House Hold - 943 | Assistant Engineer | Junior Engineer | ORD/000191/2021-2022 | 2890/BQA | 22/11/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 77.95 | 0 | 0
3958 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 2 nos. i.e. Baramara-149 & kulaijuri-134 , Total House Hold -793 | Assistant Engineer | Junior Engineer | ORD/000193/2021-2022 | 3026/BQA | 29/11/2021 | 30 | UNIVERSAL CONSTRUCTION | 70.43 | 60.62 | 0
3959 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 08 nos. i.e. Dhabani- 136, Chitrang-137,Baliguma-138, Indkuri-139,Taldangra-140,Domberya-141,Majdiha-142 and Hetagara-143 Total house hold - 799 ( Out of 949) | Assistant Engineer | Junior Engineer | ORD/000195/2021-2022 | 3029/BQA | 29/11/2021 | 30 | SUMITA UPADHYAY | 61.96 | 0 | 0
3960 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136), Suritari (139), Kanthalia (140), Gobindasol (141), Bheduasol (142), Muchikata (143), Churku (144) & Syamadihi (145) mouzas by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 18 Nos. Total Household:- 3581 Nos. |  | Junior Engineer | ORD/000316/2021-2022 | 09/BQA | 03/01/2022 | 60 | GOPAL CHANDRA CHOUDHURY | 210.38 | 210.32 | 0
3961 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Bansdiha (130) (Part) & Jhilimili (131) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | ORD/000502/2021-2022 | 738/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.72 | 4.7 | 0
3962 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Jhilimili (131) (Part) & Bhurrudanga (133) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) |  | Junior Engineer | ORD/000503/2021-2022 | 741/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.97 | 4.97 | 0
3963 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kanthalia (140) (Part), Muchikata (143), Churku (144) & Syamadihi (145) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12) |  | Junior Engineer | ORD/000504/2021-2022 | 743/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 3.78 | 3.78 | 0
3964 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Serengda (135), Tilabani (136) & Suritari (139) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) |  | Junior Engineer | ORD/000505/2021-2022 | 746/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.95 | 4.94 | 0
3965 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Suritari (139) (Part) & Kanthalia (140) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000506/2021-2022 | 748/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.89 | 4.88 | 0
3966 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Rudra (38), Mahespur (52), Chirkun Kanali (54) & Budh Khila (60) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  | Junior Engineer | ORD/000507/2021-2022 | 750/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 2.53 | 0 | 0
3967 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Rautara (129) (Part) & Bansdiha (130) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) |  | Junior Engineer | ORD/000508/2021-2022 | 752/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.87 | 4.87 | 0
3968 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Rautara (129) mouza (Part) for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) |  | Junior Engineer | ORD/000509/2021-2022 | 756/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.98 | 4.98 | 0
3969 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Tamakhun (62) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 28) |  | Junior Engineer | ORD/000510/2021-2022 | 758/BQA | 28/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.45 | 0 | 0
3970 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kasakend (134) mouza for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No. 22) |  | Junior Engineer | ORD/000525/2021-2022 | 83/KSD | 09/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.98 | 4.96 | 0
3971 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Kasakend (134) mouza for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No. 23) |  | Junior Engineer | ORD/000526/2021-2022 | 84/KSD | 09/03/2022 | 10 | GOPAL CHANDRA CHOWDHURY | 4.99 | 4.99 | 0
3972 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Chiltore & its adjoining mouzas water supply scheme under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | ORD/000596/2022-2023 | 171/KSD | 17/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.97 | 0.97 | 0
3973 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136), Suritari (139), Kanthalia (140), Gobindasol (141), Bheduasol (142), Muchikata (143), Churku (144) & Syamadihi (145) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  | Junior Engineer | ORD/000684/2021-2022 | 859/KSD | 31/12/2021 | 90 | TAPAS DEY | 1.19 | 0.55 | 0
3974 | Bankura Division | Khatra Sub-Division | UPVC pipe line damaged during construction of drain from the end of Indas Panchayat samity in connection with Jal Jeevan Mission (JJM) of Indas Water Supply scheme under Bishnupur Sub Division PHE Dte of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000820/2022-2023 | 23/VSD | 15/02/2023 | 1 | SONU SINGH | 0.15 | 0.15 | 0
3975 | Bankura Division | Khatra Sub-Division | Extra pipe line for increase pressure Gosaipur, Gobindrapur & Godhardihi retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) of GADARDIHI (Zone- E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. |  | Junior Engineer | ORD/000826/2022-2023 | 216/BSD | 28/02/2023 | 15 | SONU SINGH | 0.97 | 0.97 | 0
3976 | Bankura Division | Khatra Sub-Division | Household survey in Gunpura (126), Khejura (127) Ramgal (128), Rautara (129) Tilabani (136) Suritari (139) Kanthalia (140) Gobindasol (141 ) .......... mouzas reation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Zone - N (Khejuria ) of improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. sl no - 20 |  | Junior Engineer | VCH/000245/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.65 | 0 | 0
3977 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Rautara( 129) mouza part Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 26 |  | Junior Engineer | VCH/000561/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.98 | 0 | 0
3978 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Rautara( 129) mouza part & Bansdiha (130) part Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 22 |  | Junior Engineer | VCH/000562/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.87 | 0 | 0
3979 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Bansdiha (130) part & Jhilimili (131) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 05 |  | Junior Engineer | VCH/000563/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.7 | 0 | 0
3980 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Jhilimili (131) part & Bhurrudanga ( 133) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  | Junior Engineer | VCH/000564/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.97 | 0 | 0
3981 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Sarengda (135) tilabani ( 136) & Suritari ( 139) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 16 |  | Junior Engineer | VCH/000565/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.94 | 0 | 0
3982 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Suritari ( 139) part & Kanthalia (140) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 16 |  | Junior Engineer | VCH/000566/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.88 | 0 | 0
3983 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Kanthalia (140) part Muchikata (143) churku (144) & Syamadihi (145) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 12 |  | Junior Engineer | VCH/000567/2022-2023 |  | 18/07/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 3.78 | 0 | 0
3984 | Bankura Division | Khatra Sub-Division | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000281/2021-2022 | 701/KSD | 29/10/2021 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0
3985 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), Bamundihi (27), Nutandihi (28), Jamkanali (29), Paryasol (30), Benachapra (31), Rajakhas (35), Chamkura (36), Ela (37), Malibana (38) & Patgara (39) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 21 Nos. Total Household:- 2356 Nos. | Assistant Engineer | Junior Engineer | ORD/000303/2021-2022 | 3350/BQA | 30/12/2021 | 1157 | SIB SANKAR CHOWDHURY | 142.27 | 112.02 | 65
3986 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), Bamundihi (27), Nutandihi (28), Jamkanali (29), Paryasol (30), Benachapra (31), Rajakhas (35), Chamkura (36), Ela (37), Malibana (38) & Patgara (39) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000581/2021-2022 | 787/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.79 | 0.67 | 0
3987 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000586/2021-2022 | 790/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.29 | 0 | 0
3988 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | VCH/002306/2021-2022 | FHTC/04 | 04/01/2022 | 0 | GANESH ROY | 3.27 | 0 | 0
3989 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002542/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHADIP KOLEY | 42.16 | 0 | 0
3990 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
3991 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 02 nos. i.e. Chotobankadaha-148 and Bandrya- 150, Total House Hold - 534 ( Out of 703) | Assistant Engineer | Junior Engineer | ORD/000194/2021-2022 | 3028/BQA | 29/11/2021 | 30 | SUBHENDU SEKHAR GORAI | 49.14 | 12.46 | 0
3992 | Bankura Division | Brishnupur Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 nos (Chapatara & Sendra) Total House Hold - 604' | Assistant Engineer | Junior Engineer | VCH/001171/2022-2023 | FHTC/14 | 14/09/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 44.27 | 0 | 0
3993 | Bankura Division | Brishnupur Sub-Division | Supplying, laying, fiting , fixing and jointing of UPVC pipes in connection with Jal Jeevan Mission Programme JJM AND Jal swapna of Andharthol zone V water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. block - bankura - I Name of OHR - Andharthol name of village - Andharthol (school more) | Assistant Engineer | Junior Engineer | VCH/001430/2022-2023 | FHTC/15 | 15/12/2022 | 0 | TARINI CHARAN UPADHYAY | 4.21 | 0 | 0
3994 | Bankura Division | Brishnupur Sub-Division | Supplying, laying, fiting , fixing and jointing of UPVC pipes in connection with Jal Jeevan Mission Programme JJM AND Jal swapna of Andharthol zone V water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. block - bankura - I Name of OHR - Andharthol name of village - Andharthol (school more) | Assistant Engineer | Junior Engineer | VCH/001431/2022-2023 | FHTC/15 | 15/12/2022 | 0 | TARINI CHARAN UPADHYAY | 4.6 | 0 | 0
3995 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline to increase pressure in Surulia (87) & Jalneja (88) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001432/2022-2023 | FHTC/15 | 15/12/2022 | 0 | SOURAV SINHA MAHAPATRA | 5.66 | 0 | 0
3996 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Kherkanali No.of Mouza :- 01 nos. ( Kaljuri)Total House Hold -120 nos. | Assistant Engineer | Junior Engineer | VCH/001433/2022-2023 | FHTC/15 | 15/12/2022 | 0 | MOHAN KUMAR ROY | 14.32 | 0 | 0
3997 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 45 | ALOK ENTERPRISE | 135.35 | 18.5 | 0
3998 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas under Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 7 Nos. Total Household:- 882 Nos. | Assistant Engineer | Junior Engineer | ORD/000196/2021-2022 | 3030/BQA | 29/11/2021 | 30 | EARTH MOVING (INDIA) | 51.76 | 0 | 0
3999 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas under Baricha, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) | Assistant Engineer | Junior Engineer | ORD/000599/2021-2022 | 799/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.29 | 0.24 | 0
4000 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0
4001 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 1 no., (Dahuka), Total House Hold - 277 nos. | Assistant Engineer | Junior Engineer | VCH/001540/2022-2023 | FHTC/19 | 19/01/2023 | 0 | GOURANGA CHATTERJEE | 4.44 | 0 | 0
4002 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipe from Pabra more to Sat-deuli village due to damage by PWD Road for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001541/2022-2023 | FHTC/19 | 19/01/2023 | 0 | LABIR MIRSHAD KHAN | 2.09 | 0 | 0
4003 | Bankura Division | Khatra Sub-Division | Laying extra UPVC Pipe Line to Cover Majit mouza and dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001542/2022-2023 | FHTC/19 | 19/01/2023 | 0 | MD. AFSAR ALI | 3.22 | 0 | 0
4004 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002542/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHADIP KOLEY | 42.16 | 0 | 0
4005 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 | Assistant Engineer | Junior Engineer | VCH/002750/2021-2022 | FHTC/3 | 03/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 2.07 | 0 | 0
4006 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 756 Nos. ( out of 2270 ) ( Part-C ) | Assistant Engineer | Junior Engineer | ORD/000017/2022-2023 | 925/BQA | 21/04/2022 | 1441 | PRINCE INDUTRIES (INDIA) | 35.9 | 18.26 | 72
4007 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2270 nos. ( 757 out of 2270 )( PART- B ) | Assistant Engineer | Junior Engineer | ORD/000035/2022-2023 | 1213/BQA | 01/06/2022 | 1400 | APEX ENTERPRISE | 35.93 | 5.49 | 15
4008 | Bankura Division | Bankura Sadar Sub-Division | Supply Laying of HDPE pipe line for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) in connection with retrofitting and different dia. CIDF Sluice Valve & fittings & Construction of valve chamber at Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. [First Part] | Assistant Engineer | Junior Engineer | ORD/000537/2025-2026 | 2152/BQA | 30/10/2025 | 428 | GOUTAM BHATTACHARYYA | 52.5 | 0 | 0
4009 | Bankura Division | Bankura Sadar Sub-Division | Schedule for supply Laying of HDPE pipe line for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) in connection with retrofitting and different dia. CIDF Sluice Valve & fittings & Construction of valve chamber at Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. [Second Part] | Assistant Engineer | Junior Engineer | ORD/000538/2025-2026 | 2153/BQA | 30/10/2025 | 90 | SABIR ALI KHAN | 52.5 | 0 | 0
4010 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2021-2022 | 95/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.76 | 0.19 | 0
4011 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000038/2021-2022 | 578/BQA | 17/03/2022 | 0 | Resource Division | 13.98 | 0 | 0
4012 | Bankura Division | Brishnupur Sub-Division | Extra Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)'at different school, ICDS, health centre and House Holds in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal zone - A and Kushmuri zone -A (BRGF ph- I) W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2022-2023 | 113/VSD | 19/04/2022 | 21 | MANORANJAN GHOSH | 4.84 | 0 | 0
4013 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000239/2022-2023 | 1303/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.06 | 1.44 | 0
4014 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kushmuri, No. of Mouza :- 09 nos. i.e. Sanpura-57, Jagaldwip-58, Dasarathbati-61, Bhabapur-100, Shyampur-97, Kushmuri - 98, Khayerbani- 99, Khatnagar 101 & Jotbehar - 102, Total House Hold - 2653 | Assistant Engineer | Junior Engineer | ORD/000252/2021-2022 | 3146/BQA | 15/12/2021 | 60 | BANDHAB ENGINEERS CO-OP SOCIETY LTD. | 169.79 | 42.3 | 0
4015 | Bankura Division | Brishnupur Sub-Division | Laying HDPE Pipe Line to increase pressure at teleghra'banki,narrah karmakarpara,sayanipara, adra,paschim ratanpur & sibrampur tantipara for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) & CHERABASTA (ZONE-K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2022-2023 | 609/BSD | 16/08/2022 | 21 | COSMIC CONSTRUCTION | 4.99 | 4.99 | 0
4016 | Bankura Division | Brishnupur Sub-Division | Shifting of pipeline from cross regulator gate of Indas Irrigation at ch 580 near Gechho village of Mangalpur GP and cart bridge at Ch 229 near Maheshpur village of Indas II GP of at Dy 01 of RBMC in connection with Jal Jeevan Mission (JJM) of Kushmuri zone A & Amrul zone B water supply scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2022-2023 | 50/VSD | 10/03/2023 | 15 | GOUTAM GHOSH | 0.97 | 0 | 10
4017 | Bankura Division | Brishnupur Sub-Division | Supplying fabrication, Eraction on suitable RCC foundation, instalation, commissioning and testing with satisfactory completion etc. of iron Elimination plant (IEP) of capasity 100 cum 3 three months trial run at Kushmuri A OHR zone - A site in Indas block under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000282/2022-2023 | FHTC/26 | 26/04/2022 | 0 | M/S TARUN KUMAR PATRA | 45.75 | 0 | 0
4018 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kushmuri, No. of Mouza :- 09 nos. i.e. Sanpura-57, Jagaldwip-58, Dasarathbati-61, Bhabapur-100, Shyampur-97, Kushmuri - 98, Khayerbani- 99, Khatnagar 101 & Jotbehar - 102, Total House Hold - 2653 | Assistant Engineer | Junior Engineer | VCH/002402/2021-2022 | FHTC/21 | 21/02/2022 | 0 | BANDHAB ENGINEERS CO-OP SOCIETY LTD. | 126.5 | 0 | 0
4019 | Bankura Division | Brishnupur Sub-Division | Rectro fitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (ZONE- D ) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 14 nos, (Alunia, Damodarpur, Monipur, Khagra, Sukhabad , Katabaid, Demramol, Beriatha, Janadudumar Rampur Raghumathpur, l, Chhatpathor, Shalroha, Nimra,) Total House Hold - 2711. | Assistant Engineer | Junior Engineer | VCH/002403/2021-2022 | FHTC/21 | 21/02/2022 | 0 | SIB SANKAR CHOWDHURY | 76 | 0 | 0
4020 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000181/2022-2023 | 1284/BQA | 15/06/2022 | 10 | UNITED TRADERS | 4.94 | 4.94 | 0
4021 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 07) | Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 1286/BQA | 15/06/2022 | 10 | EARTH MOVING (INDIA) | 4.95 | 4.95 | 0
4022 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000183/2022-2023 | 1288/BQA | 15/06/2022 | 10 | UNITED TRADERS | 4.94 | 4.94 | 0
4023 | Bankura Division | Khatra Sub-Division | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No. 11) | Assistant Engineer | Junior Engineer | ORD/000185/2022-2023 | 1290/BQA | 15/06/2022 | 10 | EARTH MOVING (INDIA) | 4.83 | 0 | 0
4024 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadamara (9) and Rengurbandh (14) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000204/2021-2022 | 3022/BQA | 29/11/2021 | 30 | D. S. ENTERPRISE | 10.22 | 10.2 | 0
4025 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baranimdiha (13) and Rajabandh (15) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000206/2021-2022 | 3024/BQA | 29/11/2021 | 30 | GANGADHAR MONDAL | 13.39 | 2.3 | 0
4026 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000207/2021-2022 | 3023/BQA | 29/11/2021 | 30 | TAPAN KUMAR MANDAL | 17.57 | 0 | 0
4027 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamara (9) & Rengurbandh (14) mouzas by retrofitting of Parsola, Zone-B of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 30) | Assistant Engineer | Junior Engineer | ORD/000493/2021-2022 | 760/BQA | 28/03/2022 | 10 | D. S. ENTERPRISE | 1.04 | 1.01 | 0
4028 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to to increase pressure at Kadamara (9) & Rengurbandh (14) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 23) | Assistant Engineer | Junior Engineer | ORD/000536/2021-2022 | 753/BQA | 28/03/2022 | 10 | ASOKE KUMAR SAHU | 4.64 | 4.52 | 61
4029 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kadamara (9), Pukhuria (10), Baranimdiha (13), Rengurbandh (14) & Rajabandh (15) mouzas under Parsola, Zone-B to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 19) | Assistant Engineer | Junior Engineer | ORD/000610/2021-2022 | 805/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.26 | 0 | 0
4030 | Bankura Division | Khatra Sub-Division | Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and laying of HDPE pipeline under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2023-2024 | 2667/BQA | 22/09/2023 | 30 | SUBHENDU BANERJEE | 9.69 | 0 | 90
4031 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadamara (9), Pukhuria (10), Baranimdiha (13), Rengurbandh (14) & Rajabandh (15) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000460/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.24 | 0 | 0
4032 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Parsola Zone - B of Simlapal W/S Scheme (BRGF ph - I project) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | VCH/000641/2022-2023 | FHTC/14 | 14/07/2022 | 0 | TAPAN KUMAR MANDAL | 2.11 | 0 | 0
4033 | Bankura Division | Khatra Sub-Division | Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/001451/2022-2023 | FHTC/06 | 06/12/2022 | 0 | EARTH MOVING (INDIA) | 4.75 | 0 | 0
4034 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
4035 | Bankura Division | Khatra Sub-Division | Laying Extra UPVC pipe line to cover sanpura & Kalipahari mouza & Dismantling & reconstruction of concrete of Saburbandh mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jorehira ( zone - B) under Chhatna block of Saltora -chhatna water supply scheme (BRGF ph - l project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002825/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TARINI CHARAN UPADHYAY | 4.27 | 0 | 0
4036 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 04 nos, (Jagannathbati Raghunathpur, Manoharpur & Mohanpur), Total House Hold - 516. | Assistant Engineer | Junior Engineer | VCH/002826/2021-2022 | FHTC/9 | 09/03/2022 | 0 | PARAMESWAR CHOWDHURY | 2.1 | 0 | 0
4037 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. | Assistant Engineer | Junior Engineer | VCH/002827/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAS KUMBHAKAR | 16.02 | 0 | 0
4038 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover (13) and Rajabandh (15) mouzas under onstruction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | VCH/003000/2021-2022 | FHTC/26 | 26/03/2022 | 0 | GANGADHAR MONDAL | 2.01 | 0 | 0
4039 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003084/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TAPAN KUMAR MANDAL | 3.73 | 0 | 0
4040 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Pukhuria (10) mouzas Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Parsola Zone - B under and its adjoining mouza under Simlapal water supply shceme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, | Assistant Engineer | Junior Engineer | VCH/003125/2021-2022 | FHTC/30 | 30/03/2022 | 0 | TAPAN KUMAR MANDAL | 3.98 | 0 | 0
4041 | Bankura Division | Bankura Sadar Sub-Division | Parallel pipe laying of HDPE pipe from Pinguri Village Hunuman mondir to Khatal Bagan Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2022-2023 | 554/BSD | 29/07/2022 | 30 | SUBHADIP KOLEY | 4.94 | 0 | 0
4042 | Bankura Division | Bankura Sadar Sub-Division | Parallel pipe laying of HDPE pipe from Khatal Bagan Village to Kuldiha ground for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000316/2022-2023 | 555/BSD | 29/07/2022 | 30 | SUBHANKAR BANERJEE | 4.94 | 4.93 | 0
4043 | Bankura Division | Bankura Sadar Sub-Division | Parallel pipe laying of HDPE pipe from Kuldiha ground to Kuldiha Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2022-2023 | 556/BSD | 29/07/2022 | 30 | SUBHANKAR BANERJEE | 3.72 | 3.7 | 0
4044 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-02( Napra(Part-B) , Bagulia ), Total House Hold -323 | Assistant Engineer | Junior Engineer | ORD/000462/2020-2021 | 858/BQA | 25/02/2021 | 30 | SARKAR CONSTRUCTION | 27.85 | 0 | 0
4045 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line connection from Hindur danga village Main road to Baguli ,Lohara boni & Molboni village ( under Baguli Mouza ) for Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000464/2022-2023 | 620/BSD | 16/08/2022 | 21 | ASHOKE KUMAR DEY | 4.86 | 0 | 0
4046 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01(Kuldiha ), Total House Hold -233 | Assistant Engineer | Junior Engineer | ORD/000504/2020-2021 | 856/BQA | 25/02/2021 | 30 | TAPAS PAL | 19.63 | 0 | 0
4047 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
4048 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Heyatnagar, No. of Mouza :- 8 nos. i.e. Srikara-31, Padua-11, Adpara Kumrul-12, Sripur-26, Heyatnagar-27, Maheshpur-28, Meral-29 & Chakmeral-30, Total House Hold - 2465 | Assistant Engineer | Junior Engineer | VCH/002445/2021-2022 | FHTC/18 | 18/02/2022 | 0 | JAYANTA KUMAR MONDAL | 140.85 | 0 | 0
4049 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. | Assistant Engineer | Junior Engineer | VCH/002827/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAS KUMBHAKAR | 16.02 | 0 | 0
4050 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe line to cover Barasali, Kukurakur mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002828/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAS KUMBHAKAR | 3.83 | 0 | 0
4051 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002830/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAN KUMAR MANDAL | 13.34 | 0 | 0
4052 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4053 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4054 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4055 | Bankura Division | RWS Bankura Sub-Division | Bandarkonda, Ps- Khatra, Dist- Bankura |  | Junior Engineer | BILL/00165/2023-2024 | FHTC/05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
4056 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4057 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4058 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
4059 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4060 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte Simchaka, Ps-Khatra Dist-Bankura |  | Junior Engineer | BILL/00775/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
4061 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4062 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4063 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 ( PART-B House Hold - 1284) |  | Junior Engineer | ORD/000063/2021-2022 | 2197/BQA | 25/08/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 112.13 | 0 | 0
4064 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | ORD/000064/2021-2022 | 2198/BQA | 25/08/2021 | 30 | M/S TARUN KUMAR PATRA | 112.13 | 0 | 0
4065 | Bankura Division | Bankura Sadar Sub-Division | Interconnection with R/M & Laying of HDPE Pipe Line from Saluni more to Gara to increase water pressure at Gara, Horidi, Metyala mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Nabagram (Zone - K) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000553/2022-2023 | 518/BQA | 14/03/2023 | 45 | M/S PARAMESWAR CHOWDHURY | 9.98 | 0 | 0
4066 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Biradihi (39) & Diktor (40) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2020-2021 | 171/BQA | 18/01/2021 | 30 | PARTHA PRATIM CHATAIT | 26.52 | 0 | 0
4067 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2020-2021 | 172/BQA | 18/02/2021 | 30 | GANESH ROY | 18.65 | 0 | 0
4068 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000173/2021-2022 | 546/KSD | 29/06/2021 | 10 | GANESH ROY | 3.27 | 0 | 0
4069 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000175/2021-2022 | 547/KSD | 29/06/2021 | 10 | GANESH ROY | 2.91 | 0 | 0
4070 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" | Assistant Engineer | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 2.75 | 0
4071 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Biradihi (39), Diktor (40) & Bamni (42) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000514/2020-2021 | 312/KSD | 29/12/2020 | 61 | GANESH ROY | 0.22 | 0 | 0
4072 | Bankura Division | Khatra Sub-Division | supplying laying fitting fixing of HDPE pipe line from near Banogram village Burn Para to Malpara towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000515/2022-2023 | 505/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.98 | 4.98 | 0
4073 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Biradihi (39) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-C (Biradihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 19) | Assistant Engineer | Junior Engineer | ORD/000696/2021-2022 | 80/KSD | 09/03/2022 | 10 | PARTHA PRATIM CHHATAIT | 1.82 | 0 | 0
4074 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001547/2022-2023 | FHTC/06 | 06/01/2023 | 0 | GANESH ROY | 6.02 | 0 | 0
4075 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 | Assistant Engineer | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
4076 | Bankura Division | Khatra Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0
4077 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
4078 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Diktor ( 40) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - C (biradihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - A | Assistant Engineer | Junior Engineer | VCH/003006/2021-2022 | FHTC/26 | 26/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.72 | 0 | 0
4079 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Diktor ( 40) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - C (biradihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B | Assistant Engineer | Junior Engineer | VCH/003007/2021-2022 | FHTC/26 | 26/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 2.82 | 0 | 0
4080 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover chholagara ( 96 ) & Dhadanga (97) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - O (Madandihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B | Assistant Engineer | Junior Engineer | VCH/003008/2021-2022 | FHTC/26 | 26/03/2022 | 0 | TAPAS GHOSH | 4.97 | 0 | 0
4081 | Bankura Division | Khatra Sub-Division | "laying & repairing of UPVC pipe line (damaged due to widening - srenghening of Ranibandh to Barikul road ) at Haludkanali (102 ) mouzas of retrofitting Zone - P (Nachna) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, Jal Jeevan Mission (JJM) and JAL SWAPNA programme fund " | Assistant Engineer | Junior Engineer | VCH/003009/2021-2022 | FHTC/26 | 26/03/2022 | 0 | PRADYUMNA KOLEY | 0.61 | 0 | 0
4082 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4083 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Uttarkamalpur Sonardanga | Assistant Engineer | Junior Engineer | BILL/00524/2022-2023 |  | 13/02/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4084 | Bankura Division | RWS Bankura Sub-Division | Ailakandi, Dakshinkamalpur Sonardanga | Assistant Engineer | Junior Engineer | BILL/00588/2022-2023 |  | 27/02/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4085 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10994. | Assistant Engineer | Junior Engineer | BILL/00765/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4086 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4087 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50.12 | 48
4088 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Balarampur" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00068/2024-2025 |  | 26/04/2024 | 0 | JHANTIPAHARI CCC | 0.12 | 0 | 0
4089 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR KARRASOL VILLAGE (Balarampur) HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00127/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | JHANTIPAHARI CCC | 0.12 | 0 | 0
4090 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4091 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4092 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30.5 | 48
4093 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Hazrachitra" Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00073/2024-2025 |  | 26/04/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
4094 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR TENTUL BERIA VILLAGE (Hazrachitra) HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00126/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
4095 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4096 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10914 | Assistant Engineer | Junior Engineer | BILL/00907/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
4097 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4098 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Hazrachitra water supply scheme(SVS) under BMD PHE Dte.(SM/10914) | Assistant Engineer | Junior Engineer | BILL/01457/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
4099 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 48
4100 | Bankura Division | Bankura Sadar Sub-Division | Quotation of WBSEDCL for the scheme of SM /10927 | Assistant Engineer | Junior Engineer | BILL/00852/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
4101 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 48
4102 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43.5 | 48
4103 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Ledapukur c/o sudip saha, Ledapukur, Ranibandh |  | Junior Engineer | BILL/00051/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
4104 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4105 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4106 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
4107 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4108 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4109 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
4110 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4111 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4112 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
4113 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4114 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4115 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
4116 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4117 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4118 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
4119 | Bankura Division | RWS Bankura Sub-Division | New Connection at Phuljhore,Ranibandh |  | Junior Engineer | BILL/00324/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
4120 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4121 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4122 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4123 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4124 | Bankura Division | RWS Bankura Sub-Division | New Connection at Tilaboni, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00431/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4125 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4126 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
4127 | Bankura Division | RWS Bankura Sub-Division | New Connection at Bhaluka, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00444/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4128 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4129 | Bankura Division | RWS Bankura Sub-Division | New Connection at Jiakanali,Taldangra,Pin-722102 PHE Dte. |  | Junior Engineer | BILL/00698/2023-2024 |  | 26/07/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4130 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4131 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4132 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte Bansnala, Ps-Khatra Dist-Bankura |  | Junior Engineer | BILL/00772/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
4133 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4134 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4135 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4136 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4137 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
4138 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4139 | Bankura Division | RWS Bankura Sub-Division | New Connection at Taltala, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00427/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4140 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4141 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
4142 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.88 | 48
4143 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Kankara M.M.P Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00262/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4144 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4145 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4146 | Bankura Division | Brishnupur Sub-Division | QUATATION FOR NEW SERVICE CONNECTION AT KANKARA | Assistant Engineer | Junior Engineer | BILL/01264/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4147 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
4148 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4149 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4150 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Ganlugara Brahmandiha | Assistant Engineer | Junior Engineer | BILL/00517/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4151 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10892. | Assistant Engineer | Junior Engineer | BILL/00762/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4152 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4153 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
4154 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - simdal, lowgram, , Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00265/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4155 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4156 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4157 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION SIMDAL | Assistant Engineer | Junior Engineer | BILL/01262/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4158 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
4159 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4160 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4161 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
4162 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4163 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakundi,Patijanara Gosaijanara |  | Junior Engineer | BILL/01120/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4164 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4165 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
4166 | Bankura Division | Khatra Sub-Division | New service connection for Krishnabati Mini water supply scheme under Bankura Division PHE DTE |  | Junior Engineer | BILL/00117/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
4167 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4168 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4169 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28.5 | 48
4170 | Bankura Division | Khatra Sub-Division | New service connection for Kansachora Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00133/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
4171 | Bankura Division | Khatra Sub-Division | New Connection at Kansachora,Machatora,Block-Simlapal, PHE Dte. |  | Junior Engineer | BILL/00318/2023-2024 | FHTC/04 | 29/04/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
4172 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4173 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4174 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
4175 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Kasachora Village (SM/11066), (2) Mini Piped Water Supply Scheme for Krishnabati Village (SM/11060), (3) Mini Piped Water Supply Scheme for Memouli Village (SM/11061), (4) Mini Piped Water Supply Scheme for Bagnada Village (SM/11059) and (5) Mini Piped Water Supply Scheme for Suknabaid Village (SM/11068) |  | Junior Engineer | ORD/002003/2024-2025 | 203\KSD | 10/03/2025 | 10 | PRADYUMNA KOLEY | 0.75 | 0 | 95
4176 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4177 | Bankura Division | Brishnupur Sub-Division | New connection of Bhabapur, Indus Block PHE Dte | Assistant Engineer | Junior Engineer | BILL/00838/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDUS CCC | 0.12 | 0 | 0
4178 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4179 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
4180 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Angarsol, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00275/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4181 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4182 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4183 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
4184 | Bankura Division | RWS Bankura Sub-Division | New service connection for Ghutia Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00162/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
4185 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4186 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4187 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
4188 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
4189 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - corkola, gopinathpur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00284/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4190 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4191 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4192 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
4193 | Bankura Division | Brishnupur Sub-Division | (site - Bhalukgere, Deshra, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00295/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4194 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4195 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4196 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Bhalukgere | Assistant Engineer | Junior Engineer | BILL/01276/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4197 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 23 | 48
4198 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Khajuri Chalka Bouripara Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00146/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
4199 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Tolchandrakona Purandihi Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00158/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
4200 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Khajuri Chalka Bouripara Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00168/2024-2025 | BP-77/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
4201 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43.59 | 48
4202 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4203 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Choto Kechanda Nayada | Assistant Engineer | Junior Engineer | BILL/01127/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4204 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4205 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
4206 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Nutangram site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00178/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
4207 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4208 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4209 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
4210 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Kumardubi site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00185/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
4211 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4212 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4213 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 41 | 48
4214 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR MATHURABATI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 1189/BQA | 22/05/2023 | 276 | PARTHA PRATIM CHHATAIT | 422.56 | 27.61 | 65
4215 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Mathurabati Piped Water Supply Scheme (SM/12417) & 4 nos. sites of Pathara Piped Water Supply Scheme (SM/14009) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001892/2024-2025 | 570/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
4216 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 6.17 | 0 | 0
4217 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 55.63 | 0 | 0
4218 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for MATHURABATI (JL NO-70,PLOT-2)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00023/2024-2025 | BP-2024-25-102 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
4219 | Bankura Mechanical | Brishnupur Sub-Division | Shifting work of 11KV HT power line at Mathurabati HW site under B.M.D PHE Dte | Assistant Engineer | Junior Engineer | BILL/01098/2024-2025 | BP-2024-25-255 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0
4220 | Bankura Mechanical | Brishnupur Sub-Division | Mathurabati Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01518/2023-2024 | BP-2023-24-117 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
4221 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Mathurabati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 874/BMD | 04/05/2023 | 180 | ABHIJIT MUKHERJEE | 35.79 | 15.18 | 43
4222 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 355.46 | 6
4223 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
4224 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000038/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 42.54 | 0 | 0
4225 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000301/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 14.49 | 0 | 0
4226 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Hetia Piped Water Supply Scheme t/w-II ,hetia gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00140/2024-2025 | BP-2024-25-101 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.72 | 0 | 0
4227 | Bankura Mechanical | Brishnupur Sub-Division | Hatia T/W -I | Assistant Engineer | Junior Engineer | BILL/01506/2023-2024 | BP-2023-24-105 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.02 | 0 | 0
4228 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Hetia Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000070/2025-2026 | 261/BMD | 14/05/2025 | 90 | M/S MANABESH ROY | 11.64 | 0 | 0
4229 | Bankura Division | Bankura Sadar Sub-Division | New Connection at vill-Karamdanga p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02591/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
4230 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
4231 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4232 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Raghudihi, Dubrajpur | Assistant Engineer | Junior Engineer | BILL/00522/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4233 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4234 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
4235 | Bankura Division | Khatra Sub-Division | REVISED ESTIMATE FOR RESTORATION OF NEWLY CONSTRUCTED DAMAGED ROAD - " CHANDRAKONA-GOALTORE-SARENGA-SIMLIGHAT ROAD BETWEEN CHAINAGE 36+410 KM TO 36+678 KM ( RESTORATION OF FLEXIBLE PAVEMENT , CONCRETE PAVEMENT AND PCC SURFACE DRAIN ) FOR LAYING WATER PIPE LINE BY PHE DEPARTMENT UNDER BANKURA HIGHWAY DIVISION , P. W. (ROADS) DIRECTORATE IN THE DISTRICT OF BANKURA AND SIMLAPAL-SARENGA-BAMUNDIAGHAT ROAD BETWEEN CHAINAGE 19+999 KM TO 25.700 KM ( RESTORATION OF CONCRETE BLOCK(PAVER BLOCK) PAVEMENT / CONCRETE PAVEMENT ) FOR LAYING WATER PIPE LINE BY PHE DEPARTMENT UNDER BANKURA HIGHWAY DIVISION , P. W. (ROADS) DIRECTORATE IN THE DISTRICT OF BANKURA | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01345/2024-2025 | BP-443/2024-25 | 11/12/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 92.53 | 0 | 0
4236 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from T01 to Asna under Sarenga Block in the District of Bankura , Vide Package No-Wb-03-239,Road Length-2.92 Km. (For Sub-Surface based Sarenga Piped Water supply scheme) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01641/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.52 | 0 | 0
4237 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline for Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000180/2024-2025 | 1892/BQA | 23/07/2024 | 344 | PRINCE INDUSTRIES (INDIA) | 32.31 | 0 | 85
4238 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
4239 | Bankura Division | Khatra Sub-Division | Laying of DI (K7) pipe and supplying, laying, fitting, fixing, jointing of HDPE (Materials grade PE-100, PN-6) pipes for distribution system along with providing ¿FHTC (Functional House Hold Tap Connection)¿ and Laying Rising Main using D.I - K9 pipes and construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work for Sub Surface water based Sarenga Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000438/2023-2024 | 2272/BQA | 01/08/2023 | 701 | PRINCE INDUTRIES (INDIA) | 640.53 | 381.01 | 84
4240 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Augmentation of Sarenga Piped Water Supply Scheme, Block : Sarenga, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000545/2021-2022 | 02/A/KSD | 06/01/2022 | 31 | INDRANIL DUTTA & ASSOCIATES | 4.07 | 4.02 | 0
4241 | Bankura Division | Khatra Sub-Division | Construction of Boundary wall, Approach road, Land Development with other allied works for Sub Surface water based Sarenga Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000587/2022-2023 | 502/BQA | 13/03/2023 | 569 | UTTAM KUMAR SINHAMAHAPATRA | 14.52 | 0 | 90
4242 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000050/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 235.37 | 0 | 0
4243 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000158/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 24.21 | 0 | 0
4244 | Bankura Mechanical | Khatra Sub-Division | New service connection for OHR site of Sarenga | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00028/2024-2025 | BP-2024-25-38 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0
4245 | Bankura Mechanical | Khatra Sub-Division | New 3 Phase service connection for Sarenga OHR | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00696/2024-2025 | BP-2024-25-187 | 13/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0
4246 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for sub-surface water base Sarenga piped water supply scheme Block-Sarenga Dist -Bankura under Bankura Mechanical Division PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000304/2023-2024 | 1407/BMD | 18/07/2023 | 60 | TAPAN KUMAR SARKAR | 55.92 | 40.62 | 15
4247 | Bankura Division | RWS Bankura Sub-Division | New Connection at Telanbandhi, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00446/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4248 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4249 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for chakadaha village | Assistant Engineer | Junior Engineer | BILL/00046/2024-2025 | FHTC/04 | 29/04/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
4250 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4251 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 16 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/002202/2024-2025 | 580\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.41 | 0 | 0
4252 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4253 | Bankura Division | Brishnupur Sub-Division | New Connection at Shankarpur,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00480/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
4254 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4255 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 39.6 | 48
4256 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Danga Makarandapur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00194/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
4257 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4258 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4259 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
4260 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4261 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4262 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 48
4263 | Bankura Division | Brishnupur Sub-Division | New Connection at Chaulya, Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00310/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
4264 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4265 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4266 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 54 | 48
4267 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4268 | Bankura Division | Brishnupur Sub-Division | New service Connection at Karasali,Pachal, Sonamukhi Block PHE Dte | Assistant Engineer | Junior Engineer | BILL/00823/2023-2024 |  | 11/08/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
4269 | Bankura Division | Brishnupur Sub-Division | New service connection at Karasali, Panchal, Sonamukhi Block PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00824/2023-2024 | FHTC/09 | 07/09/2023 | 0 | BELIATORE CCC | 0.12 | 0 | 0
4270 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4271 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
4272 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4273 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4274 | Bankura Division | Brishnupur Sub-Division | New service connection at Uttar Amritpara (Bud Bud) Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02610/2023-2024 | FHTC/03 | 12/03/2024 | 0 | BUDBUD CCC | 3.01 | 0 | 0
4275 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4276 | Bankura Division | Brishnupur Sub-Division | New Connection at Aliganj, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00296/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
4277 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4278 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4279 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
4280 | Bankura Division | Bankura Sadar Sub-Division | Nabanda-Joykrishnapur road from 8.00 km ti 8.23 km (instretches) permanent restoration work of road for the purpose of laying of Diga water supply pipe line by PHE department scheme under Bankura Highway Division P.W. roads directorate in the district of Bankura, (1) Ground water based Diga pipe water supply scheme, under Bankura Division, Block -Onda, Dist - Bankura. | Assistant Engineer | Junior Engineer | BILL/02663/2023-2024 | FHTC/03 | 22/03/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 6.48 | 0 | 0
4281 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of of Diga Pipe Water Based Water Supply Scheme , Block-Onda under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000282/2024-2025 | 2152/BQA | 09/08/2024 | 597 | PRINCE INDUSTRIES (INDIA) | 126.63 | 0 | 47
4282 | Bankura Division | Bankura Sadar Sub-Division | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Diga Piped water Supply Scheme of Onda Block, Dist - Bankura under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2023-2024 | 1963/BQA | 18/07/2023 | 985 | PRINCE INDUTRIES (INDIA) | 311.37 | 71.2 | 62
4283 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/10/2012) in connection with Jal Jeevan Mission (JJM) for Proposed of Diga PWSS under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Onda , District -Bankura . Name of Muza - Diga ,Sahapur & Dubrajpur | Assistant Engineer | Junior Engineer | ORD/000638/2022-2023 | 577/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
4284 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Dubrajpur (JL No- 110), Sahapor (JL No- 111) & Diga (JL No- 112) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001087/2021-2022 | 285\BSD | 21/03/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 4 | 4 | 95
4285 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000038/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 9.19 | 0 | 0
4286 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.43 | 0 | 0
4287 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000214/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.43 | 0 | 0
4288 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000304/2023-2024 | 998/BQA | 22/03/2024 | 0 | Resource Division | 6.5 | 0 | 0
4289 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Digha w/s scheme under BMD ,PHE ,Dte. SM/11923 | Assistant Engineer | Junior Engineer | BILL/00524/2024-2025 | BP-2023-24-144 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.24 | 0 | 0
4290 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Name of Work: Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Digha piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 937/BMD | 12/05/2023 | 1080 | KINGKINI TRADERS | 37.12 | 20.06 | 80
4291 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Churamanipur, Bongopalpur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00151/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
4292 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Churamanipur, Bongopalpur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00171/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
4293 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
4294 | Bankura Division | RWS Bankura Sub-Division | New service connection for Birudi Mini water supply scheme under Bankura Division PHE DTE |  | Junior Engineer | BILL/00144/2024-2025 |  | 16/05/2024 | 0 | RAIPUR CCC | 0.12 | 0 | 0
4295 | Bankura Division | RWS Bankura Sub-Division | New service connection for Birudi Mini water supply scheme under Bankura Division PHE DTE |  | Junior Engineer | BILL/00166/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | RAIPUR CCC | 0.12 | 0 | 0
4296 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4297 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4298 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18.06 | 48
4299 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-36, Mouza-Turubandh, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00288/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
4300 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4301 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4302 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 33 | 48
4303 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-7A) (Sl. No. 12) | Assistant Engineer | Junior Engineer | ORD/000632/2022-2023 | 190/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.89 | 2.41 | 0
4304 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001305/2023-2024 | 908/BQA | 14/03/2024 | 90 | GON ASSOCIATES | 20.66 | 15.39 | 80
4305 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 45 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, chlorine room, pump house, CWR and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VII/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001767/2024-2025 | 490/BQA | 25/02/2025 | 243 | BIKASH MANDAL | 8.91 | 0 | 0
4306 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VII/A Water supply scheme (SM/14650), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VII/B Water supply scheme (SM/16936), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VIII/A Water supply scheme (SM/16261), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VIII/B Water supply scheme (SM/15003), 1 no. site of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme (SM/10295), 1 no. site of Augmentation of Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (SM/17123) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001913/2024-2025 | 157\KSD | 07/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 90
4307 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000210/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.13 | 0 | 0
4308 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 1128/BMD | 24/05/2023 | 30 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0
4309 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 100 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, boundary wall and laying distribution pipeline with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- IV/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000221/2025-2026 | 1421/BQA | 26/06/2025 | 90 | ASOKE KUMAR SAHU | 54.02 | 0 | 0
4310 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- IV/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000536/2022-2023 | 432/BQA | 06/03/2023 | 90 | PRADIP CHAKRABORTY | 82.63 | 69.76 | 85
4311 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-4A) (Sl. No. 07) | Assistant Engineer | Junior Engineer (Contractual) | ORD/000628/2022-2023 | 185/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.31 | 2.7 | 0
4312 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000205/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.75 | 0 | 0
4313 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000247/2023-2024 | 1131/BMD | 24/05/2023 | 30 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0
4314 | Bankura Division | Brishnupur Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 10.55 | 100
4315 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 117.29 | 6
4316 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000065/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 57.78 | 0 | 0
4317 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I at Patrabandh W/S scheme | Assistant Engineer | Junior Engineer | BILL/00420/2024-2025 | BP-2024-25-100 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.7 | 0 | 0
4318 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Patrabandh W/S scheme | Assistant Engineer | Junior Engineer | BILL/01346/2024-2025 | BP-2024-25-352 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.18 | 0 | 0
4319 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pratapbandh Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000151/2025-2026 | 446/BMD | 10/06/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 11.84 | 0 | 0
4320 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) and Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000084/2020-2021 | 489/BQA | 05/02/2021 | 30 | MUNMUN UPADHYAY | 48.45 | 23.46 | 70
4321 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (252), Labdapara (265) & Birkham (266) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000327/2020-2021 | 40/KSD | 15/01/2021 | 20 | UTTAM KUMAR SINHAMAHAPATRA | 4.54 | 0 | 20
4322 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Dahala (250) & Bahadurpur (251) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 29) | Assistant Engineer | Junior Engineer | ORD/000532/2020-2021 | 330/KSD | 29/12/2020 | 2 | TAPAS DEY | 0.23 | 0.17 | 0
4323 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Dahala More to Balardihi village to increase pressure in Dahala (250) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001049/2022-2023 | 920/BQA | 19/04/2022 | 30 | TARINI CHARAN UPADHYAY | 10.46 | 10.42 | 90
4324 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash (Zone - B) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur Name of OHR - Gumut No.of Mouza :- 02 nos, Beliara - 66, Dejjat - 66 Total House Hold - 977 | Assistant Engineer | Junior Engineer | VCH/002688/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PARAMESWAR CHOWDHURY | 60.61 | 0 | 0
4325 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 392.97 | 6
4326 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
4327 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 4 nos. sites of Madhab Bati Piped Water Supply Scheme (SM/14522) & 2 nos. sites of Pankhai Piped Water Supply Scheme (SM/12427) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001831/2024-2025 | 547/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.9 | 0 | 0
4328 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2025-2026 | 1624/BQA | 21/07/2025 | 0 | Resource Division | 35.17 | 0 | 0
4329 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000052/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 67.43 | 0 | 0
4330 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Madhabbati Piped Water Supply Scheme t/w-II ,Madhabbati, Kuchiakole of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00130/2024-2025 | BP-2024-25-22 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.49 | 0 | 0
4331 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Madhab bati Piped Water Supply Scheme t/w-III ,Madhabbati,Kuchiakole of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00534/2024-2025 | BP-2024-25-150 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.37 | 0 | 0
4332 | Bankura Mechanical | Brishnupur Sub-Division | Madhab Bati Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01495/2023-2024 | BP-2023-24-99 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.7 | 0 | 0
4333 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Madhabbati Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000063/2025-2026 | 259/BMD | 14/05/2025 | 90 | TAPAN KUMAR SARKAR | 11.97 | 0 | 0
4334 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 368.35 | 6
4335 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
4336 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Ghagara Piped Water Supply Scheme (SM/12426) & 3 nos. sites of Rautkhanda Piped Water Supply Scheme (SM/14524) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001829/2024-2025 | 546/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.75 | 0 | 0
4337 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000077/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 80.11 | 0 | 0
4338 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000299/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 21.32 | 0 | 0
4339 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Basantapur Piped Water Supply Scheme t/w-II ,Basantapur, Routhkhanda of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00135/2024-2025 | BP-2024-25-21 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
4340 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Routhkhanda Piped Water Supply Scheme t/w-III ,Routhkhanda gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01242/2024-2025 | BP-2024-25-314 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.14 | 0 | 0
4341 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Routhkhanda Piped Water Supply Scheme t/w-II ,Routhkhanda gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01243/2024-2025 | BP-2024-25-315 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0
4342 | Bankura Mechanical | Brishnupur Sub-Division | Rautkhanda Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01511/2023-2024 | BP-2023-24-98 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
4343 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Routhkhanda Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 454/BMD | 10/06/2025 | 90 | DEY ENTERPRISE | 13.05 | 0 | 0
4344 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 200.4 | 6
4345 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000082/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 83.89 | 0 | 0
4346 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Karakberia W/S scheme | Assistant Engineer | Junior Engineer | BILL/00531/2024-2025 | BP-2024-25-151 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.42 | 0 | 0
4347 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Karakberia W/S scheme | Assistant Engineer | Junior Engineer | BILL/00532/2024-2025 | BP-2024-25-152 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.17 | 0 | 0
4348 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Karak Beriya Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000146/2025-2026 | 441/BMD | 10/06/2025 | 90 | P.K. ENGINEERING | 11.79 | 0 | 0
4349 | Bankura Division | Bankura Sadar Sub-Division | Laying of balance distribution system of pipeline with allied works for Augmentation of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, (for mugathole, Khoyerboni, Benagoria, Arajuri & chandra village) | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 1300/BQA | 17/06/2025 | 198 | TARINI CHARAN UPADHYAY | 40.77 | 0 | 0
4350 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, Total House Hold - 350 Nos. | Assistant Engineer | Junior Engineer | ORD/000689/2022-2023 | 590/BQA | 20/03/2023 | 1108 | MUNMUN UPADHYAY | 86.2 | 80.3 | 90
4351 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Jorehira (Zone-B) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2023-2024 | 2975/BQA | 31/10/2023 | 30 | MEASURE LAND | 1.8 | 1.77 | 100
4352 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000091/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.51 | 0 | 0
4353 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000262/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.51 | 0 | 0
4354 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House, Low Lift Pump House, Boundary Wall and Laying Distribution system under Augmentation works for Joytunga (Zone - H) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 1505/BQA | 18/06/2024 | 562 | SAIKAT CHOWDHURY | 82.04 | 0 | 10
4355 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 (One) no 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Location:- Mouza- Maithagopinathpur, J.L. No.- 315, LR Plot No.- 485/1184) | Assistant Engineer | Junior Engineer | ORD/000155/2025-2026 | 1299/BQA | 17/06/2025 | 45 | UNIVERSAL CONSTRUCTION | 11.02 | 0 | 0
4356 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 658/BSD | 10/06/2024 | 15 | GOUTAM MUKHERJEE | 0.96 | 0.96 | 100
4357 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000306/2024-2025 | 659/BSD | 10/06/2024 | 15 | GOUTAM MUKHERJEE | 0.8 | 0.8 | 100
4358 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- C) | Assistant Engineer | Junior Engineer | ORD/000307/2024-2025 | 660/BSD | 10/06/2024 | 15 | DAUD ALI KHAN | 0.96 | 0.96 | 100
4359 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- D) | Assistant Engineer | Junior Engineer | ORD/000308/2024-2025 | 661/BSD | 10/06/2024 | 15 | DAUD ALI KHAN | 0.97 | 0.97 | 100
4360 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000079/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.93 | 0 | 0
4361 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000235/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.93 | 0 | 0
4362 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00143/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4363 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Barabendya CWR Site under Joytunga (zone-H) Water supply scheme Barjora block under BMD,PHE Dte. (SM/16961) | Assistant Engineer | Junior Engineer | BILL/01343/2024-2025 | BP-2024-25-344 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.51 | 0 | 0
4364 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for JOYTUNGA (Zone-H) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 504/BMD | 09/07/2024 | 120 | A.G.ENTERPRISE | 13.16 | 0 | 0
4365 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Joytunga (Zone - H), No. of Mouza :- 17 nos., Name of mouza:- (Jorshal, Dhenga kend, Kushma, Golhati, Bonomadhavpur, Ladna, Mathana, Kodalia, Bandarkhola, Ramharipur, Katapesia, Kolaberia, Maitha Gopinathpur, Bara Bendya, Joytunga, Kostia & Khemua), No. of Household- 3372 nos. | Assistant Engineer | Junior Engineer | ORD/000395/2023-2024 | 2080/BQA | 27/07/2023 | 1009 | UNIVERSAL CONSTRUCTION | 210.96 | 96.5 | 50
4366 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Joytunga (Zone- H) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2023-2024 | 434/BQA | 08/02/2024 | 30 | LEMNISCATE | 3.7 | 0 | 100
4367 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joytunga ( Zone-H) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000529/2023-2024 | 1893/BMD | 17/08/2023 | 120 | A.G.ENTERPRISE | 81.78 | 50.13 | 62
4368 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. No. of House Hold :- 100 | Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 2780/BQA | 09/10/2023 | 905 | M/S TARUN KUMAR PATRA | 71.41 | 15.99 | 20
4369 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. No. of House Hold :- 100 | Assistant Engineer | Junior Engineer | ORD/000749/2023-2024 | 2781/BQA | 09/10/2023 | 270 | ASOKE BHATTACHARYYA | 71.41 | 19.58 | 20
4370 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (700 CUM CAPACITY) under Augmentation works for CHATURDIHI (Zone- U2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2023-2024 | 3041/BQA | 06/11/2023 | 695 | G.MITRA AND ASSOCIATES | 0.63 | 0 | 100
4371 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001205/2023-2024 | 458//BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 5.98 | 0 | 100
4372 | Bankura Division | Bankura Sadar Sub-Division | Barbed wire Fencing works at CHATURDIHI (Zone - U-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001480/2023-2024 | 208/BSD | 02/02/2024 | 10 | M/S BANERJEE & BANERJEE | 0.69 | 0.69 | 100
4373 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000086/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.36 | 0 | 0
4374 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000247/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.36 | 0 | 0
4375 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement charges for CHATURDIHI OHR under Bankura -I,II & Borjora (BRGF Ph-I) water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00379/2024-2025 | BP-2024-25-81 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
4376 | Bankura Mechanical | Bankura Sadar Sub-Division | New service conection at puramouli mouza of Chaturdihi augmentation site undfer Bankura-I,II & Barjora water supply scheme at Bankura-I block under BMD PHE dte.(SM/16971) | Assistant Engineer | Junior Engineer | BILL/01358/2024-2025 | BP-2024-25-342 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.24 | 0 | 0
4377 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation works for CHATURDIHI (Zone U) under Bankura I, II and Barjora Block Water Supply Scheme (BRGF Ph I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001039/2023-2024 | 2971/BMD | 29/02/2024 | 360 | ORIENTAL ENGINEERING CO. | 97.69 | 0 | 53
4378 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone‐ VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/16936) | Assistant Engineer | Junior Engineer | BILL/00661/2024-2025 |  | 09/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 5.65 | 0 | 0
4379 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone‐ VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/16936) | Assistant Engineer | Junior Engineer | BILL/01241/2024-2025 | BP-226/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 5.65 | 0 | 0
4380 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
4381 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2023-2024 | 2736/BQA | 04/10/2023 | 1090 | PARAMESWAR CHOWDHURY | 227.44 | 72.96 | 45
4382 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-7B) (Sl. No. 13) | Assistant Engineer | Junior Engineer | ORD/000972/2022-2023 | 191/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.3 | 3.06 | 0
4383 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001314/2023-2024 | 921/BQA | 15/03/2024 | 90 | SANDIP PATI | 4.63 | 0 | 0
4384 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001387/2024-2025 | 34/BQA | 02/01/2025 | 45 | PARAMESWAR CHOWDHURY | 27.43 | 0 | 90
4385 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 1.65 | 0 | 0
4386 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000211/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.81 | 0 | 0
4387 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 1129/BMD | 24/05/2023 | 30 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0
4388 | Bankura Division | Bankura Sadar Sub-Division | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Proposed Ground Water Based Patappur (Manachar) Piped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Mouza - Patappur (50%), Sitarampur (50%) under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000436/2023-2024 | 2270/BQA | 01/08/2023 | 270 | AMARANJALI CONSTRUCTION | 104.51 | 0 | 65
4389 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Sitarampur [Part] (JL No- 16) & Pratappur [Part] (JL No- 15) mouza under Barjora Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001185/2022-2023 | 353\BSD | 12/04/2022 | 15 | M/S. R. DUTTA & CO. | 1.43 | 1.43 | 95
4390 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000065/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.14 | 0 | 0
4391 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000216/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.14 | 0 | 0
4392 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000305/2023-2024 | 997/BQA | 22/03/2024 | 0 | Resource Division | 2.69 | 0 | 0
4393 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer |  | BILL/00132/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
4394 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL Service connection charge for Pratappur (Manachar) water supply scheme, Barjora block under BMD,PHE Dte. (sm/16695 ) | Assistant Engineer |  | BILL/01096/2024-2025 | BP-2024-25-254 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.3 | 0 | 0
4395 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Pratappur( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer |  | ORD/000450/2023-2024 | 1777/BMD | 01/08/2023 | 706 | UNITED TRADERS | 32.7 | 16.2 | 80
4396 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machineries and other electromechanical accessories for Ground water based Krishnanagar (Manachar) piped water supply scheme under Bankura Mechanical Division, P.H.E Dte.Block Barjora Dist: Bankura | Assistant Engineer |  | ORD/000578/2024-2025 | 1400/BMD | 12/12/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 39.35 | 0 | 0
4397 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer |  | ORD/000580/2024-2025 | 1401/BMD | 12/12/2024 | 120 | GOPAL CHANDRA CHOWDHURY | 21.44 | 0 | 0
4398 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House with all allied works at Kanchanpur (Zone- C), OHR Site under Augmentation of Kanchanpur (Zone- C) Water Supply Scheme under Jal Jeevan Mission (JJM) under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000188/2024-2025 | 1852/BQA | 12/07/2024 | 232 | M/S ASHA ENGINEERING | 13.94 | 0 | 100
4399 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low lift Pump House, Boundary Wall under Augmentation works for Kanchanpur (Zone- C) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 1863/BQA | 12/07/2024 | 90 | SUBHADIP KOLE | 22.81 | 0 | 0
4400 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 2030/BQA | 24/07/2023 | 989 | PRINCE INDUTRIES (INDIA) | 300.97 | 210.32 | 80
4401 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kanchanpur (Zone- C) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001177/2023-2024 | 429/BQA | 08/02/2024 | 30 | LEMNISCATE | 3.54 | 0 | 100
4402 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/001282/2023-2024 | 07/BSD | 03/01/2024 | 10 | SUBHADIP KOLE | 0.96 | 0.96 | 100
4403 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/001283/2023-2024 | 08/BSD | 03/01/2024 | 10 | SUBHADIP KOLE | 0.96 | 0.96 | 100
4404 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/001284/2023-2024 | 09/BSD | 03/01/2024 | 10 | SUBHADIP KOLE | 0.96 | 0.96 | 100
4405 | Bankura Division | Bankura Sadar Sub-Division | Continuation engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from (01.03.2025 to 30.04.2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002113/2024-2025 | 302/BSD | 28/02/2025 | 61 | GOUTAM GHOSH | 0.29 | 0 | 0
4406 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.32 | 0 | 0
4407 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000225/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.32 | 0 | 0
4408 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00161/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
4409 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- D) | Assistant Engineer | Junior Engineer | ORD/001286/2023-2024 | 10/BSD | 03/01/2024 | 10 | SUBHADIP KOLE | 0.96 | 0.96 | 100
4410 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- E) | Assistant Engineer | Junior Engineer | ORD/001497/2023-2024 | 34/BSD | 08/01/2024 | 10 | SUBHADIP KOLE | 0.96 | 0.96 | 100
4411 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- F) | Assistant Engineer | Junior Engineer | ORD/001498/2023-2024 | 35/BSD | 08/01/2024 | 10 | SUBHADIP KOLE | 0.92 | 0.92 | 100
4412 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- G) | Assistant Engineer | Junior Engineer | ORD/001499/2023-2024 | 36/BSD | 08/01/2024 | 10 | SUBHADIP KOLE | 0.54 | 0.53 | 100
4413 | Bankura Division | Bankura Sadar Sub-Division | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- H) | Assistant Engineer | Junior Engineer | ORD/001500/2023-2024 | 37\BSD | 08/01/2024 | 10 | SUBHADIP KOLE | 0.54 | 0.54 | 100
4414 | Bankura Division | Bankura Sadar Sub-Division | Continuation hiring of car equivalent to Motor cab & Maruti Omni (Standard) with Mass emission standard of BS- III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/03/2025 to 30/04/2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002112/2024-2025 | 301/BSD | 28/02/2025 | 61 | GOURANGA NANDI | 0.29 | 0 | 0
4415 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement Service connection charge for Kanchanpur (zone-C) OHR site water supply scheme Barjora block under BMD,PHE Dte. (SM/16956) | Assistant Engineer | Junior Engineer | BILL/02193/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.89 | 0 | 0
4416 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Kanchanpur (Zone-C) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 502/BMD | 09/07/2024 | 360 | KINGKINI TRADERS | 23.07 | 0 | 25
4417 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kanchanpur ( Zone C) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1885/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.06 | 69
4418 | Bankura Division | Brishnupur Sub-Division | Balanced ancillary works for Gopalpur Water Supply Scheme under Kotulpur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2025-2026 | 1452/BQA | 01/07/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 102.61 | 0 | 90
4419 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GOPALPUR PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000470/2023-2024 | 2325/BQA | 14/08/2023 | 540 | GOPAL CHANDRA CHOWDHURY | 598.08 | 198.15 | 70
4420 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 98.39 | 0 | 0
4421 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Gopalpur W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01241/2024-2025 | BP-2024-25-313 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.7 | 0 | 0
4422 | Bankura Mechanical | Brishnupur Sub-Division | Gopalpur | Assistant Engineer | Junior Engineer | BILL/01504/2023-2024 | BP-2023-24-94 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.11 | 0 | 0
4423 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Gopalpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 885/BMD | 04/05/2023 | 698 | ORIENTAL ENGINEERING CO. | 40.24 | 14.33 | 36
4424 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 01 no. i.e. Bamania-113 , Total House Hold - 753 | Assistant Engineer | Junior Engineer | ORD/000164/2021-2022 | 2848/BQA | 16/11/2021 | 30 | AMITAVA CHAKRABORTY | 63.93 | 37.53 | 0
4425 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000239/2022-2023 | 1303/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.06 | 1.61 | 0
4426 | Bankura Division | Brishnupur Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" | Assistant Engineer | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 30 | SOUMITRA BHATTACHARYA | 41.63 | 0.64 | 0
4427 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR MANIK BAZAR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2023-2024 | 2033/BQA | 24/07/2023 | 270 | PARTHA PRATIM CHHATAIT | 407.94 | 116.47 | 75
4428 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000026/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 16.45 | 0 | 0
4429 | Bankura Mechanical | Brishnupur Sub-Division | Manik Bazar Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01512/2023-2024 | BP-2023-24-114 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.85 | 0 | 0
4430 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Manikbazar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 886/BMD | 04/05/2023 | 60 | KINGKINI TRADERS | 37.08 | 19.35 | 45
4431 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AMRUL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000345/2023-2024 | 1969/BQA | 18/07/2023 | 623 | S.N POLYMERS PVT LTD | 159.83 | 78.66 | 85
4432 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House and Boundary Wall for Augmentation of Amrul (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001380/2024-2025 | 17/BQA | 02/01/2025 | 90 | KASTURI ROY | 12.97 | 0 | 90
4433 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 3 nos. sites of Augmentation of Amrul Zone-A Water Supply Scheme (SM/17229) & 3 nos. sites of Augmentation of Amrul Zone-B Water Supply Scheme (SM/17230) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001813/2024-2025 | 539/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
4434 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00180/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
4435 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AMRUL ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00435/2024-2025 | BP-2024-25-112 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
4436 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Nuriduri (8Amrul Zone-A) | Assistant Engineer | Junior Engineer | BILL/01339/2024-2025 | BP-2024-25-340 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.35 | 0 | 0
4437 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01622/2023-2024 | BP-2023-24-159 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0
4438 | Bankura Mechanical | Brishnupur Sub-Division | Quotation money bill for new power application at Mourai boosting pump house under Augmentation of Amrul Zone-A water supply scheme, SM Code-SM/17229, Application no-2005272877, Ref. id-204646763 | Assistant Engineer | Junior Engineer | BILL/01703/2025-2026 |  | 06/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.31 | 0 | 0
4439 | Bankura Mechanical | Brishnupur Sub-Division | Quotation money bill for new electric connection at Amrul boosting pump house under Augmentation of Amrul Zone-A, Scheme code-SM/17229, Ref. Application No. 2005511388, Ref. Id. 204751657 | Assistant Engineer | Junior Engineer | BILL/01704/2025-2026 |  | 06/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
4440 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Amrul (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 1696/BMD | 28/07/2023 | 60 | PRADIP KUMAR DHABAL | 54.01 | 28.75 | 53
4441 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Functional House Hold Tap Connection with Jal Jeevan Mission (JJM) for Augumentation of BARJORA Water Supply Scheme(Left out Mouzas of Barjora Block under B.R.G.F Phase-I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, P.H.E Dte.(Zone-IB) | Assistant Engineer | Junior Engineer | ORD/000411/2023-2024 | 2005/BQA | 19/07/2023 | 270 | PRAVAT SARKAR | 425.16 | 101.76 | 38
4442 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (600 CUM CAPACITY) under Augmentation of Barjora Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. (Zone- IB) | Assistant Engineer | Junior Engineer | ORD/000887/2023-2024 | 3038/BQA | 06/11/2023 | 30 | K S GROUP | 0.49 | 0.49 | 100
4443 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001185/2023-2024 | 437/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.69 | 0 | 100
4444 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000101/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.86 | 0 | 0
4445 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000279/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.86 | 0 | 0
4446 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). | Assistant Engineer | Junior Engineer | BILL/00155/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
4447 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Bhairabpur Pump House augmentation work under Barjora (Left out mouza) (zone-IB) water supply scheme (SM/17245) | Assistant Engineer | Junior Engineer | BILL/00722/2024-2025 | BP-2024-25-199 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.18 | 0 | 0
4448 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IB) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2024-2025 | 499/BMD | 09/07/2024 | 360 | UNITED TRADERS | 13.19 | 0 | 83
4449 | Bankura Mechanical | Bankura Sadar Sub-Division | Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IB) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1400/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.81 | 61.5 | 74
4450 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) | Assistant Engineer | Junior Engineer | ORD/000486/2023-2024 | 2338/BQA | 14/08/2023 | 270 | SIB SANKAR CHOWDHURY | 227.04 | 160.59 | 81
4451 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001186/2023-2024 | 438/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.62 | 0 | 100
4452 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000102/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4.63 | 0 | 0
4453 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000281/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 4.63 | 0 | 0
4454 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | Assistant Engineer | Junior Engineer | BILL/00156/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
4455 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000513/2023-2024 | 1878/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69
4456 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Sub-Station Equipment and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001031/2023-2024 | 2963/BMD | 29/02/2024 | 540 | COMBINE ENTERPRISES | 28.82 | 0 | 35
4457 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, Total House Hold - 06 nos (Part-A) | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 644/BSD | 10/06/2024 | 7 | MOHAMMED RAFIK MANDAL | 0.89 | 0.89 | 1
4458 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, (Part-B) | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 645/BSD | 10/06/2024 | 7 | INJAMAMUL HAQUE MONDAL | 0.78 | 0.73 | 1
4459 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, (Part-C) | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 646/BSD | 10/06/2024 | 7 | INJAMAMUL HAQUE MONDAL | 0.77 | 0.76 | 1
4460 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul Upar Para) of Kalipur (Zone-C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, Total House Hold - 08 nos (Part-A) | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 647/BSD | 10/06/2024 | 211 | BAYEN CONSTRUCTION | 0.92 | 0.91 | 100
4461 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul Upar Para) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, (Part-B) | Assistant Engineer | Junior Engineer | ORD/000291/2024-2025 | 648/BSD | 10/06/2024 | 236 | BAYEN CONSTRUCTION | 0.96 | 0.95 | 100
4462 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Kalipur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - KALIPUR, Total House Hold - 250 nos. | Assistant Engineer | Junior Engineer | ORD/000803/2022-2023 | 711/BQA | 30/03/2023 | 1008 | APEX ENTERPRISE | 99.27 | 21.22 | 32
4463 | Bankura Division | Bankura Sadar Sub-Division | Digital structurization of pipeline alignment and asset evaluation through survey and preparation of map of Kalipur Zone-C under Saltora- Chhatna Water Supply Scheme, Bankura District under the jurisdiction of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001669/2024-2025 | 387/BQA | 07/02/2025 | 30 | TECHVISION | 2.98 | 2.98 | 5
4464 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000104/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.7 | 0 | 0
4465 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000284/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.7 | 0 | 0
4466 | Bankura Division | Bankura Sadar Sub-Division | Augmentation for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2023-2024 | 2081/BQA | 27/07/2023 | 270 | MUNMUN UPADHYAY | 127.08 | 80.05 | 98
4467 | Bankura Division | Bankura Sadar Sub-Division | Supplying of different dia. CIDF sluice valve PN- 1.0 in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A,B,C & D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000713/2022-2023 | 621/BQA | 23/03/2023 | 30 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.52 | 3.76 | 20
4468 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 (one) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method and Repairing and Renovation of RCC Elevated Over Head Reservoir of 350 Cum capacity under Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | ORD/001393/2024-2025 | 40/BQA | 02/01/2025 | 456 | MUNMUN UPADHYAY | 26.62 | 0 | 45
4469 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinganiand adjoining mouzas W/S Scheme & Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001939/2024-2025 | 655/BQA | 11/03/2025 | 86 | SWAPAN KUMAR BIT | 12.23 | 0 | 0
4470 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.29 | 0 | 0
4471 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000292/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.29 | 0 | 0
4472 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories w for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000323/2024-2025 | 864/BMD | 29/08/2024 | 360 | AMITAVA CHAKRABORTY | 35.75 | 0 | 90
4473 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-D) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000716/2023-2024 | 2173/BMD | 30/10/2023 | 120 | PRADIP KUMAR DHABAL | 32.67 | 21.75 | 60
4474 | Bankura Division | Brishnupur Sub-Division | Balanced ancillary works for Awditawbati Water Supply Scheme under Kotulpur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001973/2024-2025 | 688/BQA | 12/03/2025 | 60 | M/S TARUN KUMAR PATRA | 87.5 | 0 | 60
4475 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 93.07 | 0 | 0
4476 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Adwaitabati W/S scheme | Assistant Engineer | Junior Engineer | BILL/00526/2024-2025 | BP-2024-25-146 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.12 | 0 | 0
4477 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Adwitabati W/S Scheme | Assistant Engineer | Junior Engineer | BILL/00533/2024-2025 | BP-2024-25-147 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.69 | 0 | 0
4478 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Adwitabati Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 766/BMD | 24/04/2023 | 1080 | TAPAN KUMAR SARKAR | 46.96 | 26.82 | 58
4479 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Bikrampur, No.of Mouza :- 13, Name of mouza:- Patadubi, Angadpur, Bhaluka, Karra, Hemchabad, Bikrampur, Indkata, Lohari Brindaban, Kochkhalui, Brindabanpur, Shusina Gobindarampur, Ramar Gram & Hatiband , Total House Hold - 150 nos. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 798/BQA | 11/04/2023 | 45 | BEAUTY CHATTERJEE | 51.43 | 49.17 | 95
4480 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000037/2023-2024 | 799/BQA | 11/04/2023 | 45 | MAA USHA CONSTRUCTION CO. | 28.04 | 12.91 | 45
4481 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 1348/BQA | 02/06/2023 | 45 | BROTIN UPADHYAY | 14.23 | 9.57 | 100
4482 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE Pipe Line for Hatibandh & Karrah in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000202/2024-2025 | 1890/BQA | 15/07/2024 | 60 | SWAPAN KUMAR DE | 15.26 | 0 | 5
4483 | Bankura Division | Bankura Sadar Sub-Division | Supplying fitting fixing of different dia. CIDF Sluice Valve & fittings & Construction of valve chamber in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001037/2023-2024 | 3465/BQA | 19/12/2023 | 90 | GOUTAM GOSWAMI | 3.84 | 0 | 0
4484 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001375/2024-2025 | 29/BQA | 02/01/2025 | 260 | SANJOY MONDAL | 12.81 | 0 | 85
4485 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000133/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.11 | 0 | 0
4486 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000253/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.11 | 0 | 0
4487 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Replacement TW for Augmentation of Bikrampur and Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 445/BMD | 27/06/2024 | 600 | M/S SWAPAN BANERJEE | 19.55 | 0 | 80
4488 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Bikrampur & Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000550/2023-2024 | 1986/BMD | 28/08/2023 | 1020 | JAGANNATH ENTERPRISE | 21.15 | 15.38 | 90
4489 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed Tubewell-II of Bikrampur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001087/2023-2024 | 3063/BMD | 12/03/2024 | 180 | M/S BIPUL BANERJEE | 25.39 | 11.78 | 40
4490 | Bankura Division | Bankura Sadar Sub-Division | Laying of distribution system of pipeline and other allied works with Jal Jeevan Mission (JJM) of augmentation work for keshra, (Zone- I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR -keshra, No.of Mouza :- ( Khirpai, Hanulia, Lakshmishol, Pithabad, Bhandarber, Shaldiha) | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 1298/BQA | 17/06/2025 | 288 | BEAUTY CHATTERJEE | 43.78 | 0 | 1
4491 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of keshra (Zone - I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000309/2023-2024 | 1955/BQA | 18/07/2023 | 988 | AJIT KUMAR PAUL | 114.57 | 59.15 | 26
4492 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000142/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.09 | 0 | 0
4493 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000243/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.09 | 0 | 0
4494 | Bankura Division | Bankura Sadar Sub-Division | Ceration of Balance FHTC with pipe line, Construction of 02 (Two) nos Pump House cum chlorine room (5.40 M X 3.6M) & Toilet with sanitary water supply arrangement including plinth protection, Ramp etc at Tail end TW-1 Site at Hirapur village & TW-2 Site at Kamla village and Construction of Boundary wall at Tail end TW- 1 Site at Hirapur village & TW- 2 Site in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Water Supply Scheme (BRGF Ph- I) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000073/2025-2026 | 1012/BQA | 25/04/2025 | 60 | M/S SUPRIYA CHATTERJEE | 73.8 | 0 | 0
4495 | Bankura Division | Bankura Sadar Sub-Division | Laying of UPVC Pipeline from Sahebganj more to Benajira village of damaged existing UPVC pipe line due to PWD Road Widening work for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000075/2025-2026 | 1014/BQA | 25/04/2025 | 341 | ASHIS KUMAR SAMANTA | 18.7 | 0 | 100
4496 | Bankura Division | Bankura Sadar Sub-Division | Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000500/2023-2024 | 2350/BQA | 14/08/2023 | 961 | ASHIS KUMAR SAMANTA | 278.43 | 212.63 | 72
4497 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000144/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.39 | 0 | 0
4498 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000238/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.39 | 0 | 0
4499 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charges for for WBSEDCL power for Aghuribandh Punisole Zone-A water supply scheme under PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01496/2024-2025 | BP-2024-25-375 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.03 | 0 | 0
4500 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000136/2024-2025 | 442/BMD | 27/06/2024 | 480 | M.S. ENTERPRISE | 60.77 | 0 | 100
4501 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000547/2023-2024 | 1983/BMD | 28/08/2023 | 840 | KASHINATH DEY | 31.55 | 0 | 75
4502 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Additional Tubewell for Augmentation works for Aguribandh Punisole (Zone C) Water Supply Scheme in the Block Onda under Bankura Mechanical Division, PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000874/2024-2025 | 2036/BMD | 07/03/2025 | 120 | SWAPAN ENTERPRISE | 17.36 | 0 | 0
4503 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-B)under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000306/2023-2024 | 1954/BQA | 18/07/2023 | 684 | SABIR ALI KHAN | 144.14 | 92.07 | 45
4504 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M Bg-. 213-29 /31) in between Rly. Station Ramsagar(RSG) & Onda Gram (ODM) Rly. station, P.S. Onda,by Jack Pushing method with 350 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Rejuvenation of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2024-2025 | 2976/BQA | 26/11/2024 | 90 | SIBSANKAR CHOWDHURY | 54.4 | 0 | 0
4505 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000141/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.09 | 0 | 0
4506 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000236/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.09 | 0 | 0
4507 | Bankura Mechanical | Bankura Sadar Sub-Division | Total payable load enhancement charges at Tetulmuri of Nikunjapur Zone-B ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00291/2024-2025 | 1 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.55 | 0 | 0
4508 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-B) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000554/2023-2024 | 1990/BMD | 28/08/2023 | 120 | DIPALI CONSTRUCTION | 47.88 | 28.5 | 76
4509 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electro-mechanical accessories for Augmentation works at CWPH at Gamidya under Nikunjapur Zone B water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001078/2023-2024 | 3057/BMD | 12/03/2024 | 480 | TAPAN KUMAR SARKAR | 38.32 | 8.95 | 100
4510 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AKUI ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1920/BQA | 13/07/2023 | 990 | PRINCE INDUTRIES (INDIA) | 186.44 | 87.56 | 80
4511 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00185/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
4512 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AKUI ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00439/2024-2025 | BP-2024-25-113 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.85 | 0 | 0
4513 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01625/2023-2024 | BP-2023-24-160 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0
4514 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of Panel with Automatic Chlorinator and Stabilizer machineries along with other allied electro-mechanical works for newly sunk TW at Akui Zone B boosting TW site of Indus water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2025-2026 | 152/BMD | 30/04/2025 | 270 | SEN BROTHERS | 18.86 | 0 | 30
4515 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000359/2023-2024 | 1695/BMD | 28/07/2023 | 669 | ABHIJIT MUKHERJEE | 74.38 | 46.82 | 36
4516 | Bankura Division | Bankura Sadar Sub-Division | Preparation of DPR for Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura under Jal Jeevan Mission (JJM) Project of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 1335/BQA | 01/06/2023 | 30 | ENVIROTECH SOLUTIONS | 3.48 | 3.46 | 100
4517 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Indpur Piped water supply scheme, Block - Bankura - I,under Bankura (Sadar) Sub - Division within Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2023-2024 | 2363/BQA | 14/08/2023 | 270 | S. S. S. ENTERPRISES | 463.15 | 110.61 | 27
4518 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Augmentation of Indpur Piped Water Supply Scheme, Block- Bankura- I, District- Bankura. | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 3037/BQA | 06/11/2023 | 30 | K S GROUP | 0.49 | 0.45 | 100
4519 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000098/2022-2023 | 731/BQA | 31/03/2023 | 0 | Resource Division | 100.35 | 0 | 0
4520 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000138/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4 | 0 | 0
4521 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000234/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 4 | 0 | 0
4522 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 50KVA to 80 KVA at 11KV having Consumer ID : 942309800 at the premises at Indpur Xone-1, Kaladihi, Bankura. | Assistant Engineer | Junior Engineer | BILL/00959/2024-2025 | BP-2024-25-228 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.92 | 0 | 0
4523 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Indpur piped water supply Scheme Block-Bankura-I under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000990/2023-2024 | 2850/BMD | 09/02/2024 | 180 | M.S. ENTERPRISE | 120.1 | 101.77 | 30
4524 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 150 mtr long of Somsar Piped water supply scheme (H/W Site) in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 1857/BQA | 12/07/2024 | 45 | FAZLUR RAHAMAN BHANGI | 8.59 | 0 | 100
4525 | Bankura Division | Brishnupur Sub-Division | Sinking of 2 nos. 300mm X 200mm X 250m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Laying distribution system and platform for FHTC in connection with Jal Jeevan Mission (JJM) of Somsar W/S Scheme under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :-Somsar No. of Mouzas Covered :- 1 nos., Name of Mouzas & JL No.:-Somsar (2) Total No. House Hold | Assistant Engineer | Junior Engineer | ORD/000794/2022-2023 | 678/BQA | 28/03/2023 | 1010 | GOUTAM GHOSH | 81.88 | 20.38 | 80
4526 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. site of Augmentation of Indas Water Supply Scheme (SM/17684 ) & 2 nos. sites of Augmentation of Somsar Water Supply Scheme (SM/17422) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001822/2024-2025 | 543/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
4527 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 2526/BQA | 08/09/2023 | 0 | Resource Division | 3.19 | 0 | 0
4528 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Somsar Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00190/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4529 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SOMSAR PH-I Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00434/2024-2025 | BP-2024-25-108 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0
4530 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SOMSAR PH-II water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00441/2024-2025 | BP-2024-25-109 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0
4531 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Somsar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000461/2023-2024 | 1787/BMD | 01/08/2023 | 300 | A.G.ENTERPRISE | 53.61 | 24.55 | 60
4532 | Bankura Division | Bankura Sadar Sub-Division | Rail bhoomi crossing seva | Assistant Engineer | Junior Engineer | BILL/00934/2023-2024 | FHTC/08 | 31/08/2023 | 0 | SOUTH EASTERN RAILWAY | 0.53 | 0 | 0
4533 | Bankura Division | Bankura Sadar Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS DHABANI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- BARJORA, DISTRICT -BANKURA . NAME OF MUZA - KANCHCHHALA, SAMANTAMARA & DHABANI UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 2275/BQA | 01/08/2023 | 853 | PRADIP RAJAK | 349.81 | 165.08 | 62
4534 | Bankura Division | Bankura Sadar Sub-Division | Route Survey Preparation of DPR for piped water supply scheme for uncover mouzas of Kanchchala (JL No- 126), Samantamara (127) & Dhabani (JL No- 128) Block- Barjora under Jal Jeevan Misson (JJM) of Bankura Sadar Sub - Division under Bankura Division, PHE Dte . | Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 2978/BQA | 31/10/2023 | 30 | LEMNISCATE | 2.67 | 0 | 100
4535 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (100 CUM CAPACITY) under Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000895/2023-2024 | 3046/BQA | 06/11/2023 | 30 | K S GROUP | 0.57 | 0.55 | 100
4536 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 26.04 | 0 | 0
4537 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000135/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.99 | 0 | 0
4538 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000233/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.99 | 0 | 0
4539 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00198/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
4540 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Dhabani water supply scheme (CWR, OHR site), Barjora block under BMD, PHE Dte. (SM/1804) | Assistant Engineer | Junior Engineer | BILL/01336/2024-2025 | BP-2024-25-329 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.3 | 0 | 0
4541 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Dhabani under Water Supply Scheme Block- Barjora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1769/BMD | 01/08/2023 | 60 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 45.35 | 26.22 | 31
4542 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Basudebpur, No. of Mouza :- 19 nos. i.e. Gosainpur - 72,Gopalpur - 73,Jangal Bankati - 74, Radhadamodarpur - 75,Kamarpukur - 76, Belsulia - 109,Dumohani - 110,Bangele - 111, Siromonipur - 104,Moyra pukur - 105,Dhenga pathar - 106,Basudebpur - 107, Tribunka - 108, Hereparbbat - 77,Madhuban - 78,Chaugan - 102,Kural Bari-103,Dundure - 116,Pirragara - 120, Total House Hold - 2785 | Assistant Engineer | Junior Engineer | ORD/000027/2022-2023 | 1086/BQA | 12/05/2022 | 360 | GOPAL CHANDRA CHOWDHURY | 235.11 | 0 | 0
4543 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Morar Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Benebandhi, No. of Mouza :- 7 nos. i.e.Dadwasbati-98, Kusumbani-99, Chougan-102, Dundure-116, Morar-117, Ghugimura-121, Jharia-122, Total House Hold -70 | Assistant Engineer | Junior Engineer | ORD/000028/2022-2023 | 110/VSD | 19/04/2022 | 21 | AJIT KUMAR DUTTA | 4.52 | 0 | 0
4544 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Basudebpur, No. of Mouza :- 01 no. i.e. Morar - 117, House Hold - 1806 | Assistant Engineer | Junior Engineer | ORD/000392/2021-2022 | 203/BQA | 01/02/2022 | 60 | M/S TARUN KUMAR PATRA | 171.51 | 154.02 | 0
4545 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2021-2022 | 271/BQA | 11/02/2022 | 0 | Resource Division | 91.96 | 0 | 0
4546 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2021-2022 | 475/BQA | 04/03/2022 | 0 | Resource Division | 11.11 | 0 | 0
4547 | Bankura Division | Brishnupur Sub-Division | Laying of UPVC pipeline for running drinking water supply arrangement to sumangalam home at Kharikasuli with in Morar post office within Bishnupur block under Morar zone - A water supply scheme (BRGF Bishnupur ) under Bishnupur sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000280/2022-2023 | FHTC/26 | 26/04/2022 | 0 | KOUSIK MONDAL | 2.58 | 0 | 0
4548 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road trom Dublala to Thakurabara under Raipur Block in the District of Bankura ,Vide Package No- WB-03-ADB-08, Road Length-2.685 Km. ( Augmentation of Dhanara & its adjoining mouzas of water supply scheme) | Assistant Engineer | Junior Engineer | BILL/01461/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.36 | 0 | 0
4549 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Sahajpur to Moulasol under Raipur Block in the Distiict of Bankura ,Vide Package No WB-03-44, Road Length-9.96 Km. ( Augmentation of Dhanara & its adjoining mouzas of water supply scheme) | Assistant Engineer | Junior Engineer | BILL/01464/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.15 | 0 | 0
4550 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve Chamber and Construction of Boundary wall at CWR site & Tubewell site for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 1828/BQA | 12/07/2024 | 264 | D. S. ENTERPRISE | 47.76 | 0 | 0
4551 | Bankura Division | Khatra Sub-Division | Sinking of 2 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿, Construction of High Lift Pump House and 200 Cum. CWR with Collecting Line ancillary works in different mouzas for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2023-2024 | 1926/BQA | 13/07/2023 | 270 | SIB SANKAR CHOWDHURY | 257.41 | 29.81 | 23
4552 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division in Bankura District, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000718/2025-2026 | 2287/BQA | 27/11/2025 | 60 | SIBSANKAR CHOWDHURY | 23.88 | 0 | 0
4553 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000836/2023-2024 | 2962/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.4 | 2.34 | 97
4554 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 4 nos. site of Augmentation of Dhanara Water Supply Scheme (SM/17297) and 2 nos. site of Retrofitting of Lurka (Zone-VA) Water Supply Scheme (BRGF Ph-I) (SM/16940) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001932/2024-2025 | 175\KSD | 07/03/2025 | 10 | SANDHYA DEY | 0.9 | 0 | 90
4555 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000189/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
4556 | Bankura Mechanical | Khatra Sub-Division | quotation Bill for New Pump house no.1 at Katalda under Danara w/s scheme augmentation work (SM/17297) | Assistant Engineer | Junior Engineer | BILL/00946/2024-2025 | BP-2024-25-231 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.3 | 0 | 0
4557 | Bankura Mechanical | Khatra Sub-Division | Quotation Bill for New Pump house no.2 at Katalda under Danara w/s scheme augmentation work (SM/17297) | Assistant Engineer | Junior Engineer | BILL/00947/2024-2025 | BP-2024-25-232 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.58 | 0 | 0
4558 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Dhanara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000989/2023-2024 | 2849/BMD | 09/02/2024 | 900 | DEY ENTERPRISE | 144.45 | 0 | 21
4559 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 400 Cum., staging height 20 Mtr.), CWR, Pump House cum Chlorine Room and Construction of Boundary Wall and Guard Room with all allied works of Augmentation works for Dhanara and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2024-2025 | 674/BQA | 12/03/2025 | 90 | SINGHA ENTERPRISE | 51.93 | 0 | 0
4560 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for Augmentation works at T/W No-II at Katalda Pump house under Dhanara Water supply scheme and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme,Under Raipur Block under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000262/2024-2025 | 517/BMD | 09/07/2024 | 120 | R.K. ENTERPRISE | 7.09 | 0 | 0
4561 | Bankura Division | Bankura Sadar Sub-Division | 02 (Two) nos. Road Crossing work by 100 mm dia MS carrier pipe & 300 mm MS casing pipe infront of Gamiddya Tubewell Site and others suitable places over Nikunjapur-Bishnupur PWD Road by Jack pushing method, inetrconnection of MS carrier pipe with HDPE pipeline including fabrication of MS pipe & allied works for Augmentation of Nikunjapur (Zone- A) Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2025-2026 | 1804/BQA | 19/08/2025 | 45 | PRADIP PATRA | 11.04 | 0 | 100
4562 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2023-2024 | 2085/BQA | 27/07/2023 | 540 | DIVINE | 177.02 | 138.23 | 80
4563 | Bankura Division | Bankura Sadar Sub-Division | Construction of Low Lift Pump House and Boundary Wall at Gamidya Mouza under Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001405/2024-2025 | 48/BQA | 02/01/2025 | 333 | GOURANGA NANDI | 14.49 | 0 | 80
4564 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000113/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.5 | 0 | 0
4565 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000290/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.5 | 0 | 0
4566 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00129/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4567 | Bankura Mechanical | Bankura Sadar Sub-Division | Total payable load enhancement charges at Angariaof Nikunjapur Zone-A ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00292/2024-2025 | BP-2024-25-98 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0
4568 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of Quotation for new service connection at Nikunjapurr Zone-A , Mouza -Gamidya.SM/ 17280 | Assistant Engineer | Junior Engineer | BILL/01239/2024-2025 | BP-2024-25-309 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.1 | 0 | 0
4569 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01628/2023-2024 | BP-2023-24-156 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.65 | 0 | 0
4570 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000553/2023-2024 | 1989/BMD | 28/08/2023 | 120 | DEBJYOTI BASU | 60.81 | 29.87 | 70
4571 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase I) at CWR site Gamirda under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001077/2023-2024 | 3056/BMD | 12/03/2024 | 480 | M.S. ENTERPRISE | 40.56 | 0 | 95
4572 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR, Repairing and painting of Over Head Reservoir (Capacity 500 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Gargaria, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2025-2026 | 1010/BQA | 25/04/2025 | 220 | GOUTAM GHOSH | 31.47 | 0 | 0
4573 | Bankura Division | Khatra Sub-Division | Work order for Laying of HDPE pipeline, Construction of Valve Chamber, Construction of Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 1829/BQA | 12/07/2024 | 539 | SWAPAN KUMAR CHANDRA | 62.38 | 0 | 83
4574 | Bankura Division | Khatra Sub-Division | Sinking of 2 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 2 Nos.Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000337/2023-2024 | 1961/BQA | 18/07/2023 | 715 | PRINCE INDUTRIES (INDIA) | 221.68 | 66.56 | 82
4575 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 2959/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.95 | 2.91 | 98
4576 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000183/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.77 | 0 | 0
4577 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00214/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4578 | Bankura Mechanical | Khatra Sub-Division | New Service Connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00382/2024-2025 | BP-2024-25-86 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
4579 | Bankura Mechanical | Khatra Sub-Division | New 3 Phase Service Connection for Gargaria Zone B | Assistant Engineer | Junior Engineer | BILL/00700/2024-2025 | 1BP-2024-25-167 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
4580 | Bankura Mechanical | Khatra Sub-Division | New connection for 3 Gargaria Zone-B, Bikrampur Hatibari , JL-216 Plot-139 | Assistant Engineer | Junior Engineer | BILL/01152/2024-2025 | BP-2024-25-270 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.31 | 0 | 0
4581 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Construction of Guard Piller for cable laying of river bed T/W with allied works for Gargaria Zone-A and Adjoining mouza for Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000320/2024-2025 | 861/BMD | 29/08/2024 | 120 | PRADIP KUMAR DHABAL | 11.13 | 11.12 | 100
4582 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000575/2023-2024 | 2030/BMD | 01/09/2023 | 120 | TAPAN KUMAR DEY | 61.7 | 17.98 | 35
4583 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Gargariya Zone A water supply scheme under Sarenga water supply scheme (BRGF Ph I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/001036/2023-2024 | 2968/BMD | 29/02/2024 | 730 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 37.8 | 18.77 | 40
4584 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries & MCC panel with other electromechanical accessories for Augmentation for Gargariya Zone-B and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001095/2023-2024 | 3070/BMD | 12/03/2024 | 480 | DEBJYOTI BASU | 67.22 | 28.47 | 55
4585 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 03(Enayetpur , Namoghansara , Ekariya ), Total House Hold - 204 |  | Junior Engineer | ORD/000028/2020-2021 | 630/BQA | 10/02/2021 | 30 | AJIT KUMAR PAUL | 15.55 | 0 | 0
4586 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-A ), Total House Hold - 200 |  | Junior Engineer | ORD/000243/2020-2021 | 2051/BQA | 29/12/2020 | 30 | SUBHANKAR BANERJEE | 15.84 | 0 | 0
4587 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 ,Gadardihi (PART-B ), Total House Hold - 115 |  | Junior Engineer | ORD/000245/2020-2021 | 2052/BQA | 29/12/2020 | 30 | BEAUTY CHATTERJEE | 9.12 | 0 | 0
4588 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-C) Total House Hold - 150 |  | Junior Engineer | ORD/000246/2020-2021 | 2053/BQA | 29/12/2020 | 30 | GOURANGA CHATTERJEE | 11.86 | 0 | 0
4589 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 |  | Junior Engineer | ORD/000247/2020-2021 | 2054/BQA | 29/12/2020 | 30 | TAPAS PAL | 12.14 | 0 | 0
4590 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-E), Total House Hold - 114 |  | Junior Engineer | ORD/000249/2020-2021 | 2055/BQA | 29/12/2020 | 30 | BEAUTY CHATTERJEE | 9 | 0 | 0
4591 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gobindapur (Part -A ), Total House Hold - 145 |  | Junior Engineer | ORD/000250/2020-2021 | 2056/BQA | 29/12/2020 | 30 | SUBHANKAR BANERJEE | 11.43 | 0 | 0
4592 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 |  | Junior Engineer | ORD/000251/2020-2021 | 2057/BQA | 29/12/2020 | 30 | AJIT KUMAR PAUL | 12.26 | 0 | 0
4593 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 3.06 | 0
4594 | Bankura Division | Bankura Sadar Sub-Division | Extra retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) of GADARDIHI (Zone- E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora ,Total House Hold -02nos. (Gadhardihi PHC, Jaganathpur SHC) |  | Junior Engineer | ORD/000824/2022-2023 | 215/BSD | 28/02/2023 | 15 | GORAI CONSTRUCTION | 0.92 | 0 | 0
4595 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Gadardihi , Salulia, Joyunga, Joykrishanapur , No Of Mouzas-73 , Total House Hold - 11815 |  | Junior Engineer | VCH/000273/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS DEY | 2.19 | 0 | 0
4596 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-C) Total House Hold - 150 |  | Junior Engineer | VCH/001418/2020-2021 |  | 01/03/2021 | 0 | GOURANGA CHATTERJEE | 10.33 | 0 | 0
4597 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Gadardihi , Salulia, Joyunga, Joykrishanapur , No Of Mouzas-73 , Total House Hold - 11815 |  | Junior Engineer | VCH/001613/2020-2021 |  | 15/03/2021 | 0 | TAPAS DEY | 2.19 | 0 | 0
4598 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
4599 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . Name of mouza -Bandarkoda |  | Junior Engineer | VCH/002418/2021-2022 | FHTC/17 | 17/02/2022 | 0 | SIB SANKAR CHOWDHURY | 4.35 | 0 | 0
4600 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) , Name of mouza -Kodma , (Part-A) |  | Junior Engineer | VCH/002419/2021-2022 | FHTC/17 | 17/02/2022 | 0 | SIB SANKAR CHOWDHURY | 4.35 | 0 | 0
4601 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) |  | Junior Engineer | VCH/002420/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 4.96 | 0 | 0
4602 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) |  | Junior Engineer | VCH/002423/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 3.72 | 0 | 0
4603 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Paryasa (169) & Purnapani Chhota Tung (170) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  | Junior Engineer | VCH/002426/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 2.87 | 0 | 0
4604 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 12) |  | Junior Engineer | VCH/002428/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 4.89 | 0 | 0
4605 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No. 13) |  | Junior Engineer | VCH/002432/2021-2022 | FHTC/17 | 17/02/2022 | 0 | UNITED TRADERS | 4 | 0 | 0
4606 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Palsona more to Ramchandrapur High School under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Palsona & Ramchandrapur |  | Junior Engineer | VCH/002656/2021-2022 | FHTC/10 | 10/02/2022 | 0 | RUFIKUL MONDAL | 4.8 | 0 | 0
4607 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, ( Simla, Bank simul, Nekrakuada ) Total House Hold - 499 |  | Junior Engineer | VCH/003100/2021-2022 | FHTC/28 | 28/03/2022 | 0 | M/S TARUN KUMAR PATRA | 37.54 | 0 | 0
4608 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 26.85 | 0
4609 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I) Name of mouza - 03 nos, Phulberia (PART- B), Sirsa & Joykrishna pur Sarenga (PART- A) |  | Junior Engineer | ORD/000180/2021-2022 | 706/BSD | 17/06/2021 | 10 | M/S T.P. HAZRA & SONS | 3.28 | 0 | 0
4610 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I), Name of mouza- Joykrishna pur Sarenga (PART- B), |  | Junior Engineer | ORD/000181/2021-2022 | 707/BSD | 17/06/2021 | 10 | M/S SUPRIYA CHATTERJEE | 3.74 | 0 | 0
4611 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Sirsha Nutanpally to Palsona more under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Sirsha, Palsona. |  | Junior Engineer | ORD/000182/2021-2022 | 708/BSD | 17/06/2021 | 10 | M/S T.P. HAZRA & SONS | 3.51 | 0 | 0
4612 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 02 ( Bahadur pur , Oltara(PART-A), Total House Hold -141 |  | Junior Engineer | ORD/000281/2020-2021 | 2082/BQA | 29/12/2020 | 30 | RUFIKUL MONDAL | 9.85 | 0 | 0
4613 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140 |  | Junior Engineer | ORD/000282/2020-2021 | 2083/BQA | 29/12/2020 | 30 | GANGADHAR MONDAL | 9.79 | 0 | 0
4614 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 |  | Junior Engineer | ORD/000283/2020-2021 | 2084/BQA | 29/12/2020 | 30 | RUFIKUL MONDAL | 10.79 | 0 | 0
4615 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 |  | Junior Engineer | ORD/000284/2020-2021 | 2085/BQA | 29/12/2020 | 30 | GANGADHAR MONDAL | 10.51 | 0 | 0
4616 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 03, Phulberia(PART-B) , Sirsa & Joykrishna pur Sarenga(PART-A), Total House Hold - 165 |  | Junior Engineer | ORD/000285/2020-2021 | 2086/BQA | 29/12/2020 | 30 | M/S T.P. HAZRA & SONS | 11.55 | 0 | 0
4617 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Joykrishna pur Sarenga(PART-B), Total House Hold - 176 |  | Junior Engineer | ORD/000286/2020-2021 | 2087/BQA | 29/12/2020 | 30 | M/S SUPRIYA CHATTERJEE | 12.29 | 0 | 0
4618 | Bankura Division | Bankura Sadar Sub-Division | Laying distribution system of UPVC pipe line with allied works from Near Beliatore police Station air valve to Oltora Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000328/2021-2022 | 758/ BSD | 26/07/2021 | 15 | ZAKIR HOSSAIN MONDAL | 4.87 | 0 | 0
4619 | Bankura Division | Bankura Sadar Sub-Division | laying distribution system of UPVC pipe line with allied works from Oltotr to Madhavpur Village & Bahadur pur Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000329/2021-2022 | 759/ BSD | 26/07/2021 | 15 | ZAKIR HOSSAIN MONDAL | 4.83 | 0 | 0
4620 | Bankura Division | Bankura Sadar Sub-Division | supplying laying fitting, fixing of HDPE pipe line at Kanchalla village & Samanta mara Adhibasi para under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000376/2022-2023 | 530/BSD | 28/07/2022 | 21 | TARINI CHARAN UPADHYAY | 3.78 | 0 | 0
4621 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000439/2020-2021 | 225/ BSD | 25/02/2021 | 15 | RUFIKUL MONDAL | 4.78 | 0 | 0
4622 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ) |  | Junior Engineer | ORD/000440/2020-2021 | 226/ BSD | 25/02/2021 | 15 | M/S SUPRIYA CHATTERJEE | 2.96 | 0 | 0
4623 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - C ) |  | Junior Engineer | ORD/000441/2020-2021 | 227/ BSD | 25/02/2021 | 15 | M/S T.P. HAZRA & SONS | 3.4 | 0 | 0
4624 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (FunctionalHouse Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - D ) & Saluka |  | Junior Engineer | ORD/000442/2020-2021 | 228/ BSD | 25/02/2021 | 15 | M/S T.P. HAZRA & SONS | 2.72 | 0 | 0
4625 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza - PHULBERIA |  | Junior Engineer | VCH/000733/2021-2022 |  | 27/07/2021 | 0 | GANGADHAR MONDAL | 3.15 | 0 | 0
4626 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipeline of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division under Bankura Division, PHE Dte. block - Barjora , name of OHR - Joykrisnapur (zone - l) name of mouza Oltara part - B sl no - 23 |  | Junior Engineer | VCH/001356/2021-2022 |  | 30/09/2021 | 0 | GANGADHAR MONDAL | 4.52 | 0 | 0
4627 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Joykrishna pur Sarenga(PART-B), Total House Hold - 176 |  | Junior Engineer | VCH/001590/2020-2021 |  | 15/03/2021 | 0 | M/S SUPRIYA CHATTERJEE | 11.6 | 0 | 0
4628 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 03, Phulberia(PART-B) , Sirsa & Joykrishna pur Sarenga(PART-A), Total House Hold - 165 |  | Junior Engineer | VCH/001591/2020-2021 |  | 15/03/2021 | 0 | M/S T.P. HAZRA & SONS | 10.75 | 0 | 0
4629 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 |  | Junior Engineer | VCH/001597/2020-2021 |  | 15/03/2021 | 0 | GANGADHAR MONDAL | 9.52 | 0 | 0
4630 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) |  | Junior Engineer | VCH/002310/2021-2022 | FHTC/20 | 20/01/2022 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 16.51 | 0 | 0
4631 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- (Dadimukha, Saldanga), Total House Hold - 55 nos. |  | Junior Engineer | VCH/002807/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHENDU SEKHAR GORAI | 3.96 | 0 | 0
4632 | Bankura Division | Bankura Sadar Sub-Division | " Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Hapania(Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000619/2023-2024 | 2540/BQA | 11/09/2023 | 90 | BISWARUP BOSE | 48.28 | 0 | 5
4633 | Bankura Division | Bankura Sadar Sub-Division | " Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Hapania(Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000622/2023-2024 | 2541/BQA | 11/09/2023 | 1208 | GOUTAM BHATTACHRYYA | 48.28 | 19.85 | 50
4634 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000137/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.74 | 0 | 0
4635 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000249/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.74 | 0 | 0
4636 | Bankura Division | Bankura Sadar Sub-Division | New service connection at vill-Baishnabpur p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02590/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
4637 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45 | 48
4638 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 02 (Ekteswar (PART ) & Sankardihi. Total House Hold - 452 nos. | Assistant Engineer | Junior Engineer | ORD/000143/2021-2022 | 2808/BQA | 12/11/2021 | 30 | GOUTAM BHOWMIK | 20.52 | 0 | 95
4639 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 01 no., (Ekteswar (PART), Total House Hold - 120 nos. | Assistant Engineer | Junior Engineer | ORD/000480/2021-2022 | 254/BSD | 15/03/2022 | 10 | GOUTAM BHOWMIK | 4.99 | 0 | 0
4640 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 01 Ekteswar (Gogesh Pally), Total House Hold - 85 nos. | Assistant Engineer | Junior Engineer | ORD/000498/2021-2022 | 256/BSD | 15/03/2022 | 1204 | MANOJ GHOSAL | 4.99 | 0 | 0
4641 | Bankura Division | Bankura Sadar Sub-Division | Repair & renovation of chokage pipe line including supply & Installation of Valve etc. of Ekteswar and its adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000748/2022-2023 | 604/BSD | 16/08/2022 | 21 | MANAS DEY | 4.9 | 0 | 0
4642 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 02 ( Kasibediya (PART) & Chingra.) Total House Hold -398 | Assistant Engineer | Junior Engineer | VCH/002727/2021-2022 | FHTC/3 | 03/03/2022 | 0 | KHAN ENTERPRISE | 2.97 | 0 | 0
4643 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 | Assistant Engineer | Junior Engineer | VCH/002728/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BEAUTY CHATTERJEE | 5.1 | 0 | 0
4644 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No.of Mouza :- 01 no., (Bhairabpur (Paschim), Total House Hold -367 nos | Assistant Engineer | Junior Engineer | VCH/002729/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BEAUTY CHATTERJEE | 21.6 | 0 | 0
4645 | Bankura Division | Bankura Sadar Sub-Division | laying Extra UPVC pipeline to cover Koshunda mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kanchanpur (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no work - 08 | Assistant Engineer | Junior Engineer | VCH/002730/2021-2022 | FHTC/3 | 03/03/2022 | 0 | ASHISH KUMAR SAMANTA | 2.77 | 0 | 0
4646 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Kaleberia,Saragara ), Total House Hold -163 | Assistant Engineer | Junior Engineer | VCH/002746/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BEAUTY CHATTERJEE | 1.16 | 0 | 0
4647 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01( Gosainpur ), Total House Hold - 127 | Assistant Engineer | Junior Engineer | VCH/002747/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BEAUTY CHATTERJEE | 0.95 | 0 | 0
4648 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos, (Roybandh), Total House Hold - 168.' | Assistant Engineer | Junior Engineer | VCH/002748/2021-2022 | FHTC/3 | 03/03/2022 | 0 | PRANABANANDA TEWARI | 1.49 | 0 | 0
4649 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002830/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAN KUMAR MANDAL | 13.34 | 0 | 0
4650 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
4651 | Bankura Division | Brishnupur Sub-Division | (site - Ankargeria, deshra , Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00297/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
4652 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4653 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4654 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW CONNECTION AT ANKARGERIA | Assistant Engineer | Junior Engineer | BILL/01279/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
4655 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
4656 | Bankura Division | Brishnupur Sub-Division | Panabhar to Lalbazar ROAD WB-03-12 | Assistant Engineer | Junior Engineer | BILL/01442/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 6.3 | 0 | 0
4657 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PANHAR PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 2742/BQA | 04/10/2023 | 820 | GOPAL CHANDRA CHOWDHURY | 806.18 | 277.51 | 85
4658 | Bankura Division | Brishnupur Sub-Division | Balanced ancillary works for Panahar Water Supply Scheme under Kotulpur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18790) | Assistant Engineer | Junior Engineer | ORD/001946/2024-2025 | 692/BQA | 12/03/2025 | 295 | GOPAL CHANDRA CHOWDHURY | 151.31 | 0 | 85
4659 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 111.45 | 0 | 0
4660 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-III of Panahar W/S scheme | Assistant Engineer | Junior Engineer | BILL/00527/2024-2025 | BP-2024-25-136 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.18 | 0 | 0
4661 | Bankura Mechanical | Brishnupur Sub-Division | New service connection connection at P/H no-I of panahar W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00528/2024-2025 | BP-2024-25-137 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.8 | 0 | 0
4662 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-III of Panahar W/S scheme | Assistant Engineer | Junior Engineer | BILL/00529/2024-2025 | BP-2024-25-138 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.99 | 0 | 0
4663 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Panahar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 2065/BMD | 11/09/2023 | 180 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 59.03 | 27.3 | 46
4664 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4665 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4666 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Kharbani | Assistant Engineer | Junior Engineer | BILL/01572/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.65 | 0 | 0
4667 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.6 | 48
4668 | Bankura Division | Brishnupur Sub-Division | New Connection at Machdoba, Sonamukhi,PHE Dte | Assistant Engineer | Junior Engineer | BILL/00328/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
4669 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4670 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4671 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
4672 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4673 | Bankura Division | RWS Bankura Sub-Division | New Connection at Jasodanandapur, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00429/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
4674 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4675 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
4676 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Barakura site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00192/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
4677 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4678 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4679 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
4680 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000092/2020-2021 | 199/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 38.78 | 3.79 | 0
4681 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 2.83 | 0
4682 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayaerpara (206), Harinarayanpur (207) & Gangnala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000380/2020-2021 | 1780/BQA | 09/12/2020 | 30 | MUNMUN UPADHYAY | 40.17 | 1.52 | 0
4683 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Murku (210) mouza by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000381/2020-2021 | 1781/BQA | 09/12/2020 | 30 | SWAPAN KUMAR UPADHYAY | 12.56 | 0.2 | 85
4684 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kayaerpara (206), Harinarayanpur (207), Murku (210) & Gangnala (230) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 41) |  | Junior Engineer | ORD/000543/2020-2021 | 283/KSD | 10/12/2020 | 1849 | SWAPAN KUMAR UPADHYAY | 0.22 | 0 | 0
4685 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), and Ganganala (230) mouzas Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  | Junior Engineer | VCH/001483/2021-2022 |  | 08/10/2021 | 0 | TARINI CHARAN UPADHYAY | 4.98 | 0 | 0
4686 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  | Junior Engineer | VCH/001484/2021-2022 |  | 08/10/2021 | 0 | SUMITA UPADHYAY | 4.89 | 0 | 0
4687 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) (Part-B) Mouza Chotobankadaha |  | Junior Engineer | VCH/001757/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
4688 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) (Part-B) Mouza Majdiha |  | Junior Engineer | VCH/001758/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.82 | 0 | 0
4689 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) chowbeta mouza, |  | Junior Engineer | VCH/001759/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
4690 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) Mouza - Chakupasole 160 |  | Junior Engineer | VCH/001760/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.78 | 0 | 0
4691 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) Mouza -Asthasole 161, |  | Junior Engineer | VCH/001761/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
4692 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) Mouza Jiabandi, |  | Junior Engineer | VCH/001762/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.58 | 0 | 0
4693 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Sonadaha, Magra, Vangahira mouzs for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001776/2021-2022 | FHTC/28 | 28/10/2021 | 0 | ASHIS PAL | 4.65 | 0 | 0
4694 | Bankura Division | Khatra Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 09) |  | Junior Engineer | VCH/001778/2021-2022 | FHTC/28 | 28/10/2021 | 0 | MUNMUN UPADHYAY | 4.83 | 0 | 0
4695 | Bankura Division | Brishnupur Sub-Division | Repair and Maintenance work of the Road from Palashdanga to T12 under Sonamukhi Block in the District to Bankura ,Vide Package No-WB-03-50, Road Length- 16.80 Km. Scheme code for i) chakai PWSS (ch-3000m to ch- 7100m)- SM/14245 ii) Birsinghapur pwss (ch- 9400m to 12100m)- SM/17223 iii) Dhulai PWSS (Ch-13100m to 16800m)- SM/18753 | Assistant Engineer | Junior Engineer | BILL/01251/2024-2025 | BP-439/2024-25 | 28/11/2024 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 30.91 | 0 | 0
4696 | Bankura Division | Brishnupur Sub-Division | Balance Ancillary Work for ¿Ranibandh¿ and ¿Dhulai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2025-2026 | 1990/BQA | 16/09/2025 | 180 | PRINCE INDUSTRIES (INDIA) | 194.43 | 0 | 15
4697 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHULAI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000741/2023-2024 | 2738/BQA | 04/10/2023 | 910 | PRINCE INDUSTRIES (INDIA) | 910.64 | 410.97 | 72
4698 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2024-2025 | 2943/BQA | 21/11/2024 | 0 | Resource Division | 31.68 | 0 | 0
4699 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 178.78 | 0 | 0
4700 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHULAI (JL NO-14,PLOT-1910)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00011/2024-2025 | BP-2024-25-5 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0
4701 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHULAI (JL NO-14, PLOT-2041/2108LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00021/2024-2025 | BP-2024-25-6 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0
4702 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHALUI (JL NO-14, PLOT-486) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00022/2024-2025 | BP-2024-25-7 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.91 | 0 | 0
4703 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Dhulai Piped water supply scheme Block : Sonamukhi under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000531/2023-2024 | 1930/BMD | 21/08/2023 | 1072 | EASTERN INDIA SALES & SERVICE | 68.77 | 0 | 10
4704 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of JAGDALLA (Zone - S) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (FHTC NO- 500) | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1917/BQA | 13/07/2023 | 1084 | GOUTAM BHOWMIK | 135.16 | 38.7 | 18
4705 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for JAGDALLA (Zone- S2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2023-2024 | 3039/BQA | 06/11/2023 | 30 | K S GROUP | 0.49 | 0 | 0
4706 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001203/2023-2024 | 456/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 2.5 | 0 | 100
4707 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000085/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.79 | 0 | 0
4708 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000246/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.79 | 0 | 0
4709 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00149/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4710 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Chichura mouza of Jagadalla augmentation site under Bankura-I,II & Barjora water supply scheme under BMD PHE dte.(SM/16970) | Assistant Engineer | Junior Engineer | BILL/01359/2024-2025 | BP-2024-25-343 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
4711 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Jagdalla ( Zone-S) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000152/2024-2025 | 495/BMD | 09/07/2024 | 120 | M/S DE ENGINEERING CONCERN | 8.8 | 0 | 0
4712 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Jagadalla (Zone-S) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1466/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.82 | 61.5 | 48
4713 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 |  | Junior Engineer | ORD/000273/2020-2021 | 2072/BQA | 29/12/2020 | 40 | UNIVERSAL CONSTRUCTION | 42.17 | 0 | 60
4714 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kodalia(PART-B), Total House Hold -429 |  | Junior Engineer | ORD/000274/2020-2021 | 2073/BQA | 29/12/2020 | 30 | UNIVERSAL CONSTRUCTION | 42.09 | 0 | 0
4715 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR:- Dhaban No. of Mouza :- Kumirdoha (PART-) , Gairabad (part) Total House Hold - 65., |  | Junior Engineer | VCH/001157/2021-2022 | FHTC/19 | 19/07/2021 | 0 | LABIR MIRSHAD KHAN | 2.25 | 0 | 0
4716 | Bankura Division | Bankura Sadar Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm, under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 28) |  | Junior Engineer | VCH/001158/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.22 | 0 | 0
4717 | Bankura Division | Bankura Sadar Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) , |  | Junior Engineer | VCH/001159/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.21 | 0 | 0
4718 | Bankura Division | Bankura Sadar Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) with Jal Jeevan Mission (JJM) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 13) |  | Junior Engineer | VCH/001160/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.35 | 0 | 0
4719 | Bankura Division | Bankura Sadar Sub-Division | House hold survey in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) |  | Junior Engineer | VCH/001161/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.39 | 0 | 0
4720 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) |  | Junior Engineer | VCH/001162/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.35 | 0 | 0
4721 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) |  | Junior Engineer | VCH/001163/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.15 | 0 | 0
4722 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 16) , |  | Junior Engineer | VCH/001164/2021-2022 | FHTC/19 | 19/07/2021 | 0 | TAPAS DEY | 0.23 | 0 | 0
4723 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chanpasol (78) mouzas by Retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF Ph-I) at Block- Hirrbandh , Dist Bankura under Jal Swapna & Jal Jeevan mission programme under Khatra Sub-Division of Bankura Division PHE Dte. (Part-D) Sl No-11 |  | Junior Engineer | VCH/001169/2021-2022 | FHTC/23 | 23/07/2021 | 0 | GOURANGA CHATTERJEE | 3.61 | 0 | 0
4724 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kodalia(PART-B), Total House Hold -429 |  | Junior Engineer | VCH/001617/2020-2021 |  | 15/02/2021 | 0 | UNIVERSAL CONSTRUCTION | 34.91 | 0 | 0
4725 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
4726 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
4727 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 06 nos, (Agaya , Pachasimul, Mechabaid , Banjurya, Haridi, Tentulberia) Total House Hold - 436 | Assistant Engineer | Junior Engineer | ORD/000047/2021-2022 | 1928/BQA | 27/07/2021 | 30 | SWAPAN KUMAR UPADHYAY | 32.04 | 4.98 | 0
4728 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Paharbedia, Nangla, Bharatpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A). | Assistant Engineer | Junior Engineer | ORD/000266/2021-2022 | 806/ BSD | 06/08/2021 | 15 | APEX ENTERPRISE | 4.99 | 0 | 0
4729 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Paharbedia, Nangla, Bharatpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B). | Assistant Engineer | Junior Engineer | ORD/000267/2021-2022 | 807/ BSD | 06/08/2021 | 15 | BHATTACHARYYA ENTERPRISE | 4.99 | 0 | 0
4730 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Paharbedia, Nangla, Bharatpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/000268/2021-2022 | 808/ BSD | 06/08/2021 | 15 | BHATTACHARYYA ENTERPRISE | 4.19 | 3.99 | 100
4731 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line from Parulia Nadi Ghat to Pechasimul Village to increase water pressure at pechasimul Mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of of Kalipur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project)under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000743/2022-2023 | 631/BQA | 24/03/2023 | 45 | RAHIBUDDIN MANDAL | 10.93 | 10.8 | 100
4732 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART-A) | Assistant Engineer | Junior Engineer | VCH/002372/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0
4733 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Purnapani (89) & Pirargari (95) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) | Assistant Engineer | Junior Engineer | VCH/002373/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DAUD ALI KHAN | 1.35 | 0 | 0
4734 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | VCH/002374/2021-2022 | FHTC/28 | 28/01/2022 | 0 | DAUD ALI KHAN | 4.26 | 0 | 0
4735 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line from Mukuti Village Tematha more to Jorjhal Roypara of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), | Assistant Engineer | Junior Engineer | VCH/002619/2021-2022 | FHTC/24 | 24/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.97 | 0 | 0
4736 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line from Jorjhal Roypara to Barabendya High School of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), | Assistant Engineer | Junior Engineer | VCH/002622/2021-2022 | FHTC/24 | 24/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.96 | 0 | 0
4737 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Kostia mouza of Retrofitting works for creation of 'FHTC (Func tional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002623/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BISWESWAR CONSTRUCTION | 3.22 | 0 | 0
4738 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line to cover Bearabendya mouza of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002626/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BISWESWAR CONSTRUCTION | 3.9 | 0 | 0
4739 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . Name.of Mouza :- Maitha Gopinathpur | Assistant Engineer | Junior Engineer | VCH/002628/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BISWESWAR CONSTRUCTION | 4.93 | 0 | 0
4740 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone- H), Name of Mouza :- Bonomadhavpur | Assistant Engineer | Junior Engineer | VCH/002630/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BISWESWAR CONSTRUCTION | 4.85 | 0 | 0
4741 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03 nos, (Gajariabari, Maslia, Chaitali), Total House Hold - 167.' | Assistant Engineer | Junior Engineer | VCH/002631/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SHYAMAL KUMAR DAS | 1.43 | 0 | 0
4742 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
4743 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-A ) , Total House Hold -124 ( Sl .No.- 1) | Assistant Engineer | Junior Engineer | ORD/000154/2020-2021 | 700/BQA | 19/02/2021 | 30 | SUBHADIP KOLEY | 11.2 | 0 | 0
4744 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-B) , Total House Hold -130 ( Sl .No.- 02 ) | Assistant Engineer | Junior Engineer | ORD/000155/2020-2021 | 701/BQA | 19/02/2021 | 30 | BIJOY KOLEY | 11.89 | 0 | 0
4745 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-C) , Total House Hold -118 ( Sl .No.- 03 ) | Assistant Engineer | Junior Engineer | ORD/000156/2020-2021 | 702/BQA | 19/02/2021 | 30 | SUBHADIP KOLEY | 10.61 | 0 | 0
4746 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-D) , Total House Hold -118 ( Sl .No.- 04 ) | Assistant Engineer | Junior Engineer | ORD/000157/2020-2021 | 703/BQA | 19/02/2021 | 30 | SANDHYA DEY | 10.82 | 0 | 0
4747 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Dhwajmonipur (PART-A) , Total House Hold -123 ( Sl .No.- 05) | Assistant Engineer | Junior Engineer | ORD/000158/2020-2021 | 704/BQA | 19/02/2021 | 30 | ASHOKE KUMAR DEY | 11.28 | 0 | 0
4748 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Dakaisini, Bansol, Dhwajmonipur (PART-B)), Total House Hold -120 ( Sl .No.- 6 ) | Assistant Engineer | Junior Engineer | ORD/000159/2020-2021 | 705/BQA | 19/02/2021 | 30 | ASHOKE KUMAR DEY | 11.91 | 0 | 0
4749 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Damodarpur), Total House Hold -226 ( Sl .No.- 7) | Assistant Engineer | Junior Engineer | ORD/000160/2020-2021 | 706/BQA | 19/02/2021 | 30 | SARKAR CONSTRUCTION | 20.5 | 0 | 0
4750 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE, GI & MS pipe line from rising main air valve near Fulberia to Damodar pur, Nirsha, Bansol, Dhwajmonipur & Kalapani mouza to increase pressure along with all allied works of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 2237/BQA | 09/12/2022 | 45 | PRADYUMNA KOLEY | 28.16 | 0 | 0
4751 | Bankura Division | Bankura Sadar Sub-Division | Extra 4 nos Sluice vaive chamber, fitting & existing pipe line repering near Fulberia to Damodar pur, Nirsha, Bansol, Dhwajmonipur & Kalapani mouza long with all allied works of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 526/BSD | 12/06/2023 | 15 | SUBHADIP KOLEY | 0.95 | 0 | 100
4752 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
4753 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. | Assistant Engineer | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
4754 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Rajsol (41) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - A Sl no - 16 | Assistant Engineer | Junior Engineer | VCH/002678/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S TARUN KUMAR PATRA | 4.23 | 0 | 0
4755 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jaynagar (47) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - B | Assistant Engineer | Junior Engineer | VCH/002682/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S TARUN KUMAR PATRA | 2.74 | 0 | 0
4756 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Sanabandh), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Sanabandh) Total House Hold - 937 nos. | Assistant Engineer | Junior Engineer | VCH/002685/2021-2022 | FHTC/2 | 02/03/2022 | 0 | NEW STAR CONSTRUCTION | 45.07 | 0 | 0
4757 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhuchu Dungri (61) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002724/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 0.28 | 0 | 0
4758 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | ORD/000064/2021-2022 | 2198/BQA | 25/08/2021 | 30 | M/S TARUN KUMAR PATRA | 112.13 | 0 | 0
4759 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- Kamalpur (part), Total House Hold :-90 nos. |  | Junior Engineer | ORD/000227/2022-2023 | 248/KSD | 12/07/2022 | 15 | M/S TARUN KUMAR PATRA | 3.87 | 0 | 0
4760 | Bankura Division | Bankura Sadar Sub-Division | Laying UPVC pipe line from rising main air valve (near Ragametia) to Chhatapathor village to increase water pressure to Chhatapathor village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000307/2022-2023 | 362/KSD | 29/08/2022 | 20 | DAUD ALI KHAN | 3.03 | 3.03 | 0
4761 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Barabeda more to Mantumura & Patjuri Agaya to Kunkhri Basa to increase water pressure at Kunkhri Basa, Mantumura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000494/2022-2023 | 382/BQA | 23/02/2023 | 45 | SAIKAT CHOWDHURY | 12.25 | 11.88 | 80
4762 | Bankura Division | Bankura Sadar Sub-Division | Inter connection with rising main air valve to distribution line at two points near Barabeda & Ragametia village to increase water pressure of Subarda, Simla, Mantumura, Patju agaya, Ragametia of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000756/2022-2023 | 370/KSD | 29/08/2022 | 20 | DAUD ALI KHAN | 3.01 | 3 | 100
4763 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ), Total House Hold - 65 |  | Junior Engineer | VCH/000507/2021-2022 |  | 08/06/2021 | 0 | RAFIKUL MONDAL | 3.52 | 0 | 0
4764 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamberia (179) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household - 160 Nos. |  | Junior Engineer | VCH/002629/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAS GHOSH | 10.78 | 0 | 0
4765 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line from Maliara OHR site to Pingrui to increase pressure for mouza - Pingrui of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. part - B |  | Junior Engineer | VCH/002632/2021-2022 | FHTC/24 | 24/02/2022 | 0 | M/S NAYAN BARDHAN | 4.85 | 0 | 0
4766 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line from Maliara OHR site to Pingrui to increase pressure for mouza - Pingrui of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. part - A sl no - 23 |  | Junior Engineer | VCH/002633/2021-2022 | FHTC/24 | 24/02/2022 | 0 | M/S NAYAN BARDHAN | 4.78 | 0 | 0
4767 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002762/2021-2022 | FHTC/4 | 04/03/2022 | 0 | MUNMUN UPADHYAY | 34.71 | 0 | 0
4768 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  | Junior Engineer | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 0 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0
4769 | Bankura Division | RWS Bankura Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 ( Upardihi & Kulmura.) Total House Hold - 441" |  | Junior Engineer | ORD/000389/2020-2021 | 1789/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0
4770 | Bankura Division | RWS Bankura Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 03 (Khejurbedia, Radhanagar(part) & Bagrakonda,) Total House Hold - 287" |  | Junior Engineer | ORD/000390/2020-2021 | 1790/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 27.62 | 0 | 0
4771 | Bankura Division | RWS Bankura Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 Radhanagar(part) & Maukara,) Total House Hold - 280" |  | Junior Engineer | ORD/000391/2020-2021 | 1791/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 26.74 | 0 | 0
4772 | Bankura Division | RWS Bankura Sub-Division | Laying HDPE Pipe Line from bakhulia to 7 Anaparato increase pressure for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000542/2022-2023 | 602/BSD | 16/08/2022 | 21 | BIDHAN BANERJEE | 4.9 | 0 | 0
4773 | Bankura Division | RWS Bankura Sub-Division | Laying extra UPVC pipe line to cover Khejurbedia, Radhanagar, Bagrakonda, Upardihi Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/000130/2021-2022 |  | 21/04/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.37 | 0 | 0
4774 | Bankura Division | RWS Bankura Sub-Division | Survey work Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 06 nos, (Khejurbedia, Upardihi, Radhanagar, Bagrakonda, Moukura & Kulmura.) Total House Hold - 1008. |  | Junior Engineer | VCH/001342/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.32 | 0 | 0
4775 | Bankura Division | RWS Bankura Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
4776 | Bankura Division | RWS Bankura Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 05 Nos. Total Household - 853 Nos. ' |  | Junior Engineer | VCH/002506/2021-2022 | FHTC/3 | 03/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 43 | 0 | 0
4777 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Dakai (268), Karra (269) & Madhabpur (252) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000064/2022-2023 | 1688/BQA | 27/07/2022 | 30 | TARINI CHARAN UPADHYAY | 10.37 | 9.54 | 0
4778 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Labdapara (265) & Birkham (266) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2022-2023 | 1690/BQA | 27/07/2022 | 30 | PARTHA PRATIM CHHATAIT | 6.2 | 0 | 0
4779 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) | Assistant Engineer | Junior Engineer | ORD/000289/2020-2021 | 30/KSD | 15/01/2021 | 20 | S. K. ENTERPRISE | 4.82 | 0 | 0
4780 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000290/2020-2021 | 31/KSD | 15/01/2021 | 20 | D. S. ENTERPRISE | 4.84 | 0 | 0
4781 | Bankura Division | Khatra Sub-Division | Supply laying & fitting fixing of MS pipe line crossing at Tentulpoha jore & repairing of existing UPVC pipe connection for Tentulpoha village for Maliara (Zone -A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) | Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 557/BSD | 29/07/2022 | 30 | SAMIRUDDIN KHAN | 2.85 | 2.24 | 0
4782 | Bankura Division | Khatra Sub-Division | Household survey in different mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chhatna-Block Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002664/2021-2022 | FHTC/2 | 02/03/2022 | 0 | TAPAS DEY | 1.9 | 0 | 0
4783 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dakai (268) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000305/2020-2021 | 32/KSD | 15/01/2021 | 20 | D. S. ENTERPRISE | 3.81 | 0 | 0
4784 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dakai (268) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | ORD/000306/2020-2021 | 33/KSD | 15/01/2021 | 20 | S. K. ENTERPRISE | 3.8 | 0 | 0
4785 | Bankura Division | Khatra Sub-Division | Restoration & renovation 100 mm dia connecting line carrying structure including all related works & Clearing the chokage of upvc line Durlavpur to Bhubanbadhi, interconnection with BRGF Line for W/S arrangement at Salma Zone- III including contruction of valve chamber at Salma zone-II Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 469/BSD | 06/06/2022 | 15 | DAUD ALI KHAN | 4.95 | 4.93 | 0
4786 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dakai (268) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 5) | Assistant Engineer | Junior Engineer | ORD/000307/2020-2021 | 34/KSD | 15/01/2021 | 20 | S. K. ENTERPRISE | 3.09 | 0 | 0
4787 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Karra (269) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) | Assistant Engineer | Junior Engineer | ORD/000309/2020-2021 | 35/KSD | 15/01/2021 | 20 | ASOKE KUMAR SAHU | 3.72 | 0 | 65
4788 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000312/2020-2021 | 36/KSD | 15/01/2021 | 20 | UTTAM KUMAR SINHAMAHAPATRA | 2.98 | 0 | 90
4789 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000315/2020-2021 | 37/KSD | 15/01/2021 | 20 | UTTAM KUMAR SINHAMAHAPATRA | 3.22 | 0 | 25
4790 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (267) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | ORD/000320/2020-2021 | 38/KSD | 15/01/2021 | 20 | TAPAN KUMAR MANDAL | 4.78 | 0 | 0
4791 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (267) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000325/2020-2021 | 39/KSD | 15/01/2021 | 20 | SUNIL KUMAR MANDAL | 4.7 | 0 | 0
4792 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (252), Labdapara (265) & Birkham (266) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000327/2020-2021 | 40/KSD | 15/01/2021 | 20 | UTTAM KUMAR SINHAMAHAPATRA | 4.54 | 0 | 20
4793 | Bankura Division | Khatra Sub-Division | Work Order for Laying additional 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, PN16) pipe to cover Dakai (268) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) | Assistant Engineer | Junior Engineer | ORD/000332/2021-2022 | 726/KSD | 12/11/2021 | 15 | ASOKE KUMAR SAHU | 2.08 | 0 | 0
4794 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 28) | Assistant Engineer | Junior Engineer | ORD/000531/2020-2021 | 329/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.23 | 0 | 0
4795 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SANJOY MONDAL | 4.55 | 0 | 0
4796 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Hetiasol (271), Dakai (268) & Karra (269) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) | Assistant Engineer | Junior Engineer | VCH/001326/2021-2022 |  | 28/09/2021 | 0 | ASOKE KUMAR SAHU | 2.2 | 0 | 0
4797 | Bankura Division | Khatra Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jharia (267) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12) | Assistant Engineer | Junior Engineer | VCH/001327/2021-2022 |  | 28/09/2021 | 0 | TAPAN KUMAR MANDAL | 0.74 | 0 | 0
4798 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
4799 | Bankura Division | Khatra Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
4800 | Bankura Division | Khatra Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | Assistant Engineer | Junior Engineer | VCH/001739/2020-2021 |  | 19/03/2021 | 0 | TAPAS DEY | 0.22 | 0 | 0
4801 | Bankura Division | Khatra Sub-Division | Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/002299/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0
4802 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 14) | Assistant Engineer | Junior Engineer | VCH/002662/2021-2022 | FHTC/2 | 02/03/2022 | 0 | KOUSIK MONDAL | 0.33 | 0 | 0
4803 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 15) | Assistant Engineer | Junior Engineer | VCH/002663/2021-2022 | FHTC/2 | 02/03/2022 | 0 | KOUSIK MONDAL | 0.09 | 0 | 0
4804 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 03 (Darpanagar, Urama & Pathrabid,, Total House Hold - 464 | Assistant Engineer | Junior Engineer | VCH/002665/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PRINCE INDUTRIES (INDIA) | 0.24 | 0 | 0
4805 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Elia Narayan pur , Rautora), Total House Hold -158 | Assistant Engineer | Junior Engineer | VCH/002666/2021-2022 | FHTC/2 | 02/03/2022 | 0 | DAUD ALI KHAN | 0.75 | 0 | 0
4806 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 01, (Kesekol (PART), Total House Hold - 517 ( Sl .No.- 20 ) | Assistant Engineer | Junior Engineer | VCH/002667/2021-2022 | FHTC/2 | 02/03/2022 | 0 | PARAMESWAR CHOWDHURY | 2.49 | 0 | 0
4807 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-A ) , Total House Hold -124 ( Sl .No.- 1) | Assistant Engineer | Junior Engineer | VCH/002670/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SUBHADIP KOLEY | 0.89 | 0 | 0
4808 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :01 , Hare Krishnapur (Part-- B), Total House Hold -101 | Assistant Engineer | Junior Engineer | VCH/002673/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOURANGA NANDI | 0.6 | 0 | 0
4809 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Gaira, Arjunpur, Pairasol, & Bahadurpur.) Total House Hold - 50 | Assistant Engineer | Junior Engineer | VCH/002676/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 1.39 | 0 | 0
4810 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Hetiasol (271) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - llB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. sl no - 20 | Assistant Engineer | Junior Engineer | VCH/003043/2021-2022 | FHTC/27 | 27/03/2022 | 0 | ASOKE KUMAR SAHU | 1.44 | 0 | 0
4811 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilna (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna (Zone - E), No. of Mouza :- 01 Ethani (Part), Total House Hold :- 17 nos. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 101/KSD | 28/04/2023 | 30 | TAPAS KUMBHAKAR | 0.95 | 0.93 | 100
4812 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | ORD/000207/2020-2021 | 806/BQA | 23/02/2021 | 30 | SOUMITRA BHATTACHARYA | 42.52 | 0 | 0
4813 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 | Assistant Engineer | Junior Engineer | ORD/000208/2020-2021 | 807/BQA | 23/02/2021 | 30 | M/S BIPUL BANERJEE | 42.82 | 0 | 0
4814 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01 no (Pinguri (Part-A ), Total House Hold -420 | Assistant Engineer | Junior Engineer | VCH/001459/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SUBHANKAR BANERJEE | 2.06 | 0 | 0
4815 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 03 nos, ( Ampahari, Gopinathpur, Chakchaki,) Total House Hold - 518 | Assistant Engineer | Junior Engineer | VCH/001489/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SUMITA UPADHYAY | 32.36 | 0 | 0
4816 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sindurpeti (239), Tiring (244), Parashi Danga (247), Khayerbani (248) Bagakhulia (249) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001501/2021-2022 | FHTC/23 | 23/11/2021 | 0 | EARTH MOVING (INDIA) | 11.93 | 0 | 0
4817 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 05 , Kolaberia (PART- A ) ,Bandarkhola, Ramharipur, Katapesia, Maitha Gopinathpur ), Total House Hold -426 | Assistant Engineer | Junior Engineer | VCH/001513/2021-2022 | FHTC/23 | 23/11/2021 | 0 | UNIVERSAL CONSTRUCTION | 6.09 | 0 | 0
4818 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Buriam (112) & Haludkanali (113) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 02 Nos. Total Household - 420 Nos. | Assistant Engineer | Junior Engineer | VCH/001519/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SUBHADIP KOLEY | 27.61 | 0 | 0
4819 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 | Assistant Engineer | Junior Engineer | VCH/001750/2021-2022 | FHTC/23 | 23/11/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 74.71 | 0 | 0
4820 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000347/2020-2021 | 1772/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 23.94 | 22.56 | 20
4821 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Kulpat, Kesia,& Bhedua(Part), Total House Hold - 435" |  | Junior Engineer | ORD/000382/2020-2021 | 1782/BQA | 09/12/2020 | 30 | PARTHA PRATIM CHATAIT | 39.65 | 0 | 100
4822 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Badra,Gopalpur, Bhedua(Part), Total House Hold - 435" |  | Junior Engineer | ORD/000383/2020-2021 | 1783/BQA | 09/12/2020 | 30 | GOUTAM BHOWMIK | 39.71 | 0 | 100
4823 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Khejurbedia, Radhanagar, Bagrakonda, Upardihi Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  | Junior Engineer | VCH/001132/2021-2022 | FHTC/23 | 23/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 3.37 | 0 | 0
4824 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , |  | Junior Engineer | VCH/001133/2021-2022 | FHTC/23 | 23/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0
4825 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 05) |  | Junior Engineer | VCH/002508/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SHOVAN DEY | 0.56 | 0 | 0
4826 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 06) |  | Junior Engineer | VCH/002509/2021-2022 | FHTC/3 | 03/02/2022 | 0 | M/S NAYAN BARDHAN | 0.59 | 0 | 0
4827 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01(Kuldiha ), Total House Hold -233 |  | Junior Engineer | VCH/002510/2021-2022 | FHTC/3 | 03/02/2022 | 0 | TAPAS PAL | 2.49 | 0 | 0
4828 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos, (Ramdihi, Choto Kalajharia, Radharaman Pur, Barokalojuria, ), Total House Hold - 429.' |  | Junior Engineer | VCH/002668/2021-2022 | FHTC/2 | 02/03/2022 | 0 | BISWARUP BOSE | 2.84 | 0 | 0
4829 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Asansola (Part- B), Total House Hold -169 |  | Junior Engineer | VCH/002669/2021-2022 | FHTC/2 | 02/03/2022 | 0 | DAUD ALI KHAN | 0.48 | 0 | 0
4830 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-A ) , Total House Hold -124 ( Sl .No.- 1) |  | Junior Engineer | VCH/002670/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SUBHADIP KOLEY | 0.89 | 0 | 0
4831 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 nos (Mobarakpur, Agra, Adra & Sirsara) Total House Hold - 605" |  | Junior Engineer | ORD/000342/2020-2021 | 1767/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 44.33 | 0 | 100
4832 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 nos (Chapatara & Sendra) Total House Hold - 604 " |  | Junior Engineer | ORD/000396/2020-2021 | 1766/BQA | 09/12/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 44.28 | 0 | 100
4833 | Bankura Division | Bankura Sadar Sub-Division | Extension of UPVC distribution pipeline of Cherabastar (Zone - K) to cover Sapargara village under Bankura - I, II & Barjora w/s scheme |  | Junior Engineer | VCH/000137/2021-2022 |  | 21/04/2021 | 0 | SUBHADIP KOLEY | 4.27 | 0 | 0
4834 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 06 nos, (Mobarakpur, Chaptara, Sendra, Agra, Adra & Sirsraa.) Total House Hold - 1209. |  | Junior Engineer | VCH/001344/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
4835 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605" |  | Junior Engineer | VCH/001389/2020-2021 |  | 01/03/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 37.19 | 0 | 0
4836 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
4837 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Penchakola (298) & Dubli (299) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3904) |  | Junior Engineer | VCH/001537/2020-2021 | FHTC/280 | 12/02/2021 | 0 | SIB SANKAR CHOWDHURY | 24.39 | 0 | 0
4838 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Gotkanali (45) , Bankhola (54) & Harinyaguri (90) mouza by retrofitting zone - ll piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3949) |  | Junior Engineer | VCH/001540/2020-2021 | FHTC/268 | 05/02/2021 | 0 | APEX ENTERPRISE | 19.97 | 0 | 0
4839 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part - E) , total house hold - 114 ( MB No - 4025)" |  | Junior Engineer | VCH/001542/2020-2021 | FHTC/276 | 08/02/2021 | 0 | BEAUTY CHATTERJEE | 7.76 | 0 | 0
4840 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part - B) , total house hold - 115 ( MB No - 4025)" |  | Junior Engineer | VCH/001543/2020-2021 | FHTC/276 | 08/02/2021 | 0 | BEAUTY CHATTERJEE | 7.76 | 0 | 0
4841 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Panchal w/s scheme (zone - l) under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (Part - A) , total house hold - 72 ( MB No - 3318)" |  | Junior Engineer | VCH/001544/2020-2021 | FHTC/276 | 08/02/2021 | 0 | MOHAN KUMAR ROY | 4.61 | 0 | 0
4842 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Radhanagar w/s scheme (zone - l) under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (Part - B) , total house hold -6 7 ( MB No - 3981)" |  | Junior Engineer | VCH/001545/2020-2021 | FHTC/276 | 08/02/2021 | 0 | SIB SANKAR CHOWDHURY | 4.64 | 0 | 0
4843 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108) Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2020-2021 | 482/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 16.61 | 16.26 | 0
4844 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover kherosol, Bhedua Purusatampur, narrah, gopinathpur, emukundi mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000216/2021-2022 | 821/BSD | 06/08/2021 | 15 | BHATTACHARYYA ENTERPRISE | 2.56 | 0 | 0
4845 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover kherosal mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATERKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2021-2022 | 820/BSD | 06/08/2021 | 15 | BHATTACHARYYA ENTERPRISE | 4.83 | 0 | 0
4846 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527." | Assistant Engineer | Junior Engineer | ORD/000343/2020-2021 | 1768/BQA | 09/12/2020 | 30 | GOUTAM BHATTACHRYYA | 37.17 | 0 | 0
4847 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 04 nos, (Talandanga, Upar Narrah, Chhatarkanali, Rampur, ), Total House Hold - 530." | Assistant Engineer | Junior Engineer | ORD/000344/2020-2021 | 1769/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 37.35 | 0 | 100
4848 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Beliatore under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001896/2020-2021 | FHTC/290 | 03/03/2021 | 0 | ASHISH PAUL | 4.56 | 0 | 0
4849 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATERKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chaterkanali, No. of Mouza :- 02 no., Gopinathpur & bhedua, Total House Hold- 45 nos. | Assistant Engineer | Junior Engineer | ORD/000662/2021-2022 | 259/BSD | 15/03/2022 | 10 | SELCO | 3.27 | 0 | 100
4850 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 07 nos, (Talandanga, Upar Narrah, Kherosol, Chhatarkanali, Rampur, Emokundi & Gopinathpur), Total House Hold - 1057. | Assistant Engineer | Junior Engineer | VCH/001346/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.3 | 0 | 0
4851 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 (Junbedia(PART), Total House Hold - 441 . ( MB No - 4002)" | Assistant Engineer | Junior Engineer | VCH/001538/2020-2021 | FHTC/280 | 12/02/2021 | 0 | PARTHA PRATIM CHATAIT | 23.67 | 0 | 0
4852 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 | Assistant Engineer | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
4853 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, (Patdoha) Total House Hold - 489 | Assistant Engineer | Junior Engineer | VCH/002315/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SUBHANKAR BANERJEE | 27.3 | 0 | 0
4854 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 | Assistant Engineer | Junior Engineer | VCH/002316/2021-2022 | FHTC/20 | 20/01/2022 | 0 | I.R.CONSTRUCTION | 9.24 | 0 | 0
4855 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. | Assistant Engineer | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
4856 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 09 Nos. ( Dhobagram, Chila bakra, Nayabadi, Sagunsora, Bhaluk geza, Shyampur, Khap, Shusunia & Dubraji) Total House Hold - 1055 |  | Junior Engineer | ORD/000041/2020-2021 | 643/BQA | 10/02/2021 | 290 | GOPAL CHANDRA CHOUDHURY | 91.82 | 0 | 0
4857 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part) Total House Hold - 75 (Sl No of Work- 06) |  | Junior Engineer | ORD/000081/2020-2021 | 98/ BSD | 12/02/2021 | 20 | MANAS DEY | 4.72 | 8.75 | 0
4858 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 09 Nos. ( Bhagabanpur,Baindhka, Bhaturi, Jharia, Makarkendi, Rajkumar, Sibarampur, Dakhin bonkati & Kendhkun. ) Total House Hold - 1050 | Assistant Engineer | Junior Engineer | ORD/000408/2020-2021 | 403/BQA | 04/02/2021 | 290 | GOPAL CHANDRA CHOUDHURY | 94.22 | 0 | 0
4859 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Bhagabanpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2020-2021 | 836/BSD | 18/08/2020 | 15 | SUBHADIP KOLEY | 4.26 | 4.19 | 0
4860 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Baindaka mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000561/2021-2022 | 835/BSD | 18/08/2021 | 15 | GOPAL CHANDRA CHOWDHURY | 4.59 | 2.31 | 0
4861 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Bhaturi mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000562/2021-2022 | 837/BSD | 18/08/2021 | 15 | GOPAL CHANDRA CHOWDHURY | 4.82 | 4.22 | 0
4862 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2020-2021 | 193/BQA | 18/01/2021 | 30 | PARAMESWAR CHOWDHURY | 43.02 | 0 | 0
4863 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) | Assistant Engineer | Junior Engineer | ORD/000525/2020-2021 | 323/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.21 | 0 | 0
4864 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline, construction and commissioning of FHTC (Functional House Hold Tap Connection), Construction of platform with all allied works of Ashatara (Zone -CE) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001128/2023-2024 | 261/BQA | 30/01/2024 | 428 | TAPAS KUMAR HAZRA | 9.97 | 7.42 | 40
4865 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, | Assistant Engineer | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
4866 | Bankura Division | Khatra Sub-Division | House hold survey of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/001738/2020-2021 |  | 19/03/2021 | 0 | TAPAS DEY | 0.21 | 0 | 0
4867 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Kastara), Total House Hold - 345 nos. | Assistant Engineer | Junior Engineer | ORD/000144/2021-2022 | 2809/BQA | 12/11/2021 | 30 | SANDHYA DEY | 15.22 | 0 | 0
4868 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Rangamati), Total House Hold - 213 nos. | Assistant Engineer | Junior Engineer | ORD/000145/2021-2022 | 2810/BQA | 12/11/2021 | 30 | GOURANGA NANDI | 10.76 | 0 | 0
4869 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Kendana), Total House Hold - 272 nos. | Assistant Engineer | Junior Engineer | ORD/000146/2021-2022 | 2811/BQA | 12/11/2021 | 30 | SK. SAHAJAHAN | 12.79 | 0 | 0
4870 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Sat Deuli), Total House Hold - 151 nos. | Assistant Engineer | Junior Engineer | ORD/000147/2021-2022 | 2812/BQA | 12/11/2021 | 30 | LABIR MIRSHAD KHAN | 7.31 | 0 | 0
4871 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipeline from OHR Zone- III to Kendana village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2022-2023 | 542/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.68 | 0 | 0
4872 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipe from Pabra more to Sat-deuli village due to damage by PWD Road for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2022-2023 | 558/BSD | 29/07/2022 | 21 | LABIR MIRSHAD KHAN | 2.12 | 0 | 0
4873 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. | Assistant Engineer | Junior Engineer | ORD/000490/2021-2022 | 220/BSD | 11/03/2022 | 10 | S K FAZLUL ALAM | 4.87 | 0 | 0
4874 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kenana), Total House Hold- 35 nos. | Assistant Engineer | Junior Engineer | ORD/000529/2021-2022 | 221/BSD | 11/03/2022 | 10 | SK. ALAMAGIR ALAM | 2.15 | 0 | 95
4875 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete at Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE- III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000531/2021-2022 | 280/BSD | 17/03/2022 | 10 | SK. ALAMAGIR ALAM | 0.87 | 0 | 0
4876 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line & extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2021-2022 | 273/BSD | 17/03/2022 | 10 | SK. SAHAJAHAN | 3.63 | 0 | 0
4877 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Rangamati), Total House Hold- 43 nos. | Assistant Engineer | Junior Engineer | ORD/000659/2021-2022 | 219/BSD | 11/03/2022 | 10 | GOURANGA NANDI | 2.16 | 0 | 0
4878 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Rangamatia mouza for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma Zone III under Saltora Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000230/2022-2023 | FHTC/11 | 11/04/2022 | 0 | GOURANGA NANDI | 4.94 | 0 | 0
4879 | Bankura Division | Bankura Sadar Sub-Division | Dismantiling & reconstruction of concrte of Rangamatia mouza for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma Zone III under Saltora Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.(Sl. No. 23) | Assistant Engineer | Junior Engineer | VCH/000231/2022-2023 | FHTC/11 | 11/04/2022 | 0 | GOURANGA NANDI | 4.83 | 0 | 0
4880 | Bankura Division | Bankura Sadar Sub-Division | Survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA & adjoining mouzas (Zone- III) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, G.P. - Salma, No.of Mouza :- 04 nos, (Kastara, Rangamati, Kendana, Sat-deuli), Total House Hold - 981 nos. | Assistant Engineer | Junior Engineer | VCH/000256/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.33 | 0 | 0
4881 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. | Assistant Engineer | Junior Engineer | VCH/000661/2022-2023 | FHTC/27 | 27/09/2022 | 0 | S K FAZLUL ALAM | 4.81 | 0 | 0
4882 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No.of Mouza :- 01 no., (Bhairabpur (Paschim), Total House Hold -367 nos | Assistant Engineer | Junior Engineer | VCH/002729/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BEAUTY CHATTERJEE | 21.6 | 0 | 0
4883 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Rangamati), Total House Hold - 213 nos. | Assistant Engineer | Junior Engineer | VCH/002866/2021-2022 | FHTC/15 | 15/03/2022 | 0 | GOURANGA NANDI | 10.75 | 0 | 0
4884 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Rangamatia mouza for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma Zone III under Saltora Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002882/2021-2022 |  | 16/03/2022 | 0 | GOURANGA NANDI | 4.94 | 0 | 0
4885 | Bankura Division | Bankura Sadar Sub-Division | Dismantiling & reconstruction of concrte of Rangamatia mouza for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma Zone III under Saltora Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.(Sl. No. 23) | Assistant Engineer | Junior Engineer | VCH/002883/2021-2022 |  | 16/03/2022 | 0 | GOURANGA NANDI | 4.83 | 0 | 0
4886 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Kastora mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Salma Zone- lll water supply scheme under Bankura sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002929/2021-2022 | FHTC/21 | 21/03/2022 | 0 | SANDHYA DEY | 3.43 | 0 | 0
4887 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Satdeuli mouzas for construction and commissioning of 'FHTC (FunCtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Salma Zone - lll under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003110/2021-2022 | FHTC/30 | 30/03/2022 | 0 | LABIR MIRSHAD KHAN | 1.83 | 0 | 0
4888 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Sat Deuli), Total House Hold - 151 nos. | Assistant Engineer | Junior Engineer | VCH/003111/2021-2022 | FHTC/30 | 30/03/2022 | 0 | LABIR MIRSHAD KHAN | 7.31 | 0 | 0
4889 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Digit mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000124/2022-2023 | 466/BSD | 06/06/2022 | 15 | TAPAN KUMAR UPADHYAY | 4.54 | 4.42 | 0
4890 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Dighit & Salbeda mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000126/2022-2023 | 467/BSD | 06/06/2022 | 15 | TAPAN KUMAR UPADHYAY | 3.55 | 3.38 | 0
4891 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Krishnapur & Salbeda mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/000128/2022-2023 | 468/BSD | 06/06/2022 | 15 | TAPAN KUMAR UPADHYAY | 3.83 | 3.8 | 0
4892 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 01 no., (Saburbandh), Total House Hold - 428 nos. | Assistant Engineer | Junior Engineer | ORD/000157/2021-2022 | 2836/BQA | 16/11/2021 | 30 | RUFIKUL MONDAL | 20.41 | 0 | 0
4893 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:- 05 nos, (Rajpara, keshar kundi, krishnapur, Digit, Salbeda), Total House Hold - 340 nos. | Assistant Engineer | Junior Engineer | ORD/000158/2021-2022 | 2837/BQA | 16/11/2021 | 30 | TAPAN KUMAR UPADHYAY | 16.4 | 8.81 | 0
4894 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 02 no., (Shirpurnama, Baiarampur), Total House Hold - 1059 nos. | Assistant Engineer | Junior Engineer | ORD/000178/2021-2022 | 2908/BQA | 23/11/2021 | 30 | DAS & CHAKRABORTY | 44.89 | 38.98 | 100
4895 | Bankura Division | Bankura Sadar Sub-Division | Repairing & relaying of UPVC Pipeline at Chatarkanali, Banspitali, Sirpuranama & tentularakha of Saburbandh Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2022-2023 | 540/BSD | 28/07/2022 | 30 | BROTIN UPADHYAY | 4.08 | 0 | 0
4896 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora . Name of OHR- Saburbadh . Name of Mouza:-- 01 no., (Tetularakh), Total House Hold - 348 nos. | Assistant Engineer | Junior Engineer | ORD/000190/2021-2022 | 2991/BQA | 25/11/2021 | 30 | N H ENTERPRISE | 16.12 | 16.11 | 0
4897 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saburbandh W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Saburbandh No.of Mouza :- 01 nos Saburbandh Total House Hold- 12 nos. | Assistant Engineer | Junior Engineer | ORD/000263/2022-2023 | 605/BSD | 16/08/2022 | 21 | MOHAMMAD HASAN KHAN | 4.52 | 4.16 | 0
4898 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saburbandh W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Saburbandh No. of Mouza :- 01 nos Saburbandh (Part), Total House Hold- 40 nos. | Assistant Engineer | Junior Engineer | ORD/000474/2021-2022 | 207/BSD | 11/03/2022 | 10 | RUFIKUL MONDAL | 3.51 | 2.49 | 0
4899 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line from keshar kundi to Rajpura village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 613/BSD | 16/08/2022 | 21 | TAPAN KUMAR UPADHYAY | 3.39 | 3.39 | 0
4900 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Rajpara, keshar kundi mouza & Dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000504/2022-2023 | 611/BSD | 16/08/2022 | 21 | TAPAN KUMAR UPADHYAY | 4.97 | 4.96 | 0
4901 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line from Saburbandh pump house to keshar kundi village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2022-2023 | 612/BSD | 16/08/2022 | 21 | M/S S.M ENTERPRISE | 4.99 | 4.98 | 0
4902 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 11 nos, (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, Saburbandh, Keshar Kundi, Rajpara, Krishnapur, Iswada, Narayanpur), Total House Hold - 2464 nos. | Assistant Engineer | Junior Engineer | ORD/000878/2021-2022 | 67/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.82 | 0.74 | 99
4903 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:- 05 nos, (Rajpara, keshar kundi, krishnapur, Digit, Salbeda), Total House Hold - 340 nos. | Assistant Engineer | Junior Engineer | VCH/000214/2022-2023 | FHTC/11 | 11/04/2022 | 0 | TAPAN KUMAR UPADHYAY | 7.59 | 0 | 0
4904 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Tetularakh mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000654/2022-2023 | FHTC/21 | 21/07/2022 | 0 | N H ENTERPRISE | 4.03 | 0 | 0
4905 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 07 (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyaldanga, Bagdiha) Total House Hold - 1131 | Assistant Engineer | Junior Engineer | VCH/002726/2021-2022 | FHTC/3 | 03/03/2022 | 0 | SIB SANKAR CHOWDHURY | 47.08 | 0 | 0
4906 | Bankura Division | Khatra Sub-Division | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Birkham (110) mouza under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 410 Nos. " | Assistant Engineer | Junior Engineer | ORD/000041/2021-2022 | 1788/BQA | 09/07/2021 | 30 | PARTHA PRATIM CHATAIT | 27.18 | 2.34 | 0
4907 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000102/2021-2022 | 2499/BQA | 23/09/2021 | 30 | APEX ENTERPRISE | 35.24 | 15.44 | 0
4908 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000459/2020-2021 | 118/KSD | 11/02/2021 | 20 | SUBHANKAR BANERJEE | 4.05 | 4.03 | 0
4909 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) | Assistant Engineer | Junior Engineer | ORD/000601/2021-2022 | 801/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.19 | 0 | 0
4910 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000209/2022-2023 | FHTC/11 | 11/04/2022 | 0 | GOUTAM BHATTACHRYYA | 32.23 | 0 | 0
4911 | Bankura Division | Khatra Sub-Division | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 | Assistant Engineer | Junior Engineer | VCH/002642/2021-2022 | FHTC/10 | 10/02/2022 | 0 | CLIFFORD FACILITY SERVICES PVT. LTD. | 6.16 | 0 | 0
4912 | Bankura Division | Khatra Sub-Division | Household survey in Madhabpur, Andharia, Kalsuli, Betharia (24) mouzas under Pasola zone -A to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 15 | Assistant Engineer | Junior Engineer | VCH/000464/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.17 | 0 | 0
4913 | Bankura Division | Khatra Sub-Division | laying Extra UPVC pipeline to cover Tilaboni (72) mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by retrofitting Zone-B (Tilaboni) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002773/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SANJOY PATRA | 4.71 | 0 | 0
4914 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of ¿FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Talanjuri purnia Total House Hold - 43 sl no - 13 | Assistant Engineer | Junior Engineer | VCH/002775/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 4.18 | 0 | 0
4915 | Bankura Division | Khatra Sub-Division | Extra UPVC pipe line for Retrofitting works for creation of FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Baharkhulia Total House Hold - 104 sl no - 15 | Assistant Engineer | Junior Engineer | VCH/002777/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 4.68 | 0 | 0
4916 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Baharkhulia Total House Hold - 104 sl no - 14 | Assistant Engineer | Junior Engineer | VCH/002778/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHANKAR BANERJEE | 4.95 | 0 | 0
4917 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-B), Total House Hold -264 | Assistant Engineer | Junior Engineer | VCH/002780/2021-2022 | FHTC/5 | 05/03/2022 | 0 | ASOKE BHATTACHARYYA | 2.27 | 0 | 0
4918 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Pathardoba, Zone-A & B and Baricha, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 58 Nos. Total Household:- 7982 Nos. Name of Mouzas:- Under Pathardoba, Zone-A :- Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) Under Pathardoba, Zone-B:- Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) Under Baricha, Zone-B:- Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) | Assistant Engineer | Junior Engineer | ORD/000025/2022-2023 | 1085/BQA | 12/05/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 482.88 | 160.87 | 0
4919 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) mouzas under Pathardoba, Zone-B to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) | Assistant Engineer | Junior Engineer | ORD/000679/2021-2022 | 808/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.81 | 0.8 | 0
4920 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 5.08 | 0 | 0
4921 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sagarchaka (258), Kamalpur (259), Sirisbani (311), Chamtabaid (312), Phulkusma (313), Namosol (314), Mandaldiha (315), Dhau (316), Benagerya (317), Pakadihi (318) & Melera (319) mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 11 Nos. Total Household:- 3319 Nos. | Assistant Engineer | Junior Engineer | ORD/000313/2021-2022 | 06/BQA | 03/01/2022 | 60 | GOPAL CHANDRA CHOUDHURY | 160.06 | 151.02 | 65
4922 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of HDPE pipeline in Sagarchaka (258), Namosol (314) & Phulkusma (313) mouza by retrofitting of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 510/BQA | 13/03/2023 | 45 | GOPAL CHANDRA CHOWDHURY | 19.91 | 19.76 | 50
4923 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Sagarchaka (258), Kamalpur (259), Sirisbani (311), Chamtabaid (312), Phulkusma (313), Namosol (314), Mandaldiha (315), Dhau (316), Benagerya (317), Pakadihi (318) & Melera (319) mouzas under Mandalkuli (Zone-IIIB) to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) | Assistant Engineer | Junior Engineer | ORD/000682/2021-2022 | 857/KSD | 31/12/2021 | 90 | TAPAS DEY | 1.11 | 0.56 | 0
4924 | Bankura Division | Khatra Sub-Division | Repairing and laying of UPVC pipe for Distribution Main along with allied works from Phulkusma Bazar to Durga Mandir [damage done during making of cement concrete road from Phulkusma Bazar to Durgamandir by Bankura Zilla Parishad] of Water Supply Scheme for Mandalkuli, Zone-IIIB under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dt | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 361/BQA | 06/02/2024 | 45 | SUBHADIP KOLE | 2.82 | 0 | 0
4925 | Bankura Division | Khatra Sub-Division | Household survey in Sagarchaka (258) Kamalpur (259) siribani (311) chamtabaid (312) Dhau ( 316) Pakadihi ( 318) Melara (319) mouzas under Mandalkuli (Zone-IIIB) to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 18 | Assistant Engineer | Junior Engineer | VCH/000462/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.41 | 0 | 0
4926 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Benjtabani (51), Benrebati (52), Tilbari (53), Sarasbakra (55), Pukhuria (56), Birsingpur (57), Bikrampur (58), Krishnapur (59), Kathjuria (60), Nuniabad (61), Harintuli (62), Kaniabali (63), Chhota Hetyagara (64), Barahetyagara (65), Gorakata (66), Pathakata (67), Malatibad (68), Talda (86), Parulia (87) & Bardi (88) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 3109 nos. | Assistant Engineer | Junior Engineer | ORD/000046/2022-2023 | 1649/BQA | 25/07/2022 | 934 | GOUTAM BHATTACHRYYA | 141.55 | 93.28 | 81
4927 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Dubrajpur Zone-A & B of Simlapal Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) [Part-A] (Sl. No. 11) | Assistant Engineer | Junior Engineer | ORD/000337/2021-2022 | 819/KSD | 15/12/2021 | 15 | BISWAJIT SINHA MAHAPATRA | 3.81 | 0 | 0
4928 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Benjtabani (51), Benrebati (52), Tilbari (53), Sarasbakra (55), Pukhuria (56), Birsingpur (57), Bikrampur (58), Krishnapur (59), Kathjuria (60), Nuniabad (61), Harintuli (62), Kaniabali (63), Chhota Hetyagara (64), Barahetyagara (65), Gorakata (66), Pathakata (67), Malatibad (68), Talda (86), Parulia (87) & Bardi (88) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21) | Assistant Engineer | Junior Engineer | ORD/000685/2021-2022 | 860/KSD | 31/12/2021 | 90 | TAPAS DEY | 1.04 | 0.62 | 0
4929 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2022-2023 | 1837/BQA | 29/08/2022 | 0 | Resource Division | 6.15 | 0 | 0
4930 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 12.99 | 0 | 0
4931 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jhumka (156) Nutangram (157), Ghaghrakhulia (169), Ekaria Jambani (170), Krishnabati (171), Chandpur (172), Putiadaha (173), Pithabakra (174), Bagnada (175) & Nekratapal (176) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000225/2021-2022 | 3085/BQA | 13/12/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 81.17 | 67.77 | 0
4932 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Jhumka (156) Nutangram (157), Ghaghrakhulia (169), Ekaria Jambani (170), Krishnabati (171), Chandpur (172), Putiadaha (173), Pithabakra (174), Bagnada (175) & Nekratapal (176) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000687/2021-2022 | 863/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.44 | 0.4 | 0
4933 | Bankura Division | Bankura Sadar Sub-Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part- A & B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-01 no, Barjora, Total House Hold -3307 nos. | Assistant Engineer | Junior Engineer | ORD/000021/2022-2023 | 1063/BQA | 10/05/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 367.48 | 179.25 | 0
4934 | Bankura Division | Bankura Sadar Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) | Assistant Engineer | Junior Engineer | ORD/000189/2022-2023 | 349/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 0
4935 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II). Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-01 no., (Barjora (Part-A)), Total House Hold -1657 nos. | Assistant Engineer | Junior Engineer | ORD/000880/2021-2022 | 82/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.55 | 0.55 | 0
4936 | Bankura Division | Bankura Sadar Sub-Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part- A & B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-01 no, Barjora, Total House Hold -3307 nos. | Assistant Engineer | Junior Engineer | ORD/000021/2022-2023 | 1063/BQA | 10/05/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 367.48 | 179.25 | 0
4937 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II), Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :- 01 no., (Barjora (Part-B), Total House Hold - 1650 nos. | Assistant Engineer | Junior Engineer | ORD/000882/2021-2022 | 83/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.55 | 0.55 | 0
4938 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Morar Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Bashudebpur, No. of Mouza :- 7 nos. i.e. Bankati-123, Padda-125, Harabati-127, Dhangasol-128, Lohari-129, Kulupukur-132, Kulaijuri-134, Total House Hold -61 | Assistant Engineer | Junior Engineer | ORD/000030/2022-2023 | 112/VSD | 19/04/2022 | 21 | AJIT KUMAR DUTTA | 4.25 | 4.25 | 0
4939 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR -Benabendi, No. of Mouza :- 12 nos. i.e. Tribanka- 108 , Belsulia- 109, Dumohoni - 110, Bangele- 111, Benabendi- 112, Khanabari- 113, Darasole- 114, Chandabila- 115, Uparsole- 156, Kharkata- 157, Pachadahara- 158 & Agunkumari- 159, Total House Hold - 1927 | Assistant Engineer | Junior Engineer | ORD/000398/2021-2022 | 247/BQA | 09/02/2022 | 60 | DAS CONSTRUCTION | 192.1 | 147.63 | 0
4940 | Bankura Division | Brishnupur Sub-Division | Rail Bhoomi Crossing Seva (IR-RBCS) | Assistant Engineer | Junior Engineer | BILL/01411/2023-2024 | FHTC/11 | 03/11/2023 | 0 | SOUTH EASTERN RAILWAY | 5.17 | 0 | 0
4941 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for augmentation of Rampur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Rampur, No. of Mouza :- 10 nos. i.e. PASCHIM NABASAN (41), DHUBRAJHATI (42), RAPATGANG (56),PARB BATIA (57), BAHULIA (58),SAL CHATURIA (59), PATJOR (60), HAMIRHATI (61), RAMPUR (65), JASHRA (67) , Total House Hold - 2112. (2nd Call) (TSM/008992) (SM/09454) (AAFS- PH212245837S000) | Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 765/BQA | 04/04/2023 | 510 | RANABIR CHATTERJEE | 92.2 | 92.2 | 100
4942 | Bankura Division | Brishnupur Sub-Division | Extra Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)'at different school, ICDS and health centre in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rampur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2022-2023 | 114/VSD | 19/04/2022 | 21 | SWAPAN KUMAR DE | 2.3 | 2.16 | 0
4943 | Bankura Division | Brishnupur Sub-Division | Laying distribution system including allied works for Augmentation of RAMPUR Piped W/S. Scheme of Sonamukhi block of Bankura District under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 903/BQA | 20/04/2023 | 407 | UNIVERSAL CONSTRUCTION | 156.6 | 125.4 | 100
4944 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.4 m x 3.6 m) at 3rd TW site for Rampur Piped Water Supply Scheme wihin Sonamukhi block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2024-2025 | 1872/BQA | 12/07/2024 | 90 | BISWAJIT SINHA MAHAPATRA | 6.57 | 0 | 100
4945 | Bankura Division | Brishnupur Sub-Division | Land Development work for construction of boundary wall at augmentation work of Rampur Water Supply Scheme Pump House No 3 Boundary wall under Bishnupur Sub Division. | Assistant Engineer | Junior Engineer | ORD/000230/2023-2024 | 151/VSD | 02/06/2023 | 15 | CHATERJEE ENTERPRISE | 0.99 | 0.97 | 20
4946 | Bankura Division | Brishnupur Sub-Division | Construction of Retaining wall for Land development work for construction of boundary wall at augmentation work of Rampur Water Supply Scheme Pump House No. 3 Boundary wall under Bishnupur Sub Division. | Assistant Engineer | Junior Engineer | ORD/000240/2023-2024 | 152/VSD | 02/06/2023 | 30 | RANABIR CHATTERJEE | 0.35 | 0.35 | 20
4947 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no 300mm X 200mm X 200m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Rampur water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 61/BQA | 05/01/2023 | 908 | MAYA CONSTRUCTION | 18.74 | 13.74 | 95
4948 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 78 mtr long at augmentation of Rampur water supply scheme (pump house no 3) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 62/BQA | 05/01/2023 | 30 | RANABIR CHATTERJEE | 5.54 | 5.54 | 20
4949 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 80 mtr long at augmentation of Rampur water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 63/BQA | 05/01/2023 | 30 | GON ASSOCIATES | 5.62 | 5.62 | 100
4950 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 20 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN SONAMUKHI BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 352/BQA | 21/02/2023 | 30 | G.MITRA AND ASSOCIATES | 18.88 | 15.11 | 100
4951 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of RCC Over Head Reservoir of capacity 350 cum and staging height 20 mtr.with allied works for Augmentation of Rampur Piped W/S underSonamukhi Block of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2021-2022 | 548/BQA | 11/03/2022 | 90 | SUBHANKAR BANERJEE | 66.77 | 65.23 | 95
4952 | Bankura Division | Brishnupur Sub-Division | Repairing of 2 nos pump house for augmentation of Rampur water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008992) (SM/09454) (AAFS- PH212245837S000 ) | Assistant Engineer | Junior Engineer | ORD/000557/2022-2023 | 521/BQA | 14/03/2023 | 45 | BIT ENTERPRISE | 3.62 | 3.17 | 100
4953 | Bankura Division | Brishnupur Sub-Division | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Rampur to accommodate FHTC under Jal Sapno Mission under Sonamukhi Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 3) [Estimated Cost Rs. Quotated Rate] | Assistant Engineer | Junior Engineer | ORD/000653/2021-2022 | 424/C/VSD | 23/09/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.66 | 2.66 | 0
4954 | Bankura Division | Brishnupur Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Rampur W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) OHR Capacity- 350 m3 | Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 146//VSD | 18/05/2022 | 15 | GLORY ENGINEERS SYNDICATE | 1.4 | 1.4 | 0
4955 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY OF CIDF PIPE LINE FOR 350 CUM OHR OF AUGMENTATION OF RAMPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM UNDER BISHNUPUR SUB DIVISION OF BANKURA DIVISION,PHE Dte. SM CODE : SM/09454 | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 3024/BQA | 03/11/2023 | 45 | SUBHANKAR BANERJEE | 5.96 | 5.96 | 100
4956 | Bankura Division | Brishnupur Sub-Division | Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 22.01.2023 to 21.07.2023. | Assistant Engineer | Junior Engineer | ORD/001105/2022-2023 | 05./BK | 19/01/2023 | 191 | CHANPA SINGHA | 0.86 | 1.35 | 30
4957 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000053/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 73.9 | 0 | 0
4958 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 2525/BQA | 08/09/2023 | 0 | Resource Division | 13.01 | 0 | 0
4959 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/00127/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
4960 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/01664/2023-2024 | BP-2023-24-177 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
4961 | Bankura Division | Brishnupur Sub-Division | Crossing of Rail Line at KM 264/5 to 264/6 by Jack pushing method (600 mm dia RCC Hume pipes for casing with laid pipe of MS) for Laying of Pipe Line for Hamirhati and its adjoining mouzas water under Augmentation of Rampur water supply scheme & Danna water supply scheme under Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001747/2024-2025 | 448/BQA | 20/02/2025 | 131 | SWAPAN KUMAR CHANDRA | 26.55 | 0 | 90
4962 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rampur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 938/BMD | 12/05/2023 | 180 | M/S BIPUL BANERJEE | 19.85 | 8.24 | 41
4963 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of -Electrical and illumination works related to instrument and laboratory requirment for proposed Water Testing Laboratory at PHED OHR site, Sonamukhi Municipal Water Supply scheme , Bankura under infrostructure development and diffrent water testing laboratories regarding NABL Accreditation recognition under Bankura Mechanical Division, PHE Dte.Dist-Bankura, Releted to supported activities under Jal Jiban Mission. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 985/BMSD | 29/07/2022 | 15 | RAJIB COMPANY | 4.27 | 3.82 | 100
4964 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply scheme for KANKI & its adjoining mouzas under Chhatna Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR:- Kanki, No.of Mouza :- 05 (Rajadal Bongaon Bikpur, Murgaboni & Kanki). Total House Hold - 438 nos. | Assistant Engineer | Junior Engineer | ORD/000142/2021-2022 | 2807/BQA | 12/11/2021 | 30 | TAPAN KUMAR MANDAL | 18.69 | 0 | 100
4965 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANKI W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kanki, Name of Mouza:-- Rajadal, Bongaon Bikpur, Murgaboni & Kanki, Total House Hold - 438 nos. | Assistant Engineer | Junior Engineer | ORD/000580/2021-2022 | 65/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.15 | 0.14 | 0
4966 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Kendboni, Kantaboni, Mamurjuri, Dhansimul, Malindasi & Sonamui part mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kendboni (Zone- p) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002731/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BIPUL BANERJEE | 4.88 | 0 | 0
4967 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Mankanali, Khirajuri & Garakusum mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kendboni (Zone- p) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002732/2021-2022 | FHTC/3 | 03/03/2022 | 0 | BIPUL BANERJEE | 4.79 | 0 | 0
4968 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 (Gopbandh ), Total House Hold -155 | Assistant Engineer | Junior Engineer | VCH/002733/2021-2022 | FHTC/3 | 03/03/2022 | 0 | DAUD ALI KHAN | 0.85 | 0 | 0
4969 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-C) Total House Hold - 150 | Assistant Engineer | Junior Engineer | VCH/002735/2021-2022 | FHTC/3 | 03/03/2022 | 0 | GOURANGA CHATTERJEE | 1.3 | 0 | 0
4970 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 | Assistant Engineer | Junior Engineer | VCH/002745/2021-2022 | FHTC/3 | 03/03/2022 | 0 | UNICON INDIA | 116.51 | 0 | 0
4971 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002830/2021-2022 | FHTC/9 | 09/03/2022 | 0 | TAPAN KUMAR MANDAL | 13.34 | 0 | 0
4972 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply scheme for KANKI & its adjoining mouzas under Chhatna Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR:- Kanki, No.of Mouza :- 05 (Rajadal Bongaon Bikpur, Murgaboni & Kanki). Total House Hold - 438 nos. | Assistant Engineer | Junior Engineer | VCH/002867/2021-2022 | FHTC/15 | 15/03/2022 | 0 | TAPAN KUMAR MANDAL | 11.43 | 0 | 0
4973 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1759 nos. | Assistant Engineer | Junior Engineer | ORD/000318/2021-2022 | 3369/BQA | 31/12/2021 | 1551 | M/S TARUN KUMAR PATRA | 75.43 | 25.13 | 0
4974 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000886/2021-2022 | 102/BSD | 28/01/2022 | 2 | TAPAS DEY | 0.59 | 0.21 | 0
4975 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2021-2022 | 573/BQA | 17/03/2022 | 0 | Resource Division | 10.84 | 0 | 0
4976 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
4977 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte Bhalaidiha, Ps-Khatra Dist-Bankura |  | Junior Engineer | BILL/00771/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
4978 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
4979 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
4980 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 |  | Junior Engineer | ORD/000314/2020-2021 | 1365/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.66 | 0 | 100
4981 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605" |  | Junior Engineer | ORD/000316/2020-2021 | 1366/BQA | 08/10/2020 | 30 | GOPAL CHANDRA CHOUDHURY | 43.67 | 0 | 100
4982 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection)¿ in connection with Jal Jeevan Mission (JJM) of CHERABASTA (Zone - K)) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Cherabasta No.of Mouza :- 02 nos. Cherabasta & uparbandh. Total House Hold -12 nos. |  | Junior Engineer | ORD/000667/2022-2023 | 60/BSD | 24/01/2023 | 7 | GOURANGA NANDI | 0.97 | 0 | 100
4983 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to Cover Ailtha, Bagneja, Uparbandh, Akurbad, Banki, Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000847/2021-2022 |  | 01/09/2021 | 0 | SUBHADIP KOLEY | 4.69 | 0 | 0
4984 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to Cover Cherabasta , Aina Gobindapur, Mukundapur Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000849/2021-2022 |  | 01/09/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.78 | 0 | 0
4985 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No. of Mouza :- 09 nos, (Nabagram, Vidyadharpur, Ailtha, Munipur, Bagneja, Upar bandh, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 1209. |  | Junior Engineer | VCH/001343/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
4986 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
4987 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3912) |  | Junior Engineer | VCH/001535/2020-2021 | FHTC/280 | 12/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 33.98 | 0 | 0
4988 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Kanchanpur (PART) Total House Hold - 507 . ( MB No - 4004)" |  | Junior Engineer | VCH/001561/2020-2021 | FHTC/283 | 22/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 40.89 | 0 | 0
4989 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
4990 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000303/2020-2021 | 1426/BQA | 09/10/2020 | 30 | SUMITA UPADHYAY | 33.29 | 1.82 | 85
4991 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280) & Dharampur (281) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000304/2020-2021 | 1427/BQA | 09/10/2020 | 30 | MUNMUN UPADHYAY | 41.55 | 0 | 0
4992 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) |  | Junior Engineer | ORD/000443/2020-2021 | 108/KSD | 11/02/2021 | 10 | SUMITA UPADHYAY | 2.07 | 0 | 0
4993 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Jetpara (280) & Dharampur (281) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) |  | Junior Engineer | ORD/000444/2020-2021 | 109/KSD | 11/02/2021 | 10 | SUMITA UPADHYAY | 4.91 | 0 | 0
4994 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Kumarpur (209) & Amdani (229) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) |  | Junior Engineer | ORD/000445/2020-2021 | 110/KSD | 11/02/2021 | 10 | MUNMUN UPADHYAY | 4.93 | 0 | 0
4995 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Kumarpur (209), Ambani (229), mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  | Junior Engineer | VCH/000020/2021-2022 |  | 12/04/2021 | 0 | MUNMUN UPADHYAY | 4.94 | 0 | 0
4996 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Kumarpur (209) & Amdani (229) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) |  | Junior Engineer | ORD/000446/2020-2021 | 111/KSD | 11/02/2021 | 10 | MUNMUN UPADHYAY | 4.94 | 0 | 0
4997 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danrkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280), Dharampur (281) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 40) |  | Junior Engineer | ORD/000542/2020-2021 | 282/KSD | 10/12/2020 | 62 | TARINI CHARAN UPADHYAY | 0.32 | 0 | 90
4998 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208)mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block - Sarenga, Dist- Bankura. |  | Junior Engineer | VCH/000017/2021-2022 |  | 12/04/2021 | 0 | SUMITA UPADHYAY | 2.07 | 0 | 0
4999 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Jetpara (280), Bharampur (281) mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  | Junior Engineer | VCH/000018/2021-2022 |  | 12/04/2021 | 0 | SUMITA UPADHYAY | 4.91 | 0 | 0
5000 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Construction and commissioning of FHTC (Functional Household Tap Connection) in Kumarpur (209), Ambani (229), mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  | Junior Engineer | VCH/000019/2021-2022 |  | 12/04/2021 | 0 | MUNMUN UPADHYAY | 4.92 | 0 | 0
5001 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
5002 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Radhanagar w/s scheme (zone - l) under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (Part - B) , total house hold -66 ( MB No - 3981)" |  | Junior Engineer | VCH/001546/2020-2021 | FHTC/276 | 08/02/2021 | 0 | I.R.CONSTRUCTION | 4.6 | 0 | 0
5003 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part - A) , total house hold - 200 ( MB No - 4024)" |  | Junior Engineer | VCH/001547/2020-2021 | FHTC/276 | 08/02/2021 | 0 | SUBHANKAR BANERJEE | 13.81 | 0 | 0
5004 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part -A) , total house hold - 145 ( MB No - 4024)" |  | Junior Engineer | VCH/001548/2020-2021 | FHTC/276 | 08/02/2021 | 0 | SUBHANKAR BANERJEE | 9.71 | 0 | 0
5005 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (29) mouzas by retrofitting zone - llB of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B ( MB No - 3953) |  | Junior Engineer | VCH/001558/2020-2021 | FHTC/283 | 22/02/2021 | 0 | SUNIL KUMAR MANDAL | 3.27 | 0 | 0
5006 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (267) mouzas by retrofitting zone - llB of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A ( MB No - 3953) |  | Junior Engineer | VCH/001559/2020-2021 | FHTC/283 | 22/02/2021 | 0 | TAPAN KUMAR MANDAL | 3.9 | 0 | 0
5007 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
5008 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5009 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5010 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
5011 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Birbandh C/o Sudip saha, Birbandh, Ranibandh |  | Junior Engineer | BILL/00047/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
5012 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5013 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5014 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
5015 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 44 | 48
5016 | Bankura Division | Bankura Sadar Sub-Division | Quotation of WBSEDCL for the scheme of SM/10926 | Assistant Engineer | Junior Engineer | BILL/00849/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
5017 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 44 | 48
5018 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 42 | 48
5019 | Bankura Division | Khatra Sub-Division | Single phase connection of Kusumkundi village under Manbazar CCC | Assistant Engineer | Junior Engineer | BILL/00029/2024-2025 | FHTC/04 | 23/04/2024 | 0 | MANBAZAR CCC | 0.12 | 0 | 0
5020 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5021 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5022 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
5023 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-92, Mouza-Lachhipur, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00285/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
5024 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5025 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5026 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
5027 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5028 | Bankura Division | RWS Bankura Sub-Division | New Connection at JL No-86, Mouza-Bhadli, Bliock-Raipur PHE Dte. |  | Junior Engineer | BILL/00625/2023-2024 | FHTC/11 | 10/11/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
5029 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5030 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.6 | 48
5031 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Jagannathpur Village (SM/11020), (2) Mini Piped Water Supply Scheme for Jarka Village (SM/11021), (3) Mini Piped Water Supply Scheme for Bhadli Village (SM/11024) and (4) Mini Piped Water Supply Scheme for Dangarsai Village (SM/11025) |  | Junior Engineer | ORD/001996/2024-2025 | 196\KSD | 10/03/2025 | 10 | M/S ASHOK KUMAR DEY | 0.6 | 0 | 90
5032 | Bankura Division | RWS Bankura Sub-Division | New Connection at Balibandh, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00414/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5033 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5034 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5035 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5036 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5037 | Bankura Division | Bankura Sadar Sub-Division | New single phase service connection at Pairasole. | Assistant Engineer | Junior Engineer | BILL/01584/2025-2026 |  | 18/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
5038 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
5039 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5040 | Bankura Division | Khatra Sub-Division | New Connection at Asnasole, Taldangra,Pin-722102 PHE Dte | Assistant Engineer | Junior Engineer | BILL/00421/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5041 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5042 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
5043 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Saharghati Village (SM/11079), (2) Mini Piped Water Supply Scheme for Asnasol Village (SM/11045), (3) Mini Piped Water Supply Scheme for Jashodanandapur Village (SM/11047), (4) Mini Piped Water Supply Scheme for Machla Village (SM/11048), (5) Mini Piped Water Supply Scheme for Balarampur Village (SM/11053) and (6) Mini Piped Water Supply Scheme for Bhandia Village (SM/11054) | Assistant Engineer | Junior Engineer | ORD/001999/2024-2025 | 199\KSD | 10/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 95
5044 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5045 | Bankura Division | RWS Bankura Sub-Division | New Connection at Nabagram, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00437/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5046 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5047 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
5048 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Kamlagora" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00075/2024-2025 |  | 26/04/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
5049 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE (Kamlagora) HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00125/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
5050 | Bankura Division | Bankura Sadar Sub-Division | Rajkumardanga, Bankura-I, 9330862734 | Assistant Engineer | Junior Engineer | BILL/00764/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
5051 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10909 | Assistant Engineer | Junior Engineer | BILL/00909/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
5052 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Kamlagora water supply scheme(SVS) under BMD PHE Dte.(SM/10909) | Assistant Engineer | Junior Engineer | BILL/01403/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
5053 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 29 | 48
5054 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5055 | Bankura Division | Bankura Sadar Sub-Division | New Service Connection for mini water supply scheme at Bamnisala, village under Saltora Block under Babkura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00826/2023-2024 | FHTC/09 | 19/09/2023 | 0 | SALTORA CCC | 0.12 | 0 | 0
5056 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5057 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
5058 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5059 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5060 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
5061 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Dharapat, Mirjapur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00276/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
5062 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5063 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5064 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
5065 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Amdohi, Lowgram , Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00261/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
5066 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5067 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5068 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27.6 | 48
5069 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Nayada | Assistant Engineer | Junior Engineer | BILL/01030/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
5070 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 29 | 48
5071 | Bankura Division | Khatra Sub-Division | New service connection for Suklabaid Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00115/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
5072 | Bankura Division | Khatra Sub-Division | New service connection for Suklabaid Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00116/2024-2025 |  | 16/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
5073 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5074 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5075 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5076 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
5077 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5078 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5079 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
5080 | Bankura Division | Brishnupur Sub-Division | (site - Baragopinathpur, pry sch, gopinathpur, Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00298/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
5081 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5082 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5083 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at BARAGOPINATHPUR | Assistant Engineer | Junior Engineer | BILL/01278/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
5084 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.6 | 48
5085 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5086 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5087 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
5088 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Jamshala Chalka Ashrampara Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00147/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
5089 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Jamshala Chalka Ashrampara Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00169/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
5090 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 46 | 48
5091 | Bankura Division | Bankura Mechanical Sub-Division | New service connection for Shyampur, Hatirampur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00155/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
5092 | Bankura Division | Bankura Mechanical Sub-Division | New service connection for Shyampur, Hatirampur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00174/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
5093 | Bankura Division | Bankura Mechanical Sub-Division | New Service connection at Mini Piped w/s scheme at village-Shyampur Po-Gourbazar under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00814/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
5094 | Bankura Division | Bankura Mechanical Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
5095 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5096 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5097 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
5098 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5099 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Kalachandpur,Brahmandiha | Assistant Engineer | Junior Engineer | BILL/00511/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
5100 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5101 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.08 | 48
5102 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Radhanagar site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00180/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
5103 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5104 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5105 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Radhanagar | Assistant Engineer | Junior Engineer | BILL/01259/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
5106 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36 | 48
5107 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5108 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5109 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
5110 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Hajipur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00184/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
5111 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5112 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5113 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 48
5114 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Nutangram site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00188/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
5115 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5116 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5117 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
5118 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45.5 | 48
5119 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5120 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Benagaria Bhatra | Assistant Engineer | Junior Engineer | BILL/01036/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
5121 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5122 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
5123 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5124 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5125 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 48
5126 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5127 | Bankura Division | RWS Bankura Sub-Division | New Connection at Kanaipur, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00445/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5128 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5129 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
5130 | Bankura Division | RWS Bankura Sub-Division | New Connection at Kukutia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00418/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5131 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5132 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing, jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 Cum. Capacity R.C.C. OHR (based on Departmental Design) with 20 mtr. staging height with allied works for Augmentation of Mukundapur Water Supply Scheme under Khatra Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2023-2024 | 1187/BQA | 22/05/2023 | 270 | PARTHA PRATIM CHHATAIT | 384.93 | 176.75 | 45
5133 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
5134 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Augmentation of Mukundapur Piped Water Supply Scheme, Block : Raipur, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000544/2021-2022 | 02/KSD | 06/01/2022 | 31 | SIRCON ENGINEERING SERVICES | 3.61 | 0 | 0
5135 | Bankura Division | Khatra Sub-Division | Laying DI Pipe (K9) pipe, Construction of 1 No. 200 mm dia x 5.5 mtr. depth horizontal river bed tube well using MS "T " and Laying, Fitting & fixing 100 mm M.S. delivery main connecting line from river bed tube well to CWR for Augmentation of Mukundapur Water Supply Scheme under Khatra Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2022-2023 | 483/BQA | 13/03/2023 | 750 | GOUTAM GHOSH | 28.41 | 15.97 | 80
5136 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukundapur and its adjoining mouzas Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000548/2022-2023 | 484/BQA | 13/03/2023 | 979 | GOUTAM GHOSH | 19.46 | 0 | 0
5137 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001388/2024-2025 | 35/BQA | 02/01/2025 | 45 | PARTHA PRATIM CHHATAIT | 20.68 | 0 | 95
5138 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 114.89 | 0 | 0
5139 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000051/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 46.12 | 0 | 0
5140 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000160/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 7.76 | 0 | 0
5141 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01673/2023-2024 | BP-2023-24-186 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.46 | 0 | 0
5142 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission program under Raipur Block in Bankura District under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000715/2023-2024 | 2172/BMD | 30/10/2023 | 960 | DEY ENTERPRISE | 50.24 | 2.55 | 78
5143 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5144 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5145 | Bankura Division | Brishnupur Sub-Division | New service connection at Chandan Keyari | Assistant Engineer | Junior Engineer | BILL/01406/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0
5146 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20.6 | 48
5147 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Adhakata site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00195/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
5148 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5149 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5150 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
5151 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Mohishkhoar site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00172/2022-2023 |  | 11/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
5152 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5153 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5154 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 52 | 48
5155 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5156 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5157 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
5158 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5159 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATHARA PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer |  | ORD/000109/2023-2024 | 1191/BQA | 22/05/2023 | 276 | PARTHA PRATIM CHHATAIT | 302.75 | 27.43 | 10
5160 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000079/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 26.5 | 0 | 0
5161 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATHRA TW-1(JL NO-153 PLOT-689)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer |  | BILL/00009/2024-2025 | BP-2024-25-29 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.97 | 0 | 0
5162 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATHRA TW-2(JL NO-153, PLOT NO-351)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer |  | BILL/00010/2024-2025 | BP-2024-25-30 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.35 | 0 | 0
5163 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Pathra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer |  | ORD/000159/2023-2024 | 871/BMD | 04/05/2023 | 180 | INDRAJIT MITRA | 31.37 | 14.56 | 46
5164 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tungi (104), Rautara (105), Siromanipur (106), Raipur Bazar (139), Dharampur (140), Kajla (141), Kajalkura (142), Kamardiha (143), Kankrasol (144), Nayapara (170), Uparbanda (171), Dublala (172) & Simli (201) mouzas by retrofitting of Raipur Bazar and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 902/BQA | 20/04/2023 | 1077 | ASHIS KUMAR SAMANTA | 208.39 | 7.28 | 45
5165 | Bankura Division | Khatra Sub-Division | Crossing road by 200 mm dia MS pipe by Jack pushing method, laying & fabrication of MS pipe and all allied works for Matgoda and its adjoining mouzas under water supply scheme for Left Out Mouzas of Raipur Block of under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (At Matgoda Bazar More) | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 936/BQA | 25/04/2023 | 30 | SUBHADIP KOLEY | 9.02 | 9 | 100
5166 | Bankura Division | Khatra Sub-Division | Crossing road by 200 mm dia MS pipe by Jack pushing method, laying & fabrication of MS pipe and all allied works for Matgoda and its adjoining mouzas under water supply scheme for Left Out Mouzas of Raipur Block of under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (At Niljora More) | Assistant Engineer | Junior Engineer | ORD/000074/2023-2024 | 937/BQA | 25/04/2023 | 30 | GOPAL CHANDRA CHOWDHURY | 7.3 | 7.29 | 100
5167 | Bankura Division | Khatra Sub-Division | Laying additioal pipeline for Construction and Commisioning of FHTC for Raipur Bazar Water Supply Scheme under Water Supply Scheme for Left Out Mouzas of Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000129/2025-2026 | 1291/BQA | 17/06/2025 | 317 | GOPAL CHANDRA CHOWDHURY | 52.55 | 0 | 0
5168 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamsol (145), Banpathari (146), Niljora (147), Kuldiha (148), Matgoda (162), Kelepara (165), Rajgan (166), Jadab Nagar (167), Jashpara (168) & Dubrajpur (169) mouzas by retrofitting of Matgoda and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1929/BQA | 13/07/2023 | 90 | PARTHA PRATIM CHHATAIT | 207.77 | 107.89 | 95
5169 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Buridhara (59), Chanpabani (60) & Chaturikalapathar (71) mouzas by retrofitting of Champabani and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza - 3 Nos. Total Household- 335 Nos. | Assistant Engineer | Junior Engineer | ORD/000584/2022-2023 | 500/BQA | 13/03/2023 | 45 | TAPAN KUMAR UPADHYAY | 23.67 | 22.48 | 75
5170 | Bankura Division | Khatra Sub-Division | Culvert crossing by MS Pipe for Rising Main and Distribution Main with other ancillary works under Water supply scheme for Left out Mouzas of Raipur Block under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000990/2023-2024 | 3286/BQA | 30/11/2023 | 30 | UTTAM KUMAR SINHAMAHAPATRA | 3.4 | 3.25 | 90
5171 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 5 nos. site of Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block (SM/14126), 1 no. site of Retrofitting of Lurka (Zone-VB) Water Supply Scheme (BRGF Ph-I) (SM/14491) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001930/2024-2025 | 173\KSD | 07/03/2025 | 10 | M/S ASHOK KUMAR DEY | 0.9 | 0 | 95
5172 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 220.33 | 55
5173 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Gopalpur Piped Water Supply Scheme (SM/16698) , 2 nos. sites of Dhula Danga Piped Water Supply Scheme (SM/14176) & 2 nos. sites of Adwaitabati Piped Water Supply Scheme (SM/16942) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001876/2024-2025 | 554/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 100
5174 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000037/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 73.19 | 0 | 0
5175 | Bankura Mechanical | Brishnupur Sub-Division | New service connection of P/H-II Dhuladanga W/S scheme | Assistant Engineer | Junior Engineer | BILL/00599/2024-2025 | BP-2024-25-169 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.62 | 0 | 0
5176 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-I of Dhuladanga W/S scheme | Assistant Engineer | Junior Engineer | BILL/01348/2024-2025 | BP-2024-25-351 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.48 | 0 | 0
5177 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhuladanga Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000144/2025-2026 | 439/BMD | 10/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 11.85 | 0 | 0
5178 | Bankura Division | Brishnupur Sub-Division | The maintenance and repair estimate is prepared in respect of the road namely T05-Melhra to 21L2 having Package No -WB-03-658 under Sonamukhi block, in the District of Bankura under PMGSY ,WBSRDA , Bishnupur Division. Road Name : METHRA to 21 LZ (WB-03-658) From Telrui Piped Water Supply Scheme (SM/13711 ) | Assistant Engineer | Junior Engineer | BILL/00471/2025-2026 |  | 20/06/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.46 | 0 | 0
5179 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 26.18 | 55
5180 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Rautara Piped Water Supply Scheme (SM/14521) & 3 nos. sites of Brindabanpur Piped Water Supply Scheme (SM/18437) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001897/2024-2025 | 575/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.75 | 0 | 0
5181 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 156.61 | 0 | 0
5182 | Bankura Mechanical | Brishnupur Sub-Division | Additional quotation for Rautora. | Assistant Engineer | Junior Engineer | BILL/00367/2025-2026 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0
5183 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for RautaraTW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) | Assistant Engineer | Junior Engineer | BILL/01249/2024-2025 | BP-2024-25-323 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.47 | 0 | 0
5184 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Rautara TW1 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) | Assistant Engineer | Junior Engineer | BILL/01250/2024-2025 | BP-2024-25-324 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.65 | 0 | 0
5185 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Routara Piped Water Supply Scheme under BMD PHE Dte Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000069/2025-2026 | 260/BMD | 14/05/2025 | 90 | SUMIT KUMAR CHAKRABORTY | 11.66 | 0 | 0
5186 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 70.88 | 55
5187 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2025-2026 | 1797/BQA | 19/08/2025 | 0 | Resource Division | 10.81 | 0 | 0
5188 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 11.26 | 0 | 0
5189 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000093/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 91.48 | 0 | 0
5190 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Pratappur. | Assistant Engineer | Junior Engineer | BILL/00421/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.61 | 0 | 0
5191 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Pratabpur W/S scheme | Assistant Engineer | Junior Engineer | BILL/00522/2024-2025 | BP-2024-25-149 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0
5192 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pratabpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 448/BMD | 10/06/2025 | 90 | ABHIJIT MUKHERJEE | 11.84 | 0 | 0
5193 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 3 nos of 200mm X 165mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 794/BQA | 11/04/2023 | 1086 | M/S TARUN KUMAR PATRA | 12.94 | 0 | 85
5194 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharthol, No.of Mouza :- 18, Name of mouza:- Chhendua, Chamkara, Fengabasa, Amlatara, Purandihi, Kumidya, Penchaldihi, Siarbada, Deba, Andharthol, Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata , FHTC-100 Nos. | Assistant Engineer | Junior Engineer | ORD/000818/2022-2023 | 723/BQA | 30/03/2023 | 90 | GOURANGA NANDI | 25.82 | 0 | 0
5195 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharthol, No.of Mouza :- 18, Name of mouza:- Chhendua, Chamkara, Fengabasa, Amlatara, Purandihi, Kumidya, Penchaldihi, Siarbada, Deba, Andharthol, Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata | Assistant Engineer | Junior Engineer | ORD/000819/2022-2023 | 724/BQA | 30/03/2023 | 793 | SUMITA UPADHYAY | 37.06 | 28.88 | 55
5196 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (300 CUM CAPACITY) under ANDHARTHOL (Zone- V2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 3042/BQA | 06/11/2023 | 695 | G.MITRA AND ASSOCIATES | 0.63 | 0 | 100
5197 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001206/2023-2024 | 459/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 2.31 | 0 | 100
5198 | Bankura Division | Bankura Sadar Sub-Division | Barbed wire Fencing works at ANDHARTHOLE (Zone - V-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001482/2023-2024 | 209/BSD | 02/02/2024 | 10 | SANTI RANJAN MANDAL | 0.85 | 0.85 | 100
5199 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000087/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.36 | 0 | 0
5200 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000252/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.36 | 0 | 0
5201 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00151/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5202 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Jamboni mouza of Andherthole augmentaion site at Bankura-I block under BMD PHE Dte.(SM/16972) | Assistant Engineer | Junior Engineer | BILL/01357/2024-2025 | BP-2024-25-341 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.45 | 0 | 0
5203 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Andharthole (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 146/BMD | 30/04/2025 | 90 | SWAPAN ENTERPRISE | 40.67 | 0 | 0
5204 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Belboni IBS, under Bankura I ,II and Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 433/BMD | 27/06/2024 | 240 | RABINDRA NATH KHAN | 96.81 | 0 | 98
5205 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Adarsole (Zone-V) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 1469/BMD | 18/07/2023 | 60 | R.N.S. TRADING | 81.81 | 0 | 0
5206 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares for Horizontal Split Cashing Centrifugal Pumping Machineries at Belboni IBS Block Bankura-II under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 1783/BMD | 01/08/2023 | 90 | B T PROJECTS PRIVATE LIMITED | 99.61 | 98.15 | 98
5207 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿at Balarampur,panchbaga & krishnanagar mouzas ICDS Centre & house hold of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 666/BSD | 10/06/2024 | 83 | SAMIRUDDIN KHAN | 0.94 | 0.86 | 100
5208 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000425/2023-2024 | 2008/BQA | 19/07/2023 | 270 | MADHU SUDAN RAKSHIT | 176.55 | 106.95 | 83
5209 | Bankura Division | Bankura Sadar Sub-Division | Construction of Staff Room cum chlorine room, Construction of High lift Pump House and Crossing of Road by Jack pushing method for Augmentation of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001126/2024-2025 | 2975/BQA | 26/11/2024 | 447 | SUBHADIP KOLE | 62.16 | 19.09 | 80
5210 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Telebedia (Zone- M) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001195/2023-2024 | 448/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.54 | 0 | 100
5211 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000080/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.67 | 0 | 0
5212 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000237/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.67 | 0 | 0
5213 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00144/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5214 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Monoharpur OHR near Bankura university at Bakura-II block under BMD PHE.(SM/16964) | Assistant Engineer | Junior Engineer | BILL/01601/2024-2025 | BP-2024-25-380 | 13/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.93 | 0 | 0
5215 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Telebedia (Zone M) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000040/2025-2026 | 244/BMD | 14/05/2025 | 90 | DAS ENTERPRISE | 27.33 | 0 | 0
5216 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Telebedia( Zone-M) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 507/BMD | 09/07/2024 | 176 | CHAKRABORTY MINING & ENGINEERING. | 13.17 | 0 | 53
5217 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Telibedia ( Zone-M) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 1770/BMD | 01/08/2023 | 60 | WEST BENGAL ENGINEERING CO. | 81.8 | 48.24 | 59
5218 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Surface water based piped water supply scheme for Sanabundh, Kargahir and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000506/2023-2024 | 2355/BQA | 14/08/2023 | 961 | GOPAL CHANDRA CHOWDHURY | 102.5 | 0 | 87
5219 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000069/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.64 | 0 | 0
5220 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000085/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 33.2 | 0 | 0
5221 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000220/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.64 | 0 | 0
5222 | Bankura Division | Bankura Sadar Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PROPOSED GROUND WATER BASED KRISHNANAGAR (MANACHAR) PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- BARJORA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 2276/BQA | 01/08/2023 | 270 | PRAVAT SARKAR | 455.89 | 0 | 5
5223 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/10/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Krishnanagar (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Paharpur (50%), Krishnanagar (50%) & Bamandihi (50%) | Assistant Engineer | Junior Engineer | ORD/000634/2022-2023 | 573/BQA | 17/03/2023 | 15 | MS G. MITRA AND ASSOCIATES | 0.68 | 0.68 | 100
5224 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Paharpur [Part] (JL No- 51), Krishnagar [Part] (JL No- 52) & Bamandihi [Part] (JL No- 54) mouza under Barjora Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001186/2022-2023 | 354\BSD | 12/04/2022 | 15 | M/S. R. DUTTA & CO. | 4.54 | 4.54 | 95
5225 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000004/2024-2025 | 1736/BQA | 05/07/2024 | 0 | Resource Division | 40.77 | 0 | 0
5226 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 2.61 | 0 | 0
5227 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 5.21 | 0 | 0
5228 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000217/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 5.21 | 0 | 0
5229 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/00130/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0
5230 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for Krishnanagar (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16696 ) | Assistant Engineer | Junior Engineer | BILL/01097/2024-2025 | BP-2024-25-253 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.35 | 0 | 0
5231 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Krishna Nagar( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000444/2023-2024 | 1773/BMD | 01/08/2023 | 970 | GOENKA ENTERPRISE | 35.15 | 13.7 | 39
5232 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machineries and other electromechanical accessories for Ground water based Krishnanagar (Manachar) piped water supply scheme under Bankura Mechanical Division, P.H.E Dte.Block Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000578/2024-2025 | 1400/BMD | 12/12/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 39.35 | 0 | 0
5233 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Pakhanna (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%)., (Total Length:- 140mtr.). | Assistant Engineer | Junior Engineer | ORD/000199/2024-2025 | 1871/BQA | 12/07/2024 | 263 | M/S SUPRIYA CHATTERJEE | 16.18 | 0 | 0
5234 | Bankura Division | Bankura Sadar Sub-Division | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Proposed Ground Water Based Pakhanna (Manachar) Piped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Mouza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%) under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2023-2024 | 2267/BQA | 01/08/2023 | 270 | MD. AAMIR KHAN | 397.46 | 34.13 | 26
5235 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2023-2024 | 3049/BQA | 06/11/2023 | 30 | K S GROUP | 0.58 | 0 | 100
5236 | Bankura Division | Bankura Sadar Sub-Division | Construction of Guard room at OHR site in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Pakhanna (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%). | Assistant Engineer | Junior Engineer | ORD/001118/2024-2025 | 2974/BQA | 26/11/2024 | 90 | SOMA BANERJEE | 4.58 | 0 | 100
5237 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Purokonda [Part] (JL No- 55), Tajpur [Part] (JL No- 56), Pakhanna- Bhairabpur [Part] (JL No- 57), Pakhanna [Part] (JL No- 58), Gopalpur [Part] (JL No- 59) & Radhakantapur [Part] (JL No- 60) mouza under Barjora Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001187/2022-2023 | 355\BSD | 12/04/2022 | 15 | LEMNISCATE | 4.25 | 4.25 | 95
5238 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 1.79 | 0 | 0
5239 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000067/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4.56 | 0 | 0
5240 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000218/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 4.56 | 0 | 0
5241 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/00131/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
5242 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL Service connection charge for Pakhanna (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16697) | Assistant Engineer | Junior Engineer | BILL/01095/2024-2025 | BP-2024-25-252 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 15.86 | 0 | 0
5243 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Pakhanna( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000447/2023-2024 | 1775/BMD | 01/08/2023 | 60 | TAPAN KUMAR SARKAR | 35.18 | 15.54 | 45
5244 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 120 | SK ENTERPRISE | 30.4 | 0 | 0
5245 | Bankura Division | Brishnupur Sub-Division | Supply, delivery, construction, commissioning and completion of all civil works including all allied, related and enabling works for Bhubut piped water supply scheme, Block- Patrasayer, Dist- Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 2929/BQA | 26/10/2023 | 579 | SHYAMA PADA DUTTA | 349.06 | 143.01 | 95
5246 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Bhubut Piped Water Supply Scheme (SM/16700), 2 nos. sites of Kaktia Piped Water Supply Scheme (SM/16701) & 2 nos. sites of Karajbani Piped Water Supply Scheme (SM/16702) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001886/2024-2025 | 564/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
5247 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 22.5 | 0 | 0
5248 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Bhubut water supply scheme (T/W-II) at Patrasayer block under BMD PHE Dte.(SM/16700) | Assistant Engineer | Junior Engineer | BILL/01237/2024-2025 | BP-2024-25-312 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.98 | 0 | 0
5249 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Bhubut (T/W-I) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/16700) | Assistant Engineer | Junior Engineer | BILL/01465/2024-2025 | BP-2024-25-363 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0
5250 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Bhubut piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 423/BMD | 27/06/2024 | 720 | ABHIJIT MUKHERJEE | 51.08 | 22.44 | 52
5251 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF MORAR ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000387/2023-2024 | 2047/BQA | 24/07/2023 | 979 | PRINCE INDUTRIES (INDIA) | 217.47 | 133.21 | 90
5252 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Morar (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001362/2024-2025 | 3124/BQA | 19/12/2024 | 90 | BIDHAN BANERJEE | 12.96 | 0 | 0
5253 | Bankura Division | Brishnupur Sub-Division | Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Dhengasole Piped Water Supply Scheme & Augmentation of Morar Zone-A Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001940/2024-2025 | 656/BQA | 11/03/2025 | 90 | SABIR ALI KHAN | 26.99 | 0 | 50
5254 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Morar Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00164/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5255 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new serrvice connection at Morar Z-A TW-I Mouza Chowgan.SM-17237 | Assistant Engineer | Junior Engineer | BILL/01093/2024-2025 | BP-2024-25-251 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0
5256 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-A TW-III Mouza Bankati.SM - 17237 | Assistant Engineer | Junior Engineer | BILL/01141/2024-2025 | BP-2024-25-288 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.75 | 0 | 0
5257 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection charges at Morar Z-A TW-II Mouza Morar JL -117 plot- 121/1313.SM/17237 | Assistant Engineer | Junior Engineer | BILL/01143/2024-2025 | BP-2024-25-289 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.69 | 0 | 0
5258 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-A piped water supply scheme (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 1708/BMD | 28/07/2023 | 900 | M.S. ENTERPRISE | 82.01 | 56.01 | 70
5259 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of CWPH pumping machineries and other electromechanical accessories for Augmentation of Marar Zone-A and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001079/2023-2024 | 3058/BMD | 12/03/2024 | 540 | M/S NABIN GOPAL SENGUPTA | 54.11 | 0 | 40
5260 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 1410/BQA | 08/06/2023 | 270 | SUBHENDU SEKHAR GORAI | 122.67 | 36.66 | 80
5261 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for KUSTORA (Zone- W2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000892/2023-2024 | 3043/BQA | 06/11/2023 | 30 | K S GROUP | 0.56 | 0 | 100
5262 | Bankura Division | Bankura Sadar Sub-Division | Support service for design of pipe network under Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001207/2023-2024 | 460/BQA | 08/02/2024 | 30 | ROY CHOWDHURY ASSOCIATES | 4 | 0 | 100
5263 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000100/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.36 | 0 | 0
5264 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000277/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.36 | 0 | 0
5265 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00152/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5266 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Kalpather of Kustora w/s scheme under BMD PHE Dte.(SM/17242) | Assistant Engineer | Junior Engineer | BILL/00364/2025-2026 |  | 12/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.08 | 0 | 0
5267 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Kalpathar of Kustara Augmentation site (SM/17242) under BMD, PHE, Dte. | Assistant Engineer | Junior Engineer | BILL/01099/2024-2025 | BP-2024-25-250 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.28 | 0 | 0
5268 | Bankura Mechanical | Bankura Sadar Sub-Division | New serevice connection at Kalpathar of Kustara(Zone-W)augmentation scheme under BMD PHE Dte.(SM/17242) | Assistant Engineer | Junior Engineer | BILL/02196/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.45 | 0 | 0
5269 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kustora (Zone-W) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2023-2024 | 1467/BMD | 18/07/2023 | 240 | RABINDRA NATH KHAN | 81.75 | 51.24 | 63
5270 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of online Boosting pumping machineries and other electromechanical accessories at OHR site of Kustora (Zone-W) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2024-2025 | 778/BMD | 20/08/2024 | 360 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.28 | 5.08 | 65
5271 | Bankura Division | Bankura Sadar Sub-Division | Extension for collecting line of River Bed Tube Well including all related works for Augmentation of SALMA & Adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2025-2026 | 1019/BQA | 25/04/2025 | 90 | PRINCE INDUSTRIES (INDIA) | 20.46 | 0 | 1
5272 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of SALMA & Adjoining mouzas Zone- (I, II & III) Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora . Total House Hold - 320 nos | Assistant Engineer | Junior Engineer | ORD/000139/2025-2026 | 1297/BQA | 17/06/2025 | 45 | EARTH MOVING (INDIA) | 74.56 | 0 | 0
5273 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of SALMA & Adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 2028/BQA | 24/07/2023 | 708 | PRINCE INDUTRIES (INDIA) | 158.21 | 102.12 | 41
5274 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Salma (Zone- III) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora No.of Mouza :- 01 nos, Kendana (Part) Total House Hold- 17 nos. (Part A) | Assistant Engineer | Junior Engineer | ORD/000668/2023-2024 | 808/BSD | 10/08/2023 | 15 | RAHUL CHATERJEE | 0.95 | 0.92 | 100
5275 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Salma (Zone- III) W/S Scheme and its adyojing mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora No.of Mouza :- 01 nos, Kendana, Total House Hold- 18 nos.(Part B) | Assistant Engineer | Junior Engineer | ORD/000671/2023-2024 | 809/BSD | 10/08/2023 | 15 | RAHUL CHATERJEE | 0.95 | 0.92 | 100
5276 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone- I & II)) under Salma W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Salma (Zone - I) No. of Mouza :- 2 nos, Kukrakuli (Part), Harakbedia (Part), Total House Hold- 19 nos. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 814/BSD | 10/08/2023 | 15 | SONU SINGH | 0.75 | 0.74 | 100
5277 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone- I & II)) under Salma W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Chhatna, Name of OHR - Salma (Zone - I), No. of Mouza :- 03 nos, Singhir (Part), Sahebdanga (Part), Bakulia (Part) Total House Hold- 20 nos. | Assistant Engineer | Junior Engineer | ORD/000684/2023-2024 | 815/BSD | 10/08/2023 | 15 | SONU SINGH | 0.78 | 0.78 | 100
5278 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipeline in Pabra & Kastara mouzas by retrofitting works for Saltora Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001679/2024-2025 | 689/BSD | 12/06/2024 | 15 | TAPAS KUMBHAKAR | 0.94 | 0 | 100
5279 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipeline in Pabra & Kastara mouzas by retrofitting works for Saltora Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/001680/2024-2025 | 690/BSD | 12/06/2024 | 15 | TAPAS KUMBHAKAR | 0.68 | 0 | 100
5280 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipeline in Pabra & Kastara mouzas by retrofitting works for Saltora Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/001681/2024-2025 | 691/BSD | 12/06/2024 | 15 | TAPAS KUMBHAKAR | 0.94 | 0 | 100
5281 | Bankura Division | Bankura Sadar Sub-Division | Balance work for laying HDPE pipe line from Durlavpur air valve to Durlavpur Muslimpara to increase water pressure at Durlavpur mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000724/2023-2024 | 825\BSD | 11/08/2023 | 15 | SOMA BANERJEE | 0.61 | 0.61 | 100
5282 | Bankura Division | Bankura Sadar Sub-Division | Extra laying of UPVC Pipe line at Bakulia, Harakbedia, Sahebdanga & Kukrakuli mouza & cleaning, washing of Pipeline at Satdeuli mouza retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001038/2023-2024 | 1141/BSD | 22/11/2023 | 10 | SRIJAN CONSTRUCTION | 0.86 | 0 | 100
5283 | Bankura Division | Bankura Sadar Sub-Division | Supplying and Laying of HDPE pipeline to increase the water pressure and other allied works at Kukhrakuri Village under Salma (Zone-I) Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora. | Assistant Engineer | Junior Engineer | ORD/001788/2024-2025 | 499/BQA | 25/02/2025 | 30 | TAPAS KUMBHAKAR | 6.37 | 0 | 0
5284 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000103/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.96 | 0 | 0
5285 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000282/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.96 | 0 | 0
5286 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall, Low Lift Pump house, Sinking of Tube well of Proposed Ground Water Based Nakaijuri PIped Water Supply Scheme & Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 812/BQA | 03/04/2025 | 273 | GOUTAM GHOSH | 36.72 | 0 | 10
5287 | Bankura Division | Bankura Sadar Sub-Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone - A) under Onda Block (BRGF Phase - I Project). | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 1910/BQA | 13/07/2023 | 270 | JAI BHARAT COMMERCIAL CORPORATION | 153.6 | 153.59 | 85
5288 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 (one) nos Tube well & Repairing and Renovation of RCC Elevated Over Head Reservoir under Augmentation of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2024-2025 | 2349/BQA | 09/09/2024 | 569 | GOUTAM GHOSH | 27.12 | 0 | 100
5289 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall at Tail end TW Site at Birsinghapur village in connection with Jal Jeevan Mission (JJM) for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Total Length:- 42 mtr.) | Assistant Engineer | Junior Engineer | ORD/000389/2025-2026 | 807/BSD | 01/09/2025 | 45 | SUMAN DIHA | 4.76 | 0 | 0
5290 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000143/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.11 | 0 | 0
5291 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000241/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.11 | 0 | 0
5292 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Soft stater Panel MCC Panel and other electromechanical acessories for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000325/2024-2025 | 866/BMD | 29/08/2024 | 240 | M.S. ENTERPRISE | 59.58 | 0 | 100
5293 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-A) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000545/2023-2024 | 1981/BMD | 28/08/2023 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 34.93 | 22.84 | 66
5294 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 300 mm X 200 mm X 150 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Pump house & Boundary wall at tubewell Site for Ground Water Based Bansi Piped Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000184/2025-2026 | 1322/BQA | 17/06/2025 | 137 | M/S. AMAL KUMAR SARKAR | 27.39 | 0 | 0
5295 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of 100 Cum. Clear Water Reservoir, Pump House, Boundary Wall, Distribution pipeline with ancillary works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Ground Water Based Bansi Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000528/2023-2024 | 2362/BQA | 14/08/2023 | 872 | SOUHARDYA BUSINESSLINE | 125.04 | 60.54 | 80
5296 | Bankura Division | Bankura Mechanical Sub-Division | Preparation of Detailed Project Report for Proposed Ground Water Based Bansi Pipe Water Supply Scheme under Bankura Division, Block : Sarenga, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001078/2023-2024 | 3540/BQA | 29/12/2023 | 30 | LEMNISCATE | 2.62 | 2.55 | 90
5297 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000013/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 0.98 | 0 | 0
5298 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000198/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.92 | 0 | 0
5299 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/00203/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
5300 | Bankura Mechanical | Bankura Mechanical Sub-Division | New 3 phase connection for Banshi water Supply Scheme | Assistant Engineer | Junior Engineer (Contractual) | BILL/00949/2024-2025 | BP-2024-25-227 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0
5301 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Bansi piped water supply scheme Block Sarenga under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000464/2023-2024 | 1806/BMD | 03/08/2023 | 1320 | M/S BIPUL BANERJEE | 35.21 | 16.42 | 35
5302 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF DHENGASOLE PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000386/2023-2024 | 2046/BQA | 24/07/2023 | 979 | PRINCE INDUTRIES (INDIA) | 166.93 | 83.22 | 90
5303 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Dhengasole Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00171/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5304 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new connection at Mouza Haraboti. Aug of Dhengasole w/s scheme.SM/17699 | Assistant Engineer | Junior Engineer | BILL/00631/2026-2027 |  | 10/06/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.85 | 0 | 0
5305 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Dhengasole Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01608/2023-2024 | BP-2023-24-135 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.74 | 0 | 0
5306 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro-mechanical accessories at Boosting tubewell for Augmentation of Dhengasole piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 143/BMD | 30/04/2025 | 90 | TAPAN KUMAR SARKAR | 21.51 | 0 | 0
5307 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW at OHR and PH site for Augmentation of Dhengasole and Adjoining mouza water supply scheme Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000153/2024-2025 | 496/BMD | 09/07/2024 | 360 | PRADIP KUMAR DHABAL | 23.32 | 0 | 61
5308 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Dhengasole piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000514/2023-2024 | 1879/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 67.88 | 0 | 50
5309 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from L053-Ramchandrapur to Bhelaidiha under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-406, Road Length-3.864 Km.( proposed sub-surface water based Handulia pipe water supply scheme) | Assistant Engineer | Junior Engineer | BILL/01438/2024-2025 | BP/569/2024-25 | 28/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0
5310 | Bankura Division | Khatra Sub-Division | Repair and Maintenance work of the Road from Bagdoba to Ramchandrapur Via Goalbathan under Simlapal Block in the District of Bankura,Vide Package No- Road Length-2.2 Km. (Proposed sub-surface water based Handulia Pipe water supply scheme.) | Assistant Engineer | Junior Engineer | BILL/01440/2024-2025 | BP/483/2024-25 | 22/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0
5311 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works, Construction of Clear Water Reservoir, Pump House, Boundary Wall with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub-surface Water Based Handulia Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2023-2024 | 2088/BQA | 27/07/2023 | 890 | SANJOY PATRA | 250.83 | 79.16 | 82
5312 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
5313 | Bankura Division | Khatra Sub-Division | Preparation of Detailed Project Report for Proposed sub-surface Water Based Handulia Piped Water Supply Scheme under Bankura Division, Block-Simlapal, District-Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001081/2023-2024 | 3544/BQA | 29/12/2023 | 30 | LEMNISCATE | 2.81 | 2.78 | 90
5314 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 5 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17440] and 1 no. site of Proposed sub-surface Water Based Handulia Piped Water Supply Scheme (SM/18044) within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001925/2024-2025 | 169\KSD | 07/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 90
5315 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 23.61 | 0 | 0
5316 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000194/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.47 | 0 | 0
5317 | Bankura Mechanical | Khatra Sub-Division | New service connection of Handulia PWSS ,Mouza-Ramchandrapur, G.p.- Parsala JL No.-5 Plot no.-8 under BMSD(D) PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00001/2024-2025 | BP-2024-25-96 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0
5318 | Bankura Mechanical | Khatra Sub-Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | Assistant Engineer | Junior Engineer | BILL/00199/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
5319 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Handulia piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000564/2023-2024 | 2031/BMD | 01/09/2023 | 836 | M/S SOMA ENTERPRISES | 48.85 | 35.67 | 30
5320 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2024-2025 | 1497/BQA | 18/06/2024 | 287 | SWAPAN KUMAR CHANDRA | 17.8 | 0 | 90
5321 | Bankura Division | Khatra Sub-Division | Supply of sluice valve, construction of valve chamber and MS pipeline work for distribution main of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2025-2026 | 1316/BQA | 17/06/2025 | 60 | PRINCE INDUSTRIES (INDIA) | 7.66 | 0 | 95
5322 | Bankura Division | Khatra Sub-Division | Sinking 3 Nos 300x200 Rig Bore Tubewell, Construction of 250 Cum OHR, 3 Nos. Pump House, Boundary Wall, Rising Main and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2023-2024 | 2330/BQA | 14/08/2023 | 688 | PRINCE INDUTRIES (INDIA) | 566.03 | 428.61 | 82
5323 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with making MS Tee and ancillary works at Baraamjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2023-2024 | 2580/BQA | 15/09/2023 | 30 | SANJOY PATRA | 4.02 | 4 | 50
5324 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000835/2023-2024 | 2961/BQA | 31/10/2023 | 30 | GEO SOLUTION | 4.45 | 4.45 | 96
5325 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
5326 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 60.93 | 0 | 0
5327 | Bankura Mechanical | Khatra Sub-Division | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00029/2024-2025 | BP-2024-25-12 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
5328 | Bankura Mechanical | Khatra Sub-Division | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00122/2024-2025 | BP-2024-25-13 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0
5329 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00218/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5330 | Bankura Division | Khatra Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 200 Metre deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001298/2023-2024 | 809/BQA | 07/03/2024 | 45 | ANJAN INFRASTUCTURE PVT LTD. | 50.34 | 46.56 | 98
5331 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 2 nos. OHR and 4 nos. Pump House site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302] within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001920/2024-2025 | 164\KSD | 07/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 90
5332 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 6 nos. Pump House site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302] within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001921/2024-2025 | 165\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
5333 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 1 no. site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302], 3 nos. site of Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17438] and 1 no. site Proposed Ground Water Based Bansi Pipe Water Supply Scheme [SM/18038] within Sarenga Block and 1 no. site of Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) [SM/17434] under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001922/2024-2025 | 166\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
5334 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 700 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Kuldiha water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001977/2024-2025 | 671/BQA | 12/03/2025 | 90 | AJIT KUMAR PAUL | 23.77 | 0 | 90
5335 | Bankura Mechanical | Khatra Sub-Division | New service connection charges for Kuldihi, Application No- 2004835893 | Assistant Engineer | Junior Engineer | BILL/00701/2024-2025 | BP-2024-25-164 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.31 | 0 | 0
5336 | Bankura Mechanical | Khatra Sub-Division | New Service Connection for Kuldihi , Application No- 2004835760 | Assistant Engineer | Junior Engineer | BILL/00702/2024-2025 | BP-2024-25-165 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
5337 | Bankura Mechanical | Khatra Sub-Division | New Service connection charge of WBSEDCL Kuldiha | Assistant Engineer | Junior Engineer | BILL/00703/2024-2025 | BP-2024-25-166 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0
5338 | Bankura Mechanical | Khatra Sub-Division | New 3 phase connection for Kuldihi W/S (Scheme) Telijant site | Assistant Engineer | Junior Engineer | BILL/00950/2024-2025 | BP-2024-25-230 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0
5339 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other allied electro-mechanical accessories for Augmentation for KULDIHI piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000135/2024-2025 | 441/BMD | 27/06/2024 | 187 | ABHIJIT MUKHERJEE | 19.59 | 4.57 | 65
5340 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kuldiha & its adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000568/2023-2024 | 2034/BMD | 01/09/2023 | 1763 | A.K.INDUSTRIES | 72.58 | 54 | 66
5341 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Kuldihi water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001094/2023-2024 | 3069/BMD | 12/03/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.85 | 36.21 | 70
5342 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 45 | UNICON INDIA | 317.75 | 0 | 100
5343 | Bankura Division | Brishnupur Sub-Division | extra UPVC pipe line from Joytunga Rising main to Chandan pur village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone- G) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2021-2022 | 845/BSD | 18/08/2021 | 15 | TARINI CHARAN UPADHYAY | 4.96 | 4.95 | 0
5344 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline from Debedia Atchala to Salghata village to increase pressure in Debedia (86) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001399/2022-2023 | FHTC/16 | 16/12/2022 | 0 | SUBHENDU SEKHAR GORAI | 8.13 | 0 | 0
5345 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC pipe line & extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001429/2022-2023 | FHTC/15 | 15/12/2022 | 0 | SK. SAHAJAHAN | 3.62 | 0 | 0
5346 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/001488/2022-2023 | FHTC/19 | 19/12/2022 | 0 | SUBHADIP KOLEY | 2.22 | 0 | 0
5347 | Bankura Division | Brishnupur Sub-Division | Household survey in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 22) | Assistant Engineer | Junior Engineer | VCH/001489/2022-2023 | FHTC/19 | 19/12/2022 | 0 | EARTH MOVING (INDIA) | 0.38 | 0 | 0
5348 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household - 2536 nos. | Assistant Engineer | Junior Engineer | VCH/001491/2022-2023 | FHTC/19 | 19/12/2022 | 0 | UNIVERSAL CONSTRUCTION | 21.12 | 0 | 0
5349 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 | Assistant Engineer | Junior Engineer | VCH/002683/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM BHOWMIK | 59.53 | 0 | 0
5350 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-A ), Total House Hold - 200 | Assistant Engineer | Junior Engineer | VCH/002701/2021-2022 | FHTC/2 | 02/03/2022 | 0 | SUBHANKAR BANERJEE | 1.95 | 0 | 0
5351 | Bankura Division | Brishnupur Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Func tional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joykrishnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Joykrishnapur (Zone - I) No.of Mouza :- Ratganj Madhavpur , sl no - 26 | Assistant Engineer | Junior Engineer | VCH/002702/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S T.P. HAZRA & SONS | 4.77 | 0 | 0
5352 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 01 no., (Radhakantapur), Total House Hold - 463 nos | Assistant Engineer | Junior Engineer | VCH/002799/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GANESH ROY | 26.6 | 0 | 0
5353 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000401/2023-2024 | 2086/BQA | 27/07/2023 | 540 | DIVINE | 175.17 | 110.56 | 80
5354 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000129/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.07 | 0 | 0
5355 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000230/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.07 | 0 | 0
5356 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chaknakaijuri & its adjoining Mouzas water supply scheme under Onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000540/2023-2024 | 1976/BMD | 28/08/2023 | 612 | INDRAJIT MITRA | 56.67 | 36.52 | 70
5357 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (phase-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2024-2025 | 1808/BQA | 11/07/2024 | 598 | M/S TARUN KUMAR PATRA | 123.21 | 0 | 100
5358 | Bankura Division | Bankura Sadar Sub-Division | 150 mm dia, 200 mm dia & 250 mm dia MS main connecting Pipe line interconnection from river bed TW Rising main,BRGF Rising main line & connection new OHR,old OHR & OHR site CWR under KENJAKURA W/S Scheme under Bankura Sadar Sub -Division of Bankura Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000258/2025-2026 | 1537/BQA | 14/07/2025 | 30 | JAGADISH BANERJEE | 12.06 | 0 | 100
5359 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001190/2023-2024 | 442/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.23 | 0 | 100
5360 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House, Low lift Pump House cum chlorine room and Sinking of 01 no. 200 mm dia. Horizontal River Bed Tube Well under Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | Assistant Engineer | Junior Engineer | ORD/001392/2024-2025 | 39/BQA | 02/01/2025 | 454 | PRANABANANDA TEWARY | 41.73 | 0 | 30
5361 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000123/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.32 | 0 | 0
5362 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000265/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.32 | 0 | 0
5363 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | Assistant Engineer | Junior Engineer | BILL/00191/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
5364 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machinery and other electro mechanical accessories for Augmentation of piped water supply scheme for Kenjakura and its adjoining Mouzas water supply scheme under Bankura Mechanical Division PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001090/2023-2024 | 3065/BMD | 12/03/2024 | 120 | SWAPAN ENTERPRISE | 18.27 | 17.98 | 100
5365 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarbati (228), Jamdoba (229), , Baruipara (236), Teliberia (238), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household-122 NOS | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1349/BQA | 02/06/2023 | 60 | SIB SANKAR CHOWDHURY | 24.06 | 23.37 | 100
5366 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000296/2023-2024 | 1914/BQA | 13/07/2023 | 993 | GOUTAM BHATTACHRYYA | 234.49 | 200.88 | 95
5367 | Bankura Division | Bankura Sadar Sub-Division | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 | Assistant Engineer | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 45 | SAMIRUDDIN KHAN | 5.4 | 1.5 | 100
5368 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 204/13 -15) in between Ramsagar Rly. Station and Bishnupur Rly. station in Sur Managar mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) & Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002046/2024-2025 | 683/BQA | 12/03/2025 | 60 | M/S TARUN KUMAR PATRA | 47.19 | 0 | 0
5369 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000115/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.8 | 0 | 0
5370 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000285/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.8 | 0 | 0
5371 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation money for load enhancement at Puncha Teliberia under BMD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00296/2024-2025 | BP-2024-25-60 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0
5372 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-B) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 2122/BMD | 22/09/2023 | 725 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 75.09 | 41.99 | 45
5373 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DANNA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2023-2024 | 2322/BQA | 14/08/2023 | 1022 | DEBAKI RANJAN SARKAR | 683.53 | 146.17 | 65
5374 | Bankura Division | Brishnupur Sub-Division | Crossing of Rail Line at KM 264/5 to 264/6 by Jack pushing method (600 mm dia RCC Hume pipes for casing with laid pipe of MS) for Laying of Pipe Line for Hamirhati and its adjoining mouzas water under Augmentation of Rampur water supply scheme & Danna water supply scheme under Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001747/2024-2025 | 448/BQA | 20/02/2025 | 131 | SWAPAN KUMAR CHANDRA | 26.55 | 0 | 90
5375 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no Tubewell and Construction of Boundary wall for Augmentation of Patrasayer Water Supply Scheme & Danna Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001938/2024-2025 | 653/BQA | 11/03/2025 | 358 | BROTIN UPADHYAY | 20.43 | 0 | 71
5376 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 245.78 | 0 | 0
5377 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Danna (T/W-II) w/s scheme at Patrasayer block under BMD PHE Dte.(SM/18302) | Assistant Engineer | Junior Engineer | BILL/01600/2024-2025 | BP-2024-25-391 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0
5378 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Danna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000034/2025-2026 | 239/BMD | 14/05/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 12.46 | 0 | 0
5379 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000125/2024-2025 | 1073/BMSD | 05/07/2024 | 60 | KASHINATH DEY | 4.38 | 0 | 0
5380 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at P/H of adjoining mouza of Danna piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 1075/BMSD | 05/07/2024 | 60 | KINGKINI TRADERS | 4.39 | 4.27 | 100
5381 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danna Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 883/BMD | 04/05/2023 | 870 | M/S NABIN GOPAL SENGUPTA | 68.09 | 29.42 | 55
5382 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary wall in connection with Jal Jeevan Mission (JJM) for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.. (Total Length:- 120mtr.). | Assistant Engineer | Junior Engineer | ORD/000077/2025-2026 | 1016/BQA | 25/04/2025 | 90 | RUFIKUL MONDAL | 14.32 | 0 | 0
5383 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe line for Mouleswar,Khamarberiya,Datina,Datina purusatampur,Gogra & Jamra madhabpur Mouzas under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2025-2026 | 1302/BQA | 17/06/2025 | 379 | SHYAMAL KUMAR DAS | 45.45 | 0 | 0
5384 | Bankura Division | Bankura Sadar Sub-Division | Crossing of Road by Jack pushing method ( 600 mm dia Hump pipe (NP3/NP4 for casing) for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Location of Site: Gogra village, Khamareberia and adjacent places beside ( NH-60 Road). | Assistant Engineer | Junior Engineer | ORD/000190/2024-2025 | 1861/BQA | 12/07/2024 | 45 | SWAPAN KUMAR CHANDRA | 21.02 | 4.64 | 100
5385 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000297/2023-2024 | 1915/BQA | 13/07/2023 | 903 | APEX ENTERPRISE | 224.56 | 180.21 | 90
5386 | Bankura Division | Bankura Sadar Sub-Division | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 | Assistant Engineer | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 45 | SAMIRUDDIN KHAN | 5.4 | 2.39 | 100
5387 | Bankura Division | Bankura Sadar Sub-Division | Construction of Sinking of 2 (two) nos DTH Tube well, Pump House & Toilet and Repairing and Renovation of 450 Cum OHR for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001326/2024-2025 | 3122/BQA | 19/12/2024 | 194 | APEX ENTERPRISE | 48.48 | 0 | 100
5388 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000114/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.85 | 0 | 0
5389 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000287/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.85 | 0 | 0
5390 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at Banshdanga under BMD, PHE dte. | Assistant Engineer | Junior Engineer | BILL/00289/2024-2025 | 1 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0
5391 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-A) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000555/2023-2024 | 1991/BMD | 28/08/2023 | 600 | ABHIJIT MUKHERJEE | 47.76 | 24.56 | 10
5392 | Bankura Division | Khatra Sub-Division | Laying Rising Main using different dia D.I - K9 pipes from WTP to Existing ESRs & Proposed OHRs at Mukutmanipur, Khatra & Ranibundh under Augmentation of Surface Water Based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibandh under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000737/2023-2024 | 2741/BQA | 04/10/2023 | 546 | SWAPAN KUMAR UPADHYAY | 217.09 | 11.72 | 20
5393 | Bankura Division | Khatra Sub-Division | Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion in all respect of all Civil , Mechanical and Electrical works ( excluding Supply and Installation of Raw Water Pumps, Clear Water High Lift Pumps , Motors, Panels, Electrical Substation and allied works, Chlorination arrangement, SCADA and Yard Lighting including related works ) including all allied , related and enabling works of Fixed type Intake Jetty with pump house, Access Bridge, Laying of Raw Water Rising Main, Bank Protection, Construction of Sub-station Building, Clear Water Pump House and 5 MLD capacity Water Treatment (WTP) based on conventional technologies with 20% overloading on EPC/ Turnkey basis in a single package for Augmentation of Mukutmanipur, Khatra & Ranibandh Piped Water Supply Scheme under Bankura Division, PHE Dte. , Dist - Bankura with impounded surface water of Kangsabati Dam at Mukutmanipur as source of water followed by 03(Three) months of Trial Run and subsequent Operation & Maintenance for 03(Three) years. | Assistant Engineer | Junior Engineer | ORD/000964/2023-2024 | 3479/BQA | 21/12/2023 | 540 | CONCORD ENGINEERING | 3377.5 | 0 | 0
5394 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000155/2023-2024 | 112/BQA | 10/01/2024 | 0 | Resource Division | 1295.36 | 0 | 0
5395 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for new WTP for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 95/BMD | 23/04/2025 | 120 | M/S P.P ELECTRICALS | 314.08 | 0 | 0
5396 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for at new intake for Augmentation of Intake WTP & rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, & Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000634/2024-2025 | 1475/BMD | 10/01/2025 | 120 | DEBJYOTI BASU | 107.35 | 0 | 0
5397 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing Yard lighting arrangement at new WTP site for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000872/2024-2025 | 2035/BMD | 07/03/2025 | 240 | UNITED TRADERS | 14 | 0 | 60
5398 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5399 | Bankura Division | RWS Bankura Sub-Division | New Connection at Sushunia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00708/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5400 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5401 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 44 | 48
5402 | Bankura Division | Bankura Sadar Sub-Division | Quotation of WBSEDCL for the scheme of SM/10921 | Assistant Engineer | Junior Engineer | BILL/00851/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
5403 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
5404 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
5405 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Kharakpur, Radhadamodarpur, Gopinathpur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00281/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
5406 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5407 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5408 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.16 | 48
5409 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-96, Mouza-Dangarsai, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00287/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
5410 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5411 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5412 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
5413 | Bankura Division | Brishnupur Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. | Assistant Engineer | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 40.2 | 24.25 | 0
5414 | Bankura Division | Brishnupur Sub-Division | Carriage of Departmental Materials i.e. FERRULE, CHOLORINE etc. In connection with Jal Jeevan Mission & JAL SWAPNA Under Bishnupur Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2022-2023 | 98/VSD | 11/04/2022 | 180 | TAPAS KUMAR HAZRA | 1.92 | 0.81 | 50
5415 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 125 out of 921 | Assistant Engineer | Junior Engineer | ORD/000413/2020-2021 | 868/BQA | 25/02/2021 | 30 | TAPAN KUMAR MANDAL | 10.08 | 0 | 0
5416 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 140 out of 921 | Assistant Engineer | Junior Engineer | ORD/000414/2020-2021 | 869/BQA | 25/02/2021 | 30 | TAPAN KUMAR MANDAL | 10.76 | 0 | 0
5417 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0 | 0
5418 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) chowbeta mouza | Assistant Engineer | Junior Engineer | VCH/001470/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
5419 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) Mouza Sankarlayekerdanga | Assistant Engineer | Junior Engineer | VCH/001471/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 2.7 | 0 | 0
5420 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) Mouza Jiabandi | Assistant Engineer | Junior Engineer | VCH/001472/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.59 | 0 | 0
5421 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} of Kotalpukur (Zone- B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001181/2021-2022 | FHTC/29 | 29/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 63.55 | 0 | 0
5422 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5423 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Kendbonadhagora Saldiha | Assistant Engineer | Junior Engineer | BILL/00527/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
5424 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10864. | Assistant Engineer | Junior Engineer | BILL/00763/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
5425 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5426 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 34.5 | 48
5427 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5428 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Niyasa,Dubrajpur | Assistant Engineer | Junior Engineer | BILL/00510/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
5429 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5430 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.52 | 48
5431 | Bankura Division | RWS Bankura Sub-Division | New Connection charge at Dhuyakaki, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00422/2023-2024 | BP-147/2024-25 | 03/07/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5432 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5433 | Bankura Division | Khatra Sub-Division | New service connection for Bamunpathri Mini water supply scheme under Bankura Division PHE DTE |  | Junior Engineer | BILL/00134/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
5434 | Bankura Division | Khatra Sub-Division | New Service Connection at Bamunpathri,Mondalgram,Simlapal Block, PHE Dte. |  | Junior Engineer | BILL/00321/2023-2024 | FHTC/04 | 29/04/2024 | 0 | SIMLAPAL CCC | 0.12 | 0 | 0
5435 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5436 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5437 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
5438 | Bankura Division | RWS Bankura Sub-Division | New Connection at Aulia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00433/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
5439 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
5440 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (98) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000102/2020-2021 | 140/KSD | 12/02/2021 | 15 | ASOKE KUMAR SAHU | 3.98 | 7.3 | 0
5441 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 ( Panchbaga.), Total House Hold - 438 | Assistant Engineer | Junior Engineer | ORD/000311/2020-2021 | 1363/BQA | 08/10/2020 | 30 | GOUTAM BHOWMIK | 37.93 | 53.32 | 0
5442 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (38) & Jhikri (40) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2020-2021 | 1774/BQA | 09/12/2020 | 30 | GOUTAM BHATTACHRYYA | 19.99 | 0 | 20
5443 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tilabani (39) & Baurisol (42) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2020-2021 | 1775/BQA | 09/12/2020 | 30 | GOUTAM BHATTACHRYYA | 23.39 | 0.93 | 20
5444 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kusumkanali (41) & Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000351/2020-2021 | 1776/BQA | 09/12/2020 | 30 | APEX ENTERPRISE | 23.87 | 1.76 | 0
5445 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.8 | 0
5446 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41), Baurisol (42) & Maidhara (46) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 39) | Assistant Engineer | Junior Engineer | ORD/000541/2020-2021 | 281/KSD | 10/12/2020 | 62 | GOUTAM BHATTACHRYYA | 0.35 | 0.23 | 0
5447 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe lineto cover Jamda (38 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- ll ) of piped water supply scheme for Lakshmisagar & its adjoining mouzas at block - Simlapal dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 07 | Assistant Engineer | Junior Engineer | VCH/000264/2022-2023 | FHTC/18 | 18/04/2022 | 0 | BHATTACHARIYA CONSTRUCTION | 3.45 | 0 | 0
5448 | Bankura Division | Khatra Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Maliara, Kotulpur, Kanchanpur , Dadhimukha, , No Of Mouzas-68 , Total House Hold - 14124. | Assistant Engineer | Junior Engineer | VCH/000272/2021-2022 | FHTC/12 | 23/04/2021 | 0 | TAPAS DEY | 2.23 | 0 | 0
5449 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | VCH/001318/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 4.92 | 0 | 0
5450 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 9) | Assistant Engineer | Junior Engineer | VCH/001319/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 4.92 | 0 | 0
5451 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | VCH/001320/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 4.96 | 0 | 0
5452 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | VCH/001321/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 4.94 | 0 | 0
5453 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 12) | Assistant Engineer | Junior Engineer | VCH/001322/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0
5454 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 13) | Assistant Engineer | Junior Engineer | VCH/001323/2021-2022 |  | 28/09/2021 | 0 | M/S TARUN KUMAR PATRA | 3.63 | 0 | 0
5455 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (38) & Jhikri (40) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001386/2020-2021 |  | 01/03/2021 | 0 | GOUTAM BHATTACHRYYA | 3.46 | 0 | 0
5456 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tilabani (39) & Baurisol (42) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001387/2020-2021 |  | 01/03/2021 | 0 | GOUTAM BHATTACHRYYA | 7.71 | 0 | 0
5457 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kusumkanali (41) & Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001388/2020-2021 |  | 01/03/2021 | 0 | APEX ENTERPRISE | 19.91 | 0 | 0
5458 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Khandarani (155) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No. 03), | Assistant Engineer | Junior Engineer | VCH/001547/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SUBHADIP KOLEY | 4.85 | 0 | 0
5459 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09), | Assistant Engineer | Junior Engineer | VCH/001548/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SUBHADIP KOLEY | 2.42 | 0 | 0
5460 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipeline to cover sonarekh( Part) , Sitaldihi , Baikunthpur , mouzas for construction and commissioning of FHTC in connection with Jal Jeevan Misssion ( JJM) and Jalswapna of Sonadaha - Zone-Q under Bankura -I,II, & Barjora Block W/S Scheme ( BRGF Ph-I ) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001549/2021-2022 | FHTC/11 | 11/10/2021 | 0 | NAYAN BARDHAN | 2.87 | 0 | 0
5461 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 04 no [Narasole, Taljhoria, Khabanigoparpur (Part), Jhikuria] Total House Hold- 359 | Assistant Engineer | Junior Engineer | VCH/001550/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAS KUMAR HAZRA | 20.59 | 0 | 0
5462 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456, | Assistant Engineer | Junior Engineer | VCH/001589/2021-2022 | FHTC/08 | 08/10/2021 | 0 | MUNMUN UPADHYAY | 33.29 | 0 | 0
5463 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2025-2026 | 1309/BQA | 17/06/2025 | 123 | GOPAL CHANDRA CHOWDHURY | 64.96 | 0 | 0
5464 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000189/2024-2025 | 1860/BQA | 12/07/2024 | 90 | TAPAS DEY | 4.62 | 0 | 0
5465 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 2215/BQA | 21/08/2024 | 377 | SUBHENDU BANERJEE | 19.46 | 0 | 0
5466 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
5467 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000492/2023-2024 | 2344/BQA | 14/08/2023 | 872 | GOPAL CHANDRA CHOWDHURY | 659.32 | 0 | 30
5468 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-3B) (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/001164/2022-2023 | 184\KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.62 | 3.62 | 100
5469 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001296/2023-2024 | 820/BQA | 11/03/2024 | 90 | COSMIC CONSTRUCTION | 8.64 | 0 | 0
5470 | Bankura Division | Khatra Sub-Division | "Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) At Karali More, (2) Near Dedua Bridge & (3) Near SDO Office More" | Assistant Engineer | Junior Engineer | ORD/001966/2024-2025 | 686/BQA | 12/03/2025 | 296 | GOPAL CHANDRA CHOWDHURY | 23.62 | 0 | 0
5471 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 49.27 | 0 | 0
5472 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000204/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 24.58 | 0 | 0
5473 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhanga Bandh (91), Bheduasol (92), Kamalpur (93), Sayer Bankra (99), Kotalpur (100), Ramnagar (101), Dhabani (102), Manipur (105), Guinandi (106), Itapanchira (107), Paharpur (108), Nischintapur (118) & Shalihan (119) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2309 nos. | Assistant Engineer | Junior Engineer | ORD/000016/2022-2023 | 927/BQA | 21/04/2022 | 60 | GOPAL CHANDRA CHOWDHURY | 122.98 | 121.4 | 100
5474 | Bankura Division | Bankura Sadar Sub-Division | Laying & fitting fixing of MS pipe line for 3rd & 4th nos ground water tube well to CWR at Aguribandh Puiisole Head Work Site (Nischintepur) of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Aguribandh Puiisole (Zone-A, Zone-B , Zone-C ,Zone-D & Zone-E) , Under Onda BRGF W/S water supply Scheme of Onda Block under Bankura Sadar Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000558/2021-2022 | 22/BSD | 07/01/2022 | 15 | ZAKIR HOSSAIN MONDAL | 4.69 | 4.66 | 0
5475 | Bankura Division | Bankura Sadar Sub-Division | Laying & fitting fixing of MS pipe line for 1st & 2nd nos ground water tube well to CWR at Aguribandh Puiisole Head Work Site (Nischintepur) of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Aguribandh Puiisole (Zone-A, Zone-B , Zone-C ,Zone-D & Zone-E) , Under Onda BRGF W/S water supply Scheme of Onda Block under Bankura Sadar Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000559/2021-2022 | 21/BSD | 07/01/2022 | 15 | M/S NAYAN BARDHAN | 4.87 | 4.81 | 0
5476 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Bhanga Bandh (91), Bheduasol (92), Kamalpur (93), Sayer Bankra (99), Kotalpur (100), Ramnagar (101), Dhabani (102), Manipur (105), Guinandi (106), Itapanchira (107), Paharpur (108), Nischintapur (118) & Shalihan (119) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000904/2021-2022 | 89/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.77 | 0.77 | 100
5477 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0
5478 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2021-2022 | 571/BQA | 17/03/2022 | 0 | Resource Division | 14.22 | 0 | 0
5479 | Bankura Division | Bankura Sadar Sub-Division | laying & repairing of UPVC pipe line (damaged due to widening - of PMGSY road from Kalisen to Monipur village ) of Aguri band and adjoining mouzas water supply scheme Zone - B Onda water supply scheme BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, Jal Jeevan Mission (JJM) and JAL SWAPNA programme fund sl no - 11 | Assistant Engineer | Junior Engineer | VCH/003078/2021-2022 | FHTC/29 | 29/03/2022 | 0 | TAPAS KUMBHAKAR | 4.99 | 0 | 0
5480 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 |  | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 28.91 | 4.07 | 95
5481 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAGDALLA (Zone - S) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla. No.of Mouza :- 01 (Dhaldanga (PART) Total House Hold - 569 |  | Junior Engineer | ORD/000185/2020-2021 | 2126/BQA | 31/12/2020 | 1916 | M/S TARUN KUMAR PATRA | 40.66 | 0 | 0
5482 | Bankura Division | Bankura Sadar Sub-Division | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAGDALLA (Zone - S) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla. No.of Mouza :- 04 (Dhaldanga (PART), Chak dhaldanga, Gobindapur & Chinchuria) Total House Hold - 569 |  | Junior Engineer | ORD/000186/2020-2021 | 2127/BQA | 31/12/2020 | 1917 | M/S TARUN KUMAR PATRA | 40.67 | 0 | 0
5483 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01 no, Shyampur (part) Total House Hold - 75 (Sl No of Work- 13) |  | Junior Engineer | ORD/000196/2020-2021 | 105/ BSD | 12/02/2021 | 20 | TAPAS KUMBHAKAR | 4.78 | 8.36 | 0
5484 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampur (part) Total House Hold - 75 (Sl No of Work- 16) |  | Junior Engineer | ORD/000199/2020-2021 | 108/ BSD | 12/02/2021 | 20 | TAPAS KUMAR HAZRA | 4.8 | 9.02 | 0
5485 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Shyamnagar (22), by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  | Junior Engineer | VCH/001175/2021-2022 | FHTC/29 | 29/07/2021 | 0 | BIKASH MANDAL | 2.53 | 0 | 0
5486 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Khandarani (155) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2020-2021 | 165/BQA | 18/01/2021 | 30 | PRADYUMNA KOLEY | 11.69 | 0 | 0
5487 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline from Dhabani Shib Mandir to Keliapathar village to increase pressure in Keliapathar village in Gobarda (152) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 210/KSD | 03/06/2022 | 20 | D. S. ENTERPRISE | 4.02 | 0 | 0
5488 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gobarda (152) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2020-2021 | 166/BQA | 18/01/2021 | 30 | SUBHENDU SEKHAR GORAI | 26.91 | 0 | 0
5489 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Itamara (60), Jambeda (64), Deulagara (153) & Domohani (154) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2020-2021 | 167/BQA | 18/01/2021 | 30 | PRADIP CHAKRABORTY | 12.31 | 0 | 0
5490 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2020-2021 | 1773/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 17.57 | 16.27 | 20
5491 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Gobarda (152) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/000366/2021-2022 | 772/KSD | 25/11/2021 | 15 | PRADYUMNA KOLEY | 2.48 | 0 | 0
5492 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sinyajora (32), Bhelaidiha (36) & Korkhi (37) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2020-2021 | 1771/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 13.16 | 25.14 | 20
5493 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) | Assistant Engineer | Junior Engineer | ORD/000510/2020-2021 | 308/KSD | 29/12/2020 | 61 | TAPAS DEY | 0.24 | 0 | 0
5494 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Itamara (60), Jambeda (64) & Domohani (154) mouza under Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block-Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000691/2021-2022 | 28/KSD | 16/02/2022 | 10 | PRADIP CHAKRABORTY | 3.43 | 0 | 45
5495 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Khandarani (155) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No. 03) | Assistant Engineer | Junior Engineer | VCH/001032/2021-2022 |  | 16/09/2021 | 0 | SUBHADIP KOLEY | 4.85 | 0 | 0
5496 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline to cover Khandarani (155) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No. 04) | Assistant Engineer | Junior Engineer | VCH/001033/2021-2022 |  | 16/09/2021 | 0 | PRADYUMNA KOLEY | 2.81 | 0 | 0
5497 | Bankura Division | Khatra Sub-Division | Household survey in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) | Assistant Engineer | Junior Engineer | VCH/001035/2021-2022 |  | 16/09/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
5498 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Khandarani (155) mouzas by retrofitting zone - A (Bhauakana) of Khatra-Hirbandh-Ranibandh w/s scheme ( BRGF PH - I) at block - Khatra under Jal Jeeval Mission (JJM) and Jal Swapna & Jal Jeevan Mission programme under Khatra sub - Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001378/2020-2021 |  | 01/03/2021 | 0 | PRADYUMNA KOLEY | 11.66 | 0 | 0
5499 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 02 (Koskunda & Kanchanpur(PART)), Total House Hold -479 | Assistant Engineer | Junior Engineer | VCH/001491/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ASHISH KUMAR SAMANTA | 2.17 | 0 | 0
5500 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Namonahar), Total House Hold -413 | Assistant Engineer | Junior Engineer | VCH/001499/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ASHISH KUMAR SAMANTA | 3.86 | 0 | 0
5501 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayaerpara (206), Harinarayanpur (207) & Gangnala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. , | Assistant Engineer | Junior Engineer | VCH/001859/2021-2022 | FHTC/03 | 03/11/2021 | 0 | MUNMUN UPADHYAY | 15 | 0 | 0
5502 | Bankura Division | Khatra Sub-Division | Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/002299/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0
5503 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jarisa (89) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002488/2021-2022 | FHTC/3 | 03/02/2022 | 0 | GOUTAM BHATTACHRYYA | 2.67 | 0 | 0
5504 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 | Assistant Engineer | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
5505 | Bankura Division | Khatra Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply scheme for KANKI & its adjoining mouzas under Chhatna Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR:- Kanki, No.of Mouza :- 05 (Rajadal Bongaon Bikpur, Murgaboni & Kanki). Total House Hold - 438 nos. | Assistant Engineer | Junior Engineer | VCH/002867/2021-2022 | FHTC/15 | 15/03/2022 | 0 | TAPAN KUMAR MANDAL | 11.43 | 0 | 0
5506 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Chakuparsole Zone - A & Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :-12 nos. i.e.Majuria-135, Dhabani-136, Chitrang-137, Indkuri-139, Majdiha-142, Hatiaghora-143, Chanchar-144, Amdohara-147, Choto Bankadaha-148, Bharamara-149, Dhandol-153, Pholbani-154, Total House Hold -65 | Assistant Engineer | Junior Engineer | ORD/000029/2022-2023 | 111/VSD | 19/04/2022 | 21 | AJIT KUMAR DUTTA | 4.73 | 0 | 0
5507 | Bankura Division | Brishnupur Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. | Assistant Engineer | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 30 | EARTH MOVING (INDIA) | 40.2 | 29.56 | 0
5508 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 60 out of 921. | Assistant Engineer | Junior Engineer | ORD/000150/2020-2021 | 58/VSD | 10/02/2021 | 21 | AJIT KUMAR DUTTA | 4.82 | 0 | 0
5509 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 65 out of 921. | Assistant Engineer | Junior Engineer | ORD/000151/2020-2021 | 59/VSD | 10/02/2021 | 21 | M/S SACHHIDANANDA MAZUMDAR | 4.85 | 0 | 0
5510 | Bankura Division | Brishnupur Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 3) | Assistant Engineer | Junior Engineer | ORD/000173/2020-2021 | 90/KSD | 09/02/2021 | 15 | SUBHADIP KOLEY | 4.82 | 8.78 | 0
5511 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) Mouza - Amdahara | Assistant Engineer | Junior Engineer | VCH/001475/2021-2022 |  | 08/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.22 | 0 | 0
5512 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} of Kotalpukur (Zone- B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001181/2021-2022 | FHTC/29 | 29/07/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 63.55 | 0 | 0
5513 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 4 ( Anchuri, Dhulkumari, Pathakdihi & Keranipur), Total House Hold - 920 ( Sl .No.- 26) | Assistant Engineer | Junior Engineer | ORD/000182/2020-2021 | 723/BQA | 19/02/2021 | 1866 | M/S TARUN KUMAR PATRA | 84.19 | 0 | 0
5514 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 3.54 | 0
5515 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipeline with in pachirdang village to increse pressure in Pachirdanga mouzas for Construction & commissioning of FHTC (Functional House Hold Tap Connection) JAL SWAPNO to (Anchuri, Dhulkumari, Pathakdihi & Keranipur) of ANCHURI OHR (Zone - T) under Bankura - I, II & Barjora Block (BRGF Ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000643/2022-2023 | FHTC/14 | 14/07/2022 | 0 | M/S BANERJEE & BANERJEE | 7.11 | 0 | 0
5516 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Jagadalla , Anchuri , Chaturdihi , Adharthol , & Kustora | Assistant Engineer | Junior Engineer | VCH/001611/2020-2021 |  | 15/03/2021 | 0 | TAPAS DEY | 1.77 | 0 | 0
5517 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 04 nos, (Kaminbedia, Sihikapahari, Dubra, Tilna) Total House Hold - 429 | Assistant Engineer | Junior Engineer | VCH/002474/2021-2022 | FHTC/1 | 01/02/2022 | 0 | PARAMESWAR CHOWDHURY | 24.86 | 0 | 0
5518 | Bankura Division | Bankura Sadar Sub-Division | Submission of estimate for permanent restoration work at saltora - Mejhia road in stretches. office of the Executive Engineer, Bankura Highway division P.W roads directorate. | Assistant Engineer | Junior Engineer | BILL/00081/2023-2024 | FHTC/05 | 03/05/2023 | 0 | EXECUTIVE ENGINEER, BANKURA DIVISION, PHE DTE | 4.82 | 0 | 0
5519 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 25/11/2022 to 30/11/2022 | Assistant Engineer | Junior Engineer | BILL/02220/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5520 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 01/12/2022 to 06/12/2022 | Assistant Engineer | Junior Engineer | BILL/02221/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5521 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 07/12/2022 to 12/12/2022 | Assistant Engineer | Junior Engineer | BILL/02222/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5522 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 19/12/2022 to 22/12/2022 | Assistant Engineer | Junior Engineer | BILL/02223/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5523 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 07/11/2022 to 11/11/2022 | Assistant Engineer | Junior Engineer | BILL/02224/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5524 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 16/01/2023 to 19/01/2023 | Assistant Engineer | Junior Engineer | BILL/02225/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5525 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 09/01/2023 to 13/01/2023 | Assistant Engineer | Junior Engineer | BILL/02226/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5526 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 20/01/2023 to 30/01/2023 | Assistant Engineer | Junior Engineer | BILL/02227/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5527 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 21/11/2022 to 24/11/2022 | Assistant Engineer | Junior Engineer | BILL/02228/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5528 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 01/11/2022 to 04/11/2022 | Assistant Engineer | Junior Engineer | BILL/02229/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5529 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 19/10/2022 to 22/10/2022 | Assistant Engineer | Junior Engineer | BILL/02230/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5530 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 10/10/2022 to 13/10/2022 | Assistant Engineer | Junior Engineer | BILL/02231/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5531 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 24/10/2022 to 29/10/2022 | Assistant Engineer | Junior Engineer | BILL/02232/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5532 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 14/10/2022 to 18/10/2022 | Assistant Engineer | Junior Engineer | BILL/02233/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5533 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 02/01/2023 to 05/01/2023 | Assistant Engineer | Junior Engineer | BILL/02235/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5534 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 15/02/2023 to 20/02/2023 | Assistant Engineer | Junior Engineer | BILL/02237/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5535 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 22/02/2023 to 27/02/2023 | Assistant Engineer | Junior Engineer | BILL/02238/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5536 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 08/02/2023 to 13/02/2023 | Assistant Engineer | Junior Engineer | BILL/02239/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5537 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 01/02/2023 to 04/02/2023 | Assistant Engineer | Junior Engineer | BILL/02240/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5538 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (one) no additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division P.H.E Dte in connection with execution of JJM works under Bankura District, For 13/12/2022 to 16/12/2022 | Assistant Engineer | Junior Engineer | BILL/02241/2023-2024 | FHTC/12 | 18/12/2023 | 0 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5539 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Routara (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, No.of Mouza :- 02 (Routara,Bagjada ) Total House Hold - 533. | Assistant Engineer | Junior Engineer | ORD/000006/2021-2022 | 1763/BQA | 09/07/2021 | 30 | SUBHENDU SEKHAR GORAI | 29.78 | 0 | 85
5540 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 02, (Haroka,Jadebpur) , Total House Hold - 517. | Assistant Engineer | Junior Engineer | ORD/000007/2021-2022 | 1764/BQA | 09/07/2021 | 30 | GOUTAM MUKHERJEE | 31.14 | 30.36 | 0
5541 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 3, (Madhabpur , Netkamal, Karkata) , Total House Hold - 435 | Assistant Engineer | Junior Engineer | ORD/000008/2021-2022 | 1765/BQA | 09/07/2021 | 30 | UNIVERSAL CONSTRUCTION | 24.91 | 0 | 0
5542 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 2, ( Adhury, Gogra (part ) , Total House Hold - 439 | Assistant Engineer | Junior Engineer | ORD/000009/2021-2022 | 1766/BQA | 09/07/2021 | 30 | UNIVERSAL CONSTRUCTION | 25.13 | 0 | 0
5543 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, (Chandra ) , Total House Hold - 273 | Assistant Engineer | Junior Engineer | ORD/000010/2021-2022 | 1767/BQA | 09/07/2021 | 30 | PARESH CHANDRA LAYEK | 14.21 | 14.21 | 0
5544 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 01/06/2023 to 07/06/2023. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 451/BSD | 30/05/2023 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5545 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 08/06/2023 to 13/06/2023 | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 498/BSD | 06/06/2023 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 0
5546 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 | Assistant Engineer | Junior Engineer | ORD/000011/2021-2022 | 1768/BQA | 09/07/2021 | 30 | BEAUTY CHATTERJEE | 12.57 | 0 | 0
5547 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block , Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampu (part) Total House Hold - 453. | Assistant Engineer | Junior Engineer | ORD/000012/2021-2022 | 1769/BQA | 09/07/2021 | 30 | GOUTAM BHATTACHRYYA | 27.54 | 0 | 0
5548 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 03 nos, (Digtore, Krishnapur, Pathordihi) Total House Hold - 673. | Assistant Engineer | Junior Engineer | ORD/000013/2021-2022 | 1770/BQA | 09/07/2021 | 30 | APEX ENTERPRISE | 38.73 | 0 | 0
5549 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 03 nos, ( Dhatala, Binodihi ,Bashkatia) Total House Hold - 394. | Assistant Engineer | Junior Engineer | ORD/000014/2021-2022 | 1771/BQA | 09/07/2021 | 30 | SAIKAT CHOWDHURY | 21.38 | 0 | 0
5550 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, (Patdoha) Total House Hold - 489 | Assistant Engineer | Junior Engineer | ORD/000015/2021-2022 | 1772/BQA | 09/07/2021 | 30 | SUBHANKAR BANERJEE | 27.89 | 0.59 | 0
5551 | Bankura Division | Bankura Sadar Sub-Division | Supply & delivery of DI Specials including Loading, Unloading & Stacking properly for Day to day O & M of Saltora & Chhatna Block Water Supply Scheme BRGF (Ph - I Project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2022-2023 | 356/KSD | 16/08/2022 | 5 | TAPAS KUMBHAKAR | 1.28 | 0 | 0
5552 | Bankura Division | Bankura Sadar Sub-Division | Supply & delivery of DI Specials including Loading, Unloading & Stacking properly for Day to day O & M of Saltora & Chhatna Block Water Supply Scheme BRGF (Ph - I Project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2022-2023 | 356/ KSD | 16/08/2022 | 7 | TAPAS KUMBHAKAR | 1.28 | 0 | 0
5553 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe Line from Lapahari to Serabedia of Saltora block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. (Under JJM Fund) | Assistant Engineer | Junior Engineer | ORD/000550/2021-2022 | 992/BSD | 25/11/2021 | 15 | ASHOKE KUMAR DEY | 4.83 | 4.83 | 0
5554 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1 nos, Barkona Total House Hold - 620. | Assistant Engineer | Junior Engineer | ORD/000016/2021-2022 | 1773/BQA | 09/07/2021 | 30 | SOUMITRA BHATTACHARYA | 37.26 | 0 | 0
5555 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 5 nos, Khatmara, Kultuka, Bojapathor, Bhadadi, Murgadoba Total House Hold - 601. | Assistant Engineer | Junior Engineer | ORD/000017/2021-2022 | 1774/BQA | 09/07/2021 | 30 | SARKAR CONSTRUCTION | 35.5 | 35.49 | 0
5556 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 4, Belebad,Moulahir, Mujrakundi Raj band Total House Hold -576 . | Assistant Engineer | Junior Engineer | ORD/000018/2021-2022 | 1775/BQA | 09/07/2021 | 30 | M/S BIPUL BANERJEE | 32.89 | 0 | 100
5557 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 2 nos, Sebapur, Machuria Total House Hold -274 . | Assistant Engineer | Junior Engineer | ORD/000019/2021-2022 | 1776/BQA | 09/07/2021 | 30 | ASHOKE BHATTACHARYYA | 15.34 | 14.36 | 15
5558 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 2 nos, Dhapali, Laxmanpur, Total House Hold -341 . | Assistant Engineer | Junior Engineer | ORD/000020/2021-2022 | 1777/BQA | 09/07/2021 | 30 | ASHOKE KUMAR DEY | 19.26 | 0 | 0
5559 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe Line from Serabedia to Sebapur of Saltora block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. (Under JJM Fund) | Assistant Engineer | Junior Engineer | ORD/000551/2021-2022 | 993/BSD | 25/11/2021 | 15 | ASOKE BHATTACHARYYA | 4.77 | 4.77 | 0
5560 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 10/10/2022 to 13/10/2022. | Assistant Engineer | Junior Engineer | ORD/000904/2022-2023 | 672/BSD | 29/09/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5561 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 14/10/2022 to 18/10/2022. | Assistant Engineer | Junior Engineer | ORD/000905/2022-2023 | 697/BSD | 12/10/2022 | 5 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5562 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 2 nos, Kanuri, Got Total House Hold - 734. | Assistant Engineer | Junior Engineer | ORD/000058/2021-2022 | 2036/BQA | 10/08/2021 | 30 | CREATION CONSTRUCTION | 41.34 | 41.34 | 0
5563 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipeline from Kankri Jharna More to Barikul Primary School to increase pressure in Barikul (179) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000061/2022-2023 | 1685/BQA | 27/07/2022 | 30 | APEX ENTERPRISE | 7.7 | 7.51 | 0
5564 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, Name of OHR:- Ranjitpur, No.of Mouza :- 14 ,(Bisjore ,Niamatpur, Pabayan Ranjitpur Dhekiya, Duiaitara Lalittakuri,Rampur,Dubrapur Bhurkurthol GonsaidihiTentultikn ,Chakparui,Pabra) Total House Hold - 3093. | Assistant Engineer | Junior Engineer | ORD/000076/2021-2022 | 2391/BQA | 15/09/2021 | 45 | DEBAKI RANJAN SARKAR | 158.66 | 83.21 | 0
5565 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (ZONE- D ) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 14 nos, (Alunia, Damodarpur, Monipur, Khagra, Sukhabad , Katabaid, Demramol, Beriatha, Janadudumar Rampur Raghumathpur, l, Chhatpathor, Shalroha, Nimra,) Total House Hold - 2711. | Assistant Engineer | Junior Engineer | ORD/000077/2021-2022 | 2392/BQA | 15/09/2021 | 45 | SIB SANKAR CHOWDHURY | 128.19 | 0 | 0
5566 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Udaypur (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Udaypur No.of Mouza :- 19 nos , (Bagulia , Nabagram Kalakunda, Shirpuranpur, Ituri, Bharatpur, Chakbaga mahisharabi, Tiluri, Binodpur, Bhaluka Bhadaspur, Bardubi, Udaypur Kashihir, Pahapur, Lakhhankata, Maldiha, Chhatimbari ) Total House Hold - 3163 | Assistant Engineer | Junior Engineer | ORD/000079/2021-2022 | 2451/BQA | 21/09/2021 | 45 | J. D. J. ENTERPRISE | 163.64 | 41.83 | 10
5567 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 19/10/2022 to 22/10/2022. | Assistant Engineer | Junior Engineer | ORD/000906/2022-2023 | 700/BSD | 18/10/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5568 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 24/10/2022 to 29/10/2022. | Assistant Engineer | Junior Engineer | ORD/000907/2022-2023 | 701/BSD | 21/10/2022 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5569 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 01/11/2022 to 04/11/2022. | Assistant Engineer | Junior Engineer | ORD/000908/2022-2023 | 702/BSD | 28/10/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5570 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part) Total House Hold - 75 (Sl No of Work- 06) | Assistant Engineer | Junior Engineer | ORD/000081/2020-2021 | 98/ BSD | 12/02/2021 | 20 | MANAS DEY | 4.72 | 0 | 0
5571 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, ,Gogra (Part) Total House Hold - 75 (Sl No of Work- 07) | Assistant Engineer | Junior Engineer | ORD/000119/2020-2021 | 99/ BSD | 12/02/2021 | 20 | ASHISH KUMAR SAMANTA | 4.73 | 0 | 0
5572 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part), Total House Hold - 75 (Sl No of Work- 08) | Assistant Engineer | Junior Engineer | ORD/000139/2020-2021 | 100/ BSD | 12/02/2021 | 20 | SANDHYA DEY | 4.75 | 0 | 0
5573 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline from Barsal to Kukhrakuri to increase pressure at Kukhrakuri village under Saltora-Block Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part-B) (JJM Programme fund) | Assistant Engineer | Junior Engineer | ORD/000139/2022-2023 | 1329/BQA | 15/06/2022 | 15 | TAPAS KUMBHAKAR | 3.79 | 3.79 | 0
5574 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline from Barsal to Kukhrakuri to increase pressure at Kukhrakuri village under Saltora-Block Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part-A) (JJM Programme fund) | Assistant Engineer | Junior Engineer | ORD/000140/2022-2023 | 1328/BQA | 15/06/2022 | 15 | TAPAS KUMBHAKAR | 4.09 | 4.08 | 0
5575 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line from Rowtora pukur par to kechka ICDS Centre by tapping rising main pipe line of Saltora- Chhatna W/S Scheme (BRGF Ph- I) under Bankura Division P.H.E. Dte. (Part- B) (Under Jal Swapna & JJM Programme Fund) | Assistant Engineer | Junior Engineer | ORD/000142/2022-2023 | 1324/BQA | 15/06/2022 | 15 | M/S T.P. HAZRA & SONS | 4.93 | 4.93 | 0
5576 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 07/11/2022 to 11/11/2022. | Assistant Engineer | Junior Engineer | ORD/000909/2022-2023 | 708/BSD | 04/11/2022 | 5 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5577 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 21/11/2022 to 24/11/2022. | Assistant Engineer | Junior Engineer | ORD/000910/2022-2023 | 732/BSD | 17/11/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5578 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 25/11/2022 to 30/11/2022. | Assistant Engineer | Junior Engineer | ORD/000911/2022-2023 | 747/BSD | 24/11/2022 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5579 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line from Rowtora pukur par to kechka ICDS Centre by tapping rising main pipe line of Saltora- Chhatna W/S Scheme (BRGF Ph- I) under Bankura Division P.H.E. Dte. (Part- A) (Under Jal Swapna & JJM Programme Fund) | Assistant Engineer | Junior Engineer | ORD/000144/2022-2023 | 1317/BQA | 15/06/2022 | 15 | TAPAS KUMAR HAZRA | 4.82 | 4.7 | 0
5580 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipeline to increase water pressure at Patdoha mouza for retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and Jal Swapna of Shyampur (Zone-E) under Saltora-Chhatna water supply scheme (BRGF Ph-I) Project of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000146/2022-2023 | 256/KSD | 12/07/2022 | 15 | TAPAS KUMBHAKAR | 4.49 | 4.37 | 0
5581 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project)) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, ,Gogra (Part) Total House Hold - 75 (Sl No of Work- 09) | Assistant Engineer | Junior Engineer | ORD/000148/2020-2021 | 101/ BSD | 12/02/2021 | 20 | ASHISH KUMAR SAMANTA | 4.77 | 0 | 0
5582 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ), Total House Hold - 65 (Sl No of Work- 10) | Assistant Engineer | Junior Engineer | ORD/000152/2020-2021 | 102/ BSD | 12/02/2021 | 20 | TAPAS KUMBHAKAR | 4.42 | 0.54 | 0
5583 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project)s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ) Total House Hold - 65 (Sl No of Work- 11) | Assistant Engineer | Junior Engineer | ORD/000153/2020-2021 | 103/ BSD | 12/02/2021 | 20 | RUFIKUL MONDAL | 4.41 | 0.89 | 0
5584 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 01/12/2022 to 06/12/2022. | Assistant Engineer | Junior Engineer | ORD/000912/2022-2023 | 752/BSD | 29/11/2022 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5585 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 07/12/2022 to 12/12/2022. | Assistant Engineer | Junior Engineer | ORD/000913/2022-2023 | 787/BSD | 05/12/2022 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5586 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 13/12/2022 to 16/12/2022. | Assistant Engineer | Junior Engineer | ORD/000914/2022-2023 | 793/BSD | 13/12/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5587 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete from Lapahari to sebapur village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2022-2023 | 1313/BQA | 15/06/2022 | 15 | MANAS DEY | 4.17 | 4.06 | 10
5588 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying Extra UPVC Pipe Line to Cover Jadavpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horaka (Zone - D) under Saltora Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 106/KSD | 28/04/2023 | 15 | RAHUL CHATERJEE | 0.56 | 0.4 | 25
5589 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horaka (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Saltora, No. of Mouza :- Jadavpur, Total House Hold :-14 nos. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 108/KSD | 28/04/2023 | 15 | RAHUL CHATERJEE | 0.73 | 0.67 | 30
5590 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra 20 mm HDPE Pipe Line to Cover Khagra, Monipur, Katabaid, Demramole mouza for retrofitting works for creacion of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Monipur (Zone- D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2022-2023 | 349/KSD | 16/08/2022 | 20 | SIB SANKAR CHOWDHURY | 4.83 | 0 | 0
5591 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction concrete at Salroha, Raghunathchak mouza for retrofitting works for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MONIPUR (Zone- D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2022-2023 | 355/KSD | 16/08/2022 | 20 | SIB SANKAR CHOWDHURY | 4.02 | 0 | 0
5592 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Monipur (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Monipur, No. of Mouza :- Chhatapathor (Part), Total House Hold :-38 nos. | Assistant Engineer | Junior Engineer | ORD/000180/2022-2023 | 354/KSD | 16/08/2022 | 20 | ASHIS PAL | 3.51 | 3.5 | 0
5593 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 19/12/2022 to 22/12/2022. | Assistant Engineer | Junior Engineer | ORD/000915/2022-2023 | 797/BSD | 16/12/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5594 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 02/01/2023 to 05/01/2023. | Assistant Engineer | Junior Engineer | ORD/000916/2022-2023 | 829/BSD | 30/12/2022 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5595 | Bankura Division | Bankura Sadar Sub-Division | Supply and delivery of different dia CIDF sluice valve for Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000192/2022-2023 | 351/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.77 | 4.77 | 0
5596 | Bankura Division | Bankura Sadar Sub-Division | Supply and delivery of different dia CIDF sluice valve for Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000194/2022-2023 | 352/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.9 | 4.9 | 0
5597 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 , Chhatpathor ( Part ) Total House Hold - 60 (Sl No of Work- 12) | Assistant Engineer | Junior Engineer | ORD/000195/2020-2021 | 104/ BSD | 12/02/2021 | 20 | ASHISH PAUL | 4.35 | 0.93 | 0
5598 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01 no, Shyampur (part) Total House Hold - 75 (Sl No of Work- 13) | Assistant Engineer | Junior Engineer | ORD/000196/2020-2021 | 105/ BSD | 12/02/2021 | 20 | TAPAS KUMBHAKAR | 4.78 | 0.59 | 0
5599 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01 no, Shyampur (part) Total House Hold - 75 (Sl No of Work- 14) | Assistant Engineer | Junior Engineer | ORD/000197/2020-2021 | 106/ BSD | 12/02/2021 | 20 | TAPAS KUMAR HAZRA | 4.79 | 0.48 | 0
5600 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 09/01/2023 to 13/01/2023. | Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 07/BSD | 06/01/2023 | 5 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5601 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 16/01/2023 to 19/01/2023. | Assistant Engineer | Junior Engineer | ORD/000918/2022-2023 | 31/BSD | 16/01/2023 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5602 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 20/01/2023 to 30/01/2023. | Assistant Engineer | Junior Engineer | ORD/000919/2022-2023 | 42/BSD | 19/01/2023 | 11 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5603 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampur (part) Total House Hold - 75 (Sl No of Work- 15) | Assistant Engineer | Junior Engineer | ORD/000198/2020-2021 | 107/ BSD | 12/02/2021 | 20 | RUFIKUL MONDAL | 4.76 | 0 | 0
5604 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampur (part) Total House Hold - 75 (Sl No of Work- 16) | Assistant Engineer | Junior Engineer | ORD/000199/2020-2021 | 108/ BSD | 12/02/2021 | 20 | TAPAS KUMAR HAZRA | 4.8 | 0.29 | 0
5605 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1, Tilabaid (PART-B) Total House Hold - 75. (Sl No of Work- 17) | Assistant Engineer | Junior Engineer | ORD/000200/2020-2021 | 109/ BSD | 12/02/2021 | 20 | MRITYUNJOY HAZRA | 4.84 | 0.77 | 0
5606 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1 no, Tilabaid (PART-B) Total House Hold - 75. (Sl No of Work- 18) | Assistant Engineer | Junior Engineer | ORD/000201/2020-2021 | 110/ BSD | 12/02/2021 | 20 | SK. ALAMAGIR ALAM | 4.81 | 0.37 | 0
5607 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No. of Mouza :- 1 no, Tilabaid (PART-B) Total House Hold - 70. (Sl No of Work- 19) | Assistant Engineer | Junior Engineer | ORD/000202/2020-2021 | 111/ BSD | 12/02/2021 | 20 | LABIR MIRSHAD KHAN | 4.58 | 0.26 | 0
5608 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 01/02/2023 to 04/02/2023. | Assistant Engineer | Junior Engineer | ORD/000920/2022-2023 | 63/BSD | 30/01/2023 | 4 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5609 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 08/02/2023 to 13/02/2023. | Assistant Engineer | Junior Engineer | ORD/000921/2022-2023 | 152/BSD | 08/02/2023 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5610 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 15/02/2023 to 20/02/2023. | Assistant Engineer | Junior Engineer | ORD/000922/2022-2023 | 202/BSD | 15/02/2023 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5611 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no., (Chandra (part) Total House Hold - 37 nos. | Assistant Engineer | Junior Engineer | ORD/000212/2022-2023 | 260/KSD | 12/07/2022 | 15 | PARESH CHANDRA LAYEK | 2.22 | 2.09 | 0
5612 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Nimra,Demramole, Monipur mouza of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur(ZONE-D ) W/S Scheme and its adjoining mouzas under Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000223/2022-2023 | 1325/BQA | 15/06/2022 | 15 | SIB SANKAR CHOWDHURY | 4.91 | 4.9 | 0
5613 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line & PVC Pipe to Cover Salroha & Rampur mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur(ZONE-D ) W/S Scheme and its adjoining mouzas under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000224/2022-2023 | 1315/BQA | 15/06/2022 | 15 | SIB SANKAR CHOWDHURY | 5 | 4.99 | 0
5614 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line & PVC Pipe to Cover Sukhabaid,katabaid, Nimra, Alunia mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur(ZONE-D ) W/S Scheme and its adjoining mouzas under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000225/2022-2023 | 1306/BQA | 15/06/2022 | 15 | SIB SANKAR CHOWDHURY | 4.99 | 4.97 | 0
5615 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line & PVC Pipe to Cover Nimra & Khagra mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur(ZONE-D ) W/S Scheme and its adjoining mouzas under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000226/2022-2023 | 1305/BQA | 15/06/2022 | 15 | SIB SANKAR CHOWDHURY | 4.98 | 4.97 | 0
5616 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line from jahurbona to Paharpur village to increase pressure in Paharpur village for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Udaypur (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000254/2022-2023 | 1320/BQA | 15/06/2022 | 15 | TAPAS KUMBHAKAR | 4.93 | 4.93 | 0
5617 | Bankura Division | Bankura Sadar Sub-Division | Engagement of 01 (One) no. additional vehicle on temporary basis for office of the Executive Engineer, Bankura Division, P.H.E. Dte. in connection with execution of JJM works under Bankura District. For 22/02/2023 to 27/02/2023. | Assistant Engineer | Junior Engineer | ORD/000923/2022-2023 | 209/BSD | 21/02/2023 | 6 | PARTHA PRATIM CHHATAIT | 0.1 | 0 | 20
5618 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas, | Assistant Engineer | Junior Engineer | VCH/002455/2021-2022 | FHTC/15 | 15/02/2022 | 0 | SUMITA UPADHYAY | 4.89 | 0 | 0
5619 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- Latulia (PART), Total House Hold - 27 nos. | Assistant Engineer | Junior Engineer | ORD/000258/2022-2023 | 249/KSD | 12/07/2022 | 15 | BEAUTY CHATTERJEE | 1.43 | 1.43 | 0
5620 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Uporgora IBS more to Lapahari with Interconnection with R/M to increase water pressure at Sebapur, Got of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone- F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2022-2023 | 2346/BQA | 12/12/2022 | 45 | MANAS DEY | 15.01 | 15 | 0
5621 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no ,Sidhaberia (Part), Total House Hold- 145 nos. | Assistant Engineer | Junior Engineer | ORD/000308/2021-2022 | 3363/BQA | 31/12/2021 | 30 | TAPAS KUMBHAKAR | 9.46 | 0 | 0
5622 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR -SHYAMPUR. No.of Mouza :- 01 no, Telidihi, Total House Hold- 244 nos. | Assistant Engineer | Junior Engineer | ORD/000309/2021-2022 | 3364/BQA | 31/12/2021 | 30 | TAPAS KUMBHAKAR | 13.16 | 0 | 0
5623 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Horoka No.of Mouza :- 01 no., Chaubata, Total House Hold- 248 nos. | Assistant Engineer | Junior Engineer | ORD/000310/2021-2022 | 3365/BQA | 31/12/2021 | 30 | MAYA CONSTRUCTION | 13.09 | 12.73 | 0
5624 | Bankura Division | Bankura Sadar Sub-Division | "Construction of temporary latrine & water supply arrangement at Mukutmanipur Development authority ( MDA) area for ensuing tourist season under Khatra Sub - Division of Bankura Division, PHE Dte. (PART),- A" | Assistant Engineer | Junior Engineer | VCH/002563/2021-2022 | FHTC/26 | 26/02/2022 | 0 | EARTH MOVING (INDIA) | 2.85 | 0 | 0
5625 | Bankura Division | Bankura Sadar Sub-Division | Construction of temporary latrine & water supply arrangement at Mukutmanipur Development authority ( MDA) area for ensuing tourist season under Khatra Sub - Division of Bankura Division, PHE Dte. (PART),- B | Assistant Engineer | Junior Engineer | VCH/002564/2021-2022 | FHTC/26 | 26/02/2022 | 0 | UNITED TRADERS | 2.46 | 0 | 0
5626 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Shyampur, No.of Mouza :- 01 no., Shyampur (Part), Total House Hold- 102 nos. | Assistant Engineer | Junior Engineer | ORD/000311/2021-2022 | 3366/BQA | 31/12/2021 | 30 | PRASANTA BHUIN | 7.41 | 7.41 | 0
5627 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover (Madhabpur, Netkamal, Karkata) mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000360/2021-2022 | 1025/ BSD | 14/12/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.98 | 0 | 0
5628 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF Ph- I Project) under Division, PHE Dte. (Part-A) Block- Saltora, Name of OHR - HORAKA, No. of Mouza :- Chowbata (Part), Gogra (Part), Total House Hold :- 180 nos. | Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 2062/BQA | 25/07/2023 | 45 | M/S BANERJEE & BANERJEE | 14.3 | 13.89 | 100
5629 | Bankura Division | Bankura Sadar Sub-Division | Laying extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Madhabpur, Netkamal, Karkata mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Block of Saltora-Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000361/2021-2022 | 1026/ BSD | 14/12/2021 | 15 | UNIVERSAL CONSTRUCTION | 4.07 | 0 | 0
5630 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF Ph- I Project) under Division, PHE Dte. (Part-B) Block- Saltora, Name of OHR - HORAKA, No. of Mouza :- Chowbata (Part), Gogra (Part), Total House Hold :- 180 nos. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 2063/BQA | 25/07/2023 | 45 | AJIT KUMAR DUTTA | 14.3 | 13.96 | 100
5631 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Saltora-Mejia main road (near sub station to Pathordihi & Krishnapur adhibasi para, Bouri para including Interconnection with A/V to increase water pressure at Pathordihi, krishnapur mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Shampur (Zone - E) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2022-2023 | 45/BQA | 05/01/2023 | 45 | GOUTAM BHATTACHRYYA | 18.85 | 18.81 | 100
5632 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Adhuri Goyala Para to Chowbata including Interconnection with wash out valve to increase water pressure at Chowbata mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horaka (Zone - G) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2022-2023 | 46/BQA | 05/01/2023 | 45 | TAPAS KUMBHAKAR | 21.13 | 21.1 | 0
5633 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Dhatala mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Shampur (Zone - E) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2022-2023 | 47/BQA | 05/01/2023 | 45 | TAPAS KUMBHAKAR | 3.04 | 3.04 | 0
5634 | Bankura Division | Bankura Sadar Sub-Division | Continuation schedule for Diesel Ambassador Car equivalent luxury Car / Bolero / Scrpio etc. having license for contract carriage permit from the Regional Transport Authority for office use of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/06/2022 to 30/11/2022) | Assistant Engineer | Junior Engineer | ORD/000409/2022-2023 | 447/ BSD | 31/05/2022 | 183 | GOURANGA NANDI | 0.86 | 1.2 | 0
5635 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Routara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Routara (Zone - A) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000410/2021-2022 | 1039/ BSD | 14/12/2021 | 15 | SUBHENDU SEKHAR GORAI | 4.89 | 0 | 0
5636 | Bankura Division | Bankura Sadar Sub-Division | Dismantaling & reconstruction concrete at Routara 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Routara (Zone - A) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000411/2021-2022 | 1040/ BSD | 14/12/2021 | 15 | SUBHENDU SEKHAR GORAI | 4.99 | 4.91 | 0
5637 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project)s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ) Total House Hold - 65 | Assistant Engineer | Junior Engineer | ORD/000456/2020-2021 | 103 / BSD | 12/02/2021 | 20 | RUFIKUL MONDAL | 4.41 | 0 | 0
5638 | Bankura Division | Bankura Sadar Sub-Division | Hiring of car equivalent to Motor cab & Maruti Omni (Standard) with Mass emission standard of BS- III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/07/2023 to 31/12/2023) (Six Months) | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 555/BSD | 21/06/2023 | 183 | GOURANGA NANDI | 0.87 | 2.39 | 40
5639 | Bankura Division | Bankura Sadar Sub-Division | Continuation for diesel Ambassador Car equivalent luxury Car / Bolero / Scrpio etc. having license for contract carriage permit from the Regional Transport Authority for office use of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/06/2023 to 30/06/2023) | Assistant Engineer | Junior Engineer | ORD/000480/2023-2024 | 455/BSD | 31/05/2023 | 30 | GOURANGA NANDI | 0.14 | 0.4 | 100
5640 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Monipur (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Monipur, No.of Mouza :- 01 no., Chhatapathor (Part), Total House Hold- 20 nos. | Assistant Engineer | Junior Engineer | ORD/000486/2021-2022 | 50/BSD | 07/01/2022 | 10 | TAPAS KUMBHAKAR | 2.53 | 2.42 | 0
5641 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Shyampur, No. of Mouza :- 01 nos (Telidihi), Total House Hold- 80 nos. | Assistant Engineer | Junior Engineer | ORD/000488/2021-2022 | 216/BSD | 11/03/2022 | 10 | TAPAS KUMAR HAZRA | 4.73 | 4.73 | 0
5642 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Shyampur, No. of Mouza :- 01 no., (Dhatala), Total House Hold- 48 nos. | Assistant Engineer | Junior Engineer | ORD/000489/2021-2022 | 217/BSD | 11/03/2022 | 10 | TAPAS KUMAR HAZRA | 2.89 | 2.87 | 0
5643 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Monipur (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Monipur, No. of Mouza :- 01 no, Chhatapathor (Part), Total House Hold- 15 nos. | Assistant Engineer | Junior Engineer | ORD/000495/2021-2022 | 51/BSD | 07/01/2022 | 10 | ASHIS PAL | 2.47 | 2.47 | 0
5644 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project)) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, ,Gogra (Part) Total House Hold - 75 | Assistant Engineer | Junior Engineer | ORD/000508/2020-2021 | 101/BSD | 12/02/2021 | 20 | ASHISH KUMAR SAMANTA | 4.77 | 0.38 | 0
5645 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete at GOT for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part -B). | Assistant Engineer | Junior Engineer | ORD/000511/2021-2022 | 278/BSD | 17/03/2022 | 10 | CREATION CONSTRUCTION | 4.8 | 4.8 | 0
5646 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete of Dubrajpur mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000512/2021-2022 | 24/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 1.63 | 1.62 | 0
5647 | Bankura Division | Bankura Sadar Sub-Division | Dismentling & reconstruction of Concrete of Pabra 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000513/2021-2022 | 38/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 4.78 | 3.83 | 0
5648 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete of Pabra 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - A) | Assistant Engineer | Junior Engineer | ORD/000514/2021-2022 | 37/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 4.97 | 4.57 | 0
5649 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete of Dhekia, Bhurkurthol, Goswamiidiihi, Tentultikni, Pabayan, Ranjitpur, Lalittakuri 'mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000515/2021-2022 | 31/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 4.2 | 4.17 | 0
5650 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction of concrete of Dhekia, Bhurkurthol, Goswamiidiihi, Tentultikni, Pabayan, Ranjitpur, Lalittakuri 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C)under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - A) | Assistant Engineer | Junior Engineer | ORD/000516/2021-2022 | 30/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 4.22 | 4.17 | 0
5651 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Monipur, No. of Mouza:- 01 no., TILABAID (Part), Total House Hold- 20 nos. | Assistant Engineer | Junior Engineer | ORD/000530/2021-2022 | 53/BSD | 07/01/2022 | 10 | SK. ALAMAGIR ALAM | 1.72 | 1.72 | 0
5652 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No. of Mouza :- 01 no, Gogra (Part) Total House Hold - 75 | Assistant Engineer | Junior Engineer | ORD/000544/2020-2021 | 98/BSD | 12/02/2021 | 20 | MANAS DEY | 4.72 | 0.34 | 0
5653 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, ,Gogra (Part) Total House Hold - 75 | Assistant Engineer | Junior Engineer | ORD/000545/2020-2021 | 100/BSD | 12/02/2021 | 20 | SANDHYA DEY | 4.75 | 0.21 | 0
5654 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Bisjore 'mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part -A) | Assistant Engineer | Junior Engineer | ORD/000546/2021-2022 | 26/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.99 | 4.99 | 0
5655 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Telidih Village of Telidihi mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block, Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2021-2022 | 212/BSD | 11/03/2022 | 10 | TAPAS KUMAR HAZRA | 4.5 | 4.49 | 0
5656 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Shibdanga Village of Telidihi mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2021-2022 | 211/BSD | 11/03/2022 | 10 | TAPAS KUMBHAKAR | 4.92 | 4.92 | 0
5657 | Bankura Division | Bankura Sadar Sub-Division | Dismentling & reconstruction of concrete of Bisjore mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000627/2021-2022 | 25/BSD | 07/01/2022 | 20 | DEBAKI RANJAN SARKAR | 2.24 | 1.65 | 0
5658 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Bisjore 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000628/2021-2022 | 27/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.89 | 4.89 | 0
5659 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Dubrajpur mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte (Part - A) | Assistant Engineer | Junior Engineer | ORD/000629/2021-2022 | 28/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 5 | 5 | 0
5660 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Dubrajpur, Bisjore mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000630/2021-2022 | 29/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.59 | 4.59 | 0
5661 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Pabra (Namo para)'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000631/2021-2022 | 33/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.95 | 9.86 | 0
5662 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Pabra (Roy para)'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000632/2021-2022 | 34/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.62 | 4.62 | 0
5663 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Pabra (Uppar para)'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000633/2021-2022 | 35/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.65 | 4.64 | 0
5664 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line including Dismantling & Reconstruction of Concrete to Cover Pabra (Adhibasi para) 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part - E) | Assistant Engineer | Junior Engineer | ORD/000634/2021-2022 | 36/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 3.67 | 3.65 | 0
5665 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Pabra (Pabra more) mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000637/2021-2022 | 32/BSD | 07/01/2022 | 15 | DEBAKI RANJAN SARKAR | 4.95 | 0 | 0
5666 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover SHYAMPUR 'mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000650/2021-2022 | 713/BSD | 17/06/2021 | 10 | M/S T.P. HAZRA & SONS | 4.06 | 3.93 | 0
5667 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover , Kanuri mouza for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000655/2021-2022 | 275/BSD | 17/03/2022 | 10 | CREATION CONSTRUCTION | 3.33 | 3.33 | 0
5668 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Got mouza for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part -A) | Assistant Engineer | Junior Engineer | ORD/000656/2021-2022 | 276/BSD | 17/03/2022 | 10 | CREATION CONSTRUCTION | 2.87 | 2.87 | 0
5669 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte.Block - Saltora, Name of OHR - Shyampur, Total House Hold -400 nos. | Assistant Engineer | Junior Engineer | ORD/000686/2022-2023 | 587/BQA | 20/03/2023 | 1013 | PRADYUMNA KOLEY | 90.36 | 61.37 | 68
5670 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of HORAKA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. Block - Saltora, Name of OHR -HORAKA, Total House Hold -100 nos. | Assistant Engineer | Junior Engineer | ORD/000687/2022-2023 | 588/BQA | 20/03/2023 | 743 | PARAMESWAR CHOWDHURY | 77.99 | 55.09 | 65
5671 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Ranjitpur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, P.H.E. Dte.Block - Saltora, Name of OHR - Ranjitpur, Total House Hold -150 nos. | Assistant Engineer | Junior Engineer | ORD/000688/2022-2023 | 589/BQA | 20/03/2023 | 1018 | APEX ENTERPRISE | 77.72 | 44.59 | 70
5672 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilabaid (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I Project) under Bankura Division, PHE Dte. Block - Saltora, Name of OHR - Tilabaid, No. of Mouza :- Khatmara, Dhapali (Part), Total House Hold :- 210 nos. | Assistant Engineer | Junior Engineer | ORD/000745/2022-2023 | 634/BQA | 24/03/2023 | 45 | RAFIKUL MONDAL | 20.89 | 19.24 | 100
5673 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Patdoha mouza & Reconstruction of concrete for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000777/2021-2022 | 47/BSD | 07/01/2022 | 15 | SUBHANKAR BANERJEE | 2.92 | 2.92 | 0
5674 | Bankura Division | Bankura Sadar Sub-Division | Household survey of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saltora Block under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000921/2021-2022 | 813/BSD | 06/08/2021 | 61 | TAPAS DEY | 3.01 | 0.51 | 98
5675 | Bankura Division | Bankura Sadar Sub-Division | Household survey of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saltora Block under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, No. of Zone:- 03 nos, Total House Hold - 7930 nos. | Assistant Engineer | Junior Engineer | ORD/000922/2021-2022 | 814/BSD | 06/08/2021 | 60 | TAPAS DEY | 2.51 | 0.51 | 98
5676 | Bankura Division | Bankura Sadar Sub-Division | Supply of 01 (One) No. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio on hire basis for official use of the Assistant Engineer, Bankura Head Quarter under Bankura Division P.H.E. Dte. for the period from 01.12.2021 to 30.11.2022 | Assistant Engineer | Junior Engineer | ORD/000928/2021-2022 | 21/BQA (H.Q.) | 30/11/2021 | 365 | MITALI CHHATAIT PARAMANIK | 1.73 | 0 | 0
5677 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra HDPE pipe Line at sebapur village of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001177/2022-2023 | 1316/BQA | 15/06/2022 | 15 | SANDHYA DEY | 4.51 | 0 | 100
5678 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for13 nos. Mouzas (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur,Birsinghapur, Sonargram, Madanhati,Hatasuria , Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III), No. of Mouza :-13 nos, ( Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold -2821 nos. | Assistant Engineer | Junior Engineer | VCH/000247/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.94 | 0 | 0
5679 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Teledihi mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Shyampur Zone- E under Saltora -block saltora - Chhatna water supply scheme (BRGF ph - I project) dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000259/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS KUMBHAKAR | 2.48 | 0 | 0
5680 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR -SHYAMPUR. No.of Mouza :- 01 no, Telidihi, Total House Hold- 244 nos. | Assistant Engineer | Junior Engineer | VCH/000260/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 12.84 | 0 | 0
5681 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dadhimukha ZONE - D under Bankura - l & ll & Barjora block W/S Scheme BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. block - Barjora. Name of OHR- Dadhimukha zone - D Name of Mouza:-- Purusattam Pur, Muktapur. Total House Hold - 80 nos. sl No- 02 | Assistant Engineer | Junior Engineer | VCH/000322/2022-2023 | FHTC/28 | 28/04/2022 | 0 | GOUTAM GHOSH | 3.95 | 0 | 0
5682 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - B ), Total House Hold - 151 | Assistant Engineer | Junior Engineer | VCH/000323/2022-2023 | FHTC/28 | 28/04/2022 | 0 | M/S SUPRIYA CHATTERJEE | 2.41 | 0 | 0
5683 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Horialgora, No. of Mouza :- 01 nos , Junbedia (Part), Total House Hold - 200 nos. | Assistant Engineer | Junior Engineer | VCH/000324/2022-2023 | FHTC/28 | 28/04/2022 | 0 | M/S SUPRIYA CHATTERJEE | 21.33 | 0 | 0
5684 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Joykrishna pur Sarenga(PART-B), Total House Hold - 176 | Assistant Engineer | Junior Engineer | VCH/000325/2022-2023 | FHTC/28 | 28/04/2022 | 0 | M/S SUPRIYA CHATTERJEE | 0.62 | 0 | 0
5685 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - C ), Total House Hold - 161 | Assistant Engineer | Junior Engineer | VCH/000326/2022-2023 | FHTC/28 | 28/04/2022 | 0 | M/S T.P. HAZRA & SONS | 3.41 | 0 | 0
5686 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - D ) & Saluka ), Total House Hold - 158 | Assistant Engineer | Junior Engineer | VCH/000327/2022-2023 | FHTC/28 | 28/04/2022 | 0 | M/S T.P. HAZRA & SONS | 0.49 | 0 | 0
5687 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 Nabada Total House Hold -388 ( Sl .No.- 24) | Assistant Engineer | Junior Engineer | VCH/000328/2022-2023 | FHTC/28 | 28/04/2022 | 0 | ASHISH KUMAR SAMANTA | 18.22 | 0 | 0
5688 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Kastara), Total House Hold - 345 nos. | Assistant Engineer | Junior Engineer | VCH/000329/2022-2023 | FHTC/28 | 28/04/2022 | 0 | SANDHYA DEY | 15.21 | 0 | 0
5689 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 4 (Ramchandra pur (Part - A ), Total House Hold - 145 sl no - 48 | Assistant Engineer | Junior Engineer | VCH/000330/2022-2023 | FHTC/28 | 28/04/2022 | 0 | RUFIKUL MONDAL | 1.17 | 0 | 0
5690 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joytunga (Zone - H ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora & Bankura - ll , Name of OHR - Joytunga (Zone - H ) . No.of Mouza :- Kolaberia Total House Hold - 62 sl no - 04 | Assistant Engineer | Junior Engineer | VCH/000331/2022-2023 | FHTC/28 | 28/04/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.05 | 0 | 0
5691 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kanchanpur (Zone - C ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - Kanchanpur (Zone - C ) . No.of Mouza :- Khandari Total House Hold - 52 sl no - 11 | Assistant Engineer | Junior Engineer | VCH/000332/2022-2023 | FHTC/28 | 28/04/2022 | 0 | BIJOY KOLEY | 3.16 | 0 | 0
5692 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dadhimukha (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Dadhimukha (Zone - D) . No.of Mouza :- Hare Krishnapur , Bhairb pur , Jaganath pur Total House Hold -65 nos. sl no - 01 | Assistant Engineer | Junior Engineer | VCH/000333/2022-2023 | FHTC/28 | 28/04/2022 | 0 | GOURANGA NANDI | 3.28 | 0 | 0
5693 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I Total House Hold -85 nos.(Part-A) | Assistant Engineer | Junior Engineer | VCH/000334/2022-2023 | FHTC/28 | 28/04/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.52 | 0 | 0
5694 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Kamalpur Mantumura mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chanabari (Zone - H) under Saltora - chhatna water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.part - C | Assistant Engineer | Junior Engineer | VCH/000379/2022-2023 | FHTC/02 | 02/05/2022 | 0 | M/S TARUN KUMAR PATRA | 4.92 | 0 | 0
5695 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 07, (Kendboni, Kantaboni, Mamurjuri, Dhansimul, Jarka, (Sonamui (PART) & Malindasi), Total House Hold - 607' | Assistant Engineer | Junior Engineer | VCH/000380/2022-2023 | FHTC/02 | 02/05/2022 | 0 | M/S BIPUL BANERJEE | 11.53 | 0 | 0
5696 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe to cover Jorehira mouza for retrofitting works Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Tilabaid zone - F W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - A | Assistant Engineer | Junior Engineer | VCH/000739/2022-2023 | FHTC/3 | 03/08/2022 | 0 | CREATION CONSTRUCTION | 3.69 | 0 | 0
5697 | Bankura Division | Bankura Sadar Sub-Division | Household survey of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Saltora Block under Salota - Chhatna block (BRGF ph - I project) under Bankura sadar sub-division of Bankura division PHE Dte. block - Saltora, no. of mouza - 03 nos total house hold - 7930 | Assistant Engineer | Junior Engineer | VCH/001357/2021-2022 |  | 30/09/2021 | 0 | TAPAS DEY | 1.75 | 0 | 0
5698 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., | Assistant Engineer | Junior Engineer | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0
5699 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Susne (178) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household - 154 Nos. | Assistant Engineer | Junior Engineer | VCH/001563/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAN KUMAR MANDAL | 10.63 | 0 | 0
5700 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 06(Narricha, Bhabanipur, Baliguma, Sapkrrara, Unara & Dharampu) Total House Hold -404, | Assistant Engineer | Junior Engineer | VCH/001564/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ASOKE BHATTACHARYYA | 34.72 | 0 | 0
5701 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 07), | Assistant Engineer | Junior Engineer | VCH/001565/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TARINI CHARAN UPADHYAY | 3.57 | 0 | 0
5702 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 02 nos, (Moyragora, Jaynagar) Total House Hold - 146, | Assistant Engineer | Junior Engineer | VCH/001566/2021-2022 | FHTC/11 | 11/10/2021 | 0 | M/S BANERJEE & BANERJEE | 6.14 | 0 | 0
5703 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), | Assistant Engineer | Junior Engineer | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 0 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0
5704 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 1, Shyampur (PART) Total House Hold - 75. | Assistant Engineer | Junior Engineer | VCH/001798/2020-2021 |  | 24/03/2021 | 0 | RAFIKUL MONDAL | 3.92 | 0 | 0
5705 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), Total House Hold -972 | Assistant Engineer | Junior Engineer | VCH/002305/2021-2022 | FHTC/04 | 04/01/2022 | 0 | M/S TARUN KUMAR PATRA | 73.08 | 0 | 0
5706 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 36.Block - Bishnupur, Name of OHR - Bhara,No. of Mouza :- 1 no. i.e. Dharampur-22 (215 out of 299), House Hold - 215 | Assistant Engineer | Junior Engineer | VCH/002458/2021-2022 | FHTC/15 | 15/02/2022 | 0 | M/S T.P. HAZRA & SONS | 16.5 | 0 | 0
5707 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Ranjitpur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, Name of OHR:- Ranjitpur, No.of Mouza :- 14 ,(Bisjore ,Niamatpur, Pabayan Ranjitpur Dhekiya, Duiaitara Lalittakuri,Rampur,Dubrapur Bhurkurthol GonsaidihiTentultikn ,Chakparui,Pabra) Total House Hold - 3093. | Assistant Engineer | Junior Engineer | VCH/002507/2021-2022 | FHTC/3 | 03/02/2022 | 0 | DEBAKI RANJAN SARKAR | 75.45 | 0 | 0
5708 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Purusattam pur(PART-B) , Bhairb pur ), Total House Hold -108 | Assistant Engineer | Junior Engineer | VCH/002535/2021-2022 | FHTC/23 | 23/02/2022 | 0 | GOURANGA NANDI | 0.67 | 0 | 0
5709 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Hare Krishnapur (Part--A ), Total House Hold -160 | Assistant Engineer | Junior Engineer | VCH/002536/2021-2022 | FHTC/23 | 23/02/2022 | 0 | GOUTAM GHOSH | 1.14 | 0 | 0
5710 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-F) Total House Hold -101 | Assistant Engineer | Junior Engineer | VCH/002537/2021-2022 | FHTC/23 | 23/02/2022 | 0 | GOUTAM GHOSH | 2.69 | 0 | 0
5711 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-C) Total House Hold -116 | Assistant Engineer | Junior Engineer | VCH/002538/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHANKAR BANERJEE | 1.78 | 0 | 0
5712 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-B) Total House Hold -115 | Assistant Engineer | Junior Engineer | VCH/002539/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHANKAR BANERJEE | 2.79 | 0 | 0
5713 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II (Part-A) , Total House Hold -345 nos. | Assistant Engineer | Junior Engineer | VCH/002540/2021-2022 | FHTC/23 | 23/02/2022 | 0 | PRADIP CHAKRABORTY | 26.13 | 0 | 0
5714 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Agaya (350) & Ampata (351) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 3 Nos. Total Household:- 265 Nos. | Assistant Engineer | Junior Engineer | VCH/002541/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHADIP KOLEY | 8.71 | 0 | 0
5715 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tentulia (27) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer | Junior Engineer | VCH/002543/2021-2022 | FHTC/23 | 23/02/2022 | 0 | BEAUTY CHATTERJEE | 4.06 | 0 | 0
5716 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Dhadkidihi (92) & Puada (94) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) | Assistant Engineer | Junior Engineer | VCH/002545/2021-2022 | FHTC/23 | 23/02/2022 | 0 | BEAUTY CHATTERJEE | 4.5 | 0 | 0
5717 | Bankura Division | Bankura Sadar Sub-Division | Restoration of concrete road at Belboni, Agya Nandapur & Kaljuri mouzas for construction and commissioning of 'FHTC' (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002548/2021-2022 | FHTC/23 | 23/02/2022 | 0 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0
5718 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-A), Total House Hold -343 | Assistant Engineer | Junior Engineer | VCH/002550/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SARKAR CONSTRUCTION | 5.82 | 0 | 0
5719 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 06(Narricha, Bhabanipur, Baliguma, Sapkrrara, Unara & Dharampu) Total House Hold -404 | Assistant Engineer | Junior Engineer | VCH/002551/2021-2022 | FHTC/23 | 23/02/2022 | 0 | ASOKE BHATTACHARYYA | 4.42 | 0 | 0
5720 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Badra, Gopalpur & Bhedua mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002552/2021-2022 | FHTC/23 | 23/02/2022 | 0 | GOUTAM BHOWMIK | 4.78 | 0 | 0
5721 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Junbedia part mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002553/2021-2022 | FHTC/23 | 23/02/2022 | 0 | GOUTAM BHOWMIK | 4.64 | 0 | 0
5722 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) & Deuli (25) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | VCH/002554/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHANKAR BANERJEE | 4.75 | 0 | 0
5723 | Bankura Division | Bankura Sadar Sub-Division | laying of HDPE pipe line from Barjora Pry. School to near Barjora BDO Office of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | VCH/002555/2021-2022 | FHTC/23 | 23/02/2022 | 0 | NAYAN BARDHAN | 4.81 | 0 | 0
5724 | Bankura Division | Bankura Sadar Sub-Division | Dismantalling & recnstruction extra concrete at Latulia mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone - G) under Saltora Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002557/2021-2022 | FHTC/23 | 23/02/2022 | 0 | BEAUTY CHATTERJEE | 3.62 | 0 | 0
5725 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 ( PART-B House Hold - 1284) | Assistant Engineer | Junior Engineer | VCH/002562/2021-2022 | FHTC/22 | 22/02/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 93.15 | 0 | 0
5726 | Bankura Division | Bankura Sadar Sub-Division | creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 05 nos, (Rangametya, Kuladabar, Burat, Deulberia, Murgathol ) Total House Hold - 520 | Assistant Engineer | Junior Engineer | VCH/002671/2021-2022 | FHTC/2 | 02/03/2022 | 0 | MUNMUN UPADHYAY | 6.54 | 0 | 0
5727 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Jaynagar (47) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - A | Assistant Engineer | Junior Engineer | VCH/002672/2021-2022 | FHTC/2 | 02/03/2022 | 0 | M/S TARUN KUMAR PATRA | 3.71 | 0 | 0
5728 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :01 , Hare Krishnapur (Part-- B), Total House Hold -101 | Assistant Engineer | Junior Engineer | VCH/002673/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOURANGA NANDI | 0.6 | 0 | 0
5729 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 03 nos, (Digtore, Krishnapur, Pathordihi) Total House Hold - 673. | Assistant Engineer | Junior Engineer | VCH/002869/2021-2022 | FHTC/15 | 15/03/2022 | 0 | APEX ENTERPRISE | 25.45 | 0 | 0
5730 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Khatmara, Kultuka, Bojapathor mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Tilabaid Zone- F Saltora block under Saltora - Chhatna scheme (BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002928/2021-2022 | FHTC/21 | 21/03/2022 | 0 | MANAS DEY | 4.72 | 0 | 0
5731 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Chandra mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horoka zone - G under Saltora - block Saltora - Chhatna water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002984/2021-2022 | FHTC/24 | 24/03/2022 | 0 | PARESH CHANDRA LAYEK | 4.97 | 0 | 0
5732 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Manora (52), Chaka Doba (58), mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/003011/2021-2022 | FHTC/28 | 28/03/2022 | 0 | PRADIP CHAKRABORTY | 1.44 | 0 | 0
5733 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Haroka, Jadebpur mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haroka Zone G of under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003013/2021-2022 | FHTC/26 | 28/03/2022 | 0 | GOUTAM MUKHERJEE | 4.98 | 0 | 0
5734 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Haroka, Jadebpur mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haroka Zone G of under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003017/2021-2022 | FHTC/28 | 28/03/2022 | 0 | GOUTAM MUKHERJEE | 3.78 | 0 | 0
5735 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Routara (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, No.of Mouza :- 02 (Routara,Bagjada ) Total House Hold - 533. | Assistant Engineer | Junior Engineer | VCH/003018/2021-2022 | FHTC/28 | 28/03/2022 | 0 | SUBHENDU SEKHAR GORAI | 9.18 | 0 | 0
5736 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 39.43 | 45.12 | 0
5737 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 16.07 | 0
5738 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 02 (Koskunda & Kanchanpur(PART)), Total House Hold -479 |  | Junior Engineer | ORD/000231/2020-2021 | 2042/BQA | 29/12/2020 | 30 | ASHISH KUMAR SAMANTA | 42.75 | 0 | 0
5739 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Kanchanpur(PART) ,Kalapani & Nirshce), Total House Hold -476 |  | Junior Engineer | ORD/000232/2020-2021 | 2043/BQA | 29/12/2020 | 30 | ASHOKE BHATTACHARYYA | 42.51 | 0 | 0
5740 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527." |  | Junior Engineer | ORD/000343/2020-2021 | 1768/BQA | 09/12/2020 | 30 | GOUTAM BHATTACHRYYA | 37.17 | 64.08 | 0
5741 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Koskunda) |  | Junior Engineer | VCH/001352/2021-2022 |  | 28/09/2021 | 0 | ASHISH KUMAR SAMANTA | 4.03 | 0 | 0
5742 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Nirsha) |  | Junior Engineer | VCH/001353/2021-2022 |  | 28/09/2021 | 0 | ASOKE BHATTACHARYYA | 4.01 | 0 | 0
5743 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Bagaldhara ICDS to Nischintapur High School to increase pressure in Nischintapur (107) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000057/2022-2023 | 1681/BQA | 27/07/2022 | 30 | M/S TARUN KUMAR PATRA | 14.01 | 13.61 | 0
5744 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dharramuli (128), Kankata (127), Bagaldhara (129) AND Jadurbankata (106) mouzas by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2020-2021 | 479/BQA | 05/02/2021 | 30 | M/S TARUN KUMAR PATRA | 37.7 | 4.83 | 0
5745 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baragajra (103), Asberya (104), Kaliahuta (105) AND Nischintapur (107) mouzas by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000074/2020-2021 | 480/BQA | 05/02/2021 | 30 | M/S TARUN KUMAR PATRA | 30.54 | 3.56 | 0
5746 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Bara Gajra (103), Asberya (104), Kaliahuta (105), Jadurbankata (106), Nischintapur (107), Kankata (127), Dharra Muli (128) & Bagaldhara (129) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-F (Masanjhar) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000523/2020-2021 | 321/KSD | 29/12/2020 | 61 | D. S. ENTERPRISE | 0.33 | 0 | 0
5747 | Bankura Division | Khatra Sub-Division | laying extra HDPE pipe line to cover Asberya (104 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - F ( Masanjhar) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, | Assistant Engineer | Junior Engineer | VCH/003069/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PRADYUMNA KOLEY | 3.9 | 0 | 0
5748 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kundurka (43) & Paira (44) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000129/2020-2021 | 186/BQA | 18/01/2021 | 30 | PARTHA PRATIM CHATAIT | 26.57 | 0 | 0
5749 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simlabandh (45), Bhedua (46) & Lutia (47) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000130/2020-2021 | 187/BQA | 18/01/2021 | 30 | PARTHA PRATIM CHATAIT | 20.19 | 0 | 0
5750 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000176/2021-2022 | 548/KSD | 29/06/2021 | 10 | GANESH ROY | 4.99 | 0 | 0
5751 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000177/2021-2022 | 549/KSD | 29/06/2021 | 10 | GANESH ROY | 4.99 | 0 | 0
5752 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Kundurka (43), Paira (44), Simlabandh (45), Bhedua (46) & Lutia (47) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000515/2020-2021 | 313/KSD | 29/12/2020 | 2 | GANESH ROY | 0.23 | 0 | 0
5753 | Bankura Division | Khatra Sub-Division | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 20 | BEAUTY CHATTERJEE | 4.95 | 0.34 | 0
5754 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
5755 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 Khyerkanali (PART-2) Total House Hold - 123 | Assistant Engineer | Junior Engineer | VCH/002314/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADIP CHAKRABORTY | 9.95 | 0 | 0
5756 | Bankura Division | Khatra Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) | Assistant Engineer | Junior Engineer | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0
5757 | Bankura Division | Khatra Sub-Division | Laying extra UPVC Pipe line to cover Shyampur mouza for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Shyampur (Zone- E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 08 | Assistant Engineer | Junior Engineer | VCH/002810/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GOUTAM BHATTACHRYYA | 4.65 | 0 | 0
5758 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 30 | M/S TARUN KUMAR PATRA | 96.69 | 10.28 | 0
5759 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 07, (Kendboni, Kantaboni, Mamurjuri, Dhansimul, Jarka, (Sonamui (PART) & Malindasi), Total House Hold - 607" |  | Junior Engineer | ORD/000328/2020-2021 | 1375/BQA | 08/10/2020 | 30 | M/S BIPUL BANERJEE | 41.76 | 0 | 100
5760 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 01, (Sonamui (PART), Total House Hold - 606 " |  | Junior Engineer | ORD/000329/2020-2021 | 1376/BQA | 08/10/2020 | 30 | M/S BIPUL BANERJEE | 41.71 | 0 | 100
5761 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos |  | Junior Engineer | VCH/000268/2022-2023 | FHTC/18 | 18/04/2022 | 0 | RANABIR CHATTERJEE | 25.21 | 0 | 0
5762 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover malindasi mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI(P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001335/2021-2022 |  | 28/09/2021 | 0 | SOUMITRA BHATTACHARYA | 4.81 | 0 | 0
5763 | Bankura Division | Bankura Sadar Sub-Division | Survey work of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 07 nos, (Kendboni, Kantaboni, Mamurjuri, Dhansimul, Jarka, Sonamui & Malindasi), Total House Hold - 1213. |  | Junior Engineer | VCH/001341/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 0.33 | 0 | 0
5764 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kendboni (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , Total House Hold - 1212." |  | Junior Engineer | VCH/001411/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
5765 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA ofKendbani (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001990/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
5766 | Bankura Division | Bankura Sadar Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) , Name of mouza -Kodma , (Part-B) |  | Junior Engineer | VCH/002417/2021-2022 | FHTC/17 | 17/02/2022 | 0 | SIB SANKAR CHOWDHURY | 2.63 | 0 | 0
5767 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kodalia(PART-B), Total House Hold -429 |  | Junior Engineer | VCH/002486/2021-2022 | FHTC/1 | 01/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 7.18 | 0 | 0
5768 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | VCH/002491/2021-2022 | FHTC/3 | 03/02/2022 | 0 | SUBHANKAR BANERJEE | 2.83 | 0 | 0
5769 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuakana (63) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002804/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHADIP KOLEY | 1.01 | 0 | 0
5770 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhuakana (63) & Bauridihi (68) mouzas by retrofitting , Zone-A of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002805/2021-2022 | FHTC/5 | 05/03/2022 | 0 | SUBHADIP KOLEY | 1.93 | 0 | 0
5771 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Khandarani (155) mouzas by retrofitting , Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/002806/2021-2022 | FHTC/5 | 05/03/2022 | 0 | PRADYUMNA KOLEY | 1.69 | 0 | 0
5772 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Kamalhit mouzas dismantling and reconstruction for retrofitting works for creaction of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/003082/2021-2022 | FHTC/30 | 30/03/2022 | 0 | JAGADISH BANERJEE | 1.47 | 0 | 0
5773 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320. |  | Junior Engineer | ORD/000067/2020-2021 | 470/BQA | 05/02/2021 | 30 | ZAKIR HOSSAIN MONDAL | 30.12 | 0 | 0
5774 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :-Amdiha, Goyaldanga,Malpara(Part) Total House Hold - 319. |  | Junior Engineer | ORD/000068/2020-2021 | 471/BQA | 05/02/2021 | 30 | ZAKIR HOSSAIN MONDAL | 30.08 | 0 | 0
5775 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Jamdoba, Ramgora, Harokabedya (Part), Palsora (Part) Total House Hold - 210. |  | Junior Engineer | ORD/000069/2020-2021 | 472/BQA | 05/02/2021 | 30 | NAYAN BARDHAN | 15.27 | 1.05 | 10
5776 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :Mangalda, Parasibonaa, Guniada, Malpara (Part), Harokbedya (Part) Total House Hold - 209 |  | Junior Engineer | ORD/000070/2020-2021 | 473/BQA | 05/02/2021 | 30 | NAYAN BARDHAN | 15.25 | 6.04 | 0
5777 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Palsora mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000261/2022-2023 | 1308/BQA | 15/06/2022 | 15 | M/S NAYAN BARDHAN | 2.82 | 2.82 | 0
5778 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | ORD/000399/2020-2021 | 857/BQA | 25/02/2021 | 30 | SUBHANKAR BANERJEE | 35.1 | 38.36 | 0
5779 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Total House Hold - 209. |  | Junior Engineer | VCH/000120/2021-2022 |  | 21/04/2021 | 0 | NAYAN BARDHAN | 9.2 | 0 | 0
5780 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
5781 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jagannathpur (110), Nimdiha (112) & Pirrabakra (113) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2020-2021 | 196/BQA | 18/01/2021 | 30 | GOUTAM BHATTACHRYYA | 32.57 | 13.6 | 0
5782 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mukundapur (114), Khakrakanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000142/2020-2021 | 197/BQA | 18/01/2021 | 30 | APEX ENTERPRISE | 37.4 | 0 | 0
5783 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000358/2020-2021 | 44/KSD | 15/01/2021 | 59 | TAPAS DEY | 0.34 | 0 | 0
5784 | Bankura Division | Khatra Sub-Division | Household survey in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 15) | Assistant Engineer | Junior Engineer | VCH/001037/2021-2022 |  | 16/09/2021 | 0 | TAPAS DEY | 0.24 | 0 | 0
5785 | Bankura Division | Khatra Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under saltora chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - chhatna, Name of OHR - Dhaban No.of Mouza :-1 , Total House Hold - 128, . | Assistant Engineer | Junior Engineer | VCH/001186/2021-2022 | FHTC/23 | 23/07/2021 | 0 | TAPAN KUMAR UPADHYAY | 7.99 | 0 | 0
5786 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Jaganathpur (110) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001481/2021-2022 |  | 08/10/2021 | 0 | APEX ENTERPRISE | 4.89 | 0 | 0
5787 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) Mouza Sankarlayekerdanga, | Assistant Engineer | Junior Engineer | VCH/001756/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 2.69 | 0 | 0
5788 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) (Part-B) Mouza Chotobankadaha | Assistant Engineer | Junior Engineer | VCH/001757/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.83 | 0 | 0
5789 | Bankura Division | Khatra Sub-Division | Lying extra upvc pipe line to cover Jagannathpur mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001485/2021-2022 |  | 08/10/2021 | 0 | APEX ENTERPRISE | 4.64 | 0 | 0
5790 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Routara (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, No.of Mouza :- 02 (Routara,Bagjada ) Total House Hold - 533., | Assistant Engineer | Junior Engineer | VCH/001660/2021-2022 | FHTC/28 | 28/10/2021 | 0 | SUBHENDU SEKHAR GORAI | 20.58 | 0 | 0
5791 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 05, (Kesekol (PART), Domanbandhi, Kumuria, Tilabedia & Kamladanga), Total House Hold - 516 | Assistant Engineer | Junior Engineer | VCH/002303/2021-2022 | FHTC/04 | 04/01/2022 | 0 | PARAMESWAR CHOWDHURY | 0.86 | 0 | 0
5792 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Sonadaha(part), Total House Hold -137' | Assistant Engineer | Junior Engineer | VCH/002304/2021-2022 | FHTC/04 | 04/01/2022 | 0 | TARINI CHARAN UPADHYAY | 2.21 | 0 | 0
5793 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. | Assistant Engineer | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
5794 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 | Assistant Engineer | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 1.25 | 0
5795 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 30 | SUMITA UPADHYAY | 13.03 | 1.54 | 0
5796 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baidyanathpur (118) mouza by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2020-2021 | 481/BQA | 05/02/2021 | 30 | APEX ENTERPRISE | 23.86 | 0.47 | 0
5797 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108) Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2020-2021 | 482/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 16.61 | 1.14 | 0
5798 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyambazar (109) Banbedia (111) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2020-2021 | 483/BQA | 05/02/2021 | 30 | GOUTAM BHATTACHRYYA | 20.37 | 2.37 | 0
5799 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 16) | Assistant Engineer | Junior Engineer | ORD/000359/2020-2021 | 45/KSD | 15/01/2021 | 59 | TAPAS DEY | 0.3 | 0 | 0
5800 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SANJOY MONDAL | 4.55 | 0 | 0
5801 | Bankura Division | Khatra Sub-Division | Laying extra UPVC pipe line to cover Shyam bazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001480/2021-2022 |  | 08/10/2021 | 0 | APEX ENTERPRISE | 4.96 | 0 | 0
5802 | Bankura Division | Khatra Sub-Division | Laying extra upvc pipeline to cover Shyambazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | VCH/001482/2021-2022 |  | 08/10/2021 | 0 | BHATTACHARYYA ENTERPRISE | 4.86 | 0 | 0
5803 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, | Assistant Engineer | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
5804 | Bankura Division | Khatra Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140, | Assistant Engineer | Junior Engineer | VCH/001561/2021-2022 | FHTC/11 | 11/10/2021 | 0 | GANGADHAR MONDAL | 8.9 | 0 | 0
5805 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) | Assistant Engineer | Junior Engineer | VCH/002930/2021-2022 | FHTC/21 | 21/03/2022 | 0 | SRIKANTA MONDAL | 1.97 | 0 | 0
5806 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line from Domnipara more to Dhuliadihi more to Cover Kalabati & Dhulidihi mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000274/2022-2023 | 10/BQA | 03/01/2023 | 819 | SOMA BANERJEE | 7.19 | 6.88 | 86
5807 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811 |  | Junior Engineer | ORD/000409/2020-2021 | 404/BQA | 04/02/2021 | 30 | PRINCE INDUTRIES (INDIA) | 72.99 | 4.82 | 0
5808 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 5.12 | 0
5809 | Bankura Division | Bankura Sadar Sub-Division | Laying extra upvc pipe line to cover Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273), Benasuli (275), Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura Under Jal Swapna & Jal Jeevan Mission Programme., |  | Junior Engineer | VCH/001643/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UNITED TRADERS | 4.95 | 0 | 0
5810 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  | Junior Engineer | VCH/001644/2021-2022 | FHTC/28 | 28/10/2021 | 0 | SOUMITRA BHATTACHARYA | 4.51 | 0 | 0
5811 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  | Junior Engineer | VCH/001645/2021-2022 | FHTC/28 | 28/10/2021 | 0 | SOUMITRA BHATTACHARYA | 4.66 | 0 | 0
5812 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Hetiasol (271), Dakai (268) & Karra (269) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  | Junior Engineer | VCH/001648/2021-2022 | FHTC/28 | 28/10/2021 | 0 | ASOKE KUMAR SAHU | 2.2 | 0 | 0
5813 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - D ) & Saluka, |  | Junior Engineer | VCH/001649/2021-2022 | FHTC/28 | 28/10/2021 | 0 | M/S T.P. HAZRA & SONS | 2.71 | 0 | 0
5814 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - C), |  | Junior Engineer | VCH/001655/2021-2022 | FHTC/28 | 28/10/2021 | 0 | M/S T.P. HAZRA & SONS | 3.3 | 0 | 0
5815 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B), |  | Junior Engineer | VCH/001656/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UNITED TRADERS | 4.95 | 0 | 0
5816 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A), |  | Junior Engineer | VCH/001657/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UNITED TRADERS | 4.94 | 0 | 0
5817 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Arkama (124) & Hazamdihi (233) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  | Junior Engineer | VCH/001658/2021-2022 | FHTC/28 | 28/10/2021 | 0 | UNITED TRADERS | 4.76 | 0 | 0
5818 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 30 | AMITAVA CHAKRABORTY | 29.71 | 14.37 | 0
5819 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Shyamdaspur), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Shyamdaspur), Total House Hold - 1112 nos. | Assistant Engineer | Junior Engineer | ORD/000126/2021-2022 | 2791/BQA | 11/11/2021 | 30 | BISWARUP BOSE | 52.83 | 35.2 | 100
5820 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mousa (Bhadul, Bhutsahar & Bejgram) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 03 nos, (Bhadul, Bhutsahar & Bejgram), Total House Hold - 1166 nos. | Assistant Engineer | Junior Engineer | ORD/000127/2021-2022 | 2792/BQA | 11/11/2021 | 30 | ASOKE BHATTACHARYYA | 58.88 | 47.29 | 0
5821 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Garerban, Ekteswar (Part, 30%), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar, No.of Mouza :- 02 no., (Garerban, Ekteswar (Part, 30%), Total House Hold - 480 nos. | Assistant Engineer | Junior Engineer | ORD/000187/2021-2022 | 2988/BQA | 25/11/2021 | 30 | MAKALI CONSTRUCTION | 21.48 | 0 | 0
5822 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Sanabandh), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Sanabandh) Total House Hold - 937 nos. | Assistant Engineer | Junior Engineer | ORD/000188/2021-2022 | 2989/BQA | 25/11/2021 | 30 | NEW STAR CONSTRUCTION | 45.11 | 0 | 0
5823 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2021-2022 | 2816/BQA | 12/11/2021 | 0 | Resource Division | 3.98 | 0 | 0
5824 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line for Shyamdaspur to Cover Shyamdaspur mouzas for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) OHR under Ekteswar and its adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 49/BQA | 05/01/2023 | 45 | BISWARUP BOSE | 4.94 | 0 | 0
5825 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line for Shyamdaspur to Cover Shyamdaspur mouzas for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) OHR under Ekteswar and its adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000373/2022-2023 | 50/BQA | 05/01/2023 | 45 | BISWARUP BOSE | 4.98 | 0 | 0
5826 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 30 | SOUMITRA BOSE | 23.15 | 9.58 | 0
5827 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II) No.of Mouza :- 07 nos, (Ekteswar Garerbon , Shyamdaspur, Bhadul, Bhutsahar, Bejagram, Sanabandh) , Total House Hold - 3695 nos. | Assistant Engineer | Junior Engineer | ORD/000920/2021-2022 | 64/BSD | 14/01/2022 | 90 | TAPAS DEY | 1.23 | 0 | 0
5828 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II) No.of Mouza :- 07 nos, (Ekteswar Garerbon , Shyamdaspur, Bhadul, Bhutsahar, Bejagram, Sanabandh) , Total House Hold - 3695 nos. | Assistant Engineer | Junior Engineer | VCH/000252/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.99 | 0 | 0
5829 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejgram & Sanbandha) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002388/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 105 | 0 | 0
5830 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mousa (Bhadul, Bhutsahar & Bejgram) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 03 nos, (Bhadul, Bhutsahar & Bejgram), Total House Hold - 1166 nos. | Assistant Engineer | Junior Engineer | VCH/002845/2021-2022 | FHTC/14 | 14/03/2022 | 0 | ASOKE BHATTACHARYYA | 11.59 | 0 | 0
5831 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 45 | ALOK ENTERPRISE | 135.35 | 21.97 | 0
5832 | Bankura Division | Brishnupur Sub-Division | Laying of extra UPVC pipeline to increase water pressure at Horakabaid mouza for rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2022-2023 | 471/BSD | 06/06/2022 | 15 | TAPAN KUMAR MANDAL | 4.94 | 0.24 | 0
5833 | Bankura Division | Brishnupur Sub-Division | Relaying of MS rising main instead of DI rising main, damaged during widening of road (Birasimul-Sahaspur road) at Rol zone-B W/S Scheme of Indas BRGF under Bishnupur Sub-Division of Bankura Division P.H.E. Dte. (1st Part) (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000157/2022-2023 | 249/VSD | 17/08/2022 | 30 | GOUTAM GHOSH | 3.69 | 3.68 | 0
5834 | Bankura Division | Brishnupur Sub-Division | Relaying of MS rising main instead of DI rising main, damaged during widening of road (Birasimul-Sahaspur road) at Rol zone-B W/S Scheme of Indas BRGF under Bishnupur Sub-Division of Bankura Division P.H.E. Dte. (2nd Part) (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000160/2022-2023 | 250/VSD | 17/08/2022 | 30 | GOUTAM GHOSH | 3.52 | 3.51 | 0
5835 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | ORD/000165/2021-2022 | 2849/BQA | 16/11/2021 | 30 | M/S TARUN KUMAR PATRA | 89.18 | 0 | 0
5836 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 01 Ekteswar (Gogesh Pally), Total House Hold - 85 nos. | Assistant Engineer | Junior Engineer | VCH/001492/2022-2023 | FHTC/23 | 23/12/2022 | 0 | MANOJ GHOSAL | 4.38 | 0 | 0
5837 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline to increase pressure in Madankata (176) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) | Assistant Engineer | Junior Engineer | VCH/001493/2022-2023 | FHTC/23 | 23/12/2022 | 0 | M/S. AMAL KUMAR SARKAR | 4.47 | 0 | 0
5838 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline from Atchala to Jaynagar Primary School to increase pressure to cover Jaynagar (47) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer | Junior Engineer | VCH/001494/2022-2023 | FHTC/23 | 23/12/2022 | 0 | M/S. AMAL KUMAR SARKAR | 3.77 | 0 | 0
5839 | Bankura Division | Brishnupur Sub-Division | Laying HDPE pipeline to increase pressure in Rajadali (156) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | VCH/001495/2022-2023 | FHTC/23 | 23/12/2022 | 0 | SUBHENDU BANERJEE | 4.51 | 0 | 0
5840 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 04 no [Narasole, Taljhoria, Khabanigoparpur (Part), Jhikuria] Total House Hold- 359 | Assistant Engineer | Junior Engineer | VCH/001496/2022-2023 | FHTC/23 | 23/12/2022 | 0 | TAPAS KUMAR HAZRA | 4.55 | 0 | 0
5841 | Bankura Division | Brishnupur Sub-Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Shyamdaspur), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Shyamdaspur), Total House Hold - 1112 nos. | Assistant Engineer | Junior Engineer | VCH/001497/2022-2023 | FHTC/23 | 23/12/2022 | 0 | BISWARUP BOSE | 7.84 | 0 | 0
5842 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001498/2022-2023 | FHTC/23 | 23/12/2022 | 0 | GOUTAM BHATTACHRYYA | 20.15 | 0 | 0
5843 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 30 | AMITAVA CHAKRABORTY | 29.71 | 14.97 | 0
5844 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | ORD/000256/2021-2022 | 3164/BQA | 17/12/2021 | 60 | PARTHA PRATIM CHATAIT | 101.36 | 37.77 | 0
5845 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia (junbedia more) Total House Hold -60 nos. | Assistant Engineer | Junior Engineer | ORD/000335/2022-2023 | 601/BSD | 16/08/2022 | 21 | GANESH ROY | 4.99 | 0 | 0
5846 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia (uttar arabindanagar & Indrapasta) Total House Hold -50 nos. | Assistant Engineer | Junior Engineer | ORD/000336/2022-2023 | 603/BSD | 16/08/2022 | 21 | GANESH ROY | 4.99 | 0 | 0
5847 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( Ramkrishnapolly & sushundanga) Total House Hold -60 nos. | Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 606/BSD | 16/08/2022 | 21 | GANESH ROY | 4.8 | 0 | 100
5848 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( chattar Bekari goly) Total House Hold -70 nos. | Assistant Engineer | Junior Engineer | ORD/000338/2022-2023 | 608/BSD | 16/08/2022 | 21 | GANESH ROY | 4.91 | 0 | 0
5849 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( Palashtala) Total House Hold -63 nos. | Assistant Engineer | Junior Engineer | ORD/000339/2022-2023 | 610/BSD | 16/08/2022 | 21 | GANESH ROY | 4.96 | 0 | 0
5850 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Harialgora, Keshra, Jugsaha, Salboni & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | ORD/000579/2021-2022 | 66/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.68 | 0.17 | 0
5851 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cove Salboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000661/2021-2022 | 268/BSD | 17/03/2022 | 10 | PARTHA PRATIM CHHATAIT | 4.97 | 4.96 | 0
5852 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Harialgora, Keshra, Jugsaha, Salboni & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | VCH/000253/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.51 | 0 | 0
5853 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipeline to increase pressure in Labdapara (265) & Birkham (266) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001427/2022-2023 | FHTC/23 | 23/12/2022 | 0 | PARTHA PRATIM CHHATAIT | 5.98 | 0 | 0
5854 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 | Assistant Engineer | Junior Engineer | VCH/002569/2021-2022 | FHTC/26 | 26/02/2022 | 0 | RUFIKUL MONDAL | 10.75 | 0 | 0
5855 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 01 no., (Saburbandh), Total House Hold - 428 nos. | Assistant Engineer | Junior Engineer | VCH/002570/2021-2022 | FHTC/26 | 28/02/2022 | 0 | RUFIKUL MONDAL | 20.4 | 0 | 0
5856 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 02 nos. i.e. Chotobankadaha-148 and Bandrya- 150, Total House Hold - 534 ( Out of 703) | Assistant Engineer | Junior Engineer | VCH/002571/2021-2022 | FHTC/26 | 26/02/2022 | 0 | SUBHENDU SEKHAR GORAI | 34.27 | 0 | 0
5857 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 140 | Assistant Engineer | Junior Engineer | VCH/002572/2021-2022 | FHTC/26 | 26/02/2022 | 0 | MOHAN KUMAR ROY | 0.66 | 0 | 0
5858 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002573/2021-2022 | FHTC/26 | 26/02/2022 | 0 | KHAN ENTERPRISE | 59.28 | 0 | 0
5859 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Keshra mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - B | Assistant Engineer | Junior Engineer | VCH/003071/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.81 | 0 | 0
5860 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Keshra mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - A. | Assistant Engineer | Junior Engineer | VCH/003072/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.89 | 0 | 0
5861 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover (Tantkanali, Harialgora, Keshra, Jugsha & shitaldihi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | VCH/003073/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 4.9 | 0 | 0
5862 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 45 | ALOK ENTERPRISE | 135.35 | 1.47 | 0
5863 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 21) | Assistant Engineer | Junior Engineer | ORD/000238/2022-2023 | 1300/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.77 | 3.77 | 0
5864 | Bankura Division | Brishnupur Sub-Division | Laying of HDPE, GI & MS pipe line from rising main air valve near Fulberia to Damodar pur, Nirsha, Bansol, Dhwajmonipur & Kalapani mouza to increase pressure along with all allied works of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 2237/BQA | 09/12/2022 | 45 | PRADYUMNA KOLEY | 28.16 | 1.18 | 0
5865 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Narikala, No. of Mouza :- 02 nos. i.e. Layak Bandh - 13 & Chua Masina - 17, Total House Hold - 2202 | Assistant Engineer | Junior Engineer | ORD/000301/2021-2022 | 3348/BQA | 31/12/2021 | 60 | UNICON INDIA | 190.97 | 0 | 100
5866 | Bankura Division | Brishnupur Sub-Division | Laying HDPE Pipe Line to increase pressure at Bibadinagar village for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2022-2023 | 624/BSD | 16/08/2022 | 21 | PRADYUMNA KOLEY | 3.56 | 3.51 | 0
5867 | Bankura Division | Brishnupur Sub-Division | Laying HDPE Pipe Line to increase pressure at panchbaga mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000476/2022-2023 | 623/BSD | 16/08/2022 | 21 | BIJOY KOLEY | 4.38 | 4.35 | 0
5868 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002573/2021-2022 | FHTC/26 | 26/02/2022 | 0 | KHAN ENTERPRISE | 59.28 | 0 | 0
5869 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002574/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S BIPUL BANERJEE | 42.66 | 0 | 0
5870 | Bankura Division | Brishnupur Sub-Division | 'Name of Work: Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 02, (Karanjora, Lapuria (PART)), Total House Hold - 606' | Assistant Engineer | Junior Engineer | VCH/002575/2021-2022 | FHTC/26 | 26/02/2022 | 0 | SOUMITRA BHATTACHARYA | 12.95 | 0 | 0
5871 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82)Total Mouza:- 30 Nos. Total Household - 4013 Nos. | Assistant Engineer | Junior Engineer | VCH/002831/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 250.78 | 0 | 0
5872 | Bankura Division | Brishnupur Sub-Division | Additional work by laying of new HDPE pipeline of uncover area in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Beside of Joykrishnapur to Ajoydhya PWD road adn Joykrinhanpur colony mete para within Radhanagar W/S Scheme zone - ll under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002958/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 4.57 | 0 | 0
5873 | Bankura Division | Brishnupur Sub-Division | Additional work by laying of new HDPE pipeline of uncover area in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Beside of Joykrishnapur village and Joykrishnapur brick Bhata within Radhanagar W/S Scheme zone - ll under Bishnupur Sub - Division of Bankura Division, PHE Dte. sl no - 03 | Assistant Engineer | Junior Engineer | VCH/002959/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 4.55 | 0 | 0
5874 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 | Assistant Engineer | Junior Engineer | ORD/000137/2021-2022 | 2806/BQA | 11/11/2021 | 30 | GOUTAM BHOWMIK | 66.34 | 4.77 | 0
5875 | Bankura Division | Brishnupur Sub-Division | Dismantaling & reconstruction of Kastora, Singhir & Majit mouza & Cleaning Wasing the pipeline from Bhaghucha to kechka for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 543/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.14 | 4.13 | 0
5876 | Bankura Division | Brishnupur Sub-Division | Repairing and renovation of pipe line work in connection with Jal Jeevan Mission(JJM) of Chuamasina Zone-B and Prakash Zone-B Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000644/2022-2023 | 44/VSD | 10/03/2023 | 15 | SONU SINGH | 0.96 | 0.62 | 0
5877 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. | Assistant Engineer | Junior Engineer | VCH/000661/2022-2023 | FHTC/27 | 27/09/2022 | 0 | S K FAZLUL ALAM | 4.81 | 0 | 0
5878 | Bankura Division | Brishnupur Sub-Division | Laying HDPE Pipe Line from Kendsayer to Harekrishnapur to Cover Harekrishnapur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000951/2022-2023 | FHTC/21 | 21/09/2022 | 0 | TAPAS KUMAR HAZRA | 13.26 | 0 | 0
5879 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001172/2022-2023 | FHTC/27 | 27/09/2022 | 0 | M/S TARUN KUMAR PATRA | 58.15 | 0 | 0
5880 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 nos (Mobarakpur, Agra, Adra & Sirsara) Total House Hold - 605' | Assistant Engineer | Junior Engineer | VCH/001200/2022-2023 | FHTC/30 | 30/09/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 20.89 | 0 | 0
5881 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49 Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) | Assistant Engineer | Junior Engineer | ORD/000092/2021-2022 | 2529/BQA | 23/09/2021 | 30 | JAI BHARAT COMMERCIAL CORPORATION | 42.21 | 0 | 0
5882 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no.49 Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 04 nos. i.e. Chakrabia-77,Arapur-79,Banberia- 80 & Petan 81 , Total House Hold - 537 (537 out of 1112) | Assistant Engineer | Junior Engineer | ORD/000113/2021-2022 | 2691/BQA | 26/10/2021 | 30 | I.R.CONSTRUCTION | 35.96 | 26.65 | 80
5883 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kalipur (Zone- C) under Chatna Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Kalipur (Zone - C) . No.of Mouza :- 03 ( Nangla, Gidhuria, Majdihi) Total House Hold -436 | Assistant Engineer | Junior Engineer | VCH/002609/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOUTAM BHATTACHRYYA | 14.34 | 0 | 0
5884 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line t to cover Valai Bhagan Village of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002613/2021-2022 | FHTC/24 | 24/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 3.72 | 0 | 0
5885 | Bankura Division | Brishnupur Sub-Division | Extra HDPE pipe line to cover Mukundrapur village of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002616/2021-2022 | FHTC/24 | 24/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.68 | 0 | 0
5886 | Bankura Division | Brishnupur Sub-Division | extra HDPE pipe line from Mukuti Village Tematha more to Jorjhal Roypara of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), | Assistant Engineer | Junior Engineer | VCH/002619/2021-2022 | FHTC/24 | 24/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 4.97 | 0 | 0
5887 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 01 no., (Radhakantapur), Total House Hold - 463 nos | Assistant Engineer | Junior Engineer | VCH/002799/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GANESH ROY | 26.6 | 0 | 0
5888 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 | Assistant Engineer | Junior Engineer | ORD/000394/2021-2022 | 205/BQA | 01/02/2022 | 60 | M/S TARUN KUMAR PATRA | 153.87 | 43.17 | 0
5889 | Bankura Division | Brishnupur Sub-Division | Shifting of UPVC pipe line due to widening of Kotulpur Indas PWD road under Kushmuri Zone -B (Indas BRGF) water supply scheme under Bishnupur Sub-Division of Bankura Division, PHE Dte.(Part A) (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000563/2021-2022 | 40/VSD | 22/02/2022 | 30 | OSMAN SEKH | 4.52 | 0 | 0
5890 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2021-2022 | 480/BQA | 04/03/2022 | 0 | Resource Division | 16.05 | 0 | 0
5891 | Bankura Division | Brishnupur Sub-Division | Supplying fabrication, Eraction on suitable RCC foundation, instalation, commissioning and testing with satisfactory completion etc. of iron Elimination plant (IEP) of capasity 100 cum 3 three months trial run at Kusmuri B OHR zone - B site in Indas block under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000281/2022-2023 | FHTC/26 | 26/04/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 45.75 | 0 | 0
5892 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 | Assistant Engineer | Junior Engineer | VCH/001546/2022-2023 | FHTC/06 | 06/01/2023 | 0 | M/S TARUN KUMAR PATRA | 93.05 | 0 | 0
5893 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 | Assistant Engineer | Junior Engineer | ORD/000304/2021-2022 | 3351/BQA | 30/12/2021 | 60 | SIB SANKAR CHOWDHURY | 179.18 | 0 | 0
5894 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2021-2022 | 476/BQA | 04/03/2022 | 0 | Resource Division | 12.79 | 0 | 0
5895 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 | Assistant Engineer | Junior Engineer | VCH/000204/2022-2023 | FHTC/11 | 11/04/2022 | 0 | SIB SANKAR CHOWDHURY | 85.33 | 0 | 0
5896 | Bankura Division | Brishnupur Sub-Division | Rectro fitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (ZONE- D ) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 14 nos, (Alunia, Damodarpur, Monipur, Khagra, Sukhabad , Katabaid, Demramol, Beriatha, Janadudumar Rampur Raghumathpur, l, Chhatpathor, Shalroha, Nimra,) Total House Hold - 2711. | Assistant Engineer | Junior Engineer | VCH/002403/2021-2022 | FHTC/21 | 21/02/2022 | 0 | SIB SANKAR CHOWDHURY | 76 | 0 | 0
5897 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Loharpara Total house hold - 35 | Assistant Engineer | Junior Engineer | VCH/002404/2021-2022 | FHTC/21 | 21/02/2022 | 0 | BIT ENTERPRISE | 2.99 | 0 | 0
5898 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-I )Total House Hold - 139.' | Assistant Engineer | Junior Engineer | VCH/002405/2021-2022 | FHTC/21 | 21/02/2022 | 0 | SK. SAHAJAHAN | 1.19 | 0 | 0
5899 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 71 (Sl No of Work- 03) | Assistant Engineer | Junior Engineer | VCH/002406/2021-2022 | FHTC/21 | 21/02/2022 | 0 | PRADIP CHAKRABORTY | 1.1 | 0 | 0
5900 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 72 (Sl No of Work- 04) | Assistant Engineer | Junior Engineer | VCH/002407/2021-2022 | FHTC/21 | 21/02/2022 | 0 | PRADIP CHAKRABORTY | 0.03 | 0 | 0
5901 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpu (Part) Total House Hold- 70 (Sl No of Work- 07) | Assistant Engineer | Junior Engineer | VCH/002408/2021-2022 | FHTC/21 | 21/02/2022 | 0 | ZAKIR HOSSAIN MONDAL | 0.49 | 0 | 0
5902 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 61 (Sl No of Work- 12) | Assistant Engineer | Junior Engineer | VCH/002409/2021-2022 | FHTC/21 | 21/02/2022 | 0 | M/S NAYAN BARDHAN | 0.54 | 0 | 0
5903 | Bankura Division | Brishnupur Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban zone - A under Saltora - Chhatna block w/s scheme ( BRGF ph - l project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR - Dhaban . No.of Mouza :-01 Bhelani ), Total House Hold - 140 , | Assistant Engineer | Junior Engineer | VCH/002410/2021-2022 | FHTC/21 | 21/02/2022 | 0 | TAPAS KUMBHAKAR | 1.96 | 0 | 0
5904 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Badra,Gopalpur, Bhedua(Part), Total House Hold - 435' | Assistant Engineer | Junior Engineer | VCH/002411/2021-2022 | FHTC/21 | 21/02/2022 | 0 | GOUTAM BHOWMIK | 4.3 | 0 | 0
5905 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph- I project) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 02 Parasiabad & LAXMI JANARDANPUR (Part), Total House Hold- 67 (Sl No of Work- 01), | Assistant Engineer | Junior Engineer | VCH/002412/2021-2022 | FHTC/21 | 21/02/2022 | 0 | M/S NAYAN BARDHAN | 0.76 | 0 | 0
5906 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kanchanpur (Zone - C) W/S Scheme under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph- I project) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte Block - Barjora, No.of Mouza :- 01 Shitla part - B . Total House Hold - 119 nos. | Assistant Engineer | Junior Engineer | VCH/002413/2021-2022 | FHTC/21 | 21/02/2022 | 0 | SANDHYA DEY | 0.96 | 0 | 0
5907 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-C) & PabayaTotal House Hold -119 | Assistant Engineer | Junior Engineer | VCH/002414/2021-2022 | FHTC/21 | 21/02/2022 | 0 | ASHOKE KUMAR DEY | 0.88 | 0 | 0
5908 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - Il , Name of OHR - Bankati . No.of Mouza :- 02 Bankati & Beldanga Total House Hold -132 | Assistant Engineer | Junior Engineer | VCH/002415/2021-2022 | FHTC/21 | 21/02/2022 | 0 | SHYAMAL KUMAR DAS | 1.16 | 0 | 0
5909 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- ChandarBardgan Para (Part- A), Total House Hold -50. | Assistant Engineer | Junior Engineer | VCH/002421/2021-2022 | FHTC/18 | 18/02/2022 | 0 | MAYA CONSTRUCTION | 0.32 | 0 | 0
5910 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 ( Panchbaga.), Total House Hold - 438 | Assistant Engineer | Junior Engineer | VCH/002422/2021-2022 | FHTC/18 | 18/02/2022 | 0 | GOUTAM BHOWMIK | 11.27 | 0 | 0
5911 | Bankura Division | Brishnupur Sub-Division | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. si no -02 | Assistant Engineer | Junior Engineer | VCH/002424/2021-2022 | FHTC/18 | 18/02/2022 | 0 | BISWESWAR CONSTRUCTION | 4.64 | 0 | 0
5912 | Bankura Division | Brishnupur Sub-Division | "extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no -03" | Assistant Engineer | Junior Engineer | VCH/002425/2021-2022 | FHTC/18 | 18/02/2022 | 0 | BISWESWAR CONSTRUCTION | 2.32 | 0 | 0
5913 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC Pipe Line to Cover PANCHBAGA 'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002427/2021-2022 | FHTC/18 | 18/02/2022 | 0 | GOUTAM BHOWMIK | 4.38 | 0 | 0
5914 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-D) , Total House Hold -173 | Assistant Engineer | Junior Engineer | VCH/002429/2021-2022 | FHTC/18 | 18/02/2022 | 0 | GOUTAM GHOSH | 1.09 | 0 | 0
5915 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC pipe Line to Cover Vangahira mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | VCH/002430/2021-2022 | FHTC/18 | 18/02/2022 | 0 | TARINI CHARAN UPADHYAY | 4.19 | 0 | 0
5916 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC pipe Line to Cover Bagatapole mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002431/2021-2022 | FHTC/18 | 18/02/2022 | 0 | ASHIS PAL | 4.9 | 0 | 0
5917 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC pipe Line to Cover Vangahira mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002433/2021-2022 | FHTC/18 | 18/02/2022 | 0 | TAPAN KUMAR UPADHYAY | 4.88 | 0 | 0
5918 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172 | Assistant Engineer | Junior Engineer | VCH/002434/2021-2022 | FHTC/18 | 18/02/2022 | 0 | ASHOKE KUMAR DEY | 1.78 | 0 | 0
5919 | Bankura Division | Brishnupur Sub-Division | Estimate for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Murku (210) mouza by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002435/2021-2022 | FHTC/18 | 18/02/2022 | 0 | SWAPAN KUMAR UPADHYAY | 7.22 | 0 | 0
5920 | Bankura Division | Brishnupur Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 | Assistant Engineer | Junior Engineer | VCH/002437/2021-2022 | FHTC/18 | 18/02/2022 | 0 | RANABIR CHATTERJEE | 2.02 | 0 | 0
5921 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kolaberia (PART- A), Total House Hold -427 | Assistant Engineer | Junior Engineer | VCH/002438/2021-2022 | FHTC/18 | 18/02/2022 | 0 | UNIVERSAL CONSTRUCTION | 8.89 | 0 | 0
5922 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 | Assistant Engineer | Junior Engineer | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 0 | KHAN ENTERPRISE | 145.4 | 0 | 0
5923 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 04 nos, (Talandanga, Upar Narrah, Chhatarkanali, Rampur, ), Total House Hold - 530.' | Assistant Engineer | Junior Engineer | VCH/002779/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 5.53 | 0 | 0
5924 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002781/2021-2022 | FHTC/4 | 04/03/2022 | 0 | KOUSIK MONDAL | 2.65 | 0 | 0
5925 | Bankura Division | Brishnupur Sub-Division | Laying extra HDPE pipeline to cover Kulmura, Radhanagar & moukura mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Arjunpur Zone-N under Bankura - l - ll & Barjora block water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002783/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SUBHADIP KOLEY | 4.4 | 0 | 0
5926 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-B) , Total House Hold -130 ( Sl .No.- 02 ) | Assistant Engineer | Junior Engineer | VCH/002784/2021-2022 | FHTC/4 | 04/03/2022 | 0 | BIJOY KOLEY | 1.18 | 0 | 0
5927 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
5928 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2021-2022 | 2500/BQA | 23/09/2021 | 30 | APEX ENTERPRISE | 47.47 | 35.02 | 0
5929 | Bankura Division | Khatra Sub-Division | Laying of HDPE, GI & MS pipe line from rising main air valve near Fulberia to Damodar pur, Nirsha, Bansol, Dhwajmonipur & Kalapani mouza to increase pressure along with all allied works of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 2237/BQA | 09/12/2022 | 45 | PRADYUMNA KOLEY | 28.16 | 26.97 | 0
5930 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000603/2021-2022 | 802/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.27 | 0 | 0
5931 | Bankura Division | Khatra Sub-Division | Household survey in Gurighati (25) penrubaid & Parsola (28) mouzas under Pasola zone -A to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 16 | Assistant Engineer | Junior Engineer | VCH/000463/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.21 | 0 | 0
5932 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Ramdungri (35 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 02 | Assistant Engineer | Junior Engineer | VCH/002837/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.55 | 0 | 0
5933 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipe lineto cover Rudra (38 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002838/2021-2022 | FHTC/9 | 09/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.49 | 0 | 0
5934 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22 nos, (Bagmara, Katharia, Bijpur, Siulibona, Palla, Sigergara, Dumda, Alutia, Chholagasa, Satkhulia, Tilajuri, Aljhara, Dhengagora, Bankati, Jamtora, Meghakata, Dhagara, Nanduara, Aturibana, Chhopania, Karkari, Garbona), Total House Hold - 2721 nos. | Assistant Engineer | Junior Engineer | ORD/000249/2021-2022 | 3362/BQA | 31/12/2021 | 60 | M/S D.K.H CONSTRUCTION | 155.31 | 57.13 | 0
5935 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Palla, Karkari mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 340/KSD | 16/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 2.88 | 2.88 | 0
5936 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Meghakata, Chholagasa mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 336/KSD | 16/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.11 | 4.11 | 0
5937 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Siulibona, Alutia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2022-2023 | 338/KSD | 16/08/2022 | 20 | M/S D.K.H CONSTRUCTION | 4.32 | 4.32 | 0
5938 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22, Name of mouza:- Alutia [194], Chholagasa [192], Satkhulia [178], Tilajuri [173], Aljharia [182], Dhengagora [183), Bagmara [185], Katharia [174], Bijpur [188], Siulibona [189], Palla [195], Sigergara [175], Dumda [172], Bankati [181], Jamtora [180], Meghakata [187], Dhagara [186], Nanduara [184], Aturibana [179], Chhopania [177], Karkari [176] & Garbona [191], Total House Hold - 2721 nos. | Assistant Engineer | Junior Engineer | ORD/000555/2021-2022 | 70/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.91 | 0.83 | 0
5939 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Chakuparsole Zone - A & Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :-12 nos. i.e.Majuria-135, Dhabani-136, Chitrang-137, Indkuri-139, Majdiha-142, Hatiaghora-143, Chanchar-144, Amdohara-147, Choto Bankadaha-148, Bharamara-149, Dhandol-153, Pholbani-154, Total House Hold -65 | Assistant Engineer | Junior Engineer | VCH/001483/2022-2023 | FHTC/19 | 19/12/2022 | 0 | AJIT KUMAR DUTTA | 4.07 | 0 | 0
5940 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 03) | Assistant Engineer | Junior Engineer | VCH/001484/2022-2023 | FHTC/19 | 19/12/2022 | 0 | SUBHANKAR BANERJEE | 4.67 | 0 | 0
5941 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01 no., (Barachaka), Total House Hold- 60 nos. | Assistant Engineer | Junior Engineer | VCH/001485/2022-2023 | FHTC/19 | 19/12/2022 | 0 | BASUDEB ACHARJEE | 4.07 | 0 | 0
5942 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Kendana), Total House Hold - 272 nos | Assistant Engineer | Junior Engineer | VCH/001486/2022-2023 | FHTC/19 | 19/12/2022 | 0 | SK. SAHAJAHAN | 12.79 | 0 | 0
5943 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 07) | Assistant Engineer | Junior Engineer | VCH/001487/2022-2023 | FHTC/19 | 19/12/2022 | 0 | PRADYUMNA KOLEY | 2.23 | 0 | 0
5944 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001490/2022-2023 | FHTC/19 | 19/12/2022 | 0 | EARTH MOVING (INDIA) | 4.62 | 0 | 0
5945 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household - 2536 nos. | Assistant Engineer | Junior Engineer | VCH/001491/2022-2023 | FHTC/19 | 19/12/2022 | 0 | UNIVERSAL CONSTRUCTION | 21.12 | 0 | 0
5946 | Bankura Division | Bankura Sadar Sub-Division | Reconstruction concrete at Jolhari mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001501/2022-2023 | FHTC/27 | 27/12/2022 | 0 | TAPAS KUMBHAKAR | 4.31 | 0 | 0
5947 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22 nos, (Bagmara, Katharia, Bijpur, Siulibona, Palla, Sigergara, Dumda, Alutia, Chholagasa, Satkhulia, Tilajuri, Aljhara, Dhengagora, Bankati, Jamtora, Meghakata, Dhagara, Nanduara, Aturibana, Chhopania, Karkari, Garbona), Total House Hold - 2721 nos. | Assistant Engineer | Junior Engineer | VCH/003063/2021-2022 | FHTC/30 | 30/03/2022 | 0 | M/S D.K.H CONSTRUCTION | 98.17 | 0 | 0
5948 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction of valve chamber at Chintore, Budhanpur, Mahesana, Chinabari mouza of Boxibandh (Zone- I) of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone- I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 104/KSD | 28/04/2023 | 15 | ASHIS KUMAR SAMANTA | 0.98 | 0.98 | 80
5949 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Construction of valve Amakunda, Upardihi, Bhuinyapara mouza of Boxibandh (Zone- I) of retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone- I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 105/KSD | 28/04/2023 | 15 | ASHIS KUMAR SAMANTA | 0.84 | 0.84 | 80
5950 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe Line at Chaka Bridge to Chaka Santal Primari School due to damage by construction of PMGSY Road & Panchayet Road of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000200/2022-2023 | 692/BSD | 11/06/2022 | 15 | SIB SANKAR CHOWDHURY | 4.94 | 4.94 | 0
5951 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete at chaka Adibasi para to Primary School for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Baksibandh (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000203/2022-2023 | 347/KSD | 16/08/2022 | 20 | SIB SANKAR CHOWDHURY | 3.86 | 3.86 | 0
5952 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Baksibandh, No.of Mouza :- 17 nos, (Mahesana, Bhudhanpur, Bhuinyapara, Rahir, Chaka, Sanotalpara, Antkuria, Maheskhapur, Khaerboni, Chaintore, Panjangora, Bakshibandh, Khobradihi, Amlatora, Upordihi, Chinabari, Amakunda ), Total House Hold - 2274 nos. | Assistant Engineer | Junior Engineer | ORD/000251/2021-2022 | 3374/ BQA | 31/12/2021 | 60 | ASHISH KUMAR SAMANTA | 115.16 | 115.16 | 0
5953 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe Line from Chaka Adibasi Para to Samsanghat of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000626/2021-2022 | 693/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 3.94 | 3.93 | 0
5954 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Maheskhapri, Upardihi,Antkuria, Chinabari,Santalpara,Baxibandh mouza for retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000425/2022-2023 | 178/BQA | 30/01/2023 | 45 | ASHIS KUMAR SAMANTA | 12.05 | 12.05 | 0
5955 | Bankura Division | Bankura Sadar Sub-Division | Interconnection with R/M including Laying of HDPE Pipe Line from Kamalpur-Harigram road to Rahir to increase water pressure at Rahir, chaka mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-A ) | Assistant Engineer | Junior Engineer | ORD/000449/2022-2023 | 237/BQA | 08/02/2023 | 1148 | ASHIS KUMAR SAMANTA | 8.56 | 0 | 5
5956 | Bankura Division | Bankura Sadar Sub-Division | Interconnection with R/M including Laying of HDPE Pipe Line from Kamalpur-Harigram road to Rahir to increase water pressure at Rahir, chaka mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000459/2022-2023 | 238/BQA | 08/02/2023 | 45 | TARINI CHARAN UPADHYAY | 8.56 | 8.56 | 50
5957 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Baksibandh, No. of Mouza :- 17 nos., (Mahesana [206], BhuinyaPasa [207], Budhanpur [208], Rahir [242], Chaka [211], Sanotalpa [209], Antkuria [213], Maheskhuri [204], Khaerboni [212], Chaintore [205], Panjongora [210], Baksibandh [203], Khobradihi [216], Amlatore [215], Upordihi [214], Chinabari [202] & Amakunda [190] , Total House Hold - 2274 nos. | Assistant Engineer | Junior Engineer | ORD/000554/2021-2022 | 71/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.76 | 0.76 | 0
5958 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Khobradihi, Amlatora, Amakunda mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000595/2021-2022 | 271/BSD | 17/03/2022 | 10 | ASHIS KUMAR SAMANTA | 4.91 | 4.91 | 0
5959 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Chaintore, Khayerboni mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000597/2021-2022 | 267/BSD | 17/03/2022 | 10 | ASHIS KUMAR SAMANTA | 4.9 | 4.9 | 0
5960 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Mahesana, Bhuinyapara, mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000598/2021-2022 | 269/BSD | 17/03/2022 | 10 | ASHIS KUMAR SAMANTA | 4.51 | 4.5 | 0
5961 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE Pipe Line to Cover Chinabari, mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2021-2022 | 265/BSD | 17/03/2022 | 10 | ASHIS KUMAR SAMANTA | 4.91 | 4.91 | 0
5962 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe Line from Chaka ICDS Centre to Harimela due to damage by construction of PMGSY Road & Panchayet Road of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000624/2021-2022 | 690/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 4.95 | 4.92 | 0
5963 | Bankura Division | Bankura Sadar Sub-Division | Construction of S.S.P including laying of P.V.C extension pipe Line at Tegori Hari Mandir to Namapara & Golgora Bouripara of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000625/2021-2022 | 691/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 4.91 | 4.91 | 0
5964 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Amlatora more to Khobradihi to increase water pressure at Khoradihi of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora Chhatna W/S Scheme (BRGF ph-I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001099/2022-2023 | 182/BQA | 30/01/2023 | 45 | ASHIS KUMAR SAMANTA | 10.99 | 10.99 | 100
5965 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 3143 nos. | Assistant Engineer | Junior Engineer | ORD/000416/2021-2022 | 439/BQA | 03/03/2022 | 60 | SIB SANKAR CHOWDHURY | 163.22 | 163.18 | 100
5966 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000556/2021-2022 | 104/BSD | 28/01/2022 | 60 | TAPAS DEY | 1.05 | 0.59 | 0
5967 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2021-2022 | 451/BQA | 03/03/2022 | 0 | Resource Division | 17.29 | 0 | 0
5968 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/000254/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.46 | 0 | 0
5969 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2017 nos. | Assistant Engineer | Junior Engineer | ORD/000404/2021-2022 | 321/BQA | 22/02/2022 | 60 | GOUTAM BHATTACHRYYA | 107.67 | 97.86 | 0
5970 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2021-2022 | 105/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.67 | 0.58 | 0
5971 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2021-2022 | 576/BQA | 17/03/2022 | 0 | Resource Division | 12.42 | 0 | 0
5972 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Handulia (1) & Metyaldoba (2) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2022-2023 | 1299/BQA | 15/06/2022 | 10 | MAKALI CONSTRUCTION | 4.88 | 4.8 | 0
5973 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 8 Nos. Total Household:- 569 Nos. | Assistant Engineer | Junior Engineer | ORD/000412/2021-2022 | 411/BQA | 28/02/2022 | 30 | MAKALI CONSTRUCTION | 34.16 | 32.4 | 0
5974 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas under Parsola, Zone-B to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) | Assistant Engineer | Junior Engineer | ORD/000611/2021-2022 | 806/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.19 | 0 | 0
5975 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Barapara (202), Anara (203), Danrpara (204), Kargarli (205), Budha Kalsapa (234), Belban (235), Amchurya (236), Benakata (237), Patlurki (238), Demushunya (239), Kumarara (263), Nepura (264), Banskana (265), Kadamdiha (267), Chelepara (268) & Akhuapal (304) mouzas under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 16 Nos. Total Household:- 2435 Nos. | Assistant Engineer | Junior Engineer | ORD/000305/2021-2022 | 3352/BQA | 30/12/2021 | 1464 | SANJOY PATRA | 116.98 | 0 | 50
5976 | Bankura Division | Khatra Sub-Division | Work Order for Supplying, laying, fiting, fixing and jointing by HDPE pipe from Matgoda Pump House to Kargali village More at Kargali Mouza (damaged during construction of village road) under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000666/2021-2022 | 735/BQA | 28/03/2022 | 10 | SUBHANKAR BANERJEE | 4.97 | 4.94 | 0
5977 | Bankura Division | Khatra Sub-Division | Work Order for Supplying, laying, fiting, fixing and jointing by HDPE pipe to increase pressure for Kargarli (205) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)?under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000667/2021-2022 | 739/BQA | 28/03/2022 | 10 | SUBHANKAR BANERJEE | 4.98 | 4.97 | 0
5978 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Barapara (202), Anara (203), Danrpara (204), Kargarli (205), Budha Kalsapa (234), Belban (235), Amchurya (236), Benakata (237), Patlurki (238), Demushunya (239), Kumarara (263), Nepura (264), Banskana (265), Kadamdiha (267), Chelepara (268) & Akhuapal (304) mouzas under Dhemushunya (Zone-IV) to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000680/2021-2022 | 855/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.81 | 0.64 | 0
5979 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) | Assistant Engineer | Junior Engineer | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0
5980 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Barapara (202), Anara (203), Danrpara (204), Kargarli (205), Budha Kalsapa (234), Belban (235), Amchurya (236), Benakata (237), Patlurki (238), Demushunya (239), Kumarara (263), Nepura (264), Banskana (265), Kadamdiha (267), Chelepara (268) & Akhuapal (304) mouzas under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 16 Nos. Total Household:- 2435 Nos. | Assistant Engineer | Junior Engineer | VCH/003015/2021-2022 | FHTC/28 | 28/03/2022 | 0 | SANJOY PATRA | 75.85 | 0 | 0
5981 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Aguri Band Punisol piped water supply scheme in Onda Block of Bankura District under BRGF programme and providing Functional House Hold Tap Connection (FHTC) to each and every house hold within command area of Zone- C of the scheme. Name of Mouzas:- Chhagulia (3),Chandramonipur (4), Khapkata (5), Hirapur (6), Bhola (7), Jagannathpur (9), Dhandakeshabpur (56), Dubrakon (57), Nutangram (58), Saheb Ganja (59), Benajira (60), Panchami (61), Majura (62), Rampur (63), Hatbari (64), Tilabani (65), Ashnasol (66), Dhengakend (67), Baga Khulya Monoharpur (69), Gangadaspur (70), Basuara (71), Ekaria (72) & Kamala (73) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Nos. of House Hold= 3539 nos. | Assistant Engineer | Junior Engineer | ORD/000397/2021-2022 | 246\BQA | 09/02/2022 | 75 | MRITUNJOY MUKHERJEE & CO. | 217.11 | 211.91 | 100
5982 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Chhagulia (3), Chandramonipur (4), Khapkata (5), Hirapur (6), Bhola (7), Jagannathpur (9), Dhandakeshabpur (56), Dubrakon (57), Nutangram (58), Saheb Ganja (59), Benajira (60), Panchami (61), Majura (62), Rampur (63), Hatbari (64), Tilabani (65), Ashnasol (66), Dhengakend (67), Baga Khulya Monoharpur (69), Gangadaspur (70), Basuara (71), Ekaria (72) & Kamala (73) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by Augmentation Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000899/2021-2022 | 90/BSD | 28/01/2022 | 59 | TAPAS DEY | 1.18 | 1.11 | 0
5983 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2021-2022 | 452/BQA | 03/03/2022 | 0 | Resource Division | 19.44 | 0 | 0
5984 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 45 | UNICON INDIA | 317.75 | 0 | 100
5985 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 | Assistant Engineer | Junior Engineer | VCH/002683/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM BHOWMIK | 59.53 | 0 | 0
5986 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1, ,Gogra (Part) Total House Hold - 75 (Sl No of Work- 07) | Assistant Engineer | Junior Engineer | VCH/002684/2021-2022 | FHTC/2 | 02/03/2022 | 0 | ASHISH KUMAR SAMANTA | 4.71 | 0 | 0
5987 | Bankura Division | Brishnupur Sub-Division | Laying Extra UPVC Pipe Line to Cover Gogra for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Horaka (Zone- G) under Saltora Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002686/2021-2022 | FHTC/2 | 02/03/2022 | 0 | ASHISH KUMAR SAMANTA | 1.3 | 0 | 0
5988 | Bankura Division | Brishnupur Sub-Division | Laying of HDPE pipe line from Pingrui to Kuldiha incresse pressure for mouza Kuldiha of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 25 | Assistant Engineer | Junior Engineer | VCH/002687/2021-2022 | FHTC/2 | 02/03/2022 | 0 | ZAKIR HOSSAIN MONDAL | 4.23 | 0 | 0
5989 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , Jagannath pur (Part- D), Asansola (Part- A), Total House Hold -170 | Assistant Engineer | Junior Engineer | VCH/002689/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM GHOSH | 1.08 | 0 | 0
5990 | Bankura Division | Brishnupur Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-E) Total House Hold -102 | Assistant Engineer | Junior Engineer | VCH/002690/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM GHOSH | 2.6 | 0 | 0
5991 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Malkururia ,Sonagara ), Total House Hold -124 | Assistant Engineer | Junior Engineer | VCH/002691/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOURANGA CHATTERJEE | 0.95 | 0 | 0
5992 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Kururia Balarampur , (Lalbazar (PART-B), Total House Hold - 140 | Assistant Engineer | Junior Engineer | VCH/002693/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOURANGA CHATTERJEE | 0.94 | 0 | 0
5993 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 0 1 , Sangrampur (Part-A),Total House Hold - 124 (Sl .No.-8) | Assistant Engineer | Junior Engineer | VCH/002694/2021-2022 | FHTC/2 | 02/03/2022 | 0 | JAGADISH BANERJEE | 1.35 | 0 | 0
5994 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002696/2021-2022 | FHTC/2 | 02/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 31.26 | 0 | 0
5995 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
5996 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. | Assistant Engineer | Junior Engineer | VCH/003048/2021-2022 | FHTC/24 | 24/03/2022 | 0 | UNICON INDIA | 59.46 | 0 | 0
5997 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
5998 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
5999 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
6000 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6001 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Krishnanagar Purusottompur |  | Junior Engineer | BILL/00528/2022-2023 |  | 13/02/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6002 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6003 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
6004 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6005 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Nuniabaid Bagdiha | Assistant Engineer | Junior Engineer | BILL/00513/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6006 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6007 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 41 | 48
6008 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Jamardihi" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00069/2024-2025 | BP-38/2024-25 | 06/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
6009 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6010 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10904 | Assistant Engineer | Junior Engineer | BILL/00912/2024-2025 | BP/455/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
6011 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6012 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Jamardihi water supply scheme(SVS)under BMD PHE Dte.(SM/10904) | Assistant Engineer | Junior Engineer | BILL/01402/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
6013 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
6014 | Bankura Division | Khatra Sub-Division | New service connection charge at Dhudiya Doba |  | Junior Engineer | BILL/01410/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.93 | 0 | 0
6015 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6016 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Balarampur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00198/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
6017 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6018 | Bankura Division | Brishnupur Sub-Division | New Connection at Balarampur,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00492/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
6019 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6020 | Bankura Division | Brishnupur Sub-Division | New Service Connection for Mini Piped water supply Scheme at Hamirpur block-Patrasayer under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02576/2023-2024 | FHTC/03 | 12/03/2024 | 0 | PATRASAYER CCC | 0.43 | 0 | 0
6021 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 29 | 48
6022 | Bankura Division | Khatra Sub-Division | New connection at Jl No-95, Mouza-Kalapathar, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00283/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
6023 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6024 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6025 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40.6 | 48
6026 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-56, Mouza-Khejurbedia, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00281/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
6027 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6028 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6029 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.5 | 48
6030 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-50, Mouza-Manhara, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00284/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
6031 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6032 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6033 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 38.6 | 48
6034 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-54, Mouza-Jarka, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00291/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
6035 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6036 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6037 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28.6 | 48
6038 | Bankura Division | RWS Bankura Sub-Division | single phase connection of Barunia village under Manbazar CCC |  | Junior Engineer | BILL/00030/2024-2025 | FHTC/04 | 23/04/2024 | 0 | MANBAZAR CCC | 0.12 | 0 | 0
6039 | Bankura Division | RWS Bankura Sub-Division | New service connection for "Barunia" Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00076/2024-2025 |  | 29/04/2024 | 0 | MANBAZAR CCC | 0.12 | 0 | 0
6040 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6041 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6042 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
6043 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Barunia Village (SM/11030), (2) Mini Piped Water Supply Scheme for Kusum Khundi Village (SM/11114), (3) Mini Piped Water Supply Scheme for Pareshnath Village (SM/11032) and (4) Mini Piped Water Supply Scheme for Javi Village (SM/11121) |  | Junior Engineer | ORD/001992/2024-2025 | 192\KSD | 10/03/2025 | 10 | UNITED TRADERS | 0.6 | 0 | 90
6044 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6045 | Bankura Division | RWS Bankura Sub-Division | New Connection at Painada Modarpur, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00424/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6046 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6047 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 17.5 | 48
6048 | Bankura Division | RWS Bankura Sub-Division | New Service Connection at Rasiagara, Taldangra Block, PHE Dte. |  | Junior Engineer | BILL/00316/2023-2024 | FHTC/08 | 04/08/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6049 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6050 | Bankura Division | RWS Bankura Sub-Division | New Connection at Resiagara, Taldangra, Pin-722102 PHE Dte |  | Junior Engineer | BILL/00697/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6051 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6052 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 48
6053 | Bankura Division | RWS Bankura Sub-Division | New Connection at Baharagarya, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00707/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6054 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 14.5 | 48
6055 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Paresnath c/o sudip saha , Paresnath, Ranibandh |  | Junior Engineer | BILL/00050/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
6056 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6057 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6058 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
6059 | Bankura Division | RWS Bankura Sub-Division | New Connection at Mahadebsinan, Ranibandh |  | Junior Engineer | BILL/00326/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
6060 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6061 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6062 | Bankura Division | RWS Bankura Sub-Division | New Connection at Chechuriya, Taldangra,Pin-722102, PHE Dte. |  | Junior Engineer | BILL/00700/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6063 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6064 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 34 | 48
6065 | Bankura Division | RWS Bankura Sub-Division | New Connection at Puneshya, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00439/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6066 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6067 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6068 | Bankura Division | Bankura Sadar Sub-Division | Krishnanagar,Bankura-I,9330862734 | Assistant Engineer | Junior Engineer | BILL/00766/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
6069 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6070 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
6071 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6072 | Bankura Division | RWS Bankura Sub-Division | New Connection at Surbhagabandh, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00420/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6073 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6074 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
6075 | Bankura Division | RWS Bankura Sub-Division | New Connection at Chakjambedia, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00417/2023-2024 |  | 15/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6076 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6077 | Bankura Division | RWS Bankura Sub-Division | New service connection for Rurobaid Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00184/2024-2025 |  | 28/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
6078 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6079 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6080 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6081 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27 | 48
6082 | Bankura Division | RWS Bankura Sub-Division | New service connection for Kamalabaid Brahmandiha Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00118/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
6083 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6084 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6085 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32.5 | 48
6086 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 |  | Junior Engineer | ORD/000210/2020-2021 | 2031/BQA | 29/12/2020 | 30 | RANABIR CHATTERJEE | 41.02 | 0 | 0
6087 | Bankura Division | Bankura Sadar Sub-Division | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :10 (Basuda, Rajprasadpur(Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar ), Total House Hold -473 |  | Junior Engineer | ORD/000213/2020-2021 | 2032/BQA | 29/12/2020 | 30 | AMIYO KUMAR BIT | 41.04 | 59.4 | 0
6088 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza :- 10 nos, (Basuda, Rajprasadpur (Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar) |  | Junior Engineer | ORD/000278/2021-2022 | 940/ BSD | 04/10/2021 | 15 | AMIYA KUMAR BIT | 4.41 | 0 | 0
6089 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KOTALPUKUR (Zone - B)) . Name.of Mouza :- 01 no., Rajprasadpur (Part) |  | Junior Engineer | VCH/001333/2021-2022 |  | 28/09/2021 | 0 | RANABIR CHATTERJEE | 4.78 | 0 | 0
6090 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 |  | Junior Engineer | VCH/001487/2021-2022 | FHTC/03 | 03/11/2021 | 0 | BEAUTY CHATTERJEE | 7.46 | 0 | 0
6091 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) Mouza Jiabandi, |  | Junior Engineer | VCH/001762/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.58 | 0 | 0
6092 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) Mouza - Amdahara, |  | Junior Engineer | VCH/001763/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 4.73 | 0 | 0
6093 | Bankura Division | Bankura Sadar Sub-Division | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 0 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0
6094 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipeline at Sangrampur to purnia village of retrofitting works for ceration of FHTC in connection with jal jeevan mission and jal swapna of Talanjuri ( Zone-F) under Bankura I,II Barjora block W/S scheme ( BRGF Ph -I ) under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. ( SL.No-14), |  | Junior Engineer | VCH/001764/2021-2022 | FHTC/29 | 29/10/2021 | 0 | SUBHANKAR BANERJEE | 4.76 | 0 | 0
6095 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Jaganathpur (110) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  | Junior Engineer | VCH/001765/2021-2022 | FHTC/29 | 29/10/2021 | 0 | APEX ENTERPRISE | 4.89 | 0 | 0
6096 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipeline of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division under Bankura Division, PHE Dte. block - Barjora , name of OHR - Joykrisnapur (zone - l) name of mouza Oltara part - B sl no - 23 |  | Junior Engineer | VCH/001766/2021-2022 | FHTC/29 | 29/10/2021 | 0 | GANGADHAR MONDAL | 4.52 | 0 | 0
6097 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172, |  | Junior Engineer | VCH/001767/2021-2022 | FHTC/29 | 29/10/2021 | 0 | ASHOKE KUMAR DEY | 13.01 | 0 | 0
6098 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipeline FROM Barjora heawork site near Kadasole to Barjora forest office of Barjora water supply scheme left out mouzas of Barjora block under BRGF PH - I within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. zone - ll Sl no - 01 |  | Junior Engineer | VCH/001854/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ZAKIR HOSSAIN MONDAL | 3.88 | 0 | 0
6099 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
6100 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Jirabad" Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00071/2024-2025 | BP-38/2024-25 | 06/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
6101 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6102 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10896 | Assistant Engineer | Junior Engineer | BILL/00913/2024-2025 |  | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
6103 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6104 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Jirabad water supply scheme(SVS) under BMD PHE Dte.(SM/10896) | Assistant Engineer | Junior Engineer | BILL/01401/2024-2025 |  | 13/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
6105 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45.91 | 48
6106 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6107 | Bankura Division | RWS Bankura Sub-Division | Supurdihi, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00768/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
6108 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6109 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 34.6 | 48
6110 | Bankura Division | RWS Bankura Sub-Division | New service connection for Radhanagar Dubrajpur Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00120/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
6111 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6112 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi,Radhanagar Nabadeulvira |  | Junior Engineer | BILL/01072/2023-2024 | FHTC/04 | 04/04/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
6113 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6114 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 28 | 48
6115 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - srirampur, Lowgram, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00270/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
6116 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6117 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6118 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Srirampur | Assistant Engineer | Junior Engineer | BILL/01260/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
6119 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
6120 | Bankura Division | Bankura Sadar Sub-Division | New connection at vill-kasakend (Dahardihi) p.o-Jhilimili (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02600/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
6121 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 47 | 48
6122 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Radhanagar, Gopinathpur, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00282/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
6123 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6124 | Bankura Division | Brishnupur Sub-Division | Quatation bill of Ramchandrapur,Gopinathpur,Kotulpur | Assistant Engineer | Junior Engineer | BILL/00671/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
6125 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6126 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Ramchandrapur | Assistant Engineer | Junior Engineer | BILL/01254/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
6127 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
6128 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 560 | Assistant Engineer | Junior Engineer | ORD/000004/2020-2021 | 605/BQA | 10/02/2021 | 30 | SIB SANKAR CHOWDHURY | 40.78 | 0 | 0
6129 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43, Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 130 | Assistant Engineer | Junior Engineer | ORD/000021/2020-2021 | 617/BQA | 10/02/2021 | 30 | I.R.CONSTRUCTION | 9.86 | 0 | 0
6130 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2020-2021 | 199/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 38.78 | 25.58 | 0
6131 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (PART-A) Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name:-Debghoria para,Biswas para, Bhattacharyay para and Chatterjee para., Total House Hold - 66 | Assistant Engineer | Junior Engineer | ORD/000095/2020-2021 | 163/VSD | 18/09/2020 | 21 | I.R.CONSTRUCTION | 4.84 | 0 | 0
6132 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (PART_A) Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name:-Chatterjee para,Jharmunia para and Biswas Pukur, Total House Hold - 67 | Assistant Engineer | Junior Engineer | ORD/000097/2020-2021 | 164/VSD | 18/09/2020 | 21 | SIB SANKAR CHOWDHURY | 4.82 | 0 | 0
6133 | Bankura Division | Brishnupur Sub-Division | Connection of bhagabunh village from existing pipe line under Bankura - I - II & Barjora block water supply (BRGF ph - I project) Chaturdihi ( OHR) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. M.B. No.3770 | Assistant Engineer | Junior Engineer | VCH/000469/2021-2022 | FHTC/03 | 03/11/2021 | 0 | ZAKIR HOSSAIN MONDAL | 3.17 | 0 | 0
6134 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 68. | Assistant Engineer | Junior Engineer | ORD/000144/2020-2021 | 23/VSD | 20/01/2021 | 30 | SIB SANKAR CHOWDHURY | 4.84 | 0 | 0
6135 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 73. | Assistant Engineer | Junior Engineer | ORD/000149/2020-2021 | 57/VSD | 10/02/2021 | 21 | M/S BANERJEE & BANERJEE | 4.8 | 0 | 0
6136 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 0 | SANJOY MONDAL | 4.55 | 0 | 0
6137 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
6138 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayaerpara (206), Harinarayanpur (207) & Gangnala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. , | Assistant Engineer | Junior Engineer | VCH/001859/2021-2022 | FHTC/03 | 03/11/2021 | 0 | MUNMUN UPADHYAY | 15 | 0 | 0
6139 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora - Chhatna water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Chhatna ,Name of OHR - Dhaban . Total House Hold -67 nos M.B. No. 5098 | Assistant Engineer | Junior Engineer | VCH/001860/2021-2022 | FHTC/03 | 03/11/2021 | 0 | SRIKANTA MONDAL | 3.06 | 0 | 0
6140 | Bankura Division | Brishnupur Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayaerpara (206), Harinarayanpur (207) & Gangnala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002298/2021-2022 | FHTC/31 | 31/01/2022 | 0 | MUNMUN UPADHYAY | 20.34 | 0 | 0
6141 | Bankura Division | Brishnupur Sub-Division | laying extra UPVC pipe line to cover kherosal mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATERKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002301/2021-2022 | FHTC/04 | 04/01/2022 | 0 | BHATTACHARYYA ENTERPRISE | 4.82 | 0 | 0
6142 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 ,Baharkhulia(part-B), Total House Hold - 124 ( Sl .No.- 11 ) | Assistant Engineer | Junior Engineer | VCH/002302/2021-2022 | FHTC/04 | 04/01/2022 | 0 | SAIKAT CHOWDHURY | 1.27 | 0 | 0
6143 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) | Assistant Engineer | Junior Engineer | VCH/002310/2021-2022 | FHTC/20 | 20/01/2022 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 16.51 | 0 | 0
6144 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 36. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Tentulara-20 (53 out of 106), House Hold - 53 (Sl. No. 02) | Assistant Engineer | Junior Engineer | VCH/002317/2021-2022 | FHTC/20 | 20/01/2022 | 0 | MANORANJAN GHOSH | 4.14 | 0 | 0
6145 | Bankura Division | Khatra Sub-Division | 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 2 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 2031/BQA | 24/07/2023 | 709 | PRINCE INDUTRIES (INDIA) | 182.82 | 80.96 | 81
6146 | Bankura Division | Khatra Sub-Division | Supplying, laying, fiting, fixing and jointing by DI (K9) for Rising Main & HDPE pipe for Distribution Main along with ancillary works due to damage done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2021-2022 | 162/BQA | 28/01/2022 | 30 | EARTH MOVING (INDIA) | 88.36 | 73.87 | 0
6147 | Bankura Division | Khatra Sub-Division | Laying extra HDPE pipeline,construction of different dia valve chambers & other allied works to increase pressure for Majuria (372), Makarkol (365), Jhukanala (366), Baispatra (367) & Deuli (369) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000664/2022-2023 | 508/BQA | 13/03/2023 | 45 | UTTAM KUMAR SINHAMAHAPATRA | 2.48 | 2.32 | 60
6148 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6149 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Shibarampur Keliapathar | Assistant Engineer | Junior Engineer | BILL/01125/2022-2023 | Elec04 | 11/04/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6150 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6151 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 23 | 48
6152 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6153 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Banagram, Hatagram | Assistant Engineer | Junior Engineer | BILL/00509/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6154 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6155 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
6156 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Brindabanpur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00186/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
6157 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6158 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6159 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 41 | 48
6160 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR RADHASHYAMPUR VILLAGE (Dahala Namopara) HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00114/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | KHATRA CCC | 0.12 | 0 | 0
6161 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6162 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6163 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
6164 | Bankura Division | Brishnupur Sub-Division | Patrasayer Market Road from 0.00 kmp to 2.50 kmp. restoration work of both side of road due to laying of pipeline by Bankura Division. PHE Dte. Ref: EE/Bankura Highway Division P.W(Roads) Dte. Office Memo No- 1330 Dated 07.1 1.2023. | Assistant Engineer | Junior Engineer | BILL/00945/2024-2025 | BP-316/2024-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 43.98 | 0 | 0
6165 | Bankura Division | Brishnupur Sub-Division | Bishbupur Patrasayer market road from 22.00 kmp 28.00 kmp restoration work of both side of road due to laying of pipeline by Bankura Division PHE Dte. under Bankura Highway Division in the district of Bankura | Assistant Engineer | Junior Engineer | BILL/02260/2023-2024 | FHTC/12 | 13/12/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 18.25 | 0 | 0
6166 | Bankura Division | Brishnupur Sub-Division | Construction & Commissioning of 400 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. of Drg.no.-PC-I/OHR/11/2012(Rev-01){Sheet-1/2 &2/2} of SE,PC-I,PHE Dte.) staging height 20 mtr. with Laying Distribution System as per LDS drawing, including FHTC works for Augmentation of Patrasayer piped water supply scheme at Patrasayer Block of Bishnupur Sub - Division under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 899/BQA | 20/04/2023 | 926 | DEBAKI RANJAN SARKAR | 345 | 291.77 | 96
6167 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.50 m x 4.5 m) for augmentation of Patrasayer Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 68/BQA | 05/01/2023 | 540 | BIDHAN BANERJEE | 6.54 | 4.73 | 85
6168 | Bankura Division | Brishnupur Sub-Division | Repairing of one no. pump house for augmentation of Patrasayer water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 69/BQA | 05/01/2023 | 45 | MOHAN KUMAR ROY | 2.07 | 1.3 | 95
6169 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 203 mtr long for augmentation of Patrasayer water supply scheme (pump house no 1) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000391/2022-2023 | 70/BQA | 05/01/2023 | 775 | MOHAN KUMAR ROY | 14.28 | 5.6 | 100
6170 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 19 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN PATRASAYER BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000415/2022-2023 | 353/BQA | 21/02/2023 | 30 | GLORY ENGINEERS SYNDICATE | 15.38 | 15.38 | 70
6171 | Bankura Division | Brishnupur Sub-Division | "Construction of boundary wall approx 126 mtr long for augmentation of Patrasayer water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008991) (SM/09926) (AAFS- PH212246951M000)" | Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 523/BQA | 14/03/2023 | 30 | MUNMUN UPADHYAY | 7.24 | 7.23 | 89
6172 | Bankura Division | Brishnupur Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Patrasayer W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) (Sl. No. 01) OHR Capacity- 400 m3 | Assistant Engineer | Junior Engineer | ORD/000652/2022-2023 | 144//VSD | 18/05/2022 | 15 | G.MITRA AND ASSOCIATES | 1.4 | 1.4 | 0
6173 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000147/2023-2024 | 3345/BQA | 06/12/2023 | 0 | Resource Division | 38.12 | 0 | 0
6174 | Bankura Division | Brishnupur Sub-Division | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Patrasayer to accommodate FHTC under Jal Sapno Mission under Patrasayer Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 2) [Estimated Cost Rs. Quotated Rate] | Assistant Engineer | Junior Engineer | ORD/000652/2021-2022 | 424/B/VSD | 23/09/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.59 | 2.59 | 0
6175 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/00126/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6176 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of installation of Pumping machineries with other electro-mechanical accessories for ground base piped water supply scheme for Patrasayar to commanded FSTC under Jal Swapna mission under Patarasyar Block in Bankura District under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 1014/BMD | 22/05/2023 | 1080 | INDRAJIT MITRA | 19.94 | 10.79 | 54
6177 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi,Tarkajor Bhatra | Assistant Engineer | Junior Engineer | BILL/01026/2023-2024 |  | 11/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6178 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6179 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6180 | Bankura Division | RWS Bankura Sub-Division | New Service connection at Mini Piped w/s scheme at village- Chhelebad Po-Baga under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00819/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
6181 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6182 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
6183 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Mahishabandi site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00189/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
6184 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6185 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6186 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
6187 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6188 | Bankura Division | Brishnupur Sub-Division | Sundarpur sihar, Kotulpur | Assistant Engineer | Junior Engineer | BILL/00677/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
6189 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6190 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.6 | 48
6191 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6192 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6193 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
6194 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Baramara village | Assistant Engineer | Junior Engineer | BILL/00045/2024-2025 | FHTC/04 | 29/04/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
6195 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Narayanpur site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00174/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
6196 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6197 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6198 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
6199 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for chak chuamosina | Assistant Engineer | Junior Engineer | BILL/00049/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | BISHNUPUR CCC | 0.13 | 0 | 0
6200 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6201 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6202 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
6203 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 13 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002199/2024-2025 | 579\VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 1.96 | 0 | 0
6204 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6205 | Bankura Division | Brishnupur Sub-Division | New Connection at Kharajbani,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00495/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
6206 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6207 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18.42 | 48
6208 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 13 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002204/2024-2025 | 581\A\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 1.96 | 0 | 0
6209 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line inter connection BANKATI Main Road to Radharamanpur Village main pipe line to increase pressure in Radharamanpur mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (ZONE-R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000285/2023-2024 | 531/BSD | 12/06/2023 | 7 | SOUMITRA KUMAR DAS | 0.28 | 0.15 | 100
6210 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000347/2020-2021 | 1772/BQA | 09/12/2020 | 30 | M/S TARUN KUMAR PATRA | 23.94 | 0.06 | 20
6211 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos (Kulpat Bonkati, Gourangadihi, Kesia & Ladadih (Part ). Total House Hold - 396" |  | Junior Engineer | ORD/000385/2020-2021 | 1785/BQA | 09/12/2020 | 30 | BISWARUP BOSE | 28.65 | 0 | 100
6212 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos (Bonkati (Part ). Total House Hold - 132" |  | Junior Engineer | ORD/000386/2020-2021 | 1786/BQA | 09/12/2020 | 30 | PRANABANANDA TEWARI | 10.53 | 0 | 100
6213 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos (Bonkati (Part ) & Beldanga (Part). Total House Hold - 132" |  | Junior Engineer | ORD/000387/2020-2021 | 1787/BQA | 09/12/2020 | 30 | SHYAMAL KUMAR DAS | 10.26 | 0 | 100
6214 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Hetiasole mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001917/2020-2021 | FHTC/294 | 01/03/2021 | 0 | D. S. ENTERPRISE | 4.8 | 0 | 0
6215 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Bangaria & Hirakon mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001918/2020-2021 | FHTC/294 | 01/03/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 4.31 | 0 | 0
6216 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Bangaria & Hirakon mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001919/2020-2021 | FHTC/294 | 01/03/2021 | 0 | UTTAM KUMAR SINHAMAHAPATRA | 3.76 | 0 | 0
6217 | Bankura Division | Bankura Sadar Sub-Division | " Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos Beldanga (Part). Total House Hold - 130 " |  | Junior Engineer | ORD/000388/2020-2021 | 1788/BQA | 09/12/2020 | 30 | SHYAMAL KUMAR DAS | 10.16 | 0 | 100
6218 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03, Gouripur,Bonkati( part) & Ladadih (part ). Total House Hold - 396 |  | Junior Engineer | ORD/000400/2020-2021 | 1784/BQA | 09/12/2020 | 30 | SOUMITRA BOSE | 28.74 | 0 | 100
6219 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Kulpat bankati, Gourandihi, Kesia, Ladadihi, Ramdihi, Choto kalajharia, Radharamanpur, Baro kalajuria mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000431/2020-2021 | 138/ BSD | 18/02/2021 | 10 | PRANABANANDA TEWARI | 3.1 | 0 | 0
6220 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover gouripur,bonkati,ladadihi mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000433/2020-2021 | 140/ BSD | 18/02/2021 | 10 | BISWARUP BOSE | 4.73 | 0 | 0
6221 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Bonkati, Beldanga, Gajabari mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000435/2020-2021 | 142/ BSD | 18/02/2021 | 10 | SHYAMAL KUMAR DAS | 4.42 | 0 | 0
6222 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03 nos, (Gajariabari, Maslia, Chaitali), Total House Hold - 167." |  | Junior Engineer | VCH/001405/2020-2021 |  | 01/03/2021 | 0 | SHYAMAL KUMAR DAS | 8.86 | 0 | 0
6223 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos, (Roybandh), Total House Hold - 168." |  | Junior Engineer | VCH/001406/2020-2021 |  | 01/03/2021 | 0 | PRANABANANDA TEWARI | 9.09 | 0 | 0
6224 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , Total House Hold - 1186." |  | Junior Engineer | VCH/001408/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
6225 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - I, Name of OHR - Bankati no .of Mouza :- 07 etc , Total House Hold -1186" |  | Junior Engineer | VCH/001412/2020-2021 |  | 01/03/2021 | 0 | TAPAS DEY | 0.38 | 0 | 0
6226 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos, (Duyaranda, Kelebela), Total House Hold - 422. ( MB No - 3996)" |  | Junior Engineer | VCH/001428/2020-2021 |  | 01/03/2021 | 0 | SOUMITRA BOSE | 23.2 | 0 | 0
6227 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 nos (Mobarakpur, Agra, Adra & Sirsara) Total House Hold - 605 . ( MB No - 4005)" |  | Junior Engineer | VCH/001563/2020-2021 | FHTC/283 | 22/02/2021 | 0 | GOPAL CHANDRA CHOUDHURY | 23.41 | 0 | 0
6228 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTH MOVING (INDIA) | 31.31 | 0 | 0
6229 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Shyamnagar & Aral Chhota (Naria) mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001923/2020-2021 | FHTC/294 | 01/03/2021 | 0 | SUNIL KUMAR MANDAL | 4.57 | 0 | 0
6230 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001991/2020-2021 | FHTC/301 | 15/03/2021 | 0 | TAPAS DEY | 0.28 | 0 | 0
6231 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 01 no, (Hatjore) Total House Hold - 149 |  | Junior Engineer | VCH/002285/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOUTAM GHOSH | 10.74 | 0 | 0
6232 | Bankura Division | Brishnupur Sub-Division | The maintenance and repair estimate prepared in respect of the road namely LO57-Palsora to MDR having Package No -WB-03-659 under Sonamukhi block, in the District of Bankura under PMGSY ,WBSRDA , Bishnupur Division. Road Name : L057-Palsora to MDR | Assistant Engineer | Junior Engineer | BILL/00474/2025-2026 |  | 20/06/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.46 | 0 | 0
6233 | Bankura Division | Brishnupur Sub-Division | Quotation for shifting of 11 kv HTOH for construction of PHE building at Teluri near Nabasan girls high school sonamukhi | Assistant Engineer | Junior Engineer | BILL/02160/2023-2024 | FHTC/11 | 27/11/2023 | 0 | DE & DIVISIONAL MANAGER BISHNUPUR D DIVISION WBSEDCL | 2.97 | 0 | 0
6234 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 169.22 | 55
6235 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 94.16 | 0 | 0
6236 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for TELRUI TW-1 (JL NO-132, PLOT-506LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00015/2024-2025 | BP-2024-25-36 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.43 | 0 | 0
6237 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Telrui Tw-2 Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00955/2024-2025 | BP-2024-25-235 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.45 | 0 | 0
6238 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Telrui Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 451/BMD | 10/06/2025 | 90 | UNITED TRADERS | 11.69 | 0 | 0
6239 | Bankura Division | Brishnupur Sub-Division | New Connection at Chokdhobakure, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00292/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
6240 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6241 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6242 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
6243 | Bankura Division | Brishnupur Sub-Division | New Connection at Amghata, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00294/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
6244 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6245 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6246 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 54 | 48
6247 | Bankura Division | Brishnupur Sub-Division | New Connection at Indkata, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00293/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
6248 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6249 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6250 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
6251 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6252 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6253 | Bankura Division | Brishnupur Sub-Division | New service connection at Uttar Bazar, Amritpara (Bud Bud) Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02609/2023-2024 | FHTC/03 | 12/03/2024 | 0 | BUDBUD CCC | 0.14 | 0 | 0
6254 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 15 | 48
6255 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 14 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002203/2024-2025 | 581\VSD | 27/09/2024 | 30 | GORAI CONSTRUCTION | 2.11 | 0 | 0
6256 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR SALKHARA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000434/2023-2024 | 2268/BQA | 01/08/2023 | 669 | PARAMESWAR CHOWDHURY | 285.23 | 58.47 | 36
6257 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000054/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 19.11 | 0 | 0
6258 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Shalkhara piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 656/BMD | 17/04/2023 | 180 | P.K. ENGINEERING | 31.31 | 15.39 | 49
6259 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 8.16 | 0 | 0
6260 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 25.37 | 0 | 0
6261 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chandalbandi T/W-II watwer supply scheme (SM/13999) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01207/2024-2025 | BP-2024-25-291 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.5 | 0 | 0
6262 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chandalbandi w/s scheme(T/W-I) at Patrasayer block under PHE Dte.(SM/13999) | Assistant Engineer | Junior Engineer | BILL/01231/2024-2025 | BP-2024-25-307 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 30.25 | 0 | 0
6263 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Chandal Bandi piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Patrashayar, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 872/BMD | 04/05/2023 | 1080 | GOENKA ENTERPRISE | 35.78 | 16.49 | 46
6264 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6265 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6266 | Bankura Division | Bankura Sadar Sub-Division | New Service connection at Murra | Assistant Engineer | Junior Engineer | BILL/01573/2024-2025 | BP/454/2024-25 | 21/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.04 | 0 | 0
6267 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.6 | 48
6268 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Pechara JIbandihi Moshiara Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00152/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
6269 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Pechara JIbandihi Moshiara Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00172/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
6270 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6271 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-29, Mouza-Kalyansaer, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00277/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
6272 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6273 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6274 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
6275 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Kalapathar Village (SM/11013), (2) Mini Piped Water Supply Scheme for Kalyansera Village (SM/13269), (3) Mini Piped Water Supply Scheme for Kalasol Village (SM/11022), (4) Mini Piped Water Supply Scheme for Kuchaipal Village (SM/11023) and (5) Mini Piped Water Supply Scheme for Rautkhana Village (SM/13271) |  | Junior Engineer | ORD/001995/2024-2025 | 195\KSD | 10/03/2025 | 10 | M/S ASHOK KUMAR DEY | 0.75 | 0 | 90
6276 | Bankura Division | Khatra Sub-Division | supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied works for Mukutmanipur, Khatra & Ranibundh (Zone- II/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000084/2023-2024 | 1061/BQA | 03/05/2023 | 975 | APEX ENTERPRISE | 196.92 | 51.61 | 31
6277 | Bankura Division | Khatra Sub-Division | Work order for Crossing of Road near Kharidungri Stadium by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- II/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2024-2025 | 1836/BQA | 12/07/2024 | 493 | SWAPAN KUMAR CHANDRA | 7.22 | 0 | 0
6278 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
6279 | Bankura Division | Khatra Sub-Division | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- II/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000540/2022-2023 | 438/BQA | 06/03/2023 | 1033 | S. B. CONSTRUCTION | 8.66 | 0 | 0
6280 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-2B) (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000626/2022-2023 | 182/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.09 | 2.89 | 0
6281 | Bankura Division | Khatra Sub-Division | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- II/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2022-2023 | 439/BQA | 06/03/2023 | 90 | BIJOY KOLEY | 4.63 | 0 | 0
6282 | Bankura Division | Khatra Sub-Division | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- II/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001297/2023-2024 | 819/BQA | 11/03/2024 | 45 | BIJOY KOLEY | 19.49 | 0 | 0
6283 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 2.07 | 0 | 0
6284 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000202/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.18 | 0 | 0
6285 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-2B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000236/2023-2024 | 1122/BMD | 24/05/2023 | 30 | UNICON | 2.38 | 0 | 0
6286 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 193.27 | 55
6287 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000025/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 28.09 | 0 | 0
6288 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000303/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 7.99 | 0 | 0
6289 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Mukundapur Water supply scheme (SM/14006) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01244/2024-2025 | BP-2024-25-316 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.2 | 0 | 0
6290 | Bankura Mechanical | Brishnupur Sub-Division | MUKUNDAPUR WATER SUPPLY SCHEME | Assistant Engineer | Junior Engineer | BILL/01669/2023-2024 | BP-2023-24-185 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.76 | 0 | 0
6291 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 172.22 | 6
6292 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
6293 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 9.41 | 0 | 0
6294 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000068/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 137.45 | 0 | 0
6295 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Nabasan Piped Water Supply Scheme t/w-I ,Nabasan, Salda of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00133/2024-2025 | BP-2024-25-33 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.63 | 0 | 0
6296 | Bankura Mechanical | Brishnupur Sub-Division | Nabasan Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01500/2023-2024 | BP-2023-24-102 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
6297 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nabasan Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000187/2025-2026 | 459/BMD | 10/06/2025 | 90 | M/S BIPUL BANERJEE | 11.85 | 0 | 0
6298 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 196.62 | 55
6299 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 101.28 | 0 | 0
6300 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 23.34 | 0 | 0
6301 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for RANPUR( JL NO-141,PLOT NO-676LR)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00019/2024-2025 | BP-2024-25-25 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.2 | 0 | 0
6302 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Ranpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14519) | Assistant Engineer | Junior Engineer | BILL/01182/2024-2025 | BP-2024-25-304 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.4 | 0 | 0
6303 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Ranpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14519) | Assistant Engineer | Junior Engineer | BILL/01183/2024-2025 | BP-2024-25-305 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0
6304 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Ranpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000155/2025-2026 | 450/BMD | 10/06/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 13.1 | 0 | 0
6305 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DANGA MAKARANDAPUR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2023-2024 | 2042/BOQ | 24/07/2023 | 982 | M/S TARUN KUMAR PATRA | 808.13 | 475.53 | 85
6306 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
6307 | Bankura Division | Brishnupur Sub-Division | Additional work of Road Crossing for Jack Pussing of Danga Makarandapur Water Supply Scheme under Joypur Block under Bishnupur Sub vision of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000873/2023-2024 | 3004/BQA | 03/11/2023 | 880 | M/S TARUN KUMAR PATRA | 34.85 | 0 | 100
6308 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Danga Makarandapur Piped Water Supply Scheme (SM/14523) & 2 nos. sites of Harinashuli Piped Water Supply Scheme (SM/12422) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001868/2024-2025 | 551/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.75 | 0 | 0
6309 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2024-2025 | 1637/BQA | 28/06/2024 | 0 | Resource Division | 15.8 | 0 | 0
6310 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000084/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 119.65 | 0 | 0
6311 | Bankura Mechanical | Brishnupur Sub-Division | Dangamakrandapur T/W-I | Assistant Engineer | Junior Engineer | BILL/00851/2023-2024 | BP-2023-24-44 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0
6312 | Bankura Mechanical | Brishnupur Sub-Division | Dangamakrandapur T/W-II | Assistant Engineer | Junior Engineer | BILL/00852/2023-2024 | BP-2023-24-45 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0
6313 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danga Makarandapur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 1706/BMD | 28/07/2023 | 1018 | P.K. ENGINEERING | 59.05 | 27.6 | 20
6314 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BAGDOBA & KHUNDANGA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 2332/BQA | 14/08/2023 | 540 | GOPAL CHANDRA CHOWDHURY | 1262.72 | 177.44 | 80
6315 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000090/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 29.17 | 0 | 0
6316 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at T/W-I of Khundanga W/S Scheme. | Assistant Engineer | Junior Engineer | BILL/01345/2024-2025 | BP-2024-25-346 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0
6317 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Khundanga W/S Scheme | Assistant Engineer | Junior Engineer | BILL/01351/2024-2025 | BP-2024-25-347 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.86 | 0 | 0
6318 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Khundanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 873/BMD | 04/05/2023 | 180 | M/S SWAPAN BANERJEE | 35.82 | 21.78 | 61
6319 | Bankura Division | RWS Bankura Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (307), Shubnabandi (308), Krishna Nagar (309), Narayanpur (310), Barkala (320), Dharampur (321), Sirsa (322), Maulasol (323), Lurka (324), Gochda (325) & Lagda (326) mouzas under Lurka (Zone-VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000111/2023-2024 | 1193/BQA | 22/05/2023 | 90 | SIB SANKAR CHOWDHURY | 280.1 | 133.82 | 65
6320 | Bankura Division | RWS Bankura Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Lurka Zone-B of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/001084/2021-2022 | 22\KSD | 10/02/2022 | 30 | SUNIL KUMAR MANDAL | 3.69 | 3.48 | 95
6321 | Bankura Division | RWS Bankura Sub-Division | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post under Lurka Zone-B of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) | Assistant Engineer | Junior Engineer | ORD/001086/2021-2022 | 23\KSD | 10/02/2022 | 30 | ANATH DANDAPAT | 2.78 | 2.52 | 95
6322 | Bankura Division | RWS Bankura Sub-Division | Laying HDPE pipeline with allied works for construction and commissioning of FHTC (Functional House Hold Tap Connection) under Lurka (Zone-VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001129/2023-2024 | 248/BQA | 25/01/2024 | 781 | TAPAN KUMAR MANDAL | 34.52 | 22.46 | 50
6323 | Bankura Division | RWS Bankura Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000054/2023-2024 | 2412/BQA | 18/08/2023 | 0 | Resource Division | 23.21 | 0 | 0
6324 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. | Assistant Engineer | Junior Engineer | ORD/000320/2021-2022 | 3371/BQA | 31/12/2021 | 30 | PRADIP CHAKRABORTY | 20.33 | 6.5 | 100
6325 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Ola (109) & Suklai (191) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000885/2021-2022 | 98/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.14 | 0.06 | 0
6326 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2021-2022 | 580/BQA | 17/03/2022 | 0 | Resource Division | 2.67 | 0 | 0
6327 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. | Assistant Engineer | Junior Engineer | VCH/000234/2022-2023 | FHTC/11 | 11/04/2022 | 0 | PRADIP CHAKRABORTY | 6.56 | 0 | 0
6328 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. | Assistant Engineer | Junior Engineer | VCH/002886/2021-2022 |  | 16/03/2022 | 0 | PRADIP CHAKRABORTY | 6.56 | 0 | 0
6329 | Bankura Division | Brishnupur Sub-Division | Basudevpur Loharpara to Khiraiboni Balram Temple (Pathashree Road ) Kataban PWSS Scheme | Assistant Engineer | Junior Engineer | BILL/00472/2025-2026 |  | 20/06/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 9.06 | 0 | 0
6330 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 321.97 | 6
6331 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
6332 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000049/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 47.47 | 0 | 0
6333 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000300/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 13.76 | 0 | 0
6334 | Bankura Mechanical | Brishnupur Sub-Division | Additional work for New service connection at Kantaban t/w-I of Kantaban Piped Water Supply Scheme of joypur block under BMD PHE Dte. SM/14526 | Assistant Engineer | Junior Engineer | BILL/01486/2024-2025 | BP-2024-25-357 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.56 | 0 | 0
6335 | Bankura Mechanical | Brishnupur Sub-Division | Kataban Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01605/2023-2024 | BP-2023-24-141 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.35 | 0 | 0
6336 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Kantaban Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 455/BMD | 10/06/2025 | 90 | JAL PRAVAHIKA PVT LTD | 11.85 | 0 | 0
6337 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Katabani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000528/2023-2024 | 1892/BMD | 17/08/2023 | 1080 | MENAKA ENTERPRISE | 36.9 | 21.69 | 90
6338 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Balarampur (138), Kubasol (139) & Ban Pukhuria (140) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000127/2020-2021 | 184/BQA | 18/01/2021 | 30 | SANJOY PATRA | 41.01 | 46.47 | 0
6339 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph- I project) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 02 Parasiabad & LAXMI JANARDANPUR (Part), Total House Hold- 67 (Sl No of Work- 01) |  | Junior Engineer | ORD/000211/2020-2021 | 145/ BSD | 18/02/2021 | 21 | M/S NAYAN BARDHAN | 4.58 | 0 | 100
6340 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Choto chaka, Total House Hold- 66 (Sl No of Work- 02) |  | Junior Engineer | ORD/000212/2020-2021 | 146/ BSD | 18/02/2021 | 21 | KASTURI ROY | 4.58 | 0 | 100
6341 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 71 (Sl No of Work- 03) |  | Junior Engineer | ORD/000214/2020-2021 | 147/ BSD | 18/02/2021 | 21 | PRADIP CHAKRABORTY | 4.61 | 0 | 100
6342 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 72 (Sl No of Work- 04) |  | Junior Engineer | ORD/000217/2020-2021 | 148/ BSD | 18/02/2021 | 21 | PRADIP CHAKRABORTY | 4.61 | 0 | 100
6343 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 05) |  | Junior Engineer | ORD/000228/2020-2021 | 149/ BSD | 18/02/2021 | 21 | SHOVAN DEY | 4.61 | 0 | 100
6344 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 06) |  | Junior Engineer | ORD/000230/2020-2021 | 150/ BSD | 18/02/2021 | 21 | M/S NAYAN BARDHAN | 4.61 | 0 | 100
6345 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpu (Part) Total House Hold- 70 (Sl No of Work- 07) |  | Junior Engineer | ORD/000234/2020-2021 | 151/ BSD | 18/02/2021 | 21 | ZAKIR HOSSAIN MONDAL | 4.61 | 0 | 100
6346 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpur (Part), Total House Hold- 70 (Sl No of Work- 08) |  | Junior Engineer | ORD/000241/2020-2021 | 152/ BSD | 18/02/2021 | 21 | ZAKIR HOSSAIN MONDAL | 4.61 | 0 | 100
6347 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Sonareka (Part), Total House Hold- 70 (Sl No of Work- 09) |  | Junior Engineer | ORD/000244/2020-2021 | 160/ BSD | 18/02/2021 | 21 | MD. AFSAR ALI | 4.6 | 0 | 100
6348 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Sonareka (Part), Total House Hold- 70 (Sl No of Work- 10) |  | Junior Engineer | ORD/000248/2020-2021 | 153/ BSD | 18/02/2021 | 21 | MANOJ GHOSAL | 4.61 | 0 | 100
6349 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 68 (Sl No of Work- 11) |  | Junior Engineer | ORD/000260/2020-2021 | 154/ BSD | 18/02/2021 | 21 | PRABIR BARDHAN | 4.61 | 0 | 100
6350 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 61 (Sl No of Work- 12) |  | Junior Engineer | ORD/000261/2020-2021 | 155/ BSD | 18/02/2021 | 21 | M/S NAYAN BARDHAN | 4.42 | 0 | 100
6351 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC pipe Line to Cover Bagatapole mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000342/2021-2022 | 877/ BSD | 08/09/2021 | 15 | ASHIS PAL | 4.9 | 0 | 0
6352 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. |  | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 30 | GOPAL CHANDRA CHOUDHURY | 234.49 | 3.56 | 0
6353 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01 no., (Barachaka), Total House Hold- 60 nos. |  | Junior Engineer | ORD/000491/2021-2022 | 147/BSD | 16/02/2022 | 10 | BASUDEB ACHARJEE | 4.27 | 0 | 0
6354 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover parasibad & Laxmijanardanpur mouzas for construction and commissioning of FHTC in connection with jal jeevan mission (JJM) and Jal Swapna of Sonadaha ( Zone-Q) under Bankura I, II & Barjora Block W/S scheme ( BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000910/2021-2022 |  | 08/09/2021 | 0 | NAYAN BARDHAN | 2.75 | 0 | 0
6355 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover sonarekh( Part) , Sitaldihi , Baikunthpur , mouzas for construction and commissioning of FHTC in connection with Jal Jeevan Misssion ( JJM) and Jalswapna of Sonadaha - Zone-Q under Bankura -I,II, & Barjora Block W/S Scheme ( BRGF Ph-I ) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  | Junior Engineer | VCH/000911/2021-2022 |  | 08/09/2021 | 0 | NAYAN BARDHAN | 2.87 | 0 | 0
6356 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/001349/2021-2022 |  | 28/09/2021 | 0 | KASTURI ROY | 2.17 | 0 | 0
6357 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 04 no [Narasole, Taljhoria, Khabanigoparpur (Part), Jhikuria] Total House Hold- 359 |  | Junior Engineer | VCH/001550/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAS KUMAR HAZRA | 20.59 | 0 | 0
6358 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jharia (267) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12), |  | Junior Engineer | VCH/001551/2021-2022 | FHTC/11 | 11/10/2021 | 0 | TAPAN KUMAR MANDAL | 0.74 | 0 | 0
6359 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jamda (98) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15), |  | Junior Engineer | VCH/001552/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ASOKE KUMAR SAHU | 1.61 | 0 | 0
6360 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
6361 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 01 ( Baikunthapur Part) Total Household-72 |  | Junior Engineer | VCH/001602/2020-2021 |  | 15/03/2021 | 0 | M/S NAYAN BARDHAN | 4.02 | 0 | 0
6362 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
6363 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 02 ( Parasibad & Laxmi Jonardanpur ) Total Household-67 |  | Junior Engineer | VCH/001603/2020-2021 |  | 15/03/2021 | 0 | M/S NAYAN BARDHAN | 3.84 | 0 | 0
6364 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 01 ( Baikunthapur Part ) Total Household-72 |  | Junior Engineer | VCH/001604/2020-2021 |  | 15/03/2021 | 0 | SHOVAN DEY | 4.05 | 0 | 0
6365 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 02 ( Sonareka Part & Sitaldihi ) Total Household-68 |  | Junior Engineer | VCH/001607/2020-2021 |  | 15/03/2021 | 0 | PRABIR BARDHAN | 3.9 | 0 | 0
6366 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 01 ( Sonareka Part ) Total Household- 70 |  | Junior Engineer | VCH/001608/2020-2021 |  | 15/03/2021 | 0 | MD. AFSAR ALI | 3.98 | 0 | 0
6367 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation for 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block-Bankura II , Name of the OHR -Sonadaha , No- of mouzas- 02 ( Laxmi Jonardhanpur Part ) Total Household-70 |  | Junior Engineer | VCH/001609/2020-2021 |  | 15/03/2021 | 0 | ZAKIR HOSSAIN MONDAL | 3.93 | 0 | 0
6368 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | VCH/002292/2021-2022 | FHTC/31 | 31/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.72 | 0 | 0
6369 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Beltikri mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002938/2021-2022 | FHTC/23 | 23/03/2022 | 0 | M/S SUPRIYA CHATTERJEE | 2.98 | 0 | 0
6370 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of OLA & adjoining mouzas and for Augmentation works of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Direct Pumping. No.of Mouza :- 02, Name of mouza:- Ola & Suklai. | Assistant Engineer | Junior Engineer | ORD/000151/2023-2024 | 1351/BQA | 02/06/2023 | 60 | SUNIL KUMAR MANDAL | 11.58 | 4.72 | 77
6371 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of OLA & adjoining mouzas and for Augmentation of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Direct Pumping. No.of Mouza :- 02, Name of mouza:- Ola & Suklai. | Assistant Engineer | Junior Engineer | ORD/000152/2023-2024 | 1352/BQA | 02/06/2023 | 60 | MANORANJAN GHOSH | 7.68 | 7.32 | 55
6372 | Bankura Division | Bankura Sadar Sub-Division | sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of SUKLAI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2023-2024 | 1353/BQA | 02/06/2023 | 180 | NAYAN BARDHAN | 12.93 | 10.89 | 95
6373 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of Suklai & adjoining mouzas and for Augmentation works of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 1849/BQA | 12/07/2024 | 45 | GON ASSOCIATES | 14.7 | 0 | 20
6374 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary Wall at Suklai River site Pump House and Sinking of 300 x 200 mm dia Tube well 120 mtr.Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source under Augmentation of Suklai and adjoining mouzas W/S Scheme under ONDA Water Supply Scheme (BRGF PH-I project) under Bankura Sadar Sub-Division of Bankura Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2024-2025 | 2970/BQA | 26/11/2024 | 271 | NAYAN BARDHAN | 17.68 | 0 | 85
6375 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000072/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 3.22 | 0 | 0
6376 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000223/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 3.22 | 0 | 0
6377 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at Add T/W for Augmentation of Ola and Suklai and its adjoining mouzas water supply scheme under onda block(BRGF Phase I) under Bankura Mechanical Division, PHE Dte Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 429/BMD | 27/06/2024 | 480 | INDRAJIT MITRA | 9.2 | 0 | 100
6378 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ola and Suktai and its adjoining mouzas water supply scheme under onda block(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000542/2023-2024 | 1978/BMD | 28/08/2023 | 120 | JAL PRAVAHIKA PVT LTD | 19.84 | 17.53 | 95
6379 | Bankura Division | Brishnupur Sub-Division | Restoration work of both side of road Habibpuskarini to Chakpatrasayer (WB-03-ADB12) of Length 365.00 Mtr. due to laying of pipeline of Kaktia PWSS [SM/16701] by Bankura Division. PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02019/2024-2025 |  | 25/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.91 | 0 | 0
6380 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KAKTIA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 2023/BQA | 24/07/2023 | 800 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 631.34 | 136.08 | 60
6381 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 71.81 | 0 | 0
6382 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Kakatia Near Baura Para (SM/16701)water supply scheme at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01175/2024-2025 | BP-2024-25-302 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
6383 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at Kaktia water supply scheme near football ground at Patrasayer block under BMD PHE Dte.(SM/16701) | Assistant Engineer | Junior Engineer | BILL/01355/2024-2025 | BP-2024-25-345 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
6384 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Kakatia water supply scheme(SM/16701) in Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02101/2024-2025 |  | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
6385 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I, TW No II, TW No III of Kaktia Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000115/2024-2025 | 426/BMD | 27/06/2024 | 360 | EASTERN INDIA SALES & SERVICE | 74.66 | 0 | 50
6386 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Talanjuri (Zone - F) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000290/2023-2024 | 1911/BQA | 13/07/2023 | 1084 | GOUTAM BHOWMIK | 150.33 | 38.34 | 64
6387 | Bankura Division | Bankura Sadar Sub-Division | Road Crossing work by 100 mm dia MS carrier pipe infront of Bandhkana More at Bahara Khuliya mouza by Jack pushing method, inetrconnection of MS carrier pipe with UPVC/HDPE pipeline including fabrication of MS pipe & allied works for Augmentation of Talanjuri (Zone- F) Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000342/2025-2026 | 1803/BQA | 19/08/2025 | 45 | PRADIP PATRA | 6.27 | 0 | 0
6388 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Talanjuri (Zone- F) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001180/2023-2024 | 432/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.23 | 0 | 100
6389 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000097/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.03 | 0 | 0
6390 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000272/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.03 | 0 | 0
6391 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00142/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6392 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for VT pump and Valves on delivery line installed at Intake (Raw water) pumping station near Durgapur Barrage Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division. | Assistant Engineer | Junior Engineer | ORD/000185/2023-2024 | 962/BMD | 19/05/2023 | 1080 | MAHADEV ENTERPRISE | 55.76 | 35.99 | 89
6393 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Talanjuri (Zone-F) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1410/BMD | 18/07/2023 | 60 | DEBJYOTI BASU | 81.81 | 65.63 | 64
6394 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for HSC pump installed at water treatment plant and pumping station at Dejuri , Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2023-2024 | 1786/BMD | 01/08/2023 | 90 | S.P. CONSTRUCTION | 70.44 | 67.16 | 95
6395 | Bankura Division | Bankura Sadar Sub-Division | Construction of low lift Pump House and Boundary Wall under Augmentation of Bhulanpur Water Supply Scheme | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 1862/BQA | 12/07/2024 | 263 | M/S SUPRIYA CHATTERJEE | 14.51 | 12.26 | 100
6396 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Bhulanpur and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2023-2024 | 2329/BQA | 14/08/2023 | 866 | PRADIP PATRA | 200.88 | 27.81 | 50
6397 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000111/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.82 | 0 | 0
6398 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000295/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.82 | 0 | 0
6399 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Bhulanpur ws scheme TW-II, Mouza-Dhabani ,SM-17261 | Assistant Engineer | Junior Engineer | BILL/01177/2024-2025 | BP-2024-25-297 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.37 | 0 | 0
6400 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of Quotation for new service connection at PH-I Gengari of Bhulanpur ws scheme.Sm-17261 | Assistant Engineer | Junior Engineer | BILL/01178/2024-2025 | BP-2024-25-298 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
6401 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Bhulanpur and its and its adjoining Mouzas water supply scheme under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000549/2023-2024 | 1985/BMD | 28/08/2023 | 840 | UNIVERSAL ENTERPRISE | 53.98 | 29.4 | 80
6402 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Bhulanpur and adjoining mouzas water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 3059/BMD | 12/03/2024 | 180 | GOENKA ENTERPRISE | 42.08 | 0 | 0
6403 | Bankura Division | Bankura Sadar Sub-Division | Augumentation of Jamadhara and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000497/2023-2024 | 2347/BQA | 14/08/2023 | 810 | SWAPAN KUMAR UPADHYAY | 198.08 | 0 | 70
6404 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.03 | 0 | 0
6405 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000294/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.03 | 0 | 0
6406 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Jamdhara w/s scheme. mouza-Bhedua.SM/17262 | Assistant Engineer | Junior Engineer | BILL/01353/2024-2025 | BP-2024-25-337 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0
6407 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Jamdhara & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1977/BMD | 28/08/2023 | 600 | GOENKA ENTERPRISE | 56.67 | 22.22 | 75
6408 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF SASHPUR ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1922/BQA | 13/07/2023 | 990 | PRINCE INDUTRIES (INDIA) | 200.83 | 91.11 | 80
6409 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Sashpur (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001398/2024-2025 | 23/BQA | 02/01/2025 | 90 | MANI SANKAR MUKHERJEE | 12.96 | 0 | 0
6410 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Sashpur Zone-A Water Supply Scheme (SM/18114 ), 3 nos. sites of Augmentation of Sashpur Zone-B Water Supply Scheme (SM/17421) & 1 no. site of Augmentation of Somsar (BRGF) Water Supply Scheme (SM/17579) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001821/2024-2025 | 542/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
6411 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00174/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6412 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SASHPUR ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00437/2024-2025 | BP-2024-25-111 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
6413 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Dharampur ( Sashpur Zone-A) | Assistant Engineer | Junior Engineer | BILL/01331/2024-2025 | BP-2024-25-328 | 28/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0
6414 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01623/2023-2024 | BP-2023-24-159 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0
6415 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000381/2023-2024 | 1705/BMD | 28/07/2023 | 427 | A.G.ENTERPRISE | 75.74 | 35.75 | 60
6416 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 1 No. 300 mm X 200 mm X 240 m deep Tubewell by Rig boring method, Laying of HDPE pipeline, Construction of Pump House, Construction of Boundary wall at Tubewell site and Sinking of 1 No. 200 mm dia x 5.5 mtr. depth horizontal river bed tube well using MS "T " and Laying, Fitting & fixing 100 mm M.S. delivery main connecting line from river bed tube well to CWR in connection with Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000065/2024-2025 | 1520/BQA | 19/06/2024 | 562 | TARINI CHARAN UPADHYAY | 68.26 | 0 | 30
6417 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 1 No. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas in connection with Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000792/2022-2023 | 677/BQA | 28/03/2023 | 90 | PARTHA PRATIM CHHATAIT | 92.98 | 48.49 | 81
6418 | Bankura Division | Bankura Mechanical Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 250 Cum., staging height 20 Mtr.) including by pass arrangement, construction of panel room, construction of boundary wall (Intake and OHR site), repairing of CWR, pump house and guard room with other allied works for Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001769/2024-2025 | 492/BQA | 25/02/2025 | 310 | TARINI CHARAN UPADHYAY | 33.69 | 0 | 0
6419 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000178/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.97 | 0 | 0
6420 | Bankura Mechanical | Bankura Mechanical Sub-Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer (Contractual) | BILL/00211/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6421 | Bankura Mechanical | Bankura Mechanical Sub-Division | New 3 phase connection at Phulberia W/S Scheme (near school) | Assistant Engineer | Junior Engineer (Contractual) | BILL/00951/2024-2025 | BP-2024-25-229 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0
6422 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Phulberia piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Sarenga , Dist Bankura | Assistant Engineer | Junior Engineer (Contractual) | ORD/000275/2024-2025 | 780/BMD | 20/08/2024 | 485 | INDRAJIT MITRA | 16.02 | 0 | 80
6423 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of piped water supply scheme at Sarenga block, Phulberia , Gargaria water supply scheme under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer (Contractual) | ORD/000416/2025-2026 | 2023/BMD | 12/09/2025 | 90 | M/S P.P ELECTRICALS | 57.8 | 0 | 0
6424 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000779/2023-2024 | 2294/BMD | 26/12/2023 | 540 | QUAZI NOZRUL ISLAM | 118.75 | 0 | 50
6425 | Bankura Division | Khatra Sub-Division | Work Order for Extension of distribution pipeline by UPVC pipe (6Kg/Sq. Cm. Water Pressure, class III) along with allied works at Rakhapara village of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2023-2024 | 263/KSD | 24/08/2023 | 15 | S. B. CONSTRUCTION | 0.96 | 0.96 | 95
6426 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 561/BQA | 17/03/2023 | 45 | MAHARAJA CONSTRUCTION CO. | 44.9 | 44.68 | 40
6427 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Rajadali village to Purnadihi village and from Hirbandh OHR site (Soul Ponamara) to Bijardihi village, in connection with Augmentation of Bhuakana (Zone-A) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001555/2024-2025 | 301/BQA | 28/01/2025 | 169 | GON ASSOCIATES | 10.62 | 0 | 90
6428 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline, providing FHTC (Functional House Hold Tap Connection), Construction of platform, valve chamber with all allied works of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part:-A) | Assistant Engineer | Junior Engineer | ORD/001964/2024-2025 | 663/BQA | 12/03/2025 | 60 | GON ASSOCIATES | 18.15 | 0 | 0
6429 | Bankura Division | Khatra Sub-Division | Laying of distribution pipeline, providing FHTC (Functional House Hold Tap Connection), Construction of platform, valve chamber with all allied works of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part:-B) | Assistant Engineer | Junior Engineer | ORD/002026/2024-2025 | 689/BQA | 12/03/2025 | 60 | SUMITA UPADHYAY | 18.15 | 0 | 0
6430 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000162/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.34 | 0 | 0
6431 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00205/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
6432 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Bhuakhana under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000045/2025-2026 | 249/BMD | 14/05/2025 | 90 | ORIENTAL ENGINEERING CO. | 28.14 | 0 | 0
6433 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF RADHANAGAR ZONE-II PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000399/2023-2024 | 2084/BQA | 27/07/2023 | 980 | S B ASSOCIATES | 124.07 | 61.3 | 95
6434 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Radhanagar Zone-II Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00163/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6435 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Janta of Augmentation of Radhanagar ws scheme under BMD ,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00297/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.68 | 0 | 0
6436 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at mouza Layer of Radhanagar ws scheme under BMD,PHED | Assistant Engineer | Junior Engineer | BILL/00298/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0
6437 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for Radhanagar OHR of Radhanagar w/s scheme. | Assistant Engineer | Junior Engineer | BILL/00535/2024-2025 | BP-2024-25-142 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0
6438 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR for Augmentation of Radhanagar (Zone II) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000121/2024-2025 | 431/BMD | 27/06/2024 | 360 | PRADIP KUMAR DHABAL | 19.46 | 0 | 61
6439 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-II) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000376/2023-2024 | 1702/BMD | 28/07/2023 | 630 | GOENKA ENTERPRISE | 40.9 | 15.11 | 45
6440 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000504/2023-2024 | 2354/BQA | 14/08/2023 | 2701 | SUBHANKAR BANERJEE | 336.21 | 33.52 | 14
6441 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for construction of OHR (450 CUM CAPACITY) under Augmentation of Kheyarkanali OHR (Zone- J) under Bankura- I, II & Barjora W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 3035/BQA | 06/11/2023 | 30 | K S GROUP | 0.49 | 0.47 | 100
6442 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Khyerkanali (Zone- J) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001192/2023-2024 | 445/BQA | 08/02/2024 | 30 | LEMNISCATE | 2 | 0 | 100
6443 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 242/1 -2) in between Beliatore Rly. Station and Belboni Rly. station in Belboni mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under KHYERKANALI(Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001337/2024-2025 | 3161/BQA | 24/12/2024 | 30 | SIBSANKAR CHOWDHURY | 51.9 | 51.84 | 100
6444 | Bankura Division | Bankura Sadar Sub-Division | Crossing of Road by Jack pushing method ( 600 mm dia Hump pipe (NP3/NP4 & MS Pipe for casing) & 200mm dia carrier pipe for Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Location of Site:- Near Belboni IBS Air valve point. | Assistant Engineer | Junior Engineer | ORD/001343/2024-2025 | 3182/BQA | 24/12/2024 | 90 | I R CONSTRUCTION | 11.42 | 6.9 | 100
6445 | Bankura Division | Bankura Sadar Sub-Division | Laying Rising Main, Construction of Boundary wall, Staff Room & Toilet of Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001412/2024-2025 | 51/BQA | 02/01/2025 | 90 | BEAUTY CHATTERJEE | 33.88 | 0 | 0
6446 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000128/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.33 | 0 | 0
6447 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000258/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.33 | 0 | 0
6448 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for KHYERKANAKI (Zone-J) OHR site under Bankura-I,II & Barjora water supply scheme(BRGF Ph-I project) | Assistant Engineer | Junior Engineer | BILL/01145/2024-2025 | BP-2024-25-280 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.31 | 0 | 0
6449 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on the delivery line at IBS Belboni, for Augmentation work for Khyerkanali ( Zone-J) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 440./BMD | 27/06/2024 | 300 | SARVATAH PROJECTS PRIVATE LIMITED | 42.76 | 23.6 | 55
6450 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 246/3 -4) in between Belboni Rly. Station - Baliator Rly. station, Block Barjora ,by HDD method with 300 mm (OD) MS Casing Pipe with 100 mm dia. MS carrier pipe for Proposed Surface Water Based Dhabani PIped Water Supply Scheme & Augmentation works for KHYERKANALI (Zone- J) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001935/2024-2025 | 658/BQA | 11/03/2025 | 30 | M/S TARUN KUMAR PATRA | 44.95 | 0 | 2
6451 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electro mechanical accessories at OHR site of Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 854/BMD | 29/08/2024 | 450 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 40.9 | 0 | 89
6452 | Bankura Division | Bankura Sadar Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Creation of Balance FHTC (Functional House Hold Tap Connection) and Construction of platform for Augmentation of Lakhmanpur (Zone - L) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 1973/BQA | 18/07/2023 | 270 | UNIVERSAL CONSTRUCTION | 145.98 | 75.64 | 45
6453 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Lakshmanpur (Zone-L) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000843/2023-2024 | 2969/BQA | 31/10/2023 | 30 | GEO SOLUTION | 4.45 | 2.33 | 100
6454 | Bankura Division | Bankura Sadar Sub-Division | Construction of Guard Room & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Lakhmanpur (Zone - L) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001408/2024-2025 | 26/BQA | 02/01/2025 | 90 | M/S S.M ENTERPRISE | 5.34 | 0 | 70
6455 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000120/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 5.36 | 0 | 0
6456 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000273/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 5.36 | 0 | 0
6457 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room, Boundary Wall, laying distribution pipeline to provide FHTC, Sinking of 6 (Six) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Mandalkuli, Zone-IIIA Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2025-2026 | 1288/BQA | 17/06/2025 | 184 | SUBHENDU SEKHAR GORAI | 96.65 | 0 | 0
6458 | Bankura Division | Khatra Sub-Division | Construction of Boundary wall, Construction of Operator room and WBSEDCL room of Mandalkuli (Zone- IIIA) of Raipur Water Supply Scheme (BRGF Ph-I)) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2025-2026 | 1312/BQA | 17/06/2025 | 90 | COSMIC CONSTRUCTION | 39.9 | 0 | 0
6459 | Bankura Division | Khatra Sub-Division | Construction & commissioning of FHTC (Functional House Hold Tap Connection) in different mouzas for Augmentation of Water Supply Scheme for Mandalkuli, Zone-IIIA and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000324/2023-2024 | 1928/BQA | 13/07/2023 | 903 | EARTH MOVING (INDIA) | 116.45 | 58.53 | 20
6460 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 2 nos. site of Augmentation of Water Supply Scheme for Mandalkuli (Zone-IIIA) [SM/17283], 1 no. site of Augmentation of Water Supply Scheme for Mandalkuli (Zone-IIIB) [SM/17435] and 2 nos. site of Augmentation of Water Supply Scheme for Dhemushunya (Zone-IV) [SM/17714] within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2024-2025 | 176\KSD | 07/03/2025 | 10 | M/S ASHOK KUMAR DEY | 0.75 | 0 | 90
6461 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000191/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
6462 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00215/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6463 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply installation of riverbed submersible pump motor and allied work for augmentation work at Mandalkuli (IIIA) under Raipur Block sub Surface Water Based Piped Water Supply Scheme , under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000015/2025-2026 | 150/BMD | 30/04/2025 | 270 | PRADIP KUMAR DHABAL | 32.25 | 0 | 10
6464 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Mandalkuli (Zone IIIA) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000878/2024-2025 | 2038/BMD | 07/03/2025 | 120 | GOENKA ENTERPRISE | 63.94 | 0 | 0
6465 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Modification and up gradation of Gaseous chlorination system at Head work site under Augmentation work of Mandalkuli (zone IIIA ) of Raipur water supply scheme (BRGF Phase I) under JJM , under Bankura Mechanical Division ,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001033/2023-2024 | 2965/BMD | 29/02/2024 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 14.2 | 14.14 | 98
6466 | Bankura Division | Bankura Sadar Sub-Division | PAYMENT TO RAIL | Assistant Engineer | Junior Engineer | BILL/00006/2023-2024 | FHTC/20 | 20/04/2023 | 0 | SOUTH EASTERN RAILWAY | 6.3 | 0 | 0
6467 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of Augmentation of Sub-Surface water based Water Supply Scheme (Left out from BRGF Mouzas for Onda ) along with interconnection and allied works under Bankura Sadar Sub Division of Bankura Division,, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000170/2024-2025 | 1810/BQA | 11/07/2024 | 264 | GOPAL CHANDRA CHOWDHURY | 140.48 | 84.38 | 10
6468 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary Wall at Onda (Zone - II) H/W Site in connection with Jal Jeevan Mission (JJM) for Augmentation of Onda Water Supply Scheme within Onda Block under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Total Length:- 300 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000213/2024-2025 | 1864/BQA | 12/07/2024 | 507 | SUBHAM CONSTRUCTION | 35.29 | 0 | 5
6469 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000471/2023-2024 | 2326/BQA | 14/08/2023 | 961 | GOPAL CHANDRA CHOWDHURY | 655.34 | 518.15 | 56
6470 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing of drilling materials for sinking of RBTW for rejuvenation of Onda water supply Scheme connection to JJM Program Block: Onda in the district of Bankura under Bankura Mechanical Division P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/000210/2022-2023 | 1346/BMD | 11/11/2022 | 30 | ALPHA ENTERPRISE | 23.3 | 23.19 | 0
6471 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sub Surface water based water supply scheme(Left outfrom BRGF Mouza) for Onda under onda block under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000543/2023-2024 | 1979/BMD | 28/08/2023 | 120 | UNITED TRADERS | 56.54 | 31.01 | 55
6472 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BAGDOBA & KHUNDANGA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 2332/BQA | 14/08/2023 | 540 | GOPAL CHANDRA CHOWDHURY | 1262.72 | 177.44 | 80
6473 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Khundanga Piped Water Supply Scheme (SM/14482) , 2 nos. sites of Jibta Piped Water Supply Scheme (SM/15018) & 2 nos. sites of Bagdoba Piped Water Supply Scheme (SM/18305) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001875/2024-2025 | 553/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 100
6474 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000081/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 167.01 | 0 | 0
6475 | Bankura Mechanical | Brishnupur Sub-Division | Bagdoba Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01547/2023-2024 | BP-2023-24-93 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.38 | 0 | 0
6476 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Bagdoba Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 881/BMD | 04/05/2023 | 1080 | TAPAN KUMAR SARKAR | 47.08 | 26.89 | 60
6477 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF KARISUNDA PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000391/2023-2024 | 2051/BQA | 24/07/2023 | 618 | SIB SANKAR CHOWDHURY | 177.69 | 26.02 | 65
6478 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 60 mtr long of Karisunda water supply scheme (BRGF) (3rd T/W Site) at mouza Karisunda (J.L No-54, Plot No-1887) in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001384/2024-2025 | 75/BQA | 06/01/2025 | 391 | M/S. RAJU SINGH | 4.42 | 0 | 0
6479 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.4 m x 3.6 m) at 4th TW site at mouza Belbandhi (J.L No-22, Plot No-8) for Karisunda Water Supply Scheme (BRGF) wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001385/2024-2025 | 31/BQA | 02/01/2025 | 90 | SK FAZLUL ALAM | 6.57 | 0 | 0
6480 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.4 m x 3.6 m) at 3rd TW site at mouza Karisunda (J.L No-54, Plot No-1887) for Karisunda Water Supply Scheme (BRGF) wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001386/2024-2025 | 33/BQA | 02/01/2025 | 90 | BIDHAN BANERJEE | 6.58 | 0 | 0
6481 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 60 mtr long of Karisunda water supply scheme (BRGF) (4th T/W Site) at mouza Belbandhi (J.L No-22, Plot No-8) in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001397/2024-2025 | 74/BQA | 06/01/2025 | 45 | BAKIRUL HOSEN KHAN | 4.2 | 0 | 100
6482 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Karisunda Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00189/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6483 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Karisunda Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01620/2023-2024 | BP-2023-24-153 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0
6484 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Karisunda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1707/BMD | 28/07/2023 | 244 | ABHIJIT MUKHERJEE | 61.17 | 40.16 | 66
6485 | Bankura Division | Brishnupur Sub-Division | Additional sinking of 1 no 300mm X 200mm X 165m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe Augmentation of Chakuparsole Zone-B of Bishnupur Block ( JJM ) under Bishnupur Sub-Division of Bankura Division P.H.E Dte. (SM/17426) | Assistant Engineer | Junior Engineer | ORD/000078/2025-2026 | 1017/BQA | 25/04/2025 | 90 | I R CONSTRUCTION | 13.94 | 0 | 0
6486 | Bankura Division | Brishnupur Sub-Division | Additional sinking of 1 no 300mm X 200mm X 165m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Chakuparsole Zone-B of Bishnupur Block (JJM) under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000124/2025-2026 | 1286/BQA | 17/06/2025 | 60 | I R CONSTRUCTION | 14.05 | 0 | 0
6487 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHAKUPARSOLE ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 2349/BQA | 14/08/2023 | 597 | I.R.CONSTRUCTION | 177.27 | 60.48 | 70
6488 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Chakuparsole (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001353/2024-2025 | 3170/BQA | 24/12/2024 | 181 | TAPAS KUMAR NANDI | 12.96 | 0 | 0
6489 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Prakash Zone-B Water Supply Scheme (SM/16945), 4 nos. sites of Augmentation of Chakuparsole Zone-B Water Supply Scheme (SM/17426 ) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001803/2024-2025 | 532/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.9 | 0 | 0
6490 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chakuparsole Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00170/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6491 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at mouza -Upar Amdahara jl no 146.SM/17426 | Assistant Engineer | Junior Engineer | BILL/00365/2025-2026 | 236/W-1262 | 12/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.58 | 0 | 0
6492 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Phulboni of Chakuparsole Zone-B ws scheme.SM/17426 | Assistant Engineer | Junior Engineer | BILL/00539/2024-2025 | BP-2024-25-208 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
6493 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Mouza Upar Amdahara of Chakuparsole Zone-B W/S scheme Boosting TW-I. SM/17426. | Assistant Engineer | Junior Engineer | BILL/00540/2024-2025 | BP-2024-25-209 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.9 | 0 | 0
6494 | Bankura Mechanical | Brishnupur Sub-Division | Additional Quotation for Mouza Fulbani ,GP Bankadaha .Chakuparsole zone-B.SM/17426 | Assistant Engineer | Junior Engineer | BILL/01341/2024-2025 | BP-2024-25-335 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.91 | 0 | 0
6495 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW II to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-B) Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 485/BMD | 09/07/2024 | 386 | GOENKA ENTERPRISE | 34.36 | 0 | 100
6496 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chakuparsole (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 1699/BMD | 28/07/2023 | 960 | S.P. CONSTRUCTION | 71.56 | 0 | 0
6497 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF ROL ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000333/2023-2024 | 2003/BQA | 19/07/2023 | 983 | PRINCE INDUTRIES (INDIA) | 183.13 | 90.98 | 80
6498 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Rol Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00183/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
6499 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for ROLL ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00431/2024-2025 | BP-2024-25-107 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
6500 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Dhamur (Roll Zone-B) | Assistant Engineer | Junior Engineer | BILL/01330/2024-2025 | BP-2024-25-331 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
6501 | Bankura Mechanical | Brishnupur Sub-Division | New three service phase connection for boosting TW site of Arapur(Gopalpur) under Roll Zone -B water supply scheme under Bankura Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/01344/2024-2025 | BP-2024-25-332 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.26 | 0 | 0
6502 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 1704/BMD | 28/07/2023 | 60 | R.N.S. TRADING | 73.25 | 0 | 0
6503 | Bankura Division | Bankura Mechanical Sub-Division | Ranibandh - Jhilimili Road from Ch.16.048 km to Ch.16.148 km, from Ch.16.810 km to Ch.16.920 km, Restoration work damage by P.H.E Department by laying Pipe line under Bankura Highway Division in the District of Bankura. Augmentation of Khejuria (Zone-N) W/S Scheme (SM/17429) | Assistant Engineer |  | BILL/01031/2024-2025 |  | 28/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 3.88 | 0 | 0
6504 | Bankura Division | Bankura Mechanical Sub-Division | Ranibandh - Jhilimili Road from Ch.16.048 km to Ch.16.148 km, from Ch.16.810 km to Ch.16.920 km, Restoration work damage by P.H.E Department by laying Pipe line under Bankura Highway Division in the District of Bankura. Augmentation of Khejuria (Zone-N) W/S Scheme (SM/17429) | Assistant Engineer |  | BILL/01246/2024-2025 | BP-347/2024-25 | 03/10/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 3.88 | 0 | 0
6505 | Bankura Division | Bankura Mechanical Sub-Division | Construction of CWR (100 Cum.) along with all allied works for Augmentation works for Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000067/2024-2025 | 1522/BQA | 19/06/2024 | 287 | PRADIP CHAKRABORTY | 22.53 | 0 | 90
6506 | Bankura Division | Bankura Mechanical Sub-Division | Work Order for Supply, Delivery and Stacking of Sluice Valve of Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000125/2023-2024 | 127/KSD | 25/05/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.94 | 0.94 | 20
6507 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000784/2022-2023 | 674/BQA | 28/03/2023 | 1422 | SWAPAN KUMAR CHANDRA | 92.14 | 29.91 | 80
6508 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 4 (Four) Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of 6 (Six) Nos. Pump Houses with ancillary works in different mouzas of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001153/2023-2024 | 357/BQA | 06/02/2024 | 422 | TARINI CHARAN UPADHYAY | 56.71 | 6.27 | 55
6509 | Bankura Division | Bankura Mechanical Sub-Division | Laying HDPE pipeline from Karapara village to Bansdiha village with all allied works of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001156/2023-2024 | 368/BQA | 06/02/2024 | 30 | MANAS DEY | 13.37 | 13.36 | 80
6510 | Bankura Division | Bankura Mechanical Sub-Division | Laying HDPE pipeline from Karapara village to Bansdiha village with all allied works of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001157/2023-2024 | 369/BQA | 06/02/2024 | 30 | DAUD ALI KHAN | 13.37 | 13.37 | 80
6511 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000176/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.39 | 0 | 0
6512 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at T/W-III of Khejuria | Assistant Engineer |  | BILL/01146/2024-2025 | BP-2024-25-271 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.71 | 0 | 0
6513 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at T/W-IV of Khejuria | Assistant Engineer |  | BILL/01147/2024-2025 | BP-2024-25-272 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0
6514 | Bankura Division | Bankura Mechanical Sub-Division | Work Order for Installation of scheme information board for 4 nos. site of Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17429) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001916/2024-2025 | 160\KSD | 07/03/2025 | 10 | S. B. CONSTRUCTION | 0.6 | 0 | 90
6515 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at P/H-I of Khejuria | Assistant Engineer |  | BILL/01149/2024-2025 | BP-2024-25-281 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.8 | 0 | 0
6516 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service Connection at Khejuria T/W-II | Assistant Engineer |  | BILL/01480/2024-2025 | BP-2024-25-370 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.88 | 0 | 0
6517 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Khejura (Zone N) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer |  | ORD/000044/2025-2026 | 248/BMD | 14/05/2025 | 90 | M.S. ENTERPRISE | 29.11 | 0 | 0
6518 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for Augmentation works for Khejuria (Zone- N) ( Boosting at OHR Site) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer |  | ORD/000170/2024-2025 | 512/BMD | 09/07/2024 | 720 | DEBJYOTI BASU | 92.97 | 0 | 68
6519 | Bankura Division | Khatra Sub-Division | Construction of 2 (Two) Nos. Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2025-2026 | 1018/BQA | 25/04/2025 | 60 | GON ASSOCIATES | 15.45 | 0 | 0
6520 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR, Repairing and painting of High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Gargaria, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000261/2025-2026 | 1542/BQA | 14/07/2025 | 60 | SAYED PAHALOWAN | 27.95 | 0 | 0
6521 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 4 nos. site of Augmentation works for Gargariya, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17281] and 2 nos. site of Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas (SM/17707) within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001919/2024-2025 | 163\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
6522 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000182/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 4 | 0 | 0
6523 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00195/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6524 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00213/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6525 | Bankura Mechanical | Khatra Sub-Division | New service connection for Gargaria water supply scheme under Bankura Mechanical Division Dte. | Assistant Engineer | Junior Engineer | BILL/00383/2024-2025 | BP-2024-25-84 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
6526 | Bankura Mechanical | Khatra Sub-Division | New service connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00384/2024-2025 | BP-2024-25-87 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0
6527 | Bankura Mechanical | Khatra Sub-Division | New 3 phase service connection for site Gargaria Zone A | Assistant Engineer | Junior Engineer | BILL/00697/2024-2025 | BP-2024-25-163 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
6528 | Bankura Mechanical | Khatra Sub-Division | New 3 phase service connection for site Gargaria Zone A | Assistant Engineer | Junior Engineer | BILL/00698/2024-2025 | BP-2024-25-168 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0
6529 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries with illumination system other electromechanical accessories for Augmentation for Gargariya Zone-A and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 514/BMD | 09/07/2024 | 600 | S.P. CONSTRUCTION | 78.81 | 0 | 20
6530 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineries with allied works for Augmentation works for Gargariya Zone B water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 862/BMD | 29/08/2024 | 240 | TAPAN KUMAR SARKAR | 34.3 | 0 | 70
6531 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000573/2023-2024 | 2029/BMD | 01/09/2023 | 1070 | S.P. CONSTRUCTION | 90.11 | 0 | 30
6532 | Bankura Division | Khatra Sub-Division | Construction of Boundary wall, Approach road, Land Development with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For OHR site) | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 754/BQA | 04/04/2023 | 45 | ASEK ALI KHAN | 14.57 | 0 | 0
6533 | Bankura Division | Khatra Sub-Division | Balance work of Rising main, Construction of Chlorine Room and Construction of Operator Room for Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For Sonagara Zone-IIB site) | Assistant Engineer | Junior Engineer | ORD/000120/2025-2026 | 1282/BQA | 17/06/2025 | 90 | SIBSANKAR CHOWDHURY | 45.08 | 0 | 0
6534 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 550 Cum., staging height 20 Mtr.), Boundary Wall and construction of Chlorination Room, Guard Room at OHR sites with all allied works under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000123/2025-2026 | 1285/BQA | 17/06/2025 | 90 | SUBHANKAR BANERJEE | 54.07 | 0 | 0
6535 | Bankura Division | Khatra Sub-Division | Laying additional HDPE pipeline, Supply of Sluice valve, construction of valve chamber with all allied works under Improvement of Sonagara Water Supply Scheme (Zone-IA) under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2025-2026 | 1307/BQA | 17/06/2025 | 199 | TARINI CHARAN UPADHYAY | 19.48 | 0 | 0
6536 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Construction of Valve chamber under balance work of Improvement of Sonagara (Zone- IA) Water Supply Scheme BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000183/2024-2025 | 1855/BQA | 12/07/2024 | 60 | GOPAL CHANDRA CHOWDHURY | 34.49 | 0 | 90
6537 | Bankura Division | Khatra Sub-Division | Construction of Boundary wall, Approach road, Land Development with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For Head Work site) | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 2382/BQA | 14/08/2023 | 841 | GANGADHAR MONDAL | 29.04 | 11.6 | 80
6538 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
6539 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000055/2023-2024 | 2470/BQA | 29/08/2023 | 0 | Resource Division | 227.39 | 0 | 0
6540 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000159/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 39.55 | 0 | 0
6541 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000297/2023-2024 | 885/BQA | 12/03/2024 | 0 | Resource Division | 143.02 | 0 | 0
6542 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of MS Delivery main Connecting river bed tube well to Common Manifold incuding supply and erecting of guard piling etc. including cost of clamp, bracket, 'U' bolt etc. all complete with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2023-2024 | 2324/BQA | 14/08/2023 | 90 | EARTH MOVING (INDIA) | 129.16 | 128.44 | 94
6543 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kalyansaer (1), Kalapathar (2), Bera (3), Kese (4), Lachankunda (5), Bhagra (6), Lalbazar (7), Digarkanali (8), Karamara (9), Damdi (10), Baburamhir (11), Raidihi (12), Bankanali (13), Indrajhor (14), Khatanga (61), Jaljura (62), Gumkihata (63), Barakharanga (64), Madhupur (65), Khalpara (66), Pairaguri (67), Siarbeda (68), Chirugora (69), Karrasol (70), Chaturi Nutandihi (72), Chaturi (73), Lachhipur (74), Manhara (75), Bishanpur (76), Rautkhana (77), Pirra (78), Rangasol (79), Birudi (80), Dundar (81) & Khejurbedia (82) mouzas for Zone- IA of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2023-2024 | 2333/BQA | 14/08/2023 | 962 | MUNMUN UPADHYAY | 208.25 | 0 | 40
6544 | Bankura Division | Khatra Sub-Division | Construction of 400 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height including foundation, pipeline connection and Providing FHTC for Zone- IB of Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000738/2023-2024 | 2737/BQA | 04/10/2023 | 270 | MD. AAMIR KHAN | 302.89 | 0 | 0
6545 | Bankura Division | Khatra Sub-Division | Crossing of Road by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Laying of DI Rising Main under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000822/2023-2024 | 2945/BQA | 30/10/2023 | 30 | SIBSANKAR CHOWDHURY | 7.37 | 0 | 90
6546 | Bankura Division | Khatra Sub-Division | Construction of High lift Pump House with all allied works for balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001085/2023-2024 | 3531/BQA | 29/12/2023 | 460 | ASOKE KUMAR SAHU | 63.51 | 30.96 | 81
6547 | Bankura Mechanical | Khatra Sub-Division | Service connection charge for SONAGARA water supply scheme (scheme code: SM/18390) | Assistant Engineer | Junior Engineer | BILL/00350/2024-2025 | BP-2024-25-82 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 36.61 | 0 | 0
6548 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 3 nos. site of Improvement of Sonagara (Zone-IA & IB) Water Supply Scheme (SM/18390) and 3 nos. site of Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas (SM/12380) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001931/2024-2025 | 174\KSD | 07/03/2025 | 10 | SANDHYA DEY | 0.9 | 0 | 95
6549 | Bankura Mechanical | Khatra Sub-Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01519/2023-2024 | BP-2023-24-119 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0
6550 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries & gaseous chlorination system and other electromechanical accessories and Making an arrangement for proper material management and handling at Ailakandi PHE Mechanical office campus for Augmentation of Sonagara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000144/2024-2025 | 487/BMD | 09/07/2024 | 390 | WEST BENGAL ENGINEERING CO. | 83.28 | 0 | 30
6551 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing of pumping machineries, Sub-Station equipment¿s and other Electro-mechanical accessories For the scheme of Laying rising main distribution system collecting line from RBTW to CWR Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including providing of FHTC under balance work of improvement of Sanagara water supply scheme under BRGF( Phase-I) under Jal Jeevan Mission Programme Block - Raipur , Dist - Bankura | Assistant Engineer | Junior Engineer | ORD/000613/2023-2024 | 2068/BMD | 12/09/2023 | 809 | WEST BENGAL ENGINEERING CO. | 409.3 | 200.9 | 56
6552 | Bankura Division | Brishnupur Sub-Division | Wayleave / Track crossing proposal with Application ID SER-ADRA-2024-WL-24 for Chak Patrasayer PWSS ( SM Code : 18401 ) | Assistant Engineer | Junior Engineer | BILL/00058/2024-2025 | FHTC/04 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY | 0.1 | 0 | 0
6553 | Bankura Division | Brishnupur Sub-Division | Way leave / Track crossing Proposal with Application ID : SER-ADRA-2024-WL-24 for Chak Patrasayer PWSS (SM Code : 18401) ( 2nd Instalment amount ). | Assistant Engineer | Junior Engineer | BILL/00179/2024-2025 | BP-78/2024-25 | 27/05/2024 | 0 | SOUTH EASTERN RAILWAY | 5.88 | 0 | 0
6554 | Bankura Division | Brishnupur Sub-Division | Balance Ancillary Works of Chak Patrasayer PWSS under Bishnupur Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000536/2025-2026 | 2151/BQA | 30/10/2025 | 90 | DEBAKI RANJAN SARKAR | 101.48 | 0 | 0
6555 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Chak Patrasaer Piped Water Supply Scheme(SM/18401) & 3 nos. sites of Rampur Piped Water Supply Scheme (SM/18349) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001885/2024-2025 | 563/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
6556 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2024-2025 | 1882/BQA | 22/07/2024 | 0 | Resource Division | 44.32 | 0 | 0
6557 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2024-2025 | 2011/BQA | 26/07/2024 | 0 | Resource Division | 19.78 | 0 | 0
6558 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000070/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 93.28 | 0 | 0
6559 | Bankura Mechanical | Brishnupur Sub-Division | Submission of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer J.L No-48,Plot No-4623 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00361/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
6560 | Bankura Mechanical | Brishnupur Sub-Division | Submissioin of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer JL no-48 plot no-4621 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00362/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
6561 | Bankura Mechanical | Brishnupur Sub-Division | Submission of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer J.L No-48,Plot No-4622 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00363/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
6562 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chak Patrasayer water supply scheme at Patrasayer block under BMD PHE Dte.(SM/18401) | Assistant Engineer | Junior Engineer | BILL/01599/2024-2025 |  | 17/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.75 | 0 | 0
6563 | Bankura Mechanical | Brishnupur Sub-Division | Chak Patrasaer Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01615/2023-2024 | BP-2023-24-132 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
6564 | Bankura Mechanical | Brishnupur Sub-Division | Chak Patrasaer Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01668/2023-2024 | BP-2023-24-176 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.03 | 0 | 0
6565 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Chak Patrasayer Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000036/2025-2026 | 241/BMD | 14/05/2025 | 90 | KASHINATH DEY | 12.22 | 0 | 0
6566 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Chak Patrasayar Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 882/BMD | 04/05/2023 | 701 | M.S. ENTERPRISE | 68.15 | 34.26 | 45
6567 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte Khataam c/o Sudip Saha , Khataam, Ranibandh |  | Junior Engineer | BILL/00048/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
6568 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6569 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6570 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
6571 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Gaighata site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00193/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
6572 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6573 | Bankura Division | Brishnupur Sub-Division | Bmsd Phe Dte site at Makarkendi, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00609/2023-2024 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.12 | 0 | 0
6574 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6575 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.77 | 48
6576 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6577 | Bankura Division | RWS Bankura Sub-Division | New Connection at Nachna, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00430/2023-2024 | FHTC/04 | 23/04/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6578 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6579 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
6580 | Bankura Division | Brishnupur Sub-Division | Chaltaknda to ODR (WB-03-318) of Scheme Name Basantapur PWSS (SM/12424) | Assistant Engineer | Junior Engineer | BILL/02022/2024-2025 |  | 25/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 6.3 | 0 | 0
6581 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 221.66 | 6
6582 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
6583 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Hetia Piped Water Supply Scheme (SM/12425) & 2 nos. sites of Basantapur Piped Water Supply Scheme (SM/12424) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001836/2024-2025 | 549/VSD | 27/09/2024 | 15 | SUBHANKAR BIT | 0.6 | 0 | 0
6584 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000034/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 53.55 | 0 | 0
6585 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000302/2023-2024 | 884/BQA | 12/03/2024 | 0 | Resource Division | 12.64 | 0 | 0
6586 | Bankura Mechanical | Brishnupur Sub-Division | Basantapur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01499/2023-2024 | BP-2023-24-106 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.47 | 0 | 0
6587 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Basantapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000184/2025-2026 | 456/BMD | 10/06/2025 | 90 | AMITAVA CHAKRABORTY | 11.91 | 0 | 0
6588 | Bankura Division | Bankura Sadar Sub-Division | New connecion at vill-jaramahul (senpara) p.o-Hizlitilabari (Ranibandh CCC) | Assistant Engineer | Junior Engineer | BILL/02598/2023-2024 | FHTC/03 | 12/03/2024 | 0 | RANIBANDH CCC | 0.12 | 0 | 0
6589 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 47 | 48
6590 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6591 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte Katar,Ps-Khatra, Dist-Bankura |  | Junior Engineer | BILL/00770/2022-2023 | FHTC/05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
6592 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6593 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
6594 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Bhalaidiha Village (SM/10948), (2) Mini Piped Water Supply Scheme for Katar Village (SM/10950), (3) Mini Piped Water Supply Scheme for Khakrakanali Village (SM/10951), (4) Mini Piped Water Supply Scheme for Bandarkonda Village (SM/10949) and (5) Mini Piped Water Supply Scheme for Bansnala Village (SM/10957) |  | Junior Engineer | ORD/001988/2024-2025 | 188\KSD | 10/03/2025 | 10 | SRIJAN CONSTRUCTION | 0.75 | 0 | 95
6595 | Bankura Division | RWS Bankura Sub-Division | New service connection for Belaruma Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00123/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
6596 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6597 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6598 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27.5 | 48
6599 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubrajpur (168) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 3357 nos. | Assistant Engineer | Junior Engineer | ORD/000045/2022-2023 | 1648/BQA | 25/07/2022 | 105 | M/S TARUN KUMAR PATRA | 144.56 | 123.04 | 95
6600 | Bankura Division | Khatra Sub-Division | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Dubrajpur Zone-A & B of Simlapal Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) [Part-B] (Sl. No. 12) | Assistant Engineer | Junior Engineer | ORD/000336/2021-2022 | 820/KSD | 15/12/2021 | 15 | SOURAV SINHA MAHAPATRA | 3.59 | 0 | 0
6601 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubrajpur (168) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 23) | Assistant Engineer | Junior Engineer | ORD/000686/2021-2022 | 862/KSD | 31/12/2021 | 90 | TAPAS DEY | 1.12 | 0.88 | 0
6602 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2022-2023 | 1838/BQA | 29/08/2022 | 0 | Resource Division | 9.23 | 0 | 0
6603 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 11.44 | 0 | 0
6604 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6605 | Bankura Division | RWS Bankura Sub-Division | New Connection at Pedda, Taldangra Pin-722101 PHE Dte. |  | Junior Engineer | BILL/00438/2023-2024 |  | 16/06/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6606 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6607 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 11 | 48
6608 | Bankura Division | RWS Bankura Sub-Division | New Connection at Kolsuli, Taldangra,Pin-722102 PHE Dte |  | Junior Engineer | BILL/00709/2023-2024 |  | 26/07/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
6609 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6610 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Raghunathpur, Bongopalpur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00150/2024-2025 |  | 16/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
6611 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Raghunathpur, Bongopalpur Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00170/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
6612 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
6613 | Bankura Division | Bankura Sadar Sub-Division | Construction of Pump House, Boundary Wall at 3nos locations i.c. Pakhanna OHR Site, Gopalpur and Purokonda and Laying additional distribution system under Augmentation works for Pakhanna and its adjoining Mouzas Water Supply Scheme within Barjora Block. | Assistant Engineer | Junior Engineer | ORD/000372/2024-2025 | 2350/BQA | 09/09/2024 | 90 | TAPAS KUMBHAKAR | 60.29 | 0 | 25
6614 | Bankura Division | Bankura Sadar Sub-Division | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Pakhanna and its adjoining mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 2048/BQA | 24/07/2023 | 979 | PRINCE INDUTRIES (INDIA) | 194.81 | 112.75 | 85
6615 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Pakhanna and its adjoining mouzas. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001176/2023-2024 | 428/BQA | 08/02/2024 | 30 | LEMNISCATE | 0.92 | 0 | 100
6616 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000088/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.25 | 0 | 0
6617 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000254/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.25 | 0 | 0
6618 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Purakanda Pump House augmentation work under Pakhanna water supply scheme (SM/03512) | Assistant Engineer | Junior Engineer | BILL/00727/2024-2025 | BP-2024-25-211 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0
6619 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge for Gopalpur Pump house under Pakhanna and its Adjoining mouzas water supply scheme Barjora block under BMD,PHE Dte.(SM/16973 ) | Assistant Engineer | Junior Engineer | BILL/02195/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.88 | 0 | 0
6620 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No-I & II at Tail End site of Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000328/2024-2025 | 867/BMD | 29/08/2024 | 120 | SK ENTERPRISE | 12.1 | 3.1 | 71
6621 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Pakhanna & its adjoining mouzas water supply scheme Block Barjora under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 1768/BMD | 01/08/2023 | 60 | M/S NABIN GOPAL SENGUPTA | 72.97 | 55 | 74
6622 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 120 | SK ENTERPRISE | 30.4 | 0 | 0
6623 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone- F ) No.of Mouza :- 02 nos, Narasinghapur, Arrah (Part) Total House Hold - 224. |  | Junior Engineer | ORD/000030/2021-2022 | 1803/BQA | 09/07/2021 | 30 | ZAKIR HOSSAIN MONDAL | 15.32 | 15.1 | 0
6624 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No.of Mouza :- 03 nos, (Barabanagram, Barsi, Gursagram (part) Total House Hold - 224 |  | Junior Engineer | ORD/000048/2021-2022 | 1929/BQA | 27/07/2021 | 1435 | JAGADISH BANERJEE | 15.41 | 0 | 10
6625 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No.of Mouza :- 03 nos, (Bandyagal, Malbedya, Gursagra (Part), Total House Hold - 229 |  | Junior Engineer | ORD/000049/2021-2022 | 1930/BQA | 27/07/2021 | 30 | GANGADHAR MONDAL | 16.06 | 15.32 | 0
6626 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal (Zone- F), Name of Mouza :- Arrah, Total House Hold :- 42 nos. |  | Junior Engineer | ORD/000055/2022-2023 | 252/KSD | 12/07/2022 | 15 | NAYAN BARDHAN | 2.69 | 2.69 | 0
6627 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No. of Mouza :- 02 no, Arrah (Part), Khudrabanagram Total House Hold - 383. |  | Junior Engineer | ORD/000057/2021-2022 | 1961 A / BQA | 30/07/2021 | 30 | NAYAN BARDHAN | 28.48 | 0 | 0
6628 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandagal (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandagal, No. of Mouza :- 03 No, Arrah (Part), Bandaga (Part), Ghuniyada (part), Total House Hold :- 19 Nos. |  | Junior Engineer | ORD/000138/2023-2024 | 99/KSD | 28/04/2023 | 30 | TAPAS KUMBHAKAR | 0.94 | 0.94 | 100
6629 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandagal (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandagal, No.of Mouza :- 03 Nos., Sihika(Part), Goyaldanga (part), Ghuniyada (part), Total House Hold :- 19 nos. |  | Junior Engineer | ORD/000139/2023-2024 | 100/KSD | 28/04/2023 | 30 | TAPAS KUMBHAKAR | 0.94 | 0.9 | 100
6630 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying Extra UPVC Pipe Line to Cover Guniyada, Arrah, Sihika, Bandyalgal, Eithani mouza for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) & Tilna (Zone - E) under Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000158/2023-2024 | 103/KSD | 28/04/2023 | 15 | TAPAS KUMAR HAZRA | 0.54 | 0 | 100
6631 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE pipe line near Rail gate to Barabanagram of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000296/2022-2023 | 361/KSD | 29/08/2022 | 20 | TARINI CHARAN UPADHYAY | 2.46 | 2.46 | 0
6632 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Arrah (Part), Khudrabanagram mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandyagal (Zone-F ) under Chhatna Block Saltora-Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000343/2021-2022 | 1027/ BSD | 14/12/2021 | 15 | NAYAN BARDHAN | 4.99 | 0 | 0
6633 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Bandyagal, Malbedya mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bandyagal (Zone-F) under Chhatna Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000613/2021-2022 | 1030/BSD | 14/12/2021 | 15 | GANGADHAR MONDAL | 4.29 | 3.67 | 0
6634 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line from Arrah to Dochama Ashram for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000760/2022-2023 | 637/BQA | 24/03/2023 | 45 | SK. ALAMGIR ALAM | 3.04 | 0 | 100
6635 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 09) |  | Junior Engineer | VCH/001778/2021-2022 | FHTC/28 | 28/10/2021 | 0 | MUNMUN UPADHYAY | 4.83 | 0 | 0
6636 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kanchanpur(Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Sl. No. 10) |  | Junior Engineer | VCH/001779/2021-2022 | FHTC/28 | 28/10/2021 | 0 | ASOKE BHATTACHARYYA | 4.41 | 0 | 0
6637 | Bankura Division | Bankura Sadar Sub-Division | Supply laying & fitting fixing of GI pipeline crossing at Sali river of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-17 |  | Junior Engineer | VCH/001780/2021-2022 | FHTC/28 | 28/10/2021 | 0 | DAUD ALI KHAN | 1.75 | 0 | 0
6638 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 0 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0
6639 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0
6640 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover dadhimukha & Jagdalla mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002588/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 4.48 | 0 | 0
6641 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II (Part-A) , Total House Hold -345 nos. |  | Junior Engineer | ORD/000093/2021-2022 | 2530/BQA | 23/09/2021 | 30 | PRADIP CHAKRABORTY | 26.16 | 0 | 0
6642 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 |  | Junior Engineer | ORD/000210/2020-2021 | 2031/BQA | 29/12/2020 | 30 | RANABIR CHATTERJEE | 41.02 | 45.59 | 0
6643 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | ORD/000399/2020-2021 | 857/BQA | 25/02/2021 | 30 | SUBHANKAR BANERJEE | 35.1 | 0 | 0
6644 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-B), Total House Hold -264 |  | Junior Engineer | ORD/000406/2020-2021 | 864/BQA | 25/02/2021 | 30 | ASHOKE BHATTACHARYYA | 22.9 | 0 | 0
6645 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172 |  | Junior Engineer | ORD/000410/2020-2021 | 865/BQA | 25/02/2021 | 30 | ASHOKE KUMAR DEY | 14.96 | 0 | 0
6646 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-D) , Total House Hold -173 |  | Junior Engineer | ORD/000411/2020-2021 | 866/BQA | 25/02/2021 | 30 | GOUTAM GHOSH | 15.02 | 0 | 0
6647 | Bankura Division | Bankura Sadar Sub-Division | Supplying laying fitting fixing of HDPE pipe line connection from Air valve of Maliara Rising main(Near Ghutgoria village ) to Hindur danga village (under Baguli Mouza ) for Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000441/2022-2023 | 619/BSD | 16/08/2022 | 21 | ASHIS KUMAR SAMANTA | 4.89 | 0 | 0
6648 | Bankura Division | Bankura Sadar Sub-Division | Supply laying & fitting fixing of GI pipeline crossing at Sali river of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-17 |  | Junior Engineer | VCH/001780/2021-2022 | FHTC/28 | 28/10/2021 | 0 | DAUD ALI KHAN | 1.75 | 0 | 0
6649 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Birkham (110) mouza under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 01 No. Total Household - 410 Nos. |  | Junior Engineer | VCH/002307/2021-2022 | FHTC/04 | 04/01/2022 | 0 | PARTHA PRATIM CHHATAIT | 24.8 | 0 | 0
6650 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  | Junior Engineer | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 0 | UNICON INDIA | 152 | 0 | 0
6651 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
6652 | Bankura Division | Khatra Sub-Division | New service connection for Khayerkundi Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00187/2024-2025 |  | 28/05/2024 | 0 | HIRBANDH CCC | 0.11 | 0 | 0
6653 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Gadapathar College More to Nanda Primary School to increase pressure in Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 896/BQA | 18/04/2022 | 30 | DEBAKI RANJAN SARKAR | 28.68 | 0 | 0
6654 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000064/2020-2021 | 477/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 30.42 | 0 | 100
6655 | Bankura Division | Khatra Sub-Division | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadia (17), Pakhuria (18), Khayer Kundi (19) Aralbara (20) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2020-2021 | 478/BQA | 05/02/2021 | 30 | DEBAKI RANJAN SARKAR | 30.87 | 0 | 90
6656 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Pakhuria (18) & Khayer Kundi (19) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 7) | Assistant Engineer | Junior Engineer | ORD/000269/2021-2022 | 615/KSD | 09/08/2021 | 15 | DEBAKI RANJAN SARKAR | 4.21 | 0 | 0
6657 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Pakhuria (18) & Khayer Kundi (19) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 8) | Assistant Engineer | Junior Engineer | ORD/000270/2021-2022 | 616/KSD | 09/08/2021 | 15 | DEBAKI RANJAN SARKAR | 3.06 | 0 | 0
6658 | Bankura Division | Khatra Sub-Division | Preparation of detailed project report for Agumentation of Saltora piped water supply scheme block - Saltora district under Bankura Division, PHE Dte. under Jal Swapna project zone - ll W/O NO - 900/BSD dt. 21.09.2021 | Assistant Engineer | Junior Engineer | VCH/000223/2022-2023 | FHTC/08 | 08/04/2022 | 0 | LEMNISCATE | 3.57 | 0 | 0
6659 | Bankura Division | Khatra Sub-Division | Route survey Preparation of detailed project report for Agumentation of Jhantipahari piped water supply scheme zone - ll under Bankura sadar sub - Division of Bankura Division, PHE Dte. under Jal Swapna project sl no - 04 | Assistant Engineer | Junior Engineer | VCH/000224/2022-2023 | FHTC/08 | 08/04/2022 | 0 | LEMNISCATE | 3.25 | 0 | 0
6660 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000519/2020-2021 | 317/KSD | 29/12/2020 | 61 | ASOKE KUMAR SAHU | 0.3 | 0 | 0
6661 | Bankura Division | Khatra Sub-Division | Route survey Preparation of detailed project report for Agumentation of Jhantipahari piped water supply scheme zone - ll under Bankura sadar sub - Division of Bankura Division, PHE Dte. under Jal Swapna project sl no - 03 W/O NO - 903/BSD dt. 24.09.2021 | Assistant Engineer | Junior Engineer | VCH/000225/2022-2023 | FHTC/08 | 08/04/2022 | 0 | LEMNISCATE | 3.04 | 0 | 0
6662 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora G.P - chandar Name of Village - Kadakuli man para . Total House Hold - 70 Tender No - 04/20-21/EE/BQA W/O NO - 556/BSD dt. 13.11.2020 | Assistant Engineer | Junior Engineer | VCH/000606/2021-2022 | FHTC/15 | 05/05/2021 | 0 | GON ASSOCIATES | 4.24 | 0 | 0
6663 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | Assistant Engineer | Junior Engineer | VCH/001228/2022-2023 | FHTC/27 | 27/09/2022 | 0 | SAMIRUDDIN KHAN | 4.97 | 0 | 0
6664 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (FunCtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dangalan, No. of Mouza :- 09 nos. i.e. Banki-85, Chotogobindapur-86, Adilpur-87 & Haldi-83, Mandra-88, Berghosh-84, Dangalan-91, Musarbar-92 & Ashwinpur-93, Total House Hold - 2639 | Assistant Engineer | Junior Engineer | VCH/001245/2022-2023 | FHTC/29 | 29/09/2022 | 0 | J. D. J. ENTERPRISE | 77 | 0 | 0
6665 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Gadapathar College More to Nanda Primary School to increase pressure in Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001418/2022-2023 | FHTC/16 | 16/12/2022 | 0 | DEBAKI RANJAN SARKAR | 19.69 | 0 | 0
6666 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe 15 mm NB pvC 9schedule 80/20 mm OD HDPE (pE 100,Ph 16) toRetrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilbaid(Zone- F) under Saltora Block under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002611/2021-2022 | FHTC/26 | 26/02/2022 | 0 | MANAS DEY | 4.79 | 0 | 0
6667 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 | Assistant Engineer | Junior Engineer | VCH/002683/2021-2022 | FHTC/2 | 02/03/2022 | 0 | GOUTAM BHOWMIK | 59.53 | 0 | 0
6668 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 4 nos, ( Paharbedia , Bharatpur (PART), Kendna, Shushunia parashibona) Total House Hold - 437 nos. | Assistant Engineer | Junior Engineer | ORD/000095/2021-2022 | 2532/BQA | 23/09/2021 | 30 | BISWARUP BOSE | 26.71 | 26.69 | 0
6669 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 02 nos, ( Jhunka, Bharatpur (Part) Total House Hold - 437 nos. | Assistant Engineer | Junior Engineer | ORD/000163/2021-2022 | 2852/BQA | 16/11/2021 | 30 | SUMIT GHOSH | 26.27 | 14.9 | 0
6670 | Bankura Division | Bankura Sadar Sub-Division | Supplying Fiting Fixing & Laying 160 mm dia. HDPE Pipe from Parasibona air valve point to firm Gate to cover Bharatpur, Gidhuria & Jaljalibansal for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part- A) (under JJM Programme Fund) | Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1318/BQA | 15/06/2022 | 15 | RAHUL CHATERJEE | 4.76 | 0 | 0
6671 | Bankura Division | Bankura Sadar Sub-Division | Supplying Fitting Fixing & Laying 160 mm dia. HDPE Pipe from Parasibona air valve point to firm Gate to cover Bharatpur, Gidhuria & Jaljalibansal for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part- B) (under JJM Programme Fund) | Assistant Engineer | Junior Engineer | ORD/000257/2022-2023 | 1326/BQA | 15/06/2022 | 15 | RAHUL CHATERJEE | 3.42 | 0 | 0
6672 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Jhunjka mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A). | Assistant Engineer | Junior Engineer | ORD/000261/2021-2022 | 804/ BSD | 06/08/2021 | 15 | APEX ENTERPRISE | 4.99 | 0 | 0
6673 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Jhunjka mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of kalipur (Zone- C) under under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B). | Assistant Engineer | Junior Engineer | ORD/000264/2021-2022 | 805/ BSD | 06/08/2021 | 15 | APEX ENTERPRISE | 4.99 | 0 | 0
6674 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Jhunka mouza for retrofitting works for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000643/2021-2022 | 270/BSD | 17/03/2022 | 10 | SUMIT GHOSH | 3.71 | 0 | 0
6675 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover Khabanigoparpur mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna Block of Saltora-Chhatna W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001081/2021-2022 | 1036/BSD | 14/12/2021 | 15 | SRIKANTA MONDAL | 3.18 | 0 | 60
6676 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR(Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 02 nos, ( Jhunka, Bharatpur (Part) Total House Hold - 437 nos. | Assistant Engineer | Junior Engineer | VCH/001383/2022-2023 | FHTC/16 | 16/11/2022 | 0 | SUMIT GHOSH | 10.71 | 0 | 0
6677 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jhunka, Shushunia parasibana, Paharbedia, Bharatpur, Kendua) of KALIPUR (Zone - C) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) | Assistant Engineer | Junior Engineer | VCH/002384/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 40 | 0 | 0
6678 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01( Gosainpur ), Total House Hold - 127 |  | Junior Engineer | ORD/000029/2020-2021 | 631/BQA | 10/02/2021 | 30 | BEAUTY CHATTERJEE | 9.66 | 0 | 0
6679 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Malkururia ,Sonagara ), Total House Hold -124 |  | Junior Engineer | ORD/000030/2020-2021 | 632/BQA | 10/02/2021 | 30 | GOURANGA CHATTERJEE | 9.47 | 0 | 0
6680 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Kaleberia,Saragara ), Total House Hold -163 |  | Junior Engineer | ORD/000031/2020-2021 | 633/BQA | 10/02/2021 | 30 | BEAUTY CHATTERJEE | 12.44 | 0 | 0
6681 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 (Lalbazar (PART-A), Total House Hold - 141 |  | Junior Engineer | ORD/000032/2020-2021 | 634/BQA | 10/02/2021 | 30 | SUBHANKAR BANERJEE | 10.69 | 0 | 0
6682 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 ( Kururia Balarampur , (Lalbazar (PART-B), Total House Hold - 140 |  | Junior Engineer | ORD/000033/2020-2021 | 635/BQA | 10/02/2021 | 30 | GOURANGA CHATTERJEE | 10.62 | 0 | 0
6683 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 (Jharia ,Kalla ), Total House Hold - 133 |  | Junior Engineer | ORD/000034/2020-2021 | 636/BQA | 10/02/2021 | 30 | TAPAS PAL | 10.11 | 0 | 0
6684 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 60. |  | Junior Engineer | ORD/000145/2020-2021 | 24/VSD | 20/01/2021 | 30 | TAPAS KUMAR HAZRA | 4.81 | 9.09 | 0
6685 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line from Soragara Village to Enayetpur village of retrofitting work for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GODARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Barjora, Name of OHR:- GODARDIHI (Zone - E), Name of Mouza:- Enayetpur. |  | Junior Engineer | ORD/000246/2021-2022 | 886/ BSD | 08/09/2021 | 15 | SUBHANKAR BANERJEE | 4.33 | 0 | 0
6686 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
6687 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
6688 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block , Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampu (part) Total House Hold - 453. |  | Junior Engineer | VCH/002809/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GOUTAM BHATTACHRYYA | 27.54 | 0 | 0
6689 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B), No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), (Part-A) |  | Junior Engineer | ORD/000245/2021-2022 | 754/ BSD | 26/07/2021 | 15 | M/S TARUN KUMAR PATRA | 3.85 | 0 | 0
6690 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone- B), No. of Mouza:- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur), (Part- B) |  | Junior Engineer | ORD/000257/2021-2022 | 755/ BSD | 27/07/2021 | 15 | M/S TARUN KUMAR PATRA | 4.85 | 0 | 0
6691 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), Total House Hold -972 |  | Junior Engineer | ORD/000461/2020-2021 | 129/SE/PIU-BANKURA | 24/02/2021 | 30 | M/S TARUN KUMAR PATRA | 82.32 | 0 | 0
6692 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 |  | Junior Engineer | VCH/001732/2021-2022 | FHTC/23 | 23/11/2021 | 0 | M/S BIPUL BANERJEE | 24.12 | 0 | 0
6693 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  | Junior Engineer | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 0 | UNICON INDIA | 75 | 0 | 0
6694 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, sibrampur Total House Hold - 151 |  | Junior Engineer | VCH/002312/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADIP CHAKRABORTY | 11.53 | 0 | 0
6695 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 02 churamonipur & bambhanpur Total House Hold - 124 ( Sl .No.-23) |  | Junior Engineer | VCH/002313/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADIP CHAKRABORTY | 9.22 | 0 | 0
6696 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  | Junior Engineer | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 0 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0
6697 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra HDPE pipeline to cover Madandihi(101) & Malcharar (100) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) |  | Junior Engineer | VCH/002319/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SUBHADIP KOLEY | 3.99 | 0 | 0
6698 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 05) |  | Junior Engineer | VCH/002320/2021-2022 | FHTC/20 | 20/01/2022 | 0 | SUBHADIP KOLEY | 4.2 | 0 | 0
6699 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) |  | Junior Engineer | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0
6700 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | VCH/002379/2021-2022 | FHTC/19 | 19/02/2022 | 0 | PRADYUMNA KOLEY | 4.71 | 0 | 0
6701 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipeline to cover Ghagra (115) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) |  | Junior Engineer | VCH/002380/2021-2022 | FHTC/19 | 19/02/2022 | 0 | SUBHADIP KOLEY | 4.99 | 0 | 0
6702 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (115 out of 714), House Hold - 115 |  | Junior Engineer | VCH/002381/2021-2022 | FHTC/19 | 19/02/2022 | 0 | PRASANTA BHUIN | 8.81 | 0 | 0
6703 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAGDALLA (Zone - S) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla. No.of Mouza :- 04 (Aralbasi, Bansi, Patakola & Debra) Total House Hold - 1164 |  | Junior Engineer | ORD/000407/2020-2021 | 402/BQA | 04/02/2021 | 1882 | M/S TARUN KUMAR PATRA | 79.17 | 0 | 0
6704 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Aral Bansi to Bansi Village to increase pressure in Bansi mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone- S) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000539/2021-2022 | 153/BSD | 16/02/2022 | 15 | BIDHAN BANERJEE | 4.73 | 4.71 | 0
6705 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No of Mouza:- Dhaban, (part) Total House Hold - 67 |  | Junior Engineer | VCH/001174/2021-2022 | FHTC/23 | 23/07/2021 | 0 | MR. DURGADAS SINGHA | 3.75 | 0 | 0
6706 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No of Mouza:- Dhaban, (part) Total House Hold - 67 |  | Junior Engineer | VCH/001176/2021-2022 | FHTC/23 | 23/07/2021 | 0 | RAHUL CHATERJEE | 3.79 | 0 | 0
6707 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR:- Dhaban (PART-) , Total House Hold - 67. |  | Junior Engineer | VCH/001178/2021-2022 | FHTC/23 | 23/07/2021 | 0 | ACHARJEE & SON | 4.14 | 0 | 0
6708 | Bankura Division | Bankura Sadar Sub-Division | Household Survey of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla, Anchuri, Chaturdihi, Andharthol & Kustora. No.of Mouza :- 114 Total House Hold - 15724. |  | Junior Engineer | VCH/001351/2021-2022 |  | 28/09/2021 | 0 | TAPAS DEY | 2.02 | 0 | 0
6709 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., |  | Junior Engineer | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 | 0 | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0
6710 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola & Debra)) of JAGDALLA OHR (Zone - S) |  | Junior Engineer | VCH/002390/2021-2022 | FHTC/21 | 21/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 4.05 | 0 | 0
6711 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 05 Nos. Total Household - 853 Nos. ' |  | Junior Engineer | VCH/002506/2021-2022 | FHTC/3 | 03/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 43 | 0 | 0
6712 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover 15 mm NB PVC to cover Gopinathdihi, Namabad mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora - Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002900/2021-2022 | FHTC/17 | 17/03/2022 | 0 | ASHIS PAL | 2.43 | 0 | 0
6713 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to increase pressure at Dangarpara (293) Agaya (350) mouza for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Gargarya (Zone - A) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002908/2021-2022 | FHTC/21 | 21/03/2022 | 0 | PRADYUMNA KOLEY | 3.28 | 0 | 0
6714 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000296/2020-2021 | 1419/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 36.53 | 0 | 20
6715 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000297/2020-2021 | 1420/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 28.21 | 0 | 20
6716 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000298/2020-2021 | 1421/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 30.11 | 0 | 20
6717 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Lakshmisagar (43) mouza to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 35) | Assistant Engineer | Junior Engineer | ORD/000538/2020-2021 | 277/KSD | 10/12/2020 | 62 | M/S TARUN KUMAR PATRA | 0.47 | 0 | 0
6718 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) | Assistant Engineer | Junior Engineer | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 0 | EARTHMOVING (INDIA) | 27.48 | 0 | 0
6719 | Bankura Division | Khatra Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Panchal (Zone - ll) under Bishnupur Sub - Division of Bankura Division, PHE Dte. part -B block - Sonamukhi , ..Total House Hold -69 ( MB No - 3313)" | Assistant Engineer | Junior Engineer | VCH/001436/2020-2021 | FHTC/284 | 03/03/2021 | 0 | BIJOY KOLEY | 4.6 | 0 | 0
6720 | Bankura Division | Khatra Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - C) ( MB No - 3946) | Assistant Engineer | Junior Engineer | VCH/001530/2020-2021 | FHTC/260 | 04/02/2021 | 0 | M/S TARUN KUMAR PATRA | 22.8 | 0 | 0
6721 | Bankura Division | Khatra Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - A) ( MB No - 3945) | Assistant Engineer | Junior Engineer | VCH/001533/2020-2021 | FHTC/260 | 04/02/2021 | 0 | M/S TARUN KUMAR PATRA | 21.68 | 0 | 0
6722 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280) & Dharampur (281) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3954) | Assistant Engineer | Junior Engineer | VCH/001553/2020-2021 | FHTC/283 | 22/02/2021 | 0 | MUNMUN UPADHYAY | 24.45 | 0 | 0
6723 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from BANKATI Main Road to Radharamanpur Village to increase presure in Radharamanpur mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (ZONE-R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000006/2022-2023 | 894/BQA | 18/04/2022 | 30 | SOUMITRA KUMAR DAS | 10.04 | 10.02 | 0
6724 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000218/2021-2022 | 818/BSD | 06/08/2021 | 15 | BISWARUP BOSE | 3.02 | 0 | 0
6725 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000219/2021-2022 | 819/BSD | 06/08/2021 | 15 | PRANABANANDA TEWARI | 2.84 | 0 | 0
6726 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos, (Duyaranda, Kelebela), Total House Hold - 422." |  | Junior Engineer | ORD/000330/2020-2021 | 1377/BQA | 08/10/2020 | 30 | SOUMITRA BOSE | 27.89 | 0 | 100
6727 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos, (Ramdihi, Choto Kalajharia, Radharaman Pur, Barokalojuria, ), Total House Hold - 429." |  | Junior Engineer | ORD/000331/2020-2021 | 1378/BQA | 08/10/2020 | 30 | BISWARUP BOSE | 28.47 | 0 | 100
6728 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos, (Roybandh), Total House Hold - 168." |  | Junior Engineer | ORD/000332/2020-2021 | 1387/BQA | 09/10/2020 | 30 | PRANABANANDA TEWARI | 11.62 | 0 | 100
6729 | Bankura Division | Bankura Sadar Sub-Division | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03 nos, (Gajariabari, Maslia, Chaitali), Total House Hold - 167." |  | Junior Engineer | ORD/000333/2020-2021 | 1386/BQA | 09/10/2020 | 30 | SHYAMAL KUMAR DAS | 11.58 | 0 | 100
6730 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Duyaranda, Kelebela mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI(Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000432/2020-2021 | 139/ BSD | 18/02/2021 | 10 | SOUMITRA BOSE | 4.84 | 0 | 0
6731 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra UPVC Pipe Line to Cover Roybandh, Bankati mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000490/2020-2021 | 141/BSD | 18/02/2021 | 10 | PRANABANANDA TEWARI | 4.39 | 0 | 0
6732 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 |  | Junior Engineer | VCH/002316/2021-2022 | FHTC/20 | 20/01/2022 | 0 | I.R.CONSTRUCTION | 9.24 | 0 | 0
6733 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) |  | Junior Engineer | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0
6734 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART- B) |  | Junior Engineer | VCH/002371/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.77 | 0 | 0
6735 | Bankura Division | Bankura Sadar Sub-Division | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART-A) |  | Junior Engineer | VCH/002372/2021-2022 | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0
6736 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | VCH/002598/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 29.87 | 0 | 0
6737 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) |  | Junior Engineer | VCH/002600/2021-2022 | FHTC/26 | 26/02/2022 | 0 | UNITED TRADERS | 2.37 | 0 | 0
6738 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Sirsha Nutanpally to Palsona more under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Sirsha, Palsona. |  | Junior Engineer | VCH/002602/2021-2022 | FHTC/26 | 26/02/2022 | 0 | M/S T.P. HAZRA & SONS | 3.48 | 0 | 0
6739 | Bankura Division | Bankura Sadar Sub-Division | "Laying extra HDPE pipe line to cover Jantadumur(178) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') by retrofitting Zone-L (Dhankura) of Khatra- Hirbandh-Ranibandh Water Supply scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under JAL SWAPNA & vJal Jeevan Mission (JJM) Programme under Khatra Sub - Division of Bankura Division, PHE Dte. " |  | Junior Engineer | VCH/002604/2021-2022 | FHTC/26 | 26/02/2022 | 0 | UNITED TRADERS | 4.55 | 0 | 0
6740 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rajadali (156), Sibarampur (157), Loadihi (158), Satsol (160), Sarga (161), Jhanti Pahari (162) & Sunrigara (163) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 07 Nos. Total Household - 149 Nos.' |  | Junior Engineer | VCH/002605/2021-2022 | FHTC/26 | 26/02/2022 | 0 | ROY CHOWDHURY ENTERPRISE | 0.54 | 0 | 0
6741 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 0 1 , Sangrampur (Part-B), Total House Hold 124 (Sl .No.- 9) |  | Junior Engineer | VCH/002606/2021-2022 | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.38 | 0 | 0
6742 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 ,Gadardihi (PART-B ), Total House Hold - 115 |  | Junior Engineer | VCH/002607/2021-2022 | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.34 | 0 | 0
6743 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ramchandrapur (5) & Nutangar (34) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000299/2020-2021 | 1422/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 31.87 | 1.84 | 20
6744 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbakra (35) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2020-2021 | 1423/BQA | 09/10/2020 | 30 | APEX ENTERPRISE | 34.84 | 3.38 | 0
6745 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Ramchandrapur (5), Nutangar (34) & Junbakra (35) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 36) | Assistant Engineer | Junior Engineer | ORD/000539/2020-2021 | 278/KSD | 10/12/2020 | 62 | M/S TARUN KUMAR PATRA | 0.31 | 0 | 0
6746 | Bankura Division | Khatra Sub-Division | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Ramchandrapur (5) & Nutangar (34) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. ( MB No - 3947) | Assistant Engineer | Junior Engineer | VCH/001532/2020-2021 | FHTC/260 | 04/02/2021 | 0 | M/S TARUN KUMAR PATRA | 19.64 | 0 | 0
6747 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 |  | Junior Engineer | ORD/000016/2020-2021 | 618/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.35 | 0 | 100
6748 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 |  | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 0 | 0
6749 | Bankura Division | Bankura Sadar Sub-Division | Supplying, laying, fiting , fixing , and joining of UPVC pipes in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol Zone - V W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Bankura - l Name of OHR - Andharthol, name of village - Andharthol (village) |  | Junior Engineer | VCH/000584/2022-2023 |  | 22/07/2022 | 0 | TARINI CHARAN UPADHYAY | 4.6 | 0 | 0
6750 | Bankura Division | Bankura Sadar Sub-Division | Supplying, laying, fiting , fixing , and joining of UPVC pipes in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol Zone - V W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Bankura - l Name of OHR - Andharthol, name of village - Andharthol (school more) |  | Junior Engineer | VCH/000585/2022-2023 |  | 22/07/2022 | 0 | TARINI CHARAN UPADHYAY | 4.21 | 0 | 0
6751 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. |  | Junior Engineer | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0
6752 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Sonadaha (Zone - Q ) under Bankura l, ll & & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . Block - Bankura l, Name of OHR - Sonadaha (Zone - Q0 No.of Mouza :- 01 no, ( Bagatapal ) part - Total House Hold - 31 nos. |  | Junior Engineer | VCH/003092/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PRADIP CHAKRABORTY | 2.61 | 0 | 0
6753 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), & Domohani (154) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | VCH/003094/2021-2022 | FHTC/30 | 30/03/2022 | 0 | PRADIP CHAKRABORTY | 2.22 | 0 | 0
6754 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 |  | Junior Engineer | VCH/003099/2021-2022 | FHTC/30 | 30/03/2022 | 0 | MUNMUN UPADHYAY | 35.35 | 0 | 0
6755 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2022-2023 | 919/BQA | 19/04/2022 | 30 | GON ASSOCIATES | 8 | 0 | 0
6756 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2020-2021 | 199/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 38.78 | 48.01 | 0
6757 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2020-2021 | 175/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 16.09 | 0 | 0
6758 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000118/2020-2021 | 176/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.82 | 0 | 50
6759 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000120/2020-2021 | 177/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.82 | 0 | 100
6760 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000121/2020-2021 | 178/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.68 | 0 | 50
6761 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000122/2020-2021 | 179/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 10.47 | 0 | 0
6762 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000124/2020-2021 | 181/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 10.39 | 0 | 0
6763 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000226/2021-2022 | 3086/BQA | 13/12/2021 | 30 | SUBHANKAR BANERJEE | 15.9 | 0 | 95
6764 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 1282/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 4.69 | 0 | 0
6765 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 21) | Assistant Engineer | Junior Engineer | ORD/000238/2022-2023 | 1300/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.77 | 0 | 0
6766 | Bankura Division | Khatra Sub-Division | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 24) | Assistant Engineer | Junior Engineer | ORD/000239/2022-2023 | 1303/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.06 | 0 | 0
6767 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000271/2021-2022 | 3180/BQA | 21/12/2021 | 30 | I.R.CONSTRUCTION | 18.4 | 15.77 | 95
6768 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) & Deuli (25) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000385/2021-2022 | 769/KSD | 25/11/2021 | 7 | SUBHANKAR BANERJEE | 4.9 | 0 | 0
6769 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000458/2020-2021 | 117/KSD | 11/02/2021 | 20 | SUBHANKAR BANERJEE | 4.76 | 0 | 0
6770 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000459/2020-2021 | 118/KSD | 11/02/2021 | 20 | SUBHANKAR BANERJEE | 4.05 | 0 | 0
6771 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 17) | Assistant Engineer | Junior Engineer | ORD/000524/2020-2021 | 322/KSD | 29/12/2020 | 61 | SUBHANKAR BANERJEE | 0.4 | 0 | 0
6772 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | VCH/001576/2020-2021 |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 9.65 | 0 | 0
6773 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/001577/2020-2021 |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 15.02 | 0 | 0
6774 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer | Junior Engineer | VCH/001578/2020-2021 |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 9.49 | 0 | 0
6775 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | VCH/001581/2020-2021 |  | 15/03/2021 | 0 | PRADIP CHAKRABORTY | 9.31 | 0 | 0
6776 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | Assistant Engineer | Junior Engineer | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0
6777 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003039/2021-2022 | FHTC/27 | 27/03/2022 | 0 | I.R.CONSTRUCTION | 4.78 | 0 | 0
6778 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Lalbazar (24 ), mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting of water supply scheme for Belatikri zone - Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/003061/2021-2022 | FHTC/30 | 30/03/2022 | 0 | I.R.CONSTRUCTION | 2.85 | 0 | 0
6779 | Bankura Division | Bankura Sadar Sub-Division | Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone -C of Puncha &Zone -E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone -C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254) .No of House Hold - 2986 nos ).( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55) .No of House Hold - 4107 nos.). Total No of House Hold = ( 2986 nos +4107 nos ) =7093. Nos |  | Junior Engineer | ORD/000024/2022-2023 | 1083/BQA | 12/05/2022 | 1389 | M/S TARUN KUMAR PATRA | 216.67 | 151.2 | 76
6780 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone- C of Puncha & Zone- E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone- C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254).No of House Hold - 2986 nos ). ( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55). No of House Hold- 4107 nos.). Total No of House Hold = (2986 nos + 4107 nos )= 7093. Nos. |  | Junior Engineer | ORD/000905/2021-2022 | 107/BSD | 28/01/2022 | 59 | TAPAS DEY | 2.37 | 1.2 | 0
6781 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000022/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 0.04 | 0 | 0
6782 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 02 no., Majit ( Part), Singhir (Part), Total House Hold - 20 nos. | Assistant Engineer | Junior Engineer | ORD/000042/2022-2023 | 462/BSD | 06/06/2022 | 10 | MD. AFSAR ALI | 1.66 | 0 | 0
6783 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Dahuka village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE- II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000118/2022-2023 | 458/BSD | 06/06/2022 | 15 | GOURANGA CHATTERJEE | 3.75 | 0 | 0
6784 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -(II), Name of Mouza:-- 1 no., (Salma), Total House Hold - 881 nos. | Assistant Engineer | Junior Engineer | ORD/000134/2021-2022 | 2799/BQA | 11/11/2021 | 30 | DAUD ALI KHAN | 38.77 | 38.77 | 0
6785 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 1 no., (Kamalhir), Total House Hold - 344 nos. | Assistant Engineer | Junior Engineer | ORD/000135/2021-2022 | 2800/BQA | 11/11/2021 | 30 | JAGADISH BANERJEE | 16.69 | 16.68 | 0
6786 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos. | Assistant Engineer | Junior Engineer | ORD/000138/2021-2022 | 2801/BQA | 11/11/2021 | 30 | ACHARJEE & SON | 12.25 | 0 | 0
6787 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 1 no., (Dahuka), Total House Hold - 277 nos. | Assistant Engineer | Junior Engineer | ORD/000139/2021-2022 | 2802/BQA | 11/11/2021 | 30 | GOURANGA CHATTERJEE | 13.68 | 8.89 | 0
6788 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe to cover Bhuban Bandi, Swattwakuri mouza for retrofitting works for creation of FHTC in connection with Jal Jeevan Mission Programme and Jal Swapna of Salma Zone -II W/S Scheme | Assistant Engineer | Junior Engineer | VCH/000553/2022-2023 |  | 18/07/2022 | 0 | GOUTAM GHOSH | 2.29 | 0 | 0
6789 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 3 nos, (Bhuban Bandi, Swattwakuri, Saltura), Total House Hold - 273 nos. | Assistant Engineer | Junior Engineer | ORD/000140/2021-2022 | 2803/BQA | 11/11/2021 | 30 | GOUTAM GHOSH | 13.5 | 13.49 | 0
6790 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 2 no., (Bhangucha , Illambajar), Total House Hold - 264 nos. | Assistant Engineer | Junior Engineer | ORD/000141/2021-2022 | 2804/BQA | 11/11/2021 | 30 | PARESH CHANDRA LAYEK | 12.67 | 12.67 | 0
6791 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 1 no., (Beltikri), Total House Hold - 242 nos. | Assistant Engineer | Junior Engineer | ORD/000150/2021-2022 | 2830/BQA | 16/11/2021 | 30 | M/S SUPRIYA CHATTERJEE | 11.6 | 11.59 | 0
6792 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. | Assistant Engineer | Junior Engineer | ORD/000151/2021-2022 | 2831/BQA | 16/11/2021 | 30 | TAPAS KUMBHAKAR | 16.02 | 0 | 0
6793 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000151/2022-2023 | 541/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0
6794 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 03 nos, (Chandbad, Chaukhuri, Singhir), Total House Hold - 257 nos. | Assistant Engineer | Junior Engineer | ORD/000152/2021-2022 | 2832/BQA | 16/11/2021 | 30 | GANGADHAR MONDAL | 12.17 | 12.17 | 0
6795 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 02 no., (Kechka, Chuaberia), Total House Hold - 483 nos. | Assistant Engineer | Junior Engineer | ORD/000153/2021-2022 | 2833/BQA | 16/11/2021 | 30 | SRIKANTA MONDAL | 22.08 | 22.08 | 0
6796 | Bankura Division | Bankura Sadar Sub-Division | Dismantaling & reconstruction of Kastora, Singhir & Majit mouza & Cleaning Wasing the pipeline from Bhaghucha to kechka for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 543/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.14 | 0 | 0
6797 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 01 no., (Majit), Total House Hold - 175 nos. | Assistant Engineer | Junior Engineer | ORD/000154/2021-2022 | 2834/BQA | 16/11/2021 | 30 | MD. AFSAR ALI | 7.96 | 0 | 0
6798 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:- 01 no., (Harakabad), Total House Hold - 174 nos. | Assistant Engineer | Junior Engineer | ORD/000155/2021-2022 | 2835/BQA | 16/11/2021 | 30 | RAHUL CHATERJEE | 6.51 | 6.51 | 0
6799 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Majit mouza and dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2022-2023 | 560/BSD | 29/07/2022 | 21 | MD. AFSAR ALI | 3.57 | 0 | 0
6800 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line from OHR Zone II to Dahuka village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000228/2022-2023 | 561/ BSD | 29/07/2022 | 21 | DAUD ALI KHAN | 4.92 | 0 | 0
6801 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC /HDPE Pipe Line to cover Dahuka village interconnection with house connection pipe & Dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000229/2022-2023 | 562/ BSD | 29/07/2022 | 21 | DAUD ALI KHAN | 0.71 | 0.71 | 0
6802 | Bankura Division | Bankura Sadar Sub-Division | Restoration & renovation 100 mm dia connecting line carrying structure including all related works & Clearing the chokage of upvc line Durlavpur to Bhubanbadhi, interconnection with BRGF Line for W/S arrangement at Salma Zone- III including contruction of valve chamber at Salma zone-II Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 469/BSD | 06/06/2022 | 15 | DAUD ALI KHAN | 4.95 | 0 | 0
6803 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Dahuka, Gopalnagar, Total House Hold- 43 nos. | Assistant Engineer | Junior Engineer | ORD/000462/2021-2022 | 222/BSD | 11/03/2022 | 10 | DAUD ALI KHAN | 3.88 | 3.14 | 0
6804 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | Assistant Engineer | Junior Engineer | ORD/000463/2021-2022 | 223/BSD | 11/03/2022 | 10 | SAMIRUDDIN KHAN | 4.98 | 0 | 0
6805 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 02 no., (Bakulia & Sahebdanga) Total House Hold- 70 nos. | Assistant Engineer | Junior Engineer | ORD/000479/2021-2022 | 253/BSD | 15/03/2022 | 10 | BASUDEB ACHARJEE | 4.96 | 0 | 0
6806 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Kukrakuli), Total House Hold- 67 nos. | Assistant Engineer | Junior Engineer | ORD/000481/2021-2022 | 218/BSD | 11/03/2022 | 10 | TAPAS KUMBHAKAR | 3.8 | 3.8 | 0
6807 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. | Assistant Engineer | Junior Engineer | ORD/000492/2021-2022 | 224/BSD | 11/03/2022 | 10 | M/S SUPRIYA CHATTERJEE | 4.57 | 4.25 | 0
6808 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover Bakulia & Sahebdanga mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - II W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000497/2021-2022 | 234/BSD | 15/03/2022 | 10 | ACHARJEE & SON | 3.32 | 3.32 | 0
6809 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover (Bhuban Bandi, Swattwakuri, Saltura), mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000501/2021-2022 | 252/BSD | 15/03/2022 | 10 | GOUTAM GHOSH | 2.34 | 2.29 | 0
6810 | Bankura Division | Bankura Sadar Sub-Division | Water supply arrangement at different school of Salma & Cleaning of Chokage Existing pipelinefrom Kastora Bouripara to Muslimpara & Bhangucha to Beltukri of Salma (Zone I & III) under Salma W/S Scheme of Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2021-2022 | 810/BSD | 06/08/2021 | 10 | TAPAN KUMAR MANDAL | 2.94 | 0 | 0
6811 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC Pipe Line to Cover , (Bhangucha , Illambajar), mouza & Dismantling & reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte . | Assistant Engineer | Junior Engineer | ORD/000567/2021-2022 | 279/BSD | 17/03/2022 | 10 | PARESH CHANDRA LAYEK | 4.32 | 4.22 | 0
6812 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. | Assistant Engineer | Junior Engineer | ORD/000612/2021-2022 | 224/BSD | 11/03/2022 | 10 | M/S SUPRIYA CHATTERJEE | 4.57 | 0 | 0
6813 | Bankura Division | Bankura Sadar Sub-Division | Laying of 15 mm NB PVC (schedule 80) /20 mm OD HDPE (PE100, Pn16) to Cover Salma mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000635/2021-2022 | 281/BSD | 17/03/2022 | 10 | DAUD ALI KHAN | 1.58 | 1.55 | 0
6814 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000636/2021-2022 | 164/BSD | 16/02/2022 | 10 | DAUD ALI KHAN | 2.6 | 0 | 0
6815 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line & extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2021-2022 | 273/BSD | 17/03/2022 | 10 | SK. SAHAJAHAN | 3.63 | 0 | 0
6816 | Bankura Division | Bankura Sadar Sub-Division | Laying HDPE Pipe Line from Durlavpur air valve to Durlavpur Muslim para for increase water pressure at Swattkuri, Kamalhir, Durlavpu for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000976/2022-2023 | 566/BSD | 29/07/2022 | 21 | JAGADISH BANERJEE | 3.35 | 0 | 0
6817 | Bankura Division | Bankura Sadar Sub-Division | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - NOT Name of Mouza:-- Ekteswar (Part) & Sankardihi, Total House Hold - 452 nos. | Assistant Engineer | Junior Engineer | VCH/000251/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.15 | 0 | 0
6818 | Bankura Division | Bankura Sadar Sub-Division | Survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 20 nos, (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, Swattwakuri, Harakabad Kukirakuri, Chandbad Chaukhuri, Singhir, Majit, Bhanguch , Illambajar, Barasal, Kechka, Chuaberia, Beltikri), Total House Hold - 3957 nos. | Assistant Engineer | Junior Engineer | VCH/000257/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 1.13 | 0 | 0
6819 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipeline to cover Kechka & Chuaberia mouzas for retrofitting works 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I ) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000646/2022-2023 | FHTC/14 | 14/07/2022 | 0 | SRIKANTA MONDAL | 3.81 | 0 | 0
6820 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos | Assistant Engineer | Junior Engineer | VCH/000726/2022-2023 | FHTC/12 | 12/08/2022 | 0 | ACHARJEE & SON | 12.25 | 0 | 0
6821 | Bankura Division | Bankura Sadar Sub-Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Harakabad of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Ba | Assistant Engineer | Junior Engineer | VCH/001209/2022-2023 | FHTC/15 | 15/09/2022 | 0 | RAHUL CHATERJEE | 2.05 | 0 | 0
6822 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 19 | Assistant Engineer | Junior Engineer | VCH/001227/2022-2023 | FHTC/27 | 27/09/2022 | 0 | DAUD ALI KHAN | 1.72 | 0 | 0
6823 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | Assistant Engineer | Junior Engineer | VCH/001228/2022-2023 | FHTC/27 | 27/09/2022 | 0 | SAMIRUDDIN KHAN | 4.97 | 0 | 0
6824 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipeline from OHR Zone- III to Kendana village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001536/2022-2023 | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.68 | 0 | 0
6825 | Bankura Division | Bankura Sadar Sub-Division | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0
6826 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002565/2021-2022 | FHTC/26 | 26/02/2022 | 0 | PARAMESWAR CHOWDHURY | 47.88 | 0 | 0
6827 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 02 ( Bahadur pur , Oltara(PART-A), Total House Hold -141 | Assistant Engineer | Junior Engineer | VCH/002567/2021-2022 | FHTC/26 | 26/02/2022 | 0 | RUFIKUL MONDAL | 9.81 | 0 | 0
6828 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 | Assistant Engineer | Junior Engineer | VCH/002569/2021-2022 | FHTC/26 | 26/02/2022 | 0 | RUFIKUL MONDAL | 10.75 | 0 | 0
6829 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Beltikri mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/002938/2021-2022 | FHTC/23 | 23/03/2022 | 0 | M/S SUPRIYA CHATTERJEE | 2.98 | 0 | 0
6830 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe lineto cover Chandbad , Chaukhuri, Singhir Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA Salma (Zone - l ) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . | Assistant Engineer | Junior Engineer | VCH/003002/2021-2022 | FHTC/26 | 26/03/2022 | 0 | GANGADHAR MONDAL | 0.74 | 0 | 0
6831 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003003/2021-2022 | FHTC/26 | 26/03/2022 | 0 | DAUD ALI KHAN | 4.07 | 0 | 0
6832 | Bankura Division | Bankura Sadar Sub-Division | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003004/2021-2022 | FHTC/26 | 26/03/2022 | 0 | DAUD ALI KHAN | 4.74 | 0 | 0
6833 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Horakabaid mouzas Retrofitting works for creation 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Salma Zone - l under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003081/2021-2022 | FHTC/30 | 30/03/2022 | 0 | RAHUL CHATERJEE | 2.52 | 0 | 0
6834 | Bankura Division | Bankura Sadar Sub-Division | laying extra UPVC pipe line to cover Kamalhit mouzas Construction and commissioning of of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/003085/2021-2022 | FHTC/30 | 30/03/2022 | 0 | SOMA BANERJEE | 4.51 | 0 | 0
6835 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas, (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IV) Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE- IV), No. of Mouza :- 03 nos, (Sahorjora, Namobandh Sitarampur, Muktatore), Total House Hold -1096 nos | Assistant Engineer | Junior Engineer | ORD/000128/2021-2022 | 2793/BQA | 11/11/2021 | 30 | APEX ENTERPRISE | 63.39 | 63.37 | 0
6836 | Bankura Division | Bankura Sadar Sub-Division | Supply of VALVE including loading, unloading, stacking etc. all comlete for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas Sahorjora ,Dejuri, Asuria Madhabpur , Namobandh Sitarampur,Muktatore , Deucha) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/000186/2022-2023 | 346/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.95 | 4.95 | 0
6837 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos Mouzas, (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IV) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IV), No.of Mouza :- 03 nos, (Dejuri, Asuria Madhabpur, Deucha), Total House Hold - 594 nos. | Assistant Engineer | Junior Engineer | ORD/000189/2021-2022 | 2990/BQA | 25/11/2021 | 30 | GOUTAM BHATTACHRYYA | 34.31 | 34.28 | 0
6838 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IV). No.of Mouza :- 06 nos, (Sahorjora , Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), Total House Hold - 1690 nos. | Assistant Engineer | Junior Engineer | VCH/000255/2022-2023 | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.56 | 0 | 0
6839 | Bankura Division | Bankura Sadar Sub-Division | Extra UPVC pipe line from Soragara Village to Enayetpur village of retrofitting work for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GODARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Barjora, Name of OHR:- GODARDIHI (Zone - E), Name of Mouza:- Enayetpur. | Assistant Engineer | Junior Engineer | VCH/002583/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SUBHANKAR BANERJEE | 4.32 | 0 | 0
6840 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | VCH/002584/2021-2022 | FHTC/24 | 24/02/2022 | 0 | SANJOY MONDAL | 0.23 | 0 | 0
6841 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) | Assistant Engineer | Junior Engineer | VCH/002586/2021-2022 | FHTC/24 | 24/02/2022 | 0 | DAUD ALI KHAN | 3.51 | 0 | 0
6842 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 02 nos (Pinguri (Part-C) &Tentuldoha ), Total House Hold -249 | Assistant Engineer | Junior Engineer | VCH/002590/2021-2022 | FHTC/24 | 24/02/2022 | 0 | BEAUTY CHATTERJEE | 1.32 | 0 | 0
6843 | Bankura Division | Bankura Sadar Sub-Division | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), and Ganganala (230) mouzas Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002591/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TARINI CHARAN UPADHYAY | 4.98 | 0 | 0
6844 | Bankura Division | Bankura Sadar Sub-Division | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 | Assistant Engineer | Junior Engineer | VCH/002592/2021-2022 | FHTC/24 | 24/02/2022 | 0 | JAGADISH BANERJEE | 2.99 | 0 | 0
6845 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 (Jharia ,Kalla ), Total House Hold - 133 | Assistant Engineer | Junior Engineer | VCH/002593/2021-2022 | FHTC/24 | 24/02/2022 | 0 | TAPAS PAL | 0.9 | 0 | 0
6846 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 03(Enayetpur , Namoghansara , Ekariya ), Total House Hold - 204 | Assistant Engineer | Junior Engineer | VCH/002594/2021-2022 | FHTC/24 | 24/02/2022 | 0 | AJIT KUMAR PAUL | 1.39 | 0 | 0
6847 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamrepara (295) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 285 Nos. | Assistant Engineer | Junior Engineer | VCH/002595/2021-2022 | FHTC/24 | 24/02/2022 | 0 | ASHIS PAL | 10.97 | 0 | 0
6848 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baranimdiha (13) and Rajabandh (15) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002596/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GANGADHAR MONDAL | 10.83 | 0 | 0
6849 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Chandar Shib mondir Namo Para & Brimhon para Total House Hold -50. | Assistant Engineer | Junior Engineer | VCH/002597/2021-2022 | FHTC/24 | 24/02/2022 | 0 | M/S PAUL BROTHERS | 0.36 | 0 | 0
6850 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Sonareka (Part), Total House Hold- 70 (Sl No of Work- 10) | Assistant Engineer | Junior Engineer | VCH/002599/2021-2022 | FHTC/24 | 24/02/2022 | 0 | MANOJ GHOSAL | 0.2 | 0 | 0
6851 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- C), Total House Hold -106 | Assistant Engineer | Junior Engineer | VCH/002601/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOURANGA NANDI | 0.77 | 0 | 0
6852 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ,Jagannath pur (Part- B), Total House Hold -107 | Assistant Engineer | Junior Engineer | VCH/002603/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOURANGA NANDI | 0.85 | 0 | 0
6853 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kalipur (Zone- C) under Chatna Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Kalipur (Zone - C) . No.of Mouza :- 03 ( Nangla, Gidhuria, Majdihi) Total House Hold -436 | Assistant Engineer | Junior Engineer | VCH/002609/2021-2022 | FHTC/24 | 24/02/2022 | 0 | GOUTAM BHATTACHRYYA | 14.34 | 0 | 0
6854 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2021-2022 | 2768/BQA | 08/11/2021 | 30 | UNIVERSAL CONSTRUCTION | 42.15 | 7.68 | 0
6855 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000467/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.29 | 0 | 0
6856 | Bankura Division | Khatra Sub-Division | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Patrasayer Sub-District Water Testing Laboratory under Bankura Division, PHE Dte. Sl no.- 05 | Assistant Engineer | Junior Engineer | VCH/002472/2021-2022 | FHTC/15 | 15/02/2022 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.83 | 0 | 0
6857 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002759/2021-2022 | FHTC/4 | 04/03/2022 | 0 | SOUMITRA BHATTACHARYA | 43.3 | 0 | 0
6858 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | Assistant Engineer | Junior Engineer | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0
6859 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | VCH/002888/2021-2022 |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0
6860 | Bankura Division | Khatra Sub-Division | laying extra UPVC pipe line to cover Kadamahara (54 ), Mayna (55) ,Gobindapur Damdi (56) Sirsa ( 131) & Baramaliara (132) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting of water supply scheme for Belatikri zone - B and its adjoning mouzas under Sarenga Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | Assistant Engineer | Junior Engineer | VCH/003059/2021-2022 | FHTC/30 | 30/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 2.9 | 0 | 0
6861 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line from Jagannath more to Tegori & Bankura-Purulia main road (NH-60) to Gholgora to increase water pressure at Gholgora, Teghori mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 1338/BQA | 01/06/2023 | 670 | SUNIL KUMAR MANDAL | 8.49 | 0 | 5
6862 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No. of Mouza :- 7 nos, (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Bansura, Naoadihi) Total House Hold - 1960 nos. | Assistant Engineer | Junior Engineer | ORD/000247/2021-2022 | 3360/BQA | 31/12/2021 | 60 | PARAMESWAR CHOWDHURY | 90.29 | 90.23 | 0
6863 | Bankura Division | Bankura Sadar Sub-Division | Construction of S.S.P including laying of P.V.C extension pipe Line at Tegori Hari Mandir to Namapara & Golgora Bouripara of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000625/2021-2022 | 691/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 4.91 | 0 | 0
6864 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block Saltora- Chhatn W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No.of Mouza :- 07 nos, (Gholgora, Teghori, Bagjuri,Dardali, Kendsaer, Niasa Naoadihi), Total House Hold - 1960 nos. | Assistant Engineer | Junior Engineer | ORD/000876/2021-2022 | 74/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.65 | 0.6 | 99
6865 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Gholgora, Naoadihi mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000966/2022-2023 | 341/KSD | 16/08/2022 | 20 | PARAMESWAR CHOWDHURY | 3.97 | 3.84 | 0
6866 | Bankura Division | Brishnupur Sub-Division | Submission of bill from 01.06.23 to 31.08.23 with running details regarding hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/02188/2023-2024 | FHTC/11 | 29/11/2023 | 0 | TAPAN KUMAR UPADHYAY | 1.01 | 0 | 0
6867 | Bankura Division | Brishnupur Sub-Division | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.06.2023 to 30.11.2023 | Assistant Engineer | Junior Engineer | BILL/02534/2023-2024 | FHTC/02 | 29/02/2024 | 0 | TAPAN KUMAR UPADHYAY | 1.1 | 0 | 0
6868 | Bankura Division | Brishnupur Sub-Division | Extra Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)'at different school, ICDS, health centre and House Holds in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal zone - A and Kushmuri zone -A (BRGF ph- I) W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2022-2023 | 113/VSD | 19/04/2022 | 21 | MANORANJAN GHOSH | 4.84 | 4.83 | 0
6869 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mangalpur, No. of Mouza :- 12 nos. i.e. Jashdighi-96, Behar-103, Parikkhapara-104, Maheshpur-105, Bagajal-106, Bhurbandi-107, Gowalapuskarini-108, Mangalpur-109 & Jadupur-110, Betanal-111, Kishorekona-115 & Baktarpur-116, Total House Hold - 3399 | Assistant Engineer | Junior Engineer | ORD/000032/2022-2023 | 1175/BQA | 25/05/2022 | 60 | KHAN ENTERPRISE | 316.87 | 246.8 | 0
6870 | Bankura Division | Brishnupur Sub-Division | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.06.2023 to 30.11.2023 | Assistant Engineer | Junior Engineer | ORD/000251/2023-2024 | 134VSD | 30/05/2023 | 184 | TAPAN KUMAR UPADHYAY | 0.86 | 0 | 25
6871 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/08/2024 to 31/08/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2024-2025 | 412/VSD | 19/07/2024 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0
6872 | Bankura Division | Brishnupur Sub-Division | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.08.2024 to 31.01.2025. | Assistant Engineer | Junior Engineer | ORD/000332/2024-2025 | 431/VSD | 31/07/2024 | 184 | TAPAN KUMAR UPADHYAY | 0.88 | 2.17 | 0
6873 | Bankura Division | Brishnupur Sub-Division | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.08.2024 to 31.01.2025. | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 432/VSD | 31/07/2024 | 184 | SWAPAN KUMAR BIT | 0.88 | 2.27 | 0
6874 | Bankura Division | Brishnupur Sub-Division | Continuation of Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.02.2023 to 31.07.2023. | Assistant Engineer | Junior Engineer | ORD/000474/2022-2023 | 11/VSD | 30/01/2023 | 181 | SWAPAN KUMAR BIT | 0.86 | 1.89 | 100
6875 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/09/2024 to 30/09/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 472/VSD | 21/08/2024 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0
6876 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/05/2025 to 31/05/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2025-2026 | 175/A/VSD | 23/04/2025 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0
6877 | Bankura Division | Brishnupur Sub-Division | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division, PHE Dte. for the period from 01/08/2023 to 31/01/2024. (Sl. No.: 01) | Assistant Engineer | Junior Engineer | ORD/000666/2023-2024 | 226/VSD | 01/08/2023 | 156 | SWAPAN KUMAR BIT | 0.75 | 2.14 | 40
6878 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/05/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000669/2023-2024 | 82VSD | 28/04/2023 | 22 | TAPAN KUMAR UPADHYAY | 0.33 | 0.32 | 20
6879 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 12 (twelve) months from 01.02.2021 to 31.01.2022. | Assistant Engineer | Junior Engineer | ORD/000837/2020-2021 | 44/VSD | 29/01/2021 | 365 | SWAPAN KUMAR BIT | 1.73 | 0 | 0
6880 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/11/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000882/2022-2023 | 300/A/VSD | 28/10/2022 | 31 | TAPAN KUMAR UPADHYAY | 0.23 | 0.23 | 0
6881 | Bankura Division | Brishnupur Sub-Division | Continuation of Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.08.2022 to 31.01.2023. | Assistant Engineer | Junior Engineer | ORD/001051/2022-2023 | 237/VSD | 26/07/2022 | 184 | SWAPAN KUMAR BIT | 0.86 | 2.03 | 35
6882 | Bankura Division | Brishnupur Sub-Division | Continuation of Hiring of addtional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 02 (two) months from 01.12.2023 to 31.01.2024. | Assistant Engineer | Junior Engineer | ORD/001107/2023-2024 | 363/A/VSD | 29/11/2023 | 61 | TAPAN KUMAR UPADHYAY | 0.29 | 0.74 | 40
6883 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2024 to 31.07.2024. | Assistant Engineer | Junior Engineer | ORD/001265/2023-2024 | 37/VSD | 31/01/2024 | 182 | SWAPAN KUMAR BIT | 0.75 | 2.06 | 0
6884 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/12/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000883/2022-2023 | 317/A/VSD | 29/11/2022 | 30 | TAPAN KUMAR UPADHYAY | 0.23 | 0.23 | 0
6885 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/01/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000884/2022-2023 | 363/VSD | 28/12/2022 | 31 | TAPAN KUMAR UPADHYAY | 0.25 | 0.25 | 0
6886 | Bankura Division | Brishnupur Sub-Division | Carriage of Departmental Materials i.e. FERRULE, CHOLORINE etc. In connection with Jal Jeevan Mission & JAL SWAPNA Under Bishnupur Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001023/2021-2022 | 437/VSD | 08/10/2021 | 180 | TAPAS KUMAR HAZRA | 3.2 | 1.3 | 100
6887 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001082/2021-2022 | 54VSD | 28/02/2022 | 31 | SWAPAN KUMAR BIT | 0.09 | 0.09 | 20
6888 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/04/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division | Assistant Engineer | Junior Engineer | ORD/001083/2021-2022 | 82A/VSD | 31/03/2022 | 30 | SWAPAN KUMAR BIT | 0.11 | 0.11 | 20
6889 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/04/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001103/2022-2023 | 63VSD | 27/03/2023 | 19 | TAPAN KUMAR UPADHYAY | 0.25 | 0.24 | 20
6890 | Bankura Division | Brishnupur Sub-Division | Hiring of addtional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2024 to 31.07.2024 | Assistant Engineer | Junior Engineer | ORD/001267/2023-2024 | 38/VSD | 30/01/2024 | 182 | TAPAN KUMAR UPADHYAY | 0.75 | 2.16 | 0
6891 | Bankura Division | Brishnupur Sub-Division | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2025 to 31.07.2025. | Assistant Engineer | Junior Engineer | ORD/001780/2024-2025 | 90/VSD | 29/01/2025 | 181 | SWAPAN KUMAR BIT | 0.87 | 0 | 0
6892 | Bankura Division | Brishnupur Sub-Division | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2025 to 31.07.2025. | Assistant Engineer | Junior Engineer | ORD/001849/2024-2025 | 91/VSD | 29/01/2025 | 181 | TAPAN KUMAR UPADHYAY | 0.87 | 1.15 | 0
6893 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/08/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001115/2022-2023 | 230VSD | 26/07/2022 | 31 | AJIT KUMAR DUTTA | 0.09 | 0.09 | 20
6894 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/09/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001116/2022-2023 | 260A/VSD | 28/08/2022 | 31 | AJIT KUMAR DUTTA | 0.09 | 0.09 | 25
6895 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/10/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001117/2022-2023 | 281A/VSD | 27/09/2022 | 30 | AJIT KUMAR DUTTA | 0.09 | 0.09 | 20
6896 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/07/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001118/2022-2023 | 181VSD | 30/06/2022 | 31 | SWAPAN KUMAR BIT | 0.1 | 0.1 | 20
6897 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/05/2023 for supervision of work releted to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division | Assistant Engineer | Junior Engineer | ORD/001119/2022-2023 | 121VSD | 28/04/2022 | 30 | SWAPAN KUMAR BIT | 0.11 | 0.11 | 20
6898 | Bankura Division | Brishnupur Sub-Division | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/06/2022 for supervision of work releted to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer | Junior Engineer | ORD/001120/2022-2023 | 160VSD | 30/05/2022 | 31 | SWAPAN KUMAR BIT | 0.1 | 0.1 | 20
6899 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/10/2024 to 31/10/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001306/2024-2025 | 626/VSD | 30/09/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0.09 | 0
6900 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/11/2024 to 30/11/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001307/2024-2025 | 655/VSD | 28/10/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0.09 | 0
6901 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/12/2024 to 31/12/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001447/2024-2025 | 776/VSD | 30/11/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0.09 | 0
6902 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/01/2025 to 31/01/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001451/2024-2025 | 857/VSD | 30/12/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0.09 | 0
6903 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/01/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division. | Assistant Engineer | Junior Engineer | ORD/001537/2023-2024 | 03/VSD | 03/01/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0.1 | 0
6904 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 29/02/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division. | Assistant Engineer | Junior Engineer | ORD/001538/2023-2024 | 40/VSD | 02/02/2024 | 29 | KHUR SHID ALAM KHAN | 0.1 | 0.09 | 0
6905 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001588/2023-2024 | 86/VSD | 01/03/2024 | 31 | KHUR SHID ALAM KHAN | 0.09 | 0.1 | 0
6906 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/04/2024 to 30/04/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJMP project within Bishnupur Sub-Division of Bankura Division. | Assistant Engineer | Junior Engineer | ORD/001589/2023-2024 | 114/A/VSD | 15/03/2024 | 31 | KHUR SHID ALAM KHAN | 0.09 | 0.1 | 0
6907 | Bankura Division | Brishnupur Sub-Division | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/04/2025 to 30/04/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002297/2024-2025 | 164/A/VSD | 25/03/2025 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0
6908 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 08 nos. i.e. Dhabani- 136, Chitrang-137,Baliguma-138, Indkuri-139,Taldangra-140,Domberya-141,Majdiha-142 and Hetagara-143 Total house hold - 799 ( Out of 949) | Assistant Engineer | Junior Engineer | ORD/000195/2021-2022 | 3029/BQA | 29/11/2021 | 30 | SUMITA UPADHYAY | 61.96 | 41.38 | 0
6909 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (FunCtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dangalan, No. of Mouza :- 09 nos. i.e. Banki-85, Chotogobindapur-86, Adilpur-87 & Haldi-83, Mandra-88, Berghosh-84, Dangalan-91, Musarbar-92 & Ashwinpur-93, Total House Hold - 2639 | Assistant Engineer | Junior Engineer | VCH/001245/2022-2023 | FHTC/29 | 29/09/2022 | 0 | J. D. J. ENTERPRISE | 77 | 0 | 0
6910 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar , Name of Village Kadakuli Man Para, Total House Hold -70 | Assistant Engineer | Junior Engineer | ORD/000463/2020-2021 | 556/ BSD | 13/11/2020 | 21 | GON ASSOCIATES | 4.59 | 0 | 0
6911 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | ORD/000464/2020-2021 | 557/ BSD | 13/11/2020 | 21 | SANJOY MONDAL | 4.82 | 0 | 0
6912 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Total House Hold -76 | Assistant Engineer | Junior Engineer | ORD/000465/2020-2021 | 558/ BSD | 13/11/2020 | 21 | TAPAS PAL | 4.85 | 0 | 0
6913 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Total House Hold -73 | Assistant Engineer | Junior Engineer | ORD/000466/2020-2021 | 559/ BSD | 13/11/2020 | 21 | M/S BANERJEE & BANERJEE | 4.71 | 0 | 0
6914 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | ORD/000467/2020-2021 | 560/ BSD | 13/11/2020 | 21 | SOMENATH ACHARYYA | 4.81 | 0 | 0
6915 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata Roy Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | ORD/000468/2020-2021 | 561/ BSD | 13/11/2020 | 21 | ASHIS PAL | 4.8 | 0 | 0
6916 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata Ghosh Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | ORD/000469/2020-2021 | 562/ BSD | 13/11/2020 | 21 | SOMA BANERJEE | 4.81 | 0 | 0
6917 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar, Name of Village - Kadakuli Man Para, Chandar Bramhon Para & Chatterjee para Total House Hold -40. | Assistant Engineer | Junior Engineer | ORD/000470/2020-2021 | 31/BSD | 06/01/2021 | 21 | GON ASSOCIATES | 4.47 | 0 | 10
6918 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Chandar Rail line para, school , health center, Total House Hold -52. | Assistant Engineer | Junior Engineer | ORD/000471/2020-2021 | 10/BSD | 06/01/2021 | 21 | SANJOY MONDAL | 4.8 | 0 | 0
6919 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Chandar Shib mondir Namo Para & Brimhon para Total House Hold -50. | Assistant Engineer | Junior Engineer | ORD/000472/2020-2021 | 26/BSD | 06/01/2021 | 21 | M/S PAUL BROTHERS | 4.7 | 0 | 0
6920 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. | Assistant Engineer | Junior Engineer | ORD/000473/2020-2021 | 11/BSD | 06/01/2021 | 21 | M/S BANERJEE & BANERJEE | 4.83 | 0 | 0
6921 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20. | Assistant Engineer | Junior Engineer | ORD/000474/2020-2021 | 28/BSD | 06/01/2021 | 21 | BIDHAN BANERJEE | 4.84 | 0 | 0
6922 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Chandar main Bazar to Chandar gram end & Baroma kali than (Chomatha), Bramhon para (Part), Chandar maibazar, Total House Hold -25. | Assistant Engineer | Junior Engineer | ORD/000475/2020-2021 | 29/BSD | 06/01/2021 | 21 | SOMENATH ACHARYYA | 4.81 | 0 | 0
6923 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata ,Main road to durga mondir (Part), Total House Hold -35. | Assistant Engineer | Junior Engineer | ORD/000476/2020-2021 | 12/BSD | 06/01/2021 | 21 | ASHIS PAL | 4.75 | 0 | 0
6924 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata ,Chandar Durgamondir para (part), Total House Hold -45. | Assistant Engineer | Junior Engineer | ORD/000477/2020-2021 | 13/BSD | 06/01/2021 | 21 | JAGADISH BANERJEE | 4.73 | 0 | 0
6925 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- ChandarBardgan Para (Part- A), Total House Hold -50. | Assistant Engineer | Junior Engineer | ORD/000478/2020-2021 | 27/BSD | 06/01/2021 | 21 | MAYA CONSTRUCTION | 4.44 | 0 | 0
6926 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- B), Total House Hold - 50. | Assistant Engineer | Junior Engineer | ORD/000479/2020-2021 | 14/BSD | 06/01/2021 | 21 | TAPAN KUMAR UPADHYAY | 4.48 | 0 | 0
6927 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- C), Total House Hold -50. | Assistant Engineer | Junior Engineer | ORD/000480/2020-2021 | 30/BSD | 06/01/2021 | 21 | MANAS DEY | 4.56 | 0 | 10
6928 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20 | Assistant Engineer | Junior Engineer | ORD/000493/2020-2021 | 28 / BSD | 06/01/2021 | 21 | BIDHAN BANERJEE | 4.84 | 0 | 0
6929 | Bankura Division | Bankura Sadar Sub-Division | retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Murakata, Total House Hold - 45 nos. | Assistant Engineer | Junior Engineer | ORD/000873/2021-2022 | 12/BSD | 07/01/2022 | 15 | BIDHAN BANERJEE | 4.98 | 0 | 0
6930 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Nabasan, Total House Hold - 35 nos. | Assistant Engineer | Junior Engineer | ORD/000874/2021-2022 | 10/BSD | 07/01/2022 | 15 | SOMENATH ACHARYYA | 4.9 | 0 | 65
6931 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Chhandar (Part), Total House Hold - 40 nos. | Assistant Engineer | Junior Engineer | ORD/000875/2021-2022 | 11/BSD | 07/01/2022 | 15 | SOMENATH ACHARYYA | 4.98 | 0 | 0
6932 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13), | Assistant Engineer | Junior Engineer | VCH/002333/2021-2022 | FHTC/25 | 25/01/2022 | 0 | GANESH ROY | 4.98 | 0 | 0
6933 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 | Assistant Engineer | Junior Engineer | VCH/002334/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SUBHENDU SEKHAR GORAI | 1.78 | 0 | 0
6934 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no. 43Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Barabaikunthapur-125 & Habispur-127 , Total House Hold - 245 (245 out of 549) | Assistant Engineer | Junior Engineer | VCH/002335/2021-2022 | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR MANDAL | 16.4 | 0 | 0
6935 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 | Assistant Engineer | Junior Engineer | VCH/002344/2021-2022 | FHTC/25 | 25/01/2022 | 0 | AMIYA KUMAR BIT | 35.44 | 0 | 0
6936 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara,Ichharia,Dhallapara,Amchura, Kalaberia, Kalyanpur,Bhramanpara,Bhabanipur & Murhura. Total House Hold - 162 | Assistant Engineer | Junior Engineer | VCH/002345/2021-2022 | FHTC/25 | 25/01/2022 | 0 | MOHAN KUMAR ROY | 4.69 | 0 | 0
6937 | Bankura Division | Bankura Sadar Sub-Division | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-II )Total House Hold - 139.' | Assistant Engineer | Junior Engineer | VCH/002346/2021-2022 | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR UPADHYAY | 2.37 | 0 | 0
6938 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 | Assistant Engineer | Junior Engineer | VCH/002347/2021-2022 | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR SARKAR | 1.1 | 0 | 0
6939 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. | Assistant Engineer | Junior Engineer | VCH/002348/2021-2022 | FHTC/25 | 25/01/2022 | 0 | M/S BANERJEE & BANERJEE | 4.81 | 0 | 0
6940 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 | Assistant Engineer | Junior Engineer | VCH/002349/2021-2022 | FHTC/25 | 25/01/2022 | 0 | SOMENATH ACHARYYA | 4.79 | 0 | 0
6941 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mukundapur (114), Khakrakanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002350/2021-2022 | FHTC/25 | 25/01/2022 | 0 | APEX ENTERPRISE | 6.7 | 0 | 0
6942 | Bankura Division | Bankura Sadar Sub-Division | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I) Name of mouza - 03 nos, Phulberia (PART- B), Sirsa & Joykrishna pur Sarenga (PART- A) | Assistant Engineer | Junior Engineer | VCH/002351/2021-2022 | FHTC/25 | 25/01/2022 | 0 | M/S T.P. HAZRA & SONS | 3.25 | 0 | 0
6943 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 36.Block - Bishnupur,Name of OHR - Bhara,No. of Mouza :- 1 no. i.e.Shaluka - 21(110 out of 125) House Hold - 110 | Assistant Engineer | Junior Engineer | VCH/002352/2021-2022 | FHTC/25 | 25/01/2022 | 0 | MRITYUNJOY HAZRA | 8.3 | 0 | 0
6944 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 | Assistant Engineer | Junior Engineer | VCH/002353/2021-2022 | FHTC/25 | 25/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0
6945 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block , Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampu (part) Total House Hold - 453. | Assistant Engineer | Junior Engineer | VCH/002809/2021-2022 | FHTC/5 | 05/03/2022 | 0 | GOUTAM BHATTACHRYYA | 27.54 | 0 | 0
6946 | Bankura Division | Khatra Sub-Division | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Baramakarkol (70) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000281/2022-2023 | 1281/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 1.58 | 1.54 | 0
6947 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Asna (72), Dhanisukni (74) & Nimaipur (80) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) | Assistant Engineer | Junior Engineer | ORD/000282/2022-2023 | 1292/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 4.86 | 4.79 | 0
6948 | Bankura Division | Khatra Sub-Division | Work Order for Laying extra UPVC pipeline to cover Baramakarkol (70), Kalabati (79), Sirsha (81) & Kallaicha (84) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) | Assistant Engineer | Junior Engineer | ORD/000283/2022-2023 | 1297/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 4.8 | 4.72 | 0
6949 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1926 nos. | Assistant Engineer | Junior Engineer | ORD/000417/2021-2022 | 437/BQA | 03/03/2022 | 45 | PRINCE INDUTRIES (INDIA) | 97.43 | 96.57 | 0
6950 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) | Assistant Engineer | Junior Engineer | ORD/000623/2021-2022 | 861/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.64 | 0.64 | 0
6951 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2021-2022 | 2497/BQA | 23/09/2021 | 30 | PARAMESWAR CHOWDHURY | 68.16 | 17.94 | 50
6952 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 01 no., (Majit), Total House Hold - 175 nos. | Assistant Engineer | Junior Engineer | ORD/000154/2021-2022 | 2834/BQA | 16/11/2021 | 30 | MD. AFSAR ALI | 7.96 | 7.66 | 0
6953 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer | Junior Engineer | ORD/000592/2021-2022 | 795/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.37 | 0 | 0
6954 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000456/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.37 | 0 | 0
6955 | Bankura Division | Khatra Sub-Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002542/2021-2022 | FHTC/23 | 23/02/2022 | 0 | SUBHADIP KOLEY | 42.16 | 0 | 0
6956 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 530 | Assistant Engineer | Junior Engineer | VCH/002546/2021-2022 | FHTC/23 | 23/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 32.04 | 0 | 0
6957 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002565/2021-2022 | FHTC/26 | 26/02/2022 | 0 | PARAMESWAR CHOWDHURY | 47.88 | 0 | 0
6958 | Bankura Division | Khatra Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | Assistant Engineer | Junior Engineer | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0
6959 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR -Narikala, No. of Mouza :- 08 nos. i.e.Bhagaband-1,Binodbati-2,Arjunpur-3,Nityanandapur-4,Balarampur-5,Tarajuri Gangarampur-14, Narikala-15,Karoan-16.Total House Hold - 1461 | Assistant Engineer | Junior Engineer | ORD/000418/2021-2022 | 438/BQA | 03/03/2022 | 1487 | PRINCE INDUTRIES (INDIA) | 107.14 | 61.78 | 80
6960 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2021-2022 | 472/BQA | 04/03/2022 | 0 | Resource Division | 8.81 | 0 | 0
6961 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Morar Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Benebandhi, No. of Mouza :- 7 nos. i.e.Dadwasbati-98, Kusumbani-99, Chougan-102, Dundure-116, Morar-117, Ghugimura-121, Jharia-122, Total House Hold -70 | Assistant Engineer | Junior Engineer | ORD/000028/2022-2023 | 110/VSD | 19/04/2022 | 21 | AJIT KUMAR DUTTA | 4.52 | 3.96 | 0
6962 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 3.85 | 0 | 0
6963 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household - 2536 nos. | Assistant Engineer | Junior Engineer | ORD/000403/2021-2022 | 318/BQA | 22/02/2022 | 60 | UNIVERSAL CONSTRUCTION | 123.11 | 40.63 | 0
6964 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2021-2022 | 87/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.85 | 0 | 100
6965 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2021-2022 | 2891/BQA | 22/11/2021 | 0 | Resource Division | 165.74 | 0 | 0
6966 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2021-2022 | 150/BQA | 27/01/2022 | 0 | Resource Division | 11.94 | 0 | 0
6967 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000027/2021-2022 | 567/BQA | 17/03/2022 | 0 | Resource Division | 15.6 | 0 | 0
6968 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas by retrofitting Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2339 nos. | Assistant Engineer | Junior Engineer | ORD/000020/2022-2023 | 1062/BQA | 10/05/2022 | 720 | M/S CARE | 122.18 | 114.94 | 97
6969 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Nikunjapur (Zone-B) Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000895/2021-2022 | 100/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.78 | 0.78 | 0
6970 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2021-2022 | 579/BQA | 17/03/2022 | 0 | Resource Division | 14.41 | 0 | 0
6971 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1713 nos. | Assistant Engineer | Junior Engineer | ORD/000414/2021-2022 | 435/BQA | 03/03/2022 | 45 | SUBHANKAR BANERJEE | 100.63 | 43.51 | 0
6972 | Bankura Division | Bankura Sadar Sub-Division | Household survey in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000894/2021-2022 | 94/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.57 | 0.19 | 20
6973 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2021-2022 | 581/BQA | 17/03/2022 | 0 | Resource Division | 10.55 | 0 | 0
6974 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6975 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6976 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
6977 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
6978 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte. Khakrakanali, Ps-Khatra Dist- Bankura |  | Junior Engineer | BILL/00779/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
6979 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
6980 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32.5 | 48
6981 | Bankura Division | Bankura Sadar Sub-Division | Construction of 450m3 capacity RCC OHR based on Departmental Design [ref Drawing No. ¿ PC ¿ 1 / OHR / 4 / 2012 Rev. No. ¿ 1 (Sheet 1 & 2)] with 20.00 mtr. Staging height including foundation, pipe line connection and cost of pipes, specials etc. and allied works for Augmentation of Surface Based Piped W/S Scheme for SANABUNDH, KARGAHIR and Adjoining Mouzas (JJM Revision) under Bankura Division, PHE Dte. (Part ¿ A) and Distribution System with FHTC for the Augmentation of Piped Water Supply Scheme for Augmentation of Surface Water Based Piped W/S Scheme for ¿SANABUNDH, KARGAHIR¿ and Adjoining Mouzas (JJM Revision) under Bankura Division, PHE Dte. (Part ¿ B) | Assistant Engineer | Junior Engineer | ORD/000033/2022-2023 | 1178/BQA | 25/05/2022 | 1407 | GOPAL CHANDRA CHOWDHURY | 395.61 | 355.94 | 86
6982 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance 'FHTC' & construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Surface Water Based Piped W/S Scheme for SANABUNDH, KARGAHIR and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2023-2024 | 1350/BQA | 02/06/2023 | 1034 | GOPAL CHANDRA CHOWDHURY | 72.42 | 40.97 | 94
6983 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Surface water based piped water supply scheme for Sanabundh, Kargahir and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000506/2023-2024 | 2355/BQA | 14/08/2023 | 961 | GOPAL CHANDRA CHOWDHURY | 102.5 | 0 | 87
6984 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 450 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Sanabundh and Kargahir and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000873/2022-2023 | 360/BSD | 13/04/2022 | 15 | SHINE ENGINEERING CONSULTANT | 1.85 | 1.85 | 0
6985 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
6986 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) | Assistant Engineer | Junior Engineer | BILL/00194/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
6987 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation od surface water based piped water supply scheme for Sanband, Kargahir and adjoining mouza under Bankura Mechanical Division PHE Dte Block-Bankura-I Dist -Bankura. | Assistant Engineer | Junior Engineer | ORD/000192/2023-2024 | 1015/BMD | 22/05/2023 | 720 | M.S. ENTERPRISE | 43.65 | 34.65 | 100
6988 | Bankura Division | Brishnupur Sub-Division | Patrasayer market road from 0.00 kmp 02.50 kmp restoration work of both side of road due to laying of pipeline by Bankura Division PHE Dte. under Bankura Highway Division in the district of Bankura, (1) Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | Assistant Engineer | Junior Engineer | BILL/02261/2023-2024 | FHTC/12 | 13/12/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 46.31 | 0 | 0
6989 | Bankura Division | Brishnupur Sub-Division | Sinking of 2 Nos. Tubewell (Rotary Method) with construction of 2 Nos. Pump House & Boundary Wall and Laying of Distribution System under Augmentation of Nabakishore Water Supply Scheme under Jal Jeevan Mission (JJM) within Patrasayer Block under Bishnupur Sub-division of Bankura Division, P.H.E. Dte. (SM/10290) | Assistant Engineer | Junior Engineer | ORD/000103/2025-2026 | 1232/BQA | 02/06/2025 | 259 | M/S S. CHOUDHURY | 158.01 | 0 | 40
6990 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 60 mtr long at 3rd TW site of Augmentation of Nabakishore water supply scheme within Patrasayer Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000195/2024-2025 | 1868/BQA | 12/07/2024 | 30 | M/S ABU KADER KHAN | 3.84 | 3.82 | 90
6991 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 132 mtr long for augmentation of Nabakishore water supply scheme (pump house no 1) under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 64/BQA | 05/01/2023 | 30 | GANGADHAR MONDAL | 9.38 | 9.2 | 10
6992 | Bankura Division | Brishnupur Sub-Division | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.50 m x 4.5 m) for augmentation of Nabakishore Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000380/2022-2023 | 65/BQA | 05/01/2023 | 90 | SANU KARMAKAR | 6.51 | 5.71 | 86
6993 | Bankura Division | Brishnupur Sub-Division | Construction & Commissioning of 700 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. of Drg.no.-PC-I/OHR/6/2012(Rev-01){Sheet-1/2 &2/2} of SE,PC-I,PHE Dte.) staging height 20 mtr. with Laying Distribution System as per LDS drawing, including FHTC works for Augmentation of Nabakishore Piped Water Supply Scheme under Patrasayer Block of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2023-2024 | 2277/BQA | 01/08/2023 | 821 | SATYANARAYAN ENGINEERS' CO-OP.SOCIETY LTD | 623.97 | 294.94 | 89
6994 | Bankura Division | Brishnupur Sub-Division | Repairing of one no pump house for augmentation of Nabakishore water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000559/2022-2023 | 522/BQA | 14/03/2023 | 45 | MOHAN KUMAR ROY | 2.01 | 1.08 | 85
6995 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Augmentation of Nabakishore water supply scheme (SM/10290), 2 nos. sites of Augmentationn of Patrasayer water supply scheme (SM/09926) & for 2 nos. sites of Chandal Bandi Piped Water Supply Scheme (SM/13999) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001882/2024-2025 | 560/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.9 | 0 | 0
6996 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2025-2026 | 1624/BQA | 21/07/2025 | 0 | Resource Division | 1.69 | 0 | 0
6997 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000146/2023-2024 | 3345/BQA | 06/12/2023 | 0 | Resource Division | 50.07 | 0 | 0
6998 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000153/2023-2024 | 111/BQA | 10/01/2024 | 0 | Resource Division | 28.91 | 0 | 0
6999 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | Assistant Engineer | Junior Engineer | BILL/00121/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.4 | 0 | 0
7000 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Nabakishore Ground Base piped water supply scheme under JJM program under Bankura Mechanical Division, PHE Dte Block : Patrasayar, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 934/BMD | 12/05/2023 | 180 | M/S NABIN GOPAL SENGUPTA | 56.49 | 43.47 | 76
7001 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7002 | Bankura Division | Bankura Sadar Sub-Division | Taribatardihi, Bankura-I | Assistant Engineer | Junior Engineer | BILL/00759/2022-2023 | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.08 | 0 | 0
7003 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7004 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30.6 | 48
7005 | Bankura Division | Bankura Sadar Sub-Division | Bmsd Phe Dte vill- Chowghora, Po-G/Dubrajpur, Ps- Chhatna | Assistant Engineer | Junior Engineer | BILL/00022/2023-2024 | FHTC/06 | 05/06/2023 | 0 | CHHATNA CCC | 0.12 | 0 | 0
7006 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7007 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7008 | Bankura Division | Bankura Sadar Sub-Division | New service connection at Chowghora | Assistant Engineer | Junior Engineer | BILL/01398/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7009 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 22.6 | 48
7010 | Bankura Division | Bankura Sadar Sub-Division | New service connection for "Pathardanga" Mini water supply scheme under Bankura Division PHE DT | Assistant Engineer | Junior Engineer | BILL/00074/2024-2025 |  | 26/04/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
7011 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE (Pathardanga) HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | Assistant Engineer | Junior Engineer | BILL/00128/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0
7012 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7013 | Bankura Division | Bankura Sadar Sub-Division | Quotation asper WBSEDCL for SM/10918 | Assistant Engineer | Junior Engineer | BILL/00911/2024-2025 | BP/456/2024-25 | 27/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0
7014 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7015 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Pathardanga water supply scheme(SVS) under BMD PHE Dte.(SM/10918) | Assistant Engineer | Junior Engineer | BILL/01400/2024-2025 | BP/449/2024-25 | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0
7016 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 35.5 | 48
7017 | Bankura Division | Bankura Sadar Sub-Division | Quotation of WBSEDCL for the scheme of SM/10932 | Assistant Engineer | Junior Engineer | BILL/00846/2024-2025 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.2 | 0 | 0
7018 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 42 | 48
7019 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dhanjhar ( C/o Sudip Saha , Dhanjhar, Ranibandh |  | Junior Engineer | BILL/00045/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
7020 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7021 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7022 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
7023 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7024 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7025 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
7026 | Bankura Division | RWS Bankura Sub-Division | Work Order Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Barapacha Village (SM/11115), (2) Mini Piped Water Supply Scheme for Ledapakur Village (SM/11116), (3) Mini Piped Water Supply Scheme for Sutan Village (SM/11120), (4) Mini Piped Water Supply Scheme for Burisal Village (SM/11117), (5) Mini Piped Water Supply Scheme for Goalmuri Village (SM/11118) and (6) Mini Piped Water Supply Scheme for Kawatanga Village (SM/11109) |  | Junior Engineer | ORD/001990/2024-2025 | 190\KSD | 10/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 90
7027 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-96, Mouza-Kalasol, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00290/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
7028 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7029 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7030 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
7031 | Bankura Division | RWS Bankura Sub-Division | New connection at Jl No-95, Mouza-Kuchaipal, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. |  | Junior Engineer | BILL/00289/2023-2024 | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0
7032 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7033 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7034 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
7035 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - sajalpuskurini, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00274/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7036 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7037 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7038 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 34 | 48
7039 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7040 | Bankura Division | RWS Bankura Sub-Division | P.H.E Dte. Parashidanga, Ps-Khatra Dist-Bankura |  | Junior Engineer | BILL/00778/2022-2023 | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0
7041 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7042 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 48
7043 | Bankura Division | RWS Bankura Sub-Division | Work Order for Installation of scheme information board for different mini piped water supply scheme within Khatra & Hirbandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Simchaka Village (SM/10952), (2) Mini Piped Water Supply Scheme for Parashidanga Village (SM/10953), (3) Mini Piped Water Supply Scheme for Bankati Village (SM/10955), (4) Mini Piped Water Supply Scheme for Damodarpur Village (SM/10956) and (5) Mini Piped Water Supply Scheme for Shyampur Village (SM/10856) |  | Junior Engineer | ORD/001989/2024-2025 | 189\KSD | 10/03/2025 | 10 | TAPAN KUMAR MANDAL | 0.75 | 0 | 95
7044 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7045 | Bankura Division | Brishnupur Sub-Division | New Connection at Dhamsa,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00494/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
7046 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7047 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 35 | 48
7048 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7049 | Bankura Division | Brishnupur Sub-Division | New Connection at Khejurmura,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00483/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
7050 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7051 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36 | 48
7052 | Bankura Division | Brishnupur Sub-Division | (site - Chakdelwar, Deshra Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00292/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7053 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7054 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7055 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at CHAKDELWAR | Assistant Engineer | Junior Engineer | BILL/01275/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7056 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
7057 | Bankura Division | Khatra Sub-Division | New service connection for Dhepua Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00183/2024-2025 | BP-85/2024-25 | 29/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
7058 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7059 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7060 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
7061 | Bankura Division | Brishnupur Sub-Division | (site - Chakraghu, M.M.P , Kotulpur) quotation bill | Assistant Engineer | Junior Engineer | BILL/00296/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7062 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7063 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7064 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at CHAKRAGHU | Assistant Engineer | Junior Engineer | BILL/01265/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7065 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
7066 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7067 | Bankura Division | Khatra Sub-Division | Quotation of WBSEDCL for the scheme of SM/11062 |  | Junior Engineer | BILL/00848/2024-2025 | BP/459/2024-25 | 21/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.86 | 0 | 0
7068 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7069 | Bankura Division | Khatra Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26.5 | 48
7070 | Bankura Division | RWS Bankura Sub-Division | New service connection for Ambedia Mini water supply scheme under Bankura Division PHE DTE. |  | Junior Engineer | BILL/00121/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0
7071 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7072 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7073 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
7074 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7075 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Gilirbona Dubrajpur |  | Junior Engineer | BILL/00519/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7076 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7077 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
7078 | Bankura Division | Bankura Sadar Sub-Division | New service connection for Bhalukkunia Mini water supply scheme under Bankura Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00186/2024-2025 |  | 28/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
7079 | Bankura Division | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE (Bhalukkunia) HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME(SM/10933) | Assistant Engineer | Junior Engineer | BILL/00195/2024-2025 | BP-91/2024-25 | 04/06/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0
7080 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 42 | 48
7081 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - gachhgere, Nr. Primary school, Lowgram, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00269/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7082 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7083 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7084 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Gachhgere | Assistant Engineer | Junior Engineer | BILL/01257/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7085 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 24 | 48
7086 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 14 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002198/2024-2025 | 578/A/VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 2.11 | 0 | 0
7087 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Diachapri, lowgram, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00287/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7088 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7089 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7090 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at DIACHAPRI | Assistant Engineer | Junior Engineer | BILL/01266/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7091 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 26 | 48
7092 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - chatpagla, Nr. Manshatala, Lowgram, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00268/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7093 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7094 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7095 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at CHATPAGLA | Assistant Engineer | Junior Engineer | BILL/01270/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7096 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40.6 | 48
7097 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7098 | Bankura Division | Brishnupur Sub-Division | Quatation bill Balita Brahamdanga, Kotulpur | Assistant Engineer | Junior Engineer | BILL/00672/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7099 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7100 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at BATILA | Assistant Engineer | Junior Engineer | BILL/01271/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7101 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 36 | 48
7102 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7103 | Bankura Division | Brishnupur Sub-Division | Bankajol Chorgere Sihar, Kotulpur | Assistant Engineer | Junior Engineer | BILL/00680/2022-2023 | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7104 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7105 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW CONNECTION AT BANKAJOL | Assistant Engineer | Junior Engineer | BILL/01274/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7106 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
7107 | Bankura Division | Khatra Sub-Division | Laying of DI (K7) pipe with supplying, laying, fitting, fixing, jointing of HDPE (Materials grade PE-100, PN-6) pipes for distribution system with ancillary works with providing ¿FHTC (Functional House Hold Tap Connection)¿, Laying Rising Main using different dia D.I. - K9 pipes and Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes, specials etc. and allied works for Augmentation for Chhoto - Birbhanpur Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2023-2024 | 970/BQA | 28/04/2023 | 270 | PARTHA PRATIM CHHATAIT | 289.03 | 167.43 | 60
7108 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Augmentation of Chhoto Birbhanpur Piped Water Supply Scheme, Block : Sarenga, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) | Assistant Engineer | Junior Engineer | ORD/000308/2022-2023 | 194/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.37 | 3.05 | 0
7109 | Bankura Division | Khatra Sub-Division | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 99
7110 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 2 nos. site of Sub Surface water based Sarenga Piped Water Supply Scheme (SM/11980), 2 nos. site of Augmentation for Chhoto-Birbhanpur Water Supply Scheme (SM/12379) and 2 nos. site of Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme (SM/17725) within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001917/2024-2025 | 161\KSD | 07/03/2025 | 10 | SUBHADIP KOLE | 0.9 | 0 | 90
7111 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 46.12 | 0 | 0
7112 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000161/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.82 | 0 | 0
7113 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | Assistant Engineer | Junior Engineer | BILL/00122/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
7114 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000188/2023-2024 | 964/BMD | 19/05/2023 | 1065 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.1 | 22.9 | 70
7115 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Name of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001353/2023-2024 | 1013/BMD | 22/05/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.59 | 0 | 0
7116 | Bankura Division | Brishnupur Sub-Division | Emergent repairing for laying of pipe line by the PHE department at Joyrambati-Kamarpukur road at Malpur Prathamik Vidyalaya under Bishnupur Division PWD in the District of Bankura during the year 2023-2024 | Assistant Engineer | Junior Engineer | BILL/02189/2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 0.96 | 0 | 0
7117 | Bankura Division | Brishnupur Sub-Division | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE department in the different stretches in joyrambati - kamarpukur road under Bishnupur division P.W.Dte. in the district of Bankura . | Assistant Engineer | Junior Engineer | BILL/02424/2023-2024 | FHTC/02 | 02/02/2024 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 43.62 | 0 | 0
7118 | Bankura Division | Brishnupur Sub-Division | Construction of Office cum Godown with sanitary and water supply arrangement at Head Work Site of 60 sqmtr. (approx) area at water supply scheme for surface water based for Augmentation of Joyrambati water supply scheme under Bishnupur Sub-Division, Bankura Division PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 763/BQA | 04/04/2023 | 728 | M/S T.P. HAZRA & SONS | 12.53 | 6.85 | 20
7119 | Bankura Division | Brishnupur Sub-Division | Construction of boundary wall approx 30 mtr long for Augmentation of Joyrambati water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 764/BQA | 04/04/2023 | 30 | MRITYUNJOY HAZRA | 1.66 | 0 | 0
7120 | Bankura Division | Brishnupur Sub-Division | Laying distribution system including allied works of Augmentation of Joyrambati Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 901/BQA | 20/04/2023 | 276 | BISWARUP BOSE | 110.15 | 109.8 | 45
7121 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for Augmentation of Joyrambati W/S Scheme Block- Kotulpur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 Block -Kotulpur, Name of OHR -Joyrambati, No. of Mouza :- 4 nos. i.e. (i) Joyrambati - J.L No-164 , (ii) Haldi J.L. No-165, (iii) Malpur J.L No-166 & (iv) Masinapur J.L No-167 . Total House Hold - 1287 | Assistant Engineer | Junior Engineer | ORD/000422/2022-2023 | 179/BQA | 30/01/2023 | 480 | DIPAYAN DEY | 66.36 | 27.14 | 35
7122 | Bankura Division | Brishnupur Sub-Division | Construction of Ground Level Reservoir (capacity 50 m3) for Matri Mandir, Joyrambati, Bankura under Joyrambati water supply scheme within Bishnupur Sub-Division of Bankura Division PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000453/2021-2022 | 661/BQA | 23/03/2022 | 90 | MOHAN KUMAR ROY | 16.99 | 14.38 | 20
7123 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Jayrambati Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00123/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
7124 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Jayrambati Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00133/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0
7125 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Joyrambati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 935/BMD | 12/05/2023 | 180 | KASHINATH DEY | 29.69 | 22.96 | 77
7126 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 49 | 48
7127 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7128 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7129 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 48
7130 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7131 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Raghunathpur Baga | Assistant Engineer | Junior Engineer | BILL/00523/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7132 | Bankura Division | RWS Bankura Sub-Division | WBSEDCL Quotation bill for Scheme code - SM/10868. | Assistant Engineer | Junior Engineer | BILL/00761/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7133 | Bankura Division | RWS Bankura Sub-Division | Phe Complex Ailakandi, Raghunathpur Nayada | Assistant Engineer | Junior Engineer | BILL/01123/2022-2023 |  | 29/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7134 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Raghunathpur Baga | Assistant Engineer | Junior Engineer | BILL/01227/2022-2023 | ELCO03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7135 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7136 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 20 | 48
7137 | Bankura Division | RWS Bankura Sub-Division | New service connection for Jagatpur, Bibarda Mini water supply scheme under Bankura Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00142/2024-2025 | BP-77/2024-25 | 22/05/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
7138 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7139 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Krishnanagar Purusottampur | Assistant Engineer | Junior Engineer | BILL/00526/2022-2023 | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7140 | Bankura Division | RWS Bankura Sub-Division | Quotation bill for Jagatpur, Durbrajpur | Assistant Engineer | Junior Engineer | BILL/00587/2022-2023 |  | 27/02/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7141 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7142 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 21 | 48
7143 | Bankura Division | Brishnupur Sub-Division | WBSEDCL service connection on Ghagara site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00177/2022-2023 | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0
7144 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7145 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7146 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 32 | 48
7147 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR HARINASHULI & JADABNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1918/BQA | 13/07/2023 | 810 | GOPAL CHANDRA CHOWDHURY | 1591.82 | 547.66 | 85
7148 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
7149 | Bankura Division | Brishnupur Sub-Division | Jack Pussing, Land development & Rock cutting for foundation of 500 M3 capacity RCC OHR with 20 Mtr. staging height of Jadabnagar Water Supply Scheme & 450 M3 capacity RCC OHR with 20 Mtr. staging height of Harinasuli Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 3001/BQA | 03/11/2023 | 45 | GOPAL CHANDRA CHOWDHURY | 74.67 | 36.64 | 95
7150 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 14.41 | 0 | 0
7151 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000056/2023-2024 | 2522/BQA | 08/09/2023 | 0 | Resource Division | 14.41 | 0 | 0
7152 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000083/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 118.81 | 0 | 0
7153 | Bankura Mechanical | Brishnupur Sub-Division | Harinsuli T/W-I | Assistant Engineer | Junior Engineer | BILL/00846/2023-2024 | BP-2023-24-46 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0
7154 | Bankura Mechanical | Brishnupur Sub-Division | Harinasuli T/W-II | Assistant Engineer | Junior Engineer | BILL/00847/2023-2024 | BP-2023-24-47 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0
7155 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk at TW No-I & T.W No-II of Harinashuli piped water supply scheme Block : Joypur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 876/BMD | 04/05/2023 | 180 | MITRA ENTERPRISE | 39.3 | 23.71 | 50
7156 | Bankura Division | Brishnupur Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 27.7 | 100
7157 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 11091.12 | 225.34 | 6
7158 | Bankura Division | Brishnupur Sub-Division | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 1.08 | 30
7159 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2025-2026 | 1620/BQA | 21/07/2025 | 0 | Resource Division | 10.73 | 0 | 0
7160 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000076/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 55.83 | 0 | 0
7161 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Pankhai t/w-II ,hetia gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00129/2024-2025 | BP-2024-25-37 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.17 | 0 | 0
7162 | Bankura Mechanical | Brishnupur Sub-Division | Pankhai Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01498/2023-2024 | BP-2023-24-103 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.68 | 0 | 0
7163 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pankhai Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 457/BMD | 10/06/2025 | 90 | A.G.ENTERPRISE | 11.86 | 0 | 0
7164 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Shantipur colony | Assistant Engineer | Junior Engineer | BILL/00048/2024-2025 | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0
7165 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
7166 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 16 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/002201/2024-2025 | 580/VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 2.41 | 0 | 0
7167 | Bankura Division | Brishnupur Sub-Division | SVS single phase connection for Dhangora village | Assistant Engineer | Junior Engineer | BILL/00052/2024-2025 | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0
7168 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7169 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7170 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 10 | 48
7171 | Bankura Division | Brishnupur Sub-Division | Installation of scheme information board for 14 nos. sites of Mini Piped Water Supply Scheme (SVS scheme) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002198/2024-2025 | 578/A/VSD | 27/09/2024 | 30 | SUBHENDU SEKHAR GORAI | 2.11 | 0 | 0
7172 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7173 | Bankura Division | Brishnupur Sub-Division | New Connection at Benda ,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00481/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
7174 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7175 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31.6 | 48
7176 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7177 | Bankura Division | Brishnupur Sub-Division | New Connection at Asabani,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00482/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
7178 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7179 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43.09 | 48
7180 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7181 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7182 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 45 | 48
7183 | Bankura Division | Brishnupur Sub-Division | New Connection at Paschim Nandarampur, Sonamukhi, PHE Dte | Assistant Engineer | Junior Engineer | BILL/00327/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
7184 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7185 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7186 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 39 | 48
7187 | Bankura Division | Brishnupur Sub-Division | New Connection at Basu Nandaram, Sonamukhi PHE Dte | Assistant Engineer | Junior Engineer | BILL/00309/2023-2024 | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0
7188 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7189 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7190 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 55 | 48
7191 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7192 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7193 | Bankura Division | Brishnupur Sub-Division | New service connection at Uttar Palsura(Bud Bud) Sonamukhi PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02611/2023-2024 | FHTC/03 | 12/03/2024 | 0 | BUDBUD CCC | 2.63 | 0 | 0
7194 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 19 | 48
7195 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7196 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7197 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 48
7198 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 27.47 | 48
7199 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- I/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000079/2023-2024 | 973/BQA | 28/04/2023 | 980 | EARTH MOVING (INDIA) | 119.88 | 86.7 | 82
7200 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-1A) (Sl. No. 01) | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000623/2022-2023 | 179/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.34 | 2.85 | 0
7201 | Bankura Division | Khatra Sub-Division | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- I/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001145/2023-2024 | 347/BQA | 05/02/2024 | 801 | SAYED PAHALOWAN | 20.11 | 0 | 90
7202 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 185 Cum., staging height 20 Mtr.) including by pass arrangement and construction of boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- I/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001761/2024-2025 | 486/BQA | 25/02/2025 | 60 | PRADIP CHAKRABORTY | 25.6 | 0 | 0
7203 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000032/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 3.99 | 0 | 0
7204 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Driller-in-Charge | Junior Engineer | RTOR000199/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.48 | 0 | 0
7205 | Bankura Mechanical | Khatra Sub-Division | New Service connection at Dhghora. | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01476/2024-2025 | BP-2024-25-373 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.06 | 0 | 0
7206 | Bankura Mechanical | Khatra Sub-Division | Payment for WBSEDCL Net Billing meter arrangement for 90KW solar power at Mukutmanipur (Old) water supply scheme [SM/115007] | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01484/2024-2025 | BP-2024-25-374 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0
7207 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-1A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000233/2023-2024 | 1119/BMD | 24/05/2023 | 45 | KASHINATH DEY | 26.4 | 0 | 0
7208 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, and installation of Flow Meter with other electro mechanical accessories of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme for OHR site Zone 1A under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001085/2023-2024 | 3062/BMD | 12/03/2024 | 360 | UNITED TRADERS | 9.08 | 0 | 100
7209 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- II/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 972/BQA | 28/04/2023 | 705 | GOUTAM BHOWMIK | 166.52 | 104.87 | 40
7210 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-2A) (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000625/2022-2023 | 181/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.44 | 3.05 | 0
7211 | Bankura Division | Khatra Sub-Division | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001146/2023-2024 | 351/BQA | 05/02/2024 | 120 | GOUR GORAI | 20.72 | 19.93 | 50
7212 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 135 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- II/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001762/2024-2025 | 487/BQA | 25/02/2025 | 259 | PARTHA SARATHI PATRA | 10.43 | 0 | 0
7213 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 2 nos. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme (SM/15008), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/B Water supply scheme (SM/15002), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- III/A Water supply scheme (SM/15005), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- III/B Water supply scheme (SM/18495) and 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- IV/A Water supply scheme (SM/15006) within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001909/2024-2025 | 153\KSD | 07/03/2025 | 10 | SRIJAN CONSTRUCTION | 0.9 | 0 | 90
7214 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 3.64 | 0 | 0
7215 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000201/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 5.9 | 0 | 0
7216 | Bankura Mechanical | Khatra Sub-Division | New service connection at OHR site Zone-2A of Augmentation of Mukutmonipur,khatra Ranibandh piped water supply scheme ( Tentulchita) | Assistant Engineer | Junior Engineer | BILL/01174/2024-2025 | BP-2024-25-303 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.62 | 0 | 0
7217 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-2A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 1784/BMD | 01/08/2023 | 120 | S P ENTERPRISE (SILIGURI) | 26.41 | 0 | 0
7218 | Bankura Division | Brishnupur Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION | Assistant Engineer | Junior Engineer | BILL/01263/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7219 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 132.11 | 55
7220 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Panahar Piped Water Supply Scheme (SM/18790) & 2 nos. sites of Lego Piped Water Supply Scheme (SM/14177) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001877/2024-2025 | 555/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 100
7221 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000087/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 86.97 | 0 | 0
7222 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-I of Lego W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01347/2024-2025 | BP-2024-25-350 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.65 | 0 | 0
7223 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Lego Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000148/2025-2026 | 443/BMD | 10/06/2025 | 90 | TAPAN KUMAR SARKAR | 11.86 | 0 | 0
7224 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 132.8 | 55
7225 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 2 nos. sites of Naruala Piped Water Supply Scheme (SM/13789), 2 nos. sites of Manik Bazar Piped Water Supply Scheme (SM/16705)within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001899/2024-2025 | 577/VSD | 27/09/2024 | 15 | PARTHA ROY | 0.6 | 0 | 0
7226 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 6.46 | 0 | 0
7227 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000069/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 13.87 | 0 | 0
7228 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for NARUALA TW-1 Water supply scheme(JLNO-123,PLOT-1041) under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00007/2024-2025 | BP-2024-25-34 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.47 | 0 | 0
7229 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for NARUALA TW-2(JL NO-122, PLOT-70) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00008/2024-2025 | BP-2023-24 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
7230 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Narula Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000154/2025-2026 | 449/BMD | 10/06/2025 | 90 | S. G. TECHNICAL SERVICE | 10.9 | 0 | 0
7231 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) | Assistant Engineer | Junior Engineer | BILL/00660/2024-2025 |  | 09/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0
7232 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) | Assistant Engineer | Junior Engineer | BILL/01236/2024-2025 | BP-226/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0
7233 | Bankura Division | Khatra Sub-Division | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1135/BQA | 15/05/2023 | 901 | SWAPAN KUMAR UPADHYAY | 228.33 | 88.61 | 45
7234 | Bankura Division | Khatra Sub-Division | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000187/2024-2025 | 1859/BQA | 12/07/2024 | 45 | M/S TARUN KUMAR PATRA | 13.69 | 0 | 100
7235 | Bankura Division | Khatra Sub-Division | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-8A) (Sl. No. 14) | Assistant Engineer | Junior Engineer | ORD/000633/2022-2023 | 192/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.46 | 3.32 | 0
7236 | Bankura Division | Khatra Sub-Division | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VIII/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001374/2024-2025 | 21/BQA | 02/01/2025 | 485 | EARTH MOVING (INDIA) | 21.51 | 0 | 75
7237 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 180 Cum., staging height 20 Mtr.) including by pass arrangement and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VIII/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001768/2024-2025 | 491/BQA | 25/02/2025 | 243 | TAPAN KUMAR MANDAL | 9.46 | 0 | 0
7238 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 1.24 | 0 | 0
7239 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000212/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 8.72 | 0 | 0
7240 | Bankura Mechanical | Khatra Sub-Division | New service connection at Mukutmonipur,Khatra & Ranibandh W/S scheme ,Zone-VIII/A (Bhurkura) | Assistant Engineer | Junior Engineer | BILL/02194/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0
7241 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-8A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 1120/BMD | 24/05/2023 | 45 | AMITAVA CHAKRABORTY | 26.24 | 0 | 0
7242 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 125 | Assistant Engineer | Junior Engineer | ORD/000008/2020-2021 | 609/BQA | 10/02/2021 | 30 | OSMAN SEKH | 8.39 | 3.14 | 0
7243 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 140 | Assistant Engineer | Junior Engineer | ORD/000009/2020-2021 | 610/BQA | 10/02/2021 | 30 | SWAPAN KUMAR BIT | 9.6 | 9.6 | 0
7244 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 290 | Assistant Engineer | Junior Engineer | ORD/000011/2020-2021 | 612/BQA | 10/02/2021 | 30 | SWAPAN KUMAR BIT | 19.65 | 14.01 | 0
7245 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 289 | Assistant Engineer | Junior Engineer | ORD/000012/2020-2021 | 613/BQA | 10/02/2021 | 30 | OSMAN SEKH | 18.09 | 10.23 | 0
7246 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 | Assistant Engineer | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 0.93 | 0
7247 | Bankura Division | Brishnupur Sub-Division | Work Order for Laying HDPE pipeline from Dhabani Shib Mandir to Keliapathar village to increase pressure in Keliapathar village in Gobarda (152) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 210/KSD | 03/06/2022 | 20 | D. S. ENTERPRISE | 4.02 | 3.88 | 0
7248 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2022-2023 | 2036/BQA | 29/09/2022 | 0 | Resource Division | 1.9 | 0 | 0
7249 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Indas W/S Scheme under Bishnupur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001559/2021-2022 | FHTC/11 | 11/10/2021 | 0 | SWAPAN KUMAR DE | 6.15 | 0 | 0
7250 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67, Total House Hold - 166 out of 1275 Part-A (Phase-2) | Assistant Engineer | Junior Engineer | ORD/000211/2021-2022 | 3047/BQA | 01/12/2021 | 30 | KOUSIK MONDAL | 12.53 | 8.46 | 0
7251 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, | Assistant Engineer | Junior Engineer | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0
7252 | Bankura Division | Brishnupur Sub-Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456, | Assistant Engineer | Junior Engineer | VCH/001589/2021-2022 | FHTC/08 | 08/10/2021 | 0 | MUNMUN UPADHYAY | 33.29 | 0 | 0
7253 | Bankura Division | Brishnupur Sub-Division | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., | Assistant Engineer | Junior Engineer | VCH/001590/2021-2022 | FHTC/08 | 08/10/2021 | 0 | KASTURI ROY | 2.17 | 0 | 0
7254 | Bankura Division | Brishnupur Sub-Division | Siromonipur to Nandagram ( WB-03-326) of Scheme Name Nandagram PWSS (SM/14248) | Assistant Engineer | Junior Engineer | BILL/02020/2024-2025 |  | 25/03/2025 | 0 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 6.3 | 0 | 0
7255 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 228.24 | 55
7256 | Bankura Division | Brishnupur Sub-Division | Supply, delivery, installation of PVC flex containing information of schemes of JJM within Joypur & Sonamukhi Blocks under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001777/2024-2025 | 464/VSD | 16/08/2024 | 10 | PARTHA ROY | 2.16 | 0 | 100
7257 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 3 nos. sites of Nandagram Piped Water Supply Scheme (SM/14248) & 2 nos. sites of Khiri Piped Water Supply Scheme (SM/18436) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001881/2024-2025 | 559/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 100
7258 | Bankura Division | Brishnupur Sub-Division | Construction of FHTC Platform, Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Joyrambati Piped Water Supply Scheme & Nandagram Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001936/2024-2025 | 657/BQA | 11/03/2025 | 90 | S B ASSOCIATES | 63.67 | 0 | 0
7259 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2024-2025 | 2994/BQA | 28/11/2024 | 0 | Resource Division | 19.29 | 0 | 0
7260 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000091/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 105.33 | 0 | 0
7261 | Bankura Mechanical | Brishnupur Sub-Division | Nandagram Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01502/2023-2024 | BP-2023-24-100 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.36 | 0 | 0
7262 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandagram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000149/2025-2026 | 444/BMD | 10/06/2025 | 90 | AMITAVA CHAKRABORTY | 12.97 | 0 | 0
7263 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Godardihi (Zone - E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000510/2023-2024 | 2361/BQA | 14/08/2023 | 870 | MUNMUN UPADHYAY | 177.79 | 58.71 | 77
7264 | Bankura Division | Bankura Sadar Sub-Division | Construction of High Lift Pump House and Boundary Wall under Augmentation works for Godardihi (Zone- E) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001400/2024-2025 | 45/BQA | 02/01/2025 | 454 | MUNMUN UPADHYAY | 31.04 | 0 | 0
7265 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000077/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.23 | 0 | 0
7266 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000228/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
7267 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00140/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
7268 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Godardihi ( Zone-E) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2023-2024 | 1405/BMD | 18/07/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.77 | 61.83 | 74
7269 | Bankura Division | Bankura Sadar Sub-Division | Balance allied works of augmentation works for Harialgara ( Zone-O ) under Bankura - I, II & Barjora Block water supply scheme. | Assistant Engineer | Junior Engineer | ORD/000186/2024-2025 | 1815/BQA | 11/07/2024 | 570 | SUBHADIP KOLE | 245 | 0 | 0
7270 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of HARIALGORA (Zone - O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 2044/BQA | 24/07/2023 | 891 | PRADIP RAJAK | 310.94 | 166.87 | 54
7271 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe line to increase pressure at junbedia gajantala & Bagdipara for Augmentation of HARIALGORA (Zone - O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2025-2026 | 809/BSD | 01/09/2025 | 15 | PRATAP CHANDRA TEWARI | 2.35 | 0 | 100
7272 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Harialgara (Zone- O) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001197/2023-2024 | 450/BQA | 08/02/2024 | 30 | LEMNISCATE | 3.08 | 0 | 100
7273 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2024-2025 | 1736/BQA | 05/07/2024 | 0 | Resource Division | 16.9 | 0 | 0
7274 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000082/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4.42 | 0 | 0
7275 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000240/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 4.42 | 0 | 0
7276 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00146/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
7277 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01613/2023-2024 | BP-2023-24-138 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
7278 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Harialgara (Zone-O) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000141/2025-2026 | 436/BMD | 10/06/2025 | 90 | M.S. ENTERPRISE | 26.28 | 0 | 0
7279 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Harialgara (Zone O) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 1882/BMD | 17/08/2023 | 120 | MAHADEV ENTERPRISE | 81.83 | 34.82 | 42
7280 | Bankura Division | Bankura Sadar Sub-Division | payment to rail | Assistant Engineer | Junior Engineer | BILL/00004/2023-2024 | Rail04 | 11/04/2023 | 0 | SOUTH EASTERN RAILWAY | 0.98 | 0 | 0
7281 | Bankura Division | Bankura Sadar Sub-Division | Proposal of i) Bankura Saltora Road from CH : 11.715 KM and CH: 14.20 KM permanent restoration of road for the purpose of Jack pushing and opened cut method and pipe laying along Bankura Saltora Road for works under Augmentation of Sarberia water supply scheme by PHE under Bankura HIGHWAY Division in the district of Bankura. | Assistant Engineer | Junior Engineer | BILL/02131/2023-2024 | FHTC/12 | 13/12/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 78.25 | 0 | 0
7282 | Bankura Division | Bankura Sadar Sub-Division | Bill for Road restoration of Bankura Saltora Road From CH:11.715 KM and CH:14.20 KM for the purpose of Jack pushing and opened cut method and pipe laying along Bankura Saltora Road for works under Augmentation of Sarberia water supply scheme | Assistant Engineer | Junior Engineer | BILL/02843/2025-2026 |  | 11/03/2026 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 78.13 | 0 | 0
7283 | Bankura Division | Bankura Sadar Sub-Division | Construction and Commissioning of Balance 'FHTC (Funtional House Hold Tap Connection) in mouzas of Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). Block - Chhatna, Dist.- Bankura under Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block : - Chhatna, Name of Zone - Sarberia (Zone - I & II), No. of Mouza :- 38 nos. (Barabakra, Khairkanali, Laxminarayanpur, Kantasol, Pinasgoria, Ghoramuli, Dubrajpur, Bamunkuli, Mandaspara, Chowghara, Panchpukhuria, Janardanpur, Jhagrapur, Bhalaidiha, Brajamohanpur, Dhengakend, Gharamora, Musibdihi, Lohagar, Benagoria, Kalpathar, Ghosergram, Chamkara, Basulibandh, Karra, Beliara, Hari bandi, Migra, Siuligarya, Sarberia, Pathardihi, Mujra Kundi, Jamdahari, Kamarkuli, Kuludihi, Gurpota, Kalaiberia & Banagram). Total House Hold - 50 nos. | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 803/BQA | 11/04/2023 | 996 | MANAS DEY | 13.61 | 0 | 91
7284 | Bankura Division | Bankura Sadar Sub-Division | Construction and Commissioning of 'FHTC (Funtional House Hold Tap Connection) in mouzas of Rejuvenation of SARBERIA W/S Scheme ( Zone-II ) (including Left out BRGF Mouzas] Block - Chhatna, Dist.- Bankura under JAL SWAPNA & Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 1197/BQA | 22/05/2023 | 90 | PARTHA PRATIM CHHATAIT | 162.81 | 0 | 5
7285 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000068/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.28 | 0 | 0
7286 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000219/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.28 | 0 | 0
7287 | Bankura Division | Bankura Sadar Sub-Division | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Proposed Ground Water Based Nakaijuri Piped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Mouza - Nakaijuri & Gorasol under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 2274/BQA | 01/08/2023 | 270 | SUBHANKAR BANERJEE | 263.83 | 46.31 | 25
7288 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 100 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/3/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Nakaijuri PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Onda, District -Bankura . Name of Muza - Gorasole & Nakaijuri | Assistant Engineer | Junior Engineer | ORD/000636/2022-2023 | 574/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 100
7289 | Bankura Division | Bankura Sadar Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Gorasol (JL No- 278), Nakaijuri (JL No- 279) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001090/2021-2022 | 284\BSD | 21/03/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.74 | 2.74 | 97
7290 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000044/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0
7291 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.56 | 0 | 0
7292 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000215/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
7293 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/01606/2023-2024 | BP-2023-24-140 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0
7294 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at TW No-III of Nakaijuri and its Adjoining mouza water supply scheme under Onda Block under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000148/2024-2025 | 491/BMD | 09/07/2024 | 120 | SWAPAN ENTERPRISE | 19.95 | 0 | 0
7295 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000387/2023-2024 | 1709/BMD | 28/07/2023 | 60 | M/S BIPUL BANERJEE | 37.92 | 18.15 | 48
7296 | Bankura Division | Bankura Sadar Sub-Division | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 | Assistant Engineer | Junior Engineer | BILL/00958/2024-2025 |  | 20/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0
7297 | Bankura Division | Bankura Sadar Sub-Division | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. | Assistant Engineer | Junior Engineer | BILL/00959/2024-2025 |  | 20/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0
7298 | Bankura Division | Bankura Sadar Sub-Division | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. | Assistant Engineer | Junior Engineer | BILL/01243/2024-2025 | BP-314/2024-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0
7299 | Bankura Division | Bankura Sadar Sub-Division | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 | Assistant Engineer | Junior Engineer | BILL/01244/2024-2025 | BP-313/2024-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0
7300 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 2269/BQA | 01/08/2023 | 974 | M/S TARUN KUMAR PATRA | 153.91 | 0 | 82
7301 | Bankura Division | Bankura Sadar Sub-Division | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for official use of Deputy Superintendig Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2023 to 30/09/2023 (183 Days). | Assistant Engineer | Junior Engineer | ORD/001175/2022-2023 | 287\BSD | 24/03/2023 | 183 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.04 | 100
7302 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000070/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.64 | 0 | 0
7303 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000221/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.64 | 0 | 0
7304 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) & Sinking of 01 (One) no. 200 mm X 165 mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura. No. of Household- 120 nos | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 795/BQA | 11/04/2023 | 90 | SAIKAT CHOWDHURY | 50.64 | 42.85 | 85
7305 | Bankura Division | Bankura Sadar Sub-Division | Construction of 01 (One) no. Pump House (5.40 M X 3.6M) including sanitary arrangement & land development work in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 886/BQA | 19/04/2023 | 713 | ARIJIT GUHA | 8.25 | 6.74 | 100
7306 | Bankura Division | Bankura Sadar Sub-Division | Construction of Boundary Wall in connection with Jal Jeevan Mission (JJM) for for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte.(Length 90 Mtr) | Assistant Engineer | Junior Engineer | ORD/000465/2023-2024 | 2387/BQA | 14/08/2023 | 930 | MUKHERJEE CONSTRUCTION | 14.97 | 8.07 | 95
7307 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation for Gouripur Water Supply Scheme. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001191/2023-2024 | 443/BQA | 08/02/2024 | 30 | LEMNISCATE | 0.46 | 0 | 100
7308 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000093/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.43 | 0 | 0
7309 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000266/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.43 | 0 | 0
7310 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation for Gouripur Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00153/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
7311 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Gouripur Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000452/2023-2024 | 1778/BMD | 01/08/2023 | 600 | KASHINATH DEY | 23.42 | 22.34 | 100
7312 | Bankura Division | Khatra Sub-Division | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of 50 Cum. Clear Water Reservoir, Pump House and Boundary Wall, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000507/2023-2024 | 2359/BQA | 14/08/2023 | 270 | SUMITA UPADHYAY | 164.56 | 0 | 30
7313 | Bankura Division | Khatra Sub-Division | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 70
7314 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000004/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 25.08 | 0 | 0
7315 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000177/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.35 | 0 | 0
7316 | Bankura Mechanical | Khatra Sub-Division | New service connection at 1st CWR site of Banpukuria Water supply scheme | Assistant Engineer | Junior Engineer | BILL/01176/2024-2025 | BP-2024-25-299 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0
7317 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation work for Banpukuria under Khatra- Hirbandh- Ranibandh water supply scheme Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2207/BMD | 21/11/2023 | 180 | M/S BIPUL BANERJEE | 40.48 | 31.94 | 78
7318 | Bankura Division | Khatra Sub-Division | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 1 No. CWR at OHR site, Construction of 1 No. Pump House at Tubewell site, Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2024-2025 | 1521/BQA | 19/06/2024 | 30 | SINGHA ENTERPRISE | 51.88 | 14.76 | 70
7319 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Arkama OHR site to Rangibari and Amdiha village to Bena G.P. Office to increase pressure at Gopisagar & Rangibari Village in connection with Augmentation of Arkama (Zone-H) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2024-2025 | 2133/BQA | 07/08/2024 | 178 | JAGABANDHU MONDAL | 3.93 | 3.84 | 70
7320 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000446/2023-2024 | 254/KSD | 24/08/2023 | 7 | M/S SUPRIYA CHATTERJEE | 0.95 | 0.94 | 20
7321 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000448/2023-2024 | 256/KSD | 24/08/2023 | 7 | M/S SUPRIYA CHATTERJEE | 0.7 | 0.7 | 20
7322 | Bankura Division | Khatra Sub-Division | Work Order for Interconnection of newly laid pipeline and existing pipeline near Sindurpeti village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2023-2024 | 258/KSD | 24/08/2023 | 7 | GOURANGA CHATTERJEE | 0.7 | 0.69 | 20
7323 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 726/BQA | 30/03/2023 | 45 | UTTAM KUMAR SINHAMAHAPATRA | 48.95 | 48.95 | 100
7324 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to increase pressure in Damodarpur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 247/BQA | 25/01/2024 | 30 | BIKASH MANDAL | 5.11 | 5.08 | 80
7325 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000169/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.96 | 0 | 0
7326 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Arkama (Zone H) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 247/BMD | 14/05/2025 | 90 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.11 | 0 | 0
7327 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for for Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000169/2024-2025 | 511/BMD | 09/07/2024 | 120 | RAJIB COMPANY | 44.01 | 0 | 0
7328 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at CWR site for for Augemention works for Arkama (zone H) Under Khatra Hirbandh Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000880/2024-2025 | 2040/BMD | 07/03/2025 | 120 | M/S TARUN KUMAR PATRA | 42.61 | 0 | 0
7329 | Bankura Division | Brishnupur Sub-Division | Sinking of 3 nos. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Kushmuri Zone- A piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 2627/BQA | 21/09/2023 | 477 | GOUTAM GHOSH | 56.84 | 0 | 70
7330 | Bankura Division | Brishnupur Sub-Division | Laying distribution system for Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000678/2023-2024 | 2628/BQA | 21/09/2023 | 222 | MAYA CONSTRUCTION | 10.92 | 9.09 | 15
7331 | Bankura Division | Brishnupur Sub-Division | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- A Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2023-2024 | 2629/BQA | 21/09/2023 | 553 | SAYED PAHALOWAN | 13.23 | 0 | 30
7332 | Bankura Division | Brishnupur Sub-Division | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- A water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2023-2024 | 2630/BQA | 21/09/2023 | 180 | ANNDAMAYEE CONSTRUCTION | 8.86 | 0 | 0
7333 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | Assistant Engineer | Junior Engineer | ORD/000757/2023-2024 | 2864/BQA | 11/10/2023 | 538 | GOURANGA NANDI | 28.65 | 20.69 | 95
7334 | Bankura Division | Brishnupur Sub-Division | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | Assistant Engineer | Junior Engineer | ORD/000759/2023-2024 | 2865/BQA | 11/10/2023 | 45 | MOHAN KUMAR ROY | 28.65 | 25.24 | 45
7335 | Bankura Division | Brishnupur Sub-Division | Construction of Boundary Wall and Pump House for Augmentation of Kushmuri (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001357/2024-2025 | 3178/BQA | 24/12/2024 | 90 | BIJOY KOLEY | 12.97 | 0 | 0
7336 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00176/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
7337 | Bankura Mechanical | Brishnupur Sub-Division | 3 phase new connection at Khatnagar (Khusmuri Zone-A) Indus Block | Assistant Engineer | Junior Engineer | BILL/01334/2024-2025 | BP-2024-25-336 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0
7338 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kushmuri CWR site under Kushmuri zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000123/2024-2025 | 1071/BMSD | 05/07/2024 | 376 | UNICON | 4.38 | 0 | 100
7339 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 776/BMD | 20/08/2024 | 120 | M.S. ENTERPRISE | 14.05 | 0 | 100
7340 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 1700/BMD | 28/07/2023 | 891 | TAPAN KUMAR SARKAR | 59.31 | 31.25 | 53
7341 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PRAKASH ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1966/BQA | 18/07/2023 | 624 | SIB SANKAR CHOWDHURY | 164.12 | 34.49 | 60
7342 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no Tubewell and Construction of Pump House for Augmentation of Prakash (Zone - A) Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001366/2024-2025 | 3130/BQA | 19/12/2024 | 90 | ZAKIR HOSSIN MONDAL | 20.45 | 0 | 15
7343 | Bankura Division | Brishnupur Sub-Division | Instalation of scheme information board for 1 no. sites of Augmentation of Prakash Zone-A Water Supply Scheme (SM/17222), 4 nos. sites of Augmentation of Chakuparsole Zone-A Water Supply Scheme (SM/17425) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001802/2024-2025 | 531/VSD | 27/09/2024 | 15 | SANTANU GARAI | 0.75 | 0 | 0
7344 | Bankura Division | Brishnupur Sub-Division | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1116/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 12.59 | 100
7345 | Bankura Division | Brishnupur Sub-Division | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 526 | MACKINTOSH BURN LIMITED | 13769.53 | 0 | 55
7346 | Bankura Division | Brishnupur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000097/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 163.02 | 0 | 0
7347 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Nandur w/s scheme at Patrasayer block under BMD PHE Dte.(SM/18252) | Assistant Engineer | Junior Engineer | BILL/00359/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0
7348 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000417/2025-2026 | 581/BMD | 04/07/2025 | 90 | OSMAN SEKH | 12.68 | 0 | 0
7349 | Bankura Division | Bankura Sadar Sub-Division | Wayleave/Track crossing proposal with application ID:SER-ADRA-WL-12 For Cherabasta (zone-k) SM Code-SM/SM/17697 | Assistant Engineer | Junior Engineer | BILL/00060/2024-2025 | FHTC/04 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY | 0.11 | 0 | 0
7350 | Bankura Division | Bankura Sadar Sub-Division | Payment of Wayleave facility charges of CHERABASTA (ZONE-K) W/S Scheme. Scheme Code-SM/17697. Application ID-SER-ADRA-2024-WL-12 | Assistant Engineer | Junior Engineer | BILL/00275/2024-2025 | BP-113/2024-25 | 19/06/2024 | 0 | SOUTH EASTERN RAILWAY | 6.4 | 0 | 0
7351 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 234/10 -11) in between Bikna Rly. Station and Bankura Rly. station in Mobarakpur mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for Rising main pipe line under Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000192/2025-2026 | 1327/BQA | 17/06/2025 | 45 | GOPAL CHANDRA CHOWDHURY | 47.66 | 0 | 0
7352 | Bankura Division | Bankura Sadar Sub-Division | Augmentation works for CHERABASTA (ZONE - K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Phase - I Project). | Assistant Engineer | Junior Engineer | ORD/000331/2023-2024 | 2001/BQA | 19/07/2023 | 983 | S.N POLYMERS PVT LTD | 297.16 | 136.23 | 55
7353 | Bankura Division | Bankura Sadar Sub-Division | Creation of Balance FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of CHERABASTA (Zone - K)) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Cherabasta No.of Mouza :- 01 nos. Teleghara . Total House Hold -13 nos. | Assistant Engineer | Junior Engineer | ORD/000562/2022-2023 | 61/BSD | 24/01/2023 | 7 | COSMIC CONSTRUCTION | 0.97 | 0.97 | 100
7354 | Bankura Division | Bankura Sadar Sub-Division | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at Gopinathpur (271), Teleghara (286 ), Bagneja (287), Ailtha (281) & Cherabasta (256), of Swajal Gram/Har Ghar Jal Villages for awareness generation among the pepole of Bankura Sadar Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001060/2023-2024 | 1176/BSD | 22/11/2023 | 15 | TAPAS DEY | 0.69 | 0.68 | 100
7355 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Cherabasta (Zone- K) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001193/2023-2024 | 446/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.31 | 0 | 100
7356 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House, Pump House cum chlorine room & Toilet, Boundary wall of Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2024-2025 | 360/BQA | 07/02/2025 | 328 | SAIKAT CHOWDHURY | 37.52 | 0 | 0
7357 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000130/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.92 | 0 | 0
7358 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000257/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.92 | 0 | 0
7359 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00136/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
7360 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Cherabasta (Zone-K) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000312/2023-2024 | 1411/BMD | 18/07/2023 | 60 | DEBJYOTI BASU | 81.81 | 65.59 | 80
7361 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- I at Tail End site of Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II and Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000315/2024-2025 | 856/BMD | 29/08/2024 | 120 | CHAKRABORTY MINING & ENGINEERING. | 9.23 | 3.87 | 60
7362 | Bankura Division | Bankura Sadar Sub-Division | Laying of 150 mm dia underground water pipe line carrier with 600 mm dia MS casing under Railway Track of KM 239/4-5 in beet ween Rly station Bikna Nabanda station beet ween Bankura Masagram section | Assistant Engineer | Junior Engineer | BILL/00026/2024-2025 | FHTC/04 | 18/04/2024 | 0 | SOUTH EASTERN RAILWAY | 5.63 | 0 | 0
7363 | Bankura Division | Bankura Sadar Sub-Division | Crossing Rail Track ( South Eastern RLY. K.M. 239/4 -5) in between Bikna-Nobanda) Rly. Station and Bankura-Masagram Rly. station in Nabanda mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Augmentation of CHAtarkanali (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2025-2026 | 1326/BQA | 17/06/2025 | 45 | M/S TARUN KUMAR PATRA | 50.82 | 0 | 0
7364 | Bankura Division | Bankura Sadar Sub-Division | Construction of High lift Pump House at OHR Site of departmental design & drawing in connection with Jal Jeevan Mission (JJM) for Augmentation of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2024-2025 | 2343/BQA | 09/09/2024 | 660 | ASHIS PAL | 18 | 0 | 0
7365 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 2271/BQA | 01/08/2023 | 270 | MADHU SUDAN RAKSHIT | 198.06 | 86.21 | 70
7366 | Bankura Division | Bankura Sadar Sub-Division | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Chatarkanali (Zone- L) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001194/2023-2024 | 447/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.69 | 0 | 100
7367 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000131/2023-2024 | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.95 | 0 | 0
7368 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000255/2023-2024 | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.95 | 0 | 0
7369 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00137/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
7370 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Narrah mouza for Chaterkanali augmentation site under BMD PHE Dte.(SM/17698) | Assistant Engineer | Junior Engineer | BILL/01468/2024-2025 | BP-2024-25-361 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
7371 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work ofProviding and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Chaterkanali (Zone-L) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 1464/BMD | 18/07/2023 | 60 | TAPAN KUMAR DEY | 81.77 | 52.56 | 64
7372 | Bankura Division | RWS Bankura Sub-Division | Laying HDPE pipeline from Dighi to Dhajamanipur and at Brahmadanga village to increase pressure at Dhajamanipur and Brahmadanga village in connection with Augmentation of Naria (Zone-E) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 2304/BQA | 04/09/2024 | 485 | MANAS DEY | 7.44 | 0 | 90
7373 | Bankura Division | RWS Bankura Sub-Division | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000452/2023-2024 | 260/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.74 | 0.74 | 25
7374 | Bankura Division | RWS Bankura Sub-Division | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 262/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.6 | 0.6 | 25
7375 | Bankura Division | RWS Bankura Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-E (Naria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 557/BQA | 17/03/2023 | 45 | ASHOKE KUMAR DEY | 72.75 | 72.72 | 55
7376 | Bankura Division | RWS Bankura Sub-Division | Laying pipeline, providing FHTC (Functional House Hold Tap Connection) with all allied works of Zone-E (Naria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001785/2024-2025 | 496/BQA | 25/02/2025 | 60 | ID MOHAMMAD MANDAL | 2.2 | 0 | 90
7377 | Bankura Division | RWS Bankura Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000166/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.59 | 0 | 0
7378 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Naria (Zone E) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000056/2025-2026 | 252/BMD | 14/05/2025 | 90 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0
7379 | Bankura Division | Brishnupur Sub-Division | Repairing and Renovation of RCC Elevated Over Head Reservoir of 250 cum capacity with staging height 20 m and other allied works in connection with Somsar (BRGF) water supply scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000373/2024-2025 | 2351/BQA | 09/09/2024 | 204 | TAPAN KUMAR MANDAL | 9.49 | 0 | 100
7380 | Bankura Division | Brishnupur Sub-Division | Sinking of 1 no. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Laying of distribution system and Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Somsar W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :-Kumna, No. of Mouzas Covered :- 3 nos., Name of Mouzas & JL No.:-Bhagabatipur (1), Palashdanga (3), Kumna (4) Total No. House Hold:- 320 | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000797/2022-2023 | 680/BQA | 28/03/2023 | 735 | SUBHENDU SEKHAR GORAI | 53.76 | 38.81 | 75
7381 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of HSC Pumping machinery set with other allied works at CWR site for augmentation of Somsar water supply scheme under Bankura Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000341/2024-2025 | 785/BMD | 20/08/2024 | 240 | ABHIJIT MUKHERJEE | 34.91 | 7.48 | 60
7382 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000099/2021-2022 | 2496/BQA | 23/09/2021 | 30 | ASOKE BHATTACHARYYA | 52.85 | 14.86 | 0
7383 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline to cover Jamirapara (50) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2021-2022 | 546/BQA | 11/03/2022 | 30 | ASHOKE KUMAR DEY | 24.68 | 23.15 | 0
7384 | Bankura Division | Khatra Sub-Division | Work Order for Household survey in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000584/2021-2022 | 789/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.32 | 0 | 0
7385 | Bankura Division | Khatra Sub-Division | Laying of extra UPVC pipeline in Parashia (47) & Jamirapara (50) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000666/2022-2023 | 509/BQA | 13/03/2023 | 45 | MANAS DEY | 4.52 | 0 | 0
7386 | Bankura Division | Khatra Sub-Division | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | VCH/000461/2022-2023 | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.3 | 0 | 0
7387 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002762/2021-2022 | FHTC/4 | 04/03/2022 | 0 | MUNMUN UPADHYAY | 34.71 | 0 | 0
7388 | Bankura Division | Khatra Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Sanpura, Kalipahari), Total House Hold - 451 | Assistant Engineer | Junior Engineer | VCH/002770/2021-2022 | FHTC/4 | 04/03/2022 | 0 | TARINI CHARAN UPADHYAY | 27.97 | 0 | 0
7389 | Bankura Division | Khatra Sub-Division | Construction of 3 (Three) Nos. Pump House and Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2025-2026 | 832/BQA | 07/04/2025 | 184 | TAPAS KUMAR HAZRA | 58.06 | 0 | 0
7390 | Bankura Division | Khatra Sub-Division | Laying of HDPE pipeline, Sinking of 3 Nos. 300 mm X 200 mm X 250 Metre deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2024-2025 | 1484/BQA | 18/06/2024 | 90 | SIBSANKAR CHOWDHURY | 96.77 | 0 | 0
7391 | Bankura Division | Khatra Sub-Division | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 01) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000327/2023-2024 | 196/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0.97 | 95
7392 | Bankura Division | Khatra Sub-Division | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 02) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2023-2024 | 197/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0.97 | 95
7393 | Bankura Division | Khatra Sub-Division | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 03) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000329/2023-2024 | 198/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0.97 | 90
7394 | Bankura Division | Khatra Sub-Division | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 04) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000330/2023-2024 | 199/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.95 | 0.9 | 95
7395 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000180/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.96 | 0 | 0
7396 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | BILL/00209/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
7397 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00385/2024-2025 | BP-2024-25-83 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
7398 | Bankura Mechanical | Khatra Sub-Division | New3 Phase Service Connection for Belatikri | Assistant Engineer | Junior Engineer | BILL/00699/2024-2025 | BP-2024-25-162 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
7399 | Bankura Division | Khatra Sub-Division | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 2039/BQA | 24/07/2023 | 270 | UNIVERSAL CONSTRUCTION | 154.39 | 98.29 | 30
7400 | Bankura Division | Khatra Sub-Division | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000824/2023-2024 | 2943/BQA | 30/10/2023 | 120 | M/S SUPRIYA CHATTERJEE | 11.74 | 11.64 | 100
7401 | Bankura Division | Khatra Sub-Division | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000825/2023-2024 | 2944/BQA | 30/10/2023 | 30 | RAHIBUDDIN MANDAL | 11.74 | 11.5 | 100
7402 | Bankura Division | Khatra Sub-Division | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000834/2023-2024 | 2960/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.37 | 2.31 | 96
7403 | Bankura Division | Khatra Sub-Division | Work Order for Installation of scheme information board for 5 nos. site of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17713] and 1 no. site of Augmentation works for Belatikri, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17292] within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001918/2024-2025 | 162\KSD | 07/03/2025 | 10 | PRADYUMNA KOLEY | 0.9 | 0 | 90
7404 | Bankura Division | Khatra Sub-Division | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001976/2024-2025 | 670/BQA | 12/03/2025 | 90 | SAIKAT CHOWDHURY | 18.11 | 0 | 0
7405 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri Zone-A JL-30, Plot-104 | Assistant Engineer | Junior Engineer | BILL/01151/2024-2025 | BP-2024-25-278 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0
7406 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri Zone-A , Jl -39, Plot-233 | Assistant Engineer | Junior Engineer | BILL/01153/2024-2025 | BP-2024-25-279 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0
7407 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Voltage Stabilizer and submersible pumping machineries with other allied works for Augmentation of Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000513/2024-2025 | 573/BMD | 23/07/2024 | 750 | TAPAN KUMAR SARKAR | 25.19 | 0 | 0
7408 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Additional work for Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Belatikri Zone-A water supply scheme(BRGF Ph-I) under Jal Jeevan Mission Progremme under Bankura Mechanical Division PHE Dte, Dist.-Bankura. | Assistant Engineer | Junior Engineer | ORD/000011/2024-2025 | 519/BMSD(D) | 11/06/2024 | 21 | M.S. ENTERPRISE | 2.8 | 2.77 | 100
7409 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000569/2023-2024 | 2026/BMD | 01/09/2023 | 911 | M.S. ENTERPRISE | 96.39 | 84.82 | 70
7410 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase-I) at tubewell No I Pump House No I under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001032/2023-2024 | 2964/BMD | 29/02/2024 | 180 | INDRAJIT MITRA | 12.8 | 8.18 | 50
7411 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No II Pump House No II under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001035/2023-2024 | 2967/BMD | 29/02/2024 | 712 | PRADIP KUMAR DHABAL | 12.8 | 0 | 65
7412 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No III Pump House No III under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001038/2023-2024 | 2970/BMD | 29/02/2024 | 180 | M/S DAS & SARKAR ENTERPRISE | 12.76 | 7.52 | 50
7413 | Bankura Division | Khatra Sub-Division | Laying HDPE pipeline from Dakai to Madhabpur village to increase pressure at Madhabpur Village in connection with Augmentation of Hetiasole (Zone-IIB) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2024-2025 | 2303/BQA | 04/09/2024 | 151 | JAGABANDHU MONDAL | 2.78 | 2.65 | 70
7414 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 559/BQA | 17/03/2023 | 45 | SK. SAHAJAHAN | 32.01 | 28.37 | 50
7415 | Bankura Division | Khatra Sub-Division | Sinking of 3 (Three) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001130/2023-2024 | 202/BQA | 24/01/2024 | 75 | UTTAM KUMAR SINHAMAHAPATRA | 22.34 | 20.94 | 90
7416 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000171/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.91 | 0 | 0
7417 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Hetiasol (Zone IIB) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000041/2025-2026 | 245/BMD | 14/05/2025 | 90 | TAPAN KUMAR DEY | 28.18 | 0 | 0
7418 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Dahala W.S Scheme under Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000151/2024-2025 | 494/BMD | 09/07/2024 | 328 | ABHIJIT MUKHERJEE | 65.43 | 0 | 63
7419 | Bankura Division | Bankura Sadar Sub-Division | Purchase of land for proposed 02 Nos. of OHR for Improvement of khatra-Hirbandh-Ranibandh w/s scheme under BRGF (Phase - I) | Assistant Engineer | Junior Engineer | BILL/00031/2022-2023 |  | 30/11/2022 | 0 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 22.6 | 0 | 0
7420 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 200 mm dia MS pipe by Jack pushing method, interconnection of Rising Main (Zone-M1 & M2) with pumping main, laying & fabrication of MS pipe in another 3 (Three) Nos. places with all allied works for balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 828/BQA | 17/04/2023 | 30 | M/S TARUN KUMAR PATRA | 12.53 | 12.52 | 100
7421 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( Total FHTC- 1033) No of FHTC- 517 ( PART-B ) | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 2534/BQA | 08/09/2023 | 936 | MUNMUN UPADHYAY | 36.75 | 0 | 0
7422 | Bankura Division | Bankura Sadar Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.05.2023 to 31.07.2023. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 85/KSD | 24/04/2023 | 92 | SRIKANTA MONDAL | 0.44 | 1.2 | 50
7423 | Bankura Division | Bankura Sadar Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2023 to 31/12/2023. | Assistant Engineer | Junior Engineer | ORD/000422/2023-2024 | 161/KSD | 30/06/2023 | 184 | BISWAJIT LAI | 0.87 | 2.16 | 40
7424 | Bankura Division | Bankura Sadar Sub-Division | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.08.2023 to 31.10.2023. | Assistant Engineer | Junior Engineer | ORD/000494/2023-2024 | 217/KSD | 31/07/2023 | 92 | SRIKANTA MONDAL | 0.44 | 1.19 | 40
7425 | Bankura Division | Bankura Sadar Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01/11/2022 to 31/01/2023. | Assistant Engineer | Junior Engineer | ORD/001114/2022-2023 | 390/KSD | 28/10/2022 | 92 | SRIKANTA MONDAL | 0.44 | 1.19 | 20
7426 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2022-2023 | 1708/BQA | 29/07/2022 | 0 | Resource Division | 155.57 | 0 | 0
7427 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 1120/BQA | 12/05/2023 | 0 | Resource Division | 182.72 | 0 | 0
7428 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 15.54 | 0 | 0
7429 | Bankura Division | Bankura Sadar Sub-Division | Balance work of construction of boundary wall including construction of Path way at Over Head Reservoir Site for for Improvement of Khatra - Ranibandh - Hirbandh water supply scheme under BRGF (Phase - I) under Bankura Division, P.H.E. Dte. (Zone-Ashatara, Distance 48 Km. from Bankura) (Length -130 Mtr, No of Columns=38 Nos. Centre to Centre-3.5 Mtr.) For Single Tie Beam. | Assistant Engineer | Junior Engineer | ORD/000581/2022-2023 | 498/BQA | 13/03/2023 | 45 | MD. AFSAR ALI | 14.25 | 0 | 0
7430 | Bankura Division | Bankura Sadar Sub-Division | Balance work of construction of boundary wall including construction of Path way at Over Head Reservoir Site for for Improvement of Khatra - Ranibandh - Hirbandh water supply scheme under BRGF (Phase - I) under Bankura Division, P.H.E. Dte. (Zone-M1, Distance 85 Km. from Bankura) (Length -110 Mtr, No of Columns=32 Nos. Centre to Centre-3.5 Mtr.) For Single Tie Beam. | Assistant Engineer | Junior Engineer | ORD/000583/2022-2023 | 499/BQA | 13/03/2023 | 45 | J.K ENTERPRISE | 12.15 | 0 | 1
7431 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000623/2023-2024 | 2533/BQA | 08/09/2023 | 45 | GANESH ROY | 36.75 | 0 | 0
7432 | Bankura Division | Bankura Sadar Sub-Division | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2022 to 31/12/2022. | Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 234/KSD | 29/06/2022 | 184 | BISWAJIT LAI | 0.87 | 1.46 | 50
7433 | Bankura Division | Bankura Sadar Sub-Division | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve of under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/001300/2023-2024 | 323\KSD | 10/11/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 1 | 1 | 100
7434 | Bankura Division | Bankura Sadar Sub-Division | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Ashatora (Zone-CE) under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001338/2024-2025 | 3163/BQA | 24/12/2024 | 90 | SUBHANKAR BANERJEE | 90.99 | 0 | 0
7435 | Bankura Division | Bankura Sadar Sub-Division | 1st Ad-interim Payment against F/F bill for the work :- Improvement of Khatra, Ranibandh-Hirbandh works supply scheme under BRGF (PH-I) | Assistant Engineer | Junior Engineer | VCH/002855/2021-2022 | IMP/K-R-H | 11/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 500 | 0 | 0
7436 | Bankura Division | Bankura Sadar Sub-Division | Laying distribution system using different dia D.I - K 7 pipes for improvement of Khatra-Ranibandh-Hirbandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. Zone - M1 sl no - 01 | Assistant Engineer | Junior Engineer | VCH/002861/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | KONAR CONSTRUCTION | 58.1 | 0 | 0
7437 | Bankura Division | Bankura Sadar Sub-Division | Laying districution system using different dia D.I K7 pipes for improvement of Khatra - Ranibandh-Hirbandh water supply scheme under BRGF ph - 1 under Bankura Division PHE Dte. Zone - K Sl no - 04 | Assistant Engineer | Junior Engineer | VCH/002902/2021-2022 | FHTC/17 | 17/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 11.88 | 0 | 0
7438 | Bankura Division | Bankura Sadar Sub-Division | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M2 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001339/2024-2025 | 3164/BQA | 24/12/2024 | 90 | S B ASSOCIATES | 91.37 | 0 | 0
7439 | Bankura Division | Bankura Sadar Sub-Division | Construction of 250 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M1 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001340/2024-2025 | 3165/BQA | 24/12/2024 | 463 | SUBHENDU SEKHAR GORAI | 92.86 | 0 | 20
7440 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Biradihi (39) & Diktor (40) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | VCH/002856/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 23.59 | 0 | 0
7441 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe lineto cover Budhkhila (60) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 19 | Assistant Engineer | Junior Engineer | VCH/002857/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.7 | 0 | 0
7442 | Bankura Division | Bankura Sadar Sub-Division | Supply of M.S pipe for laying the sa,e during HDD boring including cutting, welding and other allied works for road crossing in connection with the work of Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 18 | Assistant Engineer | Junior Engineer | VCH/002858/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.38 | 0 | 0
7443 | Bankura Division | Bankura Sadar Sub-Division | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 16 | Assistant Engineer | Junior Engineer | VCH/002859/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.93 | 0 | 0
7444 | Bankura Division | Bankura Sadar Sub-Division | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 17 | Assistant Engineer | Junior Engineer | VCH/002860/2021-2022 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.71 | 0 | 0
7445 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing And Installation Of Pumping Machineries, Substation Equipments And Other Electro-Mechanical Accessories at Head Works site for Improvement of Khatra-Ranibandh-Hirbandh Water supply Scheme, Block- Ranibandh, Dist- Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001000/2020-2021 | 1319/BMD | 18/11/2020 | 181 | DEY ENTERPRISE | 107.65 | 105.5 | 95
7446 | Bankura Division | Khatra Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-CE (Ashatora) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 556/BQA | 17/03/2023 | 90 | LABIR MIRSHAD KHAN | 19.63 | 19.32 | 90
7447 | Bankura Division | Khatra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000173/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.91 | 0 | 0
7448 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7449 | Bankura Division | RWS Bankura Sub-Division | New service connection at Mini Piped w/s scheme at Menjua, P.O-Bheduasole under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | BILL/00844/2023-2024 | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0
7450 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7451 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
7452 | Bankura Division | RWS Bankura Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, Mirzapur, Kotulpur) |  | Junior Engineer | BILL/00273/2022-2023 |  | 18/01/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7453 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7454 | Bankura Division | RWS Bankura Sub-Division | New Connection at Dhunduria,Taldangra,Pin-722102,PHE Dte |  | Junior Engineer | BILL/00699/2023-2024 | FHTC/11 | 10/11/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0
7455 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7456 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31 | 48
7457 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7458 | Bankura Division | Brishnupur Sub-Division | New service connection at Khag Baikuntapur, Panchal Sonamukhi, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00822/2023-2024 | FHTC/09 | 07/09/2023 | 0 | BELIATORE CCC | 0.12 | 0 | 0
7459 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7460 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 50 | 48
7461 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 3 Nos. 300 mm X 200 mm X 200 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction of 3 Nos. Pump Houses with ancillary works, Laying of HDPE pipeline and Construction of Valve Chamber with all allied works in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000062/2024-2025 | 1485/BQA | 18/06/2024 | 45 | S B ASSOCIATES | 96.61 | 0 | 80
7462 | Bankura Division | Bankura Mechanical Sub-Division | Laying additional pipeline in connection with Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000186/2025-2026 | 1324/BQA | 17/06/2025 | 45 | GOUTAM BHOWMIK | 18.24 | 0 | 0
7463 | Bankura Division | Bankura Mechanical Sub-Division | Work Order for Repairing of Collecting line with other allied works of Lakshmisagar Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000453/2023-2024 | 261/KSD | 24/08/2023 | 7 | S.S. CONSTRUCTION | 0.97 | 0 | 0
7464 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000516/2023-2024 | 2453/BQA | 28/08/2023 | 948 | GOUTAM BHOWMIK | 93.63 | 35.43 | 20
7465 | Bankura Division | Bankura Mechanical Sub-Division | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm dia M.S collecting line from river bed tube well to CWR with allied works for in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001155/2023-2024 | 359/BQA | 06/02/2024 | 30 | SIBSANKAR CHOWDHURY | 50.22 | 33.75 | 45
7466 | Bankura Division | Bankura Mechanical Sub-Division | Repairing and painting of 2 Nos. Over Head Reservoir (Capacity 450 Cum. & 350 Cum., staging height 20 Mtr.) including by pass arrangement, construction of boundary wall (OHR site Zone- I & II, Intake site), repairing of CWR, pump house, WBSEDCL room, guard room with all other allied woorks for Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (Zone-I & II) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001770/2024-2025 | 493/BQA | 25/02/2025 | 60 | BEAUTY CHATTERJEE | 39.16 | 0 | 0
7467 | Bankura Division | Bankura Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer (Contractual) | RTOR000184/2023-2024 | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.03 | 0 | 0
7468 | Bankura Mechanical | Bankura Mechanical Sub-Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer (Contractual) | BILL/01661/2023-2024 | BP-2023-24-175 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.19 | 0 | 0
7469 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation works for Augmentation of piped water supply scheme for Lakshmisagar and its adjoining mouzas under Jal Jeevan mission programe under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000618/2023-2024 | 2090/BMD | 12/09/2023 | 840 | MAHADEV ENTERPRISE | 86.97 | 0 | 13
7470 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories in boosting site and HWS site for Augmentation works for Piped Water Supply Scheme for Lakshmisagar and Its Adjoining Mouzas under Jal Jeevan Mission Programme under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000145/2024-2025 | 488/BMD | 09/07/2024 | 600 | MAHADEV ENTERPRISE | 54.94 | 0 | 23
7471 | Bankura Division | RWS Bankura Sub-Division | Bmsd Phe Dte sutan C/o Sudip saha,sutan, Ranibandh |  | Junior Engineer | BILL/00040/2023-2024 | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0
7472 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7473 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7474 | Bankura Division | RWS Bankura Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. |  | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 33 | 48
7475 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7476 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7477 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 30 | 48
7478 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7479 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7480 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25 | 48
7481 | Bankura Division | Brishnupur Sub-Division | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, deshra, Kotulpur) | Assistant Engineer | Junior Engineer | BILL/00280/2022-2023 | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0
7482 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7483 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7484 | Bankura Division | Brishnupur Sub-Division | Quotation for New service connection at Pritchak | Assistant Engineer | Junior Engineer | BILL/01256/2024-2025 | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
7485 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 33.5 | 48
7486 | Bankura Division | Bankura Sadar Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 48
7487 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 | Assistant Engineer | Junior Engineer | ORD/000052/2020-2021 | 459/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 11.01 | 1.76 | 0
7488 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 | Assistant Engineer | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 28.91 | 0 | 95
7489 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 02 no, (Jirra, Ramnathpur), Total House Hold - 645 nos. | Assistant Engineer | Junior Engineer | ORD/000096/2021-2022 | 2533/BQA | 23/09/2021 | 30 | BISWARUP BOSE | 36.29 | 28.9 | 0
7490 | Bankura Division | Bankura Sadar Sub-Division | Dismantling & reconstruction of concrete at Phaspa mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. [Jal Jeevan Mission (JJM) and JAL SWAPNA Fund] | Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 344/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 3.61 | 3.61 | 80
7491 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2022-2023 | 346/BSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 4.94 | 0 | 0
7492 | Bankura Division | Bankura Sadar Sub-Division | Laying Extra HDPE Pipe Line to Cover Susunia (Upor Para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 348/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 2.36 | 2.36 | 0
7493 | Bankura Division | Bankura Sadar Sub-Division | Laying extra HDPE pipe line to cover Susunia mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2021-2022 | 934/ BSD | 04/10/2021 | 15 | I.R.CONSTRUCTION | 3.39 | 0 | 0
7494 | Bankura Division | Bankura Sadar Sub-Division | Restoration of concrete at Susunia mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- D) under Saltora- Block, Saltora-Chhatna W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000235/2021-2022 | 935/ BSD | 04/10/2021 | 15 | I.R.CONSTRUCTION | 4.11 | 4.09 | 0
7495 | Bankura Division | Bankura Sadar Sub-Division | Laying of HDPE Pipe Line from Susunia More to Murut Baha Eco-Park at Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 636/BQA | 24/03/2023 | 45 | SK SAMSA ALAM | 1.96 | 1.94 | 10
7496 | Bankura Division | Bankura Sadar Sub-Division | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debgram (296) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 201 Nos. | Assistant Engineer | Junior Engineer | VCH/002294/2021-2022 | FHTC/31 | 31/01/2022 | 0 | SANJOY MONDAL | 9.21 | 0 | 0
7497 | Bankura Division | Bankura Sadar Sub-Division | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 4, Belebad,Moulahir, Mujrakundi Raj band Total House Hold -576 . | Assistant Engineer | Junior Engineer | VCH/002494/2021-2022 | FHTC/3 | 03/02/2022 | 0 | M/S BIPUL BANERJEE | 20.03 | 0 | 0
7498 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0
7499 | Bankura Division | Brishnupur Sub-Division | New Connection at Saibuni,Patrasayer Bishnupur PHE Dte | Assistant Engineer | Junior Engineer | BILL/00491/2023-2024 | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0
7500 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0
7501 | Bankura Division | Brishnupur Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 40 | 48
7502 | Bankura Division | Bankura Sadar Sub-Division | Service connection charge for Beliatore OHR site water supply scheme at head works site Barjora block under BMD,PHE Dte.(SM/09924) | Assistant Engineer | Junior Engineer | BILL/00656/2024-2025 | BP-242/2024-25 | 28/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.63 | 0 | 0
7503 | Bankura Division | Bankura Sadar Sub-Division | Rail bhoomi crossing seva | Assistant Engineer | Junior Engineer | BILL/00933/2023-2024 | FHTC/08 | 31/08/2023 | 0 | SOUTH EASTERN RAILWAY | 1.06 | 0 | 0
7504 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 300 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC & DI pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Beliatore Girls High School at Beliatore) | Assistant Engineer | Junior Engineer | ORD/000081/2025-2026 | 1020/BQA | 25/04/2025 | 90 | I R CONSTRUCTION | 9.71 | 0 | 0
7505 | Bankura Division | Bankura Sadar Sub-Division | Survey work for Augmentation for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for 10 nos. Mouzas of proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora , District -Bankura | Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 1069/BQA | 04/05/2023 | 360 | TAPAS DEY | 1.15 | 0.76 | 70
7506 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site Beliatore - Sonamukhi More at Beliatore) | Assistant Engineer | Junior Engineer | ORD/000162/2025-2026 | 1303/BQA | 17/06/2025 | 45 | I R CONSTRUCTION | 12.43 | 0 | 0
7507 | Bankura Division | Bankura Sadar Sub-Division | Laying DI (K7) & UPVC pipe line for distribution system and Construction and commissioning of 500 m3 capacity R.C.C. OHR (based on Departmental Design Ref. Drawing No. PC - 1 / OHR / 5 / 12 (Sheet 1 & 2) with 20 mtr. Staging height including foundation, pipeline connection and cost of pipes, specials etc. and allied works for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, District - Bankura (Part - A) and Construction and commissioning of 500 m3 capacity RCC OHR (based on Departmental Design Ref. Drawing No. PC - 1 / OHR / 5 / 12 (Sheet 1 & 2) with 20 mtr. staging including foundation, pipeline connection and cost of pipes, specials etc., and allied works for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining (JJM) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, District - Bankura (Part - B) | Assistant Engineer | Junior Engineer | ORD/000222/2022-2023 | 1973/BQA | 22/09/2022 | 540 | SIB SANKAR CHOWDHURY | 349.96 | 188.44 | 48
7508 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 500 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000260/2022-2023 | 358/BSD | 13/04/2022 | 15 | VISCOUS ENGINEERS PVT. LTD. | 1.84 | 1.84 | 0
7509 | Bankura Division | Bankura Sadar Sub-Division | Augmentation of Beliatore and its adjoining mouzas under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 1959/BQA | 18/07/2023 | 270 | I.R.CONSTRUCTION | 125.11 | 37.26 | 35
7510 | Bankura Division | Bankura Sadar Sub-Division | Laying Rising Main DI (K9) pipe & Construction of CWR (100 CUM CAPACITY) with plinth protection for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora , District -Bankura. ( Sl.No-03) | Assistant Engineer | Junior Engineer | ORD/000444/2021-2022 | 524/BQA | 10/03/2022 | 1574 | AJIT KUMAR PAUL | 22.63 | 16.47 | 75
7511 | Bankura Division | Bankura Sadar Sub-Division | Repair & Restoration of collecting Pipe line 4 (four) nos 100mm dia. from river bed Tube Well to CWR in river Sali under Beliatore W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2023-2024 | 2946/BQA | 30/10/2023 | 30 | SOMA BANERJEE | 10.86 | 10.82 | 100
7512 | Bankura Division | Bankura Sadar Sub-Division | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 100 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/3/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Surface Water Based Dhabani PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Kanchchhala, Samantamara & Dhabani. | Assistant Engineer | Junior Engineer | ORD/000614/2022-2023 | 571/BQA | 17/03/2023 | 15 | MS G. MITRA AND ASSOCIATES | 0 | 0 | 0
7513 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Indira Statue at Beliatore towards Sonamukhi Road) | Assistant Engineer | Junior Engineer | ORD/000877/2023-2024 | 3005/BQA | 03/11/2023 | 45 | SIBSANKAR CHOWDHURY | 6.01 | 0 | 0
7514 | Bankura Division | Bankura Sadar Sub-Division | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Murakata Village Road) | Assistant Engineer | Junior Engineer | ORD/000878/2023-2024 | 3006/BQA | 03/11/2023 | 45 | SIBSANKAR CHOWDHURY | 6.55 | 0 | 0
7515 | Bankura Division | Bankura Sadar Sub-Division | Construction of High Lift Pump House with all allied works at Beliatore under Augmentation of Beliatore Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001336/2024-2025 | 3155/BQA | 24/12/2024 | 342 | ASHIS PAL | 25.67 | 0 | 75
7516 | Bankura Division | Bankura Sadar Sub-Division | Cannel/Drain Crossing work by 150 mm dia MS carrier pipe & 300 mm dia casing pipe by Jack pushing method on the road SH-8 from Beliatore towards Chandar inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works and laying different dia proposed extra HDPE line to be laid at mouza Beliatore city, Natungram, Challa, Dangar para for Augmentation of Beliatore Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001953/2024-2025 | 691/BQA | 12/03/2025 | 190 | SIBSANKAR CHOWDHURY | 176.06 | 0 | 31
7517 | Bankura Division | Bankura Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000072/2022-2023 | 79BQA | 06/01/2023 | 0 | Resource Division | 26.02 | 0 | 0
7518 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Chhandar,Molbagan Pump House tail end T/W under Beliatore water supply scheme Barjora block under BMD,PHE Dte. (sm/09924) | Assistant Engineer | Junior Engineer | BILL/01342/2024-2025 | BP-2024-25-354 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.55 | 0 | 0
7519 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Beliatore w/s scheme under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000263/2024-2025 | 518/BMD | 09/07/2024 | 120 | DEY ENTERPRISE | 17.63 | 0 | 0
7520 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Beliatore its adjoining mouzas piped water supply scheme (JJM Revision) under Bankura Mechanical Division PHE Dte Block Borjora Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 1876/BMD | 17/08/2023 | 720 | DEY ENTERPRISE | 64.51 | 0 | 51
Total | [10 empty] | 7453928.29 | 66894.58