## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000112/2022-2023 | 648/PD | 22/04/2022 | 45 | KABERI DUTTA | 9.84 | 6.54 | 100
2 | Purulia Division | Purulia Sadar Sub-Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000159/2020-2021 | 1412/PD | 29/12/2020 | 45 | SWAPAN MANDAL | 68.85 | 13.2 | 100
3 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000623/2022-2023 | 1390/PD | 01/09/2022 | 45 | SOUVIK MANDAL | 23.21 | 14.25 | 100
4 | Purulia Division | Purulia Sadar Sub-Division | Construction of Guard Room & boundarry wall near Guest House Campus and with drawing and relaying of CI pipes under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001022/2022-2023 | 184/PD | 07/02/2023 | 100 | MANATOSH SINGH | 4.19 | 0 | 0
5 | Purulia Division | Purulia Sadar Sub-Division | Re-Sinking of No-1 Tube-well 200mm 200mm dia river bed tube-well at riverbed of Kansai at Pindra site of Bongabari W/s Scheme. (Tender No. 868/EE/PD of 2019-20) | Assistant Engineer |  | VCH/000229/2021-2022 | 95/8443116 | 19/07/2021 | 0 | SANTANU BANERJEE | 0.45 | 0 | 0
6 | Purulia Division | Purulia Sadar Sub-Division | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.567/EE/PD of 2021-22) | Assistant Engineer |  | VCH/000727/2021-2022 | 264/8443156/1 | 20/12/2021 | 0 | SWAPAN MANDAL | 4.27 | 0 | 0
7 | Purulia Division | Purulia Sadar Sub-Division | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.14/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000728/2021-2022 | 264/8443156/2 | 20/12/2021 | 0 | SWAPAN MANDAL | 13.72 | 0 | 0
8 | Purulia Division | Purulia Sadar Sub-Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/s Scheme under Jal Swapna Programme. (Tender No. 14/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000892/2020-2021 | 448/8443187 | 30/03/2021 | 0 | SWAPAN MANDAL | 26.54 | 0 | 0
9 | Purulia Division | Purulia Sadar Sub-Division | Laying of HDPE pipe & distribution main (loop line) from Surulia Roads side Hari Mandir to Surulia Shiv Mandir in Surulia village for deinking water supply through FHTC to metup the water crisis at upar Surulia village from existing Bongabari W/s Scheme under Jaal Swapna Programme. (Tender No.1031/EE/PD of 2021-22) | Assistant Engineer |  | VCH/001055/2021-2022 | 368/8443191 | 31/03/2022 | 0 | SOUVIK MANDAL | 4.29 | 0 | 0
10 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-J) | Assistant Engineer |  | ORD/000243/2020-2021 | 21/PSD | 13/01/2021 | 45 | M/S ACHARJEE CONSTRUCTION | 4.5 | 0 | 100
11 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-E) (Tender No. 417/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000012/2021-2022 | BP-2021-22-41 | 19/07/2021 | 0 | INDRAJIT SARKAR | 2.91 | 0 | 0
12 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-C) (Tender No. 339/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000013/2021-2022 | BP-2021-22-42 | 19/07/2021 | 0 | ANUDIP SAHA | 2.62 | 0 | 0
13 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000014/2021-2022 |  | 12/04/2021 | 0 | M/S S & P CONSTRUCTION | 2.66 | 0 | 0
14 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block (Tender No:- 328/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000121/2021-2022 | BP-2021-22-52 | 20/07/2021 | 0 | BHAGABANDAS KUMAR | 10.04 | 0 | 0
15 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Satra village of Hensia G.P. under command area of Satra W/S Scheme at Arsha Block (Part- H) (Tender No:- 21/EE/PD of 2021-22) | Assistant Engineer |  | VCH/000122/2021-2022 | BP-2021-22-53 | 20/07/2021 | 0 | PRATIK SAHA | 2.8 | 0 | 0
16 | Purulia Division | Purulia Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-F) (Tender No.317/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000181/2021-2022 | BP-2021-22-81 | 23/08/2021 | 0 | RAKSHIT ENTERPRISE | 2.57 | 0 | 0
17 | Purulia Division | Purulia Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-I) (Tender No.350/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000182/2021-2022 | BP-2021-22-97 | 23/08/2021 | 0 | S.K IRFAN | 2.94 | 0 | 0
18 | Purulia Division | Purulia Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-A) (Tender No.287/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000183/2021-2022 | BP-2021-22-83 | 16/08/2021 | 0 | GYANRANJAN SEN | 3.01 | 0 | 0
19 | Purulia Division | Purulia Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Harnama & Nimdiha village of Beldih G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000184/2021-2022 | BP-2021-22-91 | 23/08/2021 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 9.31 | 0 | 0
20 | Purulia Division | Purulia Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No:- 263/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000219/2021-2022 |  | 09/08/2021 | 0 | SUBODH PRAMANIK | 31.87 | 0 | 0
21 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000241/2021-2022 | BP-2021-22-44 | 19/07/2021 | 0 | M/S. S.P CONSTRUCTION | 2.66 | 0 | 0
22 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-G) (Tender No. 284/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000327/2021-2022 | BP-2021-22-122 | 11/10/2021 | 0 | TUSHAR KANTI GORAI | 3.69 | 0 | 0
23 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-B) (Tender No. 338/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000328/2021-2022 | BP-2021-22-117 | 11/10/2021 | 0 | SIDDHARTHA SANKAR SARKAR | 3.85 | 0 | 0
24 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-K) (Tender No.352/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000329/2021-2022 | BP-2021-22-119 | 11/10/2021 | 0 | SIDDHARTHA SANKAR SARKAR | 3.16 | 0 | 0
25 | Purulia Division | Purulia Sadar Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-J) (Tender No.269/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000330/2021-2022 | BP-2021-22-135 | 11/10/2021 | 0 | M/S ACHARJEE CONSTRUCTION | 3.43 | 0 | 0
26 | Purulia Division | Purulia Sadar Sub-Division | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1 & 2 ) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Kansai River) at Satra under Satra W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. (Tender No.863/EE/PD of 2021-22) | Assistant Engineer |  | VCH/000807/2021-2022 | BP-2021-22-235 | 03/02/2022 | 0 | SUBODH PRAMANIK | 9.7 | 0 | 0
27 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) (Tender No.339/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000985/2021-2022 | BP-2021-22-245 | 16/02/2022 | 0 | ANUDIP SAHA | 0.92 | 0 | 0
28 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-E) (Tender No.417/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000986/2021-2022 | BP-2021-22-242 | 16/02/2022 | 0 | INDRAJIT SARKAR | 1.05 | 0 | 0
29 | Purulia Division | Purulia Sadar Sub-Division | Laying op UPVC pipe as distribution main (Loop Line) from Satra Junior High School to Satra uppar para for drinking water supply through FHTC meet up the water crisis at Satra W/s Scheme. (Tender No.864/EE/PD of 2021-2022) | Assistant Engineer |  | VCH/000988/2021-2022 | BP-2021-22-239 | 16/02/2022 | 0 | SUBODH PRAMANIK | 7.31 | 0 | 0
30 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Harnama and Nimdih village of Beldih G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) | Assistant Engineer |  | VCH/001004/2021-2022 | BP-2021-22-262 | 28/02/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 0.23 | 0 | 0
31 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-D) (Tender No.264/EE/PD of 2020-21) | Assistant Engineer |  | VCH/001006/2021-2022 | BP-2021-22-254 | 25/02/2022 | 0 | M/S. S.P CONSTRUCTION | 0.96 | 0 | 0
32 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-H) (Tender No.21/EE/PD of 2021-22) | Assistant Engineer |  | VCH/001007/2021-2022 | BP-2021-22-256 | 25/02/2022 | 0 | PRATIK SAHA | 1.66 | 0 | 0
33 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.328/EE/PD of 2020-21) | Assistant Engineer |  | VCH/001008/2021-2022 | BP-2021-22-255 | 28/02/2022 | 0 | BHAGABANDAS KUMAR | 4.89 | 0 | 0
34 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.263/EE/PD of 2020-21) | Assistant Engineer |  | VCH/001011/2021-2022 | BP-2021-22-259 | 28/02/2022 | 0 | SUBODH PRAMANIK | 7.97 | 0 | 0
35 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-I). (Tender No.350/EE/PD of 2020-21) | Assistant Engineer |  | VCH/001018/2021-2022 | BP-2021-22-260 | 28/02/2022 | 0 | S.K IRFAN | 0.64 | 0 | 0
36 | Purulia Division | Purulia Sadar Sub-Division | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) | Assistant Engineer |  | VCH/001139/2021-2022 | BP-2021-22-293 | 09/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0
37 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
38 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Miscellaneous collection for Indian Railways against invoice ID No.WL00000000038190 dt.02-03-2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/01880/2023-2024 | BP-2023-24-867 | 08/03/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
39 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000206/2020-2021 | 23/RNP | 11/01/2021 | 15 | TUMPA GORAIN | 4.78 | 0.26 | 100
40 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000227/2021-2022 | 729/RNP | 06/12/2021 | 20 | MS MITRA SENGUPTA ENTERPRISES | 1.09 | 0 | 100
41 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing FHTC & Supplying & laying different dia HDPE pipe line of distribution linewith allied works from OHR (zone-1) site to Mathorgoria village More & Balitora bauripara end to bramhan para of Balitora village under zone-I of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Mouza- Balitora, Habitation :-Balitora) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000328/2021-2022 | 36/PD | 07/01/2022 | 60 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 37.4 | 0 | 100
42 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000329/2021-2022 | 37/PD | 07/01/2022 | 30 | SANDIP KUMAR DUBEY | 7.54 | 0 | 100
43 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Probable estimate for shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Kapashdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000330/2021-2022 | 38/PD | 07/01/2022 | 1180 | KHITISH CHANDRA PATHAK | 34.11 | 0 | 75
44 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000332/2021-2022 | 40/PD | 07/01/2022 | 30 | M/S. S.P CONSTRUCTION | 10.77 | 0.43 | 100
45 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and renovation of existing structure excluding OHR under Balitora W/S Scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000333/2021-2022 | 41/PD | 07/01/2022 | 60 | SANTANU BANERJEE | 14.26 | 11.3 | 100
46 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of 3 (three) Nos. Over Head Reservoir (Capcaity 180cum at Bakulia, 70 cum near Mokra and 120 cum at Barsal) and other allied works under Balitora W/S scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000334/2021-2022 | 42/PD | 07/01/2022 | 60 | SANTANU BANERJEE | 13.21 | 10.56 | 0
47 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional House Hold Tap Connection (FHTC) at Deuli and supplying & laying different dia HDPE pipe line of distribution line with allied works at Sunuri & Upardih village (Zone-1) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000388/2022-2023 | 346/RNP | 01/06/2022 | 20 | AMIT PATHAK | 3.87 | 3.79 | 100
48 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Chowkage clearence of Distribution line at Deuli village and shifting of DI, GI, MS Pipe from Manbazar Pump house site to Balitora Zone-I OHR campus under Balitora W/S Scheme (Zone-I) Raghunathpur Sub-Divn, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000501/2023-2024 | 396/RNP | 05/09/2023 | 15 | M/S SAYAK BHATTACHARYA | 0.96 | 0.95 | 100
49 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauri Para to Danesdih Village & end of Batka Village to Siyaldanga Village & Kastagora Village (Zone-III) of Balitora W/S Scheme under Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000594/2022-2023 | 488/RNP | 28/07/2022 | 20 | M/S. S.P CONSTRUCTION | 4.81 | 4.78 | 100
50 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Shifting of Rising Main of underground DI pipe line including supplying & laying of DI pipe from Jagannathdih more to boundary wall of Barshal OHR (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000871/2022-2023 | 1839/PD | 12/12/2022 | 45 | M/S SAYAK BHATTACHARYA | 23.27 | 3.06 | 30
51 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New Sinking of 4 (Four) Nos 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/001195/2022-2023 | 467/PD | 28/03/2023 | 45 | KHITISH CHANDRA PATHAK | 15.93 | 2.52 | 100
52 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | RTOR000006/2022-2023 | 957/PD | 20/06/2022 | 0 | Resource Division | 26.31 | 0 | 0
53 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | RTOR000016/2022-2023 | 977/PD | 22/06/2022 | 0 | Resource Division | 143.77 | 0 | 0
54 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing FHTC supplying & laying different dia HDPE pipe line under zone-I of Balitora W/S Scheme (Tender No- 934/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000035/2022-2023 | BP-2022-23-20 | 07/04/2022 | 0 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 9.81 | 0 | 0
55 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Deuli, Habitation - Deuli (70 Nos.), Mouza-Sunuri, Habitation - Sunuri (42 Nos.) (Tender No.348/EE/PD of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000160/2022-2023 | BP-2022-23-25 | 07/04/2022 | 0 | SK ABBAS | 1.01 | 0 | 0
56 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | FHTC including other allied works of Baltora W/S Scheme at Santuri block (Tender No- 262/2020-21 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000194/2022-2023 | BP-2022-23-47 | 17/05/2022 | 0 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0
57 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (T/N-948/21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000241/2022-2023 |  | 05/07/2022 | 0 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0
58 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No.804/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000597/2022-2023 | BP-2022-23-311 | 26/09/2022 | 0 | TUMPA GORAIN | 0.97 | 0 | 0
59 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauro Para to Danesdih village & end of Batka village to Syaldanga village & kastagora village (Zone-III) site under (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub- Division under Purulia Division PHE Dte. (Tender No- 948/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000884/2022-2023 | BP-2022-23-80 | 01/07/2022 | 0 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0
60 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 923/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000949/2022-2023 | BP-2022-23-111 | 16/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 7.33 | 0 | 0
61 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Balitora, Habitation- Bagergoria (24) Nos. Balitora (88) Nos. (Tender No:- 802/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000976/2022-2023 | BP-2022-23-146 | 25/07/2022 | 0 | SUDHANSHU OJHA | 1.29 | 0 | 0
62 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division, PHE Dte. at Mouza- Balitora, Habitation- Begergoria (24) Balitora (88) Nos. (Tender No:- 281/EE/PD of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000980/2022-2023 | BP-2022-23-147 | 25/07/2022 | 0 | SUDHANSHU OJHA | 0.26 | 0 | 0
63 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Balitora Water Supply Scheme of Santuri Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. at mouza- Balitora, Habitation- Balitora (108) nos. (Tender No- 288/20-21 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000987/2022-2023 | BP-2022-23-152 | 26/07/2022 | 0 | NANIGOPAL DEY | 0.36 | 0 | 0
64 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Potable estimate for Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Kapasdanga village end to Mokra Pry. School through Jagannathdih & Saluni village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 937/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/000988/2022-2023 | BP-2022-23-153 | 26/07/2022 | 0 | KHITISH CHANDRA PATHAK | 5.49 | 0 | 0
65 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 5 & 6) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, under Purulia Division PHE Dte. PHE Dte. (Tender No.404/EE/PD of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001010/2021-2022 | BP-2021-22-252 | 25/02/2022 | 0 | ASHOK KUMAR CHATTERJEE | 19.66 | 0 | 0
66 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.995/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001015/2022-2023 | BP-2022-23-295 | 23/09/2022 | 0 | SANDIP KUMAR DUBEY | 1.79 | 0 | 0
67 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional House Hold Connection (FHTC) in connection with other allied works of Baltora W/s Scheme at Santuri Block (Mouza- Sunuri, Habitation-Sunuri) [Part-I] (Tender No.908/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001020/2021-2022 | BP-2021-22-263 | 28/02/2022 | 0 | RAHIBUDDIN MONDAL | 3.75 | 0 | 0
68 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and laying different dia HDPE pipe line of Distribution line with allied works from Makra village more to Jadudih village under (Zone-II) Balitora W/s Scheme. (Tender No.995/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001121/2021-2022 | BP-2021-22-384 | 28/03/2022 | 0 | SANDIP KUMAR DUBEY | 5.73 | 0 | 0
69 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional works for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block Raghunathpur Sub_Division under Purulia Division PHE Dte. Mouza- Dandahit, Hab-Dandahit (112 Nos) (Tender No.823/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001131/2021-2022 | BP-2021-22-317 | 22/03/2022 | 0 | SIKHA ENTERPRISES | 2.01 | 0 | 0
70 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection FHTC including other allied works of Balitora Water supply Scheme at Santuri Block part- II [Tender No- 907/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001150/2021-2022 | BP-2021-22-276 | 03/03/2022 | 0 | RAHIBUDDIN MONDAL | 0.93 | 0 | 0
71 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001161/2021-2022 | BP-2021-22-363 | 28/03/2022 | 0 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0
72 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Shifting of underground HDPE & DIpipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/s Scheme. (Tender No.923/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001163/2021-2022 | BP-2021-22-349 | 28/03/2022 | 0 | BASANTA KUMAR SINGHADEO | 14 | 0 | 0
73 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Dandahit Habitation-Batka, Dandahit (Tender No- 855/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001182/2021-2022 | BP-2021-22-327 | 22/03/2022 | 0 | ROY CONSTRUCTION | 0.54 | 0 | 0
74 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No- 804/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001197/2021-2022 | BP-2021-22-338 | 25/03/2022 | 0 | TUMPA GORAIN | 2.14 | 0 | 0
75 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Deuli, Hab-Deuli, Mouza-Suburi, Hab-Santuri. (Tender No- 803/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | VCH/001198/2021-2022 | BP-2021-22-321 | 22/03/2022 | 0 | SK ABBAS | 4.28 | 0 | 0
76 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of contractual demand from 71 KVA to 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o The Ex.Engg PMD PHE Dte.(Consumer ID : 950006038) to their premises at Balitora Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00042/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 6.74 | 0 | 0
77 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment for New Electric connection charge at Madhukunda O.H.R. Site , Mouja : Madhukunda under Augmentation of Balitora Water Supply to Santuri CCC of WBSEDCL . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00147/2024-2025 | BP-24-25-26 | 11/06/2024 | 0 | SANTURI CCC | 0.94 | 0 | 0
78 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment of new Electric service connection charge to WBSEDCL ,Santuri CCC at Santuri Mouja ( O.H.R. No.2 under Balitora W.S.Scheme ) ,application no.- 2004753984 , Ref. Id.- 204318171 , Contact Demand - 1330 watt . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00173/2024-2025 | BP-24-25-41 | 02/07/2024 | 0 | SANTURI CCC | 0.05 | 0 | 0
79 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment for New Service Connection charge at Manpur , JL - 31 , Plot - 479 under Purulia Mechanical Division P.H.E. Dte. to WBSEDCL , Purulia , Santuri CCC . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00177/2024-2025 | BP-24-25-42 | 02/07/2024 | 0 | SANTURI CCC | 3.6 | 0 | 0
80 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of the contract demand from 71 KVA at 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Balitora Water Supply | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00867/2023-2024 | BP-23-24-310 | 21/03/2024 | 0 | WBSEDCL PURULIA | 11.11 | 0 | 0
81 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, MCC panel Flowmeter and other allied works for augmentation of Balitora water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000033/2023-2024 | 438/PMD | 19/04/2023 | 60 | PREMNATH MITRA | 46.28 | 0 | 90
82 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Balitora w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000133/2023-2024 | 648/PMD | 08/06/2023 | 60 | PREMNATH MITRA | 12.15 | 0 | 91
83 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of Balitora water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000404/2022-2023 | 232/PMD | 03/03/2023 | 60 | ASHOKE ADHIKARY | 12.85 | 12.85 | 80
84 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
85 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing of DI rising main pipeline including cleaning of chokage & Construction of 100 Cum capacity RCC clear water reservoir (CWR) and Construction of Meter Room, Panel Room, undercut pump house with other allied works at river site campus and providing 456 nos functional household tap connection at chirka mouza in connection with Jal Jeevan Mission (JJM) for Augmentation of Sindri-ChasmoreW/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000037/2023-2024 | 655/PD | 17/05/2023 | 60 | SB CONSTRUCTION | 59.68 | 10.94 | 100
86 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM) and Jal Sapna at Chirka village of Garaphushara G.P. under command area of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2022-2023 | 171/PSD | 18/04/2022 | 25 | SK ABBAS | 4.85 | 0 | 0
87 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2022-2023 | 629/PD | 22/04/2022 | 45 | ZEST INFRACON | 68.48 | 0 | 100
88 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Left out Loop Pipe Line for distribution System at Sindri and Garafusro Mouza under command area of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000216/2024-2025 | 1085/PD | 07/06/2024 | 60 | SADHAN GORAIN | 24.37 | 0 | 100
89 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of MS pipe distribution line at Garafusro under command area of Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000447/2024-2025 | 1509/PD | 27/08/2024 | 158 | SADHAN GORAIN | 32.27 | 0 | 100
90 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and renovation of the Over Head reservoir (OHR) of 250 m3 Capacity, Staging Height 20 mtr. of Sindri-Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000737/2022-2023 | 1477/PD | 20/09/2022 | 90 | SADHAN GORAIN | 11.8 | 0 | 100
91 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC common manifold camber and Laying of 250 mm dia DI rising main from manifold chamber to CWR at river site of Sindri- chas more W/S scheme in connection of Jal Jeevan Mission (JJM) under Sindri-chas more W/S scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000879/2023-2024 | 1529/PD | 16/10/2023 | 45 | SADHAN GORAIN | 11.86 | 0 | 100
92 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Pushing of 600mm dia MS pipe and 100 mm dia MS water carrier pipe by hydraulic jacking method across Purulia to Jhalda Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission at 04 (Four) different location Near Chas more for Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001620/2023-2024 | 1830/PD | 12/12/2023 | 60 | MS GORAIN CONCERN | 41.39 | 0 | 45
93 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing of DI rising main pipeline including cleaning of chokage & Construction of Boundary wall, pathway and landfilling with other allied works at river site of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Divn. under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001621/2023-2024 | 1831/PD | 12/12/2023 | 60 | M/S SB CONSTRUCTION | 18.02 | 0 | 70
94 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing & renovation of 100 cum capacity CWR & Pump house, Boundary Wall (OHR Site and River Site) & Tranformar room, Meter room with Guard room at Sindri-Chasmore river site Pump house campus of Sindri-Chsmore W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001814/2023-2024 | 42/PD | 09/01/2024 | 631 | M/S SB CONSTRUCTION | 21.36 | 0 | 90
95 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 250 mm dia MS Pipe and Road Crossing and Construction of PCC Approach Road at OHR site for Sindri-Chas W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003966/2023-2024 | 509/PD | 16/03/2024 | 60 | SADHAN GORAIN | 22.84 | 0 | 100
96 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) (Tender No- 315/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001035/2022-2023 | BP-2022-23-383 | 19/10/2022 | 0 | ZEST INFRACON | 45.52 | 0 | 0
97 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of the contract demand from 80 KVA at 0.4 KV to 105/105//105//105//105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE SINDRI CHASMORE Water Supply, (Consumer ID -942413800) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00865/2023-2024 | BP-23-24-308 | 19/03/2024 | 0 | WBSEDCL PURULIA | 1.44 | 0 | 0
98 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 M.T capacity single girder H.O.T crane with gantry girder and square rail for Sindrichasmore w/s scheme new CWR Pump house under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000049/2024-2025 | 968/PMD | 20/06/2024 | 60 | RABINDRA NATH KHAN | 8.09 | 0 | 100
99 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination with other allied works for augmentation of existing pump house & new CWR pump house of Sindrichasmore water supply scheme under Purulia Mechanical Division , PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000054/2024-2025 | 972/PMD | 20/06/2024 | 226 | COMBINE ENTERPRISES | 18.83 | 0 | 20
100 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply of valves, pipes and miscellaneous works for new proposed CWR & existing P.H of Sindrichasmore w/s scheme under PMD, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 995/PMD | 21/06/2024 | 60 | RABINDRA NATH KHAN | 1.61 | 0 | 0
101 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing internal and external illumination arrangement at proposed CWR of Sindrichasmore W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000153/2023-2024 | 649/PMD | 08/06/2023 | 60 | MAHIPAL MAJHI | 6.13 | 0 | 5
102 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, flowmeter with necessary substitutes and allied electrical panel at existing pump house at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000365/2022-2023 | 207/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 66.49 | 30.88 | 60
103 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tubewell with supply of necessary substitutes at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000366/2022-2023 | 208/PMD | 28/02/2023 | 704 | RABINDRA NATH KHAN | 17.88 | 4.98 | 85
104 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, Voltage Stabilizer with necessary substitutes and allied electrical panel at for Proposed CWR at intake side of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000376/2022-2023 | 206/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 31.34 | 0 | 15
105 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Sindrichasmore Water Supply scheme Block Purulia-II under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000382/2022-2023 | 213/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 12.88 | 60
106 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 30
107 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and laying of cables for taking power & Misc. works for Pump house of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000593/2024-2025 | 1451/PMD | 01/10/2024 | 30 | RABINDRA NATH KHAN | 6.21 | 0 | 0
108 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & installation of Glow Sign board & Lighting conductor under Sindri Chas more Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000596/2024-2025 | 350/PMSD(W/S) | 04/09/2024 | 15 | PINTU DEY | 0.48 | 0 | 100
109 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of Indoor type Vacuum Circuit breaker and allied works for Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000620/2024-2025 | 1542/PMD | 11/11/2024 | 385 | RABINDRA NATH KHAN | 12.07 | 0 | 100
110 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System & Miscellaneous works at Pump House under Sindrichasmore W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000621/2024-2025 | 1543/PMD | 11/11/2024 | 60 | MAHIPAL MAJHI | 3.63 | 0 | 100
111 | Purulia Division | Raghunathpur Sub-Division | Car bill for hair charges for office purpose against vehicle reg. no.WB55A/7171 for the period form March,23 to April,23. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | BILL/00264/2023-2024 | BP-2023-24-231 | 14/06/2023 | 0 | NIRUPAMA DEY | 0.71 | 0 | 0
112 | Purulia Division | Raghunathpur Sub-Division | New sinking of 5(Five) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river ( Amrakocha Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Manguria-Lalpur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000073/2022-2023 | 650/PD | 22/04/2022 | 45 | NANIGOPAL DEY | 18.95 | 5.56 | 0
113 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000076/2022-2023 | 653/PD | 22/04/2022 | 30 | KANAILAL PAL | 4.69 | 3.97 | 90
114 | Purulia Division | Raghunathpur Sub-Division | Making Two nos Bypass arrangement with allied works in between of over flow line to distribution main at Maguria Lalpur Zone-I & II OHR site under Maguria Lalpur water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000112/2023-2024 | 880/PD | 03/07/2023 | 30 | ALOK KUMAR CHAKRABORTY | 4.2 | 4.2 | 100
115 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe Near Doldoli Bridge to Doldoli Bastri to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000174/2023-2024 | 990/PD | 26/07/2023 | 60 | CHANCHAL MISHRA | 5.79 | 5.78 | 100
116 | Purulia Division | Raghunathpur Sub-Division | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000279/2021-2022 | 1554/PD | 15/12/2021 | 60 | PREMNATH MITRA | 78.3 | 9.15 | 85
117 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 300 cum at Manguria OHR under Manguria-Lalpur W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000372/2021-2022 | 158/PD | 25/01/2022 | 60 | KANAILAL PAL | 7.43 | 6.75 | 95
118 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A)(Chatumadar G.P.)(300 Nos) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000375/2021-2022 | 161/PD | 25/01/2022 | 45 | ALOK KUMAR CHAKRABORTY | 13.88 | 6.88 | 65
119 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000376/2021-2022 | 162/PD | 25/01/2022 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.95 | 0 | 35
120 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room-Cum-Chlorine Room at Amrakocha Pump House Site under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000417/2021-2022 | 85/RNP | 28/02/2022 | 90 | M/S SAYAK BHATTACHARYA | 4.39 | 3.75 | 90
121 | Purulia Division | Raghunathpur Sub-Division | Additional work of Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) (Daldali G.P.) (220 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000498/2021-2022 | 144/RNP | 31/03/2022 | 14 | M/S CHAKRABORTY CONSTRUCTION | 4.55 | 0 | 0
122 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000660/2023-2024 | 1353/PD | 13/09/2023 | 45 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 100
123 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Chatumather Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000686/2023-2024 | 1357/PD | 13/09/2023 | 45 | PRAMIT CHATTERJEE | 18.04 | 0 | 100
124 | Purulia Division | Raghunathpur Sub-Division | Clearing of chokage and making HDPE loop line for Kalali , Amlatora, Chatumadar, & Hijuli under under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000861/2022-2023 | 1814/PD | 01/12/2022 | 180 | ALOK KUMAR CHAKRABORTY | 8.16 | 0 | 100
125 | Purulia Division | Raghunathpur Sub-Division | Supplying and laying of HDPE pipe line from existing CWR to Karandih through Amrakotcha village under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000862/2022-2023 | 1815/PD | 06/12/2022 | 45 | ALOK KUMAR CHAKRABORTY | 14.41 | 14.21 | 100
126 | Purulia Division | Raghunathpur Sub-Division | Allied works for repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/001015/2022-2023 | 183/PD | 07/02/2023 | 30 | KANAILAL PAL | 2.64 | 2.64 | 100
127 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | RTOR000007/2022-2023 | 960/PD | 20/06/2022 | 0 | Resource Division | 39.43 | 0 | 0
128 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.946/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000144/2022-2023 | BP-2022-23-31 | 08/04/2022 | 0 | M/S CHAKRABORTY CONSTRUCTION | 8.65 | 0 | 0
129 | Purulia Division | Raghunathpur Sub-Division | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.22/EE/PD of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000174/2022-2023 | BP-2022-23-51 | 17/05/2022 | 0 | M/S CHAKRABORTY CONSTRUCTION | 4.54 | 0 | 0
130 | Purulia Division | Raghunathpur Sub-Division | Additional work for FHTC including other allied works of Manguria-lalpur W/S Scheme at Hura Block (Part- C) [Tender No- 939/2021-22 of EE/PD] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000184/2022-2023 | BP-2022-23-63 | 24/05/2022 | 0 | SWAPAN MANDAL | 18.23 | 0 | 0
131 | Purulia Division | Raghunathpur Sub-Division | New sinking of 05 (Five) Nos. 200 mm dia river bed tube well (Horizontal) at Kansabati river (Amrakocha Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Manguria-lalpur W/S Scheme under Raghunathpur Sub- Division, PHE Dte. (Tender No- 53/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000895/2022-2023 | BP-2022-23-72 | 01/07/2022 | 0 | NANIGOPAL DEY | 10.12 | 0 | 0
132 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A( Mouza-Amlatara,Chatumadar,Kajali,Karamadi under Chatumadar G.P). (987 Nos.) (Tender No.409/EE/PD of 2020-2021) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000989/2021-2022 | BP-2021-22-240 | 16/02/2022 | 0 | ALOK KUMAR CHAKRABORTY | 2.61 | 0 | 0
133 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.)(300 Nos) (Tender No..902/EE/PD OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000999/2022-2023 | BP-2022-23-238 | 05/09/2022 | 0 | ALOK KUMAR CHAKRABORTY | 6.2 | 0 | 0
134 | Purulia Division | Raghunathpur Sub-Division | Additional Functional Household Tap Connection (FHTC) in connection with other allied works of Manguria-Lalpur W/s Scheme. (Tender No.901/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001009/2021-2022 | BP-2021-22-258 | 25/02/2022 | 0 | ALOK KUMAR CHAKRABORTY | 5.92 | 0 | 0
135 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001116/2021-2022 | BP-2021-22-326 | 22/03/2022 | 0 | SWAPAN MANDAL | 8.16 | 0 | 0
136 | Purulia Division | Raghunathpur Sub-Division | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001137/2021-2022 | BP-2021-22-292 | 09/03/2022 | 0 | PREMNATH MITRA | 53.06 | 0 | 0
137 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Manguria lalpur Water Supply scheme Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000081/2021-2022 | 166/PMD | 07/03/2022 | 30 | JAL PRAVAHIKA PVT. LTD | 20.5 | 11.71 | 100
138 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well and existing one no tube well with allied cable line and other allied works for augmentation of Manguria Lalpur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000289/2022-2023 | 80/PMD | 01/02/2023 | 60 | RAJIB COMPANY | 24.65 | 22.9 | 100
139 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Manguria Lalpur water supply scheme under PMD PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000290/2022-2023 | 82/PMD | 01/02/2023 | 60 | SWAPAN ENTERPRISE | 13.25 | 0 | 100
140 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Manguria Lalpur water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000294/2022-2023 | 81/PMD | 01/02/2023 | 60 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 49.6 | 0 | 100
141 | Purulia Mechanical | Raghunathpur Sub-Division | SUPPLY DELIVERY & INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM OF AUGMENTATION OF MANGURIA LALPUR W/S SCHEME, HURA BLOCK UNDER PMD PHE DTE.(TR.NO 371 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000081/2022-2023 | C042211603113 | 08/04/2022 | 0 | JAL PRAVAHIKA PVT. LTD | 8.78 | 0 | 0
142 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 110 KVA AT 0.4 KV TO 160/160/160/160/160 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , THE EX ENGG PMD PHE DTE(CONSUMER ID : 950009505) TO THEIR PREMISES AT MANGURIA LALPUR WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000427/2022-2023 |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 9.17 | 0 | 0
143 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Regarding laying of water supply pipe line along PWD Land on (i) Manbazar_Bansa Road at ch.0.00 Kmp to 0.765 Km & Damda-Chakoltore-Dradi-Kenda-Manbazar Road at ch. 45.526 to 46.00 Kmp (ii) Indkuri-Manbazar Road at ch.0.00 Km to 0.850 Km, (iii) Sindri-Manbazar Road at ch. 17.00 Kmp to 17.80 Km, (iV) Manbazar-Bandwan-Kuilapal Road at ch. 0.00 kmp to 0.636 Km in respect of Augumentation of Manbazar Water suplly Scheme under JJM. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00028/2022-2023 | BP-2022-23-464 | 09/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 146.74 | 0 | 0
144 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipeline at different School & ICDS center for providing 21 nos Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of Manbazar W/S Scheme of Manbazar-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000007/2023-2024 | 535/PD | 12/04/2023 | 60 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 4.4 | 3.99 | 91
145 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Manbazar (Harekristapur) river site for Augmentation of Manbazar W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000023/2023-2024 | 542/PD | 12/04/2023 | 100 | BASANTA PARAMANIK | 14.05 | 0 | 70
146 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Shifting and laying of DI rising main and HDPE distribution main pipeline from manbazar Bus stand to warehouse along manbazar- Bandwan road due to widening of PWD road at Manbazar-1 block under Manbazar-I Water Supply Scheme Under Purulia Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000039/2023-2024 | 667/PD | 17/05/2023 | 60 | ROY CONSTRUCTION | 15.28 | 0 | 75
147 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of high & low lift pump house including other allied works at Harekristapur river site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000041/2023-2024 | 658/PD | 17/05/2023 | 45 | INDRAJIT SARKAR | 4.4 | 4.27 | 97
148 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Reconditioning of filter Bed by Changing of Filter Media of WTP and Inside & Outside Painting Of WTP Structures & Intake Bridge at Mouza Ghat of Manbazar II Block (part) W/S Scheme of Purulia Sadar Sub-Division under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000109/2023-2024 | 871/PD | 30/06/2023 | 30 | ANUP KUMAR SAHA | 25.51 | 9.26 | 80
149 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : KASATORA (Part), MANBAZAR (Part) VILLAGE] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000302/2022-2023 | 835/PD | 19/05/2022 | 243 | NANIGOPAL DEY | 43.62 | 18.63 | 90
150 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000303/2022-2023 | 836/PD | 19/05/2022 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 26.43 | 100
151 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-II) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000319/2022-2023 | 869/PD | 23/05/2022 | 618 | ZAKIR HOSSIN MONDAL | 86.39 | 63.88 | 100
152 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-II) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000324/2022-2023 | 857/PD | 23/05/2022 | 496 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 14.06 | 10.62 | 100
153 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000326/2022-2023 | 858/PD | 23/05/2022 | 100 | ROY CONSTRUCTION | 13.86 | 12.93 | 98
154 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000502/2022-2023 | 438/PSD | 24/06/2022 | 10 | RAKSHIT ENTERPRISE | 4.39 | 0 | 100
155 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : CHARKI, RAMNAGAR, KHALPARA, KENBEDYA, KASATORA (Part), MANBAZAR (Part) VILLAGE] (2nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000533/2022-2023 | 1049/PD | 08/07/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 128.82 | 64.46 | 90
156 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000541/2022-2023 | 1060/PD | 08/07/2022 | 30 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 28.64 | 14.75 | 0
157 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-I, Zone-II & Zone-V of Habitation- Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-I),(1. GP-Kumari, Habitation-Toparbad,Tilaboni,Susunia,Rangametya, Manikdi, Kumari, Kuchlifela, Dhanda, Boch ,Khariduara Alis Balarampur, 2) Dighi GP-Tamakhun, Jhariadi.) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000620/2022-2023 | 1393/PD | 01/09/2022 | 45 | ANUP KUMAR SAHA | 11.23 | 10.03 | 100
158 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Balaance Work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area Zone-III, & Zone-IV of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000738/2022-2023 | 1478/PD | 20/09/2022 | 45 | SADHAN GORAIN | 21.29 | 0 | 100
159 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : MADHUPUR, BOLUDI & JHARBAGDA (Part) VILLAGE] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000793/2022-2023 | 1444/PD | 14/09/2022 | 742 | MACHINO TECHNO | 122.46 | 9.55 | 65
160 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : MANBAZAR (Part), PATHARMOHORA VILLAGE] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000794/2022-2023 | 1445/PD | 14/09/2022 | 742 | MACHINO TECHNO | 123.8 | 31.78 | 64
161 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of R.C.C. Elevated Reservoir, Capcaity 600 cum (Intze Type), Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000924/2022-2023 | 1897/PD | 15/12/2022 | 270 | DEBAKI RANJAN SARKAR | 148.87 | 105.73 | 72
162 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Pump house cum switch room including other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001128/2022-2023 | 377/PD | 15/03/2023 | 45 | ROY CONSTRUCTION | 2.19 | 0 | 100
163 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Inter connection of 200 mm dia DI pipe with newly constructed CWR including Repairing and Renovation of Guard Room cum Store Room, Boundary wall with sanitary, plumbing & electrification work with other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001129/2022-2023 | 376/PD | 15/03/2023 | 45 | ROY CONSTRUCTION | 6.54 | 2.27 | 100
164 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000012/2022-2023 | 968/PD | 21/06/2022 | 0 | Resource Division | 120.16 | 0 | 0
165 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000026/2022-2023 | 988/PD | 23/06/2022 | 0 | Resource Division | 0.47 | 0 | 0
166 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000028/2022-2023 | 1016/PD | 05/07/2022 | 0 | Resource Division | 132.89 | 0 | 0
167 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000039/2022-2023 | 241/PD | 20/02/2023 | 0 | Resource Division | 217.33 | 0 | 0
168 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Manbazar W/S Scheme, Block- Manbazar-I) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 539/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000916/2022-2023 | BP-2022-23-118 | 16/07/2022 | 0 | RADIANT | 6.62 | 0 | 0
169 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No- 577/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001069/2022-2023 | BP-2022-23-422 | 11/11/2022 | 0 | RAKSHIT ENTERPRISE | 4.34 | 0 | 0
170 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for new connection | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00453/2023-2024 | BP-23-24-220 | 05/12/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
171 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0
172 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house buiding, substation building,OHR site Chorination room at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000181/2023-2024 | 1171/PMD | 03/11/2023 | 456 | RABINDRA NATH KHAN | 34.4 | 0 | 35
173 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000428/2022-2023 | 246/PMD | 03/03/2023 | 788 | NUPUR CHANDRA HALDER | 69.09 | 0 | 65
174 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000432/2022-2023 | 251PMD | 06/03/2023 | 60 | MOON LIGHT HOUSE | 12.08 | 0 | 80
175 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell at Manbazar w/s(zone-1) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000433/2022-2023 | 252/PMD | 06/03/2023 | 60 | SANTANU BANERJEE | 48.12 | 0 | 57
176 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 175kva voltage stabilizer for Augmentation of Manbazar w/s(Zone-1) scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000434/2022-2023 | 253/PMD | 06/03/2023 | 703 | SANTU MITRA | 18.25 | 0 | 59
177 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000003/2023-2024 | 612/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0
178 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000006/2023-2024 | 529/PD | 11/04/2023 | 60 | AQUEDUCT PLASTICS PVT LTD | 447.81 | 32.76 | 8
179 | Purulia Division | Raghunathpur Sub-Division | Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/06/2023 to 31/10/2023) | Assistant Engineer |  | ORD/000161/2023-2024 | 220/RNP | 30/05/2023 | 153 | CHANDRA SHEKHAR KUNDU | 0.74 | 1.58 | 100
180 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 100
181 | Purulia Division | Raghunathpur Sub-Division | Continuous work order for the work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/11/2023 to 31/03/2024) | Assistant Engineer |  | ORD/000844/2023-2024 | 466/RNP | 10/10/2023 | 152 | CHANDRA SHEKHAR KUNDU | 0.74 | 0 | 60
182 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 100
183 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 100
184 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
185 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
186 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
187 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
188 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 331 cum and other allied works under Raghunathpur W/S Scheme (Zone-VII-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001171/2024-2025 | 2325/PD | 31/12/2024 | 381 | NANIGOPAL DEY | 13.17 | 0 | 0
189 | Purulia Division | Raghunathpur Sub-Division | Continuation Work Order for the Work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/04/2024 to 31/08/2024) | Assistant Engineer |  | ORD/003683/2023-2024 | 139/RNP | 12/03/2024 | 153 | CHANDRA SHEKHAR KUNDU | 0.74 | 0 | 0
190 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000035/2022-2023 | 79/PD | 17/01/2023 | 0 | Resource Division | 0.15 | 0 | 0
191 | Purulia Division | Purulia Sadar Sub-Division | Repairing, renovation of Boundary Wall at WTP & OHR site of Hutmura W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000165/2023-2024 | 936/PD | 19/07/2023 | 30 | M/S. DESTINY CONSTRUCTION | 9.67 | 1.4 | 100
192 | Purulia Division | Purulia Sadar Sub-Division | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer |  | ORD/000338/2024-2025 | 1364/PD | 25/07/2024 | 240 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 50
193 | Purulia Division | Purulia Sadar Sub-Division | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 650 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Hutumura W/S Scheme for source augmentation | Assistant Engineer |  | ORD/000542/2023-2024 | 1339/PD | 08/09/2023 | 730 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 248.15 | 0 | 40
194 | Purulia Mechanical | Purulia Sadar Sub-Division | Priming arrangement for two nos centrifugal pump and two back wash pump and other allied works at Hutmura (OHR) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | Assistant Engineer |  | ORD/000065/2024-2025 | 994/PMD | 21/06/2024 | 60 | SUBRATA DUTTA | 1.06 | 0 | 100
195 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply, Delivery and installation of submersible pumping machineries, flowmeter, backwash pump, chlorination system, external lighting arrangement with other allied works in connection with new WTP for augmentation of Hutmura(Intake side & new CWR Zone ) w/s scheme under PMD, PHE Dte. in the District of Purulia. | Assistant Engineer |  | ORD/000682/2024-2025 | 1694/PMD | 06/12/2024 | 90 | DEY ENTERPRISE, HOWRAH | 55.15 | 0 | 0
196 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying Distribution System including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII B) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000005/2023-2024 | 530/PD | 11/04/2023 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 280.39 | 75.61 | 48
197 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Distribution System including providing Functional Household Tap Connection (FHTC), Construction of 350 cum OHR and staging height of 20 mtr. and other other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone - VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000033/2023-2024 | 583/PD | 20/04/2023 | 270 | PRAVAT SARKAR | 321.22 | 170.69 | 78
198 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying Distribution System of pipe line from Borsolia culvert to Sagarka more & Danduya Village including providing House Hold Tap Connection (FHTC)other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone -VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000491/2024-2025 | 1708/PD | 05/09/2024 | 483 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 51.67 | 0 | 80
199 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000656/2024-2025 | 1875/PD | 01/10/2024 | 45 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 21.26 | 0 | 0
200 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | RTOR000036/2022-2023 | 76/PD | 17/01/2023 | 0 | Resource Division | 65.11 | 0 | 0
201 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | For new connection of Augmentation of Raghunathpur zone VII B | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | BILL/00776/2023-2024 | BP-23-24-278 | 01/02/2024 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0
202 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-IV) under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000009/2025-2026 | 620/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0
203 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VII B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000044/2023-2024 | 450/PMD | 20/04/2023 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 65
204 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B under Purulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000584/2024-2025 | 1443/PMD | 01/10/2024 | 60 | M/S A.D. CONCERN | 3.87 | 0 | 0
205 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and laying of cable and other works, at OHR site Ketlapur of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000609/2024-2025 | 857/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.64 | 0 | 95
206 | Purulia Division | Raghunathpur Sub-Division | Construction of 1 No. Secondary Pannel cum meter Room at Lakhanpur W.T.P. near Intake Bridge under Raghunathpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000115/2023-2024 | 883/PD | 03/07/2023 | 30 | CHANDAN CHATTERJEE | 6.78 | 3.94 | 100
207 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC), and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IIA)within Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-3) | Assistant Engineer |  | ORD/000266/2023-2024 | 1020/PD | 01/08/2023 | 669 | ANUP KUMAR SAHA | 401.92 | 0 | 100
208 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur W/S (Zone-VI-B) at Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000354/2024-2025 | 1382/PD | 25/07/2024 | 90 | SOUVIK MANDAL | 92.92 | 0 | 0
209 | Purulia Division | Raghunathpur Sub-Division | Construction of Substation Building at Boosting station (Seleta mouza) under Raghunathpur water supply scheme and Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000379/2024-2025 | 1402/PD | 25/07/2024 | 526 | SUBRATA SINGHADEO | 40.98 | 0 | 75
210 | Purulia Division | Raghunathpur Sub-Division | Construction of Rcc Over Head Reservoir (Torch type with solid raft)of capacity 150 cum and staging heght 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC)and other alliedworks for Aug. work of Raghunathpur Watersupply scheme (German Assisted) (Zone-II B) within Raghunathpur Sub-Division under Purulia Division,PHE Dte.(SL-4) | Assistant Engineer |  | ORD/000555/2023-2024 | 1337/PD | 08/09/2023 | 755 | MANIRUL ISLAM SK | 261.26 | 0 | 63
211 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room with toilet block at Zone-IIA under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001040/2024-2025 | 2100/PD | 05/12/2024 | 60 | PURNA CHANDRA TEWARI | 6.42 | 0 | 0
212 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room with toilet block at Zone-IIB under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001041/2024-2025 | 2101/PD | 05/12/2024 | 60 | CHANCHAL MISHRA | 6.43 | 0 | 0
213 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, hi-lifting boundary wall and other allied works under Raghunathpur W/S Scheme (Zone-II-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001118/2024-2025 | 2190/PD | 13/12/2024 | 90 | DILIP MISHRA | 12.66 | 0 | 0
214 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-II B) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001145/2024-2025 | 2299/PD | 31/12/2024 | 181 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 78.64 | 0 | 0
215 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room Cum Chlorin Room at Zone-II-B (Khajura) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001361/2023-2024 | 1730/PD | 04/12/2023 | 180 | MAA TARA CONSTRUCTION | 4.86 | 0 | 100
216 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000031/2022-2023 | 77/PD | 17/01/2023 | 0 | Resource Division | 4.22 | 0 | 0
217 | Purulia Mechanical | Raghunathpur Sub-Division | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE IIB | Assistant Engineer |  | BILL/00478/2023-2024 | BP-23-24-248 | 04/01/2024 | 0 | WBSEDCL PURULIA | 2.87 | 0 | 0
218 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with allied works, at OHR site-II B, Khajura under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000016/2025-2026 | 635/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.37 | 0 | 0
219 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone II B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000121/2023-2024 | 802/PMD | 12/07/2023 | 30 | A G ENTERPRISE | 21.84 | 0 | 85
220 | Purulia Mechanical | Raghunathpur Sub-Division | Earthing arrangement and other works, at OHR site Uporkhajura of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000605/2024-2025 | 899/PMD | 10/06/2024 | 15 | ANUP KUMAR SAHA | 0.5 | 0 | 90
221 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000655/2024-2025 | 1027/PMD | 25/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 95
222 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Scada Room and Chlorine Room at Balarampur (Zone - III, IV & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000221/2025-2026 | 1086/PD | 17/06/2025 | 120 | RANI SATI CONSTRUCTION | 43.06 | 0 | 0
223 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Division, PHE Dte. (w.e.f.01.09.2023 to 31.08.2024.) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/004200/2023-2024 | 477/A/PR | 31/08/2023 | 366 | ANUP KUMAR SAHA | 1.76 | 0 | 0
224 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Executive Engineer, Purulia Mechanical Division PHE, Dte. (01/10/24 to 31/03/25) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000615/2024-2025 | 400/PMSD(W/S) | 23/09/2024 | 182 | TAPAN KUMAR DEY | 0.86 | 0 | 0
225 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411410689904167XX DT.24-10-2024. | Assistant Engineer |  | BILL/00943/2024-2025 | BP-2024-25-520 | 29/10/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.93 | 0 | 0
226 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411113832563388047XX DT.24-10-2024. | Assistant Engineer |  | BILL/00944/2024-2025 | BP-2024-25-521 | 29/10/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.04 | 0 | 0
227 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050912202411333713585370XX DT.09-12-2024. | Assistant Engineer |  | BILL/01062/2024-2025 | BP-2024-25-535 | 13/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
228 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401322652788750XX DT.16-12-2024. | Assistant Engineer |  | BILL/01078/2024-2025 | BP-2024-25-539 | 19/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
229 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401360237000585XX DT.16-12-2024. | Assistant Engineer |  | BILL/01079/2024-2025 | BP-2024-25-538 | 19/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
230 | Purulia Division | Purulia Sadar Sub-Division | Sinking of 3 nos New 200 mm dia horizontal tube-well and laying of 100mm dia GI pipe collecting main from RBT to common manifold at river side of Satra Head Works site of Purulia water supply scheme (Northern Sector) under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000206/2024-2025 | 1064/PD | 07/06/2024 | 45 | SUBODH PRAMANIK | 32.54 | 0 | 100
231 | Purulia Division | Purulia Sadar Sub-Division | Providing Left Out &Parallal distribution pipe line including Functional Household Tap Connection (FHTC) and Distribution main in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000217/2024-2025 | 1246/PD | 04/07/2024 | 271 | S.S. CONSTRUCTION | 95.44 | 0 | 0
232 | Purulia Division | Purulia Sadar Sub-Division | Providing Left Out &Parallal distribution pipe line in connection with Jal Jeevan Mission (JJM and) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000241/2024-2025 | 1245/PD | 04/07/2024 | 271 | M/S. S. CHOUDHURY | 66.92 | 0 | 0
233 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and Providing FHTC including other allied work for Nadiyara mouza ( Zone-V Part-B) Northern Zone at Purulia-I Block under Purulia Water Supply Scheme Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000246/2024-2025 | 1136/PD | 18/06/2024 | 60 | NANIGOPAL DEY | 74.58 | 0 | 0
234 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone I H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000282/2023-2024 | 1139/PD | 17/08/2023 | 684 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 100
235 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone II H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte | Assistant Engineer |  | ORD/000283/2023-2024 | 1140/PD | 17/08/2023 | 958 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 0
236 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone I H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000284/2023-2024 | 1141/PD | 17/08/2023 | 30 | MAA TARA CONSTRUCTION | 18.03 | 0 | 100
237 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone III H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000285/2023-2024 | 1143/PD | 17/08/2023 | 30 | BABA LOKNATH ENTERPRISE | 18.56 | 0 | 100
238 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone VI H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000287/2023-2024 | 1146/PD | 17/08/2023 | 30 | HUSSAIN CONSTRUCTION | 21.51 | 0 | 70
239 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone VII H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000288/2023-2024 | 1147/PD | 17/08/2023 | 30 | GANGULY ENTERPRISES | 16.72 | 0 | 100
240 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone V H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000289/2023-2024 | 1145/PD | 17/08/2023 | 30 | SUMIT KUMAR MITRA | 15.1 | 0 | 100
241 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone II H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000290/2023-2024 | 1142/PD | 17/08/2023 | 30 | SANTOSH KUMAR | 15.35 | 0 | 100
242 | Purulia Division | Purulia Sadar Sub-Division | New sinking of 2(Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line of Puncha W/S at Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000346/2024-2025 | 1376/PD | 25/07/2024 | 30 | SOUVIK MANDAL | 7.56 | 0 | 100
243 | Purulia Division | Purulia Sadar Sub-Division | Making arrangement of interconnection at distribution pipeline with newly laid distribution pipeline & installation of sluice valves on pipeline at jiudaru mouza under Kotshila W/S at Purulia Water Supply scheme (Northern Sector) under Purulia Division,PHEDte. | Assistant Engineer |  | ORD/000347/2024-2025 | 1377/PD | 25/07/2024 | 60 | GOUTAM CHAKRABORTY | 12.21 | 0 | 100
244 | Purulia Division | Purulia Sadar Sub-Division | Fencing work with concrete pillars for 15 Nos vested land for Northern & Southern Sector water supply scheme Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000452/2024-2025 | 1513/PD | 27/08/2024 | 45 | CHATTERJEE CONSTRUCTION | 5.9 | 0 | 100
245 | Purulia Division | Purulia Sadar Sub-Division | Road Crossing of Distribution Main by jack pushing at PWD Road & supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I V OHR site to Panjunia Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) & with all allied works at Kolaboni under Keliyathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000644/2024-2025 | 1655/PD | 30/08/2024 | 90 | MS GORAIN CONCERN | 50.19 | 0 | 100
246 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(Sl No. 8) | Assistant Engineer |  | ORD/000779/2023-2024 | 1423/PD | 29/09/2023 | 540 | KHAN ENTERPRISE | 430.24 | 0 | 20
247 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (SL-16) | Assistant Engineer |  | ORD/000780/2023-2024 | 1418/PD | 29/09/2023 | 540 | KOUSHIK CHATTERJEE | 274.47 | 0 | 70
248 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL-5) | Assistant Engineer |  | ORD/000783/2023-2024 | 1420/PD | 29/09/2023 | 675 | MS D.PALIT AND CO. | 373.13 | 0 | 50
249 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 6) | Assistant Engineer |  | ORD/000793/2023-2024 | 1429/PD | 29/09/2023 | 672 | PRAVAT SARKAR | 406.17 | 0 | 30
250 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 300 CUM andstaging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone-I of Purulia-2 block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-5) | Assistant Engineer |  | ORD/000835/2023-2024 | 1427/PD | 29/09/2023 | 270 | HANNAN BUILDERS PRIVATE LIMITED | 441.37 | 0 | 0
251 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | Assistant Engineer |  | ORD/000836/2023-2024 | 1425/PD | 29/09/2023 | 703 | SUJIT SAHANA | 274.06 | 0 | 22
252 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 500 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-V Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | Assistant Engineer |  | ORD/000896/2023-2024 | 1558/PD | 18/10/2023 | 270 | M/S TARUN KUMAR PATRA | 869.94 | 0 | 0
253 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTC for the period of thirty six month (36) at Zone-V of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-2) | Assistant Engineer |  | ORD/000916/2023-2024 | 1597/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 536.56 | 0 | 5
254 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone- I of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 1) | Assistant Engineer |  | ORD/000919/2023-2024 | 1596/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 405.49 | 0 | 8
255 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Zone- V & VI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL N.3) | Assistant Engineer |  | ORD/000922/2023-2024 | 1595/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 1031.22 | 0 | 12
256 | Purulia Division | Purulia Sadar Sub-Division | Laying a dedicated pipe Line for Jaratanr, briddhitanr for the distribution System and repairing work at Gungligora of BORAM Under Purulia W/S scheme (Northern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001050/2024-2025 | 2111/PD | 05/12/2024 | 479 | SOUMITRA CHAKRABORTY | 11.94 | 0 | 50
257 | Purulia Division | Purulia Sadar Sub-Division | Laying of Balance Pipeline under Command area of Purulia -1 (Northern Sector) under Jal Jeevan Mission Project under Purulia Division, PHE Dte (Bhul Mouza) | Assistant Engineer |  | ORD/001051/2024-2025 | 2112/PD | 05/12/2024 | 60 | SOUMITRA CHAKRABORTY | 38.35 | 0 | 70
258 | Purulia Division | Purulia Sadar Sub-Division | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tube well along with necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Maheshnadi Under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001053/2024-2025 | 2114/PD | 05/12/2024 | 150 | ASHOKE KUMAR CHATTERJEE | 19.19 | 0 | 0
259 | Purulia Division | Purulia Sadar Sub-Division | Laying pipe line across railway track near Mouza-Gangpur for supply of water under Ramchandrapur (Zone-I) Under Purulia W/S scheme (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001058/2024-2025 | 2119/PD | 05/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 34.39 | 0 | 100
260 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC) including other allied work at gap portion of Tiyashi for Zone-IV of Santuri Block under Purulia Pipe water supply scheme (Northern section) under Purulia Dvision PHED te [ Part-A Mouza- Tiyashi, Marbedya, Ghoramurga]. | Assistant Engineer |  | ORD/001060/2024-2025 | 2121/PD | 05/12/2024 | 392 | AMIT PATHAK | 44.28 | 0 | 0
261 | Purulia Division | Purulia Sadar Sub-Division | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tube well along with necessary 110 mm dia HDPE collecting line from River bed Tube well to common manifold chamber at river bank (Damodar River) at Bhamuria Under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001063/2024-2025 | 2124/PD | 05/12/2024 | 45 | KHITISH CHANDRA PATHAK | 12.46 | 0 | 100
262 | Purulia Division | Purulia Sadar Sub-Division | Making arrangement for support structure for completion of Jack Pushing work under railway line for laying of distribution pipeline & other allied works at lagda Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001064/2024-2025 | 2125/PD | 05/12/2024 | 60 | SADHAN GORAIN | 11.12 | 0 | 100
263 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work under Balitora Zone-1 at Balitora under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001069/2024-2025 | 2129/PD | 05/12/2024 | 177 | KHITISH CHANDRA PATHAK | 27.97 | 0 | 75
264 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001147/2024-2025 | 2187/PD | 13/12/2024 | 60 | JOGMAYA CONSTRUCTION | 20.09 | 0 | 0
265 | Purulia Division | Purulia Sadar Sub-Division | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Satra under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | Assistant Engineer |  | ORD/001210/2024-2025 | 109/PD | 21/01/2025 | 376 | AKUL SUTRADHAR | 3.92 | 0 | 60
266 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Dulmi mouza under Purulia Water Supply Scheme ( Northern Sector) Under Purulia Division , PHE Dte. | Assistant Engineer |  | ORD/001251/2023-2024 | 1699/PD | 30/11/2023 | 60 | SUNNY ELECTRIC CO | 72.3 | 0 | 0
267 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Rudra Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001253/2023-2024 | 1700/PD | 30/11/2023 | 610 | M/S CHAKRABORTY CONSTRUCTION | 59.01 | 0 | 0
268 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Belguma mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001256/2023-2024 | 1514/PD | 16/10/2023 | 45 | SEKH ABBAS | 28.09 | 0 | 0
269 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Maguria mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001257/2023-2024 | 1515/PD | 16/10/2023 | 45 | SOUVIK MANDAL | 45.44 | 0 | 0
270 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Raibandh Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001258/2023-2024 | 1561/PD | 18/10/2023 | 45 | CHATTERJEE CONSTRUCTION | 12.16 | 0 | 0
271 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Chakda mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001259/2023-2024 | 1562/PD | 18/10/2023 | 45 | M DHARA & BROTHERS | 38.95 | 0 | 0
272 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kalipur mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001261/2023-2024 | 1568/PD | 26/10/2023 | 45 | PRADIPTA CHOUDHURY | 1.3 | 0 | 0
273 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Simulia mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001262/2023-2024 | 1600/PD | 31/10/2023 | 45 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 31.76 | 0 | 0
274 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kotloi Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001264/2023-2024 | 1603/PD | 01/11/2023 | 410 | SUBODH PRAMANIK | 37.61 | 0 | 0
275 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Dulmi Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001265/2023-2024 | 1604/PD | 01/11/2023 | 45 | CHANCHAL MISHRA | 8.03 | 0 | 0
276 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including FHTC and other allied work for Zone-III of Purulia-I block for Simulbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001330/2023-2024 | 1713/PD | 04/12/2023 | 60 | THE STAR & CO. | 41.68 | 0 | 0
277 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ketuabera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001331/2023-2024 | 1714/PD | 04/12/2023 | 60 | M/S SB CONSTRUCTION | 47.7 | 0 | 0
278 | Purulia Division | Purulia Sadar Sub-Division | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector ), Kashipur Block Zone XI & XII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001331/2024-2025 | 477/PD | 25/03/2025 | 120 | SUJIT SAHANA | 29.95 | 0 | 0
279 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Kukurgarya mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001332/2023-2024 | 1715/PD | 04/12/2023 | 724 | HIRAK KUMAR SAO | 72.48 | 0 | 65
280 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ghagharjuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001333/2023-2024 | 1716/PD | 04/12/2023 | 100 | BALAJI UDDYOG | 93.8 | 0 | 0
281 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) with allied works for purulia water supply scheme.(Location:-Block-Purulia -I, Zone-III) for Northern Zone. | Assistant Engineer |  | ORD/001334/2023-2024 | 1717/PD | 04/12/2023 | 270 | M/S RAJ KUMAR KHAN | 96.67 | 0 | 30
282 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - I of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 145 mtr.) | Assistant Engineer |  | ORD/001338/2023-2024 | 1721/PD | 04/12/2023 | 60 | S.PATHAK & CO. | 19.47 | 0 | 100
283 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - II of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 132 mtr.) | Assistant Engineer |  | ORD/001339/2023-2024 | 1722/PD | 04/12/2023 | 542 | SAIBAL SARKAR | 18.17 | 0 | 65
284 | Purulia Division | Purulia Sadar Sub-Division | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone XIII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001339/2024-2025 | 488/PD | 25/03/2025 | 120 | MADHU SUDAN RAKSHIT | 59.38 | 0 | 95
285 | Purulia Division | Purulia Sadar Sub-Division | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone VI within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001344/2024-2025 | 493/PD | 25/03/2025 | 251 | PRINCE INDUSTRIES ( INDIA) | 89.76 | 0 | 50
286 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012), Laying of Distribution Pipe line & providing Functional Household Tap Connection (FHTC) including other allied works, for Zone- I of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A, Mouza - Mohanpur] | Assistant Engineer |  | ORD/001345/2023-2024 | 697/PD | 22/05/2023 | 680 | KHITISH CHANDRA PATHAK | 93.94 | 0 | 40
287 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - III of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 115 mtr.) | Assistant Engineer |  | ORD/001348/2023-2024 | 1723/PD | 04/12/2023 | 575 | CHANCHAL MISHRA | 16.47 | 0 | 100
288 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - IV of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 115 mtr.) | Assistant Engineer |  | ORD/001350/2023-2024 | 1724/PD | 04/12/2023 | 60 | MOUSUMI BANERJEE | 16.44 | 0 | 75
289 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - V of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 165 mtr.) | Assistant Engineer |  | ORD/001352/2023-2024 | 1725/PD | 04/12/2023 | 60 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 21.47 | 0 | 100
290 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Talberya (20%)] | Assistant Engineer |  | ORD/001356/2023-2024 | 1726/PD | 04/12/2023 | 60 | VINCI CONSTRUCTION | 12.23 | 0 | 60
291 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -H , Mouza - Nabaghanadi alias Patharbad&Khayerbasia Chak] | Assistant Engineer |  | ORD/001357/2023-2024 | 1727/PD | 04/12/2023 | 60 | IKBAL CONSTRUCTION | 19.32 | 0 | 0
292 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Gopalpur, Mahukura] | Assistant Engineer |  | ORD/001448/2023-2024 | 1807/PD | 08/12/2023 | 45 | S. S. ENTERPRISE | 30.88 | 0 | 64
293 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer |  | ORD/001449/2023-2024 | 1767/PD | 08/12/2023 | 456 | PRINCE INDUSTRIES ( INDIA) | 21.48 | 0 | 100
294 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | Assistant Engineer |  | ORD/001450/2023-2024 | 1768/PD | 08/12/2023 | 60 | CHAIL CONSTRUCTION | 21.95 | 0 | 100
295 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | Assistant Engineer |  | ORD/001451/2023-2024 | 1769/PD | 08/12/2023 | 60 | M/S SAYAK BHATTACHARYA | 21.97 | 0 | 100
296 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 125 mtr.) | Assistant Engineer |  | ORD/001452/2023-2024 | 1770/PD | 08/12/2023 | 60 | CHINMOY SEN | 17.39 | 0 | 70
297 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - V of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer |  | ORD/001453/2023-2024 | 1771/PD | 08/12/2023 | 60 | SUBHAS CHANDRA MAHATO | 22.82 | 0 | 98
298 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 137 mtr.) | Assistant Engineer |  | ORD/001454/2023-2024 | 1772/PD | 08/12/2023 | 456 | PRINCE INDUSTRIES ( INDIA) | 18.68 | 0 | 100
299 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer |  | ORD/001456/2023-2024 | 1773/PD | 08/12/2023 | 60 | NANIGOPAL DEY | 23.75 | 0 | 10
300 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 145 mtr.) | Assistant Engineer |  | ORD/001457/2023-2024 | 1774/PD | 08/12/2023 | 60 | IKBAL CONSTRUCTION | 19.41 | 0 | 0
301 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - X of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001460/2023-2024 | 1776/PD | 08/12/2023 | 60 | CHANCHAL MISHRA | 20.96 | 0 | 97
302 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer |  | ORD/001462/2023-2024 | 1777/PD | 08/12/2023 | 60 | BHUTNATH MISHRA | 23.66 | 0 | 100
303 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer |  | ORD/001463/2023-2024 | 1778/PD | 08/12/2023 | 60 | M/S KHAN ENTERPRISE | 21.46 | 0 | 60
304 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001465/2023-2024 | 1779/PD | 08/12/2023 | 796 | MADHU SUDAN RAKSHIT | 20.95 | 0 | 0
305 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 65 mtr.) | Assistant Engineer |  | ORD/001466/2023-2024 | 1780/PD | 08/12/2023 | 60 | PURNA CHANDRA TEWARI | 11.43 | 0 | 98
306 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 205 mtr.) | Assistant Engineer |  | ORD/001467/2023-2024 | 1781/PD | 08/12/2023 | 469 | CHANDAN CHATTERJEE | 25.44 | 0 | 100
307 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XVI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer |  | ORD/001469/2023-2024 | 1782/PD | 08/12/2023 | 540 | PARTHASARATHI SAHABABU | 20.67 | 0 | 50
308 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001470/2023-2024 | 1783/PD | 08/12/2023 | 756 | SUBRATA SINGHADEO | 20.81 | 0 | 65
309 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001471/2023-2024 | 1784/PD | 08/12/2023 | 60 | BISWAJIT MAJI | 20.94 | 0 | 100
310 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001473/2023-2024 | 1785/PD | 08/12/2023 | 353 | KM ENTERPRISES | 20.98 | 0 | 100
311 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001474/2023-2024 | 1786/PD | 08/12/2023 | 755 | SUBRATA SINGHADEO | 20.83 | 0 | 0
312 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - V of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001476/2023-2024 | 1787/PD | 08/12/2023 | 755 | PRINCE INDUSTRIES ( INDIA) | 20.98 | 0 | 90
313 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VI of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001477/2023-2024 | 1788/PD | 08/12/2023 | 60 | SOUVIK MANDAL | 20.95 | 0 | 80
314 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer |  | ORD/001478/2023-2024 | 1789/PD | 08/12/2023 | 471 | DEBAKI RANJAN SARKAR | 21.19 | 0 | 65
315 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1 , Zone-VII ) for Northern Zone | Assistant Engineer |  | ORD/001480/2023-2024 | 1791/PD | 08/12/2023 | 612 | SAHADEV HALDER | 70.08 | 0 | 65
316 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1, Zone-VI) for Northern Zone | Assistant Engineer |  | ORD/001481/2023-2024 | 1792/PD | 08/12/2023 | 270 | SADHAN GORAIN | 74.45 | 0 | 0
317 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Golbera mouza (Zone-VII) Under Purulia Divn PHE DTE | Assistant Engineer |  | ORD/001483/2023-2024 | 1795/PD | 08/12/2023 | 45 | SEKH ABBAS | 19.55 | 0 | 0
318 | Purulia Division | Purulia Sadar Sub-Division | Laying of Collecting line from Kanshabati Riverbed to Harekishtapur Riversite Pump House under Manbazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/001485/2023-2024 | 1798/PD | 08/12/2023 | 60 | RAJAT KARMAKAR | 24.44 | 0 | 100
319 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including providing FHTC including other allied work allied works for purulia water supply scheme.(Northern Sector ) at Purulia -I Block (Zone-IV) for Hulka Mouza under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001495/2023-2024 | 1794/PD | 08/12/2023 | 480 | SUBRATA MAHAPATRA | 82.06 | 0 | 65
320 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-III of Purulia-I block for Belkundi mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001611/2023-2024 | 1824/PD | 12/12/2023 | 567 | GOUTAM CHAKRABORTY | 86.92 | 0 | 75
321 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Nadiyara Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001613/2023-2024 | 1825/PD | 12/12/2023 | 750 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 53.85 | 0 | 1
322 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-VIII) for Rudra mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001615/2023-2024 | 1827/PD | 12/12/2023 | 60 | SUSANTA KR DUTTA | 24.58 | 0 | 0
323 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1 , Zone-V ) for Northern Zone. | Assistant Engineer |  | ORD/001616/2023-2024 | 1828/PD | 12/12/2023 | 270 | M/S SB CONSTRUCTION | 70.03 | 0 | 60
324 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (part) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001637/2023-2024 | 1826/PD | 12/12/2023 | 60 | BARI ENTERPRISE | 29.81 | 0 | 0
325 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-V) for Mahalitora mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001692/2023-2024 | 1867/PD | 21/12/2023 | 60 | BHAGABANDAS KUMAR | 15.2 | 0 | 0
326 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001819/2023-2024 | 51/PD | 09/01/2024 | 60 | ANUP KUMAR SAHA | 148.36 | 0 | 0
327 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-XIV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | Assistant Engineer |  | ORD/003493/2023-2024 | 348/PD | 04/03/2024 | 60 | UTTAM KUMAR DUTTA | 19.44 | 0 | 0
328 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003521/2023-2024 | 349/PD | 04/03/2024 | 60 | SUMIT KUMAR MITRA | 19.31 | 0 | 60
329 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division-under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003523/2023-2024 | 350/PD | 04/03/2024 | 60 | BHAGABANDAS KUMAR | 22.86 | 0 | 100
330 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003524/2023-2024 | 351/PD | 04/03/2024 | 60 | JAHANGIR ANSARI | 19.45 | 0 | 100
331 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003525/2023-2024 | 352/PD | 04/03/2024 | 60 | AMITAVA KUNDU | 19.47 | 0 | 100
332 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003528/2023-2024 | 354/PD | 04/03/2024 | 572 | KANJILAL AND CO. | 29.22 | 0 | 30
333 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-I ,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division,PHE Dte. | Assistant Engineer |  | ORD/003530/2023-2024 | 355/PD | 04/03/2024 | 515 | KM ENTERPRISES | 21.04 | 0 | 45
334 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003531/2023-2024 | 356/PD | 04/03/2024 | 60 | CHOUDHURY STONE CRUSHING | 25.14 | 0 | 85
335 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-XI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte.. | Assistant Engineer |  | ORD/003534/2023-2024 | 358/PD | 04/03/2024 | 420 | SINGHA ENTERPRISE | 21.01 | 0 | 0
336 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003535/2023-2024 | 359/PD | 04/03/2024 | 60 | SAZID HOSSEN ANSARI | 25.1 | 0 | 0
337 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Under Northern Sector W/S Scheme) | Assistant Engineer |  | ORD/003956/2023-2024 | 498/PD | 16/03/2024 | 60 | SEKH ABBAS | 25.08 | 0 | 0
338 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) | Assistant Engineer |  | ORD/003957/2023-2024 | 499/PD | 16/03/2024 | 60 | BANERJEE CONSTRUCTION | 20.41 | 0 | 100
339 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) | Assistant Engineer |  | ORD/003960/2023-2024 | 502/PD | 16/03/2024 | 60 | SUMIT KUMAR MITRA | 23.95 | 0 | 0
340 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector ) at Purulia-I Block(Zone-VII) For Kalidasdi Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/003987/2023-2024 | 492/PD | 16/03/2024 | 60 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 34.47 | 0 | 0
341 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Shyamdasdi Alias shyampur Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/003988/2023-2024 | 530/PD | 16/03/2024 | 60 | M/S ACHARJEE CONSTRUCTION | 33.22 | 0 | 0
342 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-II) For Bhalumara Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/004026/2023-2024 | 490/PD | 16/03/2024 | 165 | RAHIBUDDIN MONDAL | 23.46 | 0 | 50
343 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Puncha,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/004042/2023-2024 | 500/PD | 16/03/2024 | 480 | SOUMITRA KUMAR DAS | 28.26 | 0 | 55
344 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-XV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/004306/2023-2024 | 503/PD | 16/03/2024 | 60 | MANTAJ ANSARI | 25.17 | 0 | 0
345 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000003/2023-2024 | 1127/PD | 17/08/2023 | 0 | Resource Division | 19846.99 | 0 | 0
346 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000033/2024-2025 | 1342/PD | 24/07/2024 | 0 | Resource Division | 1191.18 | 0 | 0
347 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000037/2024-2025 | 1980/PD | 18/11/2024 | 0 | Resource Division | 9544.07 | 0 | 0
348 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000039/2024-2025 | 2253/PD | 19/12/2024 | 0 | Resource Division | 8838.63 | 0 | 0
349 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000028/2024-2025 | 941/PMD | 19/06/2024 | 365 | WEST BENGAL ENGINEERING CO | 568.2 | 0 | 0
350 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000029/2024-2025 | 942/PMD | 19/06/2024 | 365 | CONCORD ENGINEERING | 516.53 | 0 | 0
351 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000030/2024-2025 | 943/PMD | 19/06/2024 | 365 | ORIENTAL ENGINEERING CO. | 723.12 | 0 | 0
352 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000031/2024-2025 | 944/PMD | 19/06/2024 | 365 | MAHADEV ENTERPRISE | 561.07 | 0 | 0
353 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000032/2024-2025 | 945/PMD | 19/06/2024 | 365 | ASHOKE ADHIKARY | 39.78 | 0 | 0
354 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000082/2024-2025 | 1018/PMD | 25/06/2024 | 365 | TAPAN KUMAR DEY | 53.82 | 0 | 0
355 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000083/2024-2025 | 1019/PMD | 25/06/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 41.16 | 0 | 0
356 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Joypur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000084/2024-2025 | 1020/PMD | 25/06/2024 | 365 | A G ENTERPRISE | 34.82 | 0 | 0
357 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Kashipur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000085/2024-2025 | 1021/PMD | 25/06/2024 | 365 | DEBJYOTI BASU | 53.82 | 0 | 0
358 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000086/2024-2025 | 1022/PMD | 25/06/2024 | 365 | SANTU MITRA | 12.66 | 0 | 0
359 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Neturia Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000087/2024-2025 | 1023/PMD | 25/06/2024 | 365 | SEN BROTHERS | 6.33 | 0 | 0
360 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Para Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000088/2024-2025 | 1024/PMD | 25/06/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 56.98 | 0 | 0
361 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Puncha Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000089/2024-2025 | 1025/PMD | 25/06/2024 | 365 | SUBRATA DUTTA | 22.15 | 0 | 0
362 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000090/2024-2025 | 1048/PMD | 28/06/2024 | 365 | ASHOKE ADHIKARY | 25.32 | 0 | 0
363 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000091/2024-2025 | 1049/PMD | 28/06/2024 | 365 | SAIBAL SARKAR | 47.49 | 0 | 0
364 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1050/PMD | 28/06/2024 | 365 | BISHWANATH NANDI | 22.86 | 0 | 0
365 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000093/2024-2025 | 1051/PMD | 28/06/2024 | 365 | S. PATHAK & CO. | 15.82 | 0 | 0
366 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Santuri Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000094/2024-2025 | 1052/PMD | 28/06/2024 | 365 | NUPUR CHANDRA HALDER | 22.16 | 0 | 0
367 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Hura Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000328/2024-2025 | 1253/PMD | 22/08/2024 | 365 | KAMAKHYA ENTERPRISE | 45.76 | 0 | 0
368 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000461/2023-2024 | 466/PMD | 14/03/2024 | 365 | DEBJYOTI BASU | 59.65 | 0 | 0
369 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000462/2023-2024 | 467/PMD | 14/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 59.66 | 0 | 0
370 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000463/2023-2024 | 468/PMD | 14/03/2024 | 365 | DAS ENTERPRISE | 49.68 | 0 | 0
371 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000464/2023-2024 | 469/PMD | 14/03/2024 | 365 | SEN BROTHERS | 19.88 | 0 | 0
372 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000465/2023-2024 | 470/PMD | 14/03/2024 | 365 | NUPUR CHANDRA HALDER | 69.62 | 0 | 0
373 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000466/2023-2024 | 471/PMD | 14/03/2024 | 365 | SUNRISE ENGINEERING CORPORATION | 19.89 | 0 | 0
374 | Purulia Mechanical | Purulia Sadar Sub-Division | Internal illumination and outdoor lighting arrangement and other allied works for Augmentation of Balitora Water Supply Scheme under Purulia Mechanical Division. PHE. Dte. | Assistant Engineer |  | ORD/000466/2024-2025 | 1292/PMD | 30/08/2024 | 60 | PREMNATH MITRA | 7.83 | 0 | 2
375 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000467/2023-2024 | 493/PMD | 15/03/2024 | 365 | A G ENTERPRISE | 413.21 | 0 | 0
376 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | Assistant Engineer |  | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 100
377 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000469/2023-2024 | 495/PMD | 15/03/2024 | 365 | EASTERN INDIA SALES AND SERVICE | 413.27 | 0 | 0
378 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000470/2023-2024 | 496/PMD | 15/03/2024 | 365 | DEY ENTERPRISE, HOWRAH | 474.14 | 0 | 0
379 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000472/2023-2024 | 498/PMD | 15/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 103.28 | 0 | 0
380 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000473/2023-2024 | 499/PMD | 15/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 51.65 | 0 | 0
381 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000475/2023-2024 | 501/PMD | 15/03/2024 | 365 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 309.93 | 0 | 0
382 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000476/2023-2024 | 502/PMD | 15/03/2024 | 365 | AHALYA ENGINEERING WORKS | 206.45 | 0 | 0
383 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000478/2023-2024 | 504/PMD | 15/03/2024 | 365 | TAPAN KUMAR DEY | 257.9 | 0 | 0
384 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000479/2023-2024 | 505/PMD | 15/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 154.78 | 0 | 0
385 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000480/2023-2024 | 506/PMD | 15/03/2024 | 365 | PREMNATH MITRA | 206.89 | 0 | 0
386 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000483/2023-2024 | 472/PMD | 14/03/2024 | 365 | M/S A.D. CONCERN | 9.94 | 0 | 0
387 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000484/2023-2024 | 473/PMD | 14/03/2024 | 365 | SAIBAL SARKAR | 39.78 | 0 | 0
388 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000485/2023-2024 | 474/PMD | 14/03/2024 | 365 | SANTU MITRA | 9.94 | 0 | 0
389 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000487/2023-2024 | 475/PMD | 14/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 39.76 | 0 | 0
390 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000488/2023-2024 | 476/PMD | 14/03/2024 | 365 | M/S D. PALIT & CO. | 19.89 | 0 | 0
391 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000489/2023-2024 | 477/PMD | 14/03/2024 | 365 | PINTU DEY | 19.89 | 0 | 0
392 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 478/PMD | 14/03/2024 | 365 | COMBINE ENTERPRISES | 29.84 | 0 | 0
393 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000662/2024-2025 | 1668/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0
394 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000663/2024-2025 | 1669/PMD | 05/12/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.32 | 0 | 0
395 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000664/2024-2025 | 1670/PMD | 05/12/2024 | 365 | SEN BROTHERS | 2.77 | 0 | 0
396 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000665/2024-2025 | 1671/PMD | 05/12/2024 | 365 | SEN BROTHERS | 1.11 | 0 | 0
397 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000666/2024-2025 | 1672/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.88 | 0 | 0
398 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000667/2024-2025 | 1673/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 1.11 | 0 | 0
399 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Para and Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000668/2024-2025 | 1674/PMD | 05/12/2024 | 365 | M/S A.D. CONCERN | 2.77 | 0 | 0
400 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia I and Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000669/2024-2025 | 1675/PMD | 05/12/2024 | 365 | SANTU MITRA | 2.77 | 0 | 0
401 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000670/2024-2025 | 1676/PMD | 05/12/2024 | 365 | ASHOKE ADHIKARY | 2.22 | 0 | 0
402 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000671/2024-2025 | 1677/PMD | 05/12/2024 | 365 | M/S D. PALIT & CO. | 1.11 | 0 | 0
403 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000672/2024-2025 | 1678/PPMD | 05/12/2024 | 365 | PINTU DEY | 1.11 | 0 | 0
404 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000673/2024-2025 | 1679/PMD | 05/12/2024 | 365 | COMBINE ENTERPRISES | 1.66 | 0 | 0
405 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | Assistant Engineer |  | ORD/000114/2020-2021 | 1241/PD | 01/12/2020 | 45 | SUSANTA KR DUTTA | 42.97 | 14.59 | 0
406 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Beldi, Bhursa, Kumirkuli, Domepara, Goaladih & Jatratanr) Part-A | Assistant Engineer |  | ORD/000157/2020-2021 | 1410/PD | 29/12/2020 | 45 | BOSE CONSTRUCTION | 43.92 | 0 | 0
407 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi water supply scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional House Hold Tap connection (FHTC) under JAL SWAPNA Program (Habitation covered Beldi, Bursha Kalimati, Dome Para, Goaladih ...) Part-A. (Tender No.08/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000380/2021-2022 | 158/8443209 | 17/09/2021 | 0 | BOSE CONSTRUCTION | 10.57 | 0 | 0
408 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Tumba Jhalda, Gouradag & Jharidih) Part-B (Tender No. 191/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000815/2020-2021 | 378/84432 | 01/03/2021 | 0 | SUSANTA KR DUTTA | 28.44 | 0 | 0
409 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Beldi, Bhursha, Kumirkuli, Domepara, Goaladih Jatratar) Part-A (Tender No. 8/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000819/2020-2021 | 387/844341 | 08/03/2021 | 0 | BOSE CONSTRUCTION | 31.34 | 0 | 0
410 | Purulia Division | Purulia Sadar Sub-Division | Repairing & restoration of the damaged elevated watch reservoir ...under Beldi water supply scheme. (Tender No.08/EE/PD of 2022-23) (Ad-interim) | Assistant Engineer |  | VCH/000830/2022-2023 | 127/8443195 | 28/09/2022 | 0 | KOUSHIK CHATTERJEE | 5.5 | 0 | 0
411 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B (Tender No.191/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000969/2021-2022 | 301/8443105/1 | 18/02/2022 | 0 | SUSANTA KR DUTTA | 1.97 | 0 | 0
412 | Purulia Division | Purulia Sadar Sub-Division | Additional pipe line of 20mm HDPE (OD) for the work of FHTC of Beldi W/s Scheme at Arsha Block Providing of FHTC under Jal Swapna Programe. (Habitation Name: Tumba Jhalda Goradag) (Tender No.191/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000970/2021-2022 | 301/8443105/2 | 18/02/2022 | 0 | SUSANTA KR DUTTA | 2.88 | 0 | 0
413 | Purulia Division | Purulia Sadar Sub-Division | Extension of distribution pipeline Providing FHTC under Jal Sapna Programme of Beldi W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Tumba Jhalda, Gouradag, Jhariadih) (Tender No.878/EE/PD of 2021-22) | Assistant Engineer |  | VCH/001052/2021-2022 | 342/8443126/1 | 22/03/2022 | 0 | BOSE CONSTRUCTION | 5.26 | 0 | 0
414 | Purulia Division | Purulia Sadar Sub-Division | Additional estimate for retrofitting of Beldi Water supply scheme for FHTC in connection with Jal Swapna Project at Arsha Block. (Tender No.324/EE/PD of 2021-22) | Assistant Engineer |  | VCH/001060/2021-2022 | 342/8443126/2 | 22/03/2022 | 0 | BOSE CONSTRUCTION | 2.83 | 0 | 0
415 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Gourangdih, Manpur, Kanchanpur & Juradi) Part-B | Assistant Engineer |  | ORD/000116/2020-2021 | 1242/PD | 01/12/2020 | 45 | HIRAK KUMAR SAO | 16.01 | 0 | 0
416 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Kudagara & Bamandia) Part-A | Assistant Engineer |  | ORD/000158/2020-2021 | 1411/PD | 29/12/2020 | 45 | GOUTAM CHAKRABORTY | 47.17 | 21.19 | 0
417 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-K) | Assistant Engineer |  | ORD/000249/2020-2021 | 23/PSD | 13/01/2021 | 45 | SIDDHARTHA SANKAR SARKAR | 3.63 | 0 | 100
418 | Purulia Division | Purulia Sadar Sub-Division | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000365/2021-2022 | 150/PD | 24/01/2022 | 45 | KOUSHIK CHATTERJEE | 25.5 | 2.33 | 100
419 | Purulia Division | Purulia Sadar Sub-Division | Emergent Repairing of 100 mm dia Collecting line damaged due to flash flood in connection with Jal Jeevan Mission (JJM) under Kudagara W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001016/2022-2023 | 185/PD | 07/02/2023 | 15 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 3.7 | 3.66 | 100
420 | Purulia Division | Purulia Sadar Sub-Division | Emergency piling work along with sand filling at collecting line treanches for protection work against flash flood Khudagara W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001479/2023-2024 | 1790/PD | 08/12/2023 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 39.43 | 0 | 100
421 | Purulia Division | Purulia Sadar Sub-Division | FHTC water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gourangdi, Manpur, Kanchanpur & Juradi Mouza of Kudagara Piped W/s Scheme (Phase-2) (Tender No.422/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000408/2021-2022 | 142/844349/1 | 08/09/2021 | 0 | HIRAK KUMAR SAO | 3.03 | 0 | 0
422 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Khudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA program (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B (Tender No.195/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000409/2021-2022 | 142/844349/2 | 08/09/2021 | 0 | HIRAK KUMAR SAO | 1.83 | 0 | 0
423 | Purulia Division | Purulia Sadar Sub-Division | FHTC water tap connection ineach house hold from existing distribution system within scheme jurisdiction in Kudagara & Bamundiha Mouza of Khudagar Piped Water Supply Scheme with in Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-2) (Tender No. 408/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000423/2021-2022 | 137/84433/2 | 01/09/2021 | 0 | M/S CHAKRABORTY CONSTRUCTION | 4.28 | 0 | 0
424 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional house hold tap connection (FHTC) under Jal Swapna Programme under Purulia Division PHE Dte. (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B. (Tender No. 195/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000906/2020-2021 | 437/8443179 | 27/03/2021 | 0 | HIRAK KUMAR SAO | 11.08 | 0 | 0
425 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Kudagar & Bamundiha) Part-A (Tender No. 12/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000914/2020-2021 | 419/8443127 | 18/03/2021 | 0 | GOUTAM CHAKRABORTY | 28.55 | 0 | 0
426 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B (Mouza- Ghatkul, Gobindapur Alis , Amaidi, Hariraidi ALIS, Birbaldi, Kalipathar, Kharbana, Kulbana, Malancha, Shalchura, Taltly under Gunyarae G.P). (590 Nos.) | Assistant Engineer | Junior Engineer-3 | ORD/000242/2020-2021 | 63/PD | 15/01/2021 | 45 | KHITISH CHANDRA PATHAK | 29.98 | 67.12 | 100
427 | Purulia Division | Raghunathpur Sub-Division | Repairing of Pressure filtre,Plumbing work of toilet,Clearing of OHR Campus and other allied works under Bathanbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000317/2020-2021 | 113/RNP | 08/02/2021 | 15 | KHITISH CHANDRA PATHAK | 1.47 | 1.29 | 90
428 | Purulia Division | Raghunathpur Sub-Division | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000015/2021-2022 | BP-2021-22-43 | 19/07/2021 | 0 | DEBAKI RANJAN SARKAR | 27.12 | 0 | 0
429 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar gate, Barbed wire, and other allied work at Bathanbari Head Work Site under Bathanbari W/s Schemeunder Raghunathpur Sub-Division PHE Dte. (Total length of Boundary Wall 42.00 mtr.) (Tender No.235/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000174/2021-2022 | BP-2021-22-65 | 12/08/2021 | 0 | KHITISH CHANDRA PATHAK | 2.76 | 0 | 0
430 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-3 | VCH/001144/2021-2022 | BP-2021-22-300 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0
431 | Purulia Division | Raghunathpur Sub-Division | Additional work for FHTC Bathanbari Water supply Scheme [Ad- Interim payment] [Tender No- 935/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/001149/2021-2022 | BP-2021-22-298 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 5 | 0 | 0
432 | Purulia Division | Raghunathpur Sub-Division | Laying of distribution pipe line ( 90 & 75 mm dia HDPE pipe ) for Kargali and Jamua villege of Raghunathpur-II Development Block under Raghunathpur Sub-Divn, P.H.E. Dte. (In connection with Paray Samadhan) | Assistant Engineer | Junior Engineer-4 | ORD/000014/2021-2022 | 743/PD | 06/07/2021 | 30 | KHITISH CHANDRA PATHAK | 11.96 | 1.08 | 80
433 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (176 Nos.) | Assistant Engineer | Junior Engineer-4 | ORD/000241/2020-2021 | 62/PD | 15/01/2021 | 45 | SHYAMAL KUMAR DEY | 9.88 | 16.25 | 0
434 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) | Assistant Engineer | Junior Engineer-4 | ORD/000282/2020-2021 | 162/PD | 01/02/2021 | 45 | BASANTA KUMAR SINGHADEO | 52.62 | 38.32 | 0
435 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -IV(1016 Nos.) | Assistant Engineer | Junior Engineer-4 | ORD/000285/2020-2021 | 164/PD | 01/02/2021 | 45 | RABIN CHANDRA CHAIL | 45.51 | 45.46 | 0
436 | Purulia Division | Raghunathpur Sub-Division | Supplying, laying and aligning of HDPE pipe line and othar allied works at Kalabani Water Supply Scheme (Zone-II) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000636/2022-2023 | 1404/PD | 01/09/2022 | 45 | NANIGOPAL DEY | 19.42 | 0 | 0
437 | Purulia Division | Raghunathpur Sub-Division | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-I OHR site under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000649/2024-2025 | 468/RNP | 26/09/2024 | 20 | RABIN CHANDRA CHAIL | 0.95 | 0 | 100
438 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block. (Zone-I) (1591 Nos) (Tender No. 345/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000016/2021-2022 | BP-2021-22-40 | 19/07/2021 | 0 | KOUSHIK CHATTERJEE | 4.69 | 0 | 0
439 | Purulia Division | Raghunathpur Sub-Division | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- II) (Tender No. 386/20-21 of EE/PD) | Assistant Engineer | Junior Engineer-4 | VCH/000029/2021-2022 | BP-2021-22-45 | 19/07/2021 | 0 | BASANTA KUMAR SINGHADEO | 4.04 | 0 | 0
440 | Purulia Division | Raghunathpur Sub-Division | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- I) (Tender No. 387/20-21 of EE/PD) | Assistant Engineer | Junior Engineer-4 | VCH/000030/2021-2022 | BP-2021-22-46 | 19/07/2021 | 0 | BASANTA KUMAR SINGHADEO | 4.32 | 0 | 0
441 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- III (970 Nos.) (Tender No:- 336/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000214/2021-2022 | BP-2021-22-89 | 23/08/2021 | 0 | PRIYATOSH MUKHERJEE | 27.81 | 0 | 0
442 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- IV (1016 Nos.) (Tender No:- 313/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000217/2021-2022 | BP-2021-22-90 | 23/08/2021 | 0 | RABIN CHANDRA CHAIL | 9.69 | 0 | 0
443 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) (Tender No.384/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000325/2021-2022 | BP-2021-22-102 | 13/09/2021 | 0 | BASANTA KUMAR SINGHADEO | 34.04 | 0 | 0
444 | Purulia Division | Raghunathpur Sub-Division | Temporary water supply arrangement through extension of Distribution Main by supplying & laying 63mm dia HDPE pipe line from Deshra More to Deshra Village (loop line) and to Bathandih Bero Bandh with allied works at Zone-III (Deshra OHR) under Kalabani W/s Scheme (Zone-III) of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 388/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000382/2021-2022 | BP-2021-22-124 | 11/10/2021 | 0 | BASANTA KUMAR SINGHADEO | 2.96 | 0 | 0
445 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Zone-IV (1016 Nos.) (Tender No. 313/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000808/2020-2021 | 10/844326/1 | 12/04/2021 | 0 | RABIN CHANDRA CHAIL | 7.95 | 0 | 0
446 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-IV) (Tender No.856/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000808/2021-2022 | BP-2021-22-233 | 03/02/2022 | 0 | RABIN CHANDRA CHAIL | 3.76 | 0 | 0
447 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone - I (1591 Nos.) (Tender No.345/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000868/2021-2022 | BP-2021-22-244 | 16/02/2022 | 0 | KOUSHIK CHATTERJEE | 4.73 | 0 | 0
448 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) (Tender No.898/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000966/2021-2022 | BP-2021-22-268 | 28/02/2022 | 0 | CHAIL CONSTRUCTION | 6.2 | 0 | 0
449 | Purulia Division | Raghunathpur Sub-Division | Additional work for FHTC including other allied works of Kalabani W/s Scheme. (Tender No.887/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/001012/2021-2022 | BP-2021-22-257 | 25/02/2022 | 0 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0
450 | Purulia Division | Raghunathpur Sub-Division | Additional work for Functional Household tap Connection (FHTC) including other allied works of kalaboni W/S Scheme at Hura block of Raghunathpur Sub- Division Zone-III (Tender No- 942/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-4 | VCH/001189/2021-2022 | BP-2021-22-316 | 22/03/2022 | 0 | PRIYATOSH MUKHERJEE | 8.11 | 0 | 0
451 | Purulia Division | Raghunathpur Sub-Division | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-4 | VCH/001190/2021-2022 | BP-2021-22-318 | 22/03/2022 | 0 | RAHIBUDDIN MONDAL | 12.46 | 0 | 0
452 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Regarding laying of water supply pipe line along road side and road crossing on Begunkodar-Arsha Road in respect of Augumentation of Jhalda (Rural Part) water supply scheme JJM in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00063/2022-2023 | BP-2022-23-511 | 22/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 12.93 | 0 | 0
453 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0
454 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Route Survey & Drawing Preparation for uncovered areas under Jhalda-II Block under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000002/2023-2024 | 525/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 3.21 | 3.16 | 100
455 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation under Zone-1A command area of Jhalda W/S Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-II, Zone-1A, Part-I, GP-Begunkodar, Habitation-Murguma, Narayanpur Alias Lakhipur) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000008/2023-2024 | 536/PD | 12/04/2023 | 45 | BOSE CONSTRUCTION | 14.61 | 11.71 | 100
456 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Augementation of Jhalda Water Supply Scheme (Rural Part) (Zone-II, Part-IV) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Habitation-Supurdih and Brindabanpur, Gp-Begunkodar) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2022-2023 | 649/PD | 22/04/2022 | 45 | BHAGABANDAS KUMAR | 21.02 | 18.85 | 100
457 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing , renovation & Construction Damaged (portion) of Boundary Wall of Masina Pump House Campus Of Jhalda W/S Scheme Under Purulia Division ,PHE DTE... | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000163/2023-2024 | 934/PD | 19/07/2023 | 30 | CHATTERJEE CONSTRUCTION | 9.37 | 0 | 80
458 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000301/2022-2023 | 827/PD | 17/05/2022 | 45 | M/S S & P CONSTRUCTION | 153.83 | 53.13 | 85
459 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000345/2021-2022 | 68/PD | 17/01/2022 | 45 | BHAGABANDAS KUMAR | 35.23 | 13.84 | 85
460 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of DI distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) in Mouza-Jaharhatu, Habitation-Gurrabera under command area (Zone-IB) of Augementation of Jhalda Water Supply Scheme (Rural Part) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000402/2021-2022 | 254/PD | 10/02/2022 | 30 | KANAILAL PAL | 10.08 | 5.45 | 0
461 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing, renovation & restoration of Store room including at Masina Pump House site of Jhalda W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000442/2021-2022 | 92/PSD | 14/03/2022 | 30 | CHATTERJEE CONSTRUCTION | 3.58 | 3.33 | 95
462 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000444/2021-2022 | 408/PD | 15/03/2022 | 60 | ZAKIR HOSSIN MONDAL | 90.73 | 19.64 | 98
463 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Emergent Dismantling of R.C.C. Elevator Reservoir, Capacity 681 Cum (Intze Type), Staging height 20 meter at Jhalda Municipality OHR site including By pass arrangement for direct supply due to Dismantling of Jhalda OHR with allied works of Jhalda W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000508/2021-2022 | 632(1-2)/PD | 24/11/2021 | 60 | ANUP KUMAR SAHA | 24.06 | 0 | 0
464 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Withdrawing & relaying of AC pipe line from Birsamor to Sramik Kalyan Kendra, Namopara to Kumarkuli Road and installation of sluice valve and Repairing of valve chamber at Jhalda under Jhalda Municipality W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000615/2022-2023 | 512/PSD | 12/08/2022 | 30 | SK MANIR | 2 | 1.92 | 0
465 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in Goverment Office,Health Centre, ICDS Centre,SSK,MSK, Primary School ,High school at Jhalda Municipalty Under Jhalda Municipalty Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000619/2022-2023 | 516/PSD | 12/08/2022 | 323 | SEKH IRFAN | 0.92 | 0 | 100
466 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000868/2022-2023 | 1810/PD | 06/12/2022 | 274 | M/S S & P CONSTRUCTION | 28.57 | 18.65 | 80
467 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001230/2022-2023 | 252/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.65 | 0.65 | 100
468 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001232/2022-2023 | 253/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.43 | 0 | 100
469 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001234/2022-2023 | 255/PD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.63 | 0.44 | 70
470 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001235/2022-2023 | 254/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.42 | 0 | 0
471 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000009/2021-2022 | 1564/PD | 16/12/2021 | 0 | Resource Division | 70.09 | 0 | 0
472 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000016/2021-2022 | 393/PD | 11/03/2022 | 0 | Resource Division | 3.18 | 0 | 0
473 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000041/2022-2023 | 240/PD | 20/02/2023 | 0 | Resource Division | 83.68 | 0 | 0
474 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) (Tender No.947/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000143/2022-2023 | BP-2022-23-26 | 07/04/2022 | 0 | BHAGABANDAS KUMAR | 18.69 | 0 | 0
475 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Jhalda Municipality W/S Scheme block-Jhalda-I) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 360/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000940/2022-2023 | BP-2022-23-105 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.97 | 0 | 0
476 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, part- I) of Jhalda-II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I Begunkodar Habitation G.P. Begunkodar) (Tender No- 34/2022-23 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000948/2022-2023 | BP-2022-23-112 | 16/07/2022 | 0 | M/S S & P CONSTRUCTION | 49.46 | 0 | 0
477 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) (Tender No- 149/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001059/2022-2023 | BP-2022-23-405 | 20/10/2022 | 0 | ZAKIR HOSSIN MONDAL | 67.77 | 0 | 0
478 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) (Tender No.34/SE/PMU of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001060/2022-2023 | BP-2022-23-408 | 20/10/2022 | 0 | M/S S & P CONSTRUCTION | 35.71 | 0 | 0
479 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with Functional household Connection of different existing PWSS Jhalda Aug. W/S Scheme (Rural Part) Block- Jhalda-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001165/2021-2022 | BP-2021-22-322 | 22/03/2022 | 0 | M/S TECH VISION | 4.69 | 0 | 0
480 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation at Begunkodar O.H.R near H.S School, Po begunkadar Ps Kotshila. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00849/2023-2024 | BILL/00849/2023 | 01/03/2024 | 0 | WBSEDCL PURULIA | 0.41 | 0 | 0
481 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2021-2022 | 113/PMD | 28/02/2022 | 30 | ANUP KUMAR SAHA | 20.47 | 8.21 | 100
482 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of essential item on the intake Burge of Jhalda Augmentation W/S Scheme under P.M.D., P.H.E.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000183/2023-2024 | 1173/PMD | 03/11/2023 | 425 | ANUP KUMAR SAHA | 6.21 | 0 | 50
483 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing external illumination arrangement at WTP area of Jhalda Aug WTP under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000230/2023-2024 | 1206/PMD | 03/11/2023 | 60 | ANUP KUMAR SAHA | 2.74 | 0 | 100
484 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, MCC panel and with necessary substitutes and allied works at the intake of the Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000254/2022-2023 | 44/PMD | 19/01/2023 | 714 | ANUP KR. SAHA | 43.88 | 37.65 | 70
485 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of centrifugal pumping machineries, MCC panel, Flowmeter With necessary substitutes and allied works at WTP area of Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000270/2022-2023 | 45/PMD | 19/01/2023 | 60 | SUNRISE ENGINEERING CORPORATION | 49.44 | 0 | 60
486 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at OHR site for Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000291/2022-2023 | 83/PMD | 01/02/2023 | 670 | ANUP KR. SAHA | 21.57 | 11.02 | 100
487 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000009/2023-2024 | 618/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
488 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF JHALDA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 343 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000084/2022-2023 | C042211566405 | 08/04/2022 | 0 | ANUP KR. SAHA | 12.25 | 0 | 0
489 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian railway Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | BILL/00127/2022-2023 | BP-2022-23-555 | 18/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.4 | 0 | 0
490 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Xerox bill office purpose. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | BILL/00433/2023-2024 | BP-2023-24-301 | 14/07/2023 | 0 | DUTTA XEROX CENTRE | 0.45 | 0 | 0
491 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
492 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work by providing functional Household Tap Connection (FHTC) and other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000173/2022-2023 | 790/PD | 05/05/2022 | 45 | SANTANU BANERJEE | 24.47 | 0 | 0
493 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Resinking of 2(Two) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (TW NO-2 & 6) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000359/2021-2022 | 144/PD | 24/01/2022 | 30 | ASHOK KUMAR CHATTERJEE | 11.43 | 5.99 | 0
494 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sinking of 8 (Eight) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi Aug. W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000366/2021-2022 | 151/PD | 24/01/2022 | 30 | ASHOK KUMAR CHATTERJEE | 41.88 | 22.46 | 0
495 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir at Zone-I & II of Capcaity 350Cum & 150 Cum and other allied works under Sutaboi W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000367/2021-2022 | 153/PD | 25/01/2022 | 70 | ASHOK KUMAR CHATTERJEE | 10.24 | 10.19 | 0
496 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Pump House at Head work site of Sutaboi W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000382/2021-2022 | 204/PD | 01/02/2022 | 120 | SUJIT CHAKRABORTY | 5.06 | 4.98 | 100
497 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000403/2021-2022 | 260/PD | 11/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 88.48 | 0 | 100
498 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Sutaboi river site under Sutaboi w/s Scheme under Raghunathpur Sub-Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000438/2021-2022 | 387/PD | 11/03/2022 | 100 | ASHOK KUMAR CHATTERJEE | 13.89 | 11.26 | 0
499 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme under zone-I & zone-ii at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000635/2022-2023 | 1403/PD | 01/09/2022 | 1034 | ASHOK KUMAR CHATTERJEE | 85.35 | 40.98 | 70
500 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0 | 100
501 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | RTOR000004/2022-2023 | 964/PD | 21/06/2022 | 0 | Resource Division | 33.36 | 0 | 0
502 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Re sinking of 02 (Two) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi ghat) alongwith laying of 100 mm dia GI collecting line with all allied works under Sutaboi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte. (TW No. 2& 6) (Tender No- 956/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000941/2022-2023 | BP-2022-23-104 | 16/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.8 | 0 | 0
503 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sutaboi Aug. Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 952/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000950/2022-2023 | BP-2022-23-99 | 16/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 19.18 | 0 | 0
504 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of switch room cum chlorine room at Head work site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 967/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000963/2022-2023 | BP-2022-23-126 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.23 | 0 | 0
505 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of switch room cum chlorine room at Zone-I OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 966/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000964/2022-2023 | BP-2022-23-125 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.22 | 0 | 0
506 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work of providing FHTC and other allied works of Sutaboi W/S Scheme at Kashipur under Raghunathpur Sub- Division, PHE Dte. (Tender No:- 54/EE/PD of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000965/2022-2023 | BP-2022-23-123 | 19/07/2022 | 0 | SANTANU BANERJEE | 24.43 | 0 | 0
507 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of switch room cum chlorine room at Zone-II OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 857/21-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000974/2022-2023 | BP-2022-23-144 | 20/07/2022 | 0 | M/S SAYAK BHATTACHARYA | 4.19 | 0 | 0
508 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 1 Site) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000006/2022-2023 | 309/PMD | 11/05/2022 | 30 | ANUP KR. SAHA | 20.47 | 19.57 | 96
509 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 2 Site ) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000007/2022-2023 | 310/PMD | 11/05/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 19.57 | 96
510 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery & installation of flow meter and with others allied works for Augmentation Sutaboi w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. (w.e.f 01.11.23 to 31.12.23) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000019/2023-2024 | 390/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 4.85 | 0 | 100
511 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal lighting arrangement at Sutaboi pump house, Chlorination room at OHR site 1&2 with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000020/2023-2024 | 391/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 2.74 | 0 | 100
512 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied works at OHR-1 for Augmentation of sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000021/2023-2024 | 392/PMD | 06/04/2023 | 60 | MOUSUMI BENERJEE | 5.88 | 0 | 100
513 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Riverbed illumination arrangement with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000022/2023-2024 | 393/PMD | 06/04/2023 | 60 | MAHIPAL MAJHI | 5.95 | 0 | 100
514 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machinery with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000046/2024-2025 | 965/PMD | 20/06/2024 | 469 | NUPUR CHANDRA HALDER | 20.18 | 0 | 20
515 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied works at OHR-2 under sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000131/2023-2024 | 869/PMD | 21/07/2023 | 60 | M/S UJJAL DIESEL SERVICE | 5.81 | 0 | 100
516 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0
517 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at Head work site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000460/2023-2024 | 440/PMD | 11/03/2024 | 570 | M/S D.G.B.ENTERPRISE | 25 | 0 | 97
518 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation submersible pumping machineries at new deep tube well, MCC panel and laying of cable line, with others allied works for augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000477/2022-2023 | 324/PMD | 22/03/2023 | 60 | COMBINE ENTERPRISES | 71.28 | 38.44 | 100
519 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of MCC panel at Sutaboi Water Supply Scheme under Purulia Mechanical Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000486/2023-2024 | 193/PMD | 16/02/2024 | 15 | SUJIT MUKHERJEE | 0.64 | 0 | 100
520 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of 150KVA oil cooled voltage stabilizer and supply cable and making cable trench with allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000487/2022-2023 | 353/PMD | 27/03/2023 | 60 | SWAPAN ENTERPRISE | 18.17 | 0 | 100
521 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of Booster pumping machinery for gaseous chlorination system at OHR-I site of Sutaboi W/S scheme under PMD P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000494/2023-2024 | 218/PMD | 20/02/2024 | 15 | S. PATHAK & CO. | 0.96 | 0 | 100
522 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal Pump set with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000582/2024-2025 | 1473/PMD | 21/10/2024 | 120 | COMBINE ENTERPRISES | 5.61 | 0 | 0
523 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION AT OHR 2 SITE OF SUTABAI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000327/2022-2023 | BP-2022-23-33 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
524 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR OHR SITE AT SUTABOI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000328/2022-2023 | BP-2022-23-32 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
525 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying laying fitting fixing of HDPE pipe from Raherdihi to Mohan Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000176/2023-2024 | 992/PD | 26/07/2023 | 60 | BISWAJIT MAJI | 10.19 | 10.14 | 100
526 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Making interconnection between existing Rising main to CWR , CWR to distribution line towards Beniasole & Gosaindanga for direct pumping under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000177/2023-2024 | 993/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 2.74 | 2.73 | 100
527 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Sinking of 2 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeswar river (Narayangarh Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000178/2023-2024 | 994/PD | 26/07/2023 | 45 | CHAIL CONSTRUCTION | 12.17 | 7.1 | 100
528 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000179/2023-2024 | 995/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 6.21 | 0 | 100
529 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of distribution pipe line ( 90 mm & 75 mm dia HDPE pipe ) towards Narayangarh Mahato Para & Majhee Para in connection with FHTC under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000180/2023-2024 | 996/PD | 26/07/2023 | 60 | TUMPA GORAIN | 3.61 | 0 | 100
530 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line for extension of distribution line in different lines of Uppar Beniasole, Mission Para and Panchudanga under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000198/2021-2022 | 579/RNP | 27/09/2021 | 45 | MS GORAIN CONCERN | 4.84 | 4.82 | 0
531 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000291/2020-2021 | 180/PD | 02/02/2021 | 45 | SADHAN GORAIN | 131.09 | 0 | 100
532 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000337/2021-2022 | 53/PD | 13/01/2022 | 45 | RABIN CHANDRA CHAIL | 63.62 | 0 | 100
533 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Arra OHR to Gosaidanga under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000341/2021-2022 | 64/PD | 17/01/2022 | 45 | RABIN CHANDRA CHAIL | 25.25 | 1.46 | 95
534 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 50m3 including ventury etc. complete at Arrah Zone-I OHR Campus,under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000342/2021-2022 | 65/PD | 17/01/2022 | 100 | RABIN CHANDRA CHAIL | 6.81 | 5.89 | 95
535 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-1) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000342/2023-2024 | 90/CAMP/RNP | 26/04/2023 | 7 | RABIN CHANDRA CHAIL | 0.93 | 0.93 | 100
536 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000343/2023-2024 | 91/CAMP/RNP | 26/04/2023 | 7 | RABIN CHANDRA CHAIL | 0.93 | 0.93 | 100
537 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-I) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Arrah. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000368/2021-2022 | 154/PD | 25/01/2022 | 45 | MS GORAIN CONCERN | 14.02 | 14.01 | 100
538 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000369/2021-2022 | 155/PD | 25/01/2022 | 45 | SUBHAS CHANDRA MAHATO | 7.15 | 4.13 | 65
539 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution pipe line ( 90 mm dia HDPE pipe ) from Arrah Pump House to Narayangarh of Kashipur Development Block under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000398/2022-2023 | 356/RNP | 01/06/2022 | 30 | SUBHAS CHANDRA MAHATO | 1.33 | 0.98 | 0
540 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Guard Room cum store at Pump House Campus under Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000407/2021-2022 | 328/PD | 28/02/2022 | 100 | SUBHAS CHANDRA MAHATO | 6.23 | 6.15 | 100
541 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 700 cum at Arrah under Arrah W/S Scheme(Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000408/2021-2022 | 329/PD | 28/02/2022 | 60 | RABIN CHANDRA CHAIL | 7.41 | 7.35 | 0
542 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying laying fitting fixing of HDPE pipe & FHTC Connection Near Amlatora more to Amlatora last matha & to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000679/2023-2024 | 1362/PD | 13/09/2023 | 45 | IKBAL CONSTRUCTION | 8.95 | 0 | 50
543 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 100 cum at Manpura under Arrah W/S Scheme(Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000865/2022-2023 | 1818/PD | 06/12/2022 | 30 | SANDIP KUMAR DUBEY | 4.46 | 3.08 | 100
544 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-I) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000891/2022-2023 | 1878/PD | 14/12/2022 | 45 | CHAIL CONSTRUCTION | 5.04 | 4.48 | 100
545 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-II) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000892/2022-2023 | 1879/PD | 14/12/2022 | 90 | SANDIP KUMAR DUBEY | 5.04 | 4.76 | 100
546 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-III) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000893/2022-2023 | 1880/PD | 14/12/2022 | 30 | CHANCHAL MISHRA | 5.04 | 0 | 100
547 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 120 cum at Gagnabad under Arrah W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000894/2022-2023 | 1881/PD | 14/12/2022 | 30 | TUMPA GORAIN | 4.19 | 2.99 | 100
548 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of 2 Nos. 3 mtr dia Intake well at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000918/2022-2023 | 1927/PD | 22/12/2022 | 314 | RABIN CHANDRA CHAIL | 19.19 | 9.79 | 100
549 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of distribution pipe line ( 75 mm dia HDPE pipe ) towards Narayangarh Bauri Para under Arrah W/S Scheme of Raghunathpur Sub-Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000930/2022-2023 | 711/RNP | 23/12/2022 | 20 | SUBHAS CHANDRA MAHATO | 0.97 | 0.97 | 0
550 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and necessary 65 mm dia collecting line at Narayanpur river side under Arrah W/S Scheme under Raghunathpur Sub Division,P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000978/2022-2023 | 83/PD | 17/01/2023 | 30 | SUBHAS CHANDRA MAHATO | 2.21 | 1.66 | 0
551 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0 | 100
552 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) including other allied works of Arrah Water Supply Scheme (Zone - I) at Raghunathpur - I Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001490/2023-2024 | 1801/PD | 08/12/2023 | 60 | CHAIL CONSTRUCTION | 7.03 | 0 | 100
553 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing House Hold Tap Connection (FHTC) at Narayangarh Majhipara and repairing and renovation of Pump House Campus under ARRAH W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001863/2023-2024 | 89/PD | 15/01/2024 | 60 | SUBHAS CHANDRA MAHATO | 5.26 | 0 | 100
554 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of distribution pipe line (90 mm dia HDPE pipe) From Milon Sporting Club to K. Mangal Rao House under Arrah W/S Scheme (Zone-I) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001894/2023-2024 | 22/RNP | 15/01/2024 | 7 | RABIN CHANDRA CHAIL | 0.96 | 0 | 100
555 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | RTOR000002/2023-2024 | 800/PD | 16/06/2023 | 0 | Resource Division | 17.7 | 0 | 0
556 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | RTOR000008/2022-2023 | 961/PD | 20/06/2022 | 0 | Resource Division | 37.97 | 0 | 0
557 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 927/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000897/2022-2023 | BP-2022-23-81 | 01/07/2022 | 0 | RABIN CHANDRA CHAIL | 22.53 | 0 | 0
558 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.927/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001068/2022-2023 | BP-2022-23-416 | 07/11/2022 | 0 | RABIN CHANDRA CHAIL | 3.94 | 0 | 0
559 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001111/2021-2022 | BP-2021-22-371 | 29/03/2022 | 0 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0
560 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. (Tender No.932/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001123/2021-2022 | BP-2021-22-378 | 28/03/2022 | 0 | SUBHAS CHANDRA MAHATO | 2.98 | 0 | 0
561 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for OHR 1 at Augmentation of Arrha Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00026/2022-2023 | BP-22-23-83 | 24/02/2023 | 0 | WBSEDCL PURULIA | 1.16 | 0 | 0
562 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for OHR 2(Manpura) under Augmentation of Arrha Water Supply Scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00027/2022-2023 | BP-23-24-271 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.31 | 0 | 0
563 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000063/2024-2025 | 992/PMD | 21/06/2024 | 60 | M/S R.K. ENTERPRISE | 4.6 | 0 | 100
564 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Arrah Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000069/2021-2022 | 114/PMD | 28/02/2022 | 30 | TAPAN KUMAR DEY | 20.47 | 11.71 | 100
565 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Augmentation of existing old LBSF unit by the new one VCB (one incoming two outgoing) at Arrah W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000119/2023-2024 | 800/PMD | 12/07/2023 | 782 | COMBINE ENTERPRISES | 29.23 | 0 | 81
566 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Internal lighting and external lighting for Arrah w/s scheme(Zone-1and Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000123/2023-2024 | 819/PMD | 14/07/2023 | 262 | M/S A.D. CONCERN | 5.9 | 0 | 100
567 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting fixing of ST pole and laying of cable line for lighting arrangement at(Z-I, Z-II and pump house) with other allied works under Arrah Water Supply Scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000216/2023-2024 | 1202/PMD | 03/11/2023 | 395 | TAPAN KUMAR DEY | 6.6 | 0 | 70
568 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Submersible pumping machineries for Direct pumping with other allied works for Augmentation at arrah w/s (zone-l) scheme under PMD, PHE, Dte. in the District of Puurlia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000298/2022-2023 | 89/PMD | 02/02/2023 | 60 | SAMAN KUMAR MAHATO | 14.03 | 9.72 | 100
569 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell for Augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000369/2022-2023 | 199/PMD | 28/02/2023 | 954 | JAL PRAVAHIKA PVT. LTD | 22.65 | 0 | 75
570 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with MCC panel, Flow meter and other allied works for Augmentation at Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000370/2022-2023 | 200/PMD | 28/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 71.89 | 12.98 | 100
571 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-1for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000383/2022-2023 | 214/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.62 | 12.91 | 100
572 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-2 for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000384/2022-2023 | 215/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 12.88 | 80
573 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer at Arrah OHR site(Z-I) for Augmentation of Arrah water supply scheme under PMD PHE Dte. in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000390/2023-2024 | 375/PMD | 04/03/2024 | 60 | BISHWANATH NANDI | 7.09 | 0 | 100
574 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF ARRAH WATER SUPPLY SCHEME UNDER KASHIPUR BLOCK (TR.NO 373 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000095/2022-2023 | C042228557261 | 13/04/2022 | 0 | TAPAN KUMAR DEY | 8.76 | 0 | 0
575 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Office purpose computer bill payment. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00431/2023-2024 | BP-2023-24-300 | 14/07/2023 | 0 | SRI KRISHNA COMPUTER | 0.95 | 0 | 0
576 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00706/2024-2025 | BP-2024-25-356 | 11/09/2024 | 0 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0
577 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000003/2022-2023 | 537/PD | 01/04/2022 | 270 | JAYANTA KUMAR MONDAL | 66.71 | 17.38 | 100
578 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Puncha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000055/2023-2024 | 662/PD | 17/05/2023 | 100 | ASHOKE ADHIKARY | 14.24 | 0 | 60
579 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000097/2022-2023 | 643/PD | 22/04/2022 | 1047 | SWAPAN MANDAL | 79.55 | 18.32 | 100
580 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of gap portion of Distribution pipeline at bridge portion Between Bahadurpur to puncha Mouzas for puncha W/S Scheme under purulia sadar Sub-Division under purulia division. PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000172/2023-2024 | 890/PD | 04/07/2023 | 30 | J.S. CONSTRUCTION | 10.39 | 0 | 100
581 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part -A) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000233/2022-2023 | 805/PD | 10/05/2022 | 1164 | SWAPAN MANDAL | 107.71 | 0 | 100
582 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000365/2021-2022 | 150/PD | 24/01/2022 | 45 | KOUSHIK CHATTERJEE | 25.5 | 0 | 100
583 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Pandui) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000396/2021-2022 | 235/PD | 09/02/2022 | 60 | SUNRISE ENGINEERING CORPORATION | 52.23 | 0 | 0
584 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000397/2021-2022 | 236/PS | 09/02/2022 | 1217 | SWAPAN MANDAL | 65.64 | 0 | 90
585 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Laulara) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000406/2022-2023 | 935/PD | 16/06/2022 | 45 | MS D.PALIT AND CO. | 112.05 | 51.99 | 85
586 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 180mm HDPE pipe with other allied works at Puncha Mouza to provide FHTC for Puncha W/S scheme under Purulia Sadar sub Division under Purulia Division ,PHE. Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000605/2022-2023 | 503/PSD | 12/08/2022 | 30 | JAYANTA KUMAR MONDAL | 4.48 | 4.25 | 100
587 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of balance distribution pipeline including other allied works for Puncha W/S scheme under Purulia Sadar Sub Division under Purulia Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000607/2022-2023 | 505/PSD | 12/08/2022 | 30 | JAYANTA KUMAR MONDAL | 4.31 | 4.25 | 100
588 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation & Supplying & laying of HDPE pipe through CWR for Distribution System of Puncha W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Tatari) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000784/2022-2023 | 1631/PD | 03/11/2022 | 1169 | SOUVIK MANDAL | 53.02 | 24.73 | 80
589 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Boundary wall at Bahadurpur OHR Site under Puncha W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000830/2022-2023 | 1722/PD | 22/11/2022 | 60 | RAHIBUDDIN MONDAL | 22.83 | 22.79 | 25
590 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of parallel line under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Laulara Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001013/2022-2023 | 180/PD | 07/02/2023 | 45 | MS D.PALIT AND CO. | 25.24 | 0 | 100
591 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of parallel distribution pipeline for providing FHTC at Tatari Mouza of Puncha Water Supply Scheme ounder Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001088/2022-2023 | 356/PD | 14/03/2023 | 30 | SOUVIK MANDAL | 3.67 | 0 | 100
592 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000011/2021-2022 | 164/PD | 27/01/2022 | 0 | Resource Division | 316.76 | 0 | 0
593 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000020/2021-2022 | 398/PD | 11/03/2022 | 0 | Resource Division | 30.45 | 0 | 0
594 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 4 nos 200 mm dia riverbed tube wells horizontal of kansai along with laying of 100mm dia GI connecting line with all allied works of Puncha W/S Scheme. (Tender No- 01/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000177/2022-2023 | BP-2022-23-49 | 19/05/2022 | 0 | KOUSHIK CHATTERJEE | 9.58 | 0 | 0
595 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No-20/SE/PMU of 21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000181/2022-2023 | BP-2022-23-52 | 17/05/2022 | 0 | JAYANTA KUMAR MONDAL | 105.31 | 0 | 0
596 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 250mm dia DI (K9) pipe rising main from riverside pump house site to OHR site under Puncha W/s Scheme (T/N-940/21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000242/2022-2023 |  | 05/07/2022 | 0 | SWAPAN MANDAL | 11.08 | 0 | 0
597 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 250 mm dia Di K9 pipe as rising main from riverside pump house site to OHR site under Puncha W/s Scheme of Purulia Sadar Sub- Division, under Purulia Division PHE Dte. (Tender No- 940/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000890/2022-2023 | BP-2022-23-75 | 01/07/2022 | 0 | SWAPAN MANDAL | 11.08 | 0 | 0
598 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Regarding laying of water supply pipe line aling road side and road croosing on Hura-Puncha Road from 19.00 Kmp to 21.00 Kmp in respect of Augmentation of Purulia water supply scheme (Dhadki more towards Puncha Girls High School) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000891/2022-2023 | BP-2022-23-430 | 24/11/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 32.27 | 0 | 0
599 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha OHR site of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 23/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000918/2022-2023 | BP-2022-23-116 | 16/07/2022 | 0 | SOUVIK MANDAL | 7.03 | 0 | 0
600 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha river site pump house of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 29/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000919/2022-2023 | BP-2022-23-121 | 16/07/2022 | 0 | KM ENTERPRISES | 7.01 | 0 | 0
601 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line from Bahadurpur CWR to Laulara mouza under command area of Puncha W/S Scheme (Tender No- 33/2022-23 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000957/2022-2023 | BP-2022-23-132 | 19/07/2022 | 0 | SWAPAN MANDAL | 85.91 | 0 | 0
602 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) (Tender No- 985/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001033/2022-2023 | BP-2022-23-382 | 19/10/2022 | 0 | SWAPAN MANDAL | 30.29 | 0 | 0
603 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part -A) (Tender No- 33/2022-23 of SE/PMU) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001046/2022-2023 | BP-2022-23-387 | 19/10/2022 | 0 | SWAPAN MANDAL | 16.59 | 0 | 0
604 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) (Tender No- 141/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001047/2022-2023 | BP-2022-23-388 | 19/10/2022 | 0 | SWAPAN MANDAL | 56.04 | 0 | 0
605 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. (Tender No- 27/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001058/2022-2023 | BP-2022-23-406 | 20/10/2022 | 0 | JAYANTA KUMAR MONDAL | 29.19 | 0 | 0
606 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Tender No- 20/2021-22 of SE/PMU/WBPWSP(P) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001220/2021-2022 | BP-2021-22-335 | 23/03/2022 | 0 | JAYANTA KUMAR MONDAL | 116.68 | 0 | 0
607 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Puncha W/S Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00251/2023-2024 | BP-2023-24-155 | 14/09/2023 | 0 | WBSEDCL PURULIA | 2.8 | 0 | 0
608 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Puncha. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00487/2023-2024 | BP-23-24-247 | 28/12/2023 | 0 | WBSEDCL PURULIA | 11.46 | 0 | 0
609 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000047/2023-2024 | 516/PMD | 05/05/2023 | 981 | EASTERN INDIA SALES AND SERVICE | 65.68 | 0 | 36
610 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000048/2023-2024 | 517/PMD | 05/05/2023 | 644 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 50.41 | 0 | 80
611 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Augmentation of Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000130/2023-2024 | 868/PMD | 21/07/2023 | 60 | SOUVIK MANDAL | 2.83 | 0 | 100
612 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing and installation of HOT Crane, Electro magnetic Flow meter and other allied woks for Augmentation of Puncha Water Supply Scheme (River Site) under purilia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000206/2023-2024 | 1196/PMD | 03/11/2023 | 180 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 10.26 | 0 | 80
613 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000438/2022-2023 | 257/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 3.01 | 0 | 90
614 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Puncha w/s scheme(OHR Site) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000439/2022-2023 | 258/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 7.71 | 4.29 | 60
615 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of submersible pumping machinery at with MCC panel newly constructed River Bed Tubewell for Augmentation of Puncha w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000440/2022-2023 | 259/PMD | 06/03/2023 | 1062 | ANUP KR. SAHA | 36.41 | 6.72 | 66
616 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 125kva voltage stabilizer for Augmentation of Puncha(River Site) w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000441/2022-2023 | 260/PMD | 06/03/2023 | 907 | SEN BROTHERS | 13.61 | 10.04 | 100
617 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery with others electro-mechanical work at Puncha River site for Augmentation of Puncha PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000756/2024-2025 | 40/PMD | 10/01/2025 | 325 | S. PATHAK & CO. | 9.44 | 0 | 100
618 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000006/2023-2024 | 615/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
619 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of distribution Pipeline of Arsha (Zone-III) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tumba Village] | Assistant Engineer |  | ORD/000248/2024-2025 | 1141/PD | 18/06/2024 | 45 | MOONLIGHT HOUSE | 6.65 | 0 | 0
620 | Purulia Division | Purulia Sadar Sub-Division | Painting, fixing of water level indicator, brickwork at ground floor and other allied works related to Over Head Reservoir of 100 Cum Capacity at fasko mouza under Arsha water supply scheme(Zone-II) of Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000277/2024-2025 | 1233/PD | 03/07/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.42 | 0 | 0
621 | Purulia Division | Purulia Sadar Sub-Division | Laying of Distribution pipeline of Arsha W/S Scheme (Zone-1) under Purulia Division PHE Dte.(Mouza Covered Rangamati,Pattanr,Asaramdih) | Assistant Engineer |  | ORD/000344/2024-2025 | 1369/PD | 25/07/2024 | 270 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 24.74 | 0 | 100
622 | Purulia Division | Purulia Sadar Sub-Division | Supplying & Laying of Distribution pipeline and Providing FHTC at Arsha W/S Scheme (Zone-3) under Purulia Division PHE Dte. (Mouza Covered-Arsha,Khedadih,Tumba) | Assistant Engineer |  | ORD/000345/2024-2025 | 1370/PD | 25/07/2024 | 447 | SADHAN GORAIN | 39.24 | 0 | 45
623 | Purulia Division | Purulia Sadar Sub-Division | Supplying & laying of Parallel line and Branch line of HDPE pipe for Distribution System of Arsha W/S Scheme(Zone-1) under Purulia Division PHE Dte. (Mouza Name-Rangamati)(Village Name-Asaramdih) | Assistant Engineer |  | ORD/000659/2023-2024 | 1350/PD | 13/09/2023 | 30 | TUMPA GORAIN | 12.98 | 0 | 100
624 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under Zone-1 command area of Arsha & its Adjoing Mouza Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Zone-1, GP-Arsha,Village-Rangamati, Habitation-Rangamati- 624 nos,Pattarn-136Nos, Santaldih-25 nos, Asharamdih-68 nos) | Assistant Engineer |  | ORD/000843/2022-2023 | 1745/PD | 22/11/2022 | 45 | TUMPA GORAIN | 62.69 | 7.56 | 100
625 | Purulia Division | Purulia Sadar Sub-Division | Laying Gap portion DI Rising Main & Distribution for zone-II and Laying in new alignment of Distribution Pipeline due to Construction village Road at Zone III with Construction protection wall for Rising Main pipeline of Arsha & Its Adjoining Mouza W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000849/2023-2024 | 1488/PD | 12/10/2023 | 30 | SADHAN GORAIN | 20.19 | 0 | 80
626 | Purulia Division | Purulia Sadar Sub-Division | Supply and Delivery of DI Fittings And Valve For Arsha and its Adjoing Mouza W/S Scheme of Purulia Sadar Sub-Division Under Purulia Division Phe Dte. | Assistant Engineer |  | ORD/000852/2022-2023 | 1756/PD | 22/11/2022 | 15 | AMAL KUMAR MUKHERJEE | 2.65 | 0 | 100
627 | Purulia Division | Purulia Sadar Sub-Division | Laying of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-2, GP-Arsha,Village-Fasko) Water Supply Scheme under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000993/2022-2023 | 106/PD | 20/01/2023 | 741 | KANTILAL SAO | 33.89 | 0 | 100
628 | Purulia Division | Purulia Sadar Sub-Division | Extension of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-3, GP-Arsha,Village-Tumba) Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000995/2022-2023 | 108/PD | 20/01/2023 | 30 | MOONLIGHT HOUSE | 24.38 | 0 | 100
629 | Purulia Division | Purulia Sadar Sub-Division | Construction of Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain etc. complete at Arsha Zone-III for Augmentation of Arsha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001083/2024-2025 | 2178/PD | 13/12/2024 | 90 | SADHAN GORAIN | 5.27 | 0 | 0
630 | Purulia Division | Purulia Sadar Sub-Division | Construction of RCC elevated reservoir of capacity 100 cum & staging height 20 mtr. for Arsha W/S Scheme at (Zone-II) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001295/2022-2023 | 802/PD | 05/05/2022 | 240 | ANUP KUMAR SAHA | 30.47 | 23 | 75
631 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall at Arsha Zone-2 OHR Site and Making Bypass Arrangement at OHR Site under Arsha W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001870/2023-2024 | 95/PD | 15/01/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 25.58 | 0 | 100
632 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 200 cum and staging height 20 mtr. with including supply of all labour & materials for Saltora -Hijli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000176/2022-2023 | 793/PD | 05/05/2022 | 270 | ASHOK KUMAR CHATTERJEE | 64.5 | 38.66 | 100
633 | Purulia Division | Raghunathpur Sub-Division | New Sinking of 200 mm dia 8 (Eight) Nos river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) under Saltora-Hijli W/S Scheme under Raghunathpur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000322/2022-2023 | 855/PD | 23/05/2022 | 30 | ASHOK KUMAR CHATTERJEE | 41.13 | 22.13 | 35
634 | Purulia Division | Raghunathpur Sub-Division | Laying of Clear Water Rising Main under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000323/2022-2023 | 856/PD | 23/05/2022 | 60 | BASANTA KUMAR SINGHADEO | 51.02 | 12.58 | 25
635 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump House (10 X 7 mtr) at Head Work site under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000333/2022-2023 | 864/PD | 23/05/2022 | 100 | M/S SAYAK BHATTACHARYA | 15.23 | 10.99 | 100
636 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Damodar river site under Saltora-Hijli W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000334/2022-2023 | 865/PD | 23/05/2022 | 100 | BALAJI UDDYOG | 13.87 | 12.42 | 0
637 | Purulia Division | Raghunathpur Sub-Division | Repairing & renovation of of CWR, Office Bldg., Pump Houses and Boundary Wall at Saltora -Hijli W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000336/2022-2023 | 867/PD | 23/05/2022 | 60 | M/S ADITYA KUMAR | 6.94 | 2.97 | 50
638 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room-Cum-Chlorine Room at River Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000367/2022-2023 | 330/RNP | 01/06/2022 | 90 | SUBRATA SINGHADEO | 4.48 | 4.04 | 95
639 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Saltore-Hijuli OHR Campus under Saltore-Hijuli W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 40.00 mtr.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000368/2022-2023 | 332/RNP | 01/06/2022 | 21 | AMIT PATHAK | 3.65 | 3.64 | 100
640 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room-Cum-Chlorine Room at OHR Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000370/2022-2023 | 331/RNP | 01/06/2022 | 90 | DEBANJAN SEAL | 4.46 | 4.44 | 100
641 | Purulia Division | Raghunathpur Sub-Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000404/2022-2023 | 343/RNP | 01/06/2022 | 30 | G.TECH INDIA | 1.4 | 0.97 | 75
642 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work (285 Nos.) of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000504/2022-2023 | 1009/PD | 29/06/2022 | 45 | PARTHA PRATIM CHHATAIT | 110.11 | 56.34 | 0
643 | Purulia Division | Raghunathpur Sub-Division | Additional work for Construction of Switch Room Cum Chlorine Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part -I) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000527/2023-2024 | 399/RNP | 05/09/2023 | 15 | DEBANJAN SEAL | 0.94 | 0.94 | 100
644 | Purulia Division | Raghunathpur Sub-Division | Additional work for Construction of Switch Room Cum Chlorin Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part - II) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000530/2023-2024 | 397/RNP | 05/09/2023 | 15 | DEBANJAN SEAL | 0.97 | 0.97 | 100
645 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work and construction of Boundary wall at OHR Site of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000913/2022-2023 | 1891/PD | 15/12/2022 | 60 | BALAJI UDDYOG | 204.07 | 83.16 | 35
646 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work and construction of approach road at Pump House of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-III | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000929/2022-2023 | 1892/PD | 15/12/2022 | 865 | PRAVAT SARKAR | 99.55 | 80.18 | 88
647 | Purulia Division | Raghunathpur Sub-Division | Additional work for Restoration work by construction of RCC Retaining wall for protection work of dedicated transformer at Saltore-Hijuli CWR site of Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Handed over to PRI Bodies ) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/001291/2022-2023 | 273/6/RNP | 19/05/2022 | 15 | BASANTA KUMAR SINGHADEO | 0.88 | 0 | 0
648 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000009/2022-2023 | 958/PD | 20/06/2022 | 0 | Resource Division | 158.64 | 0 | 0
649 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000021/2022-2023 | 979/PD | 22/06/2022 | 0 | Resource Division | 118.82 | 0 | 0
650 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000043/2022-2023 | 426/PD | 21/03/2023 | 0 | Resource Division | 37.42 | 0 | 0
651 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 973/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000969/2022-2023 | BP-2022-23-137 | 19/07/2022 | 0 | M/S TECH VISION | 0.41 | 0 | 0
652 | Purulia Division | Raghunathpur Sub-Division | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 543/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000970/2022-2023 | BP-2022-23-138 | 19/07/2022 | 0 | M/S TECH VISION | 4.08 | 0 | 0
653 | Purulia Mechanical | Raghunathpur Sub-Division | New service connection at Saltore Hijuli OHR site | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00111/2024-2025 | BP-24-25-15 | 24/05/2024 | 0 | WBSEDCL SALTORE CCC | 0.11 | 0 | 0
654 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for removal of one 63 KVA DTR along with one span HT & one span LT line at the premises of Saltore Hijuli PHE | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00435/2023-2024 | BP-23-24-222 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.09 | 0 | 0
655 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Saltore Hijuli Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000040/2023-2024 | 446/PMD | 20/04/2023 | 30 | T.N.BANERJEE | 21.56 | 0 | 50
656 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 8 nos. River bed submersible pumps motor sets with other allied works for SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000058/2023-2024 | 527/PMD | 05/05/2023 | 60 | INDRAJIT MITRA | 23.5 | 0 | 8
657 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and Installation of Submersible pumping machineries for newly constructed tube wells and other allied works for Augmentation of Saltore hijuli W/S scheme under PMD Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000058/2024-2025 | 976/PMD | 20/06/2024 | 60 | BISHWANATH NANDI | 8.76 | 0 | 70
658 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and delivery of Free chlorine test kit at different Pumping water supply scheme under Purulia Mechanical Division, PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000321/2023-2024 | 46/PMSD(W/S) | 08/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.94 | 0 | 100
659 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of CWR Submersible pumping machineries, MCC Panels, flow meter with others allied works for Augmentation at SALTORE HIJULI ( ZONE-3) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000347/2022-2023 | 132/PMD | 20/02/2023 | 60 | M/S D. PALIT & CO. | 27.01 | 0 | 35
660 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels, flow meter, HOT crane with others allied works for Augmentation at SALTORE HIJULI (ZONE-1 and 2) w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000349/2022-2023 | 134/PMD | 20/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 70.46 | 9.06 | 100
661 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works at SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000350/2022-2023 | 135/PMD | 20/02/2023 | 60 | BISHWANATH NANDI | 7.64 | 7.63 | 0
662 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and fitting fixing of Mainswitch and cable for Pumphouse and internal and external illumination of OHR site for Augmentation at Saltore Hijuli(Zone-1 & 2) w/s supply scheme under PMD,PHE Dte .in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000391/2023-2024 | 376/PMD | 04/03/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 10.49 | 0 | 100
663 | Purulia Mechanical | Raghunathpur Sub-Division | Testing commissioning of Gaseous chlorination system and extension of solution line upto OLD CWR for Augmentation at Saltore Hijuli (Zone-1 & 2) under PMD, PHE Dte in the district of Purulia. (2ND Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000566/2024-2025 | 353/PMSD(W/S) | 04/09/2024 | 392 | BISHWANATH NANDI | 0.81 | 0 | 100
664 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System for zone-III & Miscellaneous works at Pump House under Saltore-Hijuli W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000642/2024-2025 | 1574/PMD | 14/11/2024 | 107 | BISHWANATH NANDI | 4.42 | 0 | 100
665 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FOR AUGMENTATION OF SALTORE HIJULI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000425/2022-2023 | BP-22-23-85 | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.68 | 0 | 0
666 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00088/2022-2023 | BP-2022-23-5175 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.27 | 0 | 0
667 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00089/2022-2023 | BP-2022-23-5176 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.34 | 0 | 0
668 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00092/2022-2023 | BP-2022-23-5179 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 45.74 | 0 | 0
669 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Emergent Dismantling of R.C.C. Elevated Reservoir, Capcaity 350 Cum (Intze Type), Staging height 20 metre at Joypur OHR Site of Joypur W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000024/2023-2024 | 553/PD | 13/04/2023 | 90 | TAPAN CHANDRA | 10.38 | 0 | 100
670 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain, Land development etc. complete at Joypur OHR Site, of Joypur W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000043/2023-2024 | 659/PD | 17/05/2023 | 100 | KM ENTERPRISES | 10.91 | 0 | 100
671 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 300mt. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000083/2023-2024 | 816/PD | 26/06/2023 | 45 | SADHAN GORAIN | 5.01 | 4.53 | 95
672 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply & delivery DI Specials for Newly Laying of Distribution Main (DI-K7) Pipe line from OHR Site to Joypur Ranibandh Rail Crossing & Towards Raghbore More under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000085/2023-2024 | 817/PD | 26/06/2023 | 45 | PRIYATOSH MUKHERJEE | 4.11 | 4.02 | 98
673 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and) at Gurrabera habitation of Mouza-Ritudih (JL-62) under command area of Joypur Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000123/2024-2025 | 890/PD | 07/05/2024 | 45 | BHAGABAN DAS KUMAR | 3.24 | 0 | 100
674 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Staff Toilet at Sirkabad OHR Site under Joypur PWSS Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000155/2024-2025 | 885/PD | 07/05/2024 | 147 | INDRAJIT SARKAR | 4.09 | 0 | 100
675 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Staff Toilet at Riversite Pump house under Joypur PWSS Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000156/2024-2025 | 886/PD | 07/05/2024 | 60 | PURNA CHANDRA TEWARI | 4.1 | 0 | 0
676 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Left Out & Parallal distribution pipe line including Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (JL-105) & Mouza- Ghaghri (JL-106) under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000219/2024-2025 | 1093/PD | 07/06/2024 | 60 | MOONLIGHT HOUSE | 4.13 | 0 | 100
677 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying DI Rising Main in new alignment from Pump house to OHR and making Inter Connection Arrangement with Distribution System for Joypur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000228/2024-2025 | 1062/PD | 07/06/2024 | 60 | BHAGABAN DAS KUMAR | 2.55 | 0 | 100
678 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Shyampur (Jl-101) & Mouza-Dhabani (Jl-103) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000309/2022-2023 | 841/PD | 23/05/2022 | 887 | SUNNY ELECTRIC CO | 56.74 | 38.42 | 100
679 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000311/2022-2023 | 845/PD | 23/05/2022 | 30 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0
680 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000312/2022-2023 | 842/PD | 23/05/2022 | 45 | PRIYATOSH MUKHERJEE | 71.27 | 43.78 | 70
681 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000313/2022-2023 | 846/PD | 23/05/2022 | 30 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0
682 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room at Joypur OHR site of Joypur W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000314/2022-2023 | 847/PD | 23/05/2022 | 90 | KM ENTERPRISES | 16.44 | 7.41 | 100
683 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (Jl-105) & Mouza-Ghaghri (Jl-106) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000315/2022-2023 | 843/PD | 23/05/2022 | 45 | MOONLIGHT HOUSE | 14.06 | 5.2 | 100
684 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing, renovation & restoration of Pump house & store cum Guard room at Deolghata Pump house campus of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000316/2022-2023 | 848/PD | 23/05/2022 | 60 | SEKH IRFAN | 5.38 | 0 | 100
685 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Clear Water Reservoir (CWR) of Capacity 100 Cum with other allied works at Deolghata Pump House campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000317/2022-2023 | 850/PD | 23/05/2022 | 100 | SK ABBAS | 10.71 | 9.64 | 0
686 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Nutandi (J.L. No.- 61) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000337/2022-2023 | 871/PD | 23/05/2022 | 45 | AJAY MONDAL | 35.11 | 16.01 | 50
687 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000339/2022-2023 | 873/PD | 23/05/2022 | 954 | M/S. S. CHOUDHURY | 72.66 | 38.29 | 55
688 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000409/2022-2023 | 936/PD | 16/06/2022 | 930 | M/S. S. CHOUDHURY | 201.33 | 74.27 | 100
689 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 2(Two ) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000440/2024-2025 | 1503/PD | 27/08/2024 | 30 | BOSE CONSTRUCTION | 18.14 | 0 | 100
690 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Barbenda (J.L. No.- 63) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000548/2022-2023 | 1039/A/PD | 07/07/2022 | 60 | PREMNATH MITRA | 80.51 | 25.67 | 32
691 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Joypur Block to supply drinking water of command area of Joypur Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000624/2022-2023 | 1394/PD | 01/09/2022 | 45 | AMAL KUMAR MUKHERJEE | 6.32 | 5.41 | 100
692 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 250mtr. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000658/2023-2024 | 1352/PD | 13/09/2023 | 45 | SADHAN GORAIN | 4.18 | 3.34 | 100
693 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Tunta (Jl-104) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000850/2022-2023 | 1754/PD | 22/11/2022 | 45 | M/S KHAN ENTERPRISE | 23.24 | 11.26 | 100
694 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Clear Water Reservoir (CWR) of Capacity 200 Cum with other allied work at OHR campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000870/2022-2023 | 1837/PD | 12/12/2022 | 361 | KM ENTERPRISES | 33.08 | 26.17 | 100
695 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing, renovation of Boundary Wall at Joypur OHR site of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000899/2022-2023 | 1838/PD | 12/12/2022 | 30 | TRINITY CONSTRUCTION | 18.79 | 4.87 | 100
696 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 1000 M3 capacity Over Head Reservoir of Joypur W/S Scheme under Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001003/2022-2023 | 112/A/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.86 | 0
697 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Over Head Reservoir (OHR) of 1000 Cum Capacity, Staging Height 20 mtr. at existing OHR Campus (Rahardaga Mouza ) of Joypur W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001027/2022-2023 | 148/PD | 03/02/2023 | 270 | SADHAN GORAIN | 229.29 | 133.96 | 92
698 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 350 cubic meter capacity Over Head Reservoir of Bandwan W/S Scheme under Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001028/2022-2023 | 231/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
699 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 200 cubic meter capacity Over Head Reservour of Darda W/S Scheme under Purulia Division P.H.E dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001029/2022-2023 | 232/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
700 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 600 cubic meter capacity Over Head Reservour of ManbazaR -I W/S Scheme under Purulia Division P.H.E dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001030/2022-2023 | 233/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
701 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 250 cubic meter capacity Over Head Reservour of Puncha W/S Scheme under Purulia Division P.H.E dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001031/2022-2023 | 234/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
702 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 750 cubic meter capacity Over Head Reservour of Kotshila W/S Scheme under Purulia Division P.H.E dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001032/2022-2023 | 235/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
703 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Soil Investigation work for proposed 100 cubic meter capacity Over Head Reservour of Arsha W/S Scheme under Purulia Division P.H.E dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001033/2022-2023 | 236/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
704 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001047/2022-2023 | 279/PD | 27/02/2023 | 30 | S. R. ENTERPRISE | 10.39 | 0 | 60
705 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing (Left Out) Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Bhaddi (J.L. No.- 65) & Mouza- Litiadih (J.L. No.-99) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001107/2022-2023 | 378/PD | 16/03/2023 | 1022 | AMAL KUMAR MUKHERJEE | 8.93 | 0 | 50
706 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001148/2022-2023 | 423/PD | 21/03/2023 | 45 | BOSE CONSTRUCTION | 43.97 | 4.81 | 60
707 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001150/2022-2023 | 424/PD | 21/03/2023 | 45 | BOSE CONSTRUCTION | 88.75 | 19.71 | 100
708 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Withdrawing of 150 mm dia. DI Pipe (distribution main) & newly laying in new trench and through culvert under Railway track near Ranibandh Rail Crossing of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001222/2022-2023 | 247/PSD | 31/03/2023 | 10 | APEX TRADERS | 0.71 | 0.68 | 0
709 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Undercut Pump house including panel room & chlorination room at Deulghata Pump House of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001496/2023-2024 | 1796/PD | 08/12/2023 | 90 | M/S CONTRACTORS SYNDICATE | 23.01 | 0 | 100
710 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extension of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001864/2023-2024 | 90/PD | 15/01/2024 | 60 | PRIYATOSH MUKHERJEE | 61.3 | 0 | 75
711 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Collecting line from Riverbed Manifold to Pump house and Laying of Distribution pipeline from Existing OHR to Main Road and other allied works complete under Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. (Under Joypur W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/003948/2023-2024 | 293/PD | 28/02/2024 | 484 | ASHOKE ADHIKARY | 12.9 | 0 | 80
712 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Pipeline from Banahata Mouza to Kachahatu Mouza for Providing FHTC at Joypur Water Supply Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/003983/2023-2024 | 529/PD | 16/03/2024 | 60 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 84.88 | 0 | 100
713 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extention of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/004250/2023-2024 | 491/PD | 16/03/2024 | 360 | UMA CONSTRUCTION | 74.86 | 0 | 100
714 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000011/2022-2023 | 970/PD | 21/06/2022 | 0 | Resource Division | 372.24 | 0 | 0
715 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Joypur W/S Scheme, Block- Joypur) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 535/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000915/2022-2023 | BP-2022-23-119 | 16/07/2022 | 0 | RADIANT | 8.59 | 0 | 0
716 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Joypur (River Side) W/S Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00245/2023-2024 | BP-2023-24-150 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
717 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection For Augmentation of Joypur | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00246/2023-2024 | BP-2023-24-149 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.45 | 0 | 0
718 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Joypur (OHR side) water supply scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000031/2023-2024 | 421/PMD | 13/04/2023 | 60 | MERCURY ENGINEERING COMPANY | 36.21 | 0 | 30
719 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Joypur(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000120/2023-2024 | 801/PMD | 12/07/2023 | 664 | M/S P.P.ELECTRICALS | 15.63 | 0 | 96
720 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water Supply Scheme (River Site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000203/2023-2024 | 1193/PMD | 03/11/2023 | 60 | S. PATHAK & CO. | 10.83 | 0 | 56
721 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Joypur OHR for Augmentation of Joypur Water supply scheme block Joypur under PMD PHE Dte. district Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000381/2022-2023 | 212/PMD | 28/02/2023 | 30 | ANUP KR. SAHA | 21.6 | 12.92 | 93
722 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of internal lighting with other allied works for augmentation of Joypur (River side & OHR side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000424/2022-2023 | 242/PMD | 03/03/2023 | 60 | MD. ASLAM | 1.21 | 0 | 60
723 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Joypur(riverside) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000425/2022-2023 | 243/PMD | 03/03/2023 | 367 | ANUP KR. SAHA | 70.91 | 33.7 | 66
724 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Joypur(Riverside) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000426/2022-2023 | 244/PMD | 03/03/2023 | 790 | COMBINE ENTERPRISES | 58.94 | 38.28 | 35
725 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Joypur(OHR Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000427/2022-2023 | 245/PMD | 03/03/2023 | 60 | ANUP KR. SAHA | 10.76 | 6.2 | 96
726 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0
727 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000004/2023-2024 | 613/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
728 | Purulia Division | Purulia Sadar Sub-Division | Searching report of land & Retainer Service by Regional Advocate(s) for direct purchase of land for public purpose by Dept. through Zilla Parisad from Intending owners WTP for surface based piped water supply scheme for Purulia District under Division PHE Dte. | Assistant Engineer |  | BILL/02079/2023-2024 | 9/2024-25 | 09/04/2024 | 0 | RANJEET CHATTERJEE | 1.97 | 0 | 0
729 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Baram, Thakurshima, Briddhitanr & Joratanr) Part-A | Assistant Engineer |  | ORD/000156/2020-2021 | 1409/PD | 29/12/2020 | 45 | KOUSHIK CHATTERJEE | 48.17 | 17.25 | 0
730 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Baram water supply scheme at Arsha Block of Purulia Sadar-Sub Division for providing functional house hold Tap connection (FHTC) under Jal Sapna program (Habitation covered Baram, Thakushima, Bridhistarh, Jharatar) Part-A. (Tender No. 9/SE/PMU of 2020-21) | Assistant Engineer |  | VCH/000741/2020-2021 | 369/8443218 | 25/02/2021 | 0 | KOUSHIK CHATTERJEE | 28.91 | 0 | 0
731 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Boram W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Mankiyari, Torang, Matkumpiri, Raipur, Jibandity) Part-B. (Tender No. 160/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000820/2020-2021 | 386/844340 | 08/03/2021 | 0 | SOUMITRA CHAKRABORTY | 20.9 | 0 | 0
732 | Purulia Division | Purulia Sadar Sub-Division | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) | Assistant Engineer |  | VCH/000822/2022-2023 | 133/8443221/1 | 29/09/2022 | 0 | SOUMITRA CHAKRABORTY | 1.2 | 0 | 0
733 | Purulia Division | Purulia Sadar Sub-Division | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) | Assistant Engineer |  | VCH/000823/2022-2023 | 133/8443221/2 | 29/09/2022 | 0 | SOUMITRA CHAKRABORTY | 0.44 | 0 | 0
734 | Purulia Division | Purulia Sadar Sub-Division | Laying of additional pipeline of 20mm HDPE (OD) for the work of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.721/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000894/2021-2022 | 278/844393/1 | 14/01/2022 | 0 | SOUMITRA CHAKRABORTY | 2.62 | 0 | 0
735 | Purulia Division | Purulia Sadar Sub-Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.160/EE/PD of 2020-21) | Assistant Engineer |  | VCH/000895/2021-2022 | 278/844393/2 | 14/01/2022 | 0 | SOUMITRA CHAKRABORTY | 5.64 | 0 | 0
736 | Purulia Division | Raghunathpur Sub-Division | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Dubra W/S Schema on Raghunathpur Chandankairy-Chas Road CH-13.963 KM to CH-15.178 Km under Purulia Division, P.W.D in the district of Purulia in the year 2023-2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00624/2023-2024 | BP-2023-24-387 | 18/08/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 95.57 | 0 | 0
737 | Purulia Division | Raghunathpur Sub-Division | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur W/S Schema along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division, P.WD in the district of Purulia in the year 2023-24. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00625/2023-2024 | BP-2023-24-386 | 18/08/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 60.8 | 0 | 0
738 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Dubra Mouza, JL No.-79, Plot No.499 at OHR site under Dubra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000015/2023-2024 | 544/PD | 12/04/2023 | 629 | ASHOK KUMAR CHATTERJEE | 14.79 | 0 | 100
739 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000114/2023-2024 | 882/PD | 03/07/2023 | 45 | SABYASACHI MISHRA | 11.94 | 6.17 | 100
740 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra Water Supply Scheme, Block- Para ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000846/2022-2023 | 1749/PD | 22/11/2022 | 30 | M/S. DESTINY CONSTRUCTION | 3.48 | 3.48 | 100
741 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room and Sinking of 2 (Two) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Dubra W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000892/2023-2024 | 1542/PD | 16/10/2023 | 777 | MANATOSH SINGH | 47.18 | 0 | 60
742 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including supply of materials including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000987/2022-2023 | 99/PD | 20/01/2023 | 1076 | NANIGOPAL DEY | 97.25 | 13.09 | 40
743 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000988/2022-2023 | 100/PD | 20/01/2023 | 90 | MANATOSH SINGH | 79.67 | 16.61 | 55
744 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-D] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000989/2022-2023 | 102/PD | 20/01/2023 | 45 | SUBRATA SINGHADEO | 39.27 | 32.2 | 100
745 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-E] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000990/2022-2023 | 103/PD | 20/01/2023 | 30 | M/S SAYAK BHATTACHARYA | 13.69 | 13.65 | 100
746 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-C] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001000/2022-2023 | 101/PD | 20/01/2023 | 30 | SOUMITRA CHAKRABORTY | 98.6 | 69.9 | 100
747 | Purulia Division | Raghunathpur Sub-Division | Supply, delivery fitting & fixing of 1 No. Scheme Description Sign board (6' X 3') under Dubra W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Head Work Site | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001944/2023-2024 | 25/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.17 | 0 | 0
748 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Dubra (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000039/2023-2024 | 445/PMD | 20/04/2023 | 30 | DEY ENTERPRISE,MALDAH | 21.63 | 0 | 70
749 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Dubra water supply scheme under PMD PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000182/2023-2024 | 1172/PMD | 03/11/2023 | 60 | SWAPAN ENTERPRISE | 7.21 | 0 | 75
750 | Purulia Mechanical | Raghunathpur Sub-Division | Internal and external illumination with other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000184/2023-2024 | 1174/PMD | 03/11/2023 | 60 | PINTU DEY | 5.37 | 0 | 25
751 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, HOT, Flowmeter and other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000456/2022-2023 | 296/PMD | 16/03/2023 | 60 | TAPAN KUMAR DEY | 42.49 | 0 | 40
752 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Muza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) | Assistant Engineer | Junior Engineer-3 | ORD/000288/2020-2021 | 213/PD | 08/02/2021 | 45 | KHAN ENTERPRISE | 70.34 | 120.56 | 0
753 | Purulia Division | Raghunathpur Sub-Division | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000844/2022-2023 | 1747/PD | 22/11/2022 | 45 | MANATOSH SINGH | 4.3 | 0 | 0
754 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) | Assistant Engineer | Junior Engineer-3 | VCH/000179/2022-2023 | BP-2022-23-46 | 02/05/2022 | 0 | S AND P CONSTRUCTION | 16.37 | 0 | 0
755 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/000190/2022-2023 | BP-2022-23-57 | 20/05/2022 | 0 | TOTAL INFRA | 3.35 | 0 | 0
756 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Sonathali W/S Scheme at Kashipur Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Kalapathar, Kendtanr, kultore, kumardih, Ushjuri Sonathol (1309) Nos. (Tender No:- 373/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000220/2021-2022 |  | 09/08/2021 | 0 | KHAN ENTERPRISE | 14.38 | 0 | 0
757 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Mouza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) (Tender No. 373/EE/PD of 2020-21) (Ad-interim) | Assistant Engineer | Junior Engineer-3 | VCH/000224/2021-2022 | 89/8443101 | 15/07/2021 | 0 | KHAN ENTERPRISE | 7.11 | 0 | 0
758 | Purulia Division | Raghunathpur Sub-Division | Functional House Hold Connection (FHTC) including other allied works of Sonatholi Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division PHE Dte. (Mouza- Kashipur, Kendtanr, Kultore, Kumardih, Ushjuri Sonatholi) (1309 nos.) (Tender No. 373/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000870/2020-2021 |  | 22/03/2021 | 0 | KHAN ENTERPRISE | 28.02 | 0 | 0
759 | Purulia Division | Raghunathpur Sub-Division | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-I) | Assistant Engineer | Junior Engineer-2 | ORD/000136/2021-2022 | 530/RNP | 27/08/2021 | 30 | SABIR ALI KHAN | 4.84 | 4.08 | 100
760 | Purulia Division | Raghunathpur Sub-Division | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-II) | Assistant Engineer | Junior Engineer-2 | ORD/000141/2021-2022 | 529/RNP | 27/08/2021 | 30 | RAHIBUDDIN MONDAL | 4.84 | 4.16 | 100
761 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation -Salani (36 Nos.), Balitora (72 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000176/2020-2021 | 17/RNP | 11/01/2021 | 15 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0
762 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Dandahit , Habitation - Dandahit (108 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000177/2020-2021 | 18/RNP | 11/01/2021 | 15 | ASHOK KUMAR CHATTERJEE | 4.83 | 0 | 0
763 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). | Assistant Engineer | Junior Engineer-2 | ORD/000178/2020-2021 | 19/RNP | 11/01/2021 | 15 | SANDIP KUMAR DUBEY | 4.81 | 0 | 0
764 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | Assistant Engineer | Junior Engineer-2 | ORD/000179/2020-2021 | 20/RNP | 11/01/2021 | 15 | MS MITRA SENGUPTA ENTERPRISES | 4.78 | 0 | 0
765 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Sunuri, Habitation -Uppardi -(63Nos)Sunuri(49Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000180/2020-2021 | 38/RNP | 11/01/2021 | 15 | UTTAM KUMAR DUTTA | 4.78 | 0 | 0
766 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Bakuliasota , Habitation - Bakulia (112 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000190/2020-2021 | 21/RNP | 11/01/2021 | 15 | DEB SHANKAR LAYEK | 4.78 | 0 | 0
767 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Baltora , Habitation - Mathorgoria (30 Nos.),Baltora (82 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000207/2020-2021 | 24/RNP | 11/01/2021 | 15 | KANAILAL PAL | 4.78 | 0.18 | 100
768 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Baltora, Habitation -Balitora (51 Nos.), Mouza- Shunuri, Habitation - Sunuri (61 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000208/2020-2021 | 25/RNP | 11/01/2021 | 15 | SUBRATA SINGHADEO | 4.73 | 0.98 | 100
769 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Dhanasdi, Habitation - Dhanasdi (84 Nos.), Mouza-Ektira, Habitation - Ektira (28 Nos.) | Assistant Engineer | Junior Engineer-2 | ORD/000231/2020-2021 | 29/RNP | 11/01/2021 | 15 | KABERI DUTTA | 4.78 | 4.44 | 100
770 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Santuri Water Supply Scheme, Block- Santuri ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000847/2022-2023 | 1750/PD | 22/11/2022 | 30 | M/S. DESTINY CONSTRUCTION | 2.3 | 0 | 100
771 | Purulia Division | Raghunathpur Sub-Division | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (112 Nos). (Tender No. 286/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000068/2021-2022 | 17/844362/1 | 21/04/2021 | 0 | CHAIL CONSTRUCTION | 4.44 | 0 | 0
772 | Purulia Division | Raghunathpur Sub-Division | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (88 Nos). (Tender No. 281/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000069/2021-2022 | 17/844362/2 | 21/04/2021 | 0 | SUDHANSHU OJHA | 4.4 | 0 | 0
773 | Purulia Division | Raghunathpur Sub-Division | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme of Santuri Block. (Tender No. 303/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000081/2021-2022 | 11/844325/1 | 12/04/2021 | 0 | ROY CONSTRUCTION | 4.54 | 0 | 0
774 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Balitora, Habitation- Balitora (108 Nos.) (Tender No:- 288/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000119/2021-2022 | BP-2021-22-50 | 20/07/2021 | 0 | NANIGOPAL DEY | 2.18 | 0 | 0
775 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Jagannathdi, Habitation-Jagannathdi (09 Nos.), Mouza- Kshatagora Habitation - Kshatagora (11 nos), Mouza- Manpur, Habitation- Manpur (46 Nos.), Siyal Danga (39) (Tender No:- 283/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000120/2021-2022 | BP-2021-22-51 | 20/07/2021 | 0 | SANDIP KUMAR DUBEY | 4.68 | 0 | 0
776 | Purulia Division | Raghunathpur Sub-Division | FHTC including other allied works of Balitora water supply scheme at Santuri Block at Mouza-Balitora, Habitation (108 Nos) (Tender No. 288/EE/PD of 2020-21) (Ad-interim) | Assistant Engineer | Junior Engineer-2 | VCH/000126/2021-2022 | 70/844369 | 18/06/2021 | 0 | NANIGOPAL DEY | 1.86 | 0 | 0
777 | Purulia Division | Raghunathpur Sub-Division | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block (Tender No. 363/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000128/2021-2022 | 59/844323 | 08/06/2021 | 0 | SUPRIYA MAHANTI MISHRA | 4.76 | 0 | 0
778 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at (Balitora, Habitation- Balitora). (112 Nos.) (Tender No.305/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000173/2021-2022 | BP-2021-22-67 | 12/08/2021 | 0 | TUMPA GORAIN | 4.52 | 0 | 0
779 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Balitora, Habitation- Mathorgoria (30 Nos.) (82 Nos.) (Tender No.337/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000175/2021-2022 | BP-2021-22-66 | 12/08/2021 | 0 | KANAILAL PAL | 4.5 | 0 | 0
780 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza-Dandahit, Habitation- Dandahit). (112 Nos.) (Tender No.279/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-2 | VCH/000178/2021-2022 | BP-2021-22-68 | 12/08/2021 | 0 | SIKHA ENTERPRISES | 4.77 | 0 | 0
781 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (86 Nos.) Mouza-Saspur, Habitation-Saspur (26 Nos.) (Tender No.302/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000185/2021-2022 | BP-2021-22-87 | 23/08/2021 | 0 | SUBRATA SINGHADEO | 4.53 | 0 | 0
782 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (112) Nos. (Tender No:- 362/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000213/2021-2022 | BP-2021-22-82 | 23/08/2021 | 0 | SUBHAS CHANDRA MAHATO | 4.58 | 0 | 0
783 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Dandahit, Habitation- Dandahit (108 Nos.) (Tender No:- 414/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000215/2021-2022 | BP-2021-22-86 | 23/08/2021 | 0 | ASHOK KUMAR CHATTERJEE | 4.79 | 0 | 0
784 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Deuli, Habitation- Deuli (70 Nos.) Mouza- Sunuri, Habitaion- Sunuri (42 Nos.) (Tender No:- 348/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000216/2021-2022 | BP-2021-22-95 | 23/08/2021 | 0 | SK ABBAS | 3.61 | 0 | 0
785 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Sunuri, Habitation- Kapasdanga (35) Sunuri (77) Nos. (Tender No:- 318/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000218/2021-2022 | BP-2021-22-84 | 23/08/2021 | 0 | KAMAKHYA ENTERPRISE | 4.58 | 0 | 0
786 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Kashatagora, Habitation- Kashatagora (112 Nos) (Tender No:- 271/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000331/2021-2022 | BP-2021-22-116 | 11/10/2021 | 0 | KHITISH CHANDRA PATHAK | 4.43 | 0 | 0
787 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Baltora, Habitation- Baltora (51 Nos), Mouza- Santuri, Habitation- Santuri (61 Nos), (Tender No:- 299/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000332/2021-2022 | BP-2021-22-118 | 11/10/2021 | 0 | SUBRATA SINGHADEO | 3.55 | 0 | 0
788 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (16 Nos.), Mouza- Santuri, Habitation- Uppardih (46 Nos.) Mouza- Ektira, Habitation- Berakural-(1), Ektira (48 Nos.) Mouza-Kastagora Habitation- Chapabera Chak-(1) (Tender No.342/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000385/2021-2022 | BP-2021-22-131 | 11/10/2021 | 0 | MS MITRA SENGUPTA ENTERPRISES | 4.63 | 0 | 0
789 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (112 Nos.) (Tender No.276/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000386/2021-2022 | BP-2021-22-132 | 11/10/2021 | 0 | DEB SHANKAR LAYEK | 4.54 | 0 | 0
790 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Sashpur, Habitation-Sashpur (112 Nos.) (Tender No.293/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000451/2021-2022 | BP-2021-22-174 | 22/11/2021 | 0 | PRATIK SAHA | 4.48 | 0 | 0
791 | Purulia Division | Raghunathpur Sub-Division | DZSGZDG | Assistant Engineer | Junior Engineer-2 | VCH/000624/2021-2022 |  | 30/11/2021 | 0 | KABERI DUTTA | 1 | 0 | 0
792 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Santuri (112 Nos.) (Tender No. 295/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000809/2020-2021 | 11/844325/2 | 12/04/2021 | 0 | M/S SAYAK BHATTACHARYA | 4.66 | 0 | 0
793 | Purulia Division | Raghunathpur Sub-Division | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Manpur, Habitation - Manpur (112 Nos.) (Tender No.-824/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-2 | VCH/000809/2021-2022 | BP-2021-22-226 | 03/02/2022 | 0 | CHAIL CONSTRUCTION | 1.36 | 0 | 0
794 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Upardih- (63 Nos.) (49 Nos.) (Tender No. 296/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-2 | VCH/000810/2020-2021 | 11/844325/3 | 12/04/2021 | 0 | UTTAM KUMAR DUTTA | 4.77 | 0 | 0
795 | Purulia Division | Raghunathpur Sub-Division | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). (Tender No.812/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-2 | VCH/000810/2021-2022 | BP-2021-22-225 | 03/02/2022 | 0 | AMIT PATHAK | 1.6 | 0 | 0
796 | Purulia Division | Raghunathpur Sub-Division | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-2 | VCH/001161/2021-2022 | BP-2021-22-363 | 28/03/2022 | 0 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0
797 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of UPVC Pipe line from Satra OHR site towards Satra Village & Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Arsha Block to supply drinking water of command area of Satra Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000017/2023-2024 | 546/PD | 12/04/2023 | 30 | SUBODH PRAMANIK | 7.41 | 7 | 0
798 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000215/2020-2021 | 10/PSD | 13/01/2021 | 45 | GYANRANJAN SEN | 4.66 | 0 | 65
799 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000234/2020-2021 | 17/PSD | 13/01/2021 | 45 | RAKSHIT ENTERPRISE | 4.48 | 0 | 100
800 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing & restoration of different works viz. Valve Chamber with replace of valve at OHR campus, Road cutting & restoration by concreting & Moorum spreading including M.S. Pipe placing as casing at different place of Satra W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000280/2021-2022 | 772/PD | 13/12/2021 | 30 | M/S SAWDESH ENTERPRISE | 3.52 | 3.3 | 95
801 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 150 mm dia DI pipe line for clear water rising main from Medical hall at Misirdih to Boosting pump house at Satra Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000281/2021-2022 | 1575/PD | 17/12/2021 | 90 | ANUDIP SAHA | 9.62 | 3.22 | 55
802 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. at Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000284/2021-2022 | 1578/PD | 17/12/2021 | 90 | SUBODH PRAMANIK | 10.25 | 9.05 | 90
803 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of UPVC pipe as distribution main from Misirdih more to East-West along the Tamna-Arsha road for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000286/2021-2022 | 1580/PD | 17/12/2021 | 90 | DEBASISH CHAKRABORTY | 6.73 | 0 | 100
804 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of UPVC pipe as distribution main (loop line) from Satra Junior High School to Satra Uppar Para for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000288/2021-2022 | 1582/PD | 17/12/2021 | 90 | SUBODH PRAMANIK | 9.87 | 1.39 | 65
805 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000289/2021-2022 | 1583/PD | 17/12/2021 | 45 | SUBODH PRAMANIK | 10.76 | 0.53 | 100
806 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000290/2021-2022 | 1592/PD | 17/12/2021 | 45 | BHAGABANDAS KUMAR | 7.17 | 0 | 100
807 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of damage pipe line including House Connection arrangement for the works related to JICA Assisted West Bengal Pipped Water Supply Project(Purulia) of Satra Water Supply Scheme under Arsha Block. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000339/2024-2025 | 1365/PD | 25/07/2024 | 60 | SUBODH PRAMANIK | 5.46 | 0 | 100
808 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Functional House hold Tap Connection (FHTC) & pipe line laying of different dia. Pipe in connection of Jal Jeevan Mission (JJM & Jal Swapna) Programme at Satra Village Uppar Para and adjacent area of Arsha Block to drinking water supply under augmentation at Satra Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000626/2022-2023 | 1396/PD | 01/09/2022 | 45 | SUBODH PRAMANIK | 18.74 | 16.77 | 100
809 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Additional work for Grouting on inside & outside of cell wall for repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. of Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000792/2022-2023 | 1639/PD | 03/11/2022 | 45 | M/S SAWDESH ENTERPRISE | 3.41 | 3.37 | 100
810 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of pump house for accommodating centrifugal pump for pumping of water from Satra Boosting Pump House site CWR to distribution zone of Satra water supply scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000863/2022-2023 | 1816/PD | 06/12/2022 | 30 | M/S SAWDESH ENTERPRISE | 16.77 | 0 | 100
811 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing, renovation & restoration of Pump house and Meter room including roof treatment & Boundary wall at satra river site & Boosting pump station of Satra W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000923/2022-2023 | 1930/PD | 22/12/2022 | 60 | SUBODH PRAMANIK | 12.92 | 0 | 100
812 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of 200 mm dia Vertical and Horizontal Tubewell & 100 mm dia G.I. collecting line upto M.S. Manifold with allied works due to flash flood of Satra W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001055/2022-2023 | 287/PD | 27/02/2023 | 30 | M/S SAWDESH ENTERPRISE | 2.69 | 2.68 | 0
813 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000006/2021-2022 | 1504/PD | 13/12/2021 | 0 | Resource Division | 58.03 | 0 | 0
814 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000015/2021-2022 | 392/PD | 11/03/2022 | 0 | Resource Division | 1.28 | 0 | 0
815 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Additional work for Extension of water supply pipe line towards Pitchkapahali, Garamthana, Lalbandh, Kishor Bharati Public School Adjacent to Patuara village from existing Satra W/s Scheme to meet up the water crisis under Jal Swapna Program. (Tender No.976/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000149/2022-2023 | BP-2022-23-33 | 20/04/2022 | 0 | SUBODH PRAMANIK | 12.45 | 0 | 0
816 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of UPVC pipe as distribution main from Misirdih More to East-West along the Tamna-Arsha Road for drinking water supply through FHTC to meet up the water crisis at Satra W/s Scheme under Jal Swapna Program. (Tender No.06/EE/PD of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000173/2022-2023 | BP-2022-23-55 | 19/05/2022 | 0 | DEBASISH CHAKRABORTY | 4.41 | 0 | 0
817 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 02 (Two) No. 200 mm dia river bed tube well (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with all allied works at Satra river site of Satra Water Supply Scheme under Purulia Division, PHE Dte. Phase-1 (Tender No- 870/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000909/2022-2023 | BP-2022-23-92 | 07/07/2022 | 0 | SUBODH PRAMANIK | 17.23 | 0 | 0
818 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Satra boosting pump house campus of Satra W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 862/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000959/2022-2023 | BP-2022-23-130 | 19/07/2022 | 0 | SUBODH PRAMANIK | 11.52 | 0 | 0
819 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.866/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001028/2022-2023 | BP-2022-23-336 | 29/09/2022 | 0 | SUBODH PRAMANIK | 8.57 | 0 | 0
820 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) (Tender No- 287/2020-21 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001088/2022-2023 | BP-2022-23-219 | 24/08/2022 | 0 | GYANRANJAN SEN | 0.7 | 0 | 0
821 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001139/2021-2022 | BP-2021-22-293 | 09/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0
822 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | providing Functional household tap Connection FHTC (leftout household) in connection with Jal Jeevan Mission (JJM & Jalswapna) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 877/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001178/2021-2022 | BP-2021-22-305 | 14/03/2022 | 0 | BHAGABANDAS KUMAR | 6.11 | 0 | 0
823 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | providing Functional household tap Connection FHTC in connection with Jal Jeevan Mission (JJM & Jalswapna) at Ramjibanpur Jhunjka, Layardih of Hensla G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 277/2020-21 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001179/2021-2022 | BP-2021-22-312 | 22/03/2022 | 0 | KANTILAL SAO | 20.32 | 0 | 0
824 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Satra Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2021-2022 | 163/PMD | 07/03/2022 | 30 | DEY ENTERPRISE | 20.5 | 12.28 | 85
825 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of two nos. submersible pumping machineries in newly constructed river bed tube well, voltage stabilizer with allied cable line and other allied works for augmentation of Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000095/2022-2023 | 521/PMD | 05/08/2022 | 30 | NUPUR CHANDRA HALDER | 22.86 | 21 | 92
826 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Centrifugal pumping machineries, floor mounted MCC panel, HOT Crane, Flow meter and other allied works at Satra high Lift (Boosting Station) for Augmentation of Satra Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000200/2023-2024 | 1190/PMD | 03/11/2023 | 90 | NUPUR CHANDRA HALDER | 43.54 | 0 | 85
827 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, augmentation of MCC panel, Flow meter and other allied works for augmentation of Satra (River side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000344/2022-2023 | 129/PMD | 20/02/2023 | 60 | NUPUR CHANDRA HALDER | 36.75 | 36.26 | 51
828 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries for river bed tube well with allied cable line and other allied works for Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000687/2024-2025 | 1699/PMD | 06/12/2024 | 30 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0
829 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000010/2023-2024 | 620/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
830 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SUPPLY DELIVERY & INSTT OF TWO NOS SUBMERSIBLE PUMP MOTOR SETS IN NEW CONSTRUCTED RIVERBED TUBE WELL AND LAYING OF DEPARTMENTALLY SUPPLIED CABLE LINE WITH OTHER ALLIED WORKS FOR SATRA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 326/21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000113/2022-2023 | C052221499438 | 11/05/2022 | 0 | NUPUR CHANDRA HALDER | 2.4 | 0 | 0
831 | Purulia Division | Purulia Sadar Sub-Division | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | Assistant Engineer |  | ORD/000009/2023-2024 | 537/PD | 12/04/2023 | 45 | MOONLIGHT HOUSE | 29.2 | 6.4 | 100
832 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | Assistant Engineer |  | ORD/000303/2022-2023 | 836/PD | 19/05/2022 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 13.12 | 100
833 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-I, II & Zone-V in different villages of Kumari, Boro-Jaragora, Dighi & Ankro-barakadam G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000333/2020-2021 | 243/PD | 10/02/2021 | 75 | ANUP KUMAR SAHA | 285.06 | 411.15 | 92
834 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-III & Zone-IV in different villages of Ankro-barakadam & Boro-Jaragora G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000334/2020-2021 | 244/PD | 10/02/2021 | 60 | SADHAN GORAIN | 132.5 | 155.6 | 100
835 | Purulia Division | Purulia Sadar Sub-Division | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000399/2022-2023 | 357/RNP | 01/06/2022 | 20 | ASHOK KUMAR CHATTERJEE | 1.76 | 0 | 100
836 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | Assistant Engineer |  | ORD/000608/2022-2023 | 517/PSD | 12/08/2022 | 40 | SADHAN GORAIN | 3.51 | 0 | 100
837 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office ,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-I, Zone-II & Zone-V of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-I) | Assistant Engineer |  | ORD/000613/2022-2023 | 510/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.8 | 0 | 70
838 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | Assistant Engineer |  | ORD/000614/2022-2023 | 511/PSD | 12/08/2022 | 45 | SADHAN GORAIN | 2.43 | 0 | 100
839 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Soil Investigation work for proposed WTP at Manbazar-II Block within within Purulia Sadar Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/001001/2022-2023 | 110/A/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
840 | Purulia Division | Purulia Sadar Sub-Division | Shifting of distribution pipe line including making temporary diversion alone Boro-Jamtara road for construction of house pipe culvert by PW (Road) protectorate of Zone II Manbazar II Block (Part) water supply scheme (Tender No- 20/2021-22 of EE/PD) | Assistant Engineer |  | VCH/000155/2022-2023 | BP-2022-23-13 | 07/04/2022 | 0 | PINAKI RANJAN MUKHERJEE | 1.23 | 0 | 0
841 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) for Zone- I, Zone- II & Zone- V in different village of Kumari, Boro Jaragora GP, Dighi GP & Ankro Barakadam GP under command area of Manbazar II block (part) water supply scheme of Manabazar II Block under Purulia Sadar Sub- Division, PHE Dte. under Purulia Division, PHE Dte. (Tender No- 34/2021-22 of SE/PMU/WBPWSP) | Assistant Engineer |  | VCH/000882/2022-2023 | BP-2022-23-67 | 01/07/2022 | 0 | ANUP KUMAR SAHA | 23.34 | 0 | 0
842 | Purulia Division | Purulia Sadar Sub-Division | Balance work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area Zone I, Zone II & Zone V of Manbazar II Block (Part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I) (Tender No- 162/2022-23 of EE/PD) | Assistant Engineer |  | VCH/001030/2022-2023 | BP-2022-23-347 | 30/09/2022 | 0 | ANUP KUMAR SAHA | 28.06 | 0 | 0
843 | Purulia Division | Raghunathpur Sub-Division | Refreshment bill paid for office meeting to Circuit House. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00575/2023-2024 | BP-2023-24-352 | 07/08/2023 | 0 | SHREEMA SWEETS | 0.22 | 0 | 0
844 | Purulia Division | Raghunathpur Sub-Division | Bill of the IEC programes done in 10 blocks during ARANYA SAPTAHA. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00676/2023-2024 | BP-2023-24-414 | 25/08/2023 | 0 | M/S SAYAK BHATTACHARYA | 0.97 | 0 | 0
845 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump House (8 mtr X 7.5 mtr) at Head Work Site under Para W/S Scheme of Raghunathpur Construction Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000094/2023-2024 | 832/PD | 26/06/2023 | 90 | GANGULY ENTERPRISES | 23.07 | 13 | 100
846 | Purulia Division | Raghunathpur Sub-Division | Connecting line with manifold at two nos Intake to Iron Elevation Plant of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000137/2024-2025 | 908/PD | 07/05/2024 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 8.8 | 0 | 100
847 | Purulia Division | Raghunathpur Sub-Division | Installation of 3000 mm dia X 1800 mm 2 Nos. Pressure Shell and Pressure Type Iron Elimination Plant for WTP at Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000175/2022-2023 | 792/PD | 05/05/2022 | 45 | ANUP KUMAR SAHA | 66.12 | 66.11 | 0
848 | Purulia Division | Raghunathpur Sub-Division | Work for Parrllel Distribution system with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. Part-II | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000181/2023-2024 | 997/PD | 26/07/2023 | 60 | NIBHAS SINHA | 95.82 | 91.19 | 100
849 | Purulia Division | Raghunathpur Sub-Division | Repairing of DI Rising Main & Sinking of 4(Four ) Nos. 200 mm dia DTH rigboredtubewell with 1 H.P. Submersible Pumping Machinary with allied works at Anara Girls' High School, Para S.N. High School, Dubra High School & Anara S.E. Railway Colony High School for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000223/2024-2025 | 1098/PD | 07/06/2024 | 60 | M/S SAYAK BHATTACHARYA | 22.57 | 0 | 100
850 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Clear water reservoir (CWR) of capacity 180 cum / 200 Cum with other allied works at Para Pump House site under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Divisioin, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000335/2022-2023 | 866/PD | 23/05/2022 | 100 | ADITYA HAZRA | 25.24 | 23.12 | 100
851 | Purulia Division | Raghunathpur Sub-Division | Construction of sump at Pump House of Para head work site under Aug. of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000350/2025-2026 | 428/RNP | 12/08/2025 | 7 | GANGULY ENTERPRISES | 0.49 | 0 | 0
852 | Purulia Division | Raghunathpur Sub-Division | Repairing of Pump House Cum Chlorine Room With Sanitary and Water Supply Arrangement at Tube Well Headwork Site under Para W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000366/2022-2023 | 329/RNP | 01/06/2022 | 21 | SABYASACHI MISHRA | 1.15 | 0 | 85
853 | Purulia Division | Raghunathpur Sub-Division | Construction of 3.60 mtr.X 3.00 mtr Blower Room at Para Water supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000369/2022-2023 | 328/RNP | 01/06/2022 | 90 | DEBDAT GANGULY | 4.04 | 2.83 | 0
854 | Purulia Division | Raghunathpur Sub-Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Para W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000387/2022-2023 | 339/RNP | 01/06/2022 | 30 | MOYTEC | 1.4 | 1.4 | 100
855 | Purulia Division | Raghunathpur Sub-Division | Bypass arrangement of Old rising main pipe line (Old OHR site ) to new rising main pipe line and new rising main pipe line to new OHR Inlet and distribution pipe line connection with all allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000461/2024-2025 | 1520/PD | 27/08/2024 | 45 | TAPAN CHANDRA | 6.63 | 0 | 100
856 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000501/2022-2023 | 1010/PD | 29/06/2022 | 45 | NIBHAS SINHA | 444.92 | 322.9 | 95
857 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000735/2022-2023 | 1253/PD | 30/08/2022 | 45 | MIDNAPUR PIPE CONCERN | 109.03 | 21.28 | 92
858 | Purulia Division | Raghunathpur Sub-Division | Construction of R.C.C. Elevated Reservoir, Capcaity 650 cum, Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000914/2022-2023 | 1888/PD | 15/12/2022 | 270 | NIBHAS SINHA | 151.46 | 56.79 | 100
859 | Purulia Division | Raghunathpur Sub-Division | Construction of 2 Nos. 3 mtr dia Intake well at Harai river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Para W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000917/2022-2023 | 1926/PD | 22/12/2022 | 90 | M/S KARUNAMOYEE CONSTRUCTION | 14.83 | 11.22 | 100
860 | Purulia Division | Raghunathpur Sub-Division | Laying of Clear Water Rising Main at Hariharpur area from intake to OHR under Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000979/2022-2023 | 84/PD | 17/01/2023 | 90 | TAPAN CHANDRA | 38.38 | 9.77 | 25
861 | Purulia Division | Raghunathpur Sub-Division | Supply, delivery fitting & fixing of 52 Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Hura & Para Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001152/2024-2025 | 2303/PD | 31/12/2024 | 60 | AMIT PATHAK | 4.75 | 0 | 100
862 | Purulia Division | Raghunathpur Sub-Division | Construction of Blower room and Other Allied Works at Para Head work Site of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001207/2024-2025 | 2331/PD | 31/12/2024 | 122 | RANI SATI CONSTRUCTION | 4.99 | 0 | 0
863 | Purulia Division | Raghunathpur Sub-Division | Laying distribution System with FHTC work (540Nos.), restoration of concrete road and with allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001689/2023-2024 | 1865/PD | 21/12/2023 | 60 | NIBHAS SINHA | 43.26 | 0 | 100
864 | Purulia Division | Raghunathpur Sub-Division | Sinking of 4 (Four) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Para W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001813/2023-2024 | 43/PD | 09/01/2024 | 45 | MANATOSH SINGH | 16.73 | 0 | 100
865 | Purulia Division | Raghunathpur Sub-Division | Supply, delivery fitting & fixing of 2 Nos. Scheme Description Sign boards (6' X 3') under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location :- (Hariharpur) & Head Work site (Hariharpur Basti) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/001930/2023-2024 | 23/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.34 | 0 | 0
866 | Purulia Division | Raghunathpur Sub-Division | Restoration of concrete check dam with Ancillary structure as and when needed at Harirampur Intake Site of Para W/S Scheme under Raghunathpur Sub-Division, Under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/003457/2023-2024 | 331/PD | 01/03/2024 | 45 | SAMAN KUMAR MAHATO | 39.52 | 0 | 100
867 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | RTOR000010/2022-2023 | 959/PD | 20/06/2022 | 0 | Resource Division | 19.57 | 0 | 0
868 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | RTOR000019/2022-2023 | 981/PD | 22/06/2022 | 0 | Resource Division | 176.36 | 0 | 0
869 | Purulia Division | Raghunathpur Sub-Division | Temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/000326/2022-2023 | BP-2022-23-171 | 11/08/2022 | 0 | NANIGOPAL DEY | 1.28 | 0 | 0
870 | Purulia Division | Raghunathpur Sub-Division | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/000327/2022-2023 |  | 03/08/2022 | 0 | NANIGOPAL DEY | 4.08 | 0 | 0
871 | Purulia Division | Raghunathpur Sub-Division | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Para W/S Scheme, Block- Para) ) to be augmentated/ retrofitting under Purulia Division, PHE Dte. (Tender No- 537/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/000917/2022-2023 | BP-2022-23-117 | 16/07/2022 | 0 | RADIANT | 6.26 | 0 | 0
872 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II (Tender No.48/22-23/SE/PMU/WBPWSP(P) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001023/2022-2023 | BP-2022-23-320 | 29/09/2022 | 0 | NIBHAS SINHA | 120.95 | 0 | 0
873 | Purulia Division | Raghunathpur Sub-Division | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I. (Tender No- 79/2022-23 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001067/2022-2023 | BP-2022-23-411 | 28/10/2022 | 0 | MIDNAPUR PIPE CONCERN | 16.62 | 0 | 0
874 | Purulia Division | Raghunathpur Sub-Division | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.233/EE/PD of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001097/2022-2023 | BP-2022-23-171 | 11/08/2022 | 0 | NANIGOPAL DEY | 4.08 | 0 | 0
875 | Purulia Division | Raghunathpur Sub-Division | Repairing of pump house cum chlorine room with sanitary and water supply arrangement at T/W head work site under Para W/s Scheme of Raghunathpur Sub- Division, PHE Dte. [Tender No 215/2022-23 of EE/PD] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001539/2022-2023 | BP-2022-23-685 | 01/03/2023 | 0 | SABYASACHI MISHRA | 0.82 | 0 | 0
876 | Purulia Division | Raghunathpur Sub-Division | Car bill paid for office purpose against Reg. No.WB-55A/7171 paid for the month of Nov & Dec,23. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001900/2022-2023 | BP-2023-24-53 | 28/04/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
877 | Purulia Division | Raghunathpur Sub-Division | Car bill for office purpose against vehicle reg. no.WB-55A/4524 & paid for the month of June to Aug,2022. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | VCH/001903/2022-2023 | BP-2023-24-57 | 04/05/2023 | 0 | ANUP KUMAR SAHA | 1.17 | 0 | 0
878 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of para W/S | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00247/2023-2024 | BP-23-24-151 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
879 | Purulia Mechanical | Raghunathpur Sub-Division | Internal and external illumination with other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000017/2023-2024 | 388/PMD | 06/04/2023 | 802 | M/S KARUNAMOYEE CONSTRUCTION | 5.33 | 0 | 40
880 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Para (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000038/2023-2024 | 444/PMD | 20/04/2023 | 30 | MS SAJAHAN CHOWDHURY | 21.63 | 0 | 100
881 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, backwash pumping machineries, MCC panel, H.O.T., Flowmwter and other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000373/2022-2023 | 203/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 76.22 | 13.88 | 100
882 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Para w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000374/2022-2023 | 204/PMD | 28/02/2023 | 60 | PINTU DEY | 10.13 | 4.41 | 100
883 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Para water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000375/2022-2023 | 205/PMD | 28/02/2023 | 60 | M/S D. PALIT & CO. | 15.06 | 0 | 100
884 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and laying of 185 sq mm XLPE cable at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000592/2024-2025 | 1450/PMD | 01/10/2024 | 30 | SUMIT KUMAR CHAKRABORTY | 4.24 | 0 | 100
885 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and Delivery and installation intake well cover & allied work at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000679/2024-2025 | 1691/PMD | 06/12/2024 | 30 | PINTU DEY | 2.04 | 0 | 100
886 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at para water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000686/2024-2025 | 1698/PMD | 06/12/2024 | 90 | KAMAKHYA ENTERPRISE | 15.46 | 0 | 0
887 | Purulia Division | Purulia Sadar Sub-Division | Laying of Distribution Pipeline From Rightgora OHR to Rithugora Village More to Connect DI Pipeline under JJM Work under Bandwan Water Supply Scheme under Purulia Dividion ,PHE Dte | Assistant Engineer |  | ORD/000187/2025-2026 | 1048/PD | 17/06/2025 | 45 | BOSE CONSTRUCTION | 4.4 | 0 | 100
888 | Purulia Division | Purulia Sadar Sub-Division | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer |  | ORD/000338/2024-2025 | 1364/PD | 25/07/2024 | 240 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 50
889 | Purulia Division | Purulia Sadar Sub-Division | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 712 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bandwan W/S Scheme for source augmentation | Assistant Engineer |  | ORD/000539/2023-2024 | 1340/PD | 08/09/2023 | 182 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 260.9 | 0 | 85
890 | Purulia Division | Purulia Sadar Sub-Division | Laying of parallel distribution pipeline to provide FHTC at Supudih Mouza of Bandwan Water Supply Scheme under Purulia Division, PHE Dte . | Assistant Engineer |  | ORD/001053/2022-2023 | 285/PD | 27/02/2023 | 45 | BANERJEE CONSTRUCTION | 11.66 | 0 | 100
891 | Purulia Division | Purulia Sadar Sub-Division | Construction of WBSEDCL Room of Bandwan W/S Scheme and and Other allied works under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003459/2023-2024 | 333/PD | 01/03/2024 | 90 | ROY CONSTRUCTION | 6.15 | 0 | 100
892 | Purulia Mechanical | Purulia Sadar Sub-Division | Different Electro-Mechanical works at Sub-Station at Bundwan under Augmentation of Bundwan Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | Assistant Engineer |  | ORD/000041/2024-2025 | 954/PMD | 19/06/2024 | 90 | M S ENTERPRISE | 30.22 | 0 | 100
893 | Purulia Mechanical | Purulia Sadar Sub-Division | Arrangement for high pressure testing of SubStation equipment for 250 KVA Sub - Station at Bundwan w/s Scheme under Purulia Mechanical Division,PHE,Dte. | Assistant Engineer |  | ORD/000079/2024-2025 | 1016/PMD | 25/06/2024 | 30 | M S ENTERPRISE | 1.19 | 0 | 100
894 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Route Survey & Drawing Preparation for uncovered areas under BAGHMUNDI Block under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000003/2023-2024 | 524/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.16 | 3.92 | 100
895 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Pump house cum switch room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000499/2023-2024 | 1333/PD | 08/09/2023 | 30 | S PATHAK AND CO | 2.89 | 0 | 100
896 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 421 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bagmundi W/S Scheme for source augmentation | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000546/2023-2024 | 1338/PD | 08/09/2023 | 182 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 227.9 | 0 | 5
897 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of pathway at OHR Site of Bugmundi W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/003458/2023-2024 | 332/PD | 01/03/2024 | 45 | ROY CONSTRUCTION | 2.21 | 0 | 100
898 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & fitting fixing of Main switch, valve and other electro-mechanical accessories at WTP site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000057/2024-2025 | 975/PMD | 20/06/2024 | 60 | SUBRATA DUTTA | 3.98 | 0 | 100
899 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machinery, Voltage stabilizer with other allied work for direct pumping at OHR site of Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000109/2024-2025 | 1173/PMD | 31/07/2024 | 478 | PINTU DEY | 29.04 | 0 | 25
900 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Bagmundi w/s scheme for under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000227/2023-2024 | 1205/PMD | 03/11/2023 | 120 | BISHWANATH NANDI | 7.74 | 0 | 100
901 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & delivery of electric cable at Bagmundi water supply scheme for Augmentation of Bagmundi PWSS under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000303/2023-2024 | 385/PMSD(W/S) | 17/10/2023 | 15 | SEN BROTHERS | 0.92 | 0 | 100
902 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
903 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Xerox copy of original DPR, drawings, mouza map etc for office purpose | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00557/2024-2025 | BP-2024-25-319 | 20/08/2024 | 0 | DUTTA XEROX CENTRE | 1.45 | 0 | 0
904 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Hiring charges of broadband at Assistant Engineer, Purulia Sadar Sub- Division, PHE Office | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00583/2024-2025 | BP-2024-25-334 | 27/08/2024 | 0 | PURULIA CABLE & BRODBAND PARISEVA | 0.13 | 0 | 0
905 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply of Tender register, HR (Materials) & contractor ledger (Including Printing & Binding complete set). | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00831/2023-2024 | BP-2023-24-532 | 07/10/2023 | 0 | SOMA PRINTING HOUSE | 0.1 | 0 | 0
906 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza- Bathanbari,Bhurkundabari under Gunyarae G.P). (1029 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000270/2020-2021 | 155/PD | 01/02/2021 | 45 | DEBAKI RANJAN SARKAR | 52.24 | 10.07 | 0
907 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0.88 | 100
908 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of swtich room cum chlorine Room at OHR site of Bathanbari W/S Scheme within Raghunathpur Sub- Division (Tender No- 828/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000178/2022-2023 | BP-2022-23-54 | 19/05/2022 | 0 | KHITISH CHANDRA PATHAK | 4.18 | 0 | 0
909 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No-935/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000182/2022-2023 | BP-2022-23-65 | 24/05/2022 | 0 | KHITISH CHANDRA PATHAK | 4.04 | 0 | 0
910 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing & renovation of RCC elevated reservoir of capacity 33000 Galon and other allied works under Bathanbari W/ S Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 936/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000942/2022-2023 | BP-2022-23-103 | 16/07/2022 | 0 | KHITISH CHANDRA PATHAK | 9.76 | 0 | 0
911 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bathanbari W/S Scheme of Neturia Block Raghunathpur Sub- Division, PHE Dte. (Tender No-348/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/001096/2022-2023 | BP-2022-23-192 | 11/08/2022 | 0 | KHITISH CHANDRA PATHAK | 4.06 | 0 | 0
912 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/001144/2021-2022 | BP-2021-22-300 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0
913 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bathanbari Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000075/2021-2022 | 160/PMD | 07/03/2022 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 20.5 | 4.38 | 100
914 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply Delivery and installation of Submersible pumping machinery, MCC Panel, Voltage stabilizer, flow meter, ilumination arrangement with allied works for augmentation of Bathanbari PWSS under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000092/2022-2023 | 518/PMD | 05/08/2022 | 60 | COMBINE ENTERPRISES | 46.66 | 40.38 | 82
915 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of fabricated M.S. structure barge with others allied works at Augmentation of Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000210/2022-2023 | 192/PMSD (W/S) | 22/06/2022 | 21 | COMBINE ENTERPRISES | 4.27 | 3.29 | 80
916 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & delivery of submersible pumping machinery at Bathanbari w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000263/2023-2024 | 1234/PMD | 08/11/2023 | 15 | COMBINE ENTERPRISES | 0.68 | 0 | 100
917 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Lagda, Dimdiha, Sonaijuri GP in Purulia-I Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000324/2022-2023 | 23/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
918 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Udyeshpur GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000325/2022-2023 | 24/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
919 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Dubra, Para GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000327/2022-2023 | 19/PMSD (Drilling) | 31/01/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
920 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Joradih GP in Raghunathpur-II Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000330/2022-2023 | 26/PMSD (Drilling) | 02/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
921 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 50
922 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and delivery of submersible pump motor sets at Bathanbari W/S scheme under PMD P.H.E Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000481/2023-2024 | 197/PMD | 16/02/2024 | 15 | PINTU DEY | 0.6 | 0 | 100
923 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and delivery of submersible pump motor sets at Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000495/2023-2024 | 343/PMD | 28/02/2024 | 15 | S PATHAK AND CO | 0.6 | 0 | 100
924 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Hose pipes and other works at Bathanbari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000531/2023-2024 | 436/PMD | 11/03/2024 | 60 | ANUP KUMAR SAHA | 15.88 | 0 | 50
925 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BATHANBARI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 347 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000087/2022-2023 | C042211590242 | 08/04/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 12.27 | 0 | 0
926 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1kg/hr gaseous chlorination system of Aug. of Bathanbari water supply scheme.(Tr.no 347 of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000512/2022-2023 | C112206903482 | 10/11/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 3.84 | 0 | 0
927 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000203/2024-2025 | 900/PD | 07/05/2024 | 60 | STABILITY INFRASTRUCTURE PVT. LTD. | 96.08 | 0 | 0
928 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000204/2024-2025 | 901/PD | 07/05/2024 | 60 | M/S ANMOL ENGICON | 96.02 | 0 | 0
929 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VI) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000205/2024-2025 | 902/PD | 07/05/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 94.42 | 0 | 0
930 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IX) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Area) | Assistant Engineer |  | ORD/000220/2024-2025 | 1072/PD | 07/06/2024 | 60 | SAROJ KUMAR SINGH | 96.58 | 0 | 0
931 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000221/2024-2025 | 1095/PD | 07/06/2024 | 60 | SUBRATA MAHAPATRA | 25.01 | 0 | 0
932 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. (Ajodhya Hill Area) | Assistant Engineer |  | ORD/000230/2024-2025 | 1065/PD | 07/06/2024 | 360 | VIVEKANANDA CONSTRUCTION | 94.95 | 0 | 35
933 | Purulia Division | Purulia Sadar Sub-Division | Construction of New Boundary wall and other allied works at Manbazar Riversite (Harekishtapur) under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000236/2024-2025 | 1077/PD | 07/06/2024 | 60 | CHANDAN CHATTERJEE | 31.23 | 0 | 0
934 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Araea) | Assistant Engineer |  | ORD/000259/2024-2025 | 1071/PD | 07/06/2024 | 60 | SHREYA ENTERPRISES | 94.55 | 0 | 0
935 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000341/2024-2025 | 1367/PD | 25/07/2024 | 30 | KOUSHIK CHATTERJEE | 20.13 | 0 | 0
936 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-X) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000486/2024-2025 | 1073/PD | 07/06/2024 | 60 | SAIKAT RAY | 95.21 | 0 | 0
937 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-V & VI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 4) | Assistant Engineer |  | ORD/000761/2023-2024 | 1367/PD | 14/09/2023 | 675 | ANUP KUMAR SAHA | 647.66 | 0 | 0
938 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 12) | Assistant Engineer |  | ORD/000762/2023-2024 | 1368/PD | 14/09/2023 | 995 | ANUP KUMAR SAHA | 449.89 | 0 | 70
939 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-X & XI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 7) | Assistant Engineer |  | ORD/000763/2023-2024 | 1369/PD | 14/09/2023 | 995 | ANUP KUMAR SAHA | 854.21 | 0 | 70
940 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL - 4) | Assistant Engineer |  | ORD/000764/2023-2024 | 1370/PD | 14/09/2023 | 1083 | SAMAN KUMAR MAHATO | 184.53 | 0 | 40
941 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-III & IV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 3) | Assistant Engineer |  | ORD/000765/2023-2024 | 1371/PD | 14/09/2023 | 945 | ANUP KUMAR SAHA | 671.47 | 0 | 40
942 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Opearation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector ) under Purulia Divn. PHE Dte. (SL-11) | Assistant Engineer |  | ORD/000777/2023-2024 | 1419/PD | 29/09/2023 | 405 | MS D.PALIT AND CO. | 400.45 | 0 | 10
943 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL-2) | Assistant Engineer |  | ORD/000781/2023-2024 | 1421/PD | 29/09/2023 | 540 | MS D.PALIT AND CO. | 478.83 | 0 | 75
944 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the peroid of thirty six (36) month at Zone- VII & VIII of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 3) | Assistant Engineer |  | ORD/000797/2023-2024 | 1430/PD | 29/09/2023 | 1080 | ANUP KUMAR SAHA | 649.84 | 0 | 55
945 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte. (SL-8) | Assistant Engineer |  | ORD/000801/2023-2024 | 1431/PD | 29/09/2023 | 270 | MD AAMIR KHAN | 552.37 | 0 | 0
946 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XIV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (3rd Call) | Assistant Engineer |  | ORD/002260/2023-2024 | 146/PD | 29/01/2024 | 3240 | ANUP KUMAR SAHA | 247.75 | 0 | 10
947 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003527/2023-2024 | 353/PD | 04/03/2024 | 60 | PRIYATOSH MUKHERJEE | 20.95 | 0 | 100
948 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000004/2023-2024 | 1128/PD | 17/08/2023 | 0 | Resource Division | 8279.54 | 0 | 0
949 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000036/2024-2025 | 1979/PD | 18/11/2024 | 0 | Resource Division | 8491.44 | 0 | 0
950 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000040/2024-2025 | 2254/PD | 19/12/2024 | 0 | Resource Division | 5956.59 | 0 | 0
951 | Purulia Mechanical | Purulia Sadar Sub-Division | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/05/25 to 28/10/25)" | Assistant Engineer |  | ORD/000021/2025-2026 | 76/PMSD(Drilling) | 28/04/2025 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0
952 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000095/2024-2025 | 1053/PMD | 28/06/2024 | 365 | DAS ENTERPRISE | 50.63 | 0 | 0
953 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000096/2024-2025 | 1054/PMD | 28/06/2024 | 365 | M/S S.G.ENTERPRISE | 31.65 | 0 | 0
954 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000097/2024-2025 | 1055/PMD | 28/06/2024 | 365 | ANUP KUMAR SAHA | 50.65 | 0 | 0
955 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000098/2024-2025 | 1056/PMD | 28/06/2024 | 365 | RABINDRA NATH KHAN | 25.32 | 0 | 0
956 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000513/2023-2024 | 515/PMD | 15/03/2024 | 365 | COMBINE ENTERPRISES | 154.79 | 0 | 0
957 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000514/2023-2024 | 516/PMD | 15/03/2024 | 365 | GOENKA ENTERPRISE | 258.09 | 0 | 0
958 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000515/2023-2024 | 517/PMD | 15/03/2024 | 365 | SINHA ELECTRICALS | 206.55 | 0 | 0
959 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000518/2023-2024 | 479/PMD | 14/03/2024 | 365 | SUBRATA DUTTA | 69.61 | 0 | 0
960 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000519/2023-2024 | 480/PMD | 14/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 69.58 | 0 | 0
961 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000520/2023-2024 | 481/PMD | 14/03/2024 | 365 | RABINDRA NATH KHAN | 109.36 | 0 | 0
962 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000521/2023-2024 | 482/PMD | 14/03/2024 | 365 | M/S D.G.B.ENTERPRISE | 39.77 | 0 | 0
963 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000674/2024-2025 | 1680/PMD | 05/12/2024 | 365 | SUBRATA DUTTA | 3.88 | 0 | 0
964 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000675/2024-2025 | 1681/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 3.88 | 0 | 0
965 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000676/2024-2025 | 1682/PMD | 05/12/2024 | 365 | RABINDRA NATH KHAN | 6.1 | 0 | 0
966 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000677/2024-2025 | 1683/PMD | 05/12/2024 | 365 | PINTU DEY | 2.22 | 0 | 0
967 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte.(2nd Call) | Assistant Engineer |  | ORD/000701/2024-2025 | 1740/PMD | 16/12/2024 | 365 | R.N.S. TRADING | 470.76 | 0 | 0
968 | Purulia Mechanical | Purulia Sadar Sub-Division | Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/11/24 to 30/04/25) | Assistant Engineer |  | ORD/000779/2024-2025 | 473/PMSD(Drilling) | 24/09/2024 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0
969 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
970 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of Pump house, Chlorine room, Toilet & Construction of Boundary wall and Other allied works at Sirkabad Riversite Site under Sirkabad W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000084/2023-2024 | 840/PD | 26/06/2023 | 455 | SK ABBAS | 15.07 | 0 | 100
971 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Installation of Street light , Laying of Cable trench, and other electrification works at Sirkabad OHR Site Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000182/2023-2024 | 4677/PSD | 27/07/2023 | 15 | CHATTERJEE CONSTRUCTION | 0.96 | 0.96 | 100
972 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of underground Cable trench from Sirkabad lab to OHR and Installation of Street light and other allied works at Sirkabad OHR Site Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000183/2023-2024 | 4678/PSD | 27/07/2023 | 15 | CHATTERJEE CONSTRUCTION | 0.85 | 0.85 | 100
973 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000349/2021-2022 | 99/PD | 18/01/2022 | 70 | ALOK KUMAR CHAKRABORTY | 63.49 | 0 | 85
974 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000350/2021-2022 | 100/PD | 18/01/2022 | 45 | HIRAK KUMAR SAO | 39.45 | 0 | 98
975 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Bhelaidih) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000351/2021-2022 | 101/PD | 18/01/2022 | 30 | SK MANIR | 13.92 | 12.1 | 90
976 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Gandhabazar) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000352/2021-2022 | 102/PD | 18/01/2022 | 60 | HIRAK KUMAR SAO | 45.46 | 45.44 | 60
977 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000353/2021-2022 | 103/PD | 18/01/2022 | 60 | KANTILAL SAO | 71.76 | 0 | 100
978 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 1 (one) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000409/2021-2022 | 330/PD | 28/02/2022 | 45 | HIRAK KUMAR SAO | 6.82 | 4.88 | 60
979 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000420/2021-2022 | 313/PD | 25/02/2022 | 45 | DEBAKI RANJAN SARKAR | 190.82 | 46.35 | 95
980 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000492/2021-2022 | 525/PD | 30/03/2022 | 30 | HIRAK KUMAR SAO | 12.95 | 7.9 | 0
981 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe for Distribution System for augumentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-(Sirkabad Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000630/2022-2023 | 1398/PD | 01/09/2022 | 45 | DEBAKI RANJAN SARKAR | 22.15 | 0 | 0
982 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-Bhelaidih,Gandhabazar,Aharrah)) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000631/2022-2023 | 1399/PD | 01/09/2022 | 60 | HIRAK KUMAR SAO | 44.91 | 41.59 | 100
983 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Boundary wall at Sirkabad OHR Site under Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001035/2022-2023 | 243/PD | 20/02/2023 | 45 | DILIP KUMAR MAHATO | 26.71 | 0 | 100
984 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line & Branch line under command area of Sirkabad Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Aharrah Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001054/2022-2023 | 286/PD | 27/02/2023 | 500 | KANTILAL SAO | 8.44 | 6.21 | 100
985 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Collecting line from Bandu Riverbed to Sirkabad Pump House of Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001091/2022-2023 | 357/PD | 14/03/2023 | 30 | HIRAK KUMAR SAO | 9 | 8.98 | 0
986 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 07 (Seven) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Sirkabad W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001093/2022-2023 | 360/PD | 14/03/2023 | 45 | HIRAK KUMAR SAO | 80.83 | 19.63 | 100
987 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and renovation of the damaged eleveted water reservoir at Sirkabad OHR Site under Sirkabad W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001095/2022-2023 | 362/PD | 14/03/2023 | 510 | SEKH IRFAN | 10.84 | 0 | 80
988 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000003/2021-2022 | 1506/PD | 13/12/2021 | 0 | Resource Division | 65.38 | 0 | 0
989 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000019/2021-2022 | 397/PD | 11/03/2022 | 0 | Resource Division | 0.76 | 0 | 0
990 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) (Tender No.903/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000150/2022-2023 | BP-2022-23-17 | 07/04/2022 | 0 | ALOK KUMAR CHAKRABORTY | 18.18 | 0 | 0
991 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and supplying & laying of HDPE Pipe for distribution system of Sirkabad Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. (Mouza- Upar Jambad) (Tender No- 903/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000991/2022-2023 | BP-2022-23-157 | 26/07/2022 | 0 | ALOK KUMAR CHAKRABORTY | 31.29 | 0 | 0
992 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001061/2022-2023 | BP-2022-23-407 | 20/10/2022 | 0 | HIRAK KUMAR SAO | 20.64 | 0 | 0
993 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) (Tender No- 24/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001110/2021-2022 | BP-2021-22-379 | 29/03/2022 | 0 | DEBAKI RANJAN SARKAR | 53.62 | 0 | 0
994 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) (Tender No.917/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001126/2021-2022 | BP-2021-22-373 | 27/03/2022 | 0 | KANTILAL SAO | 31.64 | 0 | 0
995 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work order for Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Sirkabad W/S Scheme & Puncha W/S Scheme Block- Puncha) to be Augmentation/ Rejuvenation (Tender No- 850/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001174/2021-2022 | BP-2021-22-323 | 22/03/2022 | 0 | MRS. R DUTTA & COMPANY | 3.45 | 0 | 0
996 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001218/2021-2022 | BP-2021-22-352 | 28/03/2022 | 0 | HIRAK KUMAR SAO | 17.27 | 0 | 0
997 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work order for the work of vendering service relating to E-return for Income Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f. 01/10/2022 to 30/09/2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001922/2022-2023 | BP-2023-24-116 | 22/05/2023 | 0 | NIGAM CONSULTANCY SERVICE | 0.67 | 0 | 0
998 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | NEW CONNECTION FOR AUGMENTATION OF SIRKABAD | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00477/2023-2024 | BP-23-24-249 | 04/01/2024 | 0 | WBSEDCL PURULIA | 7.42 | 0 | 0
999 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and lowering of submersible pump motor sets at newly constructed River Bed Tubewell with supply of necessary substitute at Sirkabad water supply scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000025/2023-2024 | 410/PMD | 10/04/2023 | 632 | M/S S.G.ENTERPRISE | 26.76 | 10.41 | 40
1000 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Flowmeter at Sirkabad water supply scheme under , PMD, PHE;Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000035/2023-2024 | 440/PMD | 19/04/2023 | 623 | BISHWANATH NANDI | 4.67 | 0 | 80
1001 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible Pump motor and other related works at Sirkabad w/s scheme under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000043/2024-2025 | 956/PMD | 19/06/2024 | 90 | RABINDRA NATH KHAN | 3.88 | 0 | 70
1002 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Yard lighting arrangement with others allied work at Sirkabad water supply scheme (Pump house & OHR site) for Augmentation of Sirkabad PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000062/2024-2025 | 991/PMD | 21/06/2024 | 178 | ASISH KR. SEN | 11.2 | 0 | 80
1003 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sirkabad Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2021-2022 | 167/PMD | 07/03/2022 | 30 | MAHADEV ENTERPRISE | 20.89 | 20.58 | 100
1004 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Centrifugal pumping machineries with necessary substitutes and allied works at Augmentation of SIRKABAD W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000444/2022-2023 | 263/PMD | 06/03/2023 | 60 | RABINDRA NATH KHAN | 56.33 | 34.99 | 70
1005 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at Sirkabad W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000446/2022-2023 | 265/PMD | 06/03/2023 | 60 | GOUTAM CHAKRABORTY | 12.75 | 9.4 | 75
1006 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and laying of Cable of river bed tube well with other allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000580/2024-2025 | 1438/PMD | 01/10/2024 | 30 | M/S S.G.ENTERPRISE | 2.91 | 0 | 50
1007 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of Submersible Pump of river bed tube well, Flowmeter & Water level transmiter with others allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000640/2024-2025 | 1572/PMD | 14/11/2024 | 90 | M/S D. PALIT & CO. | 22.94 | 0 | 0
1008 | Purulia Division | Raghunathpur Sub-Division | Rig Bored Tubewell by DTH Method of Lachhyara Piped Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000322/2021-2022 | 34/PD | 05/01/2022 | 45 | ASHOK KUMAR CHATTERJEE | 19.43 | 2.52 | 100
1009 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room Cum Chlorine Room of Lachhyara Pipe Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000338/2021-2022 | 54/PD | 13/01/2022 | 100 | ASHOK KUMAR CHATTERJEE | 4.89 | 0 | 100
1010 | Purulia Division | Raghunathpur Sub-Division | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000339/2021-2022 | 55/PD | 13/01/2022 | 1234 | ASHOK KUMAR CHATTERJEE | 85.67 | 10.72 | 82
1011 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra W/S Scheme, Block ¿ Para, & Lachhiyara W/S Schem, Block ¿ Raghunathpur - II) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000442/2020-2021 | 357/G/PD | 25/02/2021 | 30 | STEELCONC AND ASSOCIATES | 4.78 | 2.84 | 65
1012 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room at Lachhiyara OHR Site of Lachhiyara W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000853/2022-2023 | 1746/PD | 22/11/2022 | 90 | TOTAL INFRA | 19.83 | 14.64 | 100
1013 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Lachhiyara OHR campus of Lachhiyara W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000854/2022-2023 | 1752/PD | 22/11/2022 | 30 | ASHOK KUMAR CHATTERJEE | 18.32 | 0 | 100
1014 | Purulia Division | Raghunathpur Sub-Division | Detail Cost Estimate for Over Head Reservoir of capacity 100 cum of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Diviasion under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000927/2022-2023 | 1933/PD | 22/12/2022 | 270 | KM ENTERPRISES | 60.72 | 34.39 | 100
1015 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | RTOR000018/2022-2023 | 980/PD | 22/06/2022 | 0 | Resource Division | 45.39 | 0 | 0
1016 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | RTOR000022/2021-2022 | 391/PD | 11/03/2022 | 0 | Resource Division | 22.76 | 0 | 0
1017 | Purulia Division | Raghunathpur Sub-Division | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.965/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000131/2022-2023 | BP-2022-23-9 | 05/04/2022 | 0 | ASHOK KUMAR CHATTERJEE | 23.96 | 0 | 0
1018 | Purulia Division | Raghunathpur Sub-Division | Repairing & renovation of existing pump house cum store room & boundary wall of Lachhyara Piped Water Supply Scheme (Tender No- 968/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000154/2022-2023 | BP-2022-23-12 | 07/04/2022 | 0 | ASHOK KUMAR CHATTERJEE | 1.12 | 0 | 0
1019 | Purulia Division | Raghunathpur Sub-Division | Distribution system of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte (Tender No- 965/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000973/2022-2023 | BP-2022-23-143 | 21/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 25.34 | 0 | 0
1020 | Purulia Division | Raghunathpur Sub-Division | Rig Board Tubewell by DTH Method of Lachhiyara piped W/s Scheme. (Tender No.958/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001167/2021-2022 | BP-2021-22-362 | 28/03/2022 | 0 | ASHOK KUMAR CHATTERJEE | 16.91 | 0 | 0
1021 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | BILL/00454/2023-2024 | BP-23-24-223 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.87 | 0 | 0
1022 | Purulia Mechanical | Raghunathpur Sub-Division | Supply,delivery and installation of Submersible pumping machineries and Al. Armoured cables for Augmentation of Lachhiyar W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000069/2024-2025 | 997/PMD | 21/06/2024 | 60 | M/S UJJAL DIESEL SERVICE | 2.83 | 0 | 74
1023 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lachayara Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000091/2021-2022 | 189/PMD | 14/03/2022 | 1022 | M/S ESTERN INDIA SALES AND SERVICE | 20.62 | 13.93 | 80
1024 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting arrangement with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000186/2023-2024 | 1176/PMD | 03/11/2023 | 60 | MOUSUMI BENERJEE | 5.02 | 0 | 76
1025 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation submersible pumping machineries at new deep tube well and laying of cable line, with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000301/2022-2023 | 90/PMD | 03/02/2023 | 708 | KOUSHIK CHATTERJEE | 32.79 | 15.21 | 50
1026 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000302/2022-2023 | 91/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 51.57 | 0 | 35
1027 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 60KVA oil cooled voltage stabilizer and allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000304/2022-2023 | 92/PMD | 03/02/2023 | 60 | EMCON | 6.79 | 0 | 75
1028 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of 30KVA oil cooled voltage stabilizer(at OLD Pump house) and Double tank dosing system Miscellaneous works at under Lachhiyara W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000639/2024-2025 | 1571/PMD | 14/11/2024 | 60 | TAPAN KUMAR DEY | 6.97 | 0 | 0
1029 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00087/2022-2023 | BP-2022-23-5174 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 7.37 | 0 | 0
1030 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000273/2021-2022 | 1549/PD | 15/12/2021 | 90 | BHAGABANDAS KUMAR | 10.72 | 0 | 100
1031 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 100 cum and staging height 20 mtr. with including supply of all labour & materials for Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000275/2021-2022 | 1550/PD | 15/12/2021 | 270 | KOUSHIK CHATTERJEE | 43.13 | 37.59 | 100
1032 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room from Chitmu Pump House to distribution area through distribution main of Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000276/2021-2022 | 1551/PD | 15/12/2021 | 90 | BHAGABANDAS KUMAR | 16.63 | 0 | 100
1033 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000405/2021-2022 | 284/PD | 17/02/2022 | 774 | MS D.PALIT AND CO. | 140.81 | 34.77 | 100
1034 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Additional work for laying 63 mm dia(OD) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Chitmu mouza under Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000503/2022-2023 | 439/PSD | 24/06/2022 | 15 | MS D.PALIT AND CO. | 3.31 | 3.04 | 95
1035 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work for Soil Investigation work for proposed 100 M3 capacity Over Head Reservoir of Chitmu W/S Scheme under Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001002/2022-2023 | 111/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.53 | 0
1036 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of damaged pipe line & Stand post at different location and construction of new stand post at primary school & ICDS center of Chitmu village to supply drinking water under Chitmu Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001050/2022-2023 | 282/PD | 27/02/2023 | 20 | BHAGABANDAS KUMAR | 1.23 | 1.23 | 0
1037 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Boundary wall with other allied works at OHR site of Chitmu W/S Scheme under Purulia Sadar Sub-Division of Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001130/2022-2023 | 410/PD | 21/03/2023 | 45 | SAZID HOSSEN ANSARI | 16.07 | 0 | 100
1038 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000008/2021-2022 | 1505/PD | 13/12/2021 | 0 | Resource Division | 10.96 | 0 | 0
1039 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000013/2021-2022 | 388/PD | 11/03/2022 | 0 | Resource Division | 7.56 | 0 | 0
1040 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No-22/2021-22 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000944/2022-2023 | BP-2022-23-100 | 16/07/2022 | 0 | MS D.PALIT AND CO. | 22.49 | 0 | 0
1041 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No.873/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001011/2022-2023 | BP-2022-23-272 | 21/09/2022 | 0 | BHAGABANDAS KUMAR | 7.79 | 0 | 0
1042 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001130/2021-2022 | BP-2021-22-366 | 29/03/2022 | 0 | MS D.PALIT AND CO. | 19.51 | 0 | 0
1043 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chitmu W/S Scheme Blalarampur W/s Scheme (Zone-I) Block Jhalda-II & Balarampur) to be Augmented / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.358/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001212/2021-2022 | BP-2021-22-372 | 29/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.39 | 0 | 0
1044 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Full deposit scheme for Chitmu water pump under Jhalda CCC | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00253/2023-2024 | BP-2023-24-147 | 15/09/2023 | 0 | WBSEDCL PURULIA | 2.45 | 0 | 0
1045 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Chitmu W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2021-2022 | 20/PMD | 19/01/2022 | 45 | M/S D. PALIT & CO. | 30.6 | 27.21 | 0
1046 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Flowmeter & 50KVA voltage stabilizer and with others allied works at Chitmu water supply scheme under , PMD, PHE;Dte.in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2023-2024 | 387/PMD | 06/04/2023 | 60 | M/S UJJAL DIESEL SERVICE | 7.49 | 0 | 100
1047 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of pumping machineries with Allied works at Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000022/2022-2023 | 306/PMD | 06/05/2022 | 30 | RABINDRA NATH KHAN | 35.6 | 29.77 | 85
1048 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machineries,, with all ancillaries & auxiliaries including allied works at CWR side pump house at Chitmu Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000023/2023-2024 | 394/PMD | 06/04/2023 | 60 | M S ENTERPRISE | 33.26 | 0 | 100
1049 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Chitmu Water Supply scheme Block Jhalda-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000083/2021-2022 | 168/PMD | 07/03/2022 | 30 | CINZANO | 20.5 | 13.97 | 100
1050 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of lighting arrangement at pump house with other allied works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000179/2023-2024 | 1150/PMD | 17/10/2023 | 30 | M/S UJJAL DIESEL SERVICE | 4.75 | 0 | 100
1051 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 2 MT capacity HOT Crane with other allied works for Augmentation of Chitmu Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000204/2023-2024 | 1194/PMD | 03/11/2023 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.27 | 0 | 100
1052 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at pumphouse site with other allied works under Chitmu w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000551/2023-2024 | 377/PMD | 04/03/2024 | 212 | M/S UJJAL DIESEL SERVICE | 5.56 | 0 | 100
1053 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of MS pipe, valves and dismantling joint at Chitmu W/S scheme under P.M.D. P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000559/2023-2024 | 72/PMSD(W/S) | 23/02/2024 | 15 | M S ENTERPRISE | 0.94 | 0 | 100
1054 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Sinking of 200mmX165mm tubewell with installation of submersible pumping machinery, Cable and other works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000617/2024-2025 | 1537/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.74 | 0 | 40
1055 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000007/2023-2024 | 616/PMD | 01/06/2023 | 0 | Resource Division | 0.34 | 0 | 0
1056 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | LOAD ENHANCEMENT APPLICATION FOR CHITMU WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000325/2022-2023 | BP-2022-23-39 | 08/09/2022 | 0 | WBSEDCL PURULIA | 1.7 | 0 | 0
1057 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
1058 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying hoisting & placing of PVC tank (10000 ltr 2 nos) over MS structural OHR and other allied work at Ajodhya OHR site of Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000108/2023-2024 | 870/PD | 30/06/2023 | 30 | SARKAR ENTERPRISE | 2.43 | 2.37 | 100
1059 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and Layingand extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000335/2021-2022 | 43/PD | 07/01/2022 | 60 | SADHAN GORAIN | 92.36 | 0 | 100
1060 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000336/2021-2022 | 44/PD | 07/01/2022 | 45 | TUMPA GORAIN | 18.54 | 0 | 100
1061 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Collecting main Line From TubeWell to Main Rising Main of Ajodhya W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000611/2022-2023 | 508/PSD | 12/08/2022 | 40 | TUMPA GORAIN | 4.85 | 4.82 | 0
1062 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Tank plateform, parapet wall, repairing & renovation gr floor staff room and sanitary Plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. under JJM & Jal Sapna. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000616/2022-2023 | 513/PSD | 12/08/2022 | 45 | TUMPA GORAIN | 2.09 | 0 | 85
1063 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of PVC Line For CRPF Camp& Ajodhya Girls Hostel & Shifting of GI Line For Construction New CWR at OHR Campus of Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000618/2022-2023 | 515/PSD | 12/08/2022 | 45 | TUMPA GORAIN | 1.68 | 1.67 | 100
1064 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte [For the period of 90 days] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000849/2022-2023 | 1753/PD | 22/11/2022 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 0
1065 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing FHTC at Kalafulia village under Ajodhya water supply scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000927/2023-2024 | 4856/PSD | 29/09/2023 | 10 | MOUSUMI BANERJEE | 1 | 0 | 100
1066 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Pushing of 600mm dia RCC pre cast pipe and 100 mm dia GI . water carrier pipe by hydraulic jacking method across Sirkabad-Ajodhya- Baghmundi PWD Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) Near Ajodhya OHR site, Bagandi mor and Matakamdi PWD branch Road Junction for Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001058/2022-2023 | 290/PD | 27/02/2023 | 45 | MS GORAIN CONCERN | 19.12 | 19.05 | 100
1067 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of dedicated distribution line for providing FHTC at kotalmara habitation, bursabera habitation & chhatni habitation under Augmentation of Ajodhya water supply scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001327/2023-2024 | 1712/PD | 04/12/2023 | 60 | TUMPA GORAIN | 31.22 | 0 | 100
1068 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipeline from Gobria to Puniasashan & providing FHTC at Puniasashan & Churingsarang village & other allied works at Ajodhya water supply scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001492/2023-2024 | 1803/PD | 08/12/2023 | 60 | ANUDIP SAHA | 12.87 | 0 | 100
1069 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extention of distribution line for providing FHTC at Sitakunda to Bagandih&Kuchlirakha habitation under Ajodhya water supply scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001618/2023-2024 | 1829/PD | 12/12/2023 | 60 | TUMPA GORAIN | 11.01 | 0 | 100
1070 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New Construction of Boundary wall & Repairing of DI Rising Main at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001872/2023-2024 | 97/PD | 15/01/2024 | 426 | BOSE CONSTRUCTION | 15.05 | 0 | 40
1071 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) (Ad- Interim Payment) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000158/2022-2023 | BP-2022-23-21 | 07/04/2022 | 0 | TUMPA GORAIN | 5.36 | 0 | 0
1072 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000159/2022-2023 | BP-2022-23-22 | 07/04/2022 | 0 | TUMPA GORAIN | 2.18 | 0 | 0
1073 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Baghmundi W/S Scheme & Ajodhya W/S Scheme block-Baghmundi) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 361/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000936/2022-2023 | BP-2022-23-107 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.18 | 0 | 0
1074 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying and Laying and extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) (Tender No- 176/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001062/2022-2023 | BP-2022-23-415 | 28/10/2022 | 0 | SADHAN GORAIN | 67.17 | 0 | 0
1075 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 cum with other allied works at Ajodhya W/s Scheme. (Tender No.859/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001173/2021-2022 | BP-2021-22-346 | 28/03/2022 | 0 | TUMPA GORAIN | 9.64 | 0 | 0
1076 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of tank platform, parapet wall, repairing & renovation Ground floor staff and sanitary plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub- Division, PHE Dte. under JJM & Jalswapna [Tender No 550/2022-2023 of EE/PD] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001533/2022-2023 | BP-2022-23-834 | 27/03/2023 | 0 | TUMPA GORAIN | 1.63 | 0 | 0
1077 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ajodhya Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000021/2022-2023 | 320/PMD | 17/05/2022 | 30 | ALPHA ENTERPRISES | 20.5 | 20.49 | 100
1078 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0
1079 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Ajodhya W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000061/2021-2022 | 107/PMD | 28/02/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 20.4 | 20.37 | 100
1080 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Submersible pumping machineries with all ancillaries & auxiliaries for augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000094/2022-2023 | 520/PMD | 05/08/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 31.83 | 31.18 | 100
1081 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machineries,with all ancillaries & auxiliaries including allied works for augmentation of Ajodhya Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000100/2022-2023 | 527/PMD | 05/08/2022 | 30 | SWAPAN ENTERPRISE | 9.45 | 8.8 | 100
1082 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of submersible pumping machinery for Direct Pumping with Flow meter for Augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000136/2023-2024 | 903/PMD | 04/08/2023 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 7.54 | 0 | 90
1083 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Indoor & outdoor illumination arrangement with others electro-mechanical work at Ajodhya water supply scheme (Low lift) for Augmentation of Ajodhya PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000230/2024-2025 | 1224/PMD | 13/08/2024 | 264 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 6.95 | 0 | 30
1084 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Electrification and Rectification of lighting arrangement at pump house with other allied works for Augmentation at Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000285/2022-2023 | 76/PMD | 01/02/2023 | 60 | BISHWANATH NANDI | 5.77 | 5.66 | 100
1085 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Big Dia R.B.T.W (200 mm × 165 mm) at Ajodhya Hill top of Bagmundi block in Purulia district under Purulia Mechanical Division PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000457/2023-2024 | 437/PMD | 11/03/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.57 | 0 | 90
1086 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Submersible pumping machinery with other allied work at Newly sunk T/W of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000579/2024-2025 | 1437/PMD | 01/10/2024 | 214 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 11.87 | 0 | 90
1087 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Voltage stabilizer with other allied work at low lift P/H no. 3 & 4 of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000618/2024-2025 | 1540/PMD | 11/11/2024 | 176 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 5.42 | 0 | 80
1088 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Rig Bore tubewell (200mm x 165 mm) by DTH method at Ajodhya for Ajodhya PWSS under Purulia Mechanical Division, P.H.Engineering Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000680/2024-2025 | 1692/PMD | 06/12/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.94 | 0 | 90
1089 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of distribution pipe line ( 110 mm & 90 mm dia HDPE pipe ) from Bankati Siv Mandir to Dejuri - Shyambathan More in connection with FHTC under Rangamati W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000019/2023-2024 | 548/PD | 12/04/2023 | 30 | M/S. DESTINY CONSTRUCTION | 7.19 | 6.4 | 0
1090 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Barrah Siv Mandir to Bankati village under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000355/2021-2022 | 105/PD | 18/01/2022 | 45 | MANATOSH SINGH | 22.36 | 0 | 100
1091 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000356/2021-2022 | 106/PD | 18/01/2022 | 100 | CHANCHAL MISHRA | 5.86 | 0 | 98
1092 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 250 cum at Barrah under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000357/2021-2022 | 107/PD | 18/01/2022 | 60 | MANATOSH SINGH | 5.27 | 4.38 | 90
1093 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Rangamati W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000433/2021-2022 | 380/PD | 11/03/2022 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 29.49 | 5.3 | 100
1094 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Guard Room cum store at Pump House Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000435/2021-2022 | 381/PD | 11/03/2022 | 100 | CHANCHAL MISHRA | 5.94 | 5.9 | 0
1095 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) including other allied works of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001623/2023-2024 | 1833/PD | 12/12/2023 | 60 | BOSE CONSTRUCTION | 4.23 | 0 | 100
1096 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | RTOR000001/2022-2023 | 965/PD | 21/06/2022 | 0 | Resource Division | 18.28 | 0 | 0
1097 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 04 (Four) No. 200 mm dia river bed tube well horizontal at Darakeswar river along with laying of 100 mm dia GI collecting with all allied works under Rangamati Water Supply Scheme under Raghunathpur Sub- division, PHE Dte. (Tender No- 11/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000920/2022-2023 | BP-2022-23-102 | 16/07/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 8.56 | 0 | 0
1098 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.889/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001027/2022-2023 | BP-2022-23-342 | 29/09/2022 | 0 | CHANCHAL MISHRA | 5.48 | 0 | 0
1099 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying different dia HDPE pipe line from Barrah Shiv Mandir to Borkha Village under Rangamati Village. (Tender No.1005/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001129/2021-2022 | BP-2021-22-375 | 29/03/2022 | 0 | MANATOSH SINGH | 14.39 | 0 | 0
1100 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) (Ad-interim) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001140/2021-2022 | BP-2021-22-275 | 03/03/2022 | 0 | SANTANU BANERJEE | 16 | 0 | 0
1101 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001143/2021-2022 | BP-2021-22-297 | 09/03/2022 | 0 | SANTANU BANERJEE | 2.49 | 0 | 0
1102 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | NEW CONNECTION FOR AUGMENTATION OF RANGAMATI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00041/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0
1103 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Rangamati water supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00248/2023-2024 | BP-23-24-203 | 17/10/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0
1104 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Rangamatia Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000054/2022-2023 | 395/PMD | 16/06/2022 | 30 | MS EMMESS | 20.5 | 20.49 | 100
1105 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal external illumination with other allied works for Augmentation of Rangamati Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000205/2023-2024 | 1195/PMD | 03/11/2023 | 60 | SANTU MITRA | 6.37 | 0 | 100
1106 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Additional work for supply delivery and laying of submersible cable with jointing kit for newly constructed river bed tube well for augmentation of Rangamati water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000239/2023-2024 | 335/PMSD(W/S) | 11/09/2023 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 100
1107 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Rangamati water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000442/2022-2023 | 261/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 46.44 | 0 | 72
1108 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000443/2022-2023 | 262/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 8.54 | 0 | 0
1109 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries into the existing CWR and in River bed Tube Well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000468/2024-2025 | 1294/PMD | 30/08/2024 | 397 | M/S A.D. CONCERN | 10 | 0 | 50
1110 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 100KVA voltage stabilizer for Augmentation of Rangamati water supply scheme under Purulia Mechanical Division PHE, Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000480/2022-2023 | 339/PMD | 24/03/2023 | 60 | SANTU MITRA | 10.39 | 6.08 | 100
1111 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and laying of cable line at Rangamati water supply scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000553/2023-2024 | 106/PMSD(W/S) | 05/03/2024 | 7 | SANTU MITRA | 0.74 | 0 | 100
1112 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room cum store at Pump House Campus under Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000343/2021-2022 | 66/PD | 17/01/2022 | 100 | M/S SHYAMASHREE ENTERPRISE | 5.2 | 5.18 | 100
1113 | Purulia Division | Raghunathpur Sub-Division | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000399/2022-2023 | 357/RNP | 01/06/2022 | 20 | ASHOK KUMAR CHATTERJEE | 1.76 | 0 | 100
1114 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of Pump House at River Side under Parbeylia W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000931/2022-2023 | 712/RNP | 23/12/2022 | 15 | AMIT PATHAK | 1 | 0.64 | 0
1115 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room Cum Chlorin Room at CWR Site of Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000966/2022-2023 | 45/PD | 09/01/2023 | 100 | M/S KARUNAMOYEE CONSTRUCTION | 4.86 | 4.82 | 100
1116 | Purulia Division | Raghunathpur Sub-Division | Installation of 3 (Three) nos. 1.00 H.P. capacity Solar Photovoltaic Submersible Pump set in pre-existing / new bore Tube well along with 1200 Watt peak capacity Solar photovoltaic array panels on steel structure including Supply & Delivery of approved quality materials & Geophysical investigation by electrologging with all allied works at different places within Neturia Block in Purulia District of Raghunathpur Sub-Division under Purulia Division, PHE Dte.[Phase-iii][Group-E] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/001098/2022-2023 | 365/PD | 14/03/2023 | 45 | ASHOK KUMAR CHATTERJEE | 30.01 | 0 | 0
1117 | Purulia Mechanical | Raghunathpur Sub-Division | New power connection at Parbeliya PWSS OHR Campus(Reference M.B.NO MB/0000210/2023-2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00870/2023-2024 | BP-23-24-300 | 05/03/2024 | 0 | WBSEDCL PURULIA | 0.11 | 0 | 0
1118 | Purulia Mechanical | Raghunathpur Sub-Division | Sub: Enhancement of the contract demand from 85 KVA at 0.4 KV to 119/119/119/119/119 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o-THE EXE. ENGG, PMD, P.H.E DTE., PURULIA, SITE- PHE PERBELIA W/S under Purulia Regional Office. (1) Application No.- L000005249. (2) Consumer Id.- 932416100 | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00892/2023-2024 | BP-23-24-339 | 27/03/2024 | 0 | WBSEDCL PURULIA | 6.85 | 0 | 0
1119 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumps motor sets with other allied works for Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000032/2023-2024 | 437/PMD | 19/04/2023 | 60 | KOUSHIK CHATTERJEE | 12.04 | 0 | 100
1120 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Parbeliya Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000040/2022-2023 | 321/PMD | 17/05/2022 | 30 | MS SAJAHAN CHOWDHURY | 20.49 | 13.97 | 100
1121 | Purulia Mechanical | Raghunathpur Sub-Division | External and internal illumination of OHR site,High lift and low lift site of Parbeliya water supply scheme and Flood light at Low lift site for Augmentation work under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000044/2024-2025 | 962/PMD | 20/06/2024 | 90 | MOON LIGHT HOUSE | 8.27 | 0 | 100
1122 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 50KVA oil cooled voltage stabilizer and allied works for Augmentation of Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000079/2023-2024 | 588/PMD | 23/05/2023 | 60 | M/S A.D. CONCERN | 5.88 | 0 | 100
1123 | Purulia Mechanical | Raghunathpur Sub-Division | Internal illumination of pump house room with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000132/2023-2024 | 647/PMD | 08/06/2023 | 60 | GOLAP KR. GHOSH | 1.46 | 0 | 100
1124 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery & installation of Electromagnetic flow meter and with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000435/2022-2023 | 254/PMD | 06/03/2023 | 60 | BISHWANATH NANDI | 6.91 | 0 | 100
1125 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 100
1126 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery of Submersible pumping machineries for Parbeliya W/S scheme under PMD P.H.E Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000501/2023-2024 | 196/PMD | 16/02/2024 | 15 | M/S A.D. CONCERN | 0.59 | 0 | 100
1127 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Dewatering submersible pump set at Parbelia w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000510/2023-2024 | 344/PMD | 28/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.55 | 0 | 100
1128 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of MCC Panel at Parbelia w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000532/2023-2024 | 354/PMD | 29/02/2024 | 300 | SUBAL SARKAR | 0.64 | 0 | 100
1129 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 500 ltr UPVC tank and pipe line for eye shower for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division, P.H.E Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000556/2023-2024 | 195/PMD | 16/02/2024 | 10 | MS SAJAHAN CHOWDHURY | 0.37 | 0 | 100
1130 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 119/119/119/119/119 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 932416100) TO THEIR PREMISES AT PARBELIYA WATER SUPPLY SARBARI NETURIA DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000423/2022-2023 | BP-22-23-86 | 28/02/2023 | 0 | WBSEDCL PURULIA | 1.98 | 0 | 0
1131 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Regarding laying of water supply pipe line along road side and road crossing on i) Manbazar-Bandwan-Kuilapal Road ii) Barabazar-Bandwan Road iii) Bandwan-Ashanpani Road in respect of Augmentation of bandwan water supply scheme in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00173/2022-2023 | BP-2022-23-662 | 23/02/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 139.71 | 0 | 0
1132 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Office stationary bill payment. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00244/2023-2024 | BP-2023-24-150 | 30/05/2023 | 0 | KETIKA CONSUMERS CO-OP STORES LTD | 1.47 | 0 | 0
1133 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
1134 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Refreshment bill paid for office meeting. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00604/2023-2024 | BP-2023-24-368 | 10/08/2023 | 0 | MATHUR DUTTA | 0.12 | 0 | 0
1135 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-851 to J-864)(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000004/2022-2023 | 150/PSD | 04/04/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.59 | 0 | 100
1136 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Various ICDS Centre and Schools and Supply of drinking water through water tanker to various places from nearby headwork sites of different W/S Scheme to mitigate draught like situation under Bandwan Block block of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000059/2022-2023 | 169/PSD | 18/04/2022 | 25 | BOSE CONSTRUCTION | 1.68 | 0 | 0
1137 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Clear water reservoir (CWR) of capacity 250 Cum with other allied works at WTP campus of Bandwan W/S scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000081/2022-2023 | 632/PD | 22/04/2022 | 100 | WRISHI ENTERPRISE | 28.1 | 27.26 | 0
1138 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chilla Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2022-2023 | 633/PD | 22/04/2022 | 60 | BOSE CONSTRUCTION | 96.26 | 43.38 | 100
1139 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Installation of 3000 mm dia x 1800 mm Pressure shell for WTP at Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000340/2021-2022 | 58/PD | 13/01/2022 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.8 | 23.79 | 100
1140 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Supudih Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000410/2022-2023 | 937/PD | 16/06/2022 | 1294 | SANTANU BANERJEE | 120.63 | 63.12 | 65
1141 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000412/2021-2022 | 333/PD | 28/02/2022 | 60 | BOSE CONSTRUCTION | 51.38 | 28.05 | 80
1142 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Jitan Village | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000413/2021-2022 | 334/PD | 28/02/2022 | 30 | ROY CONSTRUCTION | 18.56 | 0 | 100
1143 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sirishgora Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000414/2021-2022 | 335/PD | 28/02/2022 | 90 | ANUP KUMAR SAHA | 95.06 | 0 | 85
1144 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-846 to J-851)(Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000449/2021-2022 | 98/PSD | 14/03/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.56 | 0 | 100
1145 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Installation of 3000 mm dia x 1800 mm (3 & 4 nos) Pressure filter shell for WTP under Augumentation of Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000489/2021-2022 | 523/PD | 30/03/2022 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.63 | 23.62 | 100
1146 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000505/2022-2023 | 441/PSD | 24/06/2022 | 10 | BOSE CONSTRUCTION | 1.26 | 0 | 80
1147 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000507/2022-2023 | 443/PSD | 24/06/2022 | 15 | ROY CONSTRUCTION | 1.07 | 0 | 100
1148 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and renovation of the damaged eleveted water reservoir at Bandwan OHR Site under Bandwan W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000834/2022-2023 | 1736/PD | 22/11/2022 | 45 | SUJIT CHAKRABORTY | 6.15 | 4.37 | 100
1149 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Augmentation of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza)Bardih Village,Jordih Village & Kodogora Village | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000855/2022-2023 | 1806/PD | 06/12/2022 | 45 | BOSE CONSTRUCTION | 11.49 | 9.61 | 25
1150 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000866/2022-2023 | 1811/PD | 06/12/2022 | 45 | ANUP KUMAR SAHA | 13.22 | 12.72 | 100
1151 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000867/2022-2023 | 18111/PD | 06/12/2022 | 45 | ANUP KUMAR SAHA | 13.22 | 0 | 0
1152 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Over Head reservoir (OHR) of capacity 350 Cum with other allied works of Bandwan W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000928/2022-2023 | 1890/PD | 15/12/2022 | 270 | PRAVAT SARKAR | 118.62 | 0 | 100
1153 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Main line and Parallel line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Bandwan Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001062/2022-2023 | 295/PD | 27/02/2023 | 45 | DEBAKI RANJAN SARKAR | 67.69 | 0 | 30
1154 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001228/2022-2023 | 250/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.72 | 0.72 | 100
1155 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001229/2022-2023 | 251/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.48 | 0 | 0
1156 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 183 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 100
1157 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000021/2021-2022 | 390/PD | 11/03/2022 | 0 | Resource Division | 37.05 | 0 | 0
1158 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000027/2022-2023 | 1015/PD | 05/07/2022 | 0 | Resource Division | 225.01 | 0 | 0
1159 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000040/2022-2023 | 239/PD | 20/02/2023 | 0 | Resource Division | 228.79 | 0 | 0
1160 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Jitan village (Tender No- 1035/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000880/2022-2023 | BP-2022-23-70 | 01/07/2022 | 0 | ROY CONSTRUCTION | 7.17 | 0 | 0
1161 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village [from node J-846 to J-851 Part A] (Tender No- 32/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000898/2022-2023 | BP-2022-23-82 | 01/07/2022 | 0 | CHATTERJEE CONSTRUCTION | 2.43 | 0 | 0
1162 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bandwan W/S Scheme & Bandwan Spot W/S Scheme block-Bandwan) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 536/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000911/2022-2023 | BP-2022-23-90 | 07/07/2022 | 0 | RADIANT | 1.26 | 0 | 0
1163 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village (from node J-851 to J-864) Part- B (Tender No- 55/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000913/2022-2023 | BP-2022-23-88 | 07/07/2022 | 0 | CHATTERJEE CONSTRUCTION | 2.47 | 0 | 0
1164 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Water supply arrangement of schools model-2 (201-500 students) at Bandwan Pry. School under Bandwan Block under RWS Purulia Sub- Division, PHE Dte. (Tender No- 1021/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000985/2022-2023 | BP-2022-23-148 | 25/07/2022 | 0 | KABERI DUTTA | 0.98 | 0 | 0
1165 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Pargela Mouza) (Tender No- 1002/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000992/2022-2023 | BP-2022-23-156 | 26/07/2022 | 0 | BOSE CONSTRUCTION | 19.67 | 0 | 0
1166 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Sirisgora Mouza) (Tender No- 998/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000993/2022-2023 | BP-2022-23-155 | 26/07/2022 | 0 | ANUP KUMAR SAHA | 55.85 | 0 | 0
1167 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 434/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001051/2022-2023 | BP-2022-23-395 | 28/10/2022 | 0 | BOSE CONSTRUCTION | 0.92 | 0 | 0
1168 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 410/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001052/2022-2023 | BP-2022-23-396 | 20/10/2022 | 0 | ROY CONSTRUCTION | 1.07 | 0 | 0
1169 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | FOR NEW SERVICE CONNECTION OF AUGMENTATION OF BUNDWAN WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00043/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0
1170 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER METER ROOM AT AUG OF BUNDWAN WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00099/2023-2024 | C072325293658 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0
1171 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Additional Quotation for PHE Connection at Chilla. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00501/2023-2024 | BP-23-24-270 | 22/01/2024 | 0 | WBSEDCL PURULIA | 4.02 | 0 | 0
1172 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | LOAD ENHANCEMENT FOR AUG OF BUNDWAN WS SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00604/2023-2024 | BP-2023-24-201 | 17/10/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0
1173 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bandwan Water Supply scheme (OHR site) Block Bandwan under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2022-2023 | 394/PMD | 16/06/2022 | 1020 | S P CONSTRUCTION | 20.5 | 0 | 100
1174 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of H.L. Centrifugal pump with allied motor as needed at 950 KLD water treatment plant, Bundwan under PMD,PHE, Dte, in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2022-2023 | 403/PMD | 17/06/2022 | 30 | RABINDRA NATH KHAN | 9.19 | 9.19 | 100
1175 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Flowmeter for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000091/2022-2023 | 526/PMD | 05/08/2022 | 911 | SUBRATA DUTTA | 8.02 | 4.67 | 100
1176 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries with necessary allied works at intake for augmentation of Bandwan w/s project under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000096/2022-2023 | 522/PMD | 05/08/2022 | 1214 | TAPAN KUMAR DEY | 27.3 | 17.41 | 65
1177 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries with necessary substitutes with allied works for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2022-2023 | 523/PMD | 05/08/2022 | 60 | RABINDRA NATH KHAN | 88.94 | 53.46 | 65
1178 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000118/2022-2023 | 537/pmd | 17/08/2022 | 60 | M/S M S ENTERPRISE | 66.56 | 40.82 | 100
1179 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house building, substation building, OHR site Chorination room for Augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000119/2022-2023 | 547/PMD | 18/08/2022 | 30 | ASHOKE ADHIKARY | 8.91 | 7.26 | 90
1180 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Sinking of 200mmX165mm tubewell and other allied works at Bandwan spot water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2023-2024 | 1179/PMD | 03/11/2023 | 15 | SAIBAL SARKAR | 7.13 | 0 | 100
1181 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and Delivery of different gaseous chlorine spare parts for Bandwan and other water supply schemes under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000343/2022-2023 | 125/PMD | 16/02/2023 | 30 | RABINDRA NATH KHAN | 10.82 | 10.82 | 100
1182 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 245/245/245/245/245 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 942408200) TO THEIR PREMISES AT BUNDWAN WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000422/2022-2023 | BP-22-23-84 | 28/02/2023 | 0 | WBSEDCL PURULIA | 9.31 | 0 | 0
1183 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing, renovation & restoration of Pump House with Panel room including roof treatment at Namo Pindra River site of Bongabari W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000045/2023-2024 | 660/PD | 17/05/2023 | 60 | SABYASACHI MISHRA | 4.19 | 0 | 0
1184 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000108/2022-2023 | 644/PD | 22/04/2022 | 985 | SIDDHARTHA SANKAR SARKAR | 10.99 | 4.35 | 100
1185 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000109/2022-2023 | 645/PD | 22/04/2022 | 45 | SUPRIYA MAHANTI MISHRA | 10.98 | 0 | 80
1186 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000110/2022-2023 | 646/PD | 22/04/2022 | 45 | INDRAJIT SARKAR | 10.99 | 7.67 | 100
1187 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000112/2022-2023 | 648/PD | 22/04/2022 | 45 | KABERI DUTTA | 9.84 | 2.99 | 100
1188 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahara Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000120/2024-2025 | 913/PD | 07/05/2024 | 604 | SANTANU BANERJEE | 29.87 | 0 | 0
1189 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Left out HDPE Distribution main Pipe line from Hatuara OHR site to existing distribution main of Bongabari W/S scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000141/2024-2025 | 924/PD | 07/05/2024 | 60 | GOUTAM CHAKRABORTY | 64.54 | 0 | 100
1190 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jitdih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000143/2024-2025 | 914/PD | 07/05/2024 | 604 | MAHARSHI BANERJEE | 32.57 | 0 | 0
1191 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dubkidi Habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000144/2024-2025 | 915/PD | 07/05/2024 | 180 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 48.75 | 0 | 100
1192 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Naudiha habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000145/2024-2025 | 916/PD | 07/05/2024 | 329 | KM ENTERPRISES | 40.61 | 0 | 0
1193 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 250 mm DI rising main from Mahara CWR to Hatuara OHR for augmentation of Bongabari W/S scheme at Purulia-II block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000147/2024-2025 | 918/PD | 07/05/2024 | 60 | TAPAN CHANDRA | 84.23 | 0 | 75
1194 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI rising main pipeline including cleaning of chokage and Construction of 200 cum capacity CWR & Pump house including panel room & chlorination room, Boundary Wall at Mahara of Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000191/2024-2025 | 922/PD | 07/05/2024 | 270 | SUBRATA MAHAPATRA | 72 | 0 | 50
1195 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New Sinking of 3 (Three) Nos 200 mm dia river bed vertical tubewell along with necessary 100 mm dia GI collecting line from River bed Tubewell to CWR at river bank (Kansabati River) at Pindra under Bangabari W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000210/2024-2025 | 1078/PD | 07/06/2024 | 45 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.94 | 0 | 100
1196 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pathardih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000247/2024-2025 | 1140/PD | 18/06/2024 | 45 | ASHOKE ADHIKARY | 31.61 | 0 | 0
1197 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of HDPE pipe as distribution main (loop line) from Surulia Road Side Hari Mandir to Surulia Shiv Mandir in Surulia village for drinking water supply through FHTC to met up the water crisis at Uppar Surulia Village from existing Bongabari W/S scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000445/2021-2022 | 94/PSD | 14/03/2022 | 15 | SOUVIK MANDAL | 4.6 | 0.27 | 100
1198 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Hatuara Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000621/2022-2023 | 1392/PD | 01/09/2022 | 1218 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 45 | 21.3 | 90
1199 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000622/2022-2023 | 1391/PD | 01/09/2022 | 45 | GOUTAM CHAKRABORTY | 39.1 | 24.88 | 100
1200 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000623/2022-2023 | 1390/PD | 01/09/2022 | 45 | SOUVIK MANDAL | 23.21 | 4.23 | 100
1201 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Temporary Car Shed near guest house under JJM / Jalswanpa under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000829/2022-2023 | 1723/PD | 22/11/2022 | 45 | BOSE CONSTRUCTION | 4.99 | 0 | 100
1202 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Palashkola and Gopalpur Mouza of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000832/2022-2023 | 1724/PD | 22/11/2022 | 1136 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 54.03 | 35.86 | 90
1203 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and Restoration of damaged 125 mm dia pipe line at bongabari near Club to Bangabari more & Rest shed to Jack pushing point and 75 mm dia from Hatuara Firm main gate to DIET-II Campus and 100mm dia GI pipe road Crossing near Surulia more for Surulia Bauri Para of Purulia-II Block area to drinking water supply under Bongabari Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000835/2022-2023 | 1737/PD | 22/11/2022 | 45 | SADHAN GORAIN | 5.7 | 5.69 | 100
1204 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 225 mm dia.(OD) HDPE Pipe as Rising main at Upar Pindra Village of Pindra G.P. of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000841/2022-2023 | 1743PD | 22/11/2022 | 1136 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 43.16 | 0 | 100
1205 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Office Room Cum Godown Room within Purulia Sadar Sub-division campus under JJM/Jal Swapna Programme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000842/2022-2023 | 1744/PD | 22/11/2022 | 180 | BOSE CONSTRUCTION | 38.36 | 0 | 100
1206 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI Pipeline and Repairing & Construction of boundary wall at Puncha Riversite Pump house Site under Puncha W/S Scheme under,Manbazar-II Purulia Sadar Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000870/2023-2024 | 1523/PD | 16/10/2023 | 587 | KANAILAL PAL | 24.14 | 0 | 100
1207 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river near Samsan Ghat at Puncha under Bongabari W/S Scheme of Purulia Sadar Sub- Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000871/2023-2024 | 1521/PD | 16/10/2023 | 60 | SOUVIK MANDAL | 43.94 | 0 | 100
1208 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river at Namopindra village of Bongabari W/S scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000874/2023-2024 | 1524/PD | 16/10/2023 | 502 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.43 | 0 | 85
1209 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing additional Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000921/2022-2023 | 1929/PD | 22/12/2022 | 45 | GOUTAM CHAKRABORTY | 38.42 | 33.07 | 100
1210 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village including extention of distribution pipe line (Gap Portion) of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001052/2022-2023 | 284/PD | 27/02/2023 | 45 | SIDDHARTHA SANKAR SARKAR | 23 | 0 | 100
1211 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Over Head Reservoir (OHR) of 500 Cum Capacity, Staging Height 25 mtr. at Birgiri Mouza of Bangabari W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E Dte. (SL - 2) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001106/2022-2023 | 354/PD | 14/03/2023 | 270 | MS CHANDI CHARAN ROY | 138.29 | 73.46 | 100
1212 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Pipe for distribution pipe line (Gap Portion) to providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001204/2022-2023 | 491/PD | 31/03/2023 | 642 | SIDDHARTHA SANKAR SARKAR | 20.25 | 11.93 | 100
1213 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001217/2022-2023 | 505/PD | 31/03/2023 | 45 | KABERI DUTTA | 2.92 | 1.31 | 100
1214 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Namo Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001218/2022-2023 | 506/PD | 31/03/2023 | 45 | SUDHANSHU OJHA | 5.3 | 0 | 100
1215 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Guard room with Toilet at Bongabari OHR campus for Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001314/2024-2025 | 457/PD | 24/03/2025 | 120 | MAHATO CONSTRUCTION | 7.22 | 0 | 0
1216 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work order for the work of Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division, P.H.E Dte. (500 cubic meter capacity Over Head Reservoir of Bongabari W/S Scheme within Purulia Sadar Sub-Division under Purulia Division P.H.E Dte.) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001324/2022-2023 | 313/PD | 02/03/2023 | 121 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 100
1217 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Boundary wall & Sinking of T/well at Mahara Tolapathardih(Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003483/2023-2024 | 361/PD | 04/03/2024 | 60 | GANGULY ENTERPRISES | 20.05 | 0 | 100
1218 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Boundary wall & Sinking of T/well at Bongabari (Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003485/2023-2024 | 360/PD | 04/03/2024 | 211 | M/S CONTRACTORS SYNDICATE | 29.93 | 0 | 100
1219 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Emergency piling work along with sand filling at collecting line trenches for protection work against flash flood at Sirkabad W/S Scheme under Purulia Division,PHE Dte.(Under Bongabari W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003545/2023-2024 | 324/PD | 01/03/2024 | 45 | SUBRATA MAHAPATRA | 34.58 | 0 | 0
1220 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of DI pipeline and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Sirkabad W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.(Under Bongabari W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003546/2023-2024 | 329/PD | 01/03/2024 | 60 | HIRAK KUMAR SAO | 8.04 | 0 | 100
1221 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000032/2024-2025 | 1103/PD | 11/06/2024 | 0 | Resource Division | 289.91 | 0 | 0
1222 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 185/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001040/2022-2023 | BP-2022-23-372 | 19/10/2022 | 0 | SUDHANSHU OJHA | 6.8 | 0 | 0
1223 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) (Tender No- 404/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001056/2022-2023 | BP-2022-23-403 | 20/10/2022 | 0 | SUPRIYA MAHANTI MISHRA | 8.44 | 0 | 0
1224 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Payment of WBSEDCL quotation for new power connection at Bongabari W/S Scheme (Zone-II), Mahara, under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00342/2024-2025 | BP-24-25-112 | 23/08/2024 | 0 | WBSEDCL PURULIA | 8.05 | 0 | 0
1225 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Proposed pump house Bongabari w/s(Zone-II) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000055/2023-2024 | 524/PMD | 05/05/2023 | 60 | DEY ENTERPRISE, HOWRAH | 37.81 | 0 | 20
1226 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machinery with other allied work for direct pumping at Mahara (Zone - III) of Augmentation of Bongabari water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2024-2025 | 1017/PMD | 25/06/2024 | 463 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 49.03 | 0 | 25
1227 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Internal lighting and external lighting at Proposed Pump House for Augmentation of Bongabari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000129/2023-2024 | 867/PMD | 21/07/2023 | 60 | KANTILAL SAO | 2.84 | 0 | 0
1228 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bongabari(Zone-III) Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000386/2022-2023 | 217/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 12.91 | 0
1229 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bongabari w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000410/2022-2023 | 238/PMD | 03/03/2023 | 60 | COMBINE ENTERPRISES | 77.44 | 0 | 15
1230 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation 75kva voltage stabilizer for Augmentation of Bongabari w/s scheme(Zone-II) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000429/2022-2023 | 239/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 8.01 | 0 | 15
1231 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of submersible pumping machinery at River Bed Tubewell for Augmentation of Bongabari w/s(River site) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000431/2022-2023 | 250/PMD | 06/03/2023 | 60 | SEN BROTHERS | 8.99 | 3.09 | 90
1232 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation at Bongabari w/s scheme(Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000469/2022-2023 | 309/PMD | 16/03/2023 | 30 | TAPAN KUMAR DEY | 21.6 | 12.87 | 0
1233 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at Proposed pump house (Zone-II) site with other allied works under Bongabari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000543/2023-2024 | 374/PMD | 04/03/2024 | 60 | TAPAN KUMAR DEY | 5.82 | 0 | 0
1234 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and Installation of Openwell submersible pumping machinery with other allied works at Bongabari w/s scheme (Pindra) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000622/2024-2025 | 1544/PMD | 11/11/2024 | 324 | M/S A.D. CONCERN | 3.09 | 0 | 30
1235 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000002/2023-2024 | 611/PMD | 01/06/2023 | 0 | Resource Division | 1.03 | 0 | 0
1236 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System including pipe carrying structure all complete including cost of materials including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-IV A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | Assistant Engineer |  | ORD/000034/2023-2024 | 584/PD | 20/04/2023 | 60 | M/S RAJ KUMAR KHAN | 267.81 | 79.85 | 80
1237 | Purulia Division | Raghunathpur Sub-Division | Supplying & laying of different dia HDPE pipe line with other allied works from Tilabani OHR Campus to Bathandih village through Rabon More at Tilabani villlage under Kalabani G.P. under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000058/2023-2024 | 665/PD | 17/05/2023 | 30 | SADHAN GORAIN | 12.88 | 12.84 | 100
1238 | Purulia Division | Raghunathpur Sub-Division | Laying of GI pipe line from Raghunathpur office campus CWR to SD Hospital CWR and other allied works under Raghunathpur W/S Scheme (Zone-IV) (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000405/2024-2025 | 180/RNP | 04/04/2024 | 7 | SOMNATH SINGH | 0.96 | 0 | 100
1239 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 100
1240 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 100
1241 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 100
1242 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1243 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1244 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1245 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1246 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of Gar Panchakot Inspection Bunglow (Ground Floor) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000967/2022-2023 | 46/PD | 09/01/2023 | 60 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 4.39 | 0 | 100
1247 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Over Head Reservoir (Torch types with solid raft) capacity 150 Cum and other allied works of Raghunathpur Water Supply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000980/2022-2023 | 92/PD | 20/01/2023 | 270 | BOSE CONSTRUCTION | 72.84 | 15.65 | 85
1248 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room with toilet block at Zone-IV A under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001042/2024-2025 | 2103/PD | 05/12/2024 | 90 | PRAKASH DESHMUKH | 6.41 | 0 | 0
1249 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room with toilet block at Zone-IV B under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001043/2024-2025 | 2104/PD | 05/12/2024 | 90 | SAANVI CONSTRUCTION | 6.41 | 0 | 0
1250 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump House (10 X 7 mtr) at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001044/2022-2023 | 276/PD | 27/02/2023 | 1040 | BASANTA KUMAR SINGHADEO | 18.56 | 0 | 40
1251 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of Panel Room at office of the Assistant Engineer, Raghunathpur Sub-Division, PHE Dte. at S.D. Hospital Campus under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001102/2022-2023 | 94/RNP | 10/03/2023 | 15 | BISWAJIT MAJI | 0.91 | 0.8 | 0
1252 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC) and other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IV B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 6) | Assistant Engineer |  | ORD/001104/2022-2023 | 270/PD | 24/02/2023 | 645 | MITHU BUILDERS | 211.47 | 82.9 | 75
1253 | Purulia Division | Raghunathpur Sub-Division | Repairing works at 8 Nos Bridge of Rising Pipe line works under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001173/2024-2025 | 2327/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.81 | 0 | 0
1254 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution Pipeline from Zone IV B OHR site to Ekunja More and other allied works for Aug. of Raghunathpur Water Supply Scheme (Zone - IV B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001886/2023-2024 | 104/PD | 15/01/2024 | 60 | MITHU BUILDERS | 27.51 | 0 | 100
1255 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000032/2022-2023 | 78/PD | 17/01/2023 | 0 | Resource Division | 0.55 | 0 | 0
1256 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-III), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000002/2025-2026 | 563/PMD | 07/04/2025 | 20 | SANTU MITRA | 0.94 | 0 | 0
1257 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-II), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000003/2025-2026 | 562/PMD | 07/04/2025 | 20 | S. PATHAK & CO. | 0.96 | 0 | 0
1258 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of earthing arrangement and other works at OHR site- Babugram (Zone-VI) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | Assistant Engineer |  | ORD/000004/2025-2026 | 561/PMD | 07/04/2025 | 20 | ANUP KUMAR SAHA | 0.96 | 0 | 0
1259 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-IV), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000010/2025-2026 | 621/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.94 | 0 | 0
1260 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with other works at OHR site-IA/II , Gobag (T/W no- 1,2,3 & 4 ) under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000015/2025-2026 | 633/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.75 | 0 | 0
1261 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone IV B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000125/2023-2024 | 861/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
1262 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000648/2024-2025 | 1108/PMD | 11/07/2024 | 82 | ANUP KUMAR SAHA | 0.81 | 0 | 90
1263 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site -Salata (I-B) (Tube Well -IV) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000651/2024-2025 | 1257/PMD | 22/08/2024 | 40 | ANUP KUMAR SAHA | 0.81 | 0 | 95
1264 | Purulia Division | Raghunathpur Sub-Division | Supplying , fitting and fixing Cast Iron heavy type spiral stiar case at Ramchandrapur under Ramchandrapur W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000258/2024-2025 | 1195/PD | 26/06/2024 | 60 | MADHU SUDAN RAKSHIT | 2.7 | 0 | 100
1265 | Purulia Division | Raghunathpur Sub-Division | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 1521 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Ramchandrrapur W/S Scheme for source augmentation. | Assistant Engineer | Junior Engineer-1 | ORD/000269/2023-2024 | 1090/PD | 10/08/2023 | 839 | ANUP KUMAR SAHA | 213.35 | 0 | 70
1266 | Purulia Division | Raghunathpur Sub-Division | Supply and installtion of Pressure Shell / Pressure filter (Size- 3000 mm dia X 1800 mm) and laying of HDPE distribution pipe line at Bathanbari under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(SM Code-SM/15039) | Assistant Engineer | Junior Engineer-1 | ORD/000333/2024-2025 | 1358/PD | 25/07/2024 | 30 | M/S SAYAK BHATTACHARYA | 48.06 | 0 | 65
1267 | Purulia Division | Raghunathpur Sub-Division | Construction of appron & other work inconnection with 100 cum CWR at Ramchandrapur WTP (Zone-II) under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000533/2023-2024 | 398/RNP | 05/09/2023 | 15 | MADHU SUDAN RAKSHIT | 0.92 | 0 | 100
1268 | Purulia Division | Raghunathpur Sub-Division | Laying pipe line across railway track near Mouza-Kotaldih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000880/2023-2024 | 1530/PD | 16/10/2023 | 30 | NIBHAS SINHA | 34.55 | 0 | 100
1269 | Purulia Division | Raghunathpur Sub-Division | Laying pipe line across railway track near Mouza-Mijhardih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000881/2023-2024 | 1531/PD | 16/10/2023 | 30 | NIBHAS SINHA | 34.09 | 0 | 100
1270 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and delivery of Submersible pumping machineries at Augmentation of Ramchandrapur Water Supply Scheme, under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000050/2024-2025 | 969/PMD | 20/06/2024 | 30 | COMBINE ENTERPRISES | 1.69 | 0 | 0
1271 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at New pump house under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000051/2024-2025 | 964/PMD | 20/06/2024 | 90 | S S ENTERPRISE | 25.29 | 0 | 80
1272 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Submersible pump, MS pipe, specials including allied works in connection with direct pumping under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000631/2024-2025 | 1549/PMD | 11/11/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 2.58 | 0 | 100
1273 | Purulia Mechanical | Raghunathpur Sub-Division | Providing indoor and outdoor lighting, making double tank system and other allied works at OHR site at Rangadanga under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000632/2024-2025 | 1552/PMD | 11/11/2024 | 60 | SEN BROTHERS | 5.73 | 0 | 0
1274 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Voltage stabilizer at New Pump house for Augmentation of Ramchandrapur water supply scheme under PMD PHE Dte. in the district of Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000633/2024-2025 | 1553/PMD | 11/11/2024 | 90 | KOUSHIK CHATTERJEE | 5.99 | 0 | 0
1275 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery, Storage, Installation and Commissioning of Pre Chlorination Arrangement at WTP and High Lift site under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000643/2024-2025 | 1575/PMD | 14/11/2024 | 90 | PREMNATH MITRA | 24.94 | 0 | 0
1276 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Demand notice for renewal of 150mm dia M.S carrier pipe with 600mm dia MS casing pipe under Rly Track at Km. N305/25-27 in between Muradih-Madhukunda station by PHED/Purulia for Ramchandrapur W/s Scheme. (Letter No.Engg./TE/1/C dt.24/08/2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00072/2022-2023 | BP-2022-23-509 | 22/12/2022 | 0 | F.A &C A.O/S.E RAILWAY GURDEN | 3.34 | 0 | 0
1277 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railway miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00409/2023-2024 | BP-2023-24-302 | 14/07/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1278 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railway miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00410/2023-2024 | BP-2023-24-303 | 14/07/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1279 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-III) of augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000096/2022-2023 | 621/PD | 20/04/2022 | 45 | ASHOK KUMAR CHATTERJEE | 195.98 | 142.82 | 100
1280 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 200 mm dia DI pipe for Rising Main including allied works of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000174/2022-2023 | 791/PD | 05/05/2022 | 1123 | ASHOK KUMAR CHATTERJEE | 12.83 | 0 | 50
1281 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 150 Cum including other allied works at OHR site of Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000229/2021-2022 | 733/RNP | 06/12/2021 | 60 | MADHU SUDAN RAKSHIT | 4.59 | 4.18 | 25
1282 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 61 | UTSAV AGENCY | 0.43 | 0 | 100
1283 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Functional Household Tap Connection (FHTC including other allied works of Ramchandrapur Water Supply Scheme (Zone - III) at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza - Murulia (Jl No. 15) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000361/2021-2022 | 147/PD | 24/01/2022 | 45 | BASANTA KUMAR SINGHADEO | 68.57 | 68.57 | 95
1284 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000362/2021-2022 | 148/PD | 24/01/2022 | 90 | MADHU SUDAN RAKSHIT | 10.63 | 10.62 | 100
1285 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Ramchandrapur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000401/2022-2023 | 340/RNP | 01/06/2022 | 30 | VOYAGER | 1.4 | 1.06 | 80
1286 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000491/2021-2022 | 524/PD | 30/03/2022 | 100 | MADHU SUDAN RAKSHIT | 16.75 | 13.85 | 100
1287 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. (Zone-II) of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000600/2022-2023 | 1198/PD | 12/08/2022 | 270 | NIBHAS SINHA | 316.96 | 176.45 | 100
1288 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room, Boundary wall and Sinking of 3 (Three) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Santuri OHR campus of Santuri W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000890/2023-2024 | 1541/PD | 16/10/2023 | 474 | CHATTERJEE CONSTRUCTION | 67.71 | 0 | 45
1289 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ramchandrapur CWR,Pump House Campus (Zone -II ) under Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 217.00 mtr.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000915/2022-2023 | 1923/PD | 22/12/2022 | 889 | MADHU SUDAN RAKSHIT | 21.27 | 16.7 | 80
1290 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and renovation of existing Boundary Wall at Ramchandrapur WTP under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000919/2022-2023 | 1924/PD | 22/12/2022 | 30 | MOONLIGHT HOUSE | 4.15 | 3.98 | 100
1291 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rangadanga High School , OHR Campus under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 175 mtr.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/001622/2023-2024 | 1832/PD | 12/12/2023 | 30 | NIBHAS SINHA | 17.72 | 0 | 100
1292 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | RTOR000020/2022-2023 | 976/PD | 22/06/2022 | 0 | Resource Division | 144.33 | 0 | 0
1293 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | RTOR000024/2021-2022 | 394 | 11/03/2022 | 0 | Resource Division | 29.79 | 0 | 0
1294 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying laying different dia HDPE and DI pipe including Functional Household Tap Connection (FHTC) for distribution system (Zone-I) augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. Sl no- 1 (Tender No- 23/2021-22 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000908/2022-2023 | BP-2022-23-93 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 87.04 | 0 | 0
1295 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Guard room near intake pathway under Ramchandrapur W/ S Scheme under Raghunathpur Sub- Division, PHE Dte.(Tender No- 569/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000943/2022-2023 | BP-2022-23-101 | 16/07/2022 | 0 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0
1296 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ramchandrapur W/S Scheme Block - Santuri) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.538/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000965/2021-2022 | BP-2021-22-274 | 03/03/2022 | 0 | RADIANT | 4.26 | 0 | 0
1297 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying laying different dia HDPE and DI pipe including Functional Household Connection (FHTC) for Distribution system (Zone-I) of Augmentation of Ramchandrapur W/s Scheme. (Tender No.23/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/001125/2021-2022 | BP-2021-22-385 | 29/03/2022 | 0 | ANUP KUMAR SAHA | 42.77 | 0 | 0
1298 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for new connection at Rangadanga OHR site under Ramchandrapur water supply scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00089/2024-2025 | BP-24-25-11 | 10/05/2024 | 0 | SANTURI CCC | 2.88 | 0 | 0
1299 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for New Connection at New Pump House at Ramchandrapur | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00112/2024-2025 | BP-24-25-14 | 24/05/2024 | 0 | SANTURI CCC | 1.29 | 0 | 0
1300 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation money payment for new connection near baranti Dam | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00168/2024-2025 | BP-2024-25-32 | 21/06/2024 | 0 | SANTURI CCC | 6.19 | 0 | 0
1301 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Bill for Load Enhancement for Aug of Ramchandrapur W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00433/2023-2024 | BP-23-24-226 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.41 | 0 | 0
1302 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ramchandrapur Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000076/2021-2022 | 161/PMD | 07/03/2022 | 30 | MERCURY ENGINEERING COMPANY | 20.5 | 20.5 | 100
1303 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and External illumination work for Augmentation Ramchandrapur Water supply scheme at Existing WTP and Intake pump house , Block: santuri , Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000099/2022-2023 | 525/PMD | 05/08/2022 | 30 | MOON LIGHT HOUSE | 9.48 | 9.13 | 55
1304 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of VT pump motor , MCC Panel and other electromechanical equipment's for Raw water intake pump house at Augmentation of Ramchandrapur PWSS, Block: Santuri, Under Purulia Mechanical Division PHE Dte Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000255/2022-2023 | 46/PMD | 19/01/2023 | 803 | EASTERN INDIA SALES AND SERVICE | 65.49 | 11.04 | 100
1305 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Centrifugal pump motor sets MCC, Flowmeter to supply Zone I & II OHR with allied works at New pump house of Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000305/2022-2023 | 93/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 36.04 | 0 | 20
1306 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of automatically controlled Chlorinator having flow rate of 100 LPH and maximum pressure of 10 kg/cm2. at Augmentation of Ramchandrapur water supply scheme OHR/pump house block Santuri, under Purulia Mechanical Division PHE, Dte. district-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000306/2022-2023 | 94/PMD | 03/02/2023 | 30 | GOLAP KR. GHOSH | 1.92 | 1.27 | 0
1307 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of voltage stabilizer at WTP site and allied works for Augmentation of Ramchandrapur water supply scheme District- Purulia, under Purulia Mechanical Division PHE, Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000307/2022-2023 | 95/PMD | 03/02/2023 | 60 | MOON LIGHT HOUSE | 6.31 | 0 | 40
1308 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Vertical multistage centrifugal pump motor sets , Panel , Flow meter and all electro mechanical equipments at Augmentation of Ramchandrapur water supply scheme for direct pumping Block- Santuri, under Purulia Mechanical Division PHE Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000308/2022-2023 | 96/PMD | 03/02/2023 | 788 | EASTERN INDIA SALES AND SERVICE | 51.14 | 0 | 100
1309 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Centrifugal pump motor sets, MCC, with allied works at WTP site for Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE Dte. Dist-Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000348/2022-2023 | 133/PMD | 20/02/2023 | 60 | DEBJYOTI BASU | 34.04 | 9.53 | 100
1310 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of H.O.T. Crane at newly constructed Pump House and old pump house under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000385/2023-2024 | 371/PMD | 04/03/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 16.98 | 0 | 100
1311 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal Illumination and Yard lighting arrangement at newly Constructed Pump House under under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000386/2023-2024 | 372/PMD | 04/03/2024 | 60 | SEN BROTHERS | 11.66 | 0 | 0
1312 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 100
1313 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New service connection for khariduara OHR campus for Aug of Manbazar (part-II) W/S scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00090/2023-2024 | BP-2023-2024-73 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1314 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New service connection for Kutni OHR campus for Aug of Manbazar -II (part II) W/S scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00091/2023-2024 |  | 22/06/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1315 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR HENSLA UNDER AUGMENTATION OF MANBAZAR-II (PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00096/2023-2024 | BP-2023-2024-72 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1316 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR DANGORDI FOR AUG OF MANBAZAR -II(PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00097/2023-2024 | BP-2023-2024-71 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1317 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR KUTNI UNDER AUG OF MANBAZAR-II(PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00098/2023-2024 | BP-2023-2024-74 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1318 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement for high pressure testing of Sub -Station equipment for 500 KVA Sub - Station at Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE,Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2024-2025 | 971/PMD | 20/06/2024 | 30 | TAPAN KUMAR DEY | 1.19 | 0 | 100
1319 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of old centrifugal pump motor sets by the new pump motor set with supply and installation of Scada compatible MCC panel at clear water pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000066/2023-2024 | 553/PMD | 16/05/2023 | 60 | RABINDRA NATH KHAN | 110.31 | 0 | 100
1320 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of Rupture & multiple jointed LT Cable line from clear water pump house to Intake pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2023-2024 | 554/PMD | 16/05/2023 | 60 | ANUP KR. SAHA | 42.18 | 0 | 100
1321 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2023-2024 | 555/PMD | 16/05/2023 | 60 | TAPAN KUMAR DEY | 61.95 | 0 | 95
1322 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-1) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2023-2024 | 556/PMD | 16/05/2023 | 60 | SWAPAN ENTERPRISE | 21.65 | 0 | 10
1323 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-2) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000070/2023-2024 | 557/PMD | 16/05/2023 | 60 | NUPUR CHANDRA HALDER | 21.66 | 0 | 65
1324 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-3) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000071/2023-2024 | 558/PMD | 16/05/2023 | 60 | GOENKA ENTERPRISE | 21.65 | 0 | 100
1325 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-4) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2023-2024 | 559/PMD | 16/05/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 21.65 | 0 | 100
1326 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing gaseous chlorination system at Manbazar-2(Part) w/s Scheme under Purulia mechanical Division, PHE, Dte. in the purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000073/2023-2024 | 561/PMD | 16/05/2023 | 60 | ASHOKE ADHIKARY | 15.5 | 0 | 100
1327 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-5) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000074/2023-2024 | 560/PMD | 16/05/2023 | 60 | H K DAS AND CO | 21.65 | 0 | 100
1328 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of internal & external lighting arrangement at conference hall & allied premises of awareness generation cum water sample collection centre at Mouza-ghat Block - Manbazar-2 under Purulia Mechanical Division under PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000077/2023-2024 | 581/PMD | 19/05/2023 | 30 | PREMNATH MITRA | 11.92 | 0 | 70
1329 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Installation of One no submersible pumping machinery at intake pump house with supply and installation of Scada compatible MCC panel at Manbazar-II (part) w/s scheme under PMD, PHE, Dte. in the district of purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2023-2024 | 582/PMD | 19/05/2023 | 60 | TAPAN KUMAR DEY | 26.38 | 0 | 60
1330 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Manbazar Water Supply scheme Block Manbazar-I under PMD PHE Dte. District Purulia. (2nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000218/2023-2024 | 1203/PMD | 03/11/2023 | 90 | PRINCE INDUSTRIES (INDIA) | 21.5 | 0 | 0
1331 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing and Installation of Electro-Mechanical Equipment¿s at Intake, Clear water Pump House and 5 nos. OHRs in Manbazar-II (Part) water supply scheme under Purulia Mechanical Division, PHE, Dte., District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000637/2024-2025 | 1569/PMD | 14/11/2024 | 90 | EASTERN INDIA SALES AND SERVICE | 80.69 | 0 | 0
1332 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Making fencing boundry at Transformer Yard of Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000690/2024-2025 | 1702/PMD | 06/12/2024 | 360 | TAPAN KUMAR DEY | 1.53 | 0 | 100
1333 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIA) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-8) | Assistant Engineer |  | ORD/000267/2023-2024 | 1041/PD | 04/08/2023 | 606 | DEBAKI RANJAN SARKAR | 310.01 | 0 | 60
1334 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-VIB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-9) | Assistant Engineer |  | ORD/000268/2023-2024 | 1021/PD | 01/08/2023 | 270 | SWAPAN MANDAL | 280.53 | 57.92 | 35
1335 | Purulia Division | Raghunathpur Sub-Division | Repairing of DI Rising Main, construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(One) no tubewell at OHR Sites of (Zone - VI B) of Raghunathpur Water Supply Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 180 m) | Assistant Engineer |  | ORD/000336/2024-2025 | 1362/PD | 25/07/2024 | 525 | BASANTA KUMAR SINGHADEO | 24.88 | 0 | 0
1336 | Purulia Division | Raghunathpur Sub-Division | Repairing & Renovation of Existing Rising Main and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL No.4) | Assistant Engineer |  | ORD/000904/2023-2024 | 1578/PD | 30/10/2023 | 823 | ANUP KUMAR SAHA | 300.79 | 0 | 65
1337 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 278 cum and other allied works under Raghunathpur W/S Scheme (Zone-VI-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001167/2024-2025 | 2321/PD | 31/12/2024 | 516 | CHAIL CONSTRUCTION | 11.41 | 0 | 0
1338 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room Cum Chlorin Room at Zone-VI B (Babugram) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001360/2023-2024 | 1729/PD | 04/12/2023 | 100 | SAANVI CONSTRUCTION | 4.81 | 0 | 100
1339 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000034/2022-2023 | 74/PD | 17/01/2023 | 0 | Resource Division | 1.75 | 0 | 0
1340 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new service connection at Zone-VI OHR(Babugram) site under Raghunathpur Aug. water supply scheme. | Assistant Engineer |  | BILL/00288/2024-2025 | BP-24-25-75 | 02/08/2024 | 0 | WBSEDCL PURULIA | 6.21 | 0 | 0
1341 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with allied works at OHR site-VII B, Ketlapur under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000014/2025-2026 | 634/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.49 | 0 | 0
1342 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VI B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000122/2023-2024 | 803/PMD | 12/07/2023 | 30 | MERCURY ENGINEERING COMPANY | 21.6 | 0 | 0
1343 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-I), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000965/2024-2025 | 517/PMD | 28/03/2025 | 20 | SUJIT MUKHERJEE | 0.99 | 0 | 0
1344 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000133/2024-2025 | 903/PD | 07/05/2024 | 60 | CHATTERJEE CONSTRUCTION | 95.89 | 0 | 0
1345 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000134/2024-2025 | 904/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 95.99 | 0 | 0
1346 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Purulia-I (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000148/2024-2025 | 919/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 61 | 0 | 50
1347 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Balarampur (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000225/2025-2026 | 1090/PD | 17/06/2025 | 120 | M/S SB CONSTRUCTION | 28.5 | 0 | 0
1348 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000226/2025-2026 | 1094/PD | 17/06/2025 | 120 | PRAKASH DESHMUKH | 28.73 | 0 | 0
1349 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - II, III & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000227/2025-2026 | 1096/PD | 17/06/2025 | 120 | SOUHARDYA BUSINESS LINE | 49.99 | 0 | 0
1350 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - VI, VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000228/2025-2026 | 1097/PD | 17/06/2025 | 120 | SUJIT SAHANA | 49.71 | 0 | 0
1351 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II, IV & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000229/2025-2026 | 1100/PD | 17/06/2025 | 120 | SAHADEV HALDER | 50.09 | 0 | 0
1352 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Bandwan (Zone - VII, XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2025-2026 | 1088/PD | 17/06/2025 | 120 | BLUEDOT CONSTRUCTION | 43.22 | 0 | 0
1353 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000233/2025-2026 | 1095/PD | 17/06/2025 | 120 | MAA SARADA CONSTRUCTION | 28.82 | 0 | 0
1354 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000237/2025-2026 | 1089/PD | 17/06/2025 | 120 | PURNIMA ELECTRICS AND DECORATORS | 28.82 | 0 | 0
1355 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Balarampur (Zone - IX&X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000238/2025-2026 | 1093/PD | 17/06/2025 | 120 | PARADISE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 28.84 | 0 | 0
1356 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution pipe line and providing FHTC including other allied work & Operation & Maintenance of Distribution, pipe line (Dt/HDPE),including Sluce Valve & FHTC for the period of thirty six (36) month at zone-Ix of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (Sl No.6) | Assistant Engineer |  | ORD/000271/2023-2024 | 1099/PD | 14/08/2023 | 540 | JAL PRAVAHIKA PVT. LTD. | 492.94 | 0 | 40
1357 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - IX, XI & XII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000273/2025-2026 | 1098/PD | 17/06/2025 | 120 | SOUMYAJIT SAHANA | 49.71 | 0 | 0
1358 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-4) | Assistant Engineer |  | ORD/000274/2023-2024 | 1092/PD | 14/08/2023 | 270 | SAMAN KUMAR MAHATO | 184.53 | 0 | 0
1359 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XV& XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000274/2025-2026 | 1092/PD | 17/06/2025 | 120 | BABA LOKNATH WORKS CONTRACTOR | 28.73 | 0 | 0
1360 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-11) | Assistant Engineer |  | ORD/000276/2023-2024 | 1108/PD | 16/08/2023 | 270 | MS D.PALIT AND CO. | 400.45 | 0 | 0
1361 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-12) | Assistant Engineer |  | ORD/000277/2023-2024 | 1104/PD | 14/08/2023 | 270 | ANUP KUMAR SAHA | 449.89 | 0 | 0
1362 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-2) | Assistant Engineer |  | ORD/000279/2023-2024 | 1095/PD | 14/08/2023 | 270 | MS D.PALIT AND CO. | 478.83 | 0 | 0
1363 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - I, IV & X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000331/2025-2026 | 1427/PD | 05/08/2025 | 120 | M/S BHABATARAN MEHTA | 42.84 | 0 | 0
1364 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VIII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000362/2025-2026 | 1521/PD | 19/08/2025 | 120 | KOUSHIK CHATTERJEE | 16.63 | 0 | 0
1365 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Bandwan (Zone - XV & XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000369/2025-2026 | 1529/PD | 19/08/2025 | 120 | ROY CONSTRUCTION | 28.49 | 0 | 0
1366 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000442/2024-2025 | 1504/PD | 27/08/2024 | 45 | RANJIB GHATAK | 21.02 | 0 | 100
1367 | Purulia Division | Purulia Sadar Sub-Division | Left out laying of Distribution Pipe Line for distribution System at Chatambari Mouza under command area of Jhalda Rural W/S Scheme Under Purulia W/S Scheme (Southern Sector) of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2024-2025 | 1507/PD | 27/08/2024 | 45 | BHAGABAN DAS KUMAR | 2.73 | 0 | 100
1368 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Balarampur (Zone - I, II & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000621/2025-2026 | 1099/PD | 17/06/2025 | 120 | M/S. SAJEDA ENTERPRISE | 50.11 | 0 | 0
1369 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-I of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-8) | Assistant Engineer |  | ORD/000905/2023-2024 | 1574/PD | 30/10/2023 | 270 | BOSE CONSTRUCTION | 181.34 | 0 | 0
1370 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-II & III of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (SL No.2) | Assistant Engineer |  | ORD/000909/2023-2024 | 1584/PD | 30/10/2023 | 790 | DEBAKI RANJAN SARKAR | 667.42 | 0 | 50
1371 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-V & VI of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.10) | Assistant Engineer |  | ORD/000914/2023-2024 | 1579/PD | 30/10/2023 | 945 | ANUP KUMAR SAHA | 982.47 | 0 | 40
1372 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-II under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001037/2024-2025 | 2097/PD | 05/12/2024 | 60 | CHINMOY SEN | 26.6 | 0 | 0
1373 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-XI under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001038/2024-2025 | 2098/PD | 05/12/2024 | 60 | INDRAJIT SARKAR | 19.27 | 0 | 0
1374 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-V under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001039/2024-2025 | 2099/PD | 05/12/2024 | 60 | BANERJEE CONSTRUCTION | 23.55 | 0 | 0
1375 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-III under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001072/2024-2025 | 2095/PD | 05/12/2024 | 60 | M D CONSTRUCTION | 25.74 | 0 | 0
1376 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001073/2024-2025 | 2167/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 84.97 | 0 | 0
1377 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-I under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001088/2024-2025 | 2094/PD | 05/12/2024 | 60 | ARATI MAHATO | 22.53 | 0 | 0
1378 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-X under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001101/2024-2025 | 2191/PD | 13/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 22.55 | 0 | 0
1379 | Purulia Division | Purulia Sadar Sub-Division | Laying of Distribution pipeline From Balarampur Bihari Bandh to Rail Phatak (bagmundiRoad ) at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001109/2024-2025 | 2201/PD | 13/12/2024 | 60 | SADHAN GORAIN | 83.98 | 0 | 0
1380 | Purulia Division | Purulia Sadar Sub-Division | Laying of Distribution pipeline From Balarampur OHR site CWR to Petrol Pump near Bihari bandh at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001110/2024-2025 | 2202/PD | 13/12/2024 | 60 | SADHAN GORAIN | 93.97 | 0 | 0
1381 | Purulia Division | Purulia Sadar Sub-Division | Repairing of existing AC/UPVC distribution pipeline due to widening of PWD Road ,Laying of Rising main Pipeline for Jica Projects on Emergency basis and Relevant other allied works at Manbazar-1 under Purulia W/S Scheme under Purulia Division,PHEDte | Assistant Engineer |  | ORD/001111/2024-2025 | 2203/PD | 13/12/2024 | 60 | MACHINO TECHNO | 10.39 | 0 | 100
1382 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001114/2024-2025 | 2206/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 87.13 | 0 | 0
1383 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001116/2024-2025 | 2164/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.04 | 0 | 0
1384 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001141/2024-2025 | 44/PD | 10/01/2025 | 45 | SUDHANSHU OJHA | 19.2 | 0 | 0
1385 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-XV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001206/2024-2025 | 111/PD | 21/01/2025 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.32 | 0 | 0
1386 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001224/2024-2025 | 2208/PD | 13/12/2024 | 60 | AKHANDAMRIT METALS PRIVATE LIMITED | 68.26 | 0 | 0
1387 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001225/2024-2025 | 2199/PD | 13/12/2024 | 60 | INFINITE INFRATECH EPC | 85.98 | 0 | 0
1388 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Ajodhya Hill of Baghmundi Block (Zone-XIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001226/2024-2025 | 2207/PD | 13/12/2024 | 60 | ELITE ENGINEERING AND CONSTRUCTION | 96.42 | 0 | 0
1389 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-II Bandwan Block within Southern Sector Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001328/2024-2025 | 476/PD | 25/03/2025 | 150 | GANGULY ENTERPRISES | 15.52 | 0 | 0
1390 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-III Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001332/2024-2025 | 480/PD | 25/03/2025 | 150 | AMITAVA KUNDU | 16.52 | 0 | 0
1391 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001337/2024-2025 | 483/PD | 25/03/2025 | 150 | ROY CONSTRUCTION | 15.71 | 0 | 0
1392 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001341/2024-2025 | 490/PD | 25/03/2025 | 150 | MOONLIGHT HOUSE | 16.2 | 0 | 0
1393 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001346/2024-2025 | 495/PD | 25/03/2025 | 150 | SINGHA ENTERPRISE | 16.53 | 0 | 0
1394 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-III Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001349/2024-2025 | 497/PD | 25/03/2025 | 150 | CHANCHAL MISHRA | 16.61 | 0 | 0
1395 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IX Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001353/2024-2025 | 501/PD | 25/03/2025 | 150 | SANJAY KUMAR NARSARIA | 16.69 | 0 | 0
1396 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XI Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001365/2024-2025 | 503/PD | 25/03/2025 | 150 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0
1397 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-X Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001366/2024-2025 | 502/PD | 25/03/2025 | 150 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0
1398 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte.(Mouza-Gagnabad , Habitation-Bauripara, Gagnabaid ,Kalu Para ,Pakhirdanga Mouza-Ghorakata(P)Habitation-Ghorakata , Mouza-Jhariatdi (P),Habitation-Jhriadihi,Mouza-Manpura , Habitation-Ganpandi,Manpura, Mouza-Narayangar Alias Karka, Habitation-Kanka,Narayan Nagar.) | Assistant Engineer | Junior Engineer-1 | ORD/000154/2020-2021 | 1407/PD | 29/12/2020 | 45 | M/S KARUNAMOYEE CONSTRUCTION | 55.9 | 111.64 | 0
1399 | Purulia Division | Raghunathpur Sub-Division | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000179/2023-2024 | 995/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 6.21 | 0 | 100
1400 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | Assistant Engineer | Junior Engineer-1 | ORD/000291/2020-2021 | 180/PD | 02/02/2021 | 45 | SADHAN GORAIN | 131.09 | 60.43 | 100
1401 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Gosaidanga,Jhariardi , Kamalasthan) (Tender No. 37/SE/PMU of 2020-21) | Assistant Engineer | Junior Engineer-1 | VCH/000949/2021-2022 | BP-2021-22-247 | 16/02/2022 | 0 | PREMNATH MITRA | 29.4 | 0 | 0
1402 | Purulia Division | Raghunathpur Sub-Division | Additional works for functional house hold tap connection (FHTC) including other allied works of Augmentation Arrah W/s Scheme (Zone-II) of Kashipur Block. (Tender No. 853/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-1 | VCH/001005/2021-2022 | BP-2021-22-264 | 28/02/2022 | 0 | SHYAMAL KUMAR DEY | 4.53 | 0 | 0
1403 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Aug. Arrah Water Supply Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) Gagnabad (Part-B) (Tender No.856/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-1 | VCH/001021/2021-2022 | BP-2021-22-265 | 28/02/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 3.73 | 0 | 0
1404 | Purulia Division | Raghunathpur Sub-Division | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-1 | VCH/001111/2021-2022 | BP-2021-22-371 | 29/03/2022 | 0 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0
1405 | Purulia Division | Raghunathpur Sub-Division | Supply & laying different dia HDPE pipe line Adra DHR to Gosaidanga under Arrah W/s Scheme. (Tender No.919/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-1 | VCH/001115/2021-2022 | BP-2021-22-342 | 25/03/2022 | 0 | RABIN CHANDRA CHAIL | 21.59 | 0 | 0
1406 | Purulia Division | Raghunathpur Sub-Division | Supplying , fitting and fixing Cast Iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000580/2022-2023 | 492/RNP | 02/08/2022 | 10 | SUBHAS CHANDRA MAHATO | 1.58 | 0 | 95
1407 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Gosaindih, Parbeliya, Gopaldhawh, Parbeliya City under Bhamuria & Saltore G.P) (493 nos.) (Tender No.324/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000811/2021-2022 | BP-2021-22-227 | 03/02/2022 | 0 | TAPAN CHANDRA | 22.48 | 0 | 0
1408 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B ( Mouza- Parbeliya City , Parbelia under Bhamuria & Saltore G.P). (1364Nos.) (Tender No. 402/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-3 | VCH/000887/2021-2022 | BP-2021-22-243 | 16/02/2022 | 0 | ASHOK KUMAR CHATTERJEE | 49.23 | 0 | 0
1409 | Purulia Division | Raghunathpur Sub-Division | Supplying fitting and fixing cast iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 544/2022-23 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/001050/2022-2023 | BP-2022-23-394 | 20/10/2022 | 0 | SUBHAS CHANDRA MAHATO | 1.43 | 0 | 0
1410 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (3331 Nos.) | Assistant Engineer | Junior Engineer-3 | ORD/000332/2020-2021 | 242/PD | 10/02/2021 | 60 | SANTANU BANERJEE | 154.04 | 174.43 | 0
1411 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Sutabai W/s Scheme at Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. (3331 Nos.) (Tender No. 35/SE/PMU of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/000872/2020-2021 | BP-2021-22-39 | 19/07/2021 | 0 | SANTANU BANERJEE | 66.81 | 0 | 0
1412 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00077/2022-2023 | BP-2022-23-5171 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.23 | 0 | 0
1413 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00090/2022-2023 | BP-2022-23-5177 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.09 | 0 | 0
1414 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Bank guarantee of Proposed Way Leave permission of Water pipe line Crossing for application ID No SER ADA-2022 WL 38, SER ADA-2022 WL 42. SER ADA 2022 WL 43, SER- ADA 2022 WL-55. SER-ADA-2022-WL-56. SER-ADA-2022 WL-60, SER ADA 2022 WL-61. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00175/2022-2023 |  | 08/02/2023 | 0 | F.A & C.A.O /S.E.RLY /GARDEN REACH-43 | 5 | 0 | 0
1415 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0
1416 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
1417 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supply of stationery materials for office use | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00988/2024-2025 | BP-2024-25-531 | 20/11/2024 | 0 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0
1418 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Lagda river site for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000029/2023-2024 | 573/PD | 19/04/2023 | 90 | SWASTIK ENTERPRISE | 14.23 | 10.41 | 80
1419 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of meter room, panel room,undercut pump house & surface drain with other allied works at Lagda OHR Site for Augmentation of Lagda W/S Scheme under Purulia sader Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000036/2023-2024 | 554/PD | 13/04/2023 | 45 | CHITTARANJAN MAJHI | 13.87 | 5.76 | 100
1420 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI rising main pipeline & repairing of FHTC & construction of pathway including other allied works of existing godown, store room, pump room & buildings at Purulia Sadar Sub-Division under Augmentation of Lagda Water supply scheme of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000214/2024-2025 | 1082/PD | 07/06/2024 | 60 | SIKHA ENTERPRISE | 43.73 | 0 | 100
1421 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000293/2021-2022 | 1585/PD | 17/12/2021 | 30 | KOUSHIK CHATTERJEE | 17.14 | 11.02 | 55
1422 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000294/2021-2022 | 1586/PD | 17/12/2021 | 30 | MANATOSH SINGH | 11.25 | 5.7 | 55
1423 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Making bypass arrangement & other allied works at lagda OHR site of Lagda W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000348/2024-2025 | 1378/PD | 25/07/2024 | 60 | M/S CHAKRABORTY CONSTRUCTION | 4.32 | 0 | 100
1424 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000381/2021-2022 | 183/PD | 31/01/2022 | 45 | GOUTAM CHAKRABORTY | 112.43 | 25.38 | 39
1425 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-B : Water Supply through direct pumping at Lagda Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000400/2021-2022 | 217/PD | 08/02/2022 | 45 | SADHAN GORAIN | 237.24 | 53.06 | 100
1426 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha river site pump house of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000490/2021-2022 | 526/PD | 30/03/2022 | 200 | KM ENTERPRISES | 10.81 | 0 | 100
1427 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. w.e.f. 14/09/2025 to 15/03/2025 | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000548/2025-2026 | 515/PSD | 11/09/2025 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0
1428 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f 14/09/2025 to 15/03/2025) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000551/2025-2026 | 523/PSD | 11/09/2025 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0
1429 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of different dia distribution pipeline (Additional length) in connection with JJM and JAL SAPNA at different habitation under command area of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000632/2022-2023 | 1400/PD | 01/09/2022 | 45 | GOUTAM CHAKRABORTY | 12.14 | 11.98 | 100
1430 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of existing 200mm and 150 mm DI rising main pipeline and Providing Functinal household tap connection (FHTC) at Baligara Village and Laying of HDPE pipe and MS Casing Pipe and other allied works under Lagda W/S Scheme under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000657/2023-2024 | 1351/PD | 13/09/2023 | 30 | GOUTAM CHAKRABORTY | 14.54 | 13.35 | 100
1431 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works in connection with Jal Jeevan Mission (JJM) and JAL SAPNA for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000831/2022-2023 | 1721/PD | 22/11/2022 | 100 | SWASTIK ENTERPRISE | 16.82 | 8.8 | 65
1432 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of distribution pipeline including placement of sluice valves at different places for providing 47 nos. Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at BALIGARA village under command area of Augmentation of LAGDA Water Supply Scheme of Purulia-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000864/2022-2023 | 1817/PD | 06/12/2022 | 90 | M/S CHAKRABORTY CONSTRUCTION | 14.17 | 4.73 | 95
1433 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001008/2022-2023 | 175/PD | 07/02/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 21.28 | 0 | 100
1434 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha OHR site of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001013/2021-2022 | 527_PD | 30/03/2022 | 100 | SOUVIK MANDAL | 10.83 | 0 | 0
1435 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI rising main pipeline & renovation of R.C.C. Elevated Reservoir of capacity 135 Cum (Intze Type), at headwork site of Lagda W/S Scheme including repairing of Pump house cum switch room (Unit-I&II) including other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001048/2022-2023 | 280/PD | 27/02/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 10.29 | 8.55 | 100
1436 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Interconnection of new & old DI rising main with new pump house & other allied works for direct supply & pathway of Lagda Water Supply Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001062/2024-2025 | 2123/PD | 05/12/2024 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.77 | 0 | 100
1437 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line LagdaRiversite Pump House to 100 Cum Capacity CWR at Lagda OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001313/2023-2024 | 1706/PD | 04/12/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 1.46 | 0 | 100
1438 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying Parallel HDPE pipe and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Puncha W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.( under Lagda Water Supply Scheme ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003495/2023-2024 | 346/PD | 04/03/2024 | 186 | JAYANTA KUMAR MONDAL | 21.97 | 0 | 100
1439 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of pathway at Ajodhya Pump House under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. Length : 115.00 Mtr. Width : 2.40 Mtr.(Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003953/2023-2024 | 495/PD | 16/03/2024 | 30 | TUMPA GORAIN | 4.13 | 0 | 0
1440 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Cleaning & Fencing at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003955/2023-2024 | 497/PD | 16/03/2024 | 45 | SARKAR ENTERPRISE | 1.08 | 0 | 100
1441 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Barudi Mouza) (Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003968/2023-2024 | 512/PD | 16/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 11.24 | 0 | 0
1442 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of Branch distribution Pipeline of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Goaladih Mouza] (Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003969/2023-2024 | 513/PD | 16/03/2024 | 60 | SOUMITRA CHAKRABORTY | 4.43 | 0 | 100
1443 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Kotshila Mouza) (Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003970/2023-2024 | 514/PD | 16/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.13 | 0 | 0
1444 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Uparbatri Mouza) (Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003971/2023-2024 | 515/PD | 16/03/2024 | 60 | SOUVIK MANDAL | 5.55 | 0 | 100
1445 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chayadih Mouza) (Under Lagda W/S Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003972/2023-2024 | 516/PD | 16/03/2024 | 60 | SABYASACHI MISHRA | 7.82 | 0 | 70
1446 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/004345/2023-2024 | 662_PD | 17/05/2023 | 534 | ASHOKE ADHIKARY | 14.24 | 0 | 60
1447 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000004/2021-2022 | 1507/PD | 13/12/2021 | 0 | Resource Division | 51.27 | 0 | 0
1448 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) (Ad-interim) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000146/2022-2023 | BP-2022-23-37 | 28/04/2022 | 0 | GOUTAM CHAKRABORTY | 50 | 0 | 0
1449 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of Augmantation of Lagda W/S Scheme. (Part-A W/S through OHR at Baligara @ Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000180/2022-2023 | BP-2022-23-45 | 02/05/2022 | 0 | GOUTAM CHAKRABORTY | 16.95 | 0 | 0
1450 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 357/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000938/2022-2023 | BP-2022-23-109 | 16/07/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.05 | 0 | 0
1451 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 848/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000939/2022-2023 | BP-2022-23-110 | 16/07/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.91 | 0 | 0
1452 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation and extension of distribution pipe line under command area of Augmentation of Lagda Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. [Part-B water supply through direct pumping at Lagda mouza] (Tender No- 21/2021-22 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000975/2022-2023 | BP-2022-23-145 | 22/07/2022 | 0 | SADHAN GORAIN | 94.59 | 0 | 0
1453 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Augmentation of River site of Lagda W/S, block- Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00863/2023-2024 | BP-23-24-298 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.63 | 0 | 0
1454 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Augmentation OHR site of Lagda W/S | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00866/2023-2024 | BP-23-24-301 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.04 | 0 | 0
1455 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lagda Water Supply scheme Block Purulia-I under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2021-2022 | 164/PMD | 07/03/2022 | 30 | ASHUTOSH DAS AND CO. | 20.5 | 8.8 | 90
1456 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Providing internal and external illumination arrangement at existing at OHR site of Lagda W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000154/2023-2024 | 650/PMD | 08/06/2023 | 60 | TUSHAR GHOSH | 6.13 | 0 | 90
1457 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tube well with supply of necessary substitutes at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000345/2022-2023 | 130/PMD | 20/02/2023 | 1046 | SANTANU BANERJEE | 26.09 | 6.24 | 40
1458 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of centrifugal pumping machineries, Flowmeter with necessary substitutes and allied electrical panel at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000346/2022-2023 | 131/PMD | 20/02/2023 | 701 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.89 | 20.5 | 70
1459 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at OHR site of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000368/2022-2023 | 210/PMD | 28/02/2023 | 672 | TUSHAR GHOSH | 7.07 | 0 | 90
1460 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible Pump motor and other related works for Augmentation work of Lagda w/s scheme (OHR Site) under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000387/2023-2024 | 373/PMD | 04/03/2024 | 515 | GOUTAM CHAKRABORTY | 4.73 | 0 | 50
1461 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at Augmentation of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000468/2022-2023 | 308/PMD | 16/03/2023 | 30 | GOUTAM CHAKRABORTY | 11.85 | 8.05 | 70
1462 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000001/2023-2024 | 610/PMD | 01/06/2023 | 0 | Resource Division | 0.86 | 0 | 0
1463 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Bill paid for Way leave Facility Charge of Rail Bhumi Crossing Seva (IR-RBCS) under South Eastern Railway, Ranchi Divison against Application ID:SER-RNC-2022-WL-8, 9, 10 dt.22/11/2022. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00009/2022-2023 | BP-2022-23-459 | 05/12/2022 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 33.83 | 0 | 0
1464 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00085/2022-2023 | BP-2022-23-5172 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 37.72 | 0 | 0
1465 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00086/2022-2023 | BP-2022-23-5173 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 8.79 | 0 | 0
1466 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Restoration of only Hard Shoulder of Purulia Ranchi Road under PWD Purulia Division from Rakbore more to Adardih Bridge after laying of Drinking water pipeline of Kotshila W/S Scheme under Jal-Jeban Mission of PHE Dte, Purulia in the District of Purulia during the year 2022-2023. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00182/2023-2024 | BP-2023-24-209 | 08/06/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 23.61 | 0 | 0
1467 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
1468 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Office stationary bill supply & bill paid for the Bill No.765,770,785,848,850,839,840,841,842,849,845,847,837,838 & 836. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01797/2023-2024 | BP-2024-25-261 | 24/07/2024 | 0 | KETIKA CONSUMERS CO-OP STORES LTD | 4.31 | 0 | 0
1469 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Pipeline from Jiudaru Mouza to Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2023-2024 | 699/PD | 22/05/2023 | 90 | RAJAT KARMAKAR | 30.33 | 0 | 10
1470 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Pipeline from Kachahatu Mouza to Jiudaru Mouza & Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2023-2024 | 700/PD | 22/05/2023 | 90 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 84.69 | 0 | 100
1471 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Adardih Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000087/2023-2024 | 818/PD | 26/06/2023 | 45 | SUSANTA KR DUTTA | 10.03 | 0 | 100
1472 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Parallel line at Jiudaru Mouza and Branch Line and Gap portion of Hanslata Mouza under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2023-2024 | 868/PD | 30/06/2023 | 30 | RAJAT KARMAKAR | 11.46 | 8.99 | 100
1473 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI Rising main (K-9) including laying of Parallel line at Jiudaru Mouza under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000166/2023-2024 | 937/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 95.31 | 0 | 80
1474 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of DI Pipeline Rising main (K-9) including laying of Parallel line at Barudi Mouza for Providing FHTC under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000167/2023-2024 | 938/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 78.98 | 0 | 100
1475 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Withdrawing & Relaying of DI(K-9) rising main pipeline including cleaning of chokage & laying of parallel pipeline at Kotshila water supply scheme under Purulia Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000168/2023-2024 | 939/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 87.21 | 0 | 70
1476 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 250 mm and 150 mm dia DI (K9) pipe as rising main from riverside pump house site to OHR site under Kotshila Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000318/2022-2023 | 849/PD | 23/05/2022 | 60 | GLOBAL CONSTRUCTION | 75.85 | 0 | 0
1477 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room from Kotshila Pump House to distribution area through distribution main of Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000327/2022-2023 | 859/PD | 23/05/2022 | 100 | CHOUDHURY STONE CRUSHING | 16.65 | 0 | 50
1478 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC Clear water reservoir (CWR) of capacity 150 Cum with other allied works at Kotshila pumphouse under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000329/2022-2023 | 860/PD | 23/05/2022 | 90 | BOSE CONSTRUCTION | 17.45 | 0 | 65
1479 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Kotshila W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000330/2022-2023 | 861/PD | 23/05/2022 | 30 | KOUSHIK CHATTERJEE | 11.39 | 2.8 | 100
1480 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with Construction of 1 nos Common Manifold Chamber at Kotshila river site of Kotshila W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000331/2022-2023 | 862/PD | 23/05/2022 | 30 | BOSE CONSTRUCTION | 23.05 | 6.48 | 100
1481 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chayadih) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000338/2022-2023 | 872/PD | 23/05/2022 | 60 | APURBA PATRA | 46.84 | 29.95 | 70
1482 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chaitandih) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000340/2022-2023 | 874/PD | 23/05/2022 | 30 | PRATIK SAHA | 23.33 | 10.63 | 75
1483 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Adardih) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000341/2022-2023 | 875/PD | 23/05/2022 | 1001 | SUSANTA KR DUTTA | 40.45 | 9.58 | 90
1484 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chiruhatu) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000342/2022-2023 | 876/PD | 23/05/2022 | 45 | GOUTAM CHAKRABORTY | 46.54 | 14.8 | 85
1485 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Uparbatri) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000407/2022-2023 | 938/PD | 16/06/2022 | 1110 | SWAPAN MANDAL | 116.02 | 60.06 | 80
1486 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000522/2022-2023 | 1041/PD | 07/07/2022 | 970 | ANUP KUMAR SAHA | 82.11 | 0 | 85
1487 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Timangda) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000523/2022-2023 | 1039/PD | 07/07/2022 | 45 | MANATOSH SINGH | 44.34 | 22.59 | 80
1488 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Shyampur) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000524/2022-2023 | 1042/PD | 07/07/2022 | 945 | S. R. ENTERPRISE | 64.93 | 49.82 | 92
1489 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Murulahar ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000525/2022-2023 | 1043/PD | 07/07/2022 | 60 | PARTHA PRATIM CHHATAIT | 91.56 | 21.28 | 70
1490 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000526/2022-2023 | 1044/PD | 07/07/2022 | 970 | ANUP KUMAR SAHA | 74.83 | 0 | 85
1491 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Tiraldih or Goaladih) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000528/2022-2023 | 1058/PD | 08/07/2022 | 60 | SOUMITRA CHAKRABORTY | 56.18 | 40.82 | 100
1492 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000529/2022-2023 | 1059/PD | 08/07/2022 | 60 | NANIGOPAL DEY | 33.35 | 0 | 90
1493 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Ghatketia) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000530/2022-2023 | 1057/PD | 08/07/2022 | 30 | ROY CONSTRUCTION | 9.1 | 3.24 | 0
1494 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Nowahatu) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000531/2022-2023 | 1056/PD | 08/07/2022 | 45 | MOLLA ENTERPRISE | 23.78 | 0 | 0
1495 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Jiudaru) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000532/2022-2023 | 1043/A/PD | 07/07/2022 | 60 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 64.02 | 24.07 | 35
1496 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Banahatu) Zone-ii | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000538/2022-2023 | 1055/PD | 08/07/2022 | 1362 | SUBODH PRAMANIK | 58.54 | 46.37 | 90
1497 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Panroma) Zone-ii | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000539/2022-2023 | 1054/PD | 08/07/2022 | 45 | M/S. MSS RISING ENTERPRISE | 36.04 | 23.35 | 65
1498 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hanslata) Zone-ii | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000540/2022-2023 | 1053/PD | 08/07/2022 | 45 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 21.95 | 13.76 | 100
1499 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Kachahatu) Zone-II | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000549/2022-2023 | 1079/PD | 12/07/2022 | 45 | PRAVAT SARKAR | 111.73 | 63.2 | 65
1500 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hetbatari) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000601/2022-2023 | 1226/PD | 22/08/2022 | 30 | SARKAR ENTERPRISE | 15.98 | 2.79 | 25
1501 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Transformer base for Installing Transformer and Cable Trench for HT & LT Line at Kotshila Pump House Campus under Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE DTE . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000856/2022-2023 | 1807/PD | 06/12/2022 | 45 | SAIBAL SARKAR | 15.18 | 5.65 | 0
1502 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Over Head Reservoir (OHR) of 750 Cum Capacity, Staging Height 20 mtr. at BDO office Campus at Kotshila under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000912/2022-2023 | 1887/PD | 15/12/2022 | 270 | ANUP KUMAR SAHA | 161.06 | 97.61 | 100
1503 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Boundary wall at Kachahatu Pump House Site under Kotshila W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000997/2022-2023 | 110/PD | 20/01/2023 | 30 | KANAILAL PAL | 14.97 | 0 | 100
1504 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Pipeline from Kachahatu Riversite Pump House to Banahata Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001010/2022-2023 | 177/PD | 07/02/2023 | 45 | SUBODH PRAMANIK | 88.16 | 0 | 100
1505 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division underPurulia Division, PHE Dte (Goaladih Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001012/2022-2023 | 179/PD | 07/02/2023 | 30 | SB CONSTRUCTION | 6.47 | 5.3 | 90
1506 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chitarpur Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001014/2022-2023 | 181/PD | 07/02/2023 | 30 | NANIGOPAL DEY | 2.71 | 0 | 90
1507 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001047/2022-2023 | 279/PD | 27/02/2023 | 30 | S. R. ENTERPRISE | 10.39 | 0 | 60
1508 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Parallel Distribution Pipeline at Banahatu Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001060/2022-2023 | 292/PD | 27/02/2023 | 45 | M/S SAWDESH ENTERPRISE | 28.73 | 21.61 | 100
1509 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 280mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001061/2022-2023 | 293/PD | 27/02/2023 | 45 | GOUTAM CHAKRABORTY | 81.35 | 63.02 | 100
1510 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 300mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001063/2022-2023 | 294/PD | 27/02/2023 | 45 | KM ENTERPRISES | 52.23 | 40.78 | 100
1511 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Main Line & Parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jiudaru Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001085/2022-2023 | 345/pd | 13/03/2023 | 90 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 79.96 | 69.65 | 100
1512 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Kotshila OHR Site for Augmentation of Kotshila W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001089/2022-2023 | 369/PD | 14/03/2023 | 100 | SABYASACHI MISHRA | 8.18 | 0 | 70
1513 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Collecting line from Kanshabati Riverbed to Kachahatu Pump house for implementation of JJM Project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001090/2022-2023 | 358/PD | 14/03/2023 | 30 | KOUSHIK CHATTERJEE | 3.1 | 0.46 | 100
1514 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Collecting line from Kanshabati Riverbed to Manifold Chamber for implementaion of JJM project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001092/2022-2023 | 359/PD | 14/03/2023 | 30 | BOSE CONSTRUCTION | 7.65 | 7.16 | 100
1515 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | 13 Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chiruhatu Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001094/2022-2023 | 361/PD | 14/03/2023 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.62 | 0 | 100
1516 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000013/2022-2023 | 969/PD | 21/06/2022 | 0 | Resource Division | 369.8 | 0 | 0
1517 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000014/2022-2023 | 968/PD | 21/06/2022 | 0 | Resource Division | 177.02 | 0 | 0
1518 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New Sinking of 02 (Two) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line other allied works of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 126/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000960/2022-2023 | BP-2022-23-128 | 19/07/2022 | 0 | KOUSHIK CHATTERJEE | 5.39 | 0 | 0
1519 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | New Sinking of 03 (Three) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with construction of 01 nos common manifold chamber at kotshila river site of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 124/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000961/2022-2023 | BP-2022-23-129 | 19/07/2022 | 0 | BOSE CONSTRUCTION | 8.56 | 0 | 0
1520 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 971/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000971/2022-2023 | BP-2022-23-139 | 19/07/2022 | 0 | HORIZEN | 1.99 | 0 | 0
1521 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 544/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000972/2022-2023 | BP-2022-23-140 | 19/07/2022 | 0 | HORIZEN | 7.98 | 0 | 0
1522 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) (Tender No.506/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001021/2022-2023 | BP-2022-23-312 | 26/09/2022 | 0 | NANIGOPAL DEY | 8.78 | 0 | 0
1523 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) (Tender No- 282/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001032/2022-2023 | BP-2022-23-377 | 19/10/2022 | 0 | ANUP KUMAR SAHA | 32.08 | 0 | 0
1524 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) (Tender No- 281/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001041/2022-2023 | BP-2022-23-376 | 19/10/2022 | 0 | ANUP KUMAR SAHA | 50.47 | 0 | 0
1525 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Car bill paid for office purpose for the month of Jan & Feb,23 against Vehicle Reg. No. WB/55A/7171. | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001819/2022-2023 |  | 30/11/2022 | 0 | NIRUPAMA DEY | 0.63 | 0 | 0
1526 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Car bill for office purpose against vehicle reg. no.WB-55A/7171 & paid for the month of Jan,23 & Feb,23. | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001904/2022-2023 | BP-2023-24-58 | 04/05/2023 | 0 | NIRUPAMA DEY | 0.63 | 0 | 0
1527 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 125 KVA AT 0.4 KV TO 281/281/281/281/281 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o EX ENGG PMD PHE DTE. (CONSUMER ID : 942406300) TO THEIR PREMISES AT KOTSHILA WATER SUPPLY SCHEME (AUGMENTATION) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00044/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 10.37 | 0 | 0
1528 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Bill for earnest money for the proposed Enhancement of the load at your premises at Kotshila W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00434/2023-2024 | BP-23-24-219 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
1529 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER ROOM AT KOTHSILA WS SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00508/2023-2024 | BP-23-24-269 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
1530 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Enhancement of the contract demand from 125KVA at 0.4 KV to 281/281//281//281//281 KVA respectively at 11 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kotshila Water Supply, (Consumer ID -942406300) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00860/2023-2024 | BP-24-25-1 | 19/04/2024 | 0 | WBSEDCL PURULIA | 10.24 | 0 | 0
1531 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and delivery of essential Electromechanical items for Augmentation of Kotshila w/s Scheme in PMD store under Purulia Mechanical Division PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000188/2023-2024 | 1178/PMD | 03/11/2023 | 60 | SAIBAL SARKAR | 5.15 | 0 | 100
1532 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KOTSHILA w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000253/2022-2023 | 43/PMD | 19/01/2023 | 60 | TAPAN KUMAR DEY | 78.43 | 17.89 | 65
1533 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of 400KVA 11/.433 KV substation with 11 KV 800A VCB Panel with others allied works for Augmentation of Kotshila w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000269/2022-2023 | 42/PMD | 19/01/2023 | 60 | CHAKRABORTY ENTERPRISE | 48.1 | 0 | 60
1534 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation 12kg/cm2 chlorine machine with others works for Augmentation of Kotshila w/s scheme under Purulia Mechanical Division, PHE, Dte. in purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000296/2022-2023 | 77/PMD | 01/02/2023 | 30 | R K ENTERPRISES | 3.6 | 0 | 91
1535 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation submersible pumping machineries & 3 core 10 Sq. mm Al Ar. cable line , with others allied works for Augmentation of Kotshila W/S scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000490/2022-2023 | 154/PMD | 24/02/2023 | 60 | M/S S.G.ENTERPRISE | 31.8 | 17.85 | 75
1536 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | DEPOSITION OF THE EARNEST MONEY FOR THE PORPOSED ENHANCEMENT OF THE LOAD AT KOTHSILA WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000326/2022-2023 | 780/PMD | 23/11/2022 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
1537 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Bill payment to Sri Krishna Computer against bill no.010/2023-24 to 017/2023-24 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00996/2023-2024 | BP-2023-24-629 | 17/10/2023 | 0 | SRI KRISHNA COMPUTER | 0.63 | 0 | 0
1538 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Bill paid for due to awareness program in the ocation of Independence Day organised by DPMU. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01228/2023-2024 | BP-2023-24-715 | 13/12/2023 | 0 | ANUDIP SAHA | 0.54 | 0 | 0
1539 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Computer service & spare parts supply bill paid. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01379/2023-2024 | BP-2023-24-750 | 05/01/2024 | 0 | SRI KRISHNA COMPUTER | 0.65 | 0 | 0
1540 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 5.0 x 3.0 mtr size Guard Room , approach road, plinth protection, surface drain etc. complete at Mankiyari OHR site for Baram W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000058/2022-2023 | 166/PSD | 18/04/2022 | 30 | SOUMITRA CHAKRABORTY | 4.71 | 3.34 | 75
1541 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Baram Pump house and Torang Pump House ,riverside) under Purulia Sadar Sub Division under Purulia Division ,PHE .DTE | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2022-2023 | 167/PSD | 18/04/2022 | 30 | AKUL SUTRADHAR | 4.85 | 4.04 | 0
1542 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000111/2020-2021 | 1240/PD | 01/12/2020 | 45 | SOUMITRA CHAKRABORTY | 29.89 | 0 | 0
1543 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Withdrawing of 150 mm dia.G.I. damaged Collecting line & newly laying of 160 mm dia HDPE Pipe line as Collecting line and 40 mm dia G.I. Guard Pilling at river bed of Kansai near Deolghata of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000184/2023-2024 | 4674/PSD | 27/07/2023 | 10 | APEX TRADERS | 0.78 | 0.78 | 100
1544 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extension of PVC pipe line in distribution system from Deolghata Pump House to River site Smashan Ghat ( Burning Ghat) with construction of a Stand post for met up the drinking water crisis under Joypur Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2023-2024 | 4681/PSD | 27/07/2023 | 10 | APEX TRADERS | 0.29 | 0.29 | 100
1545 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply and delivery of ferric alum at different water supply scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000436/2021-2022 | 382/PD | 11/03/2022 | 10 | ROY CONSTRUCTION | 5.71 | 0 | 20
1546 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 02 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000836/2022-2023 | 1738/PD | 22/11/2022 | 30 | SOUMITRA CHAKRABORTY | 18.35 | 4.59 | 100
1547 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 01 (One) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000837/2022-2023 | 1739/PD | 22/11/2022 | 30 | SOUMITRA CHAKRABORTY | 8.91 | 2.68 | 100
1548 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing 1 no Horizontal Tubewell at Kansai River at Torang Riverside and other allied works Baram W/S Scheme under Purulia Sadar Sub Division under Purulia Division , PHE Dte.(T/W no-3) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000857/2022-2023 | 1808/Pd | 06/12/2022 | 30 | SOUMITRA CHAKRABORTY | 1.73 | 1.68 | 100
1549 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply delivery fitting & fixing of sign board (ACP Sheet) at 10nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-C) SL NO. 07 | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001076/2022-2023 | 97/PR | 28/02/2023 | 30 | MRINAL KANTI GORAI | 0.65 | 0 | 100
1550 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001298/2022-2023 | 308-PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.73 | 1.26 | 100
1551 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001299/2022-2023 | 309_PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.97 | 1.67 | 100
1552 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection, surface drain etc.complete at Sirkabad OHR Site for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001811/2023-2024 | 35/PD | 08/01/2024 | 100 | KABERI DUTTA | 5.05 | 0 | 0
1553 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000186/2022-2023 | BP-2022-23-58 | 20/05/2022 | 0 | SOUMITRA CHAKRABORTY | 19.28 | 0 | 0
1554 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000187/2022-2023 | BP-2022-23-59 | 20/05/2022 | 0 | SOUMITRA CHAKRABORTY | 5.88 | 0 | 0
1555 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Installation of new staircase spiral for OHR & other allied works at Baram W/S Scheme (Tender No-365/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000193/2022-2023 | BP-2022-23-48 | 17/05/2022 | 0 | SOUMITRA CHAKRABORTY | 3.06 | 0 | 0
1556 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing of 1 no. horizontal tube well with changing of collecting line and other allied works at Torang river side of Baram W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 239/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000994/2022-2023 | BP-2022-23-158 | 27/07/2022 | 0 | SOUMITRA CHAKRABORTY | 2.17 | 0 | 0
1557 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Baram(River Side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2023-2024 | 522/PMD | 05/05/2023 | 607 | P K ENGINEERING | 39.21 | 0 | 100
1558 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baram Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2021-2022 | 112/PMD | 28/02/2022 | 30 | A G ENTERPRISE | 20.48 | 20.17 | 99
1559 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Baram(River Side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000408/2022-2023 | 236/PMD | 03/03/2023 | 60 | SUMIT KR. CHAKRABORTY | 11.33 | 0 | 20
1560 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Baram(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000409/2022-2023 | 237/PMD | 03/03/2023 | 60 | S. PATHAK & CO. | 10.86 | 6.3 | 65
1561 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 50
1562 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000011/2023-2024 | 619/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
1563 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Seleta Mouza, JL No.-41, Plot No.237 at Boosting Pump Station site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000014/2023-2024 | 543/PD | 12/04/2023 | 60 | SUBRATA SINGHADEO | 33.43 | 13.68 | 42
1564 | Purulia Division | Raghunathpur Sub-Division | Repairing of DI rising main and repairing, renovation of Boundary wall (Total lenght =148 mtr) at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000016/2023-2024 | 545/PD | 12/04/2023 | 30 | M/S SAYAK BHATTACHARYA | 10.93 | 10.91 | 0
1565 | Purulia Division | Raghunathpur Sub-Division | Repairing of DI Rising Main and new Construction of Boundary wall, RCC Pillar, Barbed wire at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000106/2023-2024 | 867/PD | 30/06/2023 | 30 | M/S SAYAK BHATTACHARYA | 4.25 | 4.24 | 100
1566 | Purulia Division | Raghunathpur Sub-Division | Repairing of DI Rising Main, construction of RCC Clear water reservoir (CWR) of capacity 150 Cum, New Boundary wall (Lenth=62 mtr) and 01 No. Sinking of RBT Tubewell (200X165 mm dia) and other allied works at Zone-VIII OHR campus of Raghunathpur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000131/2024-2025 | 897/PD | 07/05/2024 | 718 | SANDIP KUMAR DUBEY | 36.14 | 0 | 60
1567 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 100
1568 | Purulia Division | Raghunathpur Sub-Division | Laying of different dia HDPE pipe in distribution pipe line , replacing existing CI Pipes and allied works of Raghunathpur Water Supply Scheme( Zone -VIII) at Raghunathpur-II Block of Raghunathpur Sub division under Purulia Division,PHE DTE. | Assistant Engineer |  | ORD/000554/2024-2025 | 1596/PD | 30/08/2024 | 579 | PREMNATH MITRA | 94.69 | 0 | 0
1569 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of "Day to day hiring and operation charges of 1 (one) number 10/15 KVA Generator set Engaging one number expert operator for the office of the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. under Raghunathpur W/S Scheme (German Project) (w.e.f. 04.04.2025 to 03.06.2025)" | Assistant Engineer |  | ORD/000575/2025-2026 | 166/RNP | 02/04/2025 | 61 | MANATOSH SINGH | 0.87 | 0 | 0
1570 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 100
1571 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 100
1572 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1573 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1574 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1575 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1576 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIII) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 10) | Assistant Engineer |  | ORD/001157/2022-2023 | 432/PD | 22/03/2023 | 1016 | PREMNATH MITRA | 414.3 | 0 | 45
1577 | Purulia Division | Raghunathpur Sub-Division | Construction of 4 Nos. Sluice Valve Chamber at Setpalash & Cheliyama Bagdipara under Raghunathpur W/S Scheme (German Assisted) Zone-VIII of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/004766/2023-2024 | 174/RNP | 27/03/2024 | 7 | JOY GURU ENTERPRISE | 0.92 | 0 | 100
1578 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000037/2022-2023 | 72/PD | 17/01/2023 | 0 | Resource Division | 1.38 | 0 | 0
1579 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Raghunathpur Pipe Water Supply scheme for Zone-VIII under Purulia Mechanical Division PHE. Dte. District Purulia | Assistant Engineer |  | ORD/000387/2022-2023 | 218/PMD | 28/02/2023 | 30 | JAL PRAVAHIKA PVT. LTD | 21.57 | 0 | 100
1580 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - B, Mouza - Dumdumi] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000061/2023-2024 | 1055/PD | 08/08/2023 | 90 | M/S SAYAK BHATTACHARYA | 73.52 | 0 | 100
1581 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - D, Mouza - PORADIHA, BELJHUPA, KALAID] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000062/2023-2024 | 1054/PD | 08/08/2023 | 90 | CHATTERJEE CONSTRUCTION | 64.43 | 0 | 63
1582 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of Switch Room Cum Chlorin Room at Santuri OHR Site of Santuri W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000171/2023-2024 | 933/PD | 19/07/2023 | 100 | PURNA CHANDRA TEWARI | 4.21 | 0 | 100
1583 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-I] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000981/2022-2023 | 93/PD | 20/01/2023 | 802 | KHITISH CHANDRA PATHAK | 59.34 | 40.34 | 80
1584 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-II] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000982/2022-2023 | 94/PD | 20/01/2023 | 30 | MS MITRA SENGUPTA ENTERPRISES | 8.37 | 3.92 | 45
1585 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-III] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000983/2022-2023 | 95/PD | 20/01/2023 | 621 | CHANDAN CHATTERJEE | 11.22 | 10.41 | 95
1586 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-V] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000984/2022-2023 | 96/PD | 20/01/2023 | 802 | AMIT PATHAK | 10.76 | 9.77 | 85
1587 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-VI] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000985/2022-2023 | 97/PD | 20/01/2023 | 30 | DEBANJAN SEAL | 4.95 | 4.62 | 85
1588 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC Over Head Reservoir (OHR) Capacity 100 cum and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000986/2022-2023 | 98/PD | 20/01/2023 | 270 | CHATTERJEE CONSTRUCTION | 56.67 | 19.68 | 100
1589 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-IV] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/001123/2022-2023 | 396/PD | 16/03/2023 | 45 | M/S ACHARJEE CONSTRUCTION | 19.01 | 11.41 | 62
1590 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Santuri | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00252/2023-2024 | BP-2023-24-148 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.95 | 0 | 0
1591 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Santuri Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000041/2023-2024 | 447/PMD | 20/04/2023 | 30 | DAS ENTERPRISE | 21.57 | 0 | 25
1592 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible pumping machineries ,Al. Armoured cables and laying of Al. armoured cables for Augmentation of Santuri W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000068/2024-2025 | 996/PMD | 21/06/2024 | 60 | SEN BROTHERS | 4.25 | 0 | 70
1593 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000457/2022-2023 | 297/PMD | 16/03/2023 | 60 | GOENKA ENTERPRISE | 33.83 | 0 | 20
1594 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of 30KVA oil cooled voltage stabilizer and allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000458/2022-2023 | 298/PMD | 16/03/2023 | 60 | BISHWANATH NANDI | 4.13 | 3.13 | 80
1595 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Yard lighting arrangement with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000459/2022-2023 | 299/PMD | 16/03/2023 | 60 | S. PATHAK & CO. | 5.02 | 0 | 20
1596 | Purulia Division | Purulia Division | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Manbazar-I & Manbazar-II Block [18 + 19 =37 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. (Part-III) | Assistant Engineer(HQ) |  | ORD/000041/2022-2023 | 159/PSD | 24/02/2023 | 21 | M/S R. DUTTA & CO. | 4.69 | 4.33 | 0
1597 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B Mouza-Daldali, Bhagabandh under Daldali G.P.(1139 Nos.) | Assistant Engineer | Junior Engineer-4 | ORD/000272/2020-2021 | 157/PD | 01/02/2021 | 45 | GOUTAM CHAKRABORTY | 56.95 | 73.29 | 85
1598 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | Assistant Engineer | Junior Engineer-4 | ORD/000660/2023-2024 | 1353/PD | 13/09/2023 | 45 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 100
1599 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-DivisionPHE Dte. (Tender No. 409/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000249/2021-2022 | BP-2021-22-98 | 23/08/2021 | 0 | ALOK KUMAR CHAKRABORTY | 28.51 | 0 | 0
1600 | Purulia Division | Raghunathpur Sub-Division | Artificial recharging of existing river bed tubewells along with all others related items of works to combat extreme drought like situation under Manguria-Lalpur W/s Scheme of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 376/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000383/2021-2022 | BP-2021-22-125 | 11/10/2021 | 0 | ALOK KUMAR CHAKRABORTY | 4.78 | 0 | 0
1601 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD OF 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000444/2021-2022 | BP-2021-22-106 | 14/09/2021 | 0 | SWAPAN MANDAL | 46.14 | 0 | 0
1602 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-III. (Tender No.827/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000812/2021-2022 | BP-2021-22-228 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.82 | 0 | 0
1603 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-IV. (Tender No.830/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000813/2021-2022 | BP-2021-22-229 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.15 | 0 | 0
1604 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-I. (Tender No.833/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000814/2021-2022 | BP-2021-22-230 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.77 | 0 | 0
1605 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-II. (Tender No.826/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/000815/2021-2022 | BP-2021-22-231 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.8 | 0 | 0
1606 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Part-B Mouza- Daldali, Bhagabandh under Daldali G.P (1139 Nos.) (Tender No. 309/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-4 | VCH/000871/2020-2021 | 9/844324/2 | 12/04/2021 | 0 | GOUTAM CHAKRABORTY | 13.28 | 0 | 0
1607 | Purulia Division | Raghunathpur Sub-Division | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) | Assistant Engineer | Junior Engineer-4 | VCH/001137/2021-2022 | BP-2021-22-292 | 09/03/2022 | 0 | PREMNATH MITRA | 53.06 | 0 | 0
1608 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation op pipe line at Lalpur & Hijuli village under Lalpur-Manguria Water supply Scheme. (Tender No.533/EE/PD of 2022-23) | Assistant Engineer | Junior Engineer-4 | VCH/001309/2022-2023 | 181/844340 | 06/12/2022 | 0 | ALOK KUMAR CHAKRABORTY | 0.86 | 0 | 0
1609 | Purulia Division | Purulia Division | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Jaipur Block [21 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000047/2022-2023 | 161/PSD | 24/02/2023 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.97 | 2.84 | 0
1610 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of 5.0 x 3.0 mtr size Meter Room including approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000038/2023-2024 | 656/PD | 17/05/2023 | 100 | SUDHANSHU OJHA | 4.92 | 1.79 | 100
1611 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000222/2021-2022 | 741/PSD | 13/12/2021 | 60 | KABERI DUTTA | 4.57 | 4 | 0
1612 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing, renovation and changing of filter media of filter bed including cleaning the tube settler to enhancement the filteration rate of water to meet up water crisis at Hutmura WTP of Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000235/2021-2022 | 745/PSD | 13/12/2021 | 20 | SHYAMAL KUMAR DEY | 2.22 | 1.65 | 85
1613 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing and renovation of the Over Head reservoir (OHR) of 30000 gallon Capacity, Staging Height 20 mtr. at Hutmura WTP campus under Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000266/2021-2022 | 1544/PD | 15/12/2021 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 7.26 | 4.52 | 85
1614 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000268/2021-2022 | 1545/PD | 15/12/2021 | 60 | SHYAMAL KUMAR DEY | 10.73 | 0.96 | 0
1615 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 200 mm dia DI (K9) pipe as rising main from intake site to WTP under Hutmura Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000304/2021-2022 | 1594/PD | 17/12/2021 | 30 | SHYAMAL KUMAR DEY | 5.7 | 0.93 | 0
1616 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000346/2021-2022 | 96/PD | 18/01/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 26.3 | 0 | 100
1617 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) under Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000347/2021-2022 | 97/PD | 18/01/2022 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 72.9 | 9.71 | 100
1618 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000348/2021-2022 | 98/PD | 18/01/2022 | 70 | M/S KARUNAMOYEE CONSTRUCTION | 82.79 | 24.38 | 100
1619 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Extention / replacement of distribution pipe line in different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000425/2021-2022 | 358/PD | 04/03/2022 | 1183 | PREMNATH MITRA | 121.12 | 23.08 | 100
1620 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000460/2021-2022 | 422/PD | 17/03/2022 | 45 | SHYAMAL KUMAR DEY | 31.94 | 5.05 | 75
1621 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Additional Pipe laying of 50 mm dia (OD) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000500/2022-2023 | 440/PSD | 24/06/2022 | 15 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 2.48 | 2.12 | 90
1622 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Extension of pipe line in distribution system for Stand Post at different School & ICDS Centre of Purulia-II Block to supply drinking water of command area including road crossing of pipe line and replacement of Sluice Valve on delivery pipe line at OHR Campus and distribution main at field of Hutmura Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000606/2022-2023 | 504/PSD | 12/08/2022 | 40 | M/S KARUNAMOYEE CONSTRUCTION | 4.14 | 4.11 | 100
1623 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000782/2022-2023 | 1629/PD | 03/11/2022 | 698 | SHYAMAL KUMAR DEY | 9.56 | 5.61 | 100
1624 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000010/2021-2022 | 1628/PD | 31/12/2021 | 0 | Resource Division | 26.12 | 0 | 0
1625 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000014/2021-2022 | 389/PD | 11/03/2022 | 0 | Resource Division | 0.72 | 0 | 0
1626 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing, renovation & restoration of pump house & Chlorine cum Alum dozing room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.831/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000176/2022-2023 | BP-2022-23-41 | 02/05/2022 | 0 | TARASANKAR DEY | 2.44 | 0 | 0
1627 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Extension/ replacement of distribution pipe line in different habitation of Hutmura Mouza (Jl No. 139) & Phulberia mouza (JL No 140) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division under Purulia Division, PHE Dte. (Tender No- 27/2021-22 of SE/PMU/WBPWSP) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000889/2022-2023 | BP-2022-23-76 | 01/07/2022 | 0 | PREMNATH MITRA | 53.19 | 0 | 0
1628 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Laying of 200 mm dia DI k9 pipe as rising main from intake site to WTP under Hutmura W/S Scheme of Purulia Sadar Sub- Division, under Purulia Division, PHE Dte (Tender No- 868/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000893/2022-2023 | BP-2022-23-73 | 01/07/2022 | 0 | SHYAMAL KUMAR DEY | 1.04 | 0 | 0
1629 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 867/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000904/2022-2023 | BP-2022-23-97 | 07/07/2022 | 0 | SHYAMAL KUMAR DEY | 8.46 | 0 | 0
1630 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Korcha mouza (JL No- 151) and replacement/extension of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 13/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000955/2022-2023 | BP-2022-23-136 | 19/07/2022 | 0 | SHYAMAL KUMAR DEY | 17.28 | 0 | 0
1631 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001013/2022-2023 | BP-2022-23-277 | 22/09/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 12.26 | 0 | 0
1632 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation of Hutmura Mouza JL No 139 & Phulberia Mouza JL No 140 under Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 05/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001019/2022-2023 | BP-2022-23-308 | 26/09/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 37.94 | 0 | 0
1633 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supply and delivery of 6mm N.B. gun Metal Ferrule for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Hutmura Mouza (JL No 139) & Phulberia mouza (JL No 140) under Hutmura Water Supply Scheme of Purulia II Block under Purulia Division, PHE Dte. (Tender No- 445/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001020/2022-2023 | BP-2022-23-310 | 26/09/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 4.76 | 0 | 0
1634 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing renovation & restoration of Store cum Guard room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.893/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001124/2021-2022 | BP-2021-22-392 | 30/03/2022 | 0 | TAPAN CHANDRA | 1.82 | 0 | 0
1635 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001128/2021-2022 | BP-2021-22-368 | 29/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 10.34 | 0 | 0
1636 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001169/2021-2022 | BP-2021-22-303 | 21/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 3.97 | 0 | 0
1637 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 849/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001176/2021-2022 | BP-2021-22-302 | 21/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.07 | 0 | 0
1638 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing renovation & restoration of switch cum meter room including roof treatment at Hutmura Dam site of Hutmura W/S Scheme under Purulia Sadar Sub- Division (Tender No- 837/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001188/2021-2022 | BP-2021-22-319 | 22/03/2022 | 0 | INDRAJIT SARKAR | 2.27 | 0 | 0
1639 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 1007/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001216/2021-2022 | BP-2021-22-347 | 28/03/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 27.68 | 0 | 0
1640 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Hutmura high lift Water supply scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00822/2023-2024 | BP-23-24-282 | 16/02/2024 | 0 | WBSEDCL PURULIA | 7.07 | 0 | 0
1641 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(OHR site) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000024/2023-2024 | 395/PMD | 06/04/2023 | 60 | MOON LIGHT HOUSE | 7.36 | 0 | 100
1642 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal and external illumination with other allied works for augmentation of Hutmura W/S scheme(both intake & OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000056/2023-2024 | 525/PMD | 05/05/2023 | 60 | ASISH KR. SEN | 5.12 | 0 | 100
1643 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Open well Submersuble pumping machinery for direct pumping with others electro-mechanical work at Hutmura W/S (OHR Site) under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2024-2025 | 993/PMD | 21/06/2024 | 406 | SUBRATA DUTTA | 15.59 | 0 | 55
1644 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Hutmura Water Supply scheme Block Purulia-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2022-2023 | 397/PMD | 16/06/2022 | 30 | SUBRATA DUTTA | 20.51 | 20.45 | 100
1645 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Repairing, overhauling thorough repairing of floating walkway with required MS work by necessary supply of materials and other allied works at Hutmura (Low Lift) w/s scheme under PMD PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000168/2021-2022 | 78/PMSD (W/S) | 08/03/2022 | 7 | SUBRATA DUTTA | 4.6 | 3.6 | 80
1646 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Augmentation of floating walkway lowering and anchoring of existing repaired floating barge with required ms work by necessary supply of materials and other allied works at Hutmura(Low Lift) W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000342/2022-2023 | 124/PMD | 15/02/2023 | 60 | ASHOKE ADHIKARY | 7.85 | 0 | 0
1647 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries with flexible hose pipe, MCC panel, flowmeter with other allied works for augmentation of Hutmura(Intake side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000422/2022-2023 | 240/PMD | 03/03/2023 | 60 | KHITISH CH. PATHAK | 18.86 | 0 | 100
1648 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of centrifugal pumping machineries, MCC panel, flowmeter and other allied works at Hutmura(OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000423/2022-2023 | 241/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 50.17 | 14.51 | 100
1649 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, fixing of PVC pipe,cable,valve etc and other allied works at Hutmura (low lift) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000502/2024-2025 | 1305/PMD | 03/09/2024 | 20 | KHITISH CH. PATHAK | 3.39 | 0 | 100
1650 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-In-Charge, PMSD (Drilling) under Purulia Mechanical Division P.H.E Dte." (W.e.f- 01.05.2024 to 31.10.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000523/2023-2024 | 49/PMSD(Drilling) | 12/03/2024 | 184 | NUPUR CHANDRA HALDER | 0.9 | 0 | 100
1651 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(low lift site) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 1448/PMD | 01/10/2024 | 90 | ASHOKE ADHIKARY | 7.37 | 0 | 0
1652 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Hutmura water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000683/2024-2025 | 1695/PMD | 06/12/2024 | 90 | SUBRATA DUTTA | 9.99 | 0 | 0
1653 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Enhancement of contract demand load for Augmentation of Hutmura Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000429/2022-2023 |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 3.08 | 0 | 0
1654 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Kusmagora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000175/2023-2024 | 991/PD | 26/07/2023 | 60 | ALOK KUMAR CHAKRABORTY | 14.14 | 0 | 100
1655 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000241/2021-2022 | 1515/PD | 13/12/2021 | 30 | NANIGOPAL DEY | 7.36 | 0 | 0
1656 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000242/2021-2022 | 1516/PD | 13/12/2021 | 30 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0
1657 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000243/2021-2022 | 1517/PD | 13/12/2021 | 30 | PRIYATOSH MUKHERJEE | 8.38 | 0 | 0
1658 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) (250 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000244/2021-2022 | 1518/PD | 13/12/2021 | 30 | RAHIBUDDIN MONDAL | 12.36 | 0 | 0
1659 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000245/2021-2022 | 1519/PD | 13/12/2021 | 30 | M/S ACHARJEE CONSTRUCTION | 12.43 | 0 | 0
1660 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room cum Chlorine Room at Deshra Zone-III OHR Campus under Kalabani W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000246/2021-2022 | 1520/PD | 13/12/2021 | 100 | BASANTA KUMAR SINGHADEO | 5.89 | 0 | 0
1661 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000247/2021-2022 | 1521/PD | 13/12/2021 | 100 | RABIN CHANDRA CHAIL | 5.92 | 0 | 96
1662 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room cum Chlorine Room at Tilabani Zone-IV OHR Campus under Kalabani W/S Scheme (Zone-IV) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000248/2021-2022 | 1522/PD | 13/12/2021 | 100 | SADHAN GORAIN | 5.95 | 4.99 | 0
1663 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Kalabani OHR Site under Kalabani W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000249/2021-2022 | 1523/PD | 13/12/2021 | 60 | RABIN CHANDRA CHAIL | 4.97 | 1.52 | 95
1664 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Ladhurka OHR Site under Kalabani W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000250/2021-2022 | 1524/PD | 13/12/2021 | 60 | NANIGOPAL DEY | 4.8 | 4.44 | 95
1665 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Deshra OHR Site under Kalabani W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000252/2021-2022 | 1525/PD | 13/12/2021 | 60 | BASANTA KUMAR SINGHADEO | 4.87 | 0 | 0
1666 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Tilabani zone- IV under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000253/2021-2022 | 1526/PD | 13/12/2021 | 60 | SADHAN GORAIN | 5 | 4.81 | 0
1667 | Purulia Division | Raghunathpur Sub-Division | Restoration work by construction of RCC Retaining wall for Protection work at Kalabani Intake site of Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000254/2021-2022 | 1527/PD | 13/12/2021 | 60 | SADHAN GORAIN | 5.68 | 0 | 0
1668 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000255/2021-2022 | 1528/PD | 13/12/2021 | 30 | CHAIL CONSTRUCTION | 7.56 | 0 | 0
1669 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of WTP campus under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000274/2021-2022 | 761/RNP | 15/12/2021 | 45 | SADHAN GORAIN | 4.46 | 3.67 | 0
1670 | Purulia Division | Raghunathpur Sub-Division | Restoration, repairing & laying of HDPE Pipe line and other allied works under Kalaboni W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000583/2022-2023 | 496/RNP | 02/08/2022 | 20 | SUBRATA SINGHADEO | 4.76 | 3.86 | 95
1671 | Purulia Division | Raghunathpur Sub-Division | Supplying & laying of HDPE of pipeline for Tentuldih Village and Interconnection work of overflow line with distribution line at Kalaboni Zone-I OHR site under Kalaboni W/S Scheme under FHTC work (Jal Swapna Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000637/2022-2023 | 1405/PD | 01/09/2022 | 45 | CHAIL CONSTRUCTION | 8.91 | 8.27 | 96
1672 | Purulia Division | Raghunathpur Sub-Division | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-IV ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000662/2023-2024 | 1355/PD | 13/09/2023 | 30 | SADHAN GORAIN | 4.34 | 4.34 | 100
1673 | Purulia Division | Raghunathpur Sub-Division | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-I ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000663/2023-2024 | 1356/PD | 13/09/2023 | 30 | CHAIL CONSTRUCTION | 3.19 | 3.19 | 100
1674 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Jabjobi Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000672/2023-2024 | 1359/PD | 13/09/2023 | 45 | M/S SAYAK BHATTACHARYA | 18.72 | 0 | 100
1675 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Hirgram & Hir Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000883/2023-2024 | 1533/PD | 16/10/2023 | 45 | CHAIL CONSTRUCTION | 18.17 | 0 | 100
1676 | Purulia Division | Raghunathpur Sub-Division | Gravel Paking around Intake, Construction of Guard Wall , Chain link fencing , Digging of earth at Kolaboni Intake site under Kaloboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/001859/2023-2024 | 87/PD | 15/01/2024 | 60 | SADHAN GORAIN | 11.17 | 0 | 100
1677 | Purulia Division | Raghunathpur Sub-Division | Supply, delivery fitting & fixing of 5 Nos. Scheme Description Sign boards (6' X 3') under Kalaboni W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Zone-I (Kalaboni), Zone-II (Ladhurka), Zone-III(Deshra), Zone-IV(Tilaboni) & WTP Campus. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/001940/2023-2024 | 24/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.86 | 0 | 0
1678 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.978/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000138/2022-2023 | BP-2022-23-1 | 05/04/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 10.69 | 0 | 0
1679 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.987/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000185/2022-2023 | BP-2022-23-64 | 24/05/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 1.67 | 0 | 0
1680 | Purulia Division | Raghunathpur Sub-Division | Repairing & renovation of RCC elevated Reservoir capacity 150 cum and boundary wall at Deshra OHR site under kalaboni W/S Scheme (zone-III of Raghunathpur Sub- Division under Purulia Division, PHE Dte. (Tender No-888/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000885/2022-2023 | BP-2022-23-79 | 01/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 4.14 | 0 | 0
1681 | Purulia Division | Raghunathpur Sub-Division | Construction of guard room along with sanitary & plumbing arrangement at OHR campus (Zone-III) at Deshra of kalaboni (Improvement) W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 886/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000962/2022-2023 | BP-2022-23-127 | 19/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 5.04 | 0 | 0
1682 | Purulia Division | Raghunathpur Sub-Division | Additional work by Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme of Hura Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. Zone-II (250) nos. (Tender No- 216/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000995/2022-2023 | BP-2022-23-159 | 27/07/2022 | 0 | RAHIBUDDIN MONDAL | 3.3 | 0 | 0
1683 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.928/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000996/2022-2023 | BP-2022-23-253 | 15/09/2022 | 0 | RABIN CHANDRA CHAIL | 5.14 | 0 | 0
1684 | Purulia Division | Raghunathpur Sub-Division | Additional work for functional House Hold Tap Connection FHTC including other allied works of Kalaboni Water Supply Scheme of Hura Block Zone- I (Tender No- 982/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001152/2021-2022 | BP-2021-22-330 | 23/03/2022 | 0 | NANIGOPAL DEY | 7.35 | 0 | 0
1685 | Purulia Division | Raghunathpur Sub-Division | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/001190/2021-2022 | BP-2021-22-318 | 22/03/2022 | 0 | RAHIBUDDIN MONDAL | 12.46 | 0 | 0
1686 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 2 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000041/2022-2023 | 322/PMD | 17/05/2022 | 30 | AHALYA ENGINEERING WORKS | 20.57 | 20.56 | 98
1687 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 3 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000042/2022-2023 | 323/PMD | 17/05/2022 | 30 | S.P. ENTERPRISE | 20.48 | 0 | 100
1688 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 4 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000043/2022-2023 | 324/PMD | 17/05/2022 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGY PVT LTD. | 20.51 | 19.02 | 100
1689 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000066/2021-2022 | 111/PMD | 28/02/2022 | 1038 | ORIENTAL ENGINEERING CO. | 20.43 | 13.93 | 100
1690 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of submersible pump-motor set instead of existing submersible pump-motor set at Kalabani w/s scheme under Purulia Mechanical Division , PHE, Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000080/2023-2024 | 592/PMD | 24/05/2023 | 30 | SUBRATA DUTTA | 9.05 | 0 | 100
1691 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Tialabani OHR site (Zone-IV) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000112/2023-2024 | 640/PMD | 08/06/2023 | 30 | MOON LIGHT HOUSE | 2.5 | 0 | 100
1692 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Kalabani OHR site (Zone-I) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000113/2023-2024 | 641/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.56 | 0 | 100
1693 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Deshra OHR site (Zone-III) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000114/2023-2024 | 642/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.45 | 0 | 100
1694 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Ladhurka OHR site (Zone-II) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000115/2023-2024 | 643/PMD | 08/06/2023 | 30 | KOUSHIK CHATTERJEE | 2.46 | 0 | 100
1695 | Purulia Mechanical | Raghunathpur Sub-Division | Sinking of 200mmX165mm tubewell and other allied works for Kalabani water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000215/2023-2024 | 1201/PMD | 03/11/2023 | 15 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 7.12 | 0 | 100
1696 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR KALABANI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000321/2022-2023 | BP-22-23-34 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
1697 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION AT PHE LADHURKA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000322/2022-2023 | BP-2022-23-35 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
1698 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR DESHRA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000323/2022-2023 | BP-2022-23-36 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
1699 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR TILABANI OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000324/2022-2023 | BP-2022-23-37 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
1700 | Purulia Division | Raghunathpur Sub-Division | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Kashipur W/S Scheme on Hura Kaaluput Adra Raghunathpur Road (From Ch.16.00 Km to Ch.16.346 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00455/2023-2024 | BP-2023-24-312 | 26/07/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 11.08 | 0 | 0
1701 | Purulia Division | Raghunathpur Sub-Division | Route Survey & Drawing Preparation for uncovered areas under Kashipur Block under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000004/2023-2024 | 526/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 4.94 | 100
1702 | Purulia Division | Raghunathpur Sub-Division | Allied works for Laying pipe line , mending good of tap connection due to damage of road during construction of drainage system in connection with Jal jiban mission within Augmentation of Kashipur w/s Scheme under Raghunathpur Sub Division PHE Dte . | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000023/2025-2026 | 580/PD | 07/04/2025 | 45 | MAHARSHI BANERJEE | 28.69 | 0 | 80
1703 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC elevated reservoir of capacity 250 cum Other allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000075/2022-2023 | 652/PD | 22/04/2022 | 270 | NANIGOPAL DEY | 62.33 | 47.22 | 100
1704 | Purulia Division | Raghunathpur Sub-Division | Laying of distribution pipe line & Restoration work by cleaning and chowkage clearance of distribution Main & including providing House Hold Tap Connection (FHTC) two no (Adivasi Hostel) and other allied works at Daldali village under Kashipur Piped water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000151/2024-2025 | 907/PD | 07/05/2024 | 60 | CHANCHAL MISHRA | 2.61 | 0 | 100
1705 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000346/2022-2023 | 881/PD | 23/05/2022 | 979 | SANTANU BANERJEE | 356.15 | 99.7 | 90
1706 | Purulia Division | Raghunathpur Sub-Division | Sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000398/2021-2022 | 237/PD | 09/02/2022 | 30 | RABIN CHANDRA CHAIL | 26.74 | 16.39 | 100
1707 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000403/2021-2022 | 260/PD | 11/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 88.48 | 18.48 | 100
1708 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump House at Head work site under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000404/2021-2022 | 261/PD | 11/02/2022 | 100 | RABIN CHANDRA CHAIL | 15.35 | 11.51 | 85
1709 | Purulia Division | Raghunathpur Sub-Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Kashipur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000405/2022-2023 | 344/RNP | 01/06/2022 | 30 | GLORY ENGINEERS SYNDICATE | 1.4 | 1.4 | 100
1710 | Purulia Division | Raghunathpur Sub-Division | Supply fitting fixing MS Specials 200 mm dia in sluice valve chamber at Kashipur under Kashipur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000487/2024-2025 | 1517/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 1.44 | 0 | 95
1711 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of R.C.C. Old and New Elevated Reservoir including Pump House and other allied works under Kashipur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000920/2022-2023 | 1928/PD | 22/12/2022 | 90 | SUDHANSHU OJHA | 11.58 | 6.46 | 75
1712 | Purulia Division | Raghunathpur Sub-Division | Construction of Meter Room at Pump House Site (Kaduri) of Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Under Kashipur Water Supply Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/003510/2023-2024 | 347/PD | 04/03/2024 | 90 | SUBHAS CHANDRA MAHATO | 2.03 | 0 | 100
1713 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | RTOR000002/2022-2023 | 962/PD | 21/06/2022 | 0 | Resource Division | 18.67 | 0 | 0
1714 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | RTOR000017/2022-2023 | 975/PD | 22/06/2022 | 0 | Resource Division | 3.52 | 0 | 0
1715 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | RTOR000023/2021-2022 | 399/PD | 11/03/2022 | 0 | Resource Division | 17.15 | 0 | 0
1716 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) (Tender No.963/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000133/2022-2023 | BP-2022-23-7 | 05/04/2022 | 0 | MUNNA AGROTECH ENTERPRISE | 62.99 | 0 | 0
1717 | Purulia Division | Raghunathpur Sub-Division | Sinking of 4 nos 200 mm dia river bed tube well (Horizon) of Darekeswar river (Baikara Ghat) along with laying of 100mm dia GI collecting line with all allied works under Kashipur W/S Scheme (Tender No- 1008/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000191/2022-2023 | BP-2022-23-56 | 20/05/2022 | 0 | RABIN CHANDRA CHAIL | 9.27 | 0 | 0
1718 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) (Tender No.37/SE/PMU of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000679/2022-2023 | BP-2022-23-360 | 30/09/2022 | 0 | SANTANU BANERJEE | 207.93 | 0 | 0
1719 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000964/2021-2022 |  | 23/02/2022 | 0 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0
1720 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/001019/2021-2022 | BP-2021-22-266 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0
1721 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.836/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/001113/2021-2022 | BP-2021-22-333 | 23/03/2022 | 0 | STEELCONC AND ASSOCIATES | 1.97 | 0 | 0
1722 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of the contract demand from 60 KVA at 0.4 KV to 105/105//105/105/105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kashipur Water Supply, (Consumer ID -950023805) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00893/2023-2024 | BP-23-24-311 | 21/03/2024 | 0 | WBSEDCL KASHIPUR CCC | 4.47 | 0 | 0
1723 | Purulia Mechanical | Raghunathpur Sub-Division | Cable laying from river bed site to pump house at kashipur water supply scheme of augumentation and other allied works under PMD, PHE Dte in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000045/2024-2025 | 963/PMD | 20/06/2024 | 30 | PINTU DEY | 1.71 | 0 | 100
1724 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kashipur Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000087/2022-2023 | 430/PMD | 23/06/2022 | 30 | PREMNATH MITRA | 20.49 | 13.97 | 100
1725 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for augmentation of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000093/2022-2023 | 519/PMD | 05/08/2022 | 30 | DEY ENTERPRISE, HOWRAH | 10.24 | 10.23 | 80
1726 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of submersible pumping machinery at River Bed Tubewell and changing cable line, clamping and other allied works at Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000242/2024-2025 | 1230/PMD | 13/08/2024 | 20 | PINTU DEY | 1.62 | 0 | 100
1727 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000251/2022-2023 | 40/PMD | 19/01/2023 | 60 | PINTU DEY | 7.98 | 4.15 | 0
1728 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting of 3 Ton capacity triple spur gear type chain pulley Block Mono rail with others allied works for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000252/2022-2023 | 41/PMD | 19/01/2023 | 60 | RABINDRA NATH KHAN | 9.64 | 9.64 | 0
1729 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KASHIPUR Water supply Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000267/2022-2023 | 39/PMD | 19/01/2023 | 60 | WEST BENGAL ENGINEERING CO | 67.56 | 0 | 43
1730 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of KASHIPUR water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000284/2022-2023 | 75/PMD | 01/02/2023 | 60 | PINTU DEY | 11.26 | 7.88 | 100
1731 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery & installation of flow meter and with others allied works for Augmentation at KASHIPUR w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000341/2022-2023 | 123/PMD | 15/02/2023 | 60 | SANTU MITRA | 3.92 | 0 | 30
1732 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for Augmentation work of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000624/2024-2025 | 1546/PMD | 11/11/2024 | 460 | PINTU DEY | 12.16 | 0 | 45
1733 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Kashipur water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000684/2024-2025 | 1696/PMD | 06/12/2024 | 360 | PINTU DEY | 13.57 | 0 | 100
1734 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 60 KVA AT 0.4 KV TO 105/105/105/105/105 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 950023805) TO THEIR PREMISES AT KASHIPUR WATER SUPPLY KASHIPUR DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000424/2022-2023 | BP-22-23-87 | 28/02/2023 | 0 | WBSEDCL PURULIA | 3.71 | 0 | 0
1735 | Purulia Division | Raghunathpur Sub-Division | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Keliathole-Palashkola W/S Scheme on Hura Kashipur Adra Raghunathpur Road (From Ch.22.163 Km to Ch.22.825 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00454/2023-2024 | BP-2023-24-313 | 26/07/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 41.92 | 0 | 0
1736 | Purulia Division | Raghunathpur Sub-Division | Sl ii) Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur WS Scheme along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division PWD in the district of Purulia in Year 2023-2024. Estimate Amount: Rs.1,21,59,280/- | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00736/2024-2025 | BP-2024-25-408 | 22/09/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 57.29 | 0 | 0
1737 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) and other allied works of Keliathole Palashkola Water Supply Scheme(Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000025/2023-2024 | 142/RNP | 06/04/2023 | 7 | AMIT PATHAK | 0.93 | 0.93 | 0
1738 | Purulia Division | Raghunathpur Sub-Division | Laying distribution pipe line and other allied work under Keliathole Palashkola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000049/2023-2024 | 673/PD | 17/05/2023 | 807 | PREMNATH MITRA | 70.11 | 30.34 | 100
1739 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rudra Mouza, JL No.-10, Plot No.68 at OHR site under Keliyathole-Palashkola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000070/2023-2024 | 701/PD | 22/05/2023 | 60 | MAHARSHI BANERJEE | 14.33 | 0 | 70
1740 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution System of pipe line at Kakdiha village is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Kalyathol & Palaskhola Piped Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000132/2024-2025 | 898/PD | 07/05/2024 | 45 | SABYASACHI MISHRA | 14.23 | 0 | 100
1741 | Purulia Division | Raghunathpur Sub-Division | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 4 & 5) along with necessary 100 mm dia GI collecting line from Riverbed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakurighat of Parbeliya W/S Scheme under Keliyathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000211/2024-2025 | 1244/PD | 04/07/2024 | 45 | M/S KARUNAMOYEE CONSTRUCTION | 4.38 | 0 | 100
1742 | Purulia Division | Raghunathpur Sub-Division | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-III OHR site & supplying laying fitting fixing Parallel pipe line at Rangadihi Village & Kharpara village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(Zone -III) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000329/2024-2025 | 1354/PD | 25/07/2024 | 90 | SUBRATA SINGHADEO | 22.28 | 0 | 100
1743 | Purulia Division | Raghunathpur Sub-Division | Sinking of 1(One) nostubewell, laying DI pipe , filling and surface dressing at OHR Site of Zone - I of Kashipur Block under Keliathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000330/2024-2025 | 1355/PD | 25/07/2024 | 30 | MAHARSHI BANERJEE | 6.26 | 0 | 80
1744 | Purulia Division | Raghunathpur Sub-Division | Repering & Renovation of connecting line at Kasai River of Maguria Lalpur & including providing House Hold Tap Connection (FHTC) of two no school (Amliatora Pry School -1no, Daldali Girls High School-2nos) and other allied works under Maguria Lalpur W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000378/2024-2025 | 1359/PD | 25/07/2024 | 60 | ALOK KUMAR CHAKRABORTY | 2.54 | 0 | 100
1745 | Purulia Division | Raghunathpur Sub-Division | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/I) (Mouza- Keliathole, Hab- Keliathole) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000381/2022-2023 | 333/RNP | 01/06/2022 | 45 | NANIGOPAL DEY | 4.58 | 4.57 | 100
1746 | Purulia Division | Raghunathpur Sub-Division | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/II) (Mouza- Keliathole, Hab.- Keliathole) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000382/2022-2023 | 334/RNP | 01/06/2022 | 45 | NANIGOPAL DEY | 4.46 | 4.29 | 100
1747 | Purulia Division | Raghunathpur Sub-Division | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/I) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000383/2022-2023 | 335/RNP | 01/06/2022 | 45 | SUBHAS CHANDRA MAHATO | 4.55 | 4.52 | 100
1748 | Purulia Division | Raghunathpur Sub-Division | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/II) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000384/2022-2023 | 336/RNP | 01/06/2022 | 45 | AMIT PATHAK | 4.55 | 4.53 | 100
1749 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Keliathole-Palashkola W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000386/2022-2023 | 338/RNP | 01/06/2022 | 45 | CHANCHAL MISHRA | 4.23 | 3.93 | 0
1750 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Keliathole -Palashkola Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000390/2022-2023 | 348/RNP | 01/06/2022 | 20 | SUBHAS CHANDRA MAHATO | 1.48 | 0 | 100
1751 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathole W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000439/2020-2021 | 357/D/PD | 25/02/2021 | 30 | STEELCONC AND ASSOCIATES | 7.72 | 7.72 | 100
1752 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe line from Chatanigoramore to Kharhbon & Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000443/2024-2025 | 1505/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 29.59 | 0 | 100
1753 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Chatanigora , & Pinrrah Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000444/2024-2025 | 1506/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 45.72 | 0 | 100
1754 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of different dia pipe line & FHTC connection repairing (Damage of Old different dia pipe line & FHTC connection due to widening of road & Drain of PWD Roads from Doldoli more to Mourandih more &Karandih village ) in connection with Jal Jeevan Mission (JJM) under Maguria Lalpur Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division uneder Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000460/2024-2025 | 1519/PD | 27/08/2024 | 45 | ALOK KUMAR CHAKRABORTY | 16.16 | 0 | 100
1755 | Purulia Division | Raghunathpur Sub-Division | Laying of Distribution line and Road Crossing and Construction of Sluice valve Chamber and other allied works for Kashipur under Kalyathol & Palaskhola W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000492/2024-2025 | 1707/PD | 05/09/2024 | 45 | MAHARSHI BANERJEE | 33.25 | 0 | 80
1756 | Purulia Division | Raghunathpur Sub-Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000547/2022-2023 | 465/RNP | 14/07/2022 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 2.79 | 100
1757 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC elevated reservoir of capacity 150 cum under Keliathole Palaskola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000633/2022-2023 | 1401/PD | 01/09/2022 | 270 | SANTANU BANERJEE | 67.83 | 0 | 90
1758 | Purulia Division | Raghunathpur Sub-Division | Construction of RCC elevated reservoir of capacity 250 cum under Keliathole Palaskola W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000634/2022-2023 | 1402/PD | 01/09/2022 | 270 | RABIN CHANDRA CHAIL | 78.62 | 62.42 | 100
1759 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000640/2022-2023 | 1162/PD | 01/08/2022 | 974 | MADHU SUDAN RAKSHIT | 121.14 | 70.07 | 90
1760 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing functional Household Tap Connection (FHTC), Laying Clear water Rising main ,Sinking of 6 (Six) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line , and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000641/2022-2023 | 1252/PD | 30/08/2022 | 945 | PRINCE INDUSTRIES ( INDIA) | 188.52 | 124.53 | 70
1761 | Purulia Division | Raghunathpur Sub-Division | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Dolang Kocha Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000670/2023-2024 | 1358/PD | 13/09/2023 | 45 | CHANDAN CHATTERJEE | 16.26 | 0 | 100
1762 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000734/2022-2023 | 1443/PD | 14/09/2022 | 1052 | PREMNATH MITRA | 265.46 | 215.57 | 95
1763 | Purulia Division | Raghunathpur Sub-Division | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-L) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000752/2022-2023 | 1421/PD | 08/09/2022 | 45 | M/S NANDY ENTERPRISE | 108.08 | 78.66 | 90
1764 | Purulia Division | Raghunathpur Sub-Division | Providing functional Household Tap Connection (FHTC) including Other allied works under Keliathole Palaskola W/S Scheme (Zone-I & III) under Raghunathpur Sub-Division, P.H.E. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000901/2022-2023 | 1893/PD | 15/12/2022 | 60 | BASANTA KUMAR SINGHADEO | 129.67 | 103.61 | 90
1765 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of Elevated Reservoir at Keliathole Zone and Palashkola Zone including Head work site and other allied works under Keliathole Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000916/2022-2023 | 1925/PD | 22/12/2022 | 90 | SUBHAS CHANDRA MAHATO | 13.16 | 0 | 100
1766 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution system ,Functional House hold tap Connection including other allied work under Keliathole Palashkola W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/001082/2024-2025 | 2177/PD | 13/12/2024 | 60 | SUBRATA SINGHADEO | 1.69 | 0 | 0
1767 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System, installation of Valve, Construction of Valve Chamber and other allied works at Gap Portion under Keliathole Palashkola w/s Scheme (Zone-I) within Raghunathpur Sub-Division Under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/001095/2024-2025 | 2184/PD | 13/12/2024 | 336 | MADHU SUDAN RAKSHIT | 19.21 | 0 | 90
1768 | Purulia Division | Raghunathpur Sub-Division | Supply, delivery fitting & fixing of 33Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Kashipur Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/001156/2024-2025 | 2308/PD | 31/12/2024 | 60 | BISWAJIT MAJI | 3.01 | 0 | 100
1769 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Guarding arrangement through Registered firm organized by Ex-Military person for Guarding of all Govt. properties laying at Keliyathol Elevated Reservoir site under Palaskola-Kelyathol W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (w.e.f. 01.09.2022 to 30.10.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/001221/2022-2023 | 1360/PD | 31/08/2022 | 60 | MANBHUM SECURITY SERVICE | 1.46 | 0 | 0
1770 | Purulia Division | Raghunathpur Sub-Division | Construction of Office Cum Godown at PHE Campus Under Keliathole Palashkola w/s Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/001869/2023-2024 | 93/PD | 15/01/2024 | 90 | KM ENTERPRISES | 25.62 | 0 | 100
1771 | Purulia Division | Raghunathpur Sub-Division | Additional estimate for laying of distribution system, mending good damage of road and other allied works under Keliathole Palashkola w/s Scheme (Zone-III) within Raghunathpur Sub Division Under Purulia Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/003976/2023-2024 | 521/PD | 16/03/2024 | 503 | PREMNATH MITRA | 87.58 | 0 | 0
1772 | Purulia Division | Raghunathpur Sub-Division | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/004361/2023-2024 | 55/PD | 09/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 8.13 | 0 | 95
1773 | Purulia Division | Raghunathpur Sub-Division | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/004362/2023-2024 | 56/PD | 09/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 8.58 | 0 | 95
1774 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | RTOR000042/2022-2023 | 314/PD | 03/03/2023 | 0 | Resource Division | 528.8 | 0 | 0
1775 | Purulia Division | Raghunathpur Sub-Division | Preparation of DPR (Consultancy Work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathol W/s Scheme, Block Kashipur) to be Augmented/Retrofitting. (Tender No.835/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000330/2022-2023 | BP-2022-23-232 | 05/09/2022 | 0 | STEELCONC AND ASSOCIATES | 2.32 | 0 | 0
1776 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.68/SE/PMU of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/001053/2022-2023 | BP-2022-23-397 | 20/10/2022 | 0 | MADHU SUDAN RAKSHIT | 44.2 | 0 | 0
1777 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of contractual demand from 90 KVA at 0.4 KV to their premises at PALASHKHOLA WATER SUPPLY, Dist- Purulia under Regional Office Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00113/2023-2024 |  | 20/07/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0
1778 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of the contract demand from 90 KVA at 0.4 KV to 180/180/180/180/180 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Palashkhola Water Supply, (Consumer ID -942406300) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00862/2023-2024 | BP-23-24-340 | 21/03/2024 | 0 | WBSEDCL PURULIA | 16.57 | 0 | 0
1779 | Purulia Mechanical | Raghunathpur Sub-Division | Rectification of Internal lighting and external lighting for Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000049/2023-2024 | 518/PMD | 05/05/2023 | 60 | RAKSHIT ENTERPRISE | 9.24 | 0 | 100
1780 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation 200 kva voltage stabilizer for Augmentation of Palashkhola Keliyathol w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000050/2023-2024 | 519/PMD | 05/05/2023 | 60 | ALPHA ENTERPRISES | 26.97 | 0 | 100
1781 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & installation of Horizontal Multistage Centrifugal pumping machinery with other allied works for Augmentation at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000118/2023-2024 | 646/PMD | 08/06/2023 | 662 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 77.49 | 0 | 100
1782 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Palashkhola Keliyathol Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000385/2022-2023 | 216/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 12.91 | 100
1783 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & installation of submersible pumping machinery at River Bed Tubewell at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000448/2022-2023 | 267/PMD | 06/03/2023 | 60 | SAIBAL SARKAR | 47.89 | 13.06 | 50
1784 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Nanduka Mouza, JL No.-63, Plot No.-476 under Raghunathpur-II Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte | Assistant Engineer |  | ORD/000067/2023-2024 | 698/PD | 22/05/2023 | 60 | AMIT PATHAK | 14.25 | 7.21 | 100
1785 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Khajura Mouza, JL No.-164, Plot No.-565 under Raghunathpur-I Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000079/2023-2024 | 766/PD | 08/06/2023 | 60 | MAA TARA CONSTRUCTION | 11.42 | 0 | 100
1786 | Purulia Division | Raghunathpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 100
1787 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 100
1788 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 100
1789 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1790 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1791 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1792 | Purulia Division | Raghunathpur Sub-Division | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 100
1793 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of Gar Panchakot Inspection Bunglow (1st Floor & outside) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001046/2022-2023 | 278/PD | 27/02/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 3.09 | 0 | 0
1794 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Simra ,Pabra , Nabagram, Muchkunda , Muldi , pratappur , Dhanuktor , Manipur) | Assistant Engineer |  | ORD/001112/2024-2025 | 2204/PD | 13/12/2024 | 60 | SANTANU BANERJEE | 96.18 | 0 | 0
1795 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VA) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 7) | Assistant Engineer |  | ORD/001192/2022-2023 | 461/PD | 27/03/2023 | 733 | SANTANU BANERJEE | 341.55 | 140.53 | 75
1796 | Purulia Division | Raghunathpur Sub-Division | Construction of Switch Room Cum Chlorin Room at Zone-V-B (Nanduka) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001359/2023-2024 | 1728/PD | 04/12/2023 | 100 | MANIK MAHATO | 4.86 | 0 | 100
1797 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000031/2024-2025 | 1104/PD | 11/06/2024 | 0 | Resource Division | 25.08 | 0 | 0
1798 | Purulia Division | Purulia Division | Survey in connection with the Mini Water Supply Scheme having house hold within 20 under Arsha, Baghmundi, Balarampur, Barabazar, Bundwan, Jaipur & Jhalda-I Block [3+14+5+22+10+6+18=78 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000052/2022-2023 | 112/A/PSD | 10/02/2023 | 21 | M/S R. DUTTA & CO. | 3.07 | 2.28 | 0
1799 | Purulia Division | Purulia Sadar Sub-Division | Electric quotation along with M.B No1200/PMD for payment of shifting of 11KV PHE feeder & 11 KV Rampur feeder from Northern Sector WTP Campus for payment from your end. | Assistant Engineer |  | BILL/01971/2023-2024 | BP-2023-24-889 | 18/03/2024 | 0 | WBSEDCL | 45.82 | 0 | 0
1800 | Purulia Division | Purulia Sadar Sub-Division | Details survey of WTP site as well as intake site to ascertion depth and area basin at Shiulibari Mouza, Nituria Block under Northern Zone W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000020/2023-2024 | 549/PD | 12/04/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 5.39 | 0 | 100
1801 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | Assistant Engineer |  | ORD/000895/2023-2024 | 1560/PD | 18/10/2023 | 1171 | RAJ BROTHERS | 264.65 | 0 | 22
1802 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - V & VI of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 270 m). | Assistant Engineer |  | ORD/001825/2023-2024 | 63/PD | 10/01/2024 | 415 | SUBHAS CHANDRA MAHATO | 37.7 | 0 | 100
1803 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000035/2024-2025 | 1904/PD | 21/10/2024 | 0 | Resource Division | 66.57 | 0 | 0
1804 | Purulia Mechanical | Purulia Sadar Sub-Division | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Assistant Engineer, Purulia Mechanical Sub-Division (W/S) PHE, Dte. (01/10/24 to 31/03/25) | Assistant Engineer |  | ORD/000614/2024-2025 | 399/PMSD(W/S) | 23/09/2024 | 182 | PINTU DEY | 0.86 | 0 | 0
1805 | Purulia Division | Purulia Sadar Sub-Division | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.924/PWD dt.19.06.2024) (Norther Sector) | Assistant Engineer |  | BILL/00579/2024-2025 | BP-2024-25-340 | 28/08/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0
1806 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050611202404020185125751XX DT.06-11-2024. | Assistant Engineer |  | BILL/00957/2024-2025 | BP-2024-25-527 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1807 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412201575410323XX DT.11-11-2024. | Assistant Engineer |  | BILL/00958/2024-2025 | BP-2024-25-529 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1808 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412211573995764XX DT.11-11-2024. | Assistant Engineer |  | BILL/00959/2024-2025 | BP-2024-25-528 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1809 | Purulia Division | Purulia Sadar Sub-Division | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.1536/PWD dt.27.09.2024) (Norther Sector) | Assistant Engineer |  | BILL/00961/2024-2025 | BP-2024-25-530 | 14/11/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0
1810 | Purulia Division | Purulia Sadar Sub-Division | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052611202406351574709356XX DT.26-11-2024. | Assistant Engineer |  | BILL/01024/2024-2025 | BP-2024-25-532 | 02/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0
1811 | Purulia Division | Purulia Sadar Sub-Division | Jack pushing between Sanka & Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000013/2025-2026 | 570/PD | 07/04/2025 | 359 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0
1812 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I & III of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000031/2025-2026 | 677/PD | 24/04/2025 | 120 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0
1813 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000032/2025-2026 | 679/PD | 24/04/2025 | 120 | BHAGABAN DAS KUMAR | 16.55 | 0 | 0
1814 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IX & X of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000033/2025-2026 | 681/PD | 24/04/2025 | 120 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0
1815 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV & V of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000034/2025-2026 | 684/PD | 24/04/2025 | 120 | GANGULY ENTERPRISES | 33.21 | 0 | 0
1816 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VIII & IX of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000035/2025-2026 | 685/PD | 24/04/2025 | 120 | SEKH ABBAS | 33.39 | 0 | 0
1817 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XII & XIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000036/2025-2026 | 687/PD | 24/04/2025 | 240 | BASANTA PARAMANIK | 33.34 | 0 | 0
1818 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XI, & XIII of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000037/2025-2026 | 686/PD | 24/04/2025 | 360 | MADHU SUDAN RAKSHIT | 33.04 | 0 | 0
1819 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV & V of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000039/2025-2026 | 680/PD | 24/04/2025 | 120 | M D CONSTRUCTION | 33.33 | 0 | 0
1820 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000040/2025-2026 | 691/PD | 24/04/2025 | 342 | PRINCE INDUSTRIES ( INDIA) | 16.7 | 0 | 0
1821 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VIII, IX & X of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000042/2025-2026 | 693/PD | 24/04/2025 | 120 | SANTANU BANERJEE | 49.72 | 0 | 0
1822 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV & V of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000044/2025-2026 | 697/PD | 24/04/2025 | 120 | M/S CONTRACTORS SYNDICATE | 33.19 | 0 | 0
1823 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VII & VIII of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000045/2025-2026 | 699/PD | 24/04/2025 | 120 | SANJAY KUMAR NARSARIA | 33.38 | 0 | 0
1824 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-V of Santuri Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000046/2025-2026 | 700/PD | 24/04/2025 | 120 | MAA TARA CONSTRUCTION | 16.7 | 0 | 0
1825 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone- IV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2025-2026 | 701/PD | 24/04/2025 | 120 | CHINMOY SEN | 16.58 | 0 | 0
1826 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XIV & XV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000048/2025-2026 | 702/PD | 24/04/2025 | 120 | CHANDAN CHATTERJEE | 33.16 | 0 | 0
1827 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VI, VII of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000052/2025-2026 | 707/PD | 24/04/2025 | 120 | SANTOSH KUMAR | 33.33 | 0 | 0
1828 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VIII of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000053/2025-2026 | 708/PD | 24/04/2025 | 120 | SUDHANSHU OJHA | 16.6 | 0 | 0
1829 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000054/2025-2026 | 709/PD | 24/04/2025 | 120 | SINGHA ENTERPRISE | 50.03 | 0 | 0
1830 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000055/2025-2026 | 710/PD | 24/04/2025 | 120 | DEBSHANKAR LAYEK | 16.62 | 0 | 0
1831 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VI, VII & VIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000057/2025-2026 | 712/PD | 24/04/2025 | 120 | AMITAVA KUNDU | 49.74 | 0 | 0
1832 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone- XI of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000058/2025-2026 | 713/PD | 24/04/2025 | 120 | CHANCHAL MISHRA | 16.66 | 0 | 0
1833 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VII of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000059/2025-2026 | 714/PD | 24/04/2025 | 120 | CHANCHAL MISHRA | 16.65 | 0 | 0
1834 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, II of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000060/2025-2026 | 715/PD | 24/04/2025 | 120 | JULI ENTERPRISE | 33.35 | 0 | 0
1835 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000061/2025-2026 | 716/PD | 24/04/2025 | 120 | TOTAL INFRA | 50.08 | 0 | 0
1836 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XVI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000062/2025-2026 | 717/PD | 24/04/2025 | 120 | JOGMAYA CONSTRUCTION | 16.54 | 0 | 0
1837 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution pipeline, providing FHTC including other allied works for Zone- II of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A Mouza- MURULIA (3.5%)] | Assistant Engineer |  | ORD/000063/2023-2024 | 694/PD | 22/05/2023 | 872 | MAHARSHI BANERJEE | 95.06 | 0 | 90
1838 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000063/2025-2026 | 719/PD | 24/04/2025 | 120 | TARA MAA SHAKTI CONSTRUCTION | 50.06 | 0 | 0
1839 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000064/2025-2026 | 721/PD | 24/04/2025 | 362 | M/S S & P CONSTRUCTION | 50.09 | 0 | 0
1840 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) with allied works for Zone- IV of Santuri Block under Purulia Piped Water Supply Scheme ( Northern Zone ) under Purulia Divn. PHE Dte. | Assistant Engineer |  | ORD/000065/2023-2024 | 693/PD | 22/05/2023 | 1045 | M/S. BADAL GHOSH | 87.8 | 0 | 65
1841 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012)with allied works for Zone- V of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. | Assistant Engineer |  | ORD/000066/2023-2024 | 692/PD | 22/05/2023 | 210 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 81.57 | 0 | 0
1842 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000066/2025-2026 | 723/PD | 24/04/2025 | 342 | PRINCE INDUSTRIES ( INDIA) | 50.11 | 0 | 0
1843 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-II, III & IV of Raghunathpur-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000067/2025-2026 | 724/PD | 24/04/2025 | 120 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 50.1 | 0 | 0
1844 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-V & VI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000069/2025-2026 | 678/PD | 24/04/2025 | 120 | AIM CONSTRUCTION | 33.38 | 0 | 0
1845 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-VII & VIII of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000070/2025-2026 | 690/PD | 24/04/2025 | 120 | SATYA NARAYAN BELTHARIA | 33.04 | 0 | 0
1846 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone- XVI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000109/2025-2026 | 694/PD | 24/04/2025 | 120 | PROBODH CHANDRA MAJHI | 16.69 | 0 | 0
1847 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI rising main including bypass arrangement & other allied works & construction of boundary wall at Baghmundi WTP Site in Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000127/2024-2025 | 895/PD | 07/05/2024 | 60 | ROY CONSTRUCTION | 36.11 | 0 | 100
1848 | Purulia Division | Purulia Sadar Sub-Division | Sinking of 1(One) nos tube well, Withdrawing and relaying of DI Pipe, Earth filling and surface dressing Near Northern Sector Head work site under Purulia Piped w/s Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000142/2024-2025 | 912/PD | 07/05/2024 | 30 | CHATTERJEE CONSTRUCTION | 7.82 | 0 | 85
1849 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Neturia (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000150/2024-2025 | 923/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 63.99 | 0 | 0
1850 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XV & XVI of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000162/2025-2026 | 695/PD | 24/04/2025 | 120 | BISHAL ENTERPRISE | 33.38 | 0 | 0
1851 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone- X of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000163/2025-2026 | 718/PD | 24/04/2025 | 120 | BISHAL ENTERPRISE | 16.68 | 0 | 0
1852 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XI of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000164/2025-2026 | 706/PD | 24/04/2025 | 120 | B.M ENTERPRISE | 16.66 | 0 | 0
1853 | Purulia Division | Purulia Sadar Sub-Division | Laying of Left-out Distribution HDPE Pipe line and other allied work for Zone - III of Raghunathpur - I Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHEDte. | Assistant Engineer |  | ORD/000195/2025-2026 | 1055/PD | 17/06/2025 | 288 | KM ENTERPRISES | 48.34 | 0 | 100
1854 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall at OHR(200 cum)site of ZONE III at Dhunari Mouza of Purulia 2 Block under Purulia piped water supply scheme( Northern Sector) under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000196/2025-2026 | 1056/PD | 17/06/2025 | 372 | BISWAJIT MAJI | 16.97 | 0 | 0
1855 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 20) | Assistant Engineer |  | ORD/000197/2024-2025 | 1031/PD | 04/06/2024 | 424 | ANUP KUMAR SAHA | 148.36 | 0 | 0
1856 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 600 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) with allied works for Zone- I of Purulia-1 Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Sl No. 01) | Assistant Engineer |  | ORD/000198/2024-2025 | 1026/PD | 04/06/2024 | 270 | SADHAN GORAIN | 141.19 | 0 | 0
1857 | Purulia Division | Purulia Sadar Sub-Division | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000198/2025-2026 | 1058/PD | 17/06/2025 | 45 | SWAPAN MANDAL | 0 | 0 | 0
1858 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and Laying Distribution Pipe Lines with allied works for Zone-II of Neturia Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.[ Part - A, Mouza- Puapur ] (Sl No. 06) | Assistant Engineer |  | ORD/000199/2024-2025 | 1029/PD | 04/06/2024 | 270 | KHITISH CHANDRA PATHAK | 157.44 | 0 | 0
1859 | Purulia Division | Purulia Sadar Sub-Division | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000199/2025-2026 | 1058/PD | 17/06/2025 | 198 | SWAPAN MANDAL | 23.25 | 0 | 80
1860 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-II of Purulia-I block for Bhul Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 02) | Assistant Engineer |  | ORD/000200/2024-2025 | 1028/PD | 04/06/2024 | 269 | SOUMITRA CHAKRABORTY | 113.07 | 0 | 50
1861 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and providing Functional Household Tap Connection (Mouza - Bhul) with allied works for Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 01) | Assistant Engineer |  | ORD/000201/2024-2025 | 1027/PD | 04/06/2024 | 270 | M DHARA & BROTHERS | 131.3 | 0 | 0
1862 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VI of Purulia-I block for Shibdi Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 30) | Assistant Engineer |  | ORD/000202/2024-2025 | 1030/PD | 04/06/2024 | 60 | MS D.PALIT AND CO. | 120.66 | 0 | 0
1863 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Neturia (Zone - I) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000208/2025-2026 | 1067/PD | 17/06/2025 | 120 | SAANVI CONSTRUCTION | 14.4 | 0 | 0
1864 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - IV & VII) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000209/2025-2026 | 1069/PD | 17/06/2025 | 120 | MANTAJ ANSARI | 28.8 | 0 | 0
1865 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Joypur (Zone - II & VIII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000210/2025-2026 | 1071/PD | 17/06/2025 | 120 | SAZID HOSSEN ANSARI | 28.82 | 0 | 0
1866 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - II & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000211/2025-2026 | 1072/PD | 17/06/2025 | 120 | SUBHAS CHANDRA MAHATO | 28.7 | 0 | 0
1867 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Hura (Zone - III & IX) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000212/2025-2026 | 1073/PD | 17/06/2025 | 120 | MOHOR CONSTRUCTION | 28.69 | 0 | 0
1868 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Hura (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000214/2025-2026 | 1075/PD | 17/06/2025 | 120 | MS D.PALIT AND CO. | 28.8 | 0 | 0
1869 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Para (Zone - V & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000215/2025-2026 | 1076/PD | 17/06/2025 | 120 | M/S CONTRACTORS SYNDICATE | 28.66 | 0 | 0
1870 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Kashipur (Zone - VII & XII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000218/2025-2026 | 1082/PD | 17/06/2025 | 360 | MADHU SUDAN RAKSHIT | 28.7 | 0 | 0
1871 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Jhalda-II (Zone - II, III & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2025-2026 | 1083/PD | 17/06/2025 | 120 | MAHATO CONSTRUCTION | 43.05 | 0 | 0
1872 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Santuri (Zone - I, VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000220/2025-2026 | 1084/PD | 17/06/2025 | 120 | CHATTERJEE CONSTRUCTION | 43.27 | 0 | 0
1873 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (Part B) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000224/2024-2025 | 1060/PD | 07/06/2024 | 60 | SOUMITRA CHAKRABORTY | 77.87 | 0 | 0
1874 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Para (Zone - X&XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000231/2025-2026 | 1077/PD | 17/06/2025 | 120 | AMRIT CONSTRUCTION | 28.63 | 0 | 0
1875 | Purulia Division | Purulia Sadar Sub-Division | Supplying fitting and fixing M.S. gate of Jail type and 600 mm (+/- 30 mm) diametre R.B.T (Reinforced Barbed Tape) Concertina fencing work of Zone - IV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000241/2025-2026 | 340/RNP | 20/06/2025 | 7 | CHINMOY SEN | 0.86 | 0 | 98
1876 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Salberya] | Assistant Engineer |  | ORD/000242/2023-2024 | 1058/PD | 08/08/2023 | 443 | SUBHAS CHANDRA MAHATO | 42.72 | 0 | 48
1877 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Bhagabandh, Kherad] | Assistant Engineer |  | ORD/000243/2023-2024 | 1059/PD | 08/08/2023 | 518 | SINGHA ENTERPRISE | 51.36 | 0 | 0
1878 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Benagaria(5%), Ghutgarya, Latulbad & Dulalgora] | Assistant Engineer |  | ORD/000244/2023-2024 | 1060/PD | 08/08/2023 | 60 | PRATIK SAHA | 93.7 | 0 | 70
1879 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000244/2025-2026 | 689/PD | 24/04/2025 | 120 | SUMANTA GHOSH | 49.86 | 0 | 0
1880 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Amlagarya, Shaltora & Rambhatdi] | Assistant Engineer |  | ORD/000245/2023-2024 | 1061/PD | 08/08/2023 | 878 | SUBRATA SINGHADEO | 76.77 | 0 | 30
1881 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-V & VII of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000245/2025-2026 | 698/PD | 24/04/2025 | 120 | SUMANTA GHOSH | 33.24 | 0 | 0
1882 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - A , Mouza - Dhenksila, Ledasan] | Assistant Engineer |  | ORD/000246/2023-2024 | 1062/PD | 08/08/2023 | 60 | BOSE CONSTRUCTION | 83.17 | 0 | 0
1883 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Benagaria] | Assistant Engineer |  | ORD/000247/2023-2024 | 1063/PD | 08/08/2023 | 60 | KABERI DUTTA | 32.36 | 0 | 76
1884 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Jiyataal, Chhayrabari, Ambari] | Assistant Engineer |  | ORD/000248/2023-2024 | 1052/PD | 08/08/2023 | 60 | M/S. BADAL GHOSH | 93.96 | 0 | 60
1885 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Tarabari, Gumra] | Assistant Engineer |  | ORD/000249/2023-2024 | 1050/PD | 08/08/2023 | 602 | KHITISH CHANDRA PATHAK | 96.93 | 0 | 60
1886 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Lapahari, Nuhichabad, Moraldi] | Assistant Engineer |  | ORD/000250/2023-2024 | 1051/PD | 08/08/2023 | 60 | SUMIT KUMAR CHAKRABORTY | 58.97 | 0 | 60
1887 | Purulia Division | Purulia Sadar Sub-Division | Allied work of laying Distribution pipe line and other allied works for Zone-III of Santuri Block Purulia pipe Water Supply Scheme (Northern Sector ) under Purulia Division PHE Dte Part-C ( Mouza- Brindabanpur, Vill.- Asharikand ) | Assistant Engineer |  | ORD/000250/2025-2026 | 1117/PD | 23/06/2025 | 45 | M/S MONDAL ENTERPRISE | 55.57 | 0 | 0
1888 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Amdiha, Bidhakata] | Assistant Engineer |  | ORD/000251/2023-2024 | 1064/PD | 08/08/2023 | 482 | CHANDAN CHATTERJEE | 37.59 | 0 | 60
1889 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Kankarkiari, Malibana, Dubrajpur] | Assistant Engineer |  | ORD/000252/2023-2024 | 1065/PD | 08/08/2023 | 1123 | MADHU SUDAN RAKSHIT | 59.37 | 0 | 65
1890 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone- VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Gorsika] | Assistant Engineer |  | ORD/000253/2023-2024 | 1068/PD | 08/08/2023 | 545 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 71.26 | 0 | 50
1891 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC) including other allied work for Zone VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza-kulal &gothbathanj] | Assistant Engineer |  | ORD/000254/2023-2024 | 1069/PD | 08/08/2023 | 60 | SK ABBAS | 31.68 | 0 | 45
1892 | Purulia Division | Purulia Sadar Sub-Division | Pushing of 600mm dia RCC pre cast pipe and 200 mm dia MS water carrier pipe by hydraulic jacking method across Pirargaria Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and Installation of 2(two) nos of Tubewell through DTH process at OHR site of Zone-III of Purulia-II Block Purulia piped W/S Scheme( Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000254/2025-2026 | 929/PD | 27/05/2025 | 219 | SOUVIK MANDAL | 13.1 | 0 | 60
1893 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Kendthol & Kharbar] | Assistant Engineer |  | ORD/000255/2023-2024 | 1070/PD | 08/08/2023 | 60 | ASHOKE ADHIKARY | 28.6 | 0 | 45
1894 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Raghunathpur-I (Zone - I & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000255/2025-2026 | 999/PD | 11/06/2025 | 120 | DILIP MISHRA | 28.4 | 0 | 0
1895 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Palash Pahari & Benrya] | Assistant Engineer |  | ORD/000256/2023-2024 | 1071/PD | 08/08/2023 | 60 | M/S KHAN ENTERPRISE | 42.09 | 0 | 70
1896 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F, Mouza - Goalberya &Matidundra] | Assistant Engineer |  | ORD/000257/2023-2024 | 1072/PD | 08/08/2023 | 60 | TAPAN CHANDRA | 49.95 | 0 | 48
1897 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A , Mouza - Kandberya & Authumajhirdi] | Assistant Engineer |  | ORD/000258/2023-2024 | 1077/PD | 10/08/2023 | 60 | M/S KALYANI ENTERPRISE | 95.29 | 0 | 60
1898 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C , Mouza - Saoradi & Kushtor] | Assistant Engineer |  | ORD/000259/2023-2024 | 1079/PD | 10/08/2023 | 45 | BASANTA PARAMANIK | 28.33 | 0 | 0
1899 | Purulia Division | Purulia Sadar Sub-Division | Continuation Order for the Work of Jack pushing between Sanka &Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000259/2025-2026 | 1208/PD | 08/07/2025 | 327 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0
1900 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Kinaidih & Majharadih] | Assistant Engineer |  | ORD/000260/2023-2024 | 1080/PD | 10/08/2023 | 529 | THE BUSINESS ENGINEERS INDIA | 25.17 | 0 | 65
1901 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Lalgarh] | Assistant Engineer |  | ORD/000261/2023-2024 | 1082/PD | 10/08/2023 | 60 | M/S SAYAK BHATTACHARYA | 71.84 | 0 | 100
1902 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Muktipur] | Assistant Engineer |  | ORD/000262/2023-2024 | 1083/PD | 10/08/2023 | 60 | CHATTERJEE CONSTRUCTION | 94.06 | 0 | 75
1903 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including submission of complete detailed drawing of distribution system, rising main etc. after execution of work and other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division , PHE Dte. [Part - C, Mouza - Pachandapur, Beliapur & Kalikapur] | Assistant Engineer |  | ORD/000263/2023-2024 | 1084/PD | 10/08/2023 | 60 | RANJIB GHATAK | 91.79 | 0 | 60
1904 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Brindabanpur] | Assistant Engineer |  | ORD/000264/2023-2024 | 1078/PD | 10/08/2023 | 60 | M/S MONDAL ENTERPRISE | 74.83 | 0 | 60
1905 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Kotaldih] | Assistant Engineer |  | ORD/000265/2023-2024 | 1081/PD | 10/08/2023 | 45 | HAFIJUR RAHAMAN MIDYA | 39.96 | 0 | 90
1906 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-6) | Assistant Engineer |  | ORD/000270/2023-2024 | 1098/PD | 14/08/2023 | 270 | PRAVAT SARKAR | 406.17 | 0 | 0
1907 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte.(SL-16) | Assistant Engineer |  | ORD/000273/2023-2024 | 1094/PD | 14/08/2023 | 270 | KOUSHIK CHATTERJEE | 274.47 | 0 | 0
1908 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-5) | Assistant Engineer |  | ORD/000275/2023-2024 | 1093/PD | 14/08/2023 | 270 | MS D.PALIT AND CO. | 373.13 | 0 | 0
1909 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution Pipe Line with allied works for Zone- VII of Santuri Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. [Part - A Mouza-Gorsika] | Assistant Engineer |  | ORD/000281/2023-2024 | 1138/PD | 17/08/2023 | 1088 | AMIT PATHAK | 94.37 | 0 | 20
1910 | Purulia Division | Purulia Sadar Sub-Division | Construction of boundary wall at Zone IV H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000286/2023-2024 | 1144/PD | 17/08/2023 | 30 | DILIP MISHRA | 17.51 | 0 | 0
1911 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000326/2025-2026 | 1384/PD | 29/07/2025 | 120 | ZAKIR HOSSIN MONDAL | 28.83 | 0 | 0
1912 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - IX & X) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000327/2025-2026 | 1390/PD | 29/07/2025 | 120 | PRASENJIT CHOUDHURY | 28.56 | 0 | 0
1913 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - IV & V) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000328/2025-2026 | 1389/PD | 29/07/2025 | 120 | DALIM ENTERPRISE | 28.27 | 0 | 0
1914 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - X & XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000329/2025-2026 | 1388/PD | 29/07/2025 | 120 | SEKH IRFAN | 28.69 | 0 | 0
1915 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-IX of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000363/2025-2026 | 1523/PD | 19/08/2025 | 120 | AMIT PATHAK | 16.61 | 0 | 0
1916 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, II & III of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000364/2025-2026 | 1524/PD | 19/08/2025 | 120 | MAHATO CONSTRUCTION | 49.86 | 0 | 0
1917 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-II of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000365/2025-2026 | 1525/PD | 19/08/2025 | 120 | DILIP MISHRA | 16.33 | 0 | 0
1918 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, & III of Manbazar-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000366/2025-2026 | 1526/PD | 19/08/2025 | 120 | SAZID HOSSEN ANSARI | 33.38 | 0 | 0
1919 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, III of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. (Group-B) | Assistant Engineer |  | ORD/000367/2025-2026 | 1527/PD | 19/08/2025 | 120 | BABA LOKNATH ENTERPRISE | 32.99 | 0 | 0
1920 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - XV & XVII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000399/2025-2026 | 1580/PD | 20/08/2025 | 120 | MAHATO CONSTRUCTION | 28.7 | 0 | 0
1921 | Purulia Division | Purulia Sadar Sub-Division | Sinking of 1(One) no 200 mm dia DTH rigbored tubewell at OHR Sites of Zone - II ( Fusrabad) of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000438/2024-2025 | 1501/PD | 27/08/2024 | 30 | BISWAJIT MAJI | 5.49 | 0 | 100
1922 | Purulia Division | Purulia Sadar Sub-Division | Sinking of 1(One) nos tubewell at OHR Site of Zone - V of Raghunathpur-II Block under Northen Sector Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000462/2024-2025 | 1521/PD | 27/08/2024 | 30 | CHAIL CONSTRUCTION | 5.08 | 0 | 100
1923 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000480/2025-2026 | 1522/PD | 19/08/2025 | 120 | PRATIMA CONSTRUCTION | 50.06 | 0 | 0
1924 | Purulia Division | Purulia Sadar Sub-Division | Repairing and Renovation of Boundary wall including other allied works at Kanchanpur boosting site in connection with Jal Jeevan Mission (JJM) at Kudagara under Purulia W/S Scheme (Northern Sector) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000500/2023-2024 | 1332/PD | 08/09/2023 | 30 | MITRA CONSTRUCTION | 2.56 | 0 | 100
1925 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Manbazar-I (Zone - II & IV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000560/2025-2026 | 1078/PD | 17/06/2025 | 120 | M/S MECHANICAL AND CIVIL | 28.8 | 0 | 0
1926 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Puncha (Zone - II) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000561/2025-2026 | 1068/PD | 17/06/2025 | 120 | M/S SAMARESH SARKAR | 13.81 | 0 | 0
1927 | Purulia Division | Purulia Sadar Sub-Division | Construction of Scada Room and Chlorine Room at Jhalda-II (Zone - VIII & XIV ) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000571/2025-2026 | 1070/PD | 17/06/2025 | 120 | BIJOY KUMAR PATRA | 28.81 | 0 | 0
1928 | Purulia Division | Purulia Sadar Sub-Division | Hiring of Ambassador Car / Bolero for JJM related works for the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. (w.e.f. 01.09.2024 to 31.08.2025) | Assistant Engineer |  | ORD/000646/2024-2025 | 1653/PD | 30/08/2024 | 365 | CHANDRA SHEKHAR KUNDU | 1.76 | 0 | 0
1929 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000653/2024-2025 | 1862/PD | 30/09/2024 | 425 | BANERJEE CONSTRUCTION | 14.37 | 0 | 20
1930 | Purulia Division | Purulia Sadar Sub-Division | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) w.e.f. 13/09/2024 to 14/03/2025 | Assistant Engineer |  | ORD/000765/2024-2025 | 431/PSD | 11/09/2024 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0
1931 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 13/09/2024 to 14/03/2025) | Assistant Engineer |  | ORD/000766/2024-2025 | 432/PSD | 11/09/2024 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0
1932 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) for Zone-III & IV of Raghunathpur - II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-21) | Assistant Engineer |  | ORD/000803/2023-2024 | 1428/PD | 29/09/2023 | 812 | NIBHAS SINHA | 863.77 | 0 | 12
1933 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied Works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone- V of Raghunathpur - II block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-22) | Assistant Engineer |  | ORD/000804/2023-2024 | 1422/PD | 29/09/2023 | 915 | RABIN CHANDRA CHAIL | 207.13 | 0 | 20
1934 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied Works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone- I of Raghunathpur - II block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-19) | Assistant Engineer |  | ORD/000805/2023-2024 | 1424/PD | 29/09/2023 | 1095 | TUMPA GORAIN | 117.63 | 0 | 15
1935 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six month for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - VII & VIII) under Purulia Divn. PHE Dte. (SL-3) | Assistant Engineer |  | ORD/000809/2023-2024 | 1416/PD | 29/09/2023 | 636 | JAYANTA KUMAR MONDAL | 888.48 | 0 | 38
1936 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six (36) month Zone - X , XI & XIV of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | Assistant Engineer |  | ORD/000832/2023-2024 | 1415/PD | 29/09/2023 | 360 | LUKE ENGICON | 1374.87 | 0 | 30
1937 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Manbazar-I Block(Zone - I to IV) under Purulia Divn. PHE Dte. (SL-4) | Assistant Engineer |  | ORD/000833/2023-2024 | 1417/PD | 29/09/2023 | 780 | SHYAM KUMAR | 1479.87 | 0 | 50
1938 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - I , II & III) under Purulia Divn. PHE Dte. (SL-1) | Assistant Engineer |  | ORD/000834/2023-2024 | 1432/PD | 29/09/2023 | 641 | HANNAN BUILDERS PRIVATE LIMITED | 1240.82 | 0 | 30
1939 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month for Zone-XI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-8) | Assistant Engineer |  | ORD/000838/2023-2024 | 1426/PD | 29/09/2023 | 703 | SUJIT SAHANA | 361.35 | 0 | 15
1940 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Mahalitora Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000852/2023-2024 | 1491/PD | 12/10/2023 | 45 | SOUVIK MANDAL | 33.54 | 0 | 0
1941 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Hulka & kultanr Alias nadiyara under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000853/2023-2024 | 1492/PD | 12/10/2023 | 452 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 41.55 | 0 | 0
1942 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-V) for Hulka & Kultanr alias nadiyara Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/000854/2023-2024 | 1493/PD | 12/10/2023 | 45 | KABERI DUTTA | 11.47 | 0 | 0
1943 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)with allied works for Purulia Water Supply Scheme.(Location:-Block-Purulia-1 , Zone-VIII) for Northern Zone | Assistant Engineer |  | ORD/000855/2023-2024 | 1494/PD | 12/10/2023 | 539 | KM ENTERPRISES | 81.93 | 0 | 45
1944 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Amandih mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000856/2023-2024 | 1495/PD | 12/10/2023 | 45 | SUSANTA KR DUTTA | 60.42 | 0 | 0
1945 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Dhadhka mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000858/2023-2024 | 1497/PD | 12/10/2023 | 45 | KOUSHIK CHATTERJEE | 22.91 | 0 | 0
1946 | Purulia Division | Purulia Sadar Sub-Division | Construction Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied work & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 10) | Assistant Engineer |  | ORD/000868/2023-2024 | 1433/PD | 29/09/2023 | 1002 | MADHU SUDAN RAKSHIT | 296.95 | 0 | 25
1947 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)Including soil testing with other allied works for Zone-III of Santuri Block under Purulia Piped Water Supply Scheme(Northern) under Puru;ia Divn. PHE Dte. | Assistant Engineer |  | ORD/000869/2023-2024 | 1282/PD | 31/08/2023 | 815 | CHATTERJEE CONSTRUCTION | 81.76 | 0 | 10
1948 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-VIII) for Dimdiha Mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/000875/2023-2024 | 1526/PD | 16/10/2023 | 45 | BHAGABANDAS KUMAR | 31.72 | 0 | 0
1949 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Dimdiha Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000876/2023-2024 | 1525/PD | 16/10/2023 | 808 | GOUTAM CHAKRABORTY | 112.33 | 0 | 0
1950 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-IV of Chakra, Kultanr alias Nadiyara,Palkiri,Baroyadi of Purulia-I block under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000877/2023-2024 | 1527/PD | 16/10/2023 | 867 | M/S SAWDESH ENTERPRISE | 63.56 | 0 | 60
1951 | Purulia Division | Purulia Sadar Sub-Division | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-IV) for Chakra, Kultanr alias Nadiyara Under Purulia Divn. PHE DTE. | Assistant Engineer |  | ORD/000878/2023-2024 | 1528/PD | 16/10/2023 | 45 | SOUHARDYA BUSINESS LINE | 34.94 | 0 | 0
1952 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A, Mouza - Marbedya, Ghoramurga] | Assistant Engineer |  | ORD/000885/2023-2024 | 1535/PD | 16/10/2023 | 868 | AMIT PATHAK | 64.16 | 0 | 55
1953 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Kalipahari, Hansdima] | Assistant Engineer |  | ORD/000886/2023-2024 | 1536/PD | 16/10/2023 | 533 | KHITISH CHANDRA PATHAK | 77.29 | 0 | 60
1954 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Chhota Pathar, Kashikunri, Baghadabar & Kushunda] | Assistant Engineer |  | ORD/000887/2023-2024 | 1537/PD | 16/10/2023 | 60 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 84.9 | 0 | 60
1955 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - E, Mouza - Nimtikuri & Manjuri] | Assistant Engineer |  | ORD/000888/2023-2024 | 1539/PD | 16/10/2023 | 747 | MAA TARA CONSTRUCTION | 47.96 | 0 | 0
1956 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Jibanpur Alias Ramjibanpur, Barhanti & Talberya] | Assistant Engineer |  | ORD/000889/2023-2024 | 1540/PD | 16/10/2023 | 443 | M/S SB CONSTRUCTION | 65.75 | 0 | 55
1957 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Pirargoriya & Lediam] | Assistant Engineer |  | ORD/000891/2023-2024 | 1538/PD | 16/10/2023 | 60 | GHOSH AND ROY ENTERPRISE | 52.38 | 0 | 55
1958 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Raghunathpur - I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-14) | Assistant Engineer |  | ORD/000893/2023-2024 | 1559/PD | 18/10/2023 | 1076 | ASHOKE KUMAR CHATTERJEE | 413.23 | 0 | 5
1959 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-7) | Assistant Engineer |  | ORD/000894/2023-2024 | 1557/PD | 18/10/2023 | 541 | RANJIB GHATAK | 277.73 | 0 | 75
1960 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-IV of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-1) | Assistant Engineer |  | ORD/000898/2023-2024 | 1564/PD | 26/10/2023 | 270 | PARTHA PRATIM CHHATAIT | 393.93 | 0 | 0
1961 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-15) | Assistant Engineer |  | ORD/000899/2023-2024 | 1567/PD | 26/10/2023 | 888 | KM ENTERPRISES | 243.33 | 0 | 65
1962 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-I of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-13) | Assistant Engineer |  | ORD/000900/2023-2024 | 1566/PD | 26/10/2023 | 270 | KOUSHIK CHATTERJEE | 144.2 | 0 | 0
1963 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) AT Zone-VIII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-12) | Assistant Engineer |  | ORD/000902/2023-2024 | 1565/PD | 26/10/2023 | 540 | BBC ENTERPRISE | 535.9 | 0 | 45
1964 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block (zone-IV & V) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 11) | Assistant Engineer |  | ORD/000903/2023-2024 | 1573/PD | 30/10/2023 | 270 | JAYANTA KUMAR MONDAL | 1398.36 | 0 | 42
1965 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 500 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-VI of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-12) | Assistant Engineer |  | ORD/000906/2023-2024 | 1575/PD | 30/10/2023 | 270 | SADHAN GORAIN | 704.66 | 0 | 0
1966 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-13) | Assistant Engineer |  | ORD/000907/2023-2024 | 1576/PD | 30/10/2023 | 270 | SADHAN GORAIN | 692.19 | 0 | 25
1967 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XVI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-6) | Assistant Engineer |  | ORD/000908/2023-2024 | 1577/PD | 30/10/2023 | 884 | PREMNATH MITRA | 498.9 | 0 | 0
1968 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VI & VII of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.7) | Assistant Engineer |  | ORD/000910/2023-2024 | 1583/PD | 30/10/2023 | 1083 | DEBAKI RANJAN SARKAR | 973.78 | 0 | 32
1969 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III & IV of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.2) | Assistant Engineer |  | ORD/000911/2023-2024 | 1582/PD | 30/10/2023 | 1083 | DEBAKI RANJAN SARKAR | 787.54 | 0 | 10
1970 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-IX of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-4) | Assistant Engineer |  | ORD/000912/2023-2024 | 1581/PD | 30/10/2023 | 601 | J.S. CONSTRUCTION | 458.06 | 0 | 20
1971 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 400 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-II of Raghunathpur-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 20) | Assistant Engineer |  | ORD/000917/2023-2024 | 1599/PD | 31/10/2023 | 1082 | DEBAKI RANJAN SARKAR | 404.59 | 0 | 0
1972 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-III of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-7) | Assistant Engineer |  | ORD/000918/2023-2024 | 1592/PD | 31/10/2023 | 640 | SWAPAN MANDAL | 295.01 | 0 | 70
1973 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-I of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 1) | Assistant Engineer |  | ORD/000920/2023-2024 | 1593/PD | 31/10/2023 | 942 | SANTANU BANERJEE | 574.33 | 0 | 70
1974 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII & VIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL No.5) | Assistant Engineer |  | ORD/000921/2023-2024 | 1591/PD | 31/10/2023 | 944 | SANTANU BANERJEE | 769.41 | 0 | 40
1975 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Zone- XIV & XV of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL-1) | Assistant Engineer |  | ORD/000923/2023-2024 | 1598/PD | 31/10/2023 | 793 | MRITYUNJOY MUKHERJEE & CO | 831.47 | 0 | 1
1976 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for different Zones in Joypur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.1) | Assistant Engineer |  | ORD/000926/2023-2024 | 1594/PD | 31/10/2023 | 725 | PRITI EPC PRIVATE LIMITED | 5517.66 | 0 | 10
1977 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I block(Zone-II) for Satar Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/000990/2023-2024 | 1632/PD | 08/11/2023 | 749 | HIRAK KUMAR SAO | 70.4 | 0 | 60
1978 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Nadiha (80%)] | Assistant Engineer |  | ORD/000992/2023-2024 | 1633/PD | 08/11/2023 | 60 | MOLLA ENTERPRISE | 67.12 | 0 | 60
1979 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Narayanpur & Nadiha (20%) ] | Assistant Engineer |  | ORD/000994/2023-2024 | 1634/PD | 08/11/2023 | 45 | BABA LOKNATH ENTERPRISE | 59.46 | 0 | 60
1980 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Ranipur Colliery & Deiliya] | Assistant Engineer |  | ORD/000996/2023-2024 | 1635/PD | 08/11/2023 | 30 | M/S SAYAK BHATTACHARYA | 89.86 | 0 | 100
1981 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Khojda Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/000998/2023-2024 | 1636/PD | 08/11/2023 | 45 | SOUVIK MANDAL | 51.27 | 0 | 0
1982 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Kanali Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001001/2023-2024 | 1637/PD | 08/11/2023 | 45 | MANATOSH SINGH | 50.19 | 0 | 0
1983 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Gondhudi Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001002/2023-2024 | 1639/PD | 08/11/2023 | 785 | M/S CHAKRABORTY CONSTRUCTION | 49.52 | 0 | 0
1984 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Bamra Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001005/2023-2024 | 1640/PD | 08/11/2023 | 60 | CHATTERJEE CONSTRUCTION | 15.46 | 0 | 0
1985 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Simulia Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001006/2023-2024 | 1641/PD | 08/11/2023 | 60 | RAJAT KARMAKAR | 43.25 | 0 | 0
1986 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kalipur Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001008/2023-2024 | 1642/PD | 08/11/2023 | 60 | DEBANJAN SEAL | 22.77 | 0 | 0
1987 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kotloi Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001013/2023-2024 | 1644/PD | 08/11/2023 | 425 | SUBODH PRAMANIK | 40.95 | 0 | 0
1988 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Chakda Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001015/2023-2024 | 1643/PD | 08/11/2023 | 60 | MS D.PALIT AND CO. | 88.91 | 0 | 0
1989 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Belguma mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001017/2023-2024 | 1645/PD | 08/11/2023 | 60 | S.R ENTERPRISE | 58.5 | 0 | 0
1990 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Raibanbh Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001018/2023-2024 | 1646/PD | 08/11/2023 | 60 | ROY CONSTRUCTION | 19.01 | 0 | 0
1991 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I Block (Zone-VI) For Buridi Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001075/2023-2024 | 1638/PD | 08/11/2023 | 45 | TAPAS KUMBHAKAR | 46.5 | 0 | 0
1992 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001102/2024-2025 | 2192/PD | 13/12/2024 | 384 | BISWAJIT MAJI | 22.64 | 0 | 0
1993 | Purulia Division | Purulia Sadar Sub-Division | Laying of distribution pipe line and other allied work for Zone-III of Santuri Block under Surface water based water supply scheme for Purulia district (Northern Sector) Under Purulia Division PHE. DTE. Part-B Mouza- Brindabanpur | Assistant Engineer |  | ORD/001135/2024-2025 | 2015/PD | 22/11/2024 | 60 | M/S MONDAL ENTERPRISE | 17.47 | 0 | 0
1994 | Purulia Division | Purulia Sadar Sub-Division | Laying of distributuion pipe line and other allied work for Zone-I of Santuri Block under Surface Water Based Water Supply Scheme for Purulia District (Northern Sector) under Purulia Division PHE. DTE. Part-C (Mouza- Pachandapur, Beliapur & Kalikapur ) | Assistant Engineer |  | ORD/001136/2024-2025 | 2014/PD | 22/11/2024 | 30 | RANJIB GHATAK | 3.49 | 0 | 100
1995 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte(w.e.f.01.09.2024 to 28.02.2025). | Assistant Engineer |  | ORD/001137/2024-2025 | 397A/PSD | 29/08/2024 | 183 | BOSE CONSTRUCTION | 0.88 | 0 | 100
1996 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-III) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001144/2024-2025 | 2298/PD | 31/12/2024 | 60 | PRATIK SAHA | 34.03 | 0 | 0
1997 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IX) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001150/2024-2025 | 2301/PD | 31/12/2024 | 60 | S S ENTERPRISE | 34.25 | 0 | 0
1998 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001154/2024-2025 | 2306/PD | 31/12/2024 | 60 | MAHATO CONSTRUCTION | 29.14 | 0 | 0
1999 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001158/2024-2025 | 2310/PD | 31/12/2024 | 335 | VIVEKANANDA CONSTRUCTION | 33.11 | 0 | 0
2000 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001160/2024-2025 | 2312/PD | 31/12/2024 | 60 | SUBHAS CHANDRA MAHATO | 31.96 | 0 | 0
2001 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001168/2024-2025 | 2322/PD | 31/12/2024 | 60 | AMIT CHOURASIA | 31.62 | 0 | 0
2002 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001169/2024-2025 | 2323/PD | 31/12/2024 | 60 | SEKH ABBAS | 34.09 | 0 | 0
2003 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-X) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001170/2024-2025 | 2324/PD | 31/12/2024 | 60 | M/S CONTRACTORS SYNDICATE | 34.06 | 0 | 0
2004 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001178/2024-2025 | 2332/PD | 31/12/2024 | 60 | UTTAM KUMAR PARAMANIK | 29.89 | 0 | 0
2005 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001179/2024-2025 | 2333/PD | 31/12/2024 | 60 | SUMIT KUMAR MITRA | 32.38 | 0 | 0
2006 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001180/2024-2025 | 2334/PD | 31/12/2024 | 366 | BHAGABAN DAS KUMAR | 30.63 | 0 | 90
2007 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001184/2024-2025 | 2339/PD | 31/12/2024 | 60 | JULI ENTERPRISE | 30.06 | 0 | 0
2008 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001185/2024-2025 | 2340/PD | 31/12/2024 | 60 | DEBANJAN SEAL | 29.19 | 0 | 0
2009 | Purulia Division | Purulia Sadar Sub-Division | Extension part of Construction of Boundary wall and earth filling in low land by carried earth at Bhuiyadi OHR site (Zone-III) at Kashipur Block under surface water based piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 55 mtr.) | Assistant Engineer |  | ORD/001187/2024-2025 | 2342/PD | 31/12/2024 | 60 | M/S SAYAK BHATTACHARYA | 48.64 | 0 | 0
2010 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001189/2024-2025 | 85/PD | 16/01/2025 | 319 | M/S KHAN ENTERPRISE | 31.36 | 0 | 95
2011 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-IX)under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001192/2024-2025 | 2318/PD | 31/12/2024 | 478 | SAPAN KUMAR PARAMANIK | 34 | 0 | 0
2012 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at PURULIA-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001193/2024-2025 | 2313/PD | 31/12/2024 | 213 | TARA MAA SHAKTI CONSTRUCTION | 37.61 | 0 | 90
2013 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-II) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001195/2024-2025 | 2348/PD | 31/12/2024 | 420 | SANTOSH KUMAR | 29.24 | 0 | 60
2014 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block (Zone-II) For Tentlo Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001200/2024-2025 | 2011/PD | 21/11/2024 | 252 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 64.02 | 0 | 0
2015 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001205/2024-2025 | 2338/PD | 31/12/2024 | 420 | PAMPA DAS AND COMPANY | 30.46 | 0 | 0
2016 | Purulia Division | Purulia Sadar Sub-Division | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001208/2024-2025 | 2305/PD | 31/12/2024 | 60 | BISWAJIT SINGH | 29.87 | 0 | 0
2017 | Purulia Division | Purulia Sadar Sub-Division | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Baram under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | Assistant Engineer |  | ORD/001209/2024-2025 | 110/PD | 21/01/2025 | 90 | AKUL SUTRADHAR | 3.86 | 0 | 0
2018 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001276/2024-2025 | 337/PD | 11/03/2025 | 60 | SAZID HOSSEN ANSARI | 24.7 | 0 | 0
2019 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001277/2024-2025 | 336/PD | 10/03/2025 | 60 | SAZID HOSSEN ANSARI | 24.78 | 0 | 0
2020 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line work for zone-l of Neturia Block at Mouza - Pochhara under Purulia water supply scheme (Northern Sector ) under Purulia Division Phe. Dte | Assistant Engineer |  | ORD/001299/2024-2025 | 439/PD | 24/03/2025 | 373 | BISWAJIT MAJI | 16 | 0 | 65
2021 | Purulia Division | Purulia Sadar Sub-Division | Left out HDPE pipe line and pushing of 600mm dia MS pre cast pipe and 100 mm dia GI water carrier pipe by hydraulic jacking method across Purulia Ranchi NH Road for laying distribution line in connection with Jal Jeevan Mission at for Zone-III of Purulia -I block for Belkuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001305/2024-2025 | 444/PD | 24/03/2025 | 283 | GOUTAM CHAKRABORTY | 64.98 | 0 | 75
2022 | Purulia Division | Purulia Sadar Sub-Division | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector ), Kashipur Block Zone -I within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001320/2024-2025 | 458/PD | 24/03/2025 | 252 | PRINCE INDUSTRIES ( INDIA) | 70.43 | 0 | 50
2023 | Purulia Division | Purulia Sadar Sub-Division | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for the Assistant Engineer to look after the ongoing works under RWS Purulia Sub-Division PHE Dte (For12 months ) (w.e.f. 01/09/2022 to 31/08/2023). | Assistant Engineer |  | ORD/001328/2022-2023 | 415/A/PR | 30/08/2022 | 365 | ANUP KUMAR SAHA | 1.76 | 0 | 100
2024 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte (w.e.f.01.03.2025 to 31.08.2025) | Assistant Engineer |  | ORD/001383/2024-2025 | 96/PSD | 27/02/2025 | 181 | BOSE CONSTRUCTION | 0.88 | 0 | 0
2025 | Purulia Division | Purulia Sadar Sub-Division | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) w.e.f. 15/03/2025 to 13/09/2025 | Assistant Engineer |  | ORD/001384/2024-2025 | 131/PSSD | 13/03/2025 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0
2026 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 15/03/2025 to 13/09/2025) | Assistant Engineer |  | ORD/001385/2024-2025 | 131A/PSSD | 13/03/2025 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0
2027 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone- I to XVIII of Para Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte. | Assistant Engineer |  | ORD/001599/2023-2024 | 1821/PD | 12/12/2023 | 720 | M/S ANAND SINGH | 7701.69 | 0 | 40
2028 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- IX to XV of Purulia-II Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | Assistant Engineer |  | ORD/001600/2023-2024 | 41/PD | 08/01/2024 | 1080 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3673.24 | 0 | 15
2029 | Purulia Division | Purulia Sadar Sub-Division | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- I,II,III,IV,V,VI,VII,VIII,IX,XII,XIII of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | Assistant Engineer |  | ORD/001606/2023-2024 | 1761/PD | 07/12/2023 | 1082 | S & P ENTERPRISE | 5304.39 | 0 | 55
2030 | Purulia Division | Purulia Sadar Sub-Division | Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte (Northen Zone) | Assistant Engineer |  | ORD/001657/2023-2024 | 4769/PSD | 21/08/2023 | 184 | ANUP KUMAR SAHA | 0.9 | 0 | 0
2031 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001658/2023-2024 | 4783/PSD | 24/08/2023 | 184 | BOSE CONSTRUCTION | 0.88 | 0 | 0
2032 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300m) | Assistant Engineer |  | ORD/001827/2023-2024 | 65/PD | 10/01/2024 | 360 | WATER TECH | 40.82 | 0 | 100
2033 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division,P.H.E. Dte.(Total Length of Boundary Wall: 280m) | Assistant Engineer |  | ORD/001828/2023-2024 | 66/PD | 10/01/2024 | 268 | M/S KALYANI ENTERPRISE | 38.8 | 0 | 100
2034 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XIII & XIV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 260m) | Assistant Engineer |  | ORD/001829/2023-2024 | 67/PD | 10/01/2024 | 357 | S.S CONSTRUCTION | 36.76 | 0 | 65
2035 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- I & II of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | Assistant Engineer |  | ORD/001830/2023-2024 | 68/PD | 10/01/2024 | 60 | AMIT PATHAK | 39.72 | 0 | 65
2036 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- III & IV of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300 m) | Assistant Engineer |  | ORD/001831/2023-2024 | 69/PD | 10/01/2024 | 416 | CHANCHAL MISHRA | 40.76 | 0 | 95
2037 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- V & VI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) | Assistant Engineer |  | ORD/001832/2023-2024 | 70/PD | 10/01/2024 | 60 | HUSSAIN CONSTRUCTION | 38.75 | 0 | 0
2038 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | Assistant Engineer |  | ORD/001833/2023-2024 | 71/PD | 10/01/2024 | 444 | SUJIT CHAKRABORTY | 39.58 | 0 | 100
2039 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) | Assistant Engineer |  | ORD/001834/2023-2024 | 72/PD | 10/01/2024 | 60 | SAMAN KUMAR MAHATO | 38.79 | 0 | 100
2040 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - VII & VIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer |  | ORD/001848/2023-2024 | 80/PD | 15/01/2024 | 60 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 38.78 | 0 | 50
2041 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XV & XVI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 290 m) | Assistant Engineer |  | ORD/001849/2023-2024 | 81/PD | 15/01/2024 | 60 | SUMIT KUMAR CHAKRABORTY | 39.78 | 0 | 50
2042 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XVII & XVIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer |  | ORD/001852/2023-2024 | 82/PD | 15/01/2024 | 60 | SANJAY KUMAR NARSARIA | 38.72 | 0 | 100
2043 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- PurbaBero, JL No-195, Plot No-1839) of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 330 mtr.) | Assistant Engineer |  | ORD/001853/2023-2024 | 83/PD | 15/01/2024 | 60 | SABYASACHI MISHRA | 38.55 | 0 | 0
2044 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat BPS Site (Mouza- Tara, JL No-182, Plot No-1587) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 400 mtr.) | Assistant Engineer |  | ORD/001854/2023-2024 | 84/PD | 15/01/2024 | 60 | NANIGOPAL DEY | 45.63 | 0 | 10
2045 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- GamarKunri, JL No-167, Plot No-756) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 380 mtr.) | Assistant Engineer |  | ORD/001855/2023-2024 | 85/PD | 15/01/2024 | 807 | CHAIL CONSTRUCTION | 43.63 | 0 | 0
2046 | Purulia Division | Purulia Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) with allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. | Assistant Engineer |  | ORD/001865/2023-2024 | 91/PD | 15/01/2024 | 272 | SIMA ENTERPRISE | 70.28 | 0 | 85
2047 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including FHTC and other allied work for Zone-I of Neturia Block at Mouza-Pochhara under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHEDte.(Part-B) | Assistant Engineer |  | ORD/001867/2023-2024 | 92/PD | 15/01/2024 | 807 | BISWAJIT MAJI | 22.45 | 0 | 60
2048 | Purulia Division | Purulia Sadar Sub-Division | Laying distribution system including providing FHTC(Lalpur Paharpur , Domsota) and other allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Part-A) | Assistant Engineer |  | ORD/001874/2023-2024 | 99/PD | 15/01/2024 | 60 | M/S SAYAK BHATTACHARYA | 51.94 | 0 | 100
2049 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line including other allied work for Zone-I of Neturia Block under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte.(Part-D) | Assistant Engineer |  | ORD/001879/2023-2024 | 94/PD | 15/01/2024 | 60 | KANJILAL AND CO. | 12.5 | 0 | 0
2050 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - I & II of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer |  | ORD/002299/2023-2024 | 192/PD | 02/02/2024 | 60 | TOTAL INFRA | 38.57 | 0 | 100
2051 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - III & IV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 260 m) | Assistant Engineer |  | ORD/002303/2023-2024 | 193/PD | 02/02/2024 | 420 | JULI ENTERPRISE | 36.69 | 0 | 100
2052 | Purulia Division | Purulia Sadar Sub-Division | Laying Distribution Pipe line and other allied work for Zone-VII of Purulia-I block for Golbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/002901/2023-2024 | 239/PD | 15/02/2024 | 60 | MARAUTI CONSTRUCTION AND CO | 83.25 | 0 | 0
2053 | Purulia Division | Purulia Sadar Sub-Division | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01/10/2023 to 31/03/2024) | Assistant Engineer |  | ORD/003320/2023-2024 | 4857/PSD | 29/09/2023 | 183 | KOUSHIK CHATTERJEE | 0.9 | 0 | 0
2054 | Purulia Division | Purulia Sadar Sub-Division | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/003465/2023-2024 | 334/PD | 01/03/2024 | 60 | VIVEKANANDA CONSTRUCTION | 22.85 | 0 | 100
2055 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(w.e.f. 01/03/2024 to 30/08/2024)=184 days | Assistant Engineer |  | ORD/003682/2023-2024 | 102/PSD | 27/02/2024 | 184 | ANUP KUMAR SAHA | 0.9 | 0 | 0
2056 | Purulia Division | Purulia Sadar Sub-Division | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Air conditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-A) | Assistant Engineer |  | ORD/004286/2023-2024 | 213/A/PR | 27/03/2024 | 180 | BOSE CONSTRUCTION | 0.88 | 0 | 0
2057 | Purulia Division | Purulia Sadar Sub-Division | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte.(01/03/2024 to 31/08/2024) | Assistant Engineer |  | ORD/004307/2023-2024 | 101/PSD | 27/02/2024 | 182 | BOSE CONSTRUCTION | 0.88 | 0 | 0
2058 | Purulia Division | Purulia Sadar Sub-Division | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | Assistant Engineer |  | ORD/004785/2023-2024 | 130A/PSD | 14/03/2024 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0
2059 | Purulia Division | Purulia Sadar Sub-Division | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | Assistant Engineer |  | ORD/004806/2023-2024 | 130B/PSD | 14/03/2024 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0
2060 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000038/2024-2025 | 2255/PD | 19/12/2024 | 0 | Resource Division | 157.32 | 0 | 0
2061 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Office Cum Godown at Ist Floor of Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000002/2022-2023 | 538/PD | 01/04/2022 | 100 | BOSE CONSTRUCTION | 20.61 | 7.51 | 98
2062 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of boundary wall for OHR campus at Bhuinghora mouza of Marbel Lake W/S Scheme at Ajodhya Hill under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000121/2020-2021 | 1280/PD | 07/12/2020 | 30 | SHAYED NADEEM AHAMAD | 9.05 | 16.64 | 0
2063 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of main drain at Baghmundi WTP Site under Piped Water Supply Scheme from Marble Lake under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000124/2024-2025 | 892/PD | 07/05/2024 | 45 | ROY CONSTRUCTION | 2.32 | 0 | 100
2064 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system and Construction of R.C.C. Elevated Reservoir, Capcaity 100 cum (Torch Type), Staging height 20 metre at Bhuinghora mouza for Marble Lake & its adjoing area W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division,P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000160/2020-2021 | 1416/PD | 29/12/2020 | 12 | ANUP KUMAR SAHA | 178.29 | 145.63 | 0
2065 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Allied Work of Construction of roof, slab, plaster etc. of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000185/2023-2024 | 4675/PSD | 27/07/2023 | 15 | BOSE CONSTRUCTION | 0.88 | 0 | 100
2066 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Parapet Wall of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000186/2023-2024 | 4676/PSD | 27/07/2023 | 15 | BOSE CONSTRUCTION | 0.95 | 0 | 100
2067 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC Back Wash Reservoir of capacity 57.00 Cum at AT WTP Campus site of Marbel Lake W/S Scheme at Ajodhya Hill W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000199/2021-2022 | 640/PSD | 21/09/2021 | 45 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 4.82 | 4.48 | 85
2068 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000363/2020-2021 | 353/PD | 25/02/2021 | 270 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 205.74 | 170.59 | 100
2069 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying HDPE distribution pipeline to cover the left out habitation of Ajodhya, Bagandih & Chatni mouza at Ajodhya Under Marble Lake W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000448/2024-2025 | 1510/PD | 27/08/2024 | 45 | TUMPA GORAIN | 23.18 | 0 | 100
2070 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of shed and other works at Manbhum Paridarshan Abas Campus under Marble Lake W/S Scheme Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000478/2024-2025 | 1499/PD | 27/08/2024 | 45 | MAHARSHI BANERJEE | 5.61 | 0 | 100
2071 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Loop Line for the distribution System at different command area of Patuara, Ramjibanpur, Bhomorbera,Lawadih etc of Satra under Marble Lake W/S Scheme Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000479/2024-2025 | 1500/PD | 27/08/2024 | 735 | SUBODH PRAMANIK | 27.42 | 0 | 80
2072 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Allied works for construction of office cum Godown at Ajodhya under Marble Lake W/S Scheme Purulia Division, PHE Dte. (JJM) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000480/2024-2025 | 1516/PD | 27/08/2024 | 45 | BOSE CONSTRUCTION | 11.59 | 0 | 100
2073 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Fencing on The Entry of Marble Lake under Marble Lake W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000610/2022-2023 | 507/PSD | 12/08/2022 | 25 | ANUP KUMAR SAHA | 1 | 0.94 | 100
2074 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Extension Of Distribution Line Near marble Lake road to Dulgubera and Laying of GI Pipe over Hatinada Khal Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000612/2022-2023 | 509/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.75 | 4.26 | 100
2075 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying Remaining Portion of distribution pipe Line due to shifting of OHR Location Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000617/2022-2023 | 514/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.62 | 4.4 | 100
2076 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-1) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000786/2022-2023 | 1633/PD | 28/10/2022 | 30 | ANUP KUMAR SAHA | 4.25 | 2.59 | 75
2077 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-2) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000787/2022-2023 | 1634/PD | 28/10/2022 | 30 | ANUP KUMAR SAHA | 4.25 | 4.05 | 100
2078 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.05.23 to 28.08.23] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000807/2023-2024 | 678/PD | 17/05/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 100
2079 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 29.08.23 to 26.11.23] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000808/2023-2024 | 1169/PD | 28/08/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 100
2080 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.02.23 to 20.05.23] | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001293/2022-2023 | 245/PD | 20/02/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 100
2081 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000006/2020-2021 | 47/PD | 15/01/2021 | 0 | Resource Division | 51.57 | 0 | 0
2082 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sail investigation work for identification of sub sail profile for proposed intake WTP & OHR site Marbel Lake its adjoining mouzas area w/s scheme (Tender No. 359/PD of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000127/2021-2022 | 58/844322 | 08/06/2021 | 0 | MOYTEC | 1.35 | 0 | 0
2083 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply delivery & installation of submersible pumping machinery for Marble lake W/S scheme of Baghmundi block (Tender No- 372/2021-22 of EE/PMD) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000153/2022-2023 | BP-2022-23-23 | 07/04/2022 | 0 | COMBINE ENTERPRISES | 1.82 | 0 | 0
2084 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty, supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No-42/SE/PMU of 20-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000183/2022-2023 | BP-2022-23-62 | 24/05/2022 | 0 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.1 | 0 | 0
2085 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No.42/SE/PMU of 2020-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001017/2021-2022 | BP-2021-22-253 | 25/02/2022 | 0 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 58.72 | 0 | 0
2086 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system & construction of RCC elevated reservoir capacity 100 cum (Torch type) staging height 20 metre at Bhuinghora mouza for marble Lake & adjoining area W/S Scheme of Purulia Sadar Sub- Division (Tender No- 10/2020-21 of SE/PMU/WBPWSP) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001191/2021-2022 | BP-2021-22-324 | 22/03/2022 | 0 | ANUP KUMAR SAHA | 89.2 | 0 | 0
2087 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of electro mechanical equipments submersible pump motor sets of Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi under Purulia Mechanical Division PHE Dte. Dist : Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000173/2021-2022 | 471/PMD | 28/07/2021 | 150 | COMBINE ENTERPRISES | 43.7 | 5.09 | 100
2088 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Voltage stabilizer ,valves, external illumination arrangement with allied works at Marble lake PWSS Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000467/2022-2023 | 307/PMD | 16/03/2023 | 30 | COMBINE ENTERPRISES | 13.17 | 0 | 60
2089 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of Pandel & other Miscellaneous works for infield training at Pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000567/2023-2024 | 23/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.54 | 0 | 100
2090 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of refreshment for infield training of pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000568/2023-2024 | 24/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.43 | 0 | 100
2091 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of PLC panel, Level transmitter with other allied work at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000645/2024-2025 | 1577/PMD | 14/11/2024 | 90 | SUBRATA DUTTA | 14.57 | 0 | 0
2092 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY AND INSTALLATION OF ELECTRO MECHANICAL EQUIPMENTS SUBMERSIBLE PUMP MOTOR SETS FOR RAW WATER PUMP HOUSE , CENTRIFUGAL PUMP MOTOR SETS FOR CLEAR WATER PUMP HOUSE AT MARBLE LAKE PIPED WATER SUPPLY SCHEME (TR.NO 179 OF 21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000562/2021-2022 | C022228319640 | 09/02/2022 | 0 | COMBINE ENTERPRISE | 37.42 | 0 | 0
2093 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Bill payment for TDS Certificate 26Q for the Q.E June,2023 to September,2023. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00019/2024-2025 | BP-2024-25-18 | 22/04/2024 | 0 | NIGAM CONSULTANCY SERVICE | 0.35 | 0 | 0
2094 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railways Miscellaneous collection | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01372/2023-2024 | BP-2023-24-758 | 11/01/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 0.01 | 0 | 0
2095 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Xerox bill paid for Raghunathpur Sub Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01613/2023-2024 | BP-2023-24-797 | 06/02/2024 | 0 | DUTTA XEROX CENTRE | 0.06 | 0 | 0
2096 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Beldi Pump house(OHR Site and Riversite) and repairing of bounday wall under Purulia Sadar Sub Division under Purulia Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000063/2022-2023 | 168/PSD | 18/04/2022 | 30 | ASHOKE ADHIKARY | 4.83 | 4.67 | 100
2097 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000114/2020-2021 | 1241/PD | 01/12/2020 | 45 | SUSANTA KR DUTTA | 42.97 | 0 | 0
2098 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete at Gouradag Riversite for Beldi W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000451/2021-2022 | 90/PSD | 14/03/2022 | 45 | KANCHAN MAHATO | 4.53 | 2.98 | 85
2099 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection,surface drain etc.complete at Sirkabad Riversite for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte.(Under Beldi Water Supply Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003511/2023-2024 | 313/PD | 01/03/2024 | 212 | MAHATO CONSTRUCTION | 5.5 | 0 | 100
2100 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of WBSEDCL Room and Repairing of old Rising Main Pipeline for Augmentation of Sirkabad W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. (Under Beldi Water Supply Scheme) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003512/2023-2024 | 314/PD | 01/03/2024 | 243 | KABERI DUTTA | 2.53 | 0 | 100
2101 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Beldi Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2021-2022 | 165/PMD | 07/03/2022 | 30 | DEBJYOTI BASU | 20.5 | 20.19 | 100
2102 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, voltage stabilizer, Flowmeter with necessary substitutes and allied works at BELDI w/s scheme under PMD, PHE Dte. in the District of Purulia.. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000371/2022-2023 | 201/PMD | 28/02/2023 | 60 | TAPAN KUMAR DEY | 34.55 | 13.19 | 60
2103 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 30
2104 | Purulia Division | Purulia Sadar Sub-Division | Regarding laying of water supply pipe line along road side and road crossing on Boro-Jamtoria Road in respect of Augumentation of Manbazar-II water supply scheme JJM in District of Purulia. | Assistant Engineer |  | BILL/01013/2023-2024 | BP-2023-24-664 | 10/11/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 6.02 | 0 | 0
2105 | Purulia Division | Purulia Sadar Sub-Division | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | Assistant Engineer |  | ORD/000009/2023-2024 | 537/PD | 12/04/2023 | 45 | MOONLIGHT HOUSE | 29.2 | 0 | 100
2106 | Purulia Division | Purulia Sadar Sub-Division | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte - i)FromBasantapur mor to Jugiadih village ii) Panra Morto Uppar pannra & Choto Pannra),Olgara, Kumari,) | Assistant Engineer |  | ORD/000010/2023-2024 | 538/PD | 12/04/2023 | 45 | RAKSHIT ENTERPRISE | 25.94 | 15.82 | 100
2107 | Purulia Division | Purulia Sadar Sub-Division | Shifting and laying of HDPE distribution main pipeline from Burudi more to Dharampur village end due to widening of PWD road at Manbazar-2 block under Manbazar-II Water Supply Scheme Under Purulia Division ,PHE Dte | Assistant Engineer |  | ORD/000047/2023-2024 | 671/PD | 17/05/2023 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 41.18 | 9.95 | 100
2108 | Purulia Division | Purulia Sadar Sub-Division | Guarding arrangement through Registered firm organized by Ex-Military person for WTP site of surface water supply scheme for Manbazar-II Block (Part) under Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | Assistant Engineer |  | ORD/000503/2021-2022 | 531/2/PD | 30/03/2022 | 30 | FRONTLINE EX-SERVICEMEN BUREAU | 1.4 | 0 | 0
2109 | Purulia Division | Purulia Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | Assistant Engineer |  | ORD/000614/2022-2023 | 511/PSD | 12/08/2022 | 45 | SADHAN GORAIN | 2.43 | 0 | 100
2110 | Purulia Division | Purulia Sadar Sub-Division | Construction of RCC Clear Water Reservoir (CWR) of capacity 15m3 including ventury etc. complete at Eklabya Model School Campus, Susunia Manbazar II Block of Manbazar II Block(part) W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000785/2022-2023 | 1632/PD | 03/11/2022 | 100 | ROY CONSTRUCTION | 4.81 | 4.04 | 0
2111 | Purulia Division | Purulia Sadar Sub-Division | Laying of Dedicated distribution pipe line For Paisagora under command area Zone-II under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer |  | ORD/000872/2022-2023 | 1840/PD | 12/12/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 32.63 | 29.81 | 100
2112 | Purulia Division | Purulia Sadar Sub-Division | 1. Identification of parallel distribution pipeline & loop pipeline including preparation of drawing & other allied works to cater the water supply problem in household tap connections at manbazar-II block under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001087/2022-2023 | 355/PD | 14/03/2023 | 30 | M/S. DESTINY CONSTRUCTION | 9.54 | 9.23 | 25
2113 | Purulia Division | Purulia Sadar Sub-Division | Conducting reconnaissance of feasible check dam site fo empounding reservoir site over rivers, recommending pinpoint site, conducting contour, longitudinal and traverse level survey on waterways and ponds with all geo reference, submission of report to E-I-C for preparation hydro graphic survey map of intake site at mukutmanipur dam & contour map of proposed WTP site of southern sector at Manbazar - II Block under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001097/2022-2023 | 364/PD | 14/03/2023 | 30 | LEMNISCATE | 11.16 | 0 | 100
2114 | Purulia Division | Purulia Sadar Sub-Division | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(From Zone-II OHR to Dhabakata village,Jaragora village Via Boro Mor) | Assistant Engineer |  | ORD/001213/2022-2023 | 502/PD | 31/03/2023 | 45 | PRIYATOSH MUKHERJEE | 94.15 | 46.32 | 100
2115 | Purulia Division | Purulia Sadar Sub-Division | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(Part-II- FromZ-II OHR to Dangardi,Boro PS to Joypur-Chotokadam-Dhadangar Mudipara, Dharampur Namopara, Goialapara Via Rampu Mahato Para) | Assistant Engineer |  | ORD/001214/2022-2023 | 503/PD | 31/03/2023 | 45 | MS D.PALIT AND CO. | 85.65 | 49.58 | 100
2116 | Purulia Division | Purulia Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000001/2023-2024 | 528/PD | 11/04/2023 | 0 | Resource Division | 644.45 | 0 | 0
2117 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Conducting route survey & investigation of command area map along the road fixing up alignment including showing existing distribution and Rising Main net works,all structures and features at Barabazar Leftout portion under PMU, WBPWSP (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000008/2022-2023 | 1300/W-181/JICA/PMU/2013 | 12/07/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 0 | 100
2118 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -I, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000011/2023-2024 | 2386/W-181/JICA/PMU/2022 | 10/08/2023 | 184 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.42 | 0 | 0
2119 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -II, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000012/2023-2024 | 2387/W-181/JICA/PMU/2022 | 10/08/2023 | 532 | TAPAN KUMAR DEY | 26.44 | 0 | 84
2120 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -III, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000013/2023-2024 | 2388/W-181/JICA/PMU/2022 | 10/08/2023 | 530 | SUBRATA DUTTA | 26.46 | 0 | 0
2121 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -IV, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000014/2023-2024 | 2389/W-181/JICA/PMU/2022 | 10/08/2023 | 521 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT. LTD. | 26.46 | 0 | 0
2122 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -V, OHR Under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000015/2023-2024 | 2390/W-181/JICA/PMU/2022 | 10/08/2023 | 694 | M/S SAJAHAN CHOWDHURY | 26.44 | 0 | 0
2123 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VI, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000016/2023-2024 | 2391/W-181/JICA/PMU/2022 | 10/08/2023 | 360 | COMBINE ENTERPRISE | 26.46 | 0 | 0
2124 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 100 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-II water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000017/2023-2024 | 2347/W-181/JICA/PMU/2022 | 09/08/2023 | 990 | M/S S & P CONSTRUCTION | 218.93 | 0 | 82
2125 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Laying of Rising Main cum Transmission Main for The Piped Water Supply Scheme for Left-Out Mouzas of Barabazar Block, Dist. Purulia under West Bengal Project Management Unit, Purulia, PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000018/2023-2024 | 2348/W-181/JICA/PMU/2022 | 09/08/2023 | 1020 | M/S S & P CONSTRUCTION | 247.24 | 0 | 86
2126 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 150 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-IV water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000019/2023-2024 | 2349/W-181/JICA/PMU/2022 | 09/08/2023 | 1080 | PARTHA PRATIM CHHATAIT | 217.07 | 0 | 40
2127 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of 600 cum capacity CWR, 75 cum capacity CWR, 1 no of Sub-station Building, 2 nos of Pump Houses & Boundary Wall of CWRs of water supply scheme of left-out mouzas of Barabazr under West Bengal Project Management Unit, Purulia, PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000020/2023-2024 | 2350/W-181/JICA/PMU/2022 | 09/08/2023 | 900 | SAMAN KUMAR MAHATO | 184.49 | 0 | 40
2128 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000021/2023-2024 | 2392/W-181/JICA/PMU/2022 | 10/08/2023 | 1075 | ANUP KUMAR SAHA | 26.46 | 0 | 0
2129 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VIII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000022/2023-2024 | 2393/W-181/JICA/PMU/2022 | 10/08/2023 | 520 | TAPAN KUMAR DEY | 26.44 | 0 | 0
2130 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-I water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000023/2023-2024 | 2351/W-181/JICA/PMU/2022 | 09/08/2023 | 990 | SANTANU BANERJEE | 459.23 | 0 | 80
2131 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-V water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000024/2023-2024 | 2352/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | NIBHAS SINHA | 465.39 | 0 | 82
2132 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000025/2023-2024 | 2353/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | S.DUTTA | 464.97 | 0 | 50
2133 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Providing Mechanical / Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Substation, Gaseous Chlorination, illumination arrangement at Intermediate Booster Pumping Station - I of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000026/2023-2024 | 2394/W-181/JICA/PMU/2022 | 10/08/2023 | 1357 | EASTERN INDIA SALES & SERVICE | 334.6 | 0 | 0
2134 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Providing Mechanical/ Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Gaseous Chlorination, Illumination arrangement at Intermediate Booster Pumping Station - II of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000027/2023-2024 | 2401/W-181/JICA/PMU/2022 | 11/08/2023 | 537 | RABINDRA NATH KHAN | 102.5 | 0 | 40
2135 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-III water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000028/2023-2024 | 2405/W-181/JICA/PMU/2022 | 11/08/2023 | 810 | DEBAKI RANJAN SARKAR | 524.57 | 0 | 30
2136 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 400 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VIII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000029/2023-2024 | 2406/W-181/JICA/PMU/2022 | 11/08/2023 | 1080 | ANUP KUMAR SAHA | 658.94 | 0 | 75
2137 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VI water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000030/2023-2024 | 2354/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | PRINCE INDUSTRIES ( INDIA) | 429.21 | 0 | 75
2138 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Providing Yard Lighting and other related works at OHRs for Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000031/2023-2024 | 2402/W-181/JICA/PMU/2022 | 11/08/2023 | 915 | PROGRESSIVE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 30.85 | 0 | 0
2139 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Soil investigation for determining the safe bearing capacity and other relevant parameters of soil in 8 nos different OHR site & 2 nos CWR site of surface Water Based Piped water Supply Scheme for left out mouzas of Barabazar Block,Purulia under JICA Assisted WBPWSP(P), PHE DTE | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | ORD/000037/2023-2024 | 2523/W-181/JICA/PMU/2022 | 22/08/2023 | 116 | MABCO CONSULTANT | 7.24 | 0 | 100
2140 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Material Requisition To Resource Division | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | RTOR000001/2023-2024 | 2068/W-34/JICA/PMU/2013 | 24/07/2023 | 0 | Resource Division | 2368.36 | 0 | 0
2141 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Material Requisition To Resource Division | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | RTOR000001/2024-2025 | 1001/W-181/JIC/PMU/2022 | 30/04/2024 | 0 | Resource Division | 194.9 | 0 | 0
2142 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Material Requisition To Resource Division | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | RTOR000002/2023-2024 | 2147/W-181/JICA/PMU/2013 | 26/07/2023 | 0 | Resource Division | 91.65 | 0 | 0
2143 | PMU - WBDWSIP - EE-II | Project Management Unit,WBPWSP,Purulia | Material Requisition To Resource Division | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | RTOR000003/2023-2024 | 594/W-181/JICA/PMU/2022 | 06/03/2024 | 0 | Resource Division | 38.92 | 0 | 0
2144 | Purulia Division | Raghunathpur Sub-Division | Laying pipe line across railway track area near mouza Shaldiha at Sutaboi under Keliathole Palashkola W/S Scheme within Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000882/2023-2024 | 1532/PD | 16/10/2023 | 30 | SADHAN GORAIN | 52.43 | 0 | 100
2145 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of existing structure (i.e. Administrative building, Cholrine House, Filter House, Chemical House ) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001335/2023-2024 | 1718/PD | 04/12/2023 | 409 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 33.25 | 0 | 100
2146 | Purulia Division | Raghunathpur Sub-Division | Repairing and renovation of existing structure (i.e. Clarifier Tank, CWR, Pump House, Switch Room etc.) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001336/2023-2024 | 1719/PD | 04/12/2023 | 453 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 28.94 | 0 | 0
2147 | Purulia Division | Raghunathpur Sub-Division | Repairing and Renovation of Over Head Reservoir Capcaity 374cum at (ESR) at Lakhanpur W.T.P. under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001337/2023-2024 | 1720/PD | 04/12/2023 | 483 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.36 | 0 | 0
2148 | Purulia Mechanical | Raghunathpur Sub-Division | WBSEDCL for Sohardi Mouza, Babugram, P.O-Sanka, Raghunathpur Water Supply Scheme | Assistant Engineer |  | BILL/00146/2024-2025 | BP-24-25-28 | 11/06/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0
2149 | Purulia Mechanical | Raghunathpur Sub-Division | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000005/2025-2026 | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0
2150 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Chemical house panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000035/2024-2025 | 948/PMD | 19/06/2024 | 90 | M/S UJJAL DIESEL SERVICE | 5.66 | 0 | 100
2151 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Filter house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE DTE. | Assistant Engineer |  | ORD/000036/2024-2025 | 949/PMD | 19/06/2024 | 90 | MOUSUMI BENERJEE | 10.45 | 0 | 100
2152 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing old Recirculation Sump Pump motor set at Lakshmanpur WTP of Raghunathpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000037/2024-2025 | 950/PMD | 19/06/2024 | 90 | SAIBAL SARKAR | 22.94 | 0 | 0
2153 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing one number old VT pump with new one at intake of Lakshmanpur WTP of Raghunathpur W/S Project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000038/2024-2025 | 951/PMD | 19/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 20.75 | 0 | 0
2154 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of internal and External illuminations arrangements at existing Pump house-2 nos, PDB room Transformer room-2 nos , DG room, VCB room-2nos, AVR room, chlorine room, filter house(first floor and ground floor), chemical house (first floor and ground floor), Administrative building and Nine nos of OHR with supply luminaires and under Raghunathpur water supply project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000039/2024-2025 | 952/PMD | 19/06/2024 | 227 | SUBRATA DUTTA | 28.81 | 0 | 100
2155 | Purulia Mechanical | Raghunathpur Sub-Division | Defixing the existing idle unit and supply delivery and installation of Electro-Magnetic Flow Meter with cable and remote display unit at different site of WTP. Intake OHR inlet and Outlet pipeline at Forest premises at Garpanchakot, WBSEDCL office premises under Raghunathpur water supply project under PMD. PHE. Dte. | Assistant Engineer |  | ORD/000040/2024-2025 | 953/PMD | 19/06/2024 | 408 | EASTERN INDIA SALES AND SERVICE | 83.58 | 0 | 65
2156 | Purulia Mechanical | Raghunathpur Sub-Division | Supply of Safety items of Gaseous Chlorination system at Lakshmanpur WTP and OHR no 5 ,6 ,7 under Raghunathpur W/S project under PMD, PHE, Dte | Assistant Engineer |  | ORD/000042/2024-2025 | 955/PMD | 19/06/2024 | 90 | TUSHAR GHOSH | 9.75 | 0 | 100
2157 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Raw water Intke pump house panel at Lakshmanpur WTP under Raghunathpur water supply project under PMD PHE DTE . | Assistant Engineer |  | ORD/000077/2024-2025 | 998/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 26.2 | 0 | 0
2158 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Clear water pump house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000078/2024-2025 | 999/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 57.19 | 0 | 0
2159 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing and rectification of Gaseous Chlorination system at OHR no. 5,6 & 7 of Raghunathpur Water Supply Project under P.M.D., P.H.E. Dte. | Assistant Engineer |  | ORD/000210/2023-2024 | 1182/PMD | 03/11/2023 | 15 | EASTERN INDIA SALES AND SERVICE | 15.26 | 0 | 100
2160 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-1 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000223/2023-2024 | 1253/PMD | 17/11/2023 | 90 | TAPAN KUMAR DEY | 21.67 | 0 | 100
2161 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-2 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000224/2023-2024 | 1254/PMD | 17/11/2023 | 90 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 21.66 | 0 | 100
2162 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-3 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000225/2023-2024 | 1255/PMD | 17/11/2023 | 90 | SAIBAL SARKAR | 21.67 | 0 | 70
2163 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-4 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000226/2023-2024 | 1256/PMD | 17/11/2023 | 90 | RABINDRA NATH KHAN | 21.67 | 0 | 50
2164 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP East side of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000238/2024-2025 | 1227/PMD | 13/08/2024 | 20 | M/S R.K. ENTERPRISE | 0.98 | 0 | 100
2165 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of 14 Ring Current Collector at Lakshmanpur WTP Clariflocculator under Raghunathpur water supply project under Purulia Mechanical Division , P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2023-2024 | 420/PMD | 11/03/2024 | 296 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 1.48 | 0 | 100
2166 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & fitting of Fire Extinguisher with refilling of Fire Extinguisher at different sections of Raghunathpur Water Supply Project under Purulia Mechanical Division PHE, Dte. | Assistant Engineer |  | ORD/000454/2023-2024 | 434/PMD | 11/03/2024 | 30 | M/S R.K. ENTERPRISE | 2.16 | 0 | 10
2167 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP West Side of Recirculation System under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000583/2024-2025 | 1441/PMD | 01/10/2024 | 30 | MD. ASLAM | 0.99 | 0 | 0
2168 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP MiddleSide of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000623/2024-2025 | 1545/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 1 | 0 | 0
2169 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & fixing of display board for depicting details of Pump and others at Pump House/Other location of Raghunathpur and other blocks in the Dist-Purulia under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000657/2024-2025 | 1260/PMD | 22/08/2024 | 131 | SUJIT MUKHERJEE | 0.85 | 0 | 100
2170 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery, laying and connection of cable for high lift pump house power connection and other works under Raghunathpur water supply project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000688/2024-2025 | 1700/PMD | 06/12/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 68.36 | 0 | 100
2171 | Purulia Mechanical | Raghunathpur Sub-Division | Additional work related to Defixing the existing old unit and installation of new Electro Magnetic Flow meter with cable and remote display unit at different site under Raghunathpur w/s project under PMD, PHE Dte. | Assistant Engineer |  | ORD/000969/2024-2025 | 529/PMD | 28/03/2025 | 60 | EASTERN INDIA SALES AND SERVICE | 5.48 | 0 | 0
2172 | Purulia Division | Raghunathpur Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000155/2020-2021 | 1408/PD | 29/12/2020 | 45 | SANTANU BANERJEE | 77.87 | 51.77 | 100
2173 | Purulia Division | Raghunathpur Sub-Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000354/2021-2022 | 104/PD | 18/01/2022 | 30 | SANTANU BANERJEE | 18.64 | 0 | 0
2174 | Purulia Division | Raghunathpur Sub-Division | Supplying & laying different dia HDPE pipe line from Barrah Siramdih to Bonkhali village under Rangamati. (Tender No.1005/EE/PD of 20210-22) | Assistant Engineer | Junior Engineer-1 | VCH/000865/2022-2023 | 121/8443142 | 23/09/2022 | 0 | MANATOSH SINGH | 3.52 | 0 | 0
2175 | Purulia Division | Raghunathpur Sub-Division | Providing Functional house hold tap connection (FHTC) in communication with Jal Dhara/ Jal Swapna under Rangamati W/s Scheme. (Tender No. 11/SE/PMU of 2020-21) | Assistant Engineer | Junior Engineer-1 | VCH/000916/2020-2021 | 424/8443137 | 22/03/2021 | 0 | SANTANU BANERJEE | 51.65 | 0 | 0
2176 | Purulia Division | Raghunathpur Sub-Division | Sinking of 2 (Two) No 200 mm dia river bed vertical tubewell (T/W No.3 & 4) alongwith necessary 100 mm dia GI collecting line to common manifold chamber Cleaning of chowkage of distribution line and other allied work under Bhamuria W/S Scheme under Raghunathpur Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000050/2023-2024 | 674/PD | 17/05/2023 | 45 | ANUP KUMAR SAHA | 11.84 | 11.83 | 100
2177 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Alkusha, Asanbani, Baruipara under Bhamuria G.P). (586 Nos.) | Assistant Engineer | Junior Engineer-3 | ORD/000236/2020-2021 | 57/PD | 15/01/2021 | 45 | ANUP KUMAR SAHA | 29.11 | 7.74 | 100
2178 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza- Bhamuria, Habitation-Sarkardih Tola under Bhamuria G.P). (655 Nos.) | Assistant Engineer | Junior Engineer-3 | ORD/000240/2020-2021 | 61/PD | 15/01/2021 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 32.49 | 0 | 100
2179 | Purulia Division | Raghunathpur Sub-Division | New Sinking of 1(one) No 200 mm dia river bed vertical tube well (T/W No. 2) along with necessary 100 mm dia GI collecting line from riverbed tube well to manifold chamber at river bank (Damodar River) at Manikeswar ghat at Hirakund under Bhamuria Improvement W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tube well No - 2) | Assistant Engineer | Junior Engineer-3 | ORD/000477/2020-2021 | 404/PD | 15/01/2021 | 30 | ANUP KUMAR SAHA | 7.38 | 0 | 0
2180 | Purulia Division | Raghunathpur Sub-Division | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -A) | Assistant Engineer | Junior Engineer-3 | ORD/000543/2022-2023 | 459/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.79 | 4.77 | 100
2181 | Purulia Division | Raghunathpur Sub-Division | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -B) | Assistant Engineer | Junior Engineer-3 | ORD/000544/2022-2023 | 460/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.85 | 4.84 | 100
2182 | Purulia Division | Raghunathpur Sub-Division | Additional work by providing Functional Household Tap Connection (FHTC) including Interconnection between Over flow and Distribution Main and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -C) | Assistant Engineer | Junior Engineer-3 | ORD/000545/2022-2023 | 461/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.21 | 4.19 | 100
2183 | Purulia Division | Raghunathpur Sub-Division | New sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 2 along with necessary 100 mm dia GI collecting line from river bed tube well to manifold chamber at river bank (Damodar river) of Manikeswar Ghat under Bhamuria Water Supply Scheme (Tender No- 14/2020-21 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/000883/2022-2023 | BP-2022-23-68 | 01/07/2022 | 0 | ANUP KUMAR SAHA | 7.14 | 0 | 0
2184 | Purulia Division | Raghunathpur Sub-Division | Re-sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 4 along with necessary 100 mm dia GI collecting under Bhamuria W/S Scheme (Tender No- 110/2022-23 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/000906/2022-2023 | BP-2022-23-95 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 4.38 | 0 | 0
2185 | Purulia Division | Raghunathpur Sub-Division | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line 250 mm dia clear water rising main in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) of Manikeswar Ghat at Hirakund under Bhamuria Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 24/2020-21 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/000907/2022-2023 | BP-2022-23-94 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 16.61 | 0 | 0
2186 | Purulia Division | Raghunathpur Sub-Division | Rejuvenation work for supplying & laying of HDPE piped distribution main with all allied works from old OHR site at Bhamuria & adjacent habitation under Bhamuria W/S Scheme (Tender No- 547/2021-22 of EE/PD) | Assistant Engineer | Junior Engineer-3 | VCH/001136/2021-2022 | BP-2021-22-334 | 23/03/2022 | 0 | ANUP KUMAR SAHA | 10.5 | 0 | 0
2187 | Purulia Division | Raghunathpur Sub-Division | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-D (Mouza-Bonra under Bhamuria GP ).( 889 Nos.) (Tender No.333/EE/PD of 2020-21) | Assistant Engineer | Junior Engineer-3 | VCH/001171/2021-2022 | BP-2021-22-365 | 28/03/2022 | 0 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 40.33 | 0 | 0
2188 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Regarding laying of water supply pipe line along road side and road crossing on i) Balrampur-Barabazar-Sindri Road from 16.780 Km to 18.90 Km and Barabazar-Bandwan Road from 0.00 Km to 0.76 Km in respect of Augmentation of Barabazar water supply scheme in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00174/2022-2023 | BP-2022-23-663 | 23/02/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 48.28 | 0 | 0
2189 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0
2190 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Supply of stationery materials for office use | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00988/2024-2025 | BP-2024-25-531 | 20/11/2024 | 0 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0
2191 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of WBSEDCL Meter Room & Guard Room with sanitary and plumbing arrangment at Barabazar River Site for Augmentation of Barabazar W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte.. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000057/2023-2024 | 663/PD | 17/05/2023 | 500 | CHATTERJEE CONSTRUCTION | 7.69 | 4.57 | 100
2192 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing ,renovation & Construction Damaged (Portion) of Boundary Wall of Brabazar OHR Side Campus Of Barabazar W/S Scheme Under Purulia Division ,PHE DTE.. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000278/2021-2022 | 1553/PD | 15/12/2021 | 45 | DEBASISH CHAKRABORTY | 10.02 | 4.89 | 55
2193 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000421/2021-2022 | 312/PD | 25/02/2022 | 45 | KOUSHIK CHATTERJEE | 152.12 | 81.03 | 100
2194 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of R.C.C. Elevated Reservoir, Capcaity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Rejuvanation of Barabazar W/S Scheme under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000431/2021-2022 | 378/PD | 11/03/2022 | 270 | PRAVAT SARKAR | 70.29 | 64.62 | 93
2195 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000432/2021-2022 | 379/PD | 11/03/2022 | 60 | PRAVAT SARKAR | 91.16 | 0 | 80
2196 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Guarding arrangement through Registered firm organized by Ex-Military person at Barabazar OHR site of Barabazar W/S Scheme under Purulia Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000504/2021-2022 | 530/4/PD | 30/03/2022 | 30 | FRONTLINE EX-SERVICEMEN BUREAU | 0.58 | 0 | 0
2197 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000608/2022-2023 | 517/PSD | 12/08/2022 | 40 | SADHAN GORAIN | 3.51 | 0 | 100
2198 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Sinking of 01 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (OHR Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001108/2024-2025 | 2200/PD | 13/12/2024 | 30 | CHATTERJEE CONSTRUCTION | 4.61 | 0 | 100
2199 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Making Interconnection and Bypass arrangemet of Rising Main and Distribution Pipeline For Newly Constructed OHR at Barabazar OHR Site of Aug. Barabazar W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001209/2022-2023 | 493/PD | 31/03/2023 | 45 | KOUSHIK CHATTERJEE | 8.09 | 0 | 100
2200 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001323/2023-2024 | 1709/PD | 04/12/2023 | 45 | CHATTERJEE CONSTRUCTION | 9.26 | 0 | 100
2201 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001491/2023-2024 | 1802/PD | 08/12/2023 | 30 | KOUSHIK CHATTERJEE | 9.26 | 0 | 100
2202 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of Guard Room at Barabazar OHR Site under Barabazar W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001493/2023-2024 | 1804/PD | 08/12/2023 | 30 | CHATTERJEE CONSTRUCTION | 1.88 | 0 | 0
2203 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Repairing of Boundary wall & DI Rising Main at Barabazar River Site under Barabazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001871/2023-2024 | 96/PD | 15/01/2024 | 60 | CHATTERJEE CONSTRUCTION | 14.67 | 0 | 0
2204 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000007/2021-2022 | 1509/PD | 13/12/2021 | 0 | Resource Division | 6.46 | 0 | 0
2205 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000038/2022-2023 | 242/PD | 20/02/2023 | 0 | Resource Division | 6.4 | 0 | 0
2206 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub- Division, PHE Dte. Part-II (Tender No- 1012/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000914/2022-2023 | BP-2022-23-122 | 16/07/2022 | 0 | PRAVAT SARKAR | 27.6 | 0 | 0
2207 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Barabazar W/s Scheme. (Tender No.1013/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001166/2021-2022 | BP-2021-22-345 | 28/03/2022 | 0 | KOUSHIK CHATTERJEE | 7.9 | 0 | 0
2208 | Purulia Division | Purulia Mechanical Sub-Division (Drilling) | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/s Scheme, Block Purulia-I, Barabazar) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (SL No.07) (Tender No.357/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001214/2021-2022 | BP-2021-22-369 | 30/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 3.55 | 0 | 0
2209 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Barabazar W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00244/2023-2024 | BP-23-24-154 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.74 | 0 | 0
2210 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Barabazar and other Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000010/2021-2022 | 19/PMD | 19/01/2022 | 30 | RABINDRA NATH KHAN | 13.59 | 2.57 | 79
2211 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000052/2023-2024 | 521/PMD | 05/05/2023 | 60 | GOENKA ENTERPRISE | 36.99 | 0 | 100
2212 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Barabazar Water Supply scheme Block Barabazar under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000063/2021-2022 | 108/PMD | 28/02/2022 | 30 | M/S M S ENTERPRISE | 20.48 | 20.24 | 100
2213 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and Installation & Commissioning of Chlorination Arrangement at Barabazar OHR for Augmentation of Barabazar water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 1090/PMD | 08/07/2024 | 60 | MOUSUMI BENERJEE | 10.14 | 0 | 70
2214 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Submersible pumping machinery with all ancillaries & auxiliaries works for Augmentation of Barabazar Water Supply Scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2022-2023 | 766/PMD | 14/11/2022 | 7 | MOUSUMI BENERJEE | 3.24 | 2.91 | 90
2215 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal and external illumination with other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000405/2022-2023 | 233/PMD | 03/03/2023 | 795 | AVISHEK ENTERPRISE | 4.86 | 0 | 100
2216 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries in newly constructed tube well with allied cable line and other allied works for augmentation of Barabazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000406/2022-2023 | 234/PMD | 03/03/2023 | 700 | MOUSUMI BENERJEE | 9.65 | 0 | 70
2217 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 75 KVA voltage stabilizer for Augmentation of Barabazar water supply scheme under PMD PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000407/2022-2023 | 235/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 7.6 | 0 | 35
2218 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | External illumination of OHR site barabazar water supply scheme for Augmentation work under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2023-2024 | 419/PMD | 11/03/2024 | 570 | BISHWANATH NANDI | 7.55 | 0 | 100
2219 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and laying of 1.1 KV grade 3.5 core 95 sq. mm XLPE insulated Al. armoured cable for Augmentation at Barabazar W/S Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000537/2023-2024 | 499/PMSD(W/S) | 21/12/2023 | 15 | MOUSUMI BENERJEE | 0.62 | 0 | 100
2220 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and fitting fixing of loop box for outdoor lighting for Augmentation at Barabazar Water Supply Scheme under PMD, PHE Dte.in the district of Purulia. (2ND Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000588/2024-2025 | 349/PMSD(W/S) | 04/09/2024 | 10 | AVISHEK ENTERPRISE | 0.17 | 0 | 100
2221 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply,delivery and Installation of Level Transmitter ,Submersible pumping machineries and other allied works for Augmentation of Barabazar W/S scheme under PMD Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000681/2024-2025 | 1693/PMD | 06/12/2024 | 111 | MOUSUMI BENERJEE | 7.51 | 0 | 50
2222 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | CONSTRUCTION OF RIG BORE TUBE WELL (200 x165) MM DIA BY DTH METHOD FOR BARABAZAR AND OTHER SCHEMES UNDER PMD PHE DTE.(TR.NO 60 OF 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000230/2022-2023 | C072218251845 | 18/07/2022 | 0 | RABINDRA NATH KHAN | 8.16 | 0 | 0
2223 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying PVC Pipe ,Mending good damage of road, Eath work in filling of Para & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000051/2023-2024 | 675/PD | 17/05/2023 | 60 | ZEST INFRACON | 15.56 | 15.54 | 100
2224 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work by Providing functional Household Tap Connection (FHTC) at different AWC ,School and other allied works of Madandih & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000172/2022-2023 | 789/PD | 05/05/2022 | 45 | MADHU SUDAN RAKSHIT | 6.23 | 6.21 | 100
2225 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000223/2021-2022 | 724/RNP | 06/12/2021 | 90 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0
2226 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Switch Room-Cum-Chlorine Room at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000224/2021-2022 | 725/RNP | 06/12/2021 | 90 | MADHU SUDAN RAKSHIT | 4.21 | 3.91 | 0
2227 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Pump House at Head work site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000317/2021-2022 | 29/PD | 07/01/2022 | 45 | SUBHAS CHANDRA MAHATO | 5.03 | 5.02 | 100
2228 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir of Capcaity 60000 Galon and other allied works under Sonathali W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000318/2021-2022 | 30/PD | 07/01/2022 | 60 | MADHU SUDAN RAKSHIT | 10.25 | 8.56 | 0
2229 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000388/2021-2022 | 209/PD | 01/02/2022 | 45 | M/S S & P CONSTRUCTION | 158.98 | 13.64 | 65
2230 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for Construction of Pump House building at Head work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000581/2022-2023 | 494/RNP | 02/08/2022 | 45 | SUBHAS CHANDRA MAHATO | 4.45 | 4.41 | 100
2231 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000844/2022-2023 | 1747/PD | 22/11/2022 | 45 | MANATOSH SINGH | 4.3 | 0 | 0
2232 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Pump House Building at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Related to JJM & Jal swapna programme) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000845/2022-2023 | 1748/PD | 22/11/2022 | 90 | MADHU SUDAN RAKSHIT | 10.31 | 10.29 | 0
2233 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000003/2022-2023 | 963/PD | 21/06/2022 | 0 | Resource Division | 33.65 | 0 | 0
2234 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000045/2022-2023 | 441/PD | 23/03/2023 | 0 | Resource Division | 32.08 | 0 | 0
2235 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000179/2022-2023 | BP-2022-23-46 | 02/05/2022 | 0 | S AND P CONSTRUCTION | 16.37 | 0 | 0
2236 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000190/2022-2023 | BP-2022-23-57 | 20/05/2022 | 0 | TOTAL INFRA | 3.35 | 0 | 0
2237 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Kalapathar Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sonatholi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 02/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000945/2022-2023 | BP-2022-23-115 | 16/07/2022 | 0 | KOUSHIK CHATTERJEE | 18.97 | 0 | 0
2238 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of SonathaliWater Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No. 17/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000960/2021-2022 | BP-2021-22-267 | 28/02/2022 | 0 | M/S S & P CONSTRUCTION | 35.45 | 0 | 0
2239 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of G.I shed at 1st floor of Raghunathpur Sub- Divisional office building under Aug. of Sonathali W/S Scheme within Raghunathpur Sub- Division, PHE Dte. [Tender No 941/2022-23 of EE/PD] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/001901/2022-2023 | BP-2023-24-85 | 16/05/2023 | 0 | MANATOSH SINGH | 4.17 | 0 | 0
2240 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sonathol Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000064/2021-2022 | 109/PMD | 28/02/2022 | 30 | R.N.S. TRADING | 20.48 | 0 | 100
2241 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Submersible pump motor ,cable line,Kiosk , MCC allied electro mechanical equipments at Augmentation of sonatholi Water supply scheme Block: kashipur, Under Purulia Mechanical Division PHE Dte. Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000286/2022-2023 | 78/PMD | 01/02/2023 | 60 | SUMIT KR. CHAKRABORTY | 25.34 | 0 | 20
2242 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Horizontal split casing centrifugal pump motor, MCC , Flow meter and All electro mechanical equipments , with allied works for Augmentation Sonathali low lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000287/2022-2023 | 79/PMD | 01/02/2023 | 60 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 37.16 | 0 | 50
2243 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination arrangement at Augmentation Sonathali low lift and High lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000472/2022-2023 | 312/PMD | 16/03/2023 | 30 | NUPUR CHANDRA HALDER | 5.13 | 0 | 45
2244 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Vertical multistage centrifugal pump motor sets ,Pannel , Flow meter and all electro mechanical equipment's at Augmentation of Sonathali High Lift Water supply scheme for direct pumping Block :Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000513/2022-2023 | 100/PMD | 09/02/2023 | 60 | R.N.S. TRADING | 45.25 | 0 | 68
2245 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 100
2246 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT. OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF SNATHOL W/S SCHEME KASHIPUR BLOCK UNDER PMD PHE DTE.(TR.NO 342 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000586/2021-2022 | C032262583160 | 28/03/2022 | 0 | R.N.S. TRADING | 13.71 | 0 | 0
2247 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi OHR site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000011/2023-2024 | 539/PD | 12/04/2023 | 100 | TOTAL INFRA | 13.85 | 5.64 | 100
2248 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Boundary wall including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000170/2023-2024 | 941/PD | 19/07/2023 | 30 | ROY CONSTRUCTION | 6.72 | 2.09 | 32
2249 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing & Restoration work including supplying & laying of HDPE Piped Distribution Main with other allied work under Baghmundi W/S Scheme under Purulia Sadar Sub-Divn, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000190/2023-2024 | 4682/PSD | 27/07/2023 | 15 | SB CONSTRUCTION | 0.96 | 0.95 | 100
2250 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 185 Cum (Intze Type) including other allied works at OHR site of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000258/2021-2022 | 1531/PD | 13/12/2021 | 180 | MANATOSH SINGH | 6.22 | 0 | 100
2251 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B : Water supply through direct pumping) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000380/2021-2022 | 182/PD | 31/01/2022 | 45 | KOUSHIK CHATTERJEE | 146.44 | 58.16 | 65
2252 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000386/2021-2022 | 208/PD | 01/02/2022 | 45 | NIBHAS SINHA | 148.62 | 0 | 100
2253 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000459/2021-2022 | 421/PD | 17/03/2022 | 100 | ANIL GORAI | 13.72 | 10.86 | 100
2254 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001151/2022-2023 | 425/PD | 21/03/2023 | 45 | KOUSHIK CHATTERJEE | 20.22 | 11.37 | 55
2255 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi WTP site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001216/2022-2023 | 504/PD | 31/03/2023 | 90 | ROY CONSTRUCTION | 13.76 | 10.12 | 100
2256 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing 30 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001226/2022-2023 | 248/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.68 | 0.68 | 100
2257 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying delivery fitting& fixing 20 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001227/2022-2023 | 249/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.46 | 0 | 0
2258 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Shifting of distribution pipeline and existing 95 Nos FHTC due to widening & strengthening work of PWDte along Gobondapur to Ajodhya More under Baghmundi water supply scheme at Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/001325/2023-2024 | 1711/PD | 04/12/2023 | 60 | NIBHAS SINHA | 13 | 0 | 0
2259 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000005/2021-2022 | 1508/PD | 13/12/2021 | 0 | Resource Division | 82.12 | 0 | 0
2260 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000017/2021-2022 | 395/PD | 11/03/2022 | 0 | Resource Division | 4.32 | 0 | 0
2261 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) (Tender No.19/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000135/2022-2023 | BP-2022-23-4 | 05/04/2022 | 0 | NIBHAS SINHA | 44.89 | 0 | 0
2262 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000714/2022-2023 |  | 12/10/2022 | 0 | NIBHAS SINHA | 39.62 | 0 | 0
2263 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-B : Water supply through OHR) (Tender No- 19/2021-22 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001049/2022-2023 | BP-2022-23-393 | 19/10/2022 | 0 | NIBHAS SINHA | 39.62 | 0 | 0
2264 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B: Water supply through direct pumping) (Tender No.18/SE/PMU of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001172/2021-2022 | BP-2021-22-344 | 28/03/2022 | 0 | KOUSHIK CHATTERJEE | 34.28 | 0 | 0
2265 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baghmundi W/S Scheme Ajodhya W/s Scheme, Block Baghmundi) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.361/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/001213/2021-2022 | BP-2021-22-370 | 30/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.34 | 0 | 0
2266 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Baghmundi | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00249/2023-2024 | BP-2023-24-153 | 14/09/2023 | 0 | WBSEDCL PURULIA | 6.08 | 0 | 0
2267 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Load Enhancement for Augmentation of Baghmundi | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00250/2023-2024 | BP-2023-24-152 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.86 | 0 | 0
2268 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of Barge and floating walkway with required MS work by necessary supply of materials and other allied works for Augmentation of Bagmundi W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000051/2023-2024 | 520/PMD | 05/05/2023 | 60 | ASHOKE ADHIKARY | 19.46 | 0 | 21
2269 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baghmundi Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000065/2021-2022 | 110/PMD | 28/02/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 4.69 | 100
2270 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(Intake Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000075/2023-2024 | 562/PMD | 16/05/2023 | 60 | H K DAS AND CO | 16.75 | 0 | 100
2271 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Bagmundi w/s scheme( WTP and OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000128/2023-2024 | 866/PMD | 21/07/2023 | 60 | ASHOKE ADHIKARY | 3.05 | 0 | 100
2272 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of external lighting and other allied works for Baghmundi (High Lift) water supply scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000185/2022-2023 | 755/PMD | 07/11/2022 | 30 | SUBRATA DUTTA | 4.01 | 3.9 | 100
2273 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000401/2022-2023 | 229/PMD | 03/03/2023 | 60 | PINTU DEY | 22.94 | 7.82 | 70
2274 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(CWR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000402/2022-2023 | 230/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 40.32 | 8.79 | 75
2275 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAGHMUNDI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000083/2022-2023 | C042211560768 | 08/04/2022 | 0 | COMBINE ENTERPRISE | 12.25 | 0 | 0
2276 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTTALATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAHGMUNDI W/S SCHEME , BAGHMUNDI BLOCK UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000100/2022-2023 | C042249065860 | 29/04/2022 | 0 | COMBINE ENTERPRISE | 3.54 | 0 | 0
2277 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Office Computer purpose bill payment. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00058/2024-2025 | BP-2024-25-58 | 14/05/2024 | 0 | SRI KRISHNA COMPUTER | 0.5 | 0 | 0
2278 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Regarding laying of water supply pipe line along road side and road crossing on i) Balarampur-Bagmundi Road and ii) Jhalda-Bagmundi Road in respect of Augumentation of Balarampur water supply scheme in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00062/2022-2023 | BP-2022-23-510 | 22/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 45.73 | 0 | 0
2279 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Indian Railways Miscellaneous collection. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00091/2022-2023 | BP-2022-23-5178 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.34 | 0 | 0
2280 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-I OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000012/2023-2024 | 540/PD | 12/04/2023 | 100 | SHYAMAL KUMAR DEY | 14.21 | 0 | 81
2281 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-II (Berma) OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000013/2023-2024 | 541/PD | 12/04/2023 | 100 | SADHAN GORAIN | 14.25 | 0 | 65
2282 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with other allied works at Zone-II OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000040/2023-2024 | 657/PD | 17/05/2023 | 472 | SADHAN GORAIN | 7.96 | 0 | 100
2283 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 180 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-I of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000054/2023-2024 | 661/PD | 17/05/2023 | 60 | SHYAMAL KUMAR DEY | 9.17 | 0 | 100
2284 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 800 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-II of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000089/2023-2024 | 819/PD | 26/06/2023 | 90 | SADHAN GORAIN | 18.27 | 0 | 100
2285 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Boundary wall including withdrawing and relaying pipeline and other allied works at Zone-II OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000113/2023-2024 | 881/PD | 03/07/2023 | 427 | MS GORAIN CONCERN | 8.19 | 0 | 100
2286 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line of Balarampur (Zone-II) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tentlow Mouza] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000118/2024-2025 | 891/PD | 07/05/2024 | 45 | SIKHA ENTERPRISES | 12.4 | 0 | 100
2287 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of High lift pump house & Sub station building including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000169/2023-2024 | 940/PD | 19/07/2023 | 30 | SAIBAL SARKAR | 5.95 | 0 | 70
2288 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : Water Supply through Direct pumping at Chhota Urma (Part), Namsol (Part) & Amruhansa Mouza] (2nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000349/2022-2023 | 877/PD | 23/05/2022 | 45 | ANUP KUMAR SAHA | 156.85 | 100.58 | 0
2289 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-M : TENTLOW(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000389/2021-2022 | 228/PD | 09/02/2022 | 30 | ANUDIP SAHA | 9.57 | 9.5 | 100
2290 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000390/2021-2022 | 229/PD | 09/02/2022 | 45 | BOSE CONSTRUCTION | 53.83 | 0 | 65
2291 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-I : BALARAMPUR(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000391/2021-2022 | 230/PD | 09/02/2022 | 45 | TUMPA GORAIN | 18.71 | 18.11 | 100
2292 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-G : RANGADIH(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000392/2021-2022 | 231/PD | 09/02/2022 | 45 | SIKHA ENTERPRISES | 11.76 | 0.73 | 100
2293 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : BERMA(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000393/2021-2022 | 232/PD | 09/02/2022 | 45 | MANATOSH SINGH | 32.6 | 0 | 70
2294 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : BERMA(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000394/2021-2022 | 233/PD | 09/02/2022 | 45 | SOUMITRA CHAKRABORTY | 21.93 | 20.46 | 100
2295 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000395/2021-2022 | 234/PD | 09/02/2022 | 603 | MS GORAIN CONCERN | 70.99 | 0 | 65
2296 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : Water Supply through OHR at Baraurma, Berada, Chhota Urma (Part), & Namsol (Part) Mouza] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000419/2021-2022 | 314/PD | 25/02/2022 | 45 | SANTANU BANERJEE | 261.89 | 152.62 | 92
2297 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-F : RANGADIH(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000426/2021-2022 | 357/PD | 04/03/2022 | 1444 | SADHAN GORAIN | 136.58 | 22.56 | 70
2298 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000427/2021-2022 | 367/PD | 04/03/2022 | 1462 | SADHAN GORAIN | 129.15 | 29.24 | 70
2299 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-H : BALARAMPUR(Part) MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2021-2022 | 366/PD | 04/03/2022 | 1436 | SADHAN GORAIN | 107.69 | 35.49 | 70
2300 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : DIRECT PUMPING AT BELA, SUNIDIH & RANGADIH MOUZA] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000440/2021-2022 | 365/PD | 04/03/2022 | 1279 | SADHAN GORAIN | 281.46 | 8.29 | 82
2301 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Boundary wall with other allied works at Balarampur Zone-I OHR site under Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub_ Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000859/2022-2023 | 1812/PD | 06/12/2022 | 45 | SHYAMAL KUMAR DEY | 15.1 | 13.55 | 91
2302 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of 6.0 x 3.50 mtr size Panel room with other allied works for Augmentation of Balarampur W/S Scheme at Balarampur WTP site of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000860/2022-2023 | 1813/PD | 06/12/2022 | 45 | SABYASACHI MISHRA | 4.09 | 0 | 100
2303 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Balarampur (Zone-II) Water Supply Scheme of Balarampur Block under Purulia Sadar Sub-Division,PHE Dte ( Mouza- SAPUA) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000873/2022-2023 | 1841/PD | 12/12/2022 | 45 | SOUMITRA CHAKRABORTY | 39.68 | 4.23 | 25
2304 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and Renovation of Boundary wall & centry room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001036/2022-2023 | 324/PD | 09/03/2023 | 30 | ANADI MAHATO | 3.27 | 0 | 100
2305 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | PCC Road restoration work due to dismantling the road for providing functional househole tap connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at Balarampur (Part) mouza for Agumentation of Balarampur (Zone -II) W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001059/2022-2023 | 291/PD | 27/02/2023 | 15 | TUMPA GORAIN | 1.88 | 0 | 100
2306 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of DI & MS distribution pipeline including installation of sluice valve due to widening & strengthening of Balarampur NH-32 of Balarampur W/S Scheme [Zone-II] of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001096/2022-2023 | 363/PD | 14/03/2023 | 30 | KOUSHIK CHATTERJEE | 7.39 | 0 | 0
2307 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of RCC clear water reservoir (CWR) of capacity 100 m3 at River site including repairing of boundary wall at OHR site & shifting of 150mm dia DI distribution pipeline for Ramnagar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001124/2022-2023 | 397/PD | 16/03/2023 | 100 | SWASTIK ENTERPRISE | 24.75 | 0 | 100
2308 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-II OHR Site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003452/2023-2024 | 328/PD | 02/03/2024 | 90 | MOHOR CONSTRUCTION | 5.29 | 0 | 100
2309 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of Parallel distribution Pipeline at Barabazar Road and Balarampur Town at Balarampur Zone-2 to Providing FHTC under Balarampur Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHEDte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003453/2023-2024 | 315/PD | 01/03/2024 | 60 | SADHAN GORAIN | 95.14 | 0 | 20
2310 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-I for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003454/2023-2024 | 323/PD | 01/03/2024 | 90 | PURNA CHANDRA TEWARI | 5.29 | 0 | 60
2311 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection(FHTC) in Connection with jal jeevan mission(JJM and Jal Jeevan) and Laying of parallel line under command area of Balarampur Water Supply Scheme of Balarampur Block under Purulia Division, PHE Dte (Kadamdih Mouza) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/003967/2023-2024 | 511/PD | 16/03/2024 | 60 | DEBASISH CHAKRABORTY | 11.92 | 0 | 0
2312 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000018/2021-2022 | 396/PD | 11/03/2022 | 0 | Resource Division | 24.46 | 0 | 0
2313 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000023/2022-2023 | 989/PD | 23/06/2022 | 0 | Resource Division | 127.38 | 0 | 0
2314 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] (Tender No.983/EE/PD of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000175/2022-2023 | BP-2022-23-44 | 02/05/2022 | 0 | BOSE CONSTRUCTION | 23.66 | 0 | 0
2315 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Balarampur W/S Scheme (Zone-II) Block- Balarampur ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 541/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000912/2022-2023 | BP-2022-23-89 | 07/07/2022 | 0 | HORIZEN | 8.39 | 0 | 0
2316 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme (Zone-I), block-Jhalda-II & Balarampur) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 844/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000921/2022-2023 | BP-2022-23-106 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.37 | 0 | 0
2317 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme Zone-I block-Jhalda II & Balarampur) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 358/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000937/2022-2023 | BP-2022-23-108 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.79 | 0 | 0
2318 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : SAPUA MOUZA] (Tender No- 90/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001039/2022-2023 | BP-2022-23-373 | 19/10/2022 | 0 | SOUMITRA CHAKRABORTY | 17.32 | 0 | 0
2319 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] (Tender No- 29/2021-22 of SE/PMU/WBPWSP(P) ) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001064/2022-2023 | BP-2022-23-410 | 28/10/2022 | 0 | SADHAN GORAIN | 11.91 | 0 | 0
2320 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] (Tender No- 168/2022-23 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001065/2022-2023 | BP-2022-23-409 | 28/10/2022 | 0 | MS GORAIN CONCERN | 35.37 | 0 | 0
2321 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line for augmentation of Balarampur (Zone-II) Water Supply Scheme of Purulia Sadar Sub- Division under Purulia Division, PHE Dte. [Part- G Rangadih (Part) Mouza] (Tender No- 979/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/001080/2022-2023 | BP-2022-23-437 | 30/11/2022 | 0 | SIKHA ENTERPRISES | 10.34 | 0 | 0
2322 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Balarampur. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00485/2023-2024 | BP-23-24-246 | 28/12/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0
2323 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Balarampur. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00486/2023-2024 | BP-23-24-245 | 28/12/2023 | 0 | WBSEDCL PURULIA | 4.7 | 0 | 0
2324 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Balarampur OHR side zone-2 for Augmentation of Balarampur Water Supply scheme Block Balarampur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000037/2023-2024 | 443/PMD | 20/04/2023 | 30 | ASHUTOSH DAS AND CO. | 21.56 | 0 | 0
2325 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination with other allied works for augmentation of Balarampur OHR site(Z-1 & Z-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000211/2023-2024 | 1197/PMD | 03/11/2023 | 60 | MOON LIGHT HOUSE | 8.85 | 0 | 0
2326 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-1) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000212/2023-2024 | 1198/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 33.66 | 0 | 55
2327 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000213/2023-2024 | 1199/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 34.58 | 0 | 60
2328 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, flowmeter, MCC panel and other allied works at intake side pump house for augmentation of Balarampur water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000256/2022-2023 | 47/PMD | 19/01/2023 | 60 | COMBINE ENTERPRISES | 74.71 | 13.61 | 100
2329 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Balarampur WTP under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000455/2022-2023 | 197/PMD | 24/02/2023 | 60 | ORIENTAL ENGINEERING CO. | 147.95 | 0 | 55
2330 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of MS pipe, specials including supply and laying of different size cables including allied works at WTP site under Augmentation of Balarampur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000626/2024-2025 | 1548/PMD | 11/11/2024 | 60 | ORIENTAL ENGINEERING CO. | 15.53 | 0 | 0
2331 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0
2332 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Toilet, Repairing of Guard Room & Remaining work of Pump House (Phase-II) at Sarbari under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000139/2024-2025 | 910/PD | 07/05/2024 | 60 | AMIT PATHAK | 7.1 | 0 | 100
2333 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Crossing of PWD Road and laying of additional HDPE pipe line(75mm & 63mm) with allied work (Zone-I) under Sarbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division,PHEDte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000212/2024-2025 | 1080/PD | 07/06/2024 | 404 | JAYANTA KUMAR MONDAL | 33.85 | 0 | 85
2334 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of DI(k-9) pipe and other allied works for rising main under Sarbari W/S Scheem within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000310/2022-2023 | 844/PD | 23/05/2022 | 45 | KHITISH CHANDRA PATHAK | 30.86 | 11.05 | 80
2335 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-A] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000320/2022-2023 | 853/PD | 23/05/2022 | 30 | KHITISH CHANDRA PATHAK | 7.79 | 6.77 | 90
2336 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-B] | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000321/2022-2023 | 854/PD | 23/05/2022 | 30 | KHITISH CHANDRA PATHAK | 7.79 | 2.13 | 95
2337 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Pump House (10 X 7 mtr) at Head Work site under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000332/2022-2023 | 863/PD | 23/05/2022 | 100 | M/S SHYAMASHREE ENTERPRISE | 15.57 | 13.54 | 100
2338 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-II) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Mouza-Neturia, Pathardiha, Kuthibari, Nawada) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000365/2022-2023 | 868/PD | 23/05/2022 | 60 | KHITISH CHANDRA PATHAK | 72.9 | 49.81 | 75
2339 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000402/2022-2023 | 341/RNP | 01/06/2022 | 30 | K.S.GROUP | 1.4 | 1.4 | 100
2340 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supplying, laying different dia HDPE and DI pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-I) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000411/2022-2023 | 984/PD | 22/06/2022 | 1120 | JAYANTA KUMAR MONDAL | 356.05 | 227.75 | 85
2341 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Withdrawing and new laying of necessary M.S. carrier pipe and all allied works at Ramkanali Ranipur village Railway Track at Erekusum village and new sinking of 2(two) no. 200 mm dia. River bed vertical at River Damodar with supplying and laying 100 mm dia GI collecting line from Riverbed Tubewell to CWR through common manifold chamber at river bank and execution of additional works for construction of (10.0 mtr x 7.0) mtr pump house drain, plinth protection under Saltora-Hijuli Under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000466/2024-2025 | 1523/PD | 27/08/2024 | 147 | M/S SAYAK BHATTACHARYA | 43.79 | 0 | 100
2342 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Tubewell (for 3 & 4) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000661/2023-2024 | 1354/PD | 13/09/2023 | 30 | KHITISH CHANDRA PATHAK | 5.56 | 0 | 100
2343 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. with including supply of all labour & materials for Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000922/2022-2023 | 1889/PD | 15/12/2022 | 270 | MD AAMIR KHAN | 131.92 | 49.36 | 100
2344 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Construction of Pump House (9 mtr X 4 mtr) at Boosting Station (Phase-II) under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000968/2022-2023 | 47/PD | 09/01/2023 | 100 | AMIT PATHAK | 10.66 | 10.44 | 100
2345 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Repairing and renovation of low-lift Pump House at River Side including drain under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/001086/2022-2023 | 97/RNP | 13/03/2023 | 15 | AMIT PATHAK | 0.97 | 0.96 | 0
2346 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Withdrawing & Laying of 2 Nos 100 mm dia GI Collecting line (1 & 2) at River bed of Damodar with fitting fixing of 40 mm dia GI guard pilling work under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/001121/2024-2025 | 607/RNP | 30/12/2024 | 152 | KHITISH CHANDRA PATHAK | 0.92 | 0 | 100
2347 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Road Crossing of rising main by jack pushing at Panchyet Road under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/003964/2023-2024 | 507/PD | 16/03/2024 | 60 | KHITISH CHANDRA PATHAK | 9.36 | 0 | 100
2348 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Supply fitting fixing D.I Specials for 200 MM dia D.I Rising Main under Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/003979/2023-2024 | 524/PD | 16/03/2024 | 45 | KHITISH CHANDRA PATHAK | 4.75 | 0 | 100
2349 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Laying of different dia HDPE Pipe line and Road crossing for additional work at Sarbori distribution line (Zone-II) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/003980/2023-2024 | 525/PD | 16/03/2024 | 60 | KHITISH CHANDRA PATHAK | 15.1 | 0 | 100
2350 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000022/2022-2023 | 978/PD | 22/06/2022 | 0 | Resource Division | 239.56 | 0 | 0
2351 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) at Chinakuri Ghat under Sarbari Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 744/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000958/2022-2023 | BP-2022-23-131 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 5.05 | 0 | 0
2352 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 972/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000967/2022-2023 | BP-2022-23-141 | 19/07/2022 | 0 | HORIZEN | 2.35 | 0 | 0
2353 | Purulia Division | Purulia Mechanical Sub-Division(W/S) | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 542/2021-22 of EE/PD) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000968/2022-2023 | BP-2022-23-134 | 19/07/2022 | 0 | HORIZEN | 4.09 | 0 | 0
2354 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | QUATATION FOR SHIFTING OF TRANSFORMER | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00476/2023-2024 | BP-23-24-238 | 13/12/2023 | 0 | WBSEDCL PURULIA | 2.36 | 0 | 0
2355 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Augmentation at SARBARI (Phase-1) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000116/2023-2024 | 644/PMD | 08/06/2023 | 30 | AVISHEK ENTERPRISE | 6.27 | 0 | 100
2356 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Rejuvenation at SARBARI (Phase-2) w/s scheme under PMD, PHE Dte. in the District of Purulia.. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000117/2023-2024 | 645/PMD | 08/06/2023 | 30 | SANTU MITRA | 4.4 | 0 | 50
2357 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels with others allied works for rejuvenation at SARBARI PHASE-2 w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000185/2023-2024 | 1175/PMD | 03/11/2023 | 120 | R.N.S. TRADING | 41.91 | 0 | 0
2358 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-1 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000201/2023-2024 | 1191/PMD | 03/11/2023 | 60 | SEN BROTHERS | 9.71 | 0 | 100
2359 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-2 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000202/2023-2024 | 1192/PMD | 03/11/2023 | 60 | P K ENGINEERING | 11.49 | 0 | 100
2360 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sarbari Water Supply scheme Neturia Block under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000292/2022-2023 | 84/PMD | 01/02/2023 | 60 | GHOSE ENGINEERING SYNDICATE | 21.61 | 0 | 100
2361 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel, Flowmeter with others allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE, Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000309/2022-2023 | 97/PMD | 03/02/2023 | 60 | GOENKA ENTERPRISE | 49.77 | 0 | 100
2362 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of 4 nos. submersible pumps motor sets at newly constructed riverbed tubewell with other allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000310/2022-2023 | 98/PMD | 03/02/2023 | 698 | AVISHEK ENTERPRISE | 12.13 | 9.86 | 100
2363 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of valves, pipes & Misc. works for Pump house of Sarbori w/s scheme under PMD, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000594/2024-2025 | 1452/PMD | 01/10/2024 | 30 | R.N.S. TRADING | 1.73 | 0 | 0
2364 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & installation of Lighting conductor under Sarbori Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000604/2024-2025 | 351/PMSD(W/S) | 04/09/2024 | 15 | BISWAJIT MAJI | 0.61 | 0 | 0
2365 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000008/2023-2024 | 617/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0
2366 | Purulia Division | Purulia Division | Route Survey & Drawing Preparation for uncovered areas under Raghunathpur-II Block under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000001/2023-2024 | 527/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 4.94 | 100
2367 | Purulia Division | Purulia Division | Construction of Guard Room at WTP Campus under Raghunathpur Pipe Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000056/2023-2024 | 664/PD | 17/05/2023 | 100 | BISWAJIT MAJI | 6.34 | 0 | 100
2368 | Purulia Division | Purulia Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ketlapur Mouza, JL No.-82, Plot No.-2790 under Para Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000080/2023-2024 | 767/PD | 08/06/2023 | 60 | PARTHA SARATHI SAHABABU | 10.96 | 0 | 100
2369 | Purulia Division | Purulia Division | Construction of RCC clear water reservoir (CWR) of capacity 500 Cum with other allied works at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/001043/2022-2023 | 275/PD | 27/02/2023 | 90 | BOSE CONSTRUCTION | 56.66 | 0 | 70
2370 | Purulia Division | Purulia Division | Laying of distribution pipe line ( 90 mm,75mm & 63 mm dia HDPE pipe ) towards Garhpanchkot Prakriti Kendra under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/001140/2022-2023 | 418/PD | 21/03/2023 | 45 | CHANDAN CHATTERJEE | 10.97 | 0 | 0
2371 | Purulia Division | Purulia Division | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 243.5 cum at Jharukhamar under Raghunathpur W/S Scheme (Zone-IA) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/001146/2024-2025 | 2300/PD | 31/12/2024 | 90 | ASHOKE KUMAR CHATTERJEE | 5.76 | 0 | 0
2372 | Purulia Division | Purulia Division | Road Crossing of rising main by jack pushing at Raghunathpur-Barakar Road (near Bundla Brize) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/001174/2024-2025 | 2328/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 17.14 | 0 | 0
2373 | Purulia Division | Purulia Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/001197/2022-2023 | 471/PD | 28/03/2023 | 826 | ASHOK KUMAR CHATTERJEE | 261.64 | 0 | 80
2374 | Purulia Division | Purulia Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), Construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/001198/2022-2023 | 472/PD | 28/03/2023 | 1096 | ASHOK KUMAR CHATTERJEE | 360.46 | 0 | 30
2375 | Purulia Division | Purulia Division | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer(HQ) |  | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 122 | COMPUTER MEDIA | 0.87 | 0 | 100
2376 | Purulia Division | Purulia Division | Supply & delivery of spreading and levelling Filter media at Rapid Gravity sand filter beds after removal of existing not functioning filter media at Laxmanpur WTP under Purulia Division,P.H.E.Dte. | Assistant Engineer(HQ) |  | ORD/003455/2023-2024 | 317/PD | 01/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 15.86 | 0 | 100
2377 | Purulia Division | Purulia Division | Sinking of 1(One) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Boosting Pump Station (Seleta Mouza) of Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/003989/2023-2024 | 518/PD | 16/03/2024 | 45 | SUBRATA SINGHADEO | 3.87 | 0 | 100
2378 | Purulia Division | Purulia Division | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer(HQ) |  | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 122 | UTSAV AGENCY | 0.87 | 0 | 100
2379 | Purulia Division | Purulia Division | Material Requisition To Resource Division | Assistant Engineer(HQ) |  | RTOR000029/2022-2023 | 75/PD | 17/01/2023 | 0 | Resource Division | 14.94 | 0 | 0
2380 | Purulia Mechanical | Purulia Division | For new connection at Gobag near uposasthya kendra under augmentation of Raghunathpur zone 1A/1 & zone 1A/II | Assistant Engineer(HQ) |  | BILL/00777/2023-2024 | BP-23-24-277 | 01/02/2024 | 0 | WBSEDCL PURULIA | 2.81 | 0 | 0
2381 | Purulia Mechanical | Purulia Division | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-III) under Raghunathpur water supply project, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000008/2025-2026 | 619/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0
2382 | Purulia Mechanical | Purulia Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone 1A/II under PMD PHE Dte. District Purulia. | Assistant Engineer(HQ) |  | ORD/000124/2023-2024 | 860/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
2383 | Purulia Mechanical | Purulia Division | Supply, delivery and laying of cable and other works, at OHR site Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000610/2024-2025 | 858/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.94 | 0 | 95
2384 | Purulia Mechanical | Purulia Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site - I (Tube Well -Il), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000646/2024-2025 | 1010/PMD | 24/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 95
2385 | Purulia Division | Raghunathpur Sub-Division | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Gobag Mouza, JL No.-58, Plot No.-620 under Neturia Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000078/2023-2024 | 768/PD | 08/06/2023 | 663 | ASHOK KUMAR CHATTERJEE | 17.28 | 0 | 65
2386 | Purulia Division | Raghunathpur Sub-Division | Land development by earth filling with carried earth , Concrete road & Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell with other allied works of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000135/2024-2025 | 905/PD | 07/05/2024 | 60 | AMIT PATHAK | 16.66 | 0 | 100
2387 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | Assistant Engineer | Junior Engineer-1 | ORD/000434/2024-2025 | 1498/PD | 27/08/2024 | 431 | M/S KARUNAMOYEE CONSTRUCTION | 30.19 | 0 | 100
2388 | Purulia Division | Raghunathpur Sub-Division | Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B)(Nanduka) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000439/2024-2025 | 1502/PD | 27/08/2024 | 30 | AMIT PATHAK | 5.07 | 0 | 100
2389 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line and other alliedworks of Raghunathpur Water Supply Scheme(Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-I] | Assistant Engineer | Junior Engineer-1 | ORD/001006/2022-2023 | 173/PD | 07/02/2023 | 1096 | MADHU SUDAN RAKSHIT | 83.87 | 0 | 75
2390 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur WaterSupply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-II | Assistant Engineer | Junior Engineer-1 | ORD/001007/2022-2023 | 174/PD | 07/02/2023 | 1209 | RABIN CHANDRA CHAIL | 77.59 | 0 | 30
2391 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer-1 | ORD/001067/2022-2023 | 302/PD | 28/02/2023 | 977 | M/S KARUNAMOYEE CONSTRUCTION | 149.48 | 82.73 | 100
2392 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-1 | RTOR000033/2022-2023 | 73/PD | 17/01/2023 | 0 | Resource Division | 113.38 | 0 | 0
2393 | Purulia Mechanical | Raghunathpur Sub-Division | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE VB | Assistant Engineer | Junior Engineer-1 | BILL/00479/2023-2024 | BP-23-24-250 | 04/01/2024 | 0 | WBSEDCL PURULIA | 1.18 | 0 | 0
2394 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone V B under PMD PHE Dte. District Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000126/2023-2024 | 862/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
2395 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Nanduka-V(B) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000564/2023-2024 | 367/PMD. | 01/03/2024 | 10 | ASHOKE ADHIKARY | 0.98 | 0 | 80
2396 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of kiosk box comprising of motor startering arrangement (DOL), at OHR site V(B) (T/W-1) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000565/2023-2024 | 445/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 1 | 0 | 60
2397 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & laying of cable and other works at OHR site- V(B) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000566/2023-2024 | 443/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 0.84 | 0 | 60
2398 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-V (Tube well-II), Nanduka under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000598/2024-2025 | 1028/PMD | 25/06/2024 | 15 | S. PATHAK & CO. | 0.95 | 0 | 90
2399 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of earthing arrangement and other works at OHR site-V, Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000599/2024-2025 | 1041/PMD | 26/06/2024 | 15 | S. PATHAK & CO. | 0.71 | 0 | 70
2400 | Purulia Division | Purulia Division | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Baghmundi Block [37 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000044/2022-2023 | 100/A/PSD | 08/02/2023 | 21 | INDRANIL DUTTA & ASSOCIATES | 4.83 | 3.49 | 60
2401 | Purulia Division | Raghunathpur Sub-Division | Maintenance work for Construction of Soak pit, Leach pit & Drain at Inspection Bunglow at Lakkhanpur WTP under Raghunathpur W/S Scheme(German Assisted) Zone-IB within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000015/2025-2026 | 572/PD | 07/04/2025 | 60 | CHANDAN CHATTERJEE | 5.63 | 0 | 0
2402 | Purulia Division | Raghunathpur Sub-Division | Supply, fitting, fixing Swajal Gram Village signboard and thorough repairing and Renovation of R.C.C. Elevated Reservoir (Intze Type with solid raft) of Capcaity 1049.84 cum and staging height 25 mtralongwith high lifting of boundary wall and construction of approach road with all allied works and laying of HDPE pipe at Soudagar Para , Goraipara, Bandanga Village and Supply of Chair, Table and Almirah for Seating arrangement of contractual Junior Engineers at the office of the Assistant Engineer, Raghunathpur Sub-Division under Raghunathpur W/S Scheme(German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000222/2024-2025 | 1096/PD | 07/06/2024 | 90 | M/S SAYAK BHATTACHARYA | 45.37 | 0 | 100
2403 | Purulia Division | Raghunathpur Sub-Division | Laying of HDPE Pipe (PE-100, PN-10) for collecting line of riverbed tubewell (for 1, 2, 3 & 4) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000235/2024-2025 | 1075/PD | 07/06/2024 | 60 | KHITISH CHANDRA PATHAK | 6.9 | 0 | 100
2404 | Purulia Division | Raghunathpur Sub-Division | Repering& renovation of 4 (Four) Nos I.E Plant under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000238/2024-2025 | 1086/PD | 07/06/2024 | 60 | SADHAN GORAIN | 22.12 | 0 | 70
2405 | Purulia Division | Raghunathpur Sub-Division | Construction of Pump House (13 X 8.5 mtr) at Laxmanpur WTP site to accommodate electromechanical equipment as well as safety device under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000328/2024-2025 | 1353/PD | 25/07/2024 | 358 | BOSE CONSTRUCTION | 31.86 | 0 | 25
2406 | Purulia Division | Raghunathpur Sub-Division | Supply of DI Specials & road crossing for Distribution line ZONE-IB of Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 1363/PD | 25/07/2024 | 745 | MADHU SUDAN RAKSHIT | 7.01 | 0 | 0
2407 | Purulia Division | Raghunathpur Sub-Division | Laying of 140 mm dia HDPE pipe line From OHR to Misson Para at Arrah under Raghunathpur Water Supply Scheme (German Assisted) (Zone-IB) of Raghunathpur Sub Division Under Purulia Division PHE Dte | Assistant Engineer |  | ORD/000361/2025-2026 | 1520/PD | 19/08/2025 | 285 | RABIN CHANDRA CHAIL | 21.16 | 0 | 0
2408 | Purulia Division | Raghunathpur Sub-Division | Sinking of 1No. 200 mm dia DTH Rigbored TW with allied works at office campus under Aug. of Raghunathpur W/S Scheme (Zone-IB) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001059/2024-2025 | 2120/PD | 05/12/2024 | 60 | MANATOSH SINGH | 4.21 | 0 | 0
2409 | Purulia Division | Raghunathpur Sub-Division | Construction of Guard Room with toilet block at Zone-III under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001071/2024-2025 | 2102/PD | 05/12/2024 | 180 | SUBHAJIT KUNDU | 6.41 | 0 | 0
2410 | Purulia Division | Raghunathpur Sub-Division | Laying balance Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Madhutati or Mautor ,Baldi , Dhanara) | Assistant Engineer |  | ORD/001093/2024-2025 | 2182/PD | 13/12/2024 | 60 | CHATTERJEE CONSTRUCTION | 90.91 | 0 | 0
2411 | Purulia Division | Raghunathpur Sub-Division | Laying balance Distribution System of Parallel pipe line and changing existing CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-(Khantra, KhairaChak , Ruknibera, Gobindapur, Paranpur, Toldi) | Assistant Engineer |  | ORD/001094/2024-2025 | 2183/PD | 13/12/2024 | 460 | NANIGOPAL DEY | 96.2 | 0 | 0
2412 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Name of Mouzas- Rangamati , Gobranda , Charanbandh , Muldi , Bagmanni , Nanduka) | Assistant Engineer |  | ORD/001140/2024-2025 | 43/PD | 10/01/2025 | 60 | KHITISH CHANDRA PATHAK | 96.11 | 0 | 0
2413 | Purulia Division | Raghunathpur Sub-Division | Laying of 250 mm D.I. pipe line for Raw water rising main with manifold at Ramchandrapur under Raghunathpur Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001175/2024-2025 | 2329/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 1.82 | 0 | 0
2414 | Purulia Division | Raghunathpur Sub-Division | Special repairing works of HDPE pipe line from River side to Karandih Village , Kajuli Village ,Kajuli more to D.ED Collage road , Daldali Majhidih Village & Guard pilling Manifold to CWR Pipe line with all allied works of Retrofitting works in connection with Jal Jeevan Mission (JJM) at Maguria Lalpur under Raghunathpur W/S Scheme (Zone-IB) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001298/2024-2025 | 438/PD | 24/03/2025 | 120 | ALOK KUMAR CHAKRABORTY | 31.69 | 0 | 75
2415 | Purulia Division | Raghunathpur Sub-Division | Laying Distribution System of Parallel pipeline and changing existing Cl main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-I-B) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001367/2024-2025 | 373/PD | 13/03/2025 | 240 | DEBAKI RANJAN SARKAR | 128.19 | 0 | 0
2416 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000005/2023-2024 | 1759/PD | 07/12/2023 | 0 | Resource Division | 40.12 | 0 | 0
2417 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000030/2022-2023 | 71/PD | 17/01/2023 | 0 | Resource Division | 1429.07 | 0 | 0
2418 | Purulia Division | Raghunathpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000034/2024-2025 | 1712/PD | 06/09/2024 | 0 | Resource Division | 408.72 | 0 | 0
2419 | Purulia Mechanical | Raghunathpur Sub-Division | Payment of New Electric Connection charge at Salata mouza ,Babugram site , Zone - IV B Raghunathpur - 1 under Augmentation of Raghunathpur W.S. Project and payment to WBSEDCL Raghunathpur CCC . Referance Id - 204346008 | Assistant Engineer |  | BILL/00191/2024-2025 | BP-24-25-48 | 16/07/2024 | 0 | ASSISTANT ENGINEER & IN CHARGE, RAGHUNATHPUR 132 KV SUB STATION (WBSETCL) | 3.11 | 0 | 0
2420 | Purulia Mechanical | Raghunathpur Sub-Division | Supply of Diesel & Mobil for vehicle WB56V-4010 for the month of March-2024 under PMD, PHE Dte. | Assistant Engineer |  | BILL/00227/2024-2025 | BP-24-25-80 | 02/08/2024 | 0 | M/S SANKAR AUTO SERVICE | 0.22 | 0 | 0
2421 | Purulia Mechanical | Raghunathpur Sub-Division | Payment to WBSEDCL , Chelyama CCC for new connection at Vill. + P.O. - Chelyama , Rghunathpur , application no,- 2004770178 , reference Id.- 204327440 . | Assistant Engineer |  | BILL/00289/2024-2025 | BP-24-25-76 | 02/08/2024 | 0 | WBSEDCL PURULIA | 5.36 | 0 | 0
2422 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00456/2023-2024 | BP-23-24-221 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
2423 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00457/2023-2024 | BP-23-24-281 | 16/02/2024 | 0 | WBSEDCL PURULIA | 1.63 | 0 | 0
2424 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00458/2023-2024 | BP-23-24-280 | 16/02/2024 | 0 | WBSEDCL PURULIA | 0.61 | 0 | 0
2425 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of Raghunathpur ZOne- I B (Nanduara) | Assistant Engineer |  | BILL/00821/2023-2024 | BP-24-25-27 | 11/06/2024 | 0 | WBSEDCL PURULIA | 0.25 | 0 | 0
2426 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of Raghunathpur ZOne-I B (Sohardi Mouza Babugram, Sanka) | Assistant Engineer |  | BILL/00823/2023-2024 |  | 08/02/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0
2427 | Purulia Mechanical | Raghunathpur Sub-Division | Bulk power supply at 11 KV, Purulia for a contractual demand of 400/400/400/400/400 KVA respectively for next consecutive five years, Mouza-Salata, Block-Raghunathpur -I , Purulia | Assistant Engineer |  | BILL/00864/2023-2024 | BP-23-24-299 | 05/03/2024 | 0 | WBSEDCL PURULIA | 38.16 | 0 | 0
2428 | Purulia Mechanical | Raghunathpur Sub-Division | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000005/2025-2026 | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0
2429 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting arrangement at different OHR site and other works under Augmentation of Raghunathpur Pipe Water Supply Project under PMD, PHE. Dte. | Assistant Engineer |  | ORD/000006/2025-2026 | 569/PMD | 07/04/2025 | 269 | BISHWANATH NANDI | 24.28 | 0 | 80
2430 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and Installation of 4KG/HR Gaseous Chlorination system and Chlorine leak absorption system at Lakshmanpur WTP under Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000174/2023-2024 | 1126PMD | 11/10/2023 | 120 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 80.55 | 0 | 0
2431 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing two number old VT pumps with new pumps at intake pump house of Lakshmanpur WTP for Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000175/2023-2024 | 1127/PMD | 11/10/2023 | 599 | COMBINE ENTERPRISES | 31.33 | 0 | 91
2432 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of electro mechanical equipment's, HSC pump motor sets, MCC, HOT, Valves, Flowmeter at Proposed Clear water pump house in Lakshmanpur WTP Under Augmentation of Raghunathpur water supply project Bolck : Neturia, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | Assistant Engineer |  | ORD/000177/2023-2024 | 458/PMD | 14/03/2024 | 120 | NEW ALIGNMENT | 192.41 | 0 | 0
2433 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of electro mechanical equipments, HSC pump motor sets, MCC, HOT, Valves, Flowmeter ,400 KVA electrical substation, Gaseous chlorination system at Clear water Boosting pump house Under Augmentation of Raghunathpur water supply project Under Purulia Mechanical Division PHE Dte Dist-Purulia. | Assistant Engineer |  | ORD/000178/2023-2024 | 1147/PMD | 16/10/2023 | 120 | MAHADEV ENTERPRISE | 331.9 | 0 | 0
2434 | Purulia Mechanical | Raghunathpur Sub-Division | Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000207/2023-2024 | 1086/PMD | 29/09/2023 | 183 | PINTU DEY | 0.89 | 0 | 84
2435 | Purulia Mechanical | Raghunathpur Sub-Division | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping machinery at Existing 8 nos OHR and Proposed 6nos OHR site under Augmentation of Raghunathpur water supply project under PMD, PHE, Dte. District Purulia. | Assistant Engineer |  | ORD/000231/2023-2024 | 1125/PMD | 11/10/2023 | 538 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.79 | 0 | 50
2436 | Purulia Mechanical | Raghunathpur Sub-Division | Strengthen the existing monorail at Chlorination Building of Lakshmanpur WTP and other allied works under Raghunathpur Water Supply Project under under Purulia Mechanical Division P.H.E. Dte. | Assistant Engineer |  | ORD/000444/2023-2024 | 424/PMD | 11/03/2024 | 386 | RABINDRA NATH KHAN | 7.76 | 0 | 100
2437 | Purulia Mechanical | Raghunathpur Sub-Division | Continuation Work Order for "Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.04.2024 to 30.09.2024 | Assistant Engineer |  | ORD/000499/2023-2024 | 525/PMD | 18/03/2024 | 183 | PINTU DEY | 0.89 | 0 | 55
2438 | Purulia Mechanical | Raghunathpur Sub-Division | Continuation Work Order for"Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.10.2024 to 31.03.2025 | Assistant Engineer |  | ORD/000570/2024-2025 | 1375/PMD | 19/09/2024 | 182 | PINTU DEY | 0.89 | 0 | 0
2439 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000576/2024-2025 | 1009/PMD | 24/06/2024 | 15 | SUJIT MUKHERJEE | 0.95 | 0 | 80
2440 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-I), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000577/2024-2025 | 906/PMD | 10/06/2024 | 15 | M/S A.D. CONCERN | 0.95 | 0 | 80
2441 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of 1 Ton A.C machine at Lakshmanpur Bungalow of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000578/2024-2025 | 1116/PMD | 12/07/2024 | 15 | TAPAN KUMAR DEY | 0.62 | 0 | 100
2442 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV - B under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000589/2024-2025 | 1447/PMD | 01/10/2024 | 151 | BISHWANATH NANDI | 13.34 | 0 | 65
2443 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of A.C Machine at Ground floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000606/2023-2024 | 446/PMD | 11/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 99
2444 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of A.C Machine at first floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000608/2023-2024 | 385/PMD | 04/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 99
2445 | Purulia Mechanical | Raghunathpur Sub-Division | Providing Mechanical / Electrical Works with all accessories for High Lift Pumping Machinary at Booster Pumping Station - Zone VIII, Augmentation of Raghunathpur Water Supply Project under PMD PHE Dte. in the District of Purulia. | Assistant Engineer |  | ORD/000638/2024-2025 | 1570/PMD | 14/11/2024 | 180 | COMBINE ENTERPRISES | 47.9 | 0 | 0
2446 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery, installation and commissioning of chlorine leak absorption System at different OHR sites of Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000644/2024-2025 | 1576/PMD | 14/11/2024 | 90 | TAPAN KUMAR DEY | 90.02 | 0 | 0
2447 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube well-3), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000647/2024-2025 | 1259/PMD | 22/08/2024 | 15 | M/S UJJAL DIESEL SERVICE | 0.96 | 0 | 90
2448 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000650/2024-2025 | 1115/PMD | 12/07/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 0
2449 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-IV), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000652/2024-2025 | 1323/PMD | 04/09/2024 | 103 | M/S A.D. CONCERN | 0.96 | 0 | 90
2450 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-V), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000653/2024-2025 | 1324/PMD | 04/09/2024 | 15 | PINTU DEY | 0.96 | 0 | 90
Total | [10 empty] | 200761.02 | 11545.92